## Information
Reference Guide for the Adapations Project Spreadsheets | Notes
1. Public and Private seawalls were classified basen on visual inspection of aerial images. Not official ownership
2. Public and Private swales were classified based on parcel proximity. Not official ownership
3. Distribution by year could change based on priorities and changes to project start dates and duration.
4. Cost shown are planning level cost and quantities
The numbers in the red box above are the total costs for each of the adaptations and the years the costs are exepcted to be incurred, if the plan schedule is followed. The plan runs from 2025 to 2045, but that can be modified.
The costs are based on a few factors.
First, we estimated what the cost per unit would be and estimated how many units would be required to complete the project. Modifiers such as engineering costs/changes and a contingency were added to account for changes over time and the actual design process.
The box above highlights the factors used to generate the costs in the red box on the right side of the sheet.
Column headers are explained below:
Unit Cost: Unit cost of the project (e.g. per linear ft length for swales)
Cost: Cost of the project/adaptation
Engineering: Percentage of Engeneering & Legal Cost
Contingency: Percentage of Contingency Cost
Subtotal: Cost including engineering and contingency
The pivot table above creates a summary for total cost for each municipality. The total cost is a function of the variables in column H thru L and the scheduling of those costs are broken down in Column T thru AN to the right.
The grand total is a sum of the Private or Homeowner costs and Public or Municipal costs.
The green box above provides data used in the mapping and identification of the adaptations.
TRACTCE: Cenus Tract ID
Ownership: Who owns the property.
StartDate: When the plan starts design and construction.
Duration: How many years design and construction takes.
Adaptation: What is the planned adaptation.
In other spreadsheets you may see:
CityName: Name of the City where asset/project is located
UID: Unique Identifier (used to join with GIS data files)
Duration: Proposed duation of project from design to construction
Level: Resilience Plan Adaptation Level (Tier1/Tier2)
Str_ID: Hydraulic Model ID
Str_BrName: Name of the canal/branch where structure/project is located
Str_Ch: Structure Chainge depicted in the Hydraulic model
Type: Type of the strcuture or project
Str_BrNa: Name of the canal/branch where structure/project is located
Max_Capaci: Pump Capacity set up in the model, cfs
max_25yr: Pump Capacity output for 25yr rain event, cfs
max_100yr: Pump Capacity used for cost. Model output 100 yr rain event, cfs
AREA_ACR: Area of proposed Seawall Drainage Project, Acre
AreaGroup: Area Group of the Seawall Drainage Project
CostAreaGroup: Total Cost of the Area Group
SizeAreaGroup: Size of the area group (sq.ft.)
Percent inAreaGroup: Percent of the project (seawall) area in larger Area Group
Cost: Cost of the adaptation (seawall drainage) project

## Swales
UID | CITYNAME | TRACTCE | Ownership | StartDate | Duration | Adaptation | Unit Cost | Cost | Engineering & Legal Costs | Contingency | Subtotal | Sum of Subtotal | Column Labels |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045
1 | WESTON | 70331 | Public | 2036 | 5 | Swales | 66.6667 | 10890.5216 | 0.2 | 0.3 | 16989.2137 | Row Labels | Private | Public | Grand Total | 0 | 1396.4972 | 1396.4972 | 1396.4972 | 1396.4972 | 1396.4972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | WESTON | 70331 | Public | 2036 | 5 | Swales | 66.6667 | 4427.9523 | 0.2 | 0.3 | 6907.6056 | BMSD | 37552.198 | 14389030.6324 | 14426582.8304 | 0 | 3674.9205 | 3674.9205 | 3674.9205 | 3674.9205 | 3674.9205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 1827.4882 | 0.2 | 0.3 | 2850.8816 | COCONUT CREEK | 23504529.058 | 8539649.8299 | 32044178.8879 | 0 | 7277.9426 | 7277.9426 | 7277.9426 | 7277.9426 | 7277.9426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 25800.0281 | 0.2 | 0.3 | 40248.0439 | COOPER CITY | 13415699.6839 | 14382860.8591 | 27798560.543 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 26557.8042 | 0.2 | 0.3 | 41430.1746 | CORAL SPRINGS | 25034841.8154 | 57448629.5963 | 82483471.4116 | 0 | 2104.3026 | 2104.3026 | 2104.3026 | 2104.3026 | 2104.3026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | WESTON | 70331 | Public | 2036 | 5 | Swales | 66.6667 | 15577.4335 | 0.2 | 0.3 | 24300.7963 | COUNTY REGIONAL FACILITY |  | 201718.47 | 201718.47 | 0 | 7795.1432 | 7795.1432 | 7795.1432 | 7795.1432 | 7795.1432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WESTON | 70331 | Public | 2036 | 5 | Swales | 66.6667 | 7075.0571 | 0.2 | 0.3 | 11037.0891 | DANIA BEACH | 5477845.2567 | 14583349.4023 | 20061194.6591 | 0 | 5211.0867 | 5211.0867 | 5211.0867 | 5211.0867 | 5211.0867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | WESTON | 70331 | Public | 2036 | 5 | Swales | 66.6667 | 16937.4131 | 0.2 | 0.3 | 26422.3645 | DAVIE | 31773440.4167 | 28378500.3404 | 60151940.7572 | 0 | 4387.0831 | 4387.0831 | 4387.0831 | 4387.0831 | 4387.0831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | WESTON | 70331 | Public | 2036 | 5 | Swales | 66.6667 | 9036.6404 | 0.2 | 0.3 | 14097.159 | DEERFIELD BEACH | 23716707.224 | 37228181.5935 | 60944888.8175 | 0 | 4253.5935 | 4253.5935 | 4253.5935 | 4253.5935 | 4253.5935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16701.476 | 0.2 | 0.3 | 26054.3026 | FORT LAUDERDALE | 9019953.2443 | 117531007.5402 | 126550960.7846 | 0 | 3575.3769 | 3575.3769 | 3575.3769 | 3575.3769 | 3575.3769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 15082.6654 | 0.2 | 0.3 | 23528.958 | HALLANDALE BEACH | 4192617.625 | 12628280.0492 | 16820897.6743 | 0 | 1930.5973 | 1930.5973 | 1930.5973 | 1930.5973 | 1930.5973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 9339.096 | 0.2 | 0.3 | 14568.9898 | HOLLYWOOD | 13045635.2463 | 73111818.1383 | 86157453.3846 | 0 | 5314.9132 | 5314.9132 | 5314.9132 | 5314.9132 | 5314.9132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 10936.2453 | 0.2 | 0.3 | 17060.5427 | LAUDERDALE BY THE SEA | 335419.2937 | 3810280.3519 | 4145699.6456 | 0 | 5392.953 | 5392.953 | 5392.953 | 5392.953 | 5392.953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | WESTON | 70331 | Public | 2036 | 5 | Swales | 66.6667 | 16737.4707 | 0.2 | 0.3 | 26110.4543 | LAUDERDALE LAKES | 4267661.2766 | 14967151.5978 | 19234812.8745 | 0 | 5203.4143 | 5203.4143 | 5203.4143 | 5203.4143 | 5203.4143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | WESTON | 70331 | Public | 2036 | 5 | Swales | 66.6667 | 9956.1511 | 0.2 | 0.3 | 15531.5957 | LAUDERHILL | 4310038.5517 | 28783661.1567 | 33093699.7085 | 0 | 9788.072 | 9788.072 | 9788.072 | 9788.072 | 9788.072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 24014.9165 | 0.2 | 0.3 | 37463.2697 | LAZY LAKE |  | 48900.7612 | 48900.7612 | 0 | 9782.0621 | 9782.0621 | 9782.0621 | 9782.0621 | 9782.0621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 24328.3575 | 0.2 | 0.3 | 37952.2376 | LIGHTHOUSE POINT | 187477.4198 | 9977349.0974 | 10164826.5171 | 0 | 5203.6006 | 5203.6006 | 5203.6006 | 5203.6006 | 5203.6006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 22243.3965 | 0.2 | 0.3 | 34699.6985 | MARGATE | 13293883.9853 | 28972883.8348 | 42266767.8201 | 0 | 8201.8578 | 8201.8578 | 8201.8578 | 8201.8578 | 8201.8578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 21516.3719 | 0.2 | 0.3 | 33565.5402 | MIRAMAR | 47408129.8958 | 30245789.9599 | 77653919.8557 | 0 | 5203.7217 | 5203.7217 | 5203.7217 | 5203.7217 | 5203.7217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 4890.5245 | 0.2 | 0.3 | 7629.2183 | NORTH LAUDERDALE | 5490777.1583 | 17191532.3127 | 22682309.4709 | 0 | 5203.7091 | 5203.7091 | 5203.7091 | 5203.7091 | 5203.7091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | WESTON | 70331 | Public | 2036 | 5 | Swales | 66.6667 | 16668.8707 | 0.2 | 0.3 | 26003.4382 | OAKLAND PARK | 3383912.8469 | 23349938.8491 | 26733851.696 | 0 | 9783.5245 | 9783.5245 | 9783.5245 | 9783.5245 | 9783.5245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | WESTON | 70331 | Public | 2036 | 5 | Swales | 66.6667 | 15722.9639 | 0.2 | 0.3 | 24527.8237 | PARKLAND | 24715421.2697 | 3311175.5088 | 28026596.7784 | 0 | 5204.0886 | 5204.0886 | 5204.0886 | 5204.0886 | 5204.0886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 7039.148 | 0.2 | 0.3 | 10981.0709 | PEMBROKE PARK | 4744710.0423 | 125482.855 | 4870192.8972 | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 19293.7826 | 0.2 | 0.3 | 30098.3009 | PEMBROKE PINES | 77385446.6498 | 43751923.1163 | 121137369.7661 | 0 | 9443.4149 | 9443.4149 | 9443.4149 | 9443.4149 | 9443.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 10438.2779 | 0.2 | 0.3 | 16283.7136 | PLANTATION | 16540446.0304 | 32859991.9251 | 49400437.9554 | 0 | 5203.678 | 5203.678 | 5203.678 | 5203.678 | 5203.678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | WESTON | 70331 | Public | 2036 | 5 | Swales | 66.6667 | 16443.2097 | 0.2 | 0.3 | 25651.4071 | POMPANO BEACH | 10014633.7292 | 68331835.1811 | 78346468.9102 | 0 | 10012.2417 | 10012.2417 | 10012.2417 | 10012.2417 | 10012.2417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 19055.5642 | 0.2 | 0.3 | 29726.6802 | SEA RANCH LAKES | 839235.2598 |  | 839235.2598 | 0 | 5532.069 | 5532.069 | 5532.069 | 5532.069 | 5532.069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 26312.035 | 0.2 | 0.3 | 41046.7746 | SOUTHWEST RANCHES |  | 1021782.1521 | 1021782.1521 | 0 | 5290.8452 | 5290.8452 | 5290.8452 | 5290.8452 | 5290.8452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 21650.2295 | 0.2 | 0.3 | 33774.3581 | SUNRISE | 21626303.4614 | 29632561.3513 | 51258864.8127 | 0 | 5239.7842 | 5239.7842 | 5239.7842 | 5239.7842 | 5239.7842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 35663.7799 | 0.2 | 0.3 | 55635.4967 | TAMARAC | 5795523.4991 | 33609863.3323 | 39405386.8314 | 0 | 5202.713 | 5202.713 | 5202.713 | 5202.713 | 5202.713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | WESTON | 70331 | Public | 2036 | 5 | Swales | 66.6667 | 4266.406 | 0.2 | 0.3 | 6655.5934 | TRIBAL LAND | 2971641.6024 | 26207.2379 | 2997848.8403 | 0 | 5649.5385 | 5649.5385 | 5649.5385 | 5649.5385 | 5649.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 12460.4435 | 0.2 | 0.3 | 19438.2918 | WEST PARK | 170954.0685 | 13080202.6817 | 13251156.7502 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | WESTON | 70331 | Public | 2036 | 5 | Swales | 66.6667 | 16929.7191 | 0.2 | 0.3 | 26410.3617 | WESTON | 32326382.8638 | 2355186.2169 | 34681569.0807 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 12491.865 | 0.2 | 0.3 | 19487.3094 | WILTON MANORS | 914099.3577 | 6651718.6497 | 7565818.0074 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16789.3527 | 0.2 | 0.3 | 26191.3902 | Grand Total | 425940920.0303 | 770528444.5814 | 1196469364.6117 | 0 | 5726.5135 | 5726.5135 | 5726.5135 | 5726.5135 | 5726.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 18218.8573 | 0.2 | 0.3 | 28421.4174 |  |  |  |  | 0 | 7085.4392 | 7085.4392 | 7085.4392 | 7085.4392 | 7085.4392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 861.5021 | 0.2 | 0.3 | 1343.9432 |  |  |  |  | 0 | 5202.9609 | 5202.9609 | 5202.9609 | 5202.9609 | 5202.9609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16462.7522 | 0.2 | 0.3 | 25681.8934 |  |  |  |  | 0 | 5203.0324 | 5203.0324 | 5203.0324 | 5203.0324 | 5203.0324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 25528.002 | 0.2 | 0.3 | 39823.6831 |  |  |  |  | 0 | 9782.5076 | 9782.5076 | 9782.5076 | 9782.5076 | 9782.5076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17230.4585 | 0.2 | 0.3 | 26879.5153 |  |  |  |  | 0 | 5203.5724 | 5203.5724 | 5203.5724 | 5203.5724 | 5203.5724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 15270.4865 | 0.2 | 0.3 | 23821.9589 |  |  |  |  | 0 | 5203.6831 | 5203.6831 | 5203.6831 | 5203.6831 | 5203.6831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 6320.2005 | 0.2 | 0.3 | 9859.5128 |  |  |  |  | 0 | 7706.0707 | 7706.0707 | 7706.0707 | 7706.0707 | 7706.0707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 875.6091 | 0.2 | 0.3 | 1365.9502 |  |  |  |  | 0 | 1420.2 | 1420.2 | 1420.2 | 1420.2 | 1420.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16690.2817 | 0.2 | 0.3 | 26036.8394 |  |  |  |  | 0 | 3172.1512 | 3172.1512 | 3172.1512 | 3172.1512 | 3172.1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 26079.3154 | 0.2 | 0.3 | 40683.732 |  |  |  |  | 0 | 2351.5532 | 2351.5532 | 2351.5532 | 2351.5532 | 2351.5532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 18297.2563 | 0.2 | 0.3 | 28543.7198 |  |  |  |  | 0 | 163.0261 | 163.0261 | 163.0261 | 163.0261 | 163.0261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17317.0724 | 0.2 | 0.3 | 27014.6329 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 2117.7295 | 0.2 | 0.3 | 3303.6581 |  |  |  |  | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 15257.7186 | 0.2 | 0.3 | 23802.041 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17728.3905 | 0.2 | 0.3 | 27656.2891 |  |  |  |  | 0 | 5960.1745 | 5960.1745 | 5960.1745 | 5960.1745 | 5960.1745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 6523.7995 | 0.2 | 0.3 | 10177.1273 |  |  |  |  | 0 | 2758.6942 | 2758.6942 | 2758.6942 | 2758.6942 | 2758.6942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 9230.3893 | 0.2 | 0.3 | 14399.4074 |  |  |  |  | 0 | 5204.5127 | 5204.5127 | 5204.5127 | 5204.5127 | 5204.5127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 29007.1514 | 0.2 | 0.3 | 45251.1562 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 6359.7311 | 0.2 | 0.3 | 9921.1805 |  |  |  |  | 0 | 9784.2184 | 9784.2184 | 9784.2184 | 9784.2184 | 9784.2184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17723.9736 | 0.2 | 0.3 | 27649.3988 |  |  |  |  | 0 | 5202.7526 | 5202.7526 | 5202.7526 | 5202.7526 | 5202.7526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 30211.2655 | 0.2 | 0.3 | 47129.5741 |  |  |  |  | 0 | 5203.0095 | 5203.0095 | 5203.0095 | 5203.0095 | 5203.0095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 32248.9952 | 0.2 | 0.3 | 50308.4325 |  |  |  |  | 0 | 2561.5565 | 2561.5565 | 2561.5565 | 2561.5565 | 2561.5565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 17243.0557 | 0.2 | 0.3 | 26899.1669 |  |  |  |  | 0 | 675.5217 | 675.5217 | 675.5217 | 675.5217 | 675.5217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 15344.9708 | 0.2 | 0.3 | 23938.1544 |  |  |  |  | 0 | 5203.3156 | 5203.3156 | 5203.3156 | 5203.3156 | 5203.3156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 2123.6921 | 0.2 | 0.3 | 3312.9597 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 29192.6733 | 0.2 | 0.3 | 45540.5703 |  |  |  |  | 0 | 5203.4544 | 5203.4544 | 5203.4544 | 5203.4544 | 5203.4544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 27188.4129 | 0.2 | 0.3 | 42413.9242 |  |  |  |  | 0 | 6168.8802 | 6168.8802 | 6168.8802 | 6168.8802 | 6168.8802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16692.4927 | 0.2 | 0.3 | 26040.2887 |  |  |  |  | 0 | 4553.9266 | 4553.9266 | 4553.9266 | 4553.9266 | 4553.9266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 13562.5655 | 0.2 | 0.3 | 21157.6022 |  |  |  |  | 0 | 5202.8237 | 5202.8237 | 5202.8237 | 5202.8237 | 5202.8237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 8418.9599 | 0.2 | 0.3 | 13133.5775 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16688.9495 | 0.2 | 0.3 | 26034.7612 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16763.1378 | 0.2 | 0.3 | 26150.495 |  |  |  |  | 0 | 5203.2661 | 5203.2661 | 5203.2661 | 5203.2661 | 5203.2661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16854.1099 | 0.2 | 0.3 | 26292.4115 |  |  |  |  | 0 | 8841.4506 | 8841.4506 | 8841.4506 | 8841.4506 | 8841.4506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 3919.0077 | 0.2 | 0.3 | 6113.6521 |  |  |  |  | 0 | 30.8005 | 30.8005 | 30.8005 | 30.8005 | 30.8005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 27183.7844 | 0.2 | 0.3 | 42406.7037 |  |  |  |  | 0 | 5202.728 | 5202.728 | 5202.728 | 5202.728 | 5202.728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 28155.2775 | 0.2 | 0.3 | 43922.233 |  |  |  |  | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17252.6413 | 0.2 | 0.3 | 26914.1205 |  |  |  |  | 0 | 5202.8637 | 5202.8637 | 5202.8637 | 5202.8637 | 5202.8637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 15296.7097 | 0.2 | 0.3 | 23862.8671 |  |  |  |  | 0 | 6431.4985 | 6431.4985 | 6431.4985 | 6431.4985 | 6431.4985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 1925.9207 | 0.2 | 0.3 | 3004.4363 |  |  |  |  | 0 | 2361.4212 | 2361.4212 | 2361.4212 | 2361.4212 | 2361.4212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 27505.313 | 0.2 | 0.3 | 42908.2883 |  |  |  |  | 0 | 5225.4531 | 5225.4531 | 5225.4531 | 5225.4531 | 5225.4531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 25552.6635 | 0.2 | 0.3 | 39862.155 |  |  |  |  | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 15932.6861 | 0.2 | 0.3 | 24854.9903 |  |  |  |  | 0 | 9784.3432 | 9784.3432 | 9784.3432 | 9784.3432 | 9784.3432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 18155.6191 | 0.2 | 0.3 | 28322.7658 |  |  |  |  | 0 | 5204.1021 | 5204.1021 | 5204.1021 | 5204.1021 | 5204.1021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17951.7324 | 0.2 | 0.3 | 28004.7025 |  |  |  |  | 0 | 5204.2373 | 5204.2373 | 5204.2373 | 5204.2373 | 5204.2373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 12553.2118 | 0.2 | 0.3 | 19583.0104 |  |  |  |  | 0 | 5513.0621 | 5513.0621 | 5513.0621 | 5513.0621 | 5513.0621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 24765.5397 | 0.2 | 0.3 | 38634.242 |  |  |  |  | 0 | 6035.4693 | 6035.4693 | 6035.4693 | 6035.4693 | 6035.4693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 7507.6285 | 0.2 | 0.3 | 11711.9004 |  |  |  |  | 0 | 5203.7275 | 5203.7275 | 5203.7275 | 5203.7275 | 5203.7275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17044.8845 | 0.2 | 0.3 | 26590.0199 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17079.1086 | 0.2 | 0.3 | 26643.4094 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 7373.0807 | 0.2 | 0.3 | 11502.0059 |  |  |  |  | 0 | 5203.3489 | 5203.3489 | 5203.3489 | 5203.3489 | 5203.3489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 26568.4025 | 0.2 | 0.3 | 41446.708 |  |  |  |  | 0 | 7039.3644 | 7039.3644 | 7039.3644 | 7039.3644 | 7039.3644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 25308.857 | 0.2 | 0.3 | 39481.8169 |  |  |  |  | 0 | 5203.0072 | 5203.0072 | 5203.0072 | 5203.0072 | 5203.0072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 21364.5798 | 0.2 | 0.3 | 33328.7445 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 28322.9433 | 0.2 | 0.3 | 44183.7916 |  |  |  |  | 0 | 5203.046 | 5203.046 | 5203.046 | 5203.046 | 5203.046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 23772.3754 | 0.2 | 0.3 | 37084.9056 |  |  |  |  | 0 | 6640.0002 | 6640.0002 | 6640.0002 | 6640.0002 | 6640.0002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 36489.8271 | 0.2 | 0.3 | 56924.1303 |  |  |  |  | 0 | 6115.31 | 6115.31 | 6115.31 | 6115.31 | 6115.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 1063.6612 | 0.2 | 0.3 | 1659.3115 |  |  |  |  | 0 | 5204.256 | 5204.256 | 5204.256 | 5204.256 | 5204.256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 7253.8829 | 0.2 | 0.3 | 11316.0574 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16937.6499 | 0.2 | 0.3 | 26422.7338 |  |  |  |  | 0 | 9784.8613 | 9784.8613 | 9784.8613 | 9784.8613 | 9784.8613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 23382.4766 | 0.2 | 0.3 | 36476.6635 |  |  |  |  | 0 | 5203.6416 | 5203.6416 | 5203.6416 | 5203.6416 | 5203.6416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17616.6448 | 0.2 | 0.3 | 27481.9659 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 20241.0561 | 0.2 | 0.3 | 31576.0476 |  |  |  |  | 0 | 8647.2703 | 8647.2703 | 8647.2703 | 8647.2703 | 8647.2703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 8022.5488 | 0.2 | 0.3 | 12515.1761 |  |  |  |  | 0 | 5806.8487 | 5806.8487 | 5806.8487 | 5806.8487 | 5806.8487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 27253.2655 | 0.2 | 0.3 | 42515.0941 |  |  |  |  | 0 | 5203.9631 | 5203.9631 | 5203.9631 | 5203.9631 | 5203.9631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 10137.8102 | 0.2 | 0.3 | 15814.9839 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 833.7056 | 0.2 | 0.3 | 1300.5807 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 12526.071 | 0.2 | 0.3 | 19540.6708 |  |  |  |  | 0 | 5204.2582 | 5204.2582 | 5204.2582 | 5204.2582 | 5204.2582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 32103.6607 | 0.2 | 0.3 | 50081.7106 |  |  |  |  | 0 | 7291.7869 | 7291.7869 | 7291.7869 | 7291.7869 | 7291.7869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16607.5943 | 0.2 | 0.3 | 25907.8471 |  |  |  |  | 0 | 5203.7785 | 5203.7785 | 5203.7785 | 5203.7785 | 5203.7785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 8791.3259 | 0.2 | 0.3 | 13714.4684 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16392.2412 | 0.2 | 0.3 | 25571.8963 |  |  |  |  | 0 | 5203.9759 | 5203.9759 | 5203.9759 | 5203.9759 | 5203.9759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 18567.3965 | 0.2 | 0.3 | 28965.1385 |  |  |  |  | 0 | 9785.7561 | 9785.7561 | 9785.7561 | 9785.7561 | 9785.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 7336.7704 | 0.2 | 0.3 | 11445.3618 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 26386.3655 | 0.2 | 0.3 | 41162.7301 |  |  |  |  | 0 | 8065.0839 | 8065.0839 | 8065.0839 | 8065.0839 | 8065.0839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 418.7115 | 0.2 | 0.3 | 653.1899 |  |  |  |  | 0 | 5201.9894 | 5201.9894 | 5201.9894 | 5201.9894 | 5201.9894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 18292.8079 | 0.2 | 0.3 | 28536.7803 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 9633.5018 | 0.2 | 0.3 | 15028.2628 |  |  |  |  | 0 | 9783.5404 | 9783.5404 | 9783.5404 | 9783.5404 | 9783.5404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 2319.1139 | 0.2 | 0.3 | 3617.8177 |  |  |  |  | 0 | 5204.0091 | 5204.0091 | 5204.0091 | 5204.0091 | 5204.0091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 12874.0857 | 0.2 | 0.3 | 20083.5736 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 13199.5267 | 0.2 | 0.3 | 20591.2617 |  |  |  |  | 0 | 6874.6337 | 6874.6337 | 6874.6337 | 6874.6337 | 6874.6337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 2702.406 | 0.2 | 0.3 | 4215.7534 |  |  |  |  | 0 | 5201.8055 | 5201.8055 | 5201.8055 | 5201.8055 | 5201.8055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 15342.5326 | 0.2 | 0.3 | 23934.3509 |  |  |  |  | 0 | 9784.7703 | 9784.7703 | 9784.7703 | 9784.7703 | 9784.7703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 20736.7651 | 0.2 | 0.3 | 32349.3535 |  |  |  |  | 0 | 5203.7286 | 5203.7286 | 5203.7286 | 5203.7286 | 5203.7286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 2687.8617 | 0.2 | 0.3 | 4193.0643 |  |  |  |  | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 12005.1647 | 0.2 | 0.3 | 18728.057 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 25151.6391 | 0.2 | 0.3 | 39236.5569 |  |  |  |  | 0 | 5203.6773 | 5203.6773 | 5203.6773 | 5203.6773 | 5203.6773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 28385.6229 | 0.2 | 0.3 | 44281.5717 |  |  |  |  | 0 | 9781.7848 | 9781.7848 | 9781.7848 | 9781.7848 | 9781.7848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 24001.6605 | 0.2 | 0.3 | 37442.5904 |  |  |  |  | 0 | 5203.8696 | 5203.8696 | 5203.8696 | 5203.8696 | 5203.8696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16928.2791 | 0.2 | 0.3 | 26408.1153 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 18086.5614 | 0.2 | 0.3 | 28215.0358 |  |  |  |  | 0 | 5204.2118 | 5204.2118 | 5204.2118 | 5204.2118 | 5204.2118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 23917.2117 | 0.2 | 0.3 | 37310.8503 |  |  |  |  | 0 | 9783.6084 | 9783.6084 | 9783.6084 | 9783.6084 | 9783.6084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 23811.2893 | 0.2 | 0.3 | 37145.6114 |  |  |  |  | 0 | 5203.7293 | 5203.7293 | 5203.7293 | 5203.7293 | 5203.7293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 20152.7875 | 0.2 | 0.3 | 31438.3486 |  |  |  |  | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 21713.4917 | 0.2 | 0.3 | 33873.047 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 23984.1441 | 0.2 | 0.3 | 37415.2648 |  |  |  |  | 0 | 5203.8939 | 5203.8939 | 5203.8939 | 5203.8939 | 5203.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 12053.2273 | 0.2 | 0.3 | 18803.0345 |  |  |  |  | 0 | 9783.1625 | 9783.1625 | 9783.1625 | 9783.1625 | 9783.1625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 6837.7667 | 0.2 | 0.3 | 10666.9161 |  |  |  |  | 0 | 5203.5482 | 5203.5482 | 5203.5482 | 5203.5482 | 5203.5482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 5556.2791 | 0.2 | 0.3 | 8667.7953 |  |  |  |  | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 6019.7212 | 0.2 | 0.3 | 9390.7651 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 19118.1338 | 0.2 | 0.3 | 29824.2887 |  |  |  |  | 0 | 5203.8883 | 5203.8883 | 5203.8883 | 5203.8883 | 5203.8883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 38.3127 | 0.2 | 0.3 | 59.7679 |  |  |  |  | 0 | 9784.5396 | 9784.5396 | 9784.5396 | 9784.5396 | 9784.5396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16315.2176 | 0.2 | 0.3 | 25451.7395 |  |  |  |  | 0 | 5203.3887 | 5203.3887 | 5203.3887 | 5203.3887 | 5203.3887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 20008.1687 | 0.2 | 0.3 | 31212.7432 |  |  |  |  | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 15371.2171 | 0.2 | 0.3 | 23979.0987 |  |  |  |  | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 12001.1739 | 0.2 | 0.3 | 18721.8313 |  |  |  |  | 0 | 5203.4815 | 5203.4815 | 5203.4815 | 5203.4815 | 5203.4815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 18068.7677 | 0.2 | 0.3 | 28187.2777 |  |  |  |  | 0 | 1463.5957 | 1463.5957 | 1463.5957 | 1463.5957 | 1463.5957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 18202.1037 | 0.2 | 0.3 | 28395.2817 |  |  |  |  | 0 | 3092.7717 | 3092.7717 | 3092.7717 | 3092.7717 | 3092.7717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 13441.1999 | 0.2 | 0.3 | 20968.2719 |  |  |  |  | 0 | 5204.0432 | 5204.0432 | 5204.0432 | 5204.0432 | 5204.0432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 39771.9809 | 0.2 | 0.3 | 62044.2903 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 25567.6855 | 0.2 | 0.3 | 39885.5894 |  |  |  |  | 0 | 5204.3457 | 5204.3457 | 5204.3457 | 5204.3457 | 5204.3457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 13819.5685 | 0.2 | 0.3 | 21558.5269 |  |  |  |  | 0 | 2080.5457 | 2080.5457 | 2080.5457 | 2080.5457 | 2080.5457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 7205.835 | 0.2 | 0.3 | 11241.1026 |  |  |  |  | 0 | 8077.7272 | 8077.7272 | 8077.7272 | 8077.7272 | 8077.7272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 16805.0521 | 0.2 | 0.3 | 26215.8812 |  |  |  |  | 0 | 8521.681 | 8521.681 | 8521.681 | 8521.681 | 8521.681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 16653.2782 | 0.2 | 0.3 | 25979.114 |  |  |  |  | 0 | 4841.4532 | 4841.4532 | 4841.4532 | 4841.4532 | 4841.4532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 18116.2181 | 0.2 | 0.3 | 28261.3003 |  |  |  |  | 0 | 9579.2835 | 9579.2835 | 9579.2835 | 9579.2835 | 9579.2835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 32252.2826 | 0.2 | 0.3 | 50313.5609 |  |  |  |  | 0 | 5204.2002 | 5204.2002 | 5204.2002 | 5204.2002 | 5204.2002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 16672.5009 | 0.2 | 0.3 | 26009.1014 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 27667.659 | 0.2 | 0.3 | 43161.548 |  |  |  |  | 0 | 5207.502 | 5207.502 | 5207.502 | 5207.502 | 5207.502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 17181.1275 | 0.2 | 0.3 | 26802.559 |  |  |  |  | 0 | 9050.3774 | 9050.3774 | 9050.3774 | 9050.3774 | 9050.3774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 12244.8374 | 0.2 | 0.3 | 19101.9463 |  |  |  |  | 0 | 9812.7093 | 9812.7093 | 9812.7093 | 9812.7093 | 9812.7093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 25399.7177 | 0.2 | 0.3 | 39623.5596 |  |  |  |  | 0 | 9817.8706 | 9817.8706 | 9817.8706 | 9817.8706 | 9817.8706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 11563.7821 | 0.2 | 0.3 | 18039.5001 |  |  |  |  | 0 | 8504.8295 | 8504.8295 | 8504.8295 | 8504.8295 | 8504.8295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 18610.3023 | 0.2 | 0.3 | 29032.0716 |  |  |  |  | 0 | 5090.1282 | 5090.1282 | 5090.1282 | 5090.1282 | 5090.1282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 4093.8868 | 0.2 | 0.3 | 6386.4634 |  |  |  |  | 0 | 8209.6788 | 8209.6788 | 8209.6788 | 8209.6788 | 8209.6788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17464.1467 | 0.2 | 0.3 | 27244.0688 |  |  |  |  | 0 | 7406.097 | 7406.097 | 7406.097 | 7406.097 | 7406.097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 10407.5588 | 0.2 | 0.3 | 16235.7917 |  |  |  |  | 0 | 5204.1599 | 5204.1599 | 5204.1599 | 5204.1599 | 5204.1599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 19170.533 | 0.2 | 0.3 | 29906.0315 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 15477.7171 | 0.2 | 0.3 | 24145.2387 |  |  |  |  | 0 | 5204.7103 | 5204.7103 | 5204.7103 | 5204.7103 | 5204.7103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 5373.7913 | 0.2 | 0.3 | 8383.1145 |  |  |  |  | 0 | 7799.1101 | 7799.1101 | 7799.1101 | 7799.1101 | 7799.1101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 1640.6672 | 0.2 | 0.3 | 2559.4408 |  |  |  |  | 0 | 6194.0244 | 6194.0244 | 6194.0244 | 6194.0244 | 6194.0244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 9623.7042 | 0.2 | 0.3 | 15012.9786 |  |  |  |  | 0 | 2911.4772 | 2911.4772 | 2911.4772 | 2911.4772 | 2911.4772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 18667.4983 | 0.2 | 0.3 | 29121.2974 |  |  |  |  | 0 | 5210.8214 | 5210.8214 | 5210.8214 | 5210.8214 | 5210.8214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 111.0555 | 0.2 | 0.3 | 173.2466 |  |  |  |  | 0 | 8779.7975 | 8779.7975 | 8779.7975 | 8779.7975 | 8779.7975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 17124.2517 | 0.2 | 0.3 | 26713.8326 |  |  |  |  | 0 | 5202.8712 | 5202.8712 | 5202.8712 | 5202.8712 | 5202.8712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 33425.5455 | 0.2 | 0.3 | 52143.8509 |  |  |  |  | 0 | 1615.81 | 1615.81 | 1615.81 | 1615.81 | 1615.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 16958.5561 | 0.2 | 0.3 | 26455.3475 |  |  |  |  | 0 | 3586.9678 | 3586.9678 | 3586.9678 | 3586.9678 | 3586.9678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 30437.6235 | 0.2 | 0.3 | 47482.6926 |  |  |  |  | 0 | 5425.2251 | 5425.2251 | 5425.2251 | 5425.2251 | 5425.2251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 89.7816 | 0.2 | 0.3 | 140.0593 |  |  |  |  | 0 | 9228.4898 | 9228.4898 | 9228.4898 | 9228.4898 | 9228.4898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 10312.3132 | 0.2 | 0.3 | 16087.2086 |  |  |  |  | 0 | 8046.9782 | 8046.9782 | 8046.9782 | 8046.9782 | 8046.9782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 29906.8228 | 0.2 | 0.3 | 46654.6436 |  |  |  |  | 0 | 8667.2608 | 8667.2608 | 8667.2608 | 8667.2608 | 8667.2608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 8615.6555 | 0.2 | 0.3 | 13440.4225 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 2557.6672 | 0.2 | 0.3 | 3989.9608 |  |  |  |  | 0 | 6761.1422 | 6761.1422 | 6761.1422 | 6761.1422 | 6761.1422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 6400.9271 | 0.2 | 0.3 | 9985.4462 |  |  |  |  | 0 | 5205.8871 | 5205.8871 | 5205.8871 | 5205.8871 | 5205.8871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17343.6292 | 0.2 | 0.3 | 27056.0616 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 13497.1793 | 0.2 | 0.3 | 21055.5998 |  |  |  |  | 0 | 5203.9011 | 5203.9011 | 5203.9011 | 5203.9011 | 5203.9011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 15164.6723 | 0.2 | 0.3 | 23656.8887 |  |  |  |  | 0 | 5203.9657 | 5203.9657 | 5203.9657 | 5203.9657 | 5203.9657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 2690.8481 | 0.2 | 0.3 | 4197.723 |  |  |  |  | 0 | 7837.8286 | 7837.8286 | 7837.8286 | 7837.8286 | 7837.8286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 4618.438 | 0.2 | 0.3 | 7204.7633 |  |  |  |  | 0 | 4968.1552 | 4968.1552 | 4968.1552 | 4968.1552 | 4968.1552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 15842.6297 | 0.2 | 0.3 | 24714.5024 |  |  |  |  | 0 | 8544.808 | 8544.808 | 8544.808 | 8544.808 | 8544.808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 4127.3761 | 0.2 | 0.3 | 6438.7068 |  |  |  |  | 0 | 4459.0504 | 4459.0504 | 4459.0504 | 4459.0504 | 4459.0504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17746.1099 | 0.2 | 0.3 | 27683.9315 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 14698.4101 | 0.2 | 0.3 | 22929.5197 |  |  |  |  | 0 | 5203.6692 | 5203.6692 | 5203.6692 | 5203.6692 | 5203.6692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 31868.9057 | 0.2 | 0.3 | 49715.4928 |  |  |  |  | 0 | 9792.6859 | 9792.6859 | 9792.6859 | 9792.6859 | 9792.6859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 29562.6166 | 0.2 | 0.3 | 46117.6819 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 90.2791 | 0.2 | 0.3 | 140.8353 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 1431.2846 | 0.2 | 0.3 | 2232.804 |  |  |  |  | 0 | 9783.8883 | 9783.8883 | 9783.8883 | 9783.8883 | 9783.8883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 29555.6518 | 0.2 | 0.3 | 46106.8168 |  |  |  |  | 0 | 5203.3872 | 5203.3872 | 5203.3872 | 5203.3872 | 5203.3872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 18537.6469 | 0.2 | 0.3 | 28918.7291 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 23036.7686 | 0.2 | 0.3 | 35937.359 |  |  |  |  | 0 | 5203.8714 | 5203.8714 | 5203.8714 | 5203.8714 | 5203.8714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 17017.4641 | 0.2 | 0.3 | 26547.244 |  |  |  |  | 0 | 5461.3794 | 5461.3794 | 5461.3794 | 5461.3794 | 5461.3794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 8507.9986 | 0.2 | 0.3 | 13272.4778 |  |  |  |  | 0 | 2349.6328 | 2349.6328 | 2349.6328 | 2349.6328 | 2349.6328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 22935.428 | 0.2 | 0.3 | 35779.2677 |  |  |  |  | 0 | 5343.8089 | 5343.8089 | 5343.8089 | 5343.8089 | 5343.8089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16909.8663 | 0.2 | 0.3 | 26379.3915 |  |  |  |  | 0 | 10241.6113 | 10241.6113 | 10241.6113 | 10241.6113 | 10241.6113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 13647.9725 | 0.2 | 0.3 | 21290.8372 |  |  |  |  | 0 | 5203.2541 | 5203.2541 | 5203.2541 | 5203.2541 | 5203.2541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 22746.9841 | 0.2 | 0.3 | 35485.2952 |  |  |  |  | 0 | 9511.0089 | 9511.0089 | 9511.0089 | 9511.0089 | 9511.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16887.2953 | 0.2 | 0.3 | 26344.1806 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 185.9371 | 0.2 | 0.3 | 290.0618 |  |  |  |  | 0 | 5203.3071 | 5203.3071 | 5203.3071 | 5203.3071 | 5203.3071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 13121.3038 | 0.2 | 0.3 | 20469.2339 |  |  |  |  | 0 | 9783.7564 | 9783.7564 | 9783.7564 | 9783.7564 | 9783.7564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 18444.6794 | 0.2 | 0.3 | 28773.6999 |  |  |  |  | 0 | 5203.4785 | 5203.4785 | 5203.4785 | 5203.4785 | 5203.4785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 18371.4097 | 0.2 | 0.3 | 28659.3992 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 23509.1194 | 0.2 | 0.3 | 36674.2263 |  |  |  |  | 0 | 8269.5563 | 8269.5563 | 8269.5563 | 8269.5563 | 8269.5563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 6971.1826 | 0.2 | 0.3 | 10875.0449 |  |  |  |  | 0 | 5201.9113 | 5201.9113 | 5201.9113 | 5201.9113 | 5201.9113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 8013.0542 | 0.2 | 0.3 | 12500.3646 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 15376.0657 | 0.2 | 0.3 | 23986.6624 |  |  |  |  | 0 | 5226.0459 | 5226.0459 | 5226.0459 | 5226.0459 | 5226.0459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 16665.9923 | 0.2 | 0.3 | 25998.948 |  |  |  |  | 0 | 2974.969 | 2974.969 | 2974.969 | 2974.969 | 2974.969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 14142.4004 | 0.2 | 0.3 | 22062.1446 |  |  |  |  | 0 | 2451.3331 | 2451.3331 | 2451.3331 | 2451.3331 | 2451.3331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 4766.2257 | 0.2 | 0.3 | 7435.3121 |  |  |  |  | 0 | 149.968 | 149.968 | 149.968 | 149.968 | 149.968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16666.0532 | 0.2 | 0.3 | 25999.043 |  |  |  |  | 0 | 2600.5501 | 2600.5501 | 2600.5501 | 2600.5501 | 2600.5501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 20545.9005 | 0.2 | 0.3 | 32051.6048 |  |  |  |  | 0 | 4946.0369 | 4946.0369 | 4946.0369 | 4946.0369 | 4946.0369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16009.1529 | 0.2 | 0.3 | 24974.2786 |  |  |  |  | 0 | 7032.1661 | 7032.1661 | 7032.1661 | 7032.1661 | 7032.1661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 1690.4545 | 0.2 | 0.3 | 2637.109 |  |  |  |  | 0 | 5224.7244 | 5224.7244 | 5224.7244 | 5224.7244 | 5224.7244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 1048.0438 | 0.2 | 0.3 | 1634.9483 |  |  |  |  | 0 | 8056.9607 | 8056.9607 | 8056.9607 | 8056.9607 | 8056.9607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 20130.6766 | 0.2 | 0.3 | 31403.8555 |  |  |  |  | 0 | 993.1949 | 993.1949 | 993.1949 | 993.1949 | 993.1949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 9801.663 | 0.2 | 0.3 | 15290.5943 |  |  |  |  | 0 | 4346.1498 | 4346.1498 | 4346.1498 | 4346.1498 | 4346.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 422.0019 | 0.2 | 0.3 | 658.3229 |  |  |  |  | 0 | 2866.2489 | 2866.2489 | 2866.2489 | 2866.2489 | 2866.2489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 25118.6577 | 0.2 | 0.3 | 39185.1061 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 18927.7911 | 0.2 | 0.3 | 29527.3541 |  |  |  |  | 0 | 8187.233 | 8187.233 | 8187.233 | 8187.233 | 8187.233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 9211.3909 | 0.2 | 0.3 | 14369.7699 |  |  |  |  | 0 | 9699.194 | 9699.194 | 9699.194 | 9699.194 | 9699.194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 24652.9752 | 0.2 | 0.3 | 38458.6413 |  |  |  |  | 0 | 5203.2966 | 5203.2966 | 5203.2966 | 5203.2966 | 5203.2966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 11444.1569 | 0.2 | 0.3 | 17852.8847 |  |  |  |  | 0 | 2039.3248 | 2039.3248 | 2039.3248 | 2039.3248 | 2039.3248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 16807.8237 | 0.2 | 0.3 | 26220.2049 |  |  |  |  | 0 | 5198.3585 | 5198.3585 | 5198.3585 | 5198.3585 | 5198.3585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 16694.9108 | 0.2 | 0.3 | 26044.0608 |  |  |  |  | 0 | 5205.263 | 5205.263 | 5205.263 | 5205.263 | 5205.263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 5613.8312 | 0.2 | 0.3 | 8757.5767 |  |  |  |  | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 25269.5163 | 0.2 | 0.3 | 39420.4455 |  |  |  |  | 0 | 3581.3457 | 3581.3457 | 3581.3457 | 3581.3457 | 3581.3457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 11231.7289 | 0.2 | 0.3 | 17521.4971 |  |  |  |  | 0 | 5578.4177 | 5578.4177 | 5578.4177 | 5578.4177 | 5578.4177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 18167.8409 | 0.2 | 0.3 | 28341.8319 |  |  |  |  | 0 | 5291.6672 | 5291.6672 | 5291.6672 | 5291.6672 | 5291.6672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 17525.5743 | 0.2 | 0.3 | 27339.896 |  |  |  |  | 0 | 7618.7474 | 7618.7474 | 7618.7474 | 7618.7474 | 7618.7474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 5599.0348 | 0.2 | 0.3 | 8734.4943 |  |  |  |  | 0 | 2782.9912 | 2782.9912 | 2782.9912 | 2782.9912 | 2782.9912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 29406.4331 | 0.2 | 0.3 | 45874.0357 |  |  |  |  | 0 | 2570.8252 | 2570.8252 | 2570.8252 | 2570.8252 | 2570.8252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 8839.2597 | 0.2 | 0.3 | 13789.2452 |  |  |  |  | 0 | 5864.9313 | 5864.9313 | 5864.9313 | 5864.9313 | 5864.9313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 19267.004 | 0.2 | 0.3 | 30056.5262 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 20262.5101 | 0.2 | 0.3 | 31609.5158 |  |  |  |  | 0 | 8389.8067 | 8389.8067 | 8389.8067 | 8389.8067 | 8389.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17062.0232 | 0.2 | 0.3 | 26616.7562 |  |  |  |  | 0 | 8714.1898 | 8714.1898 | 8714.1898 | 8714.1898 | 8714.1898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
239 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 18185.0459 | 0.2 | 0.3 | 28368.6716 |  |  |  |  | 0 | 2603.5826 | 2603.5826 | 2603.5826 | 2603.5826 | 2603.5826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 34007.2126 | 0.2 | 0.3 | 53051.2517 |  |  |  |  | 0 | 6247.4296 | 6247.4296 | 6247.4296 | 6247.4296 | 6247.4296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 4522.344 | 0.2 | 0.3 | 7054.8566 |  |  |  |  | 0 | 5916.574 | 5916.574 | 5916.574 | 5916.574 | 5916.574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 9275.382 | 0.2 | 0.3 | 14469.5959 |  |  |  |  | 0 | 7237.4108 | 7237.4108 | 7237.4108 | 7237.4108 | 7237.4108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17692.6094 | 0.2 | 0.3 | 27600.4707 |  |  |  |  | 0 | 5191.0878 | 5191.0878 | 5191.0878 | 5191.0878 | 5191.0878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 579.7291 | 0.2 | 0.3 | 904.3773 |  |  |  |  | 0 | 6140.564 | 6140.564 | 6140.564 | 6140.564 | 6140.564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 33928.8601 | 0.2 | 0.3 | 52929.0217 |  |  |  |  | 0 | 7485.3363 | 7485.3363 | 7485.3363 | 7485.3363 | 7485.3363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 29377.4887 | 0.2 | 0.3 | 45828.8823 |  |  |  |  | 0 | 3699.0839 | 3699.0839 | 3699.0839 | 3699.0839 | 3699.0839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 9200.7485 | 0.2 | 0.3 | 14353.1677 |  |  |  |  | 0 | 5361.5342 | 5361.5342 | 5361.5342 | 5361.5342 | 5361.5342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17412.8776 | 0.2 | 0.3 | 27164.0891 |  |  |  |  | 0 | 5613.8562 | 5613.8562 | 5613.8562 | 5613.8562 | 5613.8562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 32967.2266 | 0.2 | 0.3 | 51428.8735 |  |  |  |  | 0 | 10316.117 | 10316.117 | 10316.117 | 10316.117 | 10316.117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
250 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 18035.5275 | 0.2 | 0.3 | 28135.4228 |  |  |  |  | 0 | 4614.1786 | 4614.1786 | 4614.1786 | 4614.1786 | 4614.1786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 17156.0384 | 0.2 | 0.3 | 26763.4199 |  |  |  |  | 0 | 2538.1531 | 2538.1531 | 2538.1531 | 2538.1531 | 2538.1531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 39554.6921 | 0.2 | 0.3 | 61705.3197 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 36201.0216 | 0.2 | 0.3 | 56473.5937 |  |  |  |  | 0 | 8633.8729 | 8633.8729 | 8633.8729 | 8633.8729 | 8633.8729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 26578.63 | 0.2 | 0.3 | 41462.6628 |  |  |  |  | 0 | 9160.2151 | 9160.2151 | 9160.2151 | 9160.2151 | 9160.2151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | WESTON | 70328 | Private | 2036 | 5 | Swales | 66.6667 | 9205.9643 | 0.2 | 0.3 | 14361.3044 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
256 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 7708.5085 | 0.2 | 0.3 | 12025.2733 |  |  |  |  | 0 | 3931.3625 | 3931.3625 | 3931.3625 | 3931.3625 | 3931.3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17865.8225 | 0.2 | 0.3 | 27870.683 |  |  |  |  | 0 | 5616.8158 | 5616.8158 | 5616.8158 | 5616.8158 | 5616.8158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
258 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 1174.1412 | 0.2 | 0.3 | 1831.6603 |  |  |  |  | 0 | 8267.3046 | 8267.3046 | 8267.3046 | 8267.3046 | 8267.3046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 13725.4252 | 0.2 | 0.3 | 21411.6633 |  |  |  |  | 0 | 46.8189 | 46.8189 | 46.8189 | 46.8189 | 46.8189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 14828.2767 | 0.2 | 0.3 | 23132.1116 |  |  |  |  | 0 | 3418.476 | 3418.476 | 3418.476 | 3418.476 | 3418.476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
261 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 14038.6513 | 0.2 | 0.3 | 21900.2961 |  |  |  |  | 0 | 6017.3282 | 6017.3282 | 6017.3282 | 6017.3282 | 6017.3282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 1081.1742 | 0.2 | 0.3 | 1686.6318 |  |  |  |  | 0 | 1799.4494 | 1799.4494 | 1799.4494 | 1799.4494 | 1799.4494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
263 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 15113.8511 | 0.2 | 0.3 | 23577.6077 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 23503.2139 | 0.2 | 0.3 | 36665.0137 |  |  |  |  | 0 | 6379.6574 | 6379.6574 | 6379.6574 | 6379.6574 | 6379.6574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17773.4815 | 0.2 | 0.3 | 27726.6312 |  |  |  |  | 0 | 7443.6014 | 7443.6014 | 7443.6014 | 7443.6014 | 7443.6014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 18225.5264 | 0.2 | 0.3 | 28431.8212 |  |  |  |  | 0 | 5439.7342 | 5439.7342 | 5439.7342 | 5439.7342 | 5439.7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 38370.6037 | 0.2 | 0.3 | 59858.1418 |  |  |  |  | 0 | 5202.5194 | 5202.5194 | 5202.5194 | 5202.5194 | 5202.5194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
268 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 17582.701 | 0.2 | 0.3 | 27429.0136 |  |  |  |  | 0 | 8776.4661 | 8776.4661 | 8776.4661 | 8776.4661 | 8776.4661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
269 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 13072.9701 | 0.2 | 0.3 | 20393.8334 |  |  |  |  | 0 | 8938.9468 | 8938.9468 | 8938.9468 | 8938.9468 | 8938.9468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 7146.9462 | 0.2 | 0.3 | 11149.2361 |  |  |  |  | 0 | 5202.7753 | 5202.7753 | 5202.7753 | 5202.7753 | 5202.7753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 25592.3091 | 0.2 | 0.3 | 39924.0021 |  |  |  |  | 0 | 6444.1828 | 6444.1828 | 6444.1828 | 6444.1828 | 6444.1828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
272 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 18536.6029 | 0.2 | 0.3 | 28917.1005 |  |  |  |  | 0 | 5473.9369 | 5473.9369 | 5473.9369 | 5473.9369 | 5473.9369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 4132.5478 | 0.2 | 0.3 | 6446.7746 |  |  |  |  | 0 | 6786.9053 | 6786.9053 | 6786.9053 | 6786.9053 | 6786.9053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
274 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 24800.4461 | 0.2 | 0.3 | 38688.6959 |  |  |  |  | 0 | 7149.6424 | 7149.6424 | 7149.6424 | 7149.6424 | 7149.6424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 42011.1831 | 0.2 | 0.3 | 65537.4456 |  |  |  |  | 0 | 5206.6327 | 5206.6327 | 5206.6327 | 5206.6327 | 5206.6327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
276 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16773.5104 | 0.2 | 0.3 | 26166.6762 |  |  |  |  | 0 | 5206.0356 | 5206.0356 | 5206.0356 | 5206.0356 | 5206.0356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 5291.3467 | 0.2 | 0.3 | 8254.5008 |  |  |  |  | 0 | 4273.4665 | 4273.4665 | 4273.4665 | 4273.4665 | 4273.4665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
278 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 26913.6918 | 0.2 | 0.3 | 41985.3592 |  |  |  |  | 0 | 8060.1897 | 8060.1897 | 8060.1897 | 8060.1897 | 8060.1897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
279 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 22228.3983 | 0.2 | 0.3 | 34676.3013 |  |  |  |  | 0 | 5907.5525 | 5907.5525 | 5907.5525 | 5907.5525 | 5907.5525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 5946.2791 | 0.2 | 0.3 | 9276.1953 |  |  |  |  | 0 | 5977.659 | 5977.659 | 5977.659 | 5977.659 | 5977.659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 27570.154 | 0.2 | 0.3 | 43009.4402 |  |  |  |  | 0 | 9023.8781 | 9023.8781 | 9023.8781 | 9023.8781 | 9023.8781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 26226.6179 | 0.2 | 0.3 | 40913.524 |  |  |  |  | 0 | 8986.3061 | 8986.3061 | 8986.3061 | 8986.3061 | 8986.3061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 20982.9961 | 0.2 | 0.3 | 32733.474 |  |  |  |  | 0 | 8750.9375 | 8750.9375 | 8750.9375 | 8750.9375 | 8750.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 24373.9177 | 0.2 | 0.3 | 38023.3116 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
285 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 947.5256 | 0.2 | 0.3 | 1478.1399 |  |  |  |  | 0 | 4314.9325 | 4314.9325 | 4314.9325 | 4314.9325 | 4314.9325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
286 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 15817.3191 | 0.2 | 0.3 | 24675.0178 |  |  |  |  | 0 | 1509.241 | 1509.241 | 1509.241 | 1509.241 | 1509.241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
287 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 38190.1789 | 0.2 | 0.3 | 59576.679 |  |  |  |  | 0 | 3456.8641 | 3456.8641 | 3456.8641 | 3456.8641 | 3456.8641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
288 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 16031.2943 | 0.2 | 0.3 | 25008.8192 |  |  |  |  | 0 | 3129.5539 | 3129.5539 | 3129.5539 | 3129.5539 | 3129.5539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
289 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 17986.3258 | 0.2 | 0.3 | 28058.6682 |  |  |  |  | 0 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 5092.1671 | 0.2 | 0.3 | 7943.7807 |  |  |  |  | 0 | 3109.4544 | 3109.4544 | 3109.4544 | 3109.4544 | 3109.4544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
291 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 16168.4644 | 0.2 | 0.3 | 25222.8045 |  |  |  |  | 0 | 1912.0763 | 1912.0763 | 1912.0763 | 1912.0763 | 1912.0763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
292 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 21499.2646 | 0.2 | 0.3 | 33538.8528 |  |  |  |  | 0 | 5204.1828 | 5204.1828 | 5204.1828 | 5204.1828 | 5204.1828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
293 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 11064.7939 | 0.2 | 0.3 | 17261.0785 |  |  |  |  | 0 | 8578.7575 | 8578.7575 | 8578.7575 | 8578.7575 | 8578.7575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 12392.3224 | 0.2 | 0.3 | 19332.0229 |  |  |  |  | 0 | 5203.1202 | 5203.1202 | 5203.1202 | 5203.1202 | 5203.1202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
295 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 34139.9577 | 0.2 | 0.3 | 53258.334 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
296 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 13622.2752 | 0.2 | 0.3 | 21250.7493 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
297 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 10992.7701 | 0.2 | 0.3 | 17148.7214 |  |  |  |  | 0 | 5200.2361 | 5200.2361 | 5200.2361 | 5200.2361 | 5200.2361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
298 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 16536.5973 | 0.2 | 0.3 | 25797.0917 |  |  |  |  | 0 | 5753.0735 | 5753.0735 | 5753.0735 | 5753.0735 | 5753.0735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
299 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 17085.8458 | 0.2 | 0.3 | 26653.9194 |  |  |  |  | 0 | 3728.342 | 3728.342 | 3728.342 | 3728.342 | 3728.342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 11377.3501 | 0.2 | 0.3 | 17748.6661 |  |  |  |  | 0 | 6917.5987 | 6917.5987 | 6917.5987 | 6917.5987 | 6917.5987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 18892.2177 | 0.2 | 0.3 | 29471.8596 |  |  |  |  | 0 | 7196.2252 | 7196.2252 | 7196.2252 | 7196.2252 | 7196.2252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 2533.6176 | 0.2 | 0.3 | 3952.4435 |  |  |  |  | 0 | 3318.9481 | 3318.9481 | 3318.9481 | 3318.9481 | 3318.9481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 27704.7414 | 0.2 | 0.3 | 43219.3966 |  |  |  |  | 0 | 7041.3115 | 7041.3115 | 7041.3115 | 7041.3115 | 7041.3115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 20375.2235 | 0.2 | 0.3 | 31785.3487 |  |  |  |  | 0 | 5203.9748 | 5203.9748 | 5203.9748 | 5203.9748 | 5203.9748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 22272.4805 | 0.2 | 0.3 | 34745.0696 |  |  |  |  | 0 | 8358.654 | 8358.654 | 8358.654 | 8358.654 | 8358.654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 12105.6975 | 0.2 | 0.3 | 18884.8882 |  |  |  |  | 0 | 5203.4449 | 5203.4449 | 5203.4449 | 5203.4449 | 5203.4449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 28713.2153 | 0.2 | 0.3 | 44792.6158 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
308 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 22387.666 | 0.2 | 0.3 | 34924.759 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 20414.4857 | 0.2 | 0.3 | 31846.5977 |  |  |  |  | 0 | 5203.6128 | 5203.6128 | 5203.6128 | 5203.6128 | 5203.6128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 43692.5184 | 0.2 | 0.3 | 68160.3287 |  |  |  |  | 0 | 6697.4404 | 6697.4404 | 6697.4404 | 6697.4404 | 6697.4404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
311 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 2934.5587 | 0.2 | 0.3 | 4577.9115 |  |  |  |  | 0 | 4679.1212 | 4679.1212 | 4679.1212 | 4679.1212 | 4679.1212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
312 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 13688.1726 | 0.2 | 0.3 | 21353.5493 |  |  |  |  | 0 | 4412.5583 | 4412.5583 | 4412.5583 | 4412.5583 | 4412.5583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
313 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16670.5806 | 0.2 | 0.3 | 26006.1057 |  |  |  |  | 0 | 4133.3652 | 4133.3652 | 4133.3652 | 4133.3652 | 4133.3652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
314 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 19906.7489 | 0.2 | 0.3 | 31054.5283 |  |  |  |  | 0 | 4071.0218 | 4071.0218 | 4071.0218 | 4071.0218 | 4071.0218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 32356.9607 | 0.2 | 0.3 | 50476.8586 |  |  |  |  | 0 | 1134.7025 | 1134.7025 | 1134.7025 | 1134.7025 | 1134.7025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
316 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 25646.3204 | 0.2 | 0.3 | 40008.2598 |  |  |  |  | 0 | 5768.1422 | 5768.1422 | 5768.1422 | 5768.1422 | 5768.1422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
317 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 16994.4597 | 0.2 | 0.3 | 26511.3572 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
318 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 18961.0319 | 0.2 | 0.3 | 29579.2097 |  |  |  |  | 0 | 9783.9817 | 9783.9817 | 9783.9817 | 9783.9817 | 9783.9817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
319 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 17345.8648 | 0.2 | 0.3 | 27059.5491 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
320 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 6641.3514 | 0.2 | 0.3 | 10360.5082 |  |  |  |  | 0 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
321 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 21751.0181 | 0.2 | 0.3 | 33931.5882 |  |  |  |  | 0 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
322 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 2267.6922 | 0.2 | 0.3 | 3537.5998 |  |  |  |  | 0 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
323 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 22920.4363 | 0.2 | 0.3 | 35755.8807 |  |  |  |  | 0 | 5205.1826 | 5205.1826 | 5205.1826 | 5205.1826 | 5205.1826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 26012.3886 | 0.2 | 0.3 | 40579.3262 |  |  |  |  | 0 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
325 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 13060.36 | 0.2 | 0.3 | 20374.1616 |  |  |  |  | 0 | 3223.006 | 3223.006 | 3223.006 | 3223.006 | 3223.006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
326 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 21933.3431 | 0.2 | 0.3 | 34216.0153 |  |  |  |  | 0 | 7359.5474 | 7359.5474 | 7359.5474 | 7359.5474 | 7359.5474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
327 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 26826.5908 | 0.2 | 0.3 | 41849.4816 |  |  |  |  | 0 | 6976.6565 | 6976.6565 | 6976.6565 | 6976.6565 | 6976.6565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 6813.3945 | 0.2 | 0.3 | 10628.8954 |  |  |  |  | 0 | 4549.4868 | 4549.4868 | 4549.4868 | 4549.4868 | 4549.4868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
329 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 18786.7221 | 0.2 | 0.3 | 29307.2864 |  |  |  |  | 0 | 5204.6211 | 5204.6211 | 5204.6211 | 5204.6211 | 5204.6211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 17478.8095 | 0.2 | 0.3 | 27266.9429 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 30227.0193 | 0.2 | 0.3 | 47154.1501 |  |  |  |  | 0 | 6631.4087 | 6631.4087 | 6631.4087 | 6631.4087 | 6631.4087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 16773.5681 | 0.2 | 0.3 | 26166.7663 |  |  |  |  | 0 | 1479.1807 | 1479.1807 | 1479.1807 | 1479.1807 | 1479.1807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
333 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 0.079133 | 0.2 | 0.3 | 0.12345 |  |  |  |  | 0 | 1271.9888 | 1271.9888 | 1271.9888 | 1271.9888 | 1271.9888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
334 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 7193.8163 | 0.2 | 0.3 | 11222.3534 |  |  |  |  | 0 | 4303.5615 | 4303.5615 | 4303.5615 | 4303.5615 | 4303.5615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
335 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17903.4717 | 0.2 | 0.3 | 27929.4158 |  |  |  |  | 0 | 9759.3527 | 9759.3527 | 9759.3527 | 9759.3527 | 9759.3527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
336 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 22908.514 | 0.2 | 0.3 | 35737.2818 |  |  |  |  | 0 | 5228.5896 | 5228.5896 | 5228.5896 | 5228.5896 | 5228.5896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
337 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 3695.0613 | 0.2 | 0.3 | 5764.2957 |  |  |  |  | 0 | 5203.246 | 5203.246 | 5203.246 | 5203.246 | 5203.246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
338 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 27140.6337 | 0.2 | 0.3 | 42339.3886 |  |  |  |  | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
339 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 22963.2643 | 0.2 | 0.3 | 35822.6923 |  |  |  |  | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
340 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 15651.6968 | 0.2 | 0.3 | 24416.647 |  |  |  |  | 0 | 5203.3897 | 5203.3897 | 5203.3897 | 5203.3897 | 5203.3897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
341 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 27205.381 | 0.2 | 0.3 | 42440.3944 |  |  |  |  | 0 | 5213.0711 | 5213.0711 | 5213.0711 | 5213.0711 | 5213.0711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
342 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 17324.3357 | 0.2 | 0.3 | 27025.9636 |  |  |  |  | 0 | 1834.6515 | 1834.6515 | 1834.6515 | 1834.6515 | 1834.6515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
343 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 2139.8045 | 0.2 | 0.3 | 3338.0951 |  |  |  |  | 0 | 5205.0462 | 5205.0462 | 5205.0462 | 5205.0462 | 5205.0462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
344 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 14495.5559 | 0.2 | 0.3 | 22613.0673 |  |  |  |  | 0 | 5204.1367 | 5204.1367 | 5204.1367 | 5204.1367 | 5204.1367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
345 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 8557.7208 | 0.2 | 0.3 | 13350.0444 |  |  |  |  | 0 | 561.1257 | 561.1257 | 561.1257 | 561.1257 | 561.1257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
346 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 19228.0115 | 0.2 | 0.3 | 29995.698 |  |  |  |  | 0 | 8689.9253 | 8689.9253 | 8689.9253 | 8689.9253 | 8689.9253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
347 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 11881.5002 | 0.2 | 0.3 | 18535.1403 |  |  |  |  | 0 | 5200.811 | 5200.811 | 5200.811 | 5200.811 | 5200.811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 4857.5425 | 0.2 | 0.3 | 7577.7662 |  |  |  |  | 0 | 7886.0751 | 7886.0751 | 7886.0751 | 7886.0751 | 7886.0751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
349 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 19060.1327 | 0.2 | 0.3 | 29733.8071 |  |  |  |  | 0 | 7090.5877 | 7090.5877 | 7090.5877 | 7090.5877 | 7090.5877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
350 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 24892.6897 | 0.2 | 0.3 | 38832.5959 |  |  |  |  | 0 | 5203.1543 | 5203.1543 | 5203.1543 | 5203.1543 | 5203.1543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
351 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 13946.4992 | 0.2 | 0.3 | 21756.5388 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
352 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 16907.6534 | 0.2 | 0.3 | 26375.9393 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
353 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 12231.2493 | 0.2 | 0.3 | 19080.749 |  |  |  |  | 0 | 5203.5324 | 5203.5324 | 5203.5324 | 5203.5324 | 5203.5324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 97.5395 | 0.2 | 0.3 | 152.1616 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 9084.8323 | 0.2 | 0.3 | 14172.3384 |  |  |  |  | 0 | 5756.1493 | 5756.1493 | 5756.1493 | 5756.1493 | 5756.1493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 27237.1659 | 0.2 | 0.3 | 42489.9789 |  |  |  |  | 0 | 5204.9596 | 5204.9596 | 5204.9596 | 5204.9596 | 5204.9596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
357 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 18231.1065 | 0.2 | 0.3 | 28440.5261 |  |  |  |  | 0 | 5204.1523 | 5204.1523 | 5204.1523 | 5204.1523 | 5204.1523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 23176.9223 | 0.2 | 0.3 | 36155.9988 |  |  |  |  | 0 | 6111.6452 | 6111.6452 | 6111.6452 | 6111.6452 | 6111.6452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
359 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 21026.0115 | 0.2 | 0.3 | 32800.5779 |  |  |  |  | 0 | 5204.4332 | 5204.4332 | 5204.4332 | 5204.4332 | 5204.4332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
360 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 20075.9982 | 0.2 | 0.3 | 31318.5572 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
361 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 20190.9015 | 0.2 | 0.3 | 31497.8063 |  |  |  |  | 0 | 4974.4609 | 4974.4609 | 4974.4609 | 4974.4609 | 4974.4609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
362 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 17274.0105 | 0.2 | 0.3 | 26947.4563 |  |  |  |  | 0 | 5129.768 | 5129.768 | 5129.768 | 5129.768 | 5129.768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
363 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 18005.8911 | 0.2 | 0.3 | 28089.1902 |  |  |  |  | 0 | 4704.8081 | 4704.8081 | 4704.8081 | 4704.8081 | 4704.8081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
364 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 14073.6476 | 0.2 | 0.3 | 21954.8903 |  |  |  |  | 0 | 7084.9344 | 7084.9344 | 7084.9344 | 7084.9344 | 7084.9344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
365 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 6670.9389 | 0.2 | 0.3 | 10406.6646 |  |  |  |  | 0 | 7772.6372 | 7772.6372 | 7772.6372 | 7772.6372 | 7772.6372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
366 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 31842.7577 | 0.2 | 0.3 | 49674.702 |  |  |  |  | 0 | 5203.6446 | 5203.6446 | 5203.6446 | 5203.6446 | 5203.6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
367 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 144.4155 | 0.2 | 0.3 | 225.2882 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 3386.5503 | 0.2 | 0.3 | 5283.0184 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 24643.8051 | 0.2 | 0.3 | 38444.336 |  |  |  |  | 0 | 5203.5992 | 5203.5992 | 5203.5992 | 5203.5992 | 5203.5992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
370 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 12145.0351 | 0.2 | 0.3 | 18946.2547 |  |  |  |  | 0 | 5205.2459 | 5205.2459 | 5205.2459 | 5205.2459 | 5205.2459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
371 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 16938.9509 | 0.2 | 0.3 | 26424.7635 |  |  |  |  | 0 | 4187.4462 | 4187.4462 | 4187.4462 | 4187.4462 | 4187.4462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
372 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 4848.6095 | 0.2 | 0.3 | 7563.8309 |  |  |  |  | 0 | 6097.2538 | 6097.2538 | 6097.2538 | 6097.2538 | 6097.2538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 29572.1347 | 0.2 | 0.3 | 46132.5302 |  |  |  |  | 0 | 3849.2216 | 3849.2216 | 3849.2216 | 3849.2216 | 3849.2216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
374 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 6240.0371 | 0.2 | 0.3 | 9734.4578 |  |  |  |  | 0 | 5682.0727 | 5682.0727 | 5682.0727 | 5682.0727 | 5682.0727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
375 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 535.5812 | 0.2 | 0.3 | 835.5067 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
376 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 6288.1749 | 0.2 | 0.3 | 9809.5529 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 6661.0269 | 0.2 | 0.3 | 10391.202 |  |  |  |  | 0 | 4872.7325 | 4872.7325 | 4872.7325 | 4872.7325 | 4872.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 19011.2949 | 0.2 | 0.3 | 29657.62 |  |  |  |  | 0 | 2673.5479 | 2673.5479 | 2673.5479 | 2673.5479 | 2673.5479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
379 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 25914.2275 | 0.2 | 0.3 | 40426.195 |  |  |  |  | 0 | 1402.0129 | 1402.0129 | 1402.0129 | 1402.0129 | 1402.0129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
380 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 14831.5349 | 0.2 | 0.3 | 23137.1944 |  |  |  |  | 0 | 26.5252 | 26.5252 | 26.5252 | 26.5252 | 26.5252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
381 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 9633.2524 | 0.2 | 0.3 | 15027.8737 |  |  |  |  | 0 | 2125.1584 | 2125.1584 | 2125.1584 | 2125.1584 | 2125.1584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
382 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 23562.0901 | 0.2 | 0.3 | 36756.8605 |  |  |  |  | 0 | 5201.8289 | 5201.8289 | 5201.8289 | 5201.8289 | 5201.8289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
383 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 25297.7251 | 0.2 | 0.3 | 39464.4511 |  |  |  |  | 0 | 5201.5266 | 5201.5266 | 5201.5266 | 5201.5266 | 5201.5266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
384 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 18065.0578 | 0.2 | 0.3 | 28181.4902 |  |  |  |  | 0 | 6516.974 | 6516.974 | 6516.974 | 6516.974 | 6516.974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
385 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 18384.9034 | 0.2 | 0.3 | 28680.4493 |  |  |  |  | 0 | 5201.7098 | 5201.7098 | 5201.7098 | 5201.7098 | 5201.7098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 22725.1771 | 0.2 | 0.3 | 35451.2763 |  |  |  |  | 0 | 10489.1627 | 10489.1627 | 10489.1627 | 10489.1627 | 10489.1627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 37940.1815 | 0.2 | 0.3 | 59186.6832 |  |  |  |  | 0 | 7209.0479 | 7209.0479 | 7209.0479 | 7209.0479 | 7209.0479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
388 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 6158.9917 | 0.2 | 0.3 | 9608.027 |  |  |  |  | 0 | 7370.7664 | 7370.7664 | 7370.7664 | 7370.7664 | 7370.7664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
389 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 8133.8585 | 0.2 | 0.3 | 12688.8192 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
390 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 8533.9351 | 0.2 | 0.3 | 13312.9387 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
391 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 33990.8791 | 0.2 | 0.3 | 53025.7714 |  |  |  |  | 0 | 7467.0415 | 7467.0415 | 7467.0415 | 7467.0415 | 7467.0415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
392 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 22429.3532 | 0.2 | 0.3 | 34989.791 |  |  |  |  | 0 | 1801.697 | 1801.697 | 1801.697 | 1801.697 | 1801.697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 8039.5299 | 0.2 | 0.3 | 12541.6667 |  |  |  |  | 0 | 6089.5786 | 6089.5786 | 6089.5786 | 6089.5786 | 6089.5786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
394 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 31173.2959 | 0.2 | 0.3 | 48630.3417 |  |  |  |  | 0 | 11902.7774 | 11902.7774 | 11902.7774 | 11902.7774 | 11902.7774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
395 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 27407.6777 | 0.2 | 0.3 | 42755.9772 |  |  |  |  | 0 | 7506.4742 | 7506.4742 | 7506.4742 | 7506.4742 | 7506.4742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
396 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 41536.2746 | 0.2 | 0.3 | 64796.5884 |  |  |  |  | 0 | 6347.2581 | 6347.2581 | 6347.2581 | 6347.2581 | 6347.2581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
397 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 1460.9341 | 0.2 | 0.3 | 2279.0571 |  |  |  |  | 0 | 5210.8125 | 5210.8125 | 5210.8125 | 5210.8125 | 5210.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 21317.8531 | 0.2 | 0.3 | 33255.8509 |  |  |  |  | 0 | 8039.0772 | 8039.0772 | 8039.0772 | 8039.0772 | 8039.0772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
399 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 34401.9138 | 0.2 | 0.3 | 53666.9855 |  |  |  |  | 0 | 8604.941 | 8604.941 | 8604.941 | 8604.941 | 8604.941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 13029.6115 | 0.2 | 0.3 | 20326.194 |  |  |  |  | 0 | 8749.5586 | 8749.5586 | 8749.5586 | 8749.5586 | 8749.5586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 6953.2372 | 0.2 | 0.3 | 10847.05 |  |  |  |  | 0 | 8962.6982 | 8962.6982 | 8962.6982 | 8962.6982 | 8962.6982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 14709.7866 | 0.2 | 0.3 | 22947.2671 |  |  |  |  | 0 | 4230.4973 | 4230.4973 | 4230.4973 | 4230.4973 | 4230.4973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 18853.7375 | 0.2 | 0.3 | 29411.8306 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
404 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 898.8139 | 0.2 | 0.3 | 1402.1497 |  |  |  |  | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 33167.841 | 0.2 | 0.3 | 51741.832 |  |  |  |  | 0 | 4952.1447 | 4952.1447 | 4952.1447 | 4952.1447 | 4952.1447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
406 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 3287.0154 | 0.2 | 0.3 | 5127.744 |  |  |  |  | 0 | 481.1205 | 481.1205 | 481.1205 | 481.1205 | 481.1205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
407 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 28788.8651 | 0.2 | 0.3 | 44910.6295 |  |  |  |  | 0 | 1907.7035 | 1907.7035 | 1907.7035 | 1907.7035 | 1907.7035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
408 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 24680.0553 | 0.2 | 0.3 | 38500.8863 |  |  |  |  | 0 | 3677.4313 | 3677.4313 | 3677.4313 | 3677.4313 | 3677.4313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 13687.5039 | 0.2 | 0.3 | 21352.506 |  |  |  |  | 0 | 6388.8252 | 6388.8252 | 6388.8252 | 6388.8252 | 6388.8252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
410 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 24368.6406 | 0.2 | 0.3 | 38015.0793 |  |  |  |  | 0 | 5210.8125 | 5210.8125 | 5210.8125 | 5210.8125 | 5210.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
411 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 28473.0574 | 0.2 | 0.3 | 44417.9695 |  |  |  |  | 0 | 5202.8049 | 5202.8049 | 5202.8049 | 5202.8049 | 5202.8049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
412 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 19858.5874 | 0.2 | 0.3 | 30979.3963 |  |  |  |  | 0 | 5199.8928 | 5199.8928 | 5199.8928 | 5199.8928 | 5199.8928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
413 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 31738.3341 | 0.2 | 0.3 | 49511.8011 |  |  |  |  | 0 | 5202.2306 | 5202.2306 | 5202.2306 | 5202.2306 | 5202.2306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
414 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 30248.1807 | 0.2 | 0.3 | 47187.1619 |  |  |  |  | 0 | 5203.3759 | 5203.3759 | 5203.3759 | 5203.3759 | 5203.3759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
415 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 853.3322 | 0.2 | 0.3 | 1331.1982 |  |  |  |  | 0 | 5201.5895 | 5201.5895 | 5201.5895 | 5201.5895 | 5201.5895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
416 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 19659.9639 | 0.2 | 0.3 | 30669.5437 |  |  |  |  | 0 | 5201.5833 | 5201.5833 | 5201.5833 | 5201.5833 | 5201.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
417 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 17053.7293 | 0.2 | 0.3 | 26603.8178 |  |  |  |  | 0 | 5201.3427 | 5201.3427 | 5201.3427 | 5201.3427 | 5201.3427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
418 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 17052.4 | 0.2 | 0.3 | 26601.744 |  |  |  |  | 0 | 8005.0102 | 8005.0102 | 8005.0102 | 8005.0102 | 8005.0102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
419 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 12532.5431 | 0.2 | 0.3 | 19550.7673 |  |  |  |  | 0 | 10408.5211 | 10408.5211 | 10408.5211 | 10408.5211 | 10408.5211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
420 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17115.5115 | 0.2 | 0.3 | 26700.198 |  |  |  |  | 0 | 10408.6943 | 10408.6943 | 10408.6943 | 10408.6943 | 10408.6943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
421 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 14637.5997 | 0.2 | 0.3 | 22834.6556 |  |  |  |  | 0 | 11925.3047 | 11925.3047 | 11925.3047 | 11925.3047 | 11925.3047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
422 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 1427.2495 | 0.2 | 0.3 | 2226.5093 |  |  |  |  | 0 | 9005.5301 | 9005.5301 | 9005.5301 | 9005.5301 | 9005.5301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
423 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 17370.9739 | 0.2 | 0.3 | 27098.7193 |  |  |  |  | 0 | 5195.6288 | 5195.6288 | 5195.6288 | 5195.6288 | 5195.6288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
424 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 5181.9063 | 0.2 | 0.3 | 8083.7738 |  |  |  |  | 0 | 5202.4834 | 5202.4834 | 5202.4834 | 5202.4834 | 5202.4834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
425 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 17877.3903 | 0.2 | 0.3 | 27888.7289 |  |  |  |  | 0 | 6907.3837 | 6907.3837 | 6907.3837 | 6907.3837 | 6907.3837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
426 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 18012.4427 | 0.2 | 0.3 | 28099.4107 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
427 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 26432.4026 | 0.2 | 0.3 | 41234.5481 |  |  |  |  | 0 | 5211.1746 | 5211.1746 | 5211.1746 | 5211.1746 | 5211.1746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
428 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 33035.4035 | 0.2 | 0.3 | 51535.2294 |  |  |  |  | 0 | 5204.0123 | 5204.0123 | 5204.0123 | 5204.0123 | 5204.0123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 8623.8188 | 0.2 | 0.3 | 13453.1573 |  |  |  |  | 0 | 5201.3372 | 5201.3372 | 5201.3372 | 5201.3372 | 5201.3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
430 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 20842.3877 | 0.2 | 0.3 | 32514.1249 |  |  |  |  | 0 | 9268.2156 | 9268.2156 | 9268.2156 | 9268.2156 | 9268.2156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
431 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 13188.9659 | 0.2 | 0.3 | 20574.7869 |  |  |  |  | 0 | 9806.7149 | 9806.7149 | 9806.7149 | 9806.7149 | 9806.7149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
432 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16956.9542 | 0.2 | 0.3 | 26452.8486 |  |  |  |  | 0 | 10408.472 | 10408.472 | 10408.472 | 10408.472 | 10408.472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
433 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 26454.6123 | 0.2 | 0.3 | 41269.1951 |  |  |  |  | 0 | 5211.4204 | 5211.4204 | 5211.4204 | 5211.4204 | 5211.4204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 28072.0147 | 0.2 | 0.3 | 43792.3429 |  |  |  |  | 0 | 5218.3102 | 5218.3102 | 5218.3102 | 5218.3102 | 5218.3102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
435 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 17175.3574 | 0.2 | 0.3 | 26793.5575 |  |  |  |  | 0 | 5211.1537 | 5211.1537 | 5211.1537 | 5211.1537 | 5211.1537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
436 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 12597.5997 | 0.2 | 0.3 | 19652.2556 |  |  |  |  | 0 | 5205.7447 | 5205.7447 | 5205.7447 | 5205.7447 | 5205.7447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
437 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 16692.0431 | 0.2 | 0.3 | 26039.5872 |  |  |  |  | 0 | 5226.5933 | 5226.5933 | 5226.5933 | 5226.5933 | 5226.5933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
438 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 17155.4894 | 0.2 | 0.3 | 26762.5635 |  |  |  |  | 0 | 5244.336 | 5244.336 | 5244.336 | 5244.336 | 5244.336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
439 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 19576.3212 | 0.2 | 0.3 | 30539.0611 |  |  |  |  | 0 | 5225.4843 | 5225.4843 | 5225.4843 | 5225.4843 | 5225.4843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
440 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 17372.3381 | 0.2 | 0.3 | 27100.8474 |  |  |  |  | 0 | 10408.4032 | 10408.4032 | 10408.4032 | 10408.4032 | 10408.4032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
441 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 14869.242 | 0.2 | 0.3 | 23196.0175 |  |  |  |  | 0 | 9291.5758 | 9291.5758 | 9291.5758 | 9291.5758 | 9291.5758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
442 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 16919.8045 | 0.2 | 0.3 | 26394.8951 |  |  |  |  | 0 | 9566.2508 | 9566.2508 | 9566.2508 | 9566.2508 | 9566.2508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
443 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 42515.9049 | 0.2 | 0.3 | 66324.8116 |  |  |  |  | 0 | 8190.8986 | 8190.8986 | 8190.8986 | 8190.8986 | 8190.8986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
444 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 20488.5972 | 0.2 | 0.3 | 31962.2116 |  |  |  |  | 0 | 5239.0125 | 5239.0125 | 5239.0125 | 5239.0125 | 5239.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
445 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 20013.3477 | 0.2 | 0.3 | 31220.8225 |  |  |  |  | 0 | 5231.107 | 5231.107 | 5231.107 | 5231.107 | 5231.107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
446 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 5467.6883 | 0.2 | 0.3 | 8529.5938 |  |  |  |  | 0 | 5244.7277 | 5244.7277 | 5244.7277 | 5244.7277 | 5244.7277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
447 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 5377.9592 | 0.2 | 0.3 | 8389.6164 |  |  |  |  | 0 | 5300.5335 | 5300.5335 | 5300.5335 | 5300.5335 | 5300.5335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
448 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 19893.3015 | 0.2 | 0.3 | 31033.5503 |  |  |  |  | 0 | 8424.283 | 8424.283 | 8424.283 | 8424.283 | 8424.283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
449 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 33821.5575 | 0.2 | 0.3 | 52761.6298 |  |  |  |  | 0 | 9008.0902 | 9008.0902 | 9008.0902 | 9008.0902 | 9008.0902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
450 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 36554.2797 | 0.2 | 0.3 | 57024.6763 |  |  |  |  | 0 | 8010.8431 | 8010.8431 | 8010.8431 | 8010.8431 | 8010.8431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
451 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 28166.0443 | 0.2 | 0.3 | 43939.0292 |  |  |  |  | 0 | 6518.8064 | 6518.8064 | 6518.8064 | 6518.8064 | 6518.8064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
452 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16667.8984 | 0.2 | 0.3 | 26001.9215 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
453 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 660.0627 | 0.2 | 0.3 | 1029.6979 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
454 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 8200.2485 | 0.2 | 0.3 | 12792.3876 |  |  |  |  | 0 | 4727.5392 | 4727.5392 | 4727.5392 | 4727.5392 | 4727.5392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
455 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 19439.3295 | 0.2 | 0.3 | 30325.3541 |  |  |  |  | 0 | 558.8902 | 558.8902 | 558.8902 | 558.8902 | 558.8902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
456 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 4590.5701 | 0.2 | 0.3 | 7161.2893 |  |  |  |  | 0 | 7869.3196 | 7869.3196 | 7869.3196 | 7869.3196 | 7869.3196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
457 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 8003.9313 | 0.2 | 0.3 | 12486.1329 |  |  |  |  | 0 | 10022.0299 | 10022.0299 | 10022.0299 | 10022.0299 | 10022.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
458 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 38.7529 | 0.2 | 0.3 | 60.4545 |  |  |  |  | 0 | 10073.8822 | 10073.8822 | 10073.8822 | 10073.8822 | 10073.8822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
459 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 5057.4985 | 0.2 | 0.3 | 7889.6977 |  |  |  |  | 0 | 9928.1333 | 9928.1333 | 9928.1333 | 9928.1333 | 9928.1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
460 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17908.8173 | 0.2 | 0.3 | 27937.7549 |  |  |  |  | 0 | 9668.9741 | 9668.9741 | 9668.9741 | 9668.9741 | 9668.9741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
461 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17977.7471 | 0.2 | 0.3 | 28045.2854 |  |  |  |  | 0 | 5851.4408 | 5851.4408 | 5851.4408 | 5851.4408 | 5851.4408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
462 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 4663.0967 | 0.2 | 0.3 | 7274.4308 |  |  |  |  | 0 | 5476.0765 | 5476.0765 | 5476.0765 | 5476.0765 | 5476.0765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
463 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16178.252 | 0.2 | 0.3 | 25238.0731 |  |  |  |  | 0 | 5403.0346 | 5403.0346 | 5403.0346 | 5403.0346 | 5403.0346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
464 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 6799.6295 | 0.2 | 0.3 | 10607.422 |  |  |  |  | 0 | 5389.9164 | 5389.9164 | 5389.9164 | 5389.9164 | 5389.9164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
465 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17352.5252 | 0.2 | 0.3 | 27069.9393 |  |  |  |  | 0 | 5447.3226 | 5447.3226 | 5447.3226 | 5447.3226 | 5447.3226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
466 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16877.2439 | 0.2 | 0.3 | 26328.5005 |  |  |  |  | 0 | 2716.9017 | 2716.9017 | 2716.9017 | 2716.9017 | 2716.9017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
467 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 16892.4169 | 0.2 | 0.3 | 26352.1704 |  |  |  |  | 0 | 2304.329 | 2304.329 | 2304.329 | 2304.329 | 2304.329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
468 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 9754.1109 | 0.2 | 0.3 | 15216.4131 |  |  |  |  | 0 | 3416.9502 | 3416.9502 | 3416.9502 | 3416.9502 | 3416.9502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
469 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 8984.0575 | 0.2 | 0.3 | 14015.1296 |  |  |  |  | 0 | 7852.7618 | 7852.7618 | 7852.7618 | 7852.7618 | 7852.7618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
470 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 7757.3325 | 0.2 | 0.3 | 12101.4388 |  |  |  |  | 0 | 3466.8102 | 3466.8102 | 3466.8102 | 3466.8102 | 3466.8102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
471 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 19982.1617 | 0.2 | 0.3 | 31172.1722 |  |  |  |  | 0 | 4413.4979 | 4413.4979 | 4413.4979 | 4413.4979 | 4413.4979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
472 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 3190.0377 | 0.2 | 0.3 | 4976.4588 |  |  |  |  | 0 | 3830.8155 | 3830.8155 | 3830.8155 | 3830.8155 | 3830.8155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
473 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 28299.6399 | 0.2 | 0.3 | 44147.4382 |  |  |  |  | 0 | 4911.1238 | 4911.1238 | 4911.1238 | 4911.1238 | 4911.1238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
474 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 29101.1305 | 0.2 | 0.3 | 45397.7636 |  |  |  |  | 0 | 9159.2269 | 9159.2269 | 9159.2269 | 9159.2269 | 9159.2269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
475 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 29406.0563 | 0.2 | 0.3 | 45873.4478 |  |  |  |  | 0 | 4716.5142 | 4716.5142 | 4716.5142 | 4716.5142 | 4716.5142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
476 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 30853.5423 | 0.2 | 0.3 | 48131.526 |  |  |  |  | 0 | 4631.0255 | 4631.0255 | 4631.0255 | 4631.0255 | 4631.0255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
477 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 119.0006 | 0.2 | 0.3 | 185.6409 |  |  |  |  | 0 | 9837.3041 | 9837.3041 | 9837.3041 | 9837.3041 | 9837.3041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
478 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 17490.9335 | 0.2 | 0.3 | 27285.8562 |  |  |  |  | 0 | 5672.0377 | 5672.0377 | 5672.0377 | 5672.0377 | 5672.0377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
479 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 18720.0908 | 0.2 | 0.3 | 29203.3416 |  |  |  |  | 0 | 5718.0277 | 5718.0277 | 5718.0277 | 5718.0277 | 5718.0277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
480 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 38044.9098 | 0.2 | 0.3 | 59350.0593 |  |  |  |  | 0 | 8083.9777 | 8083.9777 | 8083.9777 | 8083.9777 | 8083.9777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
481 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 22269.6527 | 0.2 | 0.3 | 34740.6582 |  |  |  |  | 0 | 8486.6979 | 8486.6979 | 8486.6979 | 8486.6979 | 8486.6979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
482 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 28823.3114 | 0.2 | 0.3 | 44964.3658 |  |  |  |  | 0 | 596.0194 | 596.0194 | 596.0194 | 596.0194 | 596.0194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
483 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 18385.4768 | 0.2 | 0.3 | 28681.3438 |  |  |  |  | 0 | 6574.0067 | 6574.0067 | 6574.0067 | 6574.0067 | 6574.0067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
484 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 25048.754 | 0.2 | 0.3 | 39076.0562 |  |  |  |  | 0 | 9872.3497 | 9872.3497 | 9872.3497 | 9872.3497 | 9872.3497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
485 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 7243.5525 | 0.2 | 0.3 | 11299.942 |  |  |  |  | 0 | 5490.5186 | 5490.5186 | 5490.5186 | 5490.5186 | 5490.5186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
486 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 19136.4364 | 0.2 | 0.3 | 29852.8408 |  |  |  |  | 0 | 5302.7485 | 5302.7485 | 5302.7485 | 5302.7485 | 5302.7485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
487 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 28966.0793 | 0.2 | 0.3 | 45187.0837 |  |  |  |  | 0 | 6051.0068 | 6051.0068 | 6051.0068 | 6051.0068 | 6051.0068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
488 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 30507.4353 | 0.2 | 0.3 | 47591.5991 |  |  |  |  | 0 | 6480.2469 | 6480.2469 | 6480.2469 | 6480.2469 | 6480.2469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
489 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 22151.9043 | 0.2 | 0.3 | 34556.9707 |  |  |  |  | 0 | 5348.6918 | 5348.6918 | 5348.6918 | 5348.6918 | 5348.6918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17221.4015 | 0.2 | 0.3 | 26865.3864 |  |  |  |  | 0 | 4219.4936 | 4219.4936 | 4219.4936 | 4219.4936 | 4219.4936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
491 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 17006.5939 | 0.2 | 0.3 | 26530.2865 |  |  |  |  | 0 | 5834.1074 | 5834.1074 | 5834.1074 | 5834.1074 | 5834.1074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
492 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 18896.1719 | 0.2 | 0.3 | 29478.0281 |  |  |  |  | 0 | 5187.1258 | 5187.1258 | 5187.1258 | 5187.1258 | 5187.1258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
493 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 18040.7967 | 0.2 | 0.3 | 28143.6429 |  |  |  |  | 0 | 6890.3483 | 6890.3483 | 6890.3483 | 6890.3483 | 6890.3483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
494 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 16792.6848 | 0.2 | 0.3 | 26196.5883 |  |  |  |  | 0 | 5231.3049 | 5231.3049 | 5231.3049 | 5231.3049 | 5231.3049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
495 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 7256.5427 | 0.2 | 0.3 | 11320.2066 |  |  |  |  | 0 | 9631.7731 | 9631.7731 | 9631.7731 | 9631.7731 | 9631.7731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
496 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 7139.6423 | 0.2 | 0.3 | 11137.8419 |  |  |  |  | 0 | 3099.0785 | 3099.0785 | 3099.0785 | 3099.0785 | 3099.0785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
497 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 16789.0749 | 0.2 | 0.3 | 26190.9569 |  |  |  |  | 0 | 2259.7193 | 2259.7193 | 2259.7193 | 2259.7193 | 2259.7193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
498 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 1679.7695 | 0.2 | 0.3 | 2620.4404 |  |  |  |  | 0 | 77.2444 | 77.2444 | 77.2444 | 77.2444 | 77.2444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
499 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 7037.9663 | 0.2 | 0.3 | 10979.2274 |  |  |  |  | 0 | 5078.9164 | 5078.9164 | 5078.9164 | 5078.9164 | 5078.9164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 32310.8389 | 0.2 | 0.3 | 50404.9087 |  |  |  |  | 0 | 174.7616 | 174.7616 | 174.7616 | 174.7616 | 174.7616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
501 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 16815.025 | 0.2 | 0.3 | 26231.439 |  |  |  |  | 0 | 5284.4632 | 5284.4632 | 5284.4632 | 5284.4632 | 5284.4632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
502 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 30983.3943 | 0.2 | 0.3 | 48334.0952 |  |  |  |  | 0 | 12977.085 | 12977.085 | 12977.085 | 12977.085 | 12977.085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
503 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 23201.2732 | 0.2 | 0.3 | 36193.9862 |  |  |  |  | 0 | 9803.1993 | 9803.1993 | 9803.1993 | 9803.1993 | 9803.1993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
504 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 23746.2558 | 0.2 | 0.3 | 37044.159 |  |  |  |  | 0 | 7716.2305 | 7716.2305 | 7716.2305 | 7716.2305 | 7716.2305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
505 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 30879.362 | 0.2 | 0.3 | 48171.8047 |  |  |  |  | 0 | 9001.0284 | 9001.0284 | 9001.0284 | 9001.0284 | 9001.0284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
506 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 43691.3144 | 0.2 | 0.3 | 68158.4505 |  |  |  |  | 0 | 9779.2621 | 9779.2621 | 9779.2621 | 9779.2621 | 9779.2621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
507 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16693.3443 | 0.2 | 0.3 | 26041.6171 |  |  |  |  | 0 | 9782.4055 | 9782.4055 | 9782.4055 | 9782.4055 | 9782.4055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
508 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16693.6393 | 0.2 | 0.3 | 26042.0774 |  |  |  |  | 0 | 9293.0651 | 9293.0651 | 9293.0651 | 9293.0651 | 9293.0651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
509 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 16813.7537 | 0.2 | 0.3 | 26229.4558 |  |  |  |  | 0 | 5807.5846 | 5807.5846 | 5807.5846 | 5807.5846 | 5807.5846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
510 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 16760.5457 | 0.2 | 0.3 | 26146.4513 |  |  |  |  | 0 | 9908.9463 | 9908.9463 | 9908.9463 | 9908.9463 | 9908.9463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
511 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 17612.6679 | 0.2 | 0.3 | 27475.7619 |  |  |  |  | 0 | 6119.7227 | 6119.7227 | 6119.7227 | 6119.7227 | 6119.7227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
512 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 12788.5746 | 0.2 | 0.3 | 19950.1764 |  |  |  |  | 0 | 10084.5029 | 10084.5029 | 10084.5029 | 10084.5029 | 10084.5029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
513 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 20.6351 | 0.2 | 0.3 | 32.1908 |  |  |  |  | 0 | 8489.5294 | 8489.5294 | 8489.5294 | 8489.5294 | 8489.5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
514 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 17807.7965 | 0.2 | 0.3 | 27780.1626 |  |  |  |  | 0 | 1688.1671 | 1688.1671 | 1688.1671 | 1688.1671 | 1688.1671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
515 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 18145.3509 | 0.2 | 0.3 | 28306.7475 |  |  |  |  | 0 | 5160.4812 | 5160.4812 | 5160.4812 | 5160.4812 | 5160.4812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
516 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 32464.4242 | 0.2 | 0.3 | 50644.5018 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
517 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 22899.5822 | 0.2 | 0.3 | 35723.3482 |  |  |  |  | 0 | 5178.9683 | 5178.9683 | 5178.9683 | 5178.9683 | 5178.9683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
518 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 21405.9547 | 0.2 | 0.3 | 33393.2893 |  |  |  |  | 0 | 9179.7874 | 9179.7874 | 9179.7874 | 9179.7874 | 9179.7874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
519 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16269.3857 | 0.2 | 0.3 | 25380.2417 |  |  |  |  | 0 | 5203.4483 | 5203.4483 | 5203.4483 | 5203.4483 | 5203.4483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
520 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16816.3379 | 0.2 | 0.3 | 26233.4872 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
521 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 12884.2455 | 0.2 | 0.3 | 20099.423 |  |  |  |  | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
522 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 6103.3669 | 0.2 | 0.3 | 9521.2524 |  |  |  |  | 0 | 5784.2748 | 5784.2748 | 5784.2748 | 5784.2748 | 5784.2748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
523 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 16689.177 | 0.2 | 0.3 | 26035.1161 |  |  |  |  | 0 | 4436.7894 | 4436.7894 | 4436.7894 | 4436.7894 | 4436.7894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
524 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 11132.6149 | 0.2 | 0.3 | 17366.8793 |  |  |  |  | 0 | 5211.9357 | 5211.9357 | 5211.9357 | 5211.9357 | 5211.9357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
525 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 12391.1506 | 0.2 | 0.3 | 19330.1949 |  |  |  |  | 0 | 5211.1711 | 5211.1711 | 5211.1711 | 5211.1711 | 5211.1711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
526 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 16871.4808 | 0.2 | 0.3 | 26319.51 |  |  |  |  | 0 | 8698.9966 | 8698.9966 | 8698.9966 | 8698.9966 | 8698.9966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
527 | WESTON | 70319 | Private | 2036 | 5 | Swales | 66.6667 | 19724.8337 | 0.2 | 0.3 | 30770.7406 |  |  |  |  | 0 | 4317.3678 | 4317.3678 | 4317.3678 | 4317.3678 | 4317.3678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
528 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 22772.3577 | 0.2 | 0.3 | 35524.8781 |  |  |  |  | 0 | 5124.1269 | 5124.1269 | 5124.1269 | 5124.1269 | 5124.1269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
529 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 39746.7564 | 0.2 | 0.3 | 62004.94 |  |  |  |  | 0 | 2489.8165 | 2489.8165 | 2489.8165 | 2489.8165 | 2489.8165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
530 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 20303.0147 | 0.2 | 0.3 | 31672.703 |  |  |  |  | 0 | 5202.8895 | 5202.8895 | 5202.8895 | 5202.8895 | 5202.8895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
531 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 3830.5079 | 0.2 | 0.3 | 5975.5923 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
532 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 20471.9501 | 0.2 | 0.3 | 31936.2422 |  |  |  |  | 0 | 5846.4226 | 5846.4226 | 5846.4226 | 5846.4226 | 5846.4226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
533 | WESTON | 70327 | Public | 2036 | 5 | Swales | 66.6667 | 22607.3793 | 0.2 | 0.3 | 35267.5117 |  |  |  |  | 0 | 9001.1298 | 9001.1298 | 9001.1298 | 9001.1298 | 9001.1298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
534 | WESTON | 70327 | Public | 2036 | 5 | Swales | 66.6667 | 20502.1309 | 0.2 | 0.3 | 31983.3243 |  |  |  |  | 0 | 5203.5739 | 5203.5739 | 5203.5739 | 5203.5739 | 5203.5739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
535 | WESTON | 70327 | Public | 2036 | 5 | Swales | 66.6667 | 24469.5095 | 0.2 | 0.3 | 38172.4349 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
536 | WESTON | 70327 | Public | 2036 | 5 | Swales | 66.6667 | 27543.6812 | 0.2 | 0.3 | 42968.1427 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
537 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 13783.9035 | 0.2 | 0.3 | 21502.8895 |  |  |  |  | 0 | 5203.8832 | 5203.8832 | 5203.8832 | 5203.8832 | 5203.8832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
538 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 28708.7745 | 0.2 | 0.3 | 44785.6882 |  |  |  |  | 0 | 5406.3358 | 5406.3358 | 5406.3358 | 5406.3358 | 5406.3358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
539 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 15083.2078 | 0.2 | 0.3 | 23529.8042 |  |  |  |  | 0 | 5206.4894 | 5206.4894 | 5206.4894 | 5206.4894 | 5206.4894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 32984.8491 | 0.2 | 0.3 | 51456.3646 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
541 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 16986.7966 | 0.2 | 0.3 | 26499.4027 |  |  |  |  | 0 | 5682.3977 | 5682.3977 | 5682.3977 | 5682.3977 | 5682.3977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
542 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 16675.4617 | 0.2 | 0.3 | 26013.7202 |  |  |  |  | 0 | 5200.1135 | 5200.1135 | 5200.1135 | 5200.1135 | 5200.1135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
543 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 17255.6655 | 0.2 | 0.3 | 26918.8381 |  |  |  |  | 0 | 5202.7092 | 5202.7092 | 5202.7092 | 5202.7092 | 5202.7092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
544 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 35009.3817 | 0.2 | 0.3 | 54614.6355 |  |  |  |  | 0 | 2600.672 | 2600.672 | 2600.672 | 2600.672 | 2600.672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
545 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 4475.9525 | 0.2 | 0.3 | 6982.4858 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
546 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17283.3733 | 0.2 | 0.3 | 26962.0624 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
547 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 11295.9293 | 0.2 | 0.3 | 17621.6498 |  |  |  |  | 0 | 8416.8487 | 8416.8487 | 8416.8487 | 8416.8487 | 8416.8487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
548 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 10860.5204 | 0.2 | 0.3 | 16942.4118 |  |  |  |  | 0 | 43.4309 | 43.4309 | 43.4309 | 43.4309 | 43.4309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
549 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 21647.1091 | 0.2 | 0.3 | 33769.4902 |  |  |  |  | 0 | 3141.1847 | 3141.1847 | 3141.1847 | 3141.1847 | 3141.1847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
550 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 16802.9443 | 0.2 | 0.3 | 26212.5932 |  |  |  |  | 0 | 8687.9355 | 8687.9355 | 8687.9355 | 8687.9355 | 8687.9355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
551 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 21035.6057 | 0.2 | 0.3 | 32815.5448 |  |  |  |  | 0 | 6103.3334 | 6103.3334 | 6103.3334 | 6103.3334 | 6103.3334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
552 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 19806.9032 | 0.2 | 0.3 | 30898.769 |  |  |  |  | 0 | 7370.3387 | 7370.3387 | 7370.3387 | 7370.3387 | 7370.3387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
553 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 26987.5459 | 0.2 | 0.3 | 42100.5717 |  |  |  |  | 0 | 8964.7153 | 8964.7153 | 8964.7153 | 8964.7153 | 8964.7153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
554 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 34555.0604 | 0.2 | 0.3 | 53905.8942 |  |  |  |  | 0 | 8057.3625 | 8057.3625 | 8057.3625 | 8057.3625 | 8057.3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
555 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 14352.6723 | 0.2 | 0.3 | 22390.1687 |  |  |  |  | 0 | 9043.8363 | 9043.8363 | 9043.8363 | 9043.8363 | 9043.8363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
556 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 4587.4433 | 0.2 | 0.3 | 7156.4115 |  |  |  |  | 0 | 1504.3111 | 1504.3111 | 1504.3111 | 1504.3111 | 1504.3111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
557 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 2654.4589 | 0.2 | 0.3 | 4140.9558 |  |  |  |  | 0 | 3395.6007 | 3395.6007 | 3395.6007 | 3395.6007 | 3395.6007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
558 | WESTON | 70320 | Private | 2036 | 5 | Swales | 66.6667 | 1257.5839 | 0.2 | 0.3 | 1961.8308 |  |  |  |  | 0 | 8626.7178 | 8626.7178 | 8626.7178 | 8626.7178 | 8626.7178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
559 | WESTON | 70327 | Private | 2036 | 5 | Swales | 66.6667 | 18622.2065 | 0.2 | 0.3 | 29050.6421 |  |  |  |  | 0 | 7845.3574 | 7845.3574 | 7845.3574 | 7845.3574 | 7845.3574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
560 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 17883.5478 | 0.2 | 0.3 | 27898.3346 |  |  |  |  | 0 | 5508.2276 | 5508.2276 | 5508.2276 | 5508.2276 | 5508.2276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
561 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 31051.9697 | 0.2 | 0.3 | 48441.0728 |  |  |  |  | 0 | 5335.7244 | 5335.7244 | 5335.7244 | 5335.7244 | 5335.7244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
562 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 11984.9389 | 0.2 | 0.3 | 18696.5047 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
563 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 21991.2569 | 0.2 | 0.3 | 34306.3608 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
564 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 25952.0328 | 0.2 | 0.3 | 40485.1712 |  |  |  |  | 0 | 7147.9356 | 7147.9356 | 7147.9356 | 7147.9356 | 7147.9356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
565 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 11258.3454 | 0.2 | 0.3 | 17563.0188 |  |  |  |  | 0 | 5226.3147 | 5226.3147 | 5226.3147 | 5226.3147 | 5226.3147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
566 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 33509.3924 | 0.2 | 0.3 | 52274.6521 |  |  |  |  | 0 | 5496.1984 | 5496.1984 | 5496.1984 | 5496.1984 | 5496.1984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
567 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 11778.5912 | 0.2 | 0.3 | 18374.6023 | [5 empty] | 9082.5568 | 9082.5568 | 9082.5568 | 9082.5568 | 9082.5568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
568 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 23326.739 | 0.2 | 0.3 | 36389.7128 | [5 empty] | 7444.5214 | 7444.5214 | 7444.5214 | 7444.5214 | 7444.5214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
569 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 6647.2757 | 0.2 | 0.3 | 10369.75 |  |  |  |  | 0 | 5204.1436 | 5204.1436 | 5204.1436 | 5204.1436 | 5204.1436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
570 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 21931.8057 | 0.2 | 0.3 | 34213.6169 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
571 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 23274.2939 | 0.2 | 0.3 | 36307.8985 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
572 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 18239.3005 | 0.2 | 0.3 | 28453.3088 |  |  |  |  | 0 | 9329.9967 | 9329.9967 | 9329.9967 | 9329.9967 | 9329.9967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
573 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 19119.2965 | 0.2 | 0.3 | 29826.1025 |  |  |  |  | 0 | 10408.5738 | 10408.5738 | 10408.5738 | 10408.5738 | 10408.5738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
574 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17184.8136 | 0.2 | 0.3 | 26808.3092 |  |  |  |  | 0 | 11764.5025 | 11764.5025 | 11764.5025 | 11764.5025 | 11764.5025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
575 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 23684.4057 | 0.2 | 0.3 | 36947.6729 |  |  |  |  | 0 | 11585.8879 | 11585.8879 | 11585.8879 | 11585.8879 | 11585.8879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
576 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 5414.3409 | 0.2 | 0.3 | 8446.3719 |  |  |  |  | 0 | 7246.5983 | 7246.5983 | 7246.5983 | 7246.5983 | 7246.5983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
577 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 24665.3694 | 0.2 | 0.3 | 38477.9763 |  |  |  |  | 0 | 5202.7339 | 5202.7339 | 5202.7339 | 5202.7339 | 5202.7339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
578 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 13539.5947 | 0.2 | 0.3 | 21121.7677 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
579 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 16769.8375 | 0.2 | 0.3 | 26160.9466 |  |  |  |  | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
580 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 16698.2691 | 0.2 | 0.3 | 26049.2997 |  |  |  |  | 0 | 7759.3198 | 7759.3198 | 7759.3198 | 7759.3198 | 7759.3198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
581 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 5717.4631 | 0.2 | 0.3 | 8919.2424 |  |  |  |  | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
582 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 18351.871 | 0.2 | 0.3 | 28628.9188 |  |  |  |  | 0 | 5261.1267 | 5261.1267 | 5261.1267 | 5261.1267 | 5261.1267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
583 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 | [5 empty] | 7055.9034 | 7055.9034 | 7055.9034 | 7055.9034 | 7055.9034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
584 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 696.4605 | 0.2 | 0.3 | 1086.4784 |  |  |  |  | 0 | 7083.7274 | 7083.7274 | 7083.7274 | 7083.7274 | 7083.7274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
585 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 23621.7106 | 0.2 | 0.3 | 36849.8685 |  |  |  |  | 0 | 5203.6532 | 5203.6532 | 5203.6532 | 5203.6532 | 5203.6532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
586 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 1105.8881 | 0.2 | 0.3 | 1725.1854 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
587 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 16842.0089 | 0.2 | 0.3 | 26273.5339 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
588 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16687.8013 | 0.2 | 0.3 | 26032.97 |  |  |  |  | 0 | 9785.7798 | 9785.7798 | 9785.7798 | 9785.7798 | 9785.7798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
589 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 6393.3225 | 0.2 | 0.3 | 9973.583 |  |  |  |  | 0 | 5206.4621 | 5206.4621 | 5206.4621 | 5206.4621 | 5206.4621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
590 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 16716.0801 | 0.2 | 0.3 | 26077.0849 |  |  |  |  | 0 | 5206.5474 | 5206.5474 | 5206.5474 | 5206.5474 | 5206.5474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
591 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 590.7262 | 0.2 | 0.3 | 921.5329 |  |  |  |  | 0 | 6450.599 | 6450.599 | 6450.599 | 6450.599 | 6450.599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
592 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 18160.9399 | 0.2 | 0.3 | 28331.0662 |  |  |  |  | 0 | 6994.8968 | 6994.8968 | 6994.8968 | 6994.8968 | 6994.8968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
593 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 7156.2007 | 0.2 | 0.3 | 11163.6731 |  |  |  |  | 0 | 5204.0127 | 5204.0127 | 5204.0127 | 5204.0127 | 5204.0127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
594 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 16684.0811 | 0.2 | 0.3 | 26027.1665 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
595 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 13292.4411 | 0.2 | 0.3 | 20736.2082 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
596 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 14565.9857 | 0.2 | 0.3 | 22722.9377 |  |  |  |  | 0 | 7513.1509 | 7513.1509 | 7513.1509 | 7513.1509 | 7513.1509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
597 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 5204.0859 | 5204.0859 | 5204.0859 | 5204.0859 | 5204.0859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
598 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 5203.9775 | 5203.9775 | 5203.9775 | 5203.9775 | 5203.9775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
599 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 11631.6075 | 0.2 | 0.3 | 18145.3076 |  |  |  |  | 0 | 14344.0812 | 14344.0812 | 14344.0812 | 14344.0812 | 14344.0812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
600 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 19012.6859 | 0.2 | 0.3 | 29659.7901 |  |  |  |  | 0 | 9772.4545 | 9772.4545 | 9772.4545 | 9772.4545 | 9772.4545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
601 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 16782.2359 | 0.2 | 0.3 | 26180.2881 |  |  |  |  | 0 | 5197.4144 | 5197.4144 | 5197.4144 | 5197.4144 | 5197.4144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
602 | WESTON | 70321 | Public | 2036 | 5 | Swales | 66.6667 | 13663.2112 | 0.2 | 0.3 | 21314.6095 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
603 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 17682.6427 | 0.2 | 0.3 | 27584.9226 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
604 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 16741.7353 | 0.2 | 0.3 | 26117.1071 |  |  |  |  | 0 | 5202.612 | 5202.612 | 5202.612 | 5202.612 | 5202.612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
605 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 16770.1169 | 0.2 | 0.3 | 26161.3823 |  |  |  |  | 0 | 6300.1587 | 6300.1587 | 6300.1587 | 6300.1587 | 6300.1587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
606 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 16889.8007 | 0.2 | 0.3 | 26348.089 |  |  |  |  | 0 | 4788.5229 | 4788.5229 | 4788.5229 | 4788.5229 | 4788.5229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
607 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 16738.0226 | 0.2 | 0.3 | 26111.3153 |  |  |  |  | 0 | 5204.1733 | 5204.1733 | 5204.1733 | 5204.1733 | 5204.1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
608 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 17105.2086 | 0.2 | 0.3 | 26684.1254 |  |  |  |  | 0 | 7030.3697 | 7030.3697 | 7030.3697 | 7030.3697 | 7030.3697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
609 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 19692.2964 | 0.2 | 0.3 | 30719.9824 |  |  |  |  | 0 | 9782.2032 | 9782.2032 | 9782.2032 | 9782.2032 | 9782.2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
610 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 29223.1823 | 0.2 | 0.3 | 45588.1644 |  |  |  |  | 0 | 5205.5238 | 5205.5238 | 5205.5238 | 5205.5238 | 5205.5238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
611 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 6744.5595 | 0.2 | 0.3 | 10521.5129 | [5 empty] | 6751.0539 | 6751.0539 | 6751.0539 | 6751.0539 | 6751.0539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
612 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 24984.4333 | 0.2 | 0.3 | 38975.716 | [5 empty] | 5203.7009 | 5203.7009 | 5203.7009 | 5203.7009 | 5203.7009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
613 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 2246.6369 | 0.2 | 0.3 | 3504.7535 |  |  |  |  | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
614 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 502.2331 | 0.2 | 0.3 | 783.4837 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
615 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 16260.3905 | 0.2 | 0.3 | 25366.2092 |  |  |  |  | 0 | 5203.7158 | 5203.7158 | 5203.7158 | 5203.7158 | 5203.7158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
616 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 2046.7143 | 0.2 | 0.3 | 3192.8743 |  |  |  |  | 0 | 6880.6569 | 6880.6569 | 6880.6569 | 6880.6569 | 6880.6569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
617 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16333.8655 | 0.2 | 0.3 | 25480.8302 |  |  |  |  | 0 | 3011.3773 | 3011.3773 | 3011.3773 | 3011.3773 | 3011.3773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
618 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 11725.7096 | 0.2 | 0.3 | 18292.107 |  |  |  |  | 0 | 3809.8868 | 3809.8868 | 3809.8868 | 3809.8868 | 3809.8868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
619 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 593.1483 | 0.2 | 0.3 | 925.3114 |  |  |  |  | 0 | 5748.9243 | 5748.9243 | 5748.9243 | 5748.9243 | 5748.9243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
620 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 21982.4583 | 0.2 | 0.3 | 34292.6349 |  |  |  |  | 0 | 2876.8332 | 2876.8332 | 2876.8332 | 2876.8332 | 2876.8332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
621 | WESTON | 70329 | Private | 2036 | 5 | Swales | 66.6667 | 2574.8702 | 0.2 | 0.3 | 4016.7975 |  |  |  |  | 0 | 9489.5377 | 9489.5377 | 9489.5377 | 9489.5377 | 9489.5377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
622 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 11615.5787 | 0.2 | 0.3 | 18120.3028 |  |  |  |  | 0 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
623 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17224.1774 | 0.2 | 0.3 | 26869.7167 |  |  |  |  | 0 | 6569.1082 | 6569.1082 | 6569.1082 | 6569.1082 | 6569.1082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
624 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 13257.4458 | 0.2 | 0.3 | 20681.6154 |  |  |  |  | 0 | 5203.5741 | 5203.5741 | 5203.5741 | 5203.5741 | 5203.5741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
625 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 30106.8307 | 0.2 | 0.3 | 46966.6558 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
626 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 15781.3032 | 0.2 | 0.3 | 24618.833 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
627 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 1797.2544 | 0.2 | 0.3 | 2803.7169 |  |  |  |  | 0 | 5203.7118 | 5203.7118 | 5203.7118 | 5203.7118 | 5203.7118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
628 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 4488.9915 | 0.2 | 0.3 | 7002.8267 |  |  |  |  | 0 | 6612.3063 | 6612.3063 | 6612.3063 | 6612.3063 | 6612.3063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
629 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 28905.4021 | 0.2 | 0.3 | 45092.4273 |  |  |  |  | 0 | 2951.0474 | 2951.0474 | 2951.0474 | 2951.0474 | 2951.0474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
630 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 23155.0483 | 0.2 | 0.3 | 36121.8754 |  |  |  |  | 0 | 3946.8662 | 3946.8662 | 3946.8662 | 3946.8662 | 3946.8662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
631 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 21887.8825 | 0.2 | 0.3 | 34145.0966 |  |  |  |  | 0 | 5502.4681 | 5502.4681 | 5502.4681 | 5502.4681 | 5502.4681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
632 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 29832.5906 | 0.2 | 0.3 | 46538.8413 |  |  |  |  | 0 | 2530.5664 | 2530.5664 | 2530.5664 | 2530.5664 | 2530.5664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
633 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 3937.4641 | 0.2 | 0.3 | 6142.4439 |  |  |  |  | 0 | 7440.0638 | 7440.0638 | 7440.0638 | 7440.0638 | 7440.0638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
634 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 23514.9817 | 0.2 | 0.3 | 36683.3714 |  |  |  |  | 0 | 3141.7405 | 3141.7405 | 3141.7405 | 3141.7405 | 3141.7405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
635 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 16860.3737 | 0.2 | 0.3 | 26302.183 |  |  |  |  | 0 | 5201.0562 | 5201.0562 | 5201.0562 | 5201.0562 | 5201.0562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
636 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 17079.1397 | 0.2 | 0.3 | 26643.4579 |  |  |  |  | 0 | 10142.5196 | 10142.5196 | 10142.5196 | 10142.5196 | 10142.5196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
637 | WESTON | 70321 | Public | 2036 | 5 | Swales | 66.6667 | 7648.7825 | 0.2 | 0.3 | 11932.1008 |  |  |  |  | 0 | 9824.0543 | 9824.0543 | 9824.0543 | 9824.0543 | 9824.0543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
638 | WESTON | 70321 | Public | 2036 | 5 | Swales | 66.6667 | 9279.2808 | 0.2 | 0.3 | 14475.678 |  |  |  |  | 0 | 4860.1613 | 4860.1613 | 4860.1613 | 4860.1613 | 4860.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
639 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 23148.0712 | 0.2 | 0.3 | 36110.9911 |  |  |  |  | 0 | 2650.6513 | 2650.6513 | 2650.6513 | 2650.6513 | 2650.6513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
640 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 5629.0719 | 5629.0719 | 5629.0719 | 5629.0719 | 5629.0719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
641 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 1380.4629 | 0.2 | 0.3 | 2153.5222 |  |  |  |  | 0 | 5180.8077 | 5180.8077 | 5180.8077 | 5180.8077 | 5180.8077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
642 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 16243.983 | 0.2 | 0.3 | 25340.6135 |  |  |  |  | 0 | 7867.283 | 7867.283 | 7867.283 | 7867.283 | 7867.283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
643 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 16702.201 | 0.2 | 0.3 | 26055.4336 | [5 empty] | 4256.0204 | 4256.0204 | 4256.0204 | 4256.0204 | 4256.0204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
644 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 14061.1639 | 0.2 | 0.3 | 21935.4157 | [5 empty] | 5202.8028 | 5202.8028 | 5202.8028 | 5202.8028 | 5202.8028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
645 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 13633.3125 | 0.2 | 0.3 | 21267.9676 | [5 empty] | 5444.6891 | 5444.6891 | 5444.6891 | 5444.6891 | 5444.6891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
646 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 19970.8607 | 0.2 | 0.3 | 31154.5426 |  |  |  |  | 0 | 6881.2961 | 6881.2961 | 6881.2961 | 6881.2961 | 6881.2961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
647 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 18569.4699 | 0.2 | 0.3 | 28968.3731 |  |  |  |  | 0 | 5203.3562 | 5203.3562 | 5203.3562 | 5203.3562 | 5203.3562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
648 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 11910.9304 | 0.2 | 0.3 | 18581.0514 |  |  |  |  | 0 | 5203.4617 | 5203.4617 | 5203.4617 | 5203.4617 | 5203.4617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
649 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 10075.1493 | 0.2 | 0.3 | 15717.233 |  |  |  |  | 0 | 5966.9815 | 5966.9815 | 5966.9815 | 5966.9815 | 5966.9815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
650 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16709.4178 | 0.2 | 0.3 | 26066.6918 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
651 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 22595.9358 | 0.2 | 0.3 | 35249.6598 |  |  |  |  | 0 | 5206.2062 | 5206.2062 | 5206.2062 | 5206.2062 | 5206.2062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
652 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 13588.0921 | 0.2 | 0.3 | 21197.4237 |  |  |  |  | 0 | 9751.9456 | 9751.9456 | 9751.9456 | 9751.9456 | 9751.9456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
653 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 10600.4653 | 0.2 | 0.3 | 16536.7258 |  |  |  |  | 0 | 3009.3794 | 3009.3794 | 3009.3794 | 3009.3794 | 3009.3794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
654 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 25470.3698 | 0.2 | 0.3 | 39733.7769 |  |  |  |  | 0 | 5174.5489 | 5174.5489 | 5174.5489 | 5174.5489 | 5174.5489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
655 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 20199.3544 | 0.2 | 0.3 | 31510.9929 |  |  |  |  | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
656 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 9629.6508 | 0.2 | 0.3 | 15022.2552 |  |  |  |  | 0 | 5568.7975 | 5568.7975 | 5568.7975 | 5568.7975 | 5568.7975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
657 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 40763.9085 | 0.2 | 0.3 | 63591.6972 |  |  |  |  | 0 | 5734.853 | 5734.853 | 5734.853 | 5734.853 | 5734.853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
658 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 1274.1255 | 0.2 | 0.3 | 1987.6358 |  |  |  |  | 0 | 5303.2913 | 5303.2913 | 5303.2913 | 5303.2913 | 5303.2913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
659 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 15754.5872 | 0.2 | 0.3 | 24577.156 |  |  |  |  | 0 | 6751.1832 | 6751.1832 | 6751.1832 | 6751.1832 | 6751.1832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
660 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 17947.4449 | 0.2 | 0.3 | 27998.014 |  |  |  |  | 0 | 5204.4792 | 5204.4792 | 5204.4792 | 5204.4792 | 5204.4792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
661 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 4711.945 | 0.2 | 0.3 | 7350.6342 |  |  |  |  | 0 | 5204.7345 | 5204.7345 | 5204.7345 | 5204.7345 | 5204.7345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
662 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 28925.6417 | 0.2 | 0.3 | 45124.001 |  |  |  |  | 0 | 6085.4028 | 6085.4028 | 6085.4028 | 6085.4028 | 6085.4028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
663 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 43562.3638 | 0.2 | 0.3 | 67957.2875 |  |  |  |  | 0 | 9987.4514 | 9987.4514 | 9987.4514 | 9987.4514 | 9987.4514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
664 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 15696.8429 | 0.2 | 0.3 | 24487.075 |  |  |  |  | 0 | 9787.2474 | 9787.2474 | 9787.2474 | 9787.2474 | 9787.2474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
665 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 20593.1311 | 0.2 | 0.3 | 32125.2846 |  |  |  |  | 0 | 9780.8319 | 9780.8319 | 9780.8319 | 9780.8319 | 9780.8319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
666 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 121.4085 | 0.2 | 0.3 | 189.3973 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
667 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 25966.2368 | 0.2 | 0.3 | 40507.3294 |  |  |  |  | 0 | 9780.4121 | 9780.4121 | 9780.4121 | 9780.4121 | 9780.4121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
668 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 18388.7684 | 0.2 | 0.3 | 28686.4787 |  |  |  |  | 0 | 5204.3471 | 5204.3471 | 5204.3471 | 5204.3471 | 5204.3471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
669 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 17989.4266 | 0.2 | 0.3 | 28063.5055 |  |  |  |  | 0 | 6504.3162 | 6504.3162 | 6504.3162 | 6504.3162 | 6504.3162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
670 | WESTON | 70321 | Public | 2036 | 5 | Swales | 66.6667 | 16995.986 | 0.2 | 0.3 | 26513.7382 |  |  |  |  | 0 | 9781.8805 | 9781.8805 | 9781.8805 | 9781.8805 | 9781.8805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
671 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 5167.6379 | 0.2 | 0.3 | 8061.5151 |  |  |  |  | 0 | 9793.7783 | 9793.7783 | 9793.7783 | 9793.7783 | 9793.7783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
672 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 19813.2473 | 0.2 | 0.3 | 30908.6658 |  |  |  |  | 0 | 7205.1448 | 7205.1448 | 7205.1448 | 7205.1448 | 7205.1448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
673 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 8613.4319 | 0.2 | 0.3 | 13436.9537 |  |  |  |  | 0 | 5278.5795 | 5278.5795 | 5278.5795 | 5278.5795 | 5278.5795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
674 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 11459.5413 | 0.2 | 0.3 | 17876.8844 | [5 empty] | 5201.8735 | 5201.8735 | 5201.8735 | 5201.8735 | 5201.8735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
675 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 6187.8117 | 0.2 | 0.3 | 9652.9863 | [5 empty] | 5202.9713 | 5202.9713 | 5202.9713 | 5202.9713 | 5202.9713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
676 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 11841.4823 | 0.2 | 0.3 | 18472.7124 | [5 empty] | 5201.6715 | 5201.6715 | 5201.6715 | 5201.6715 | 5201.6715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
677 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16667.3651 | 0.2 | 0.3 | 26001.0895 |  |  |  |  | 0 | 5200.7526 | 5200.7526 | 5200.7526 | 5200.7526 | 5200.7526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
678 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17098.4641 | 0.2 | 0.3 | 26673.604 |  |  |  |  | 0 | 8306.9511 | 8306.9511 | 8306.9511 | 8306.9511 | 8306.9511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
679 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 4123.602 | 0.2 | 0.3 | 6432.8191 |  |  |  |  | 0 | 5205.7797 | 5205.7797 | 5205.7797 | 5205.7797 | 5205.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
680 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 21788.1358 | 0.2 | 0.3 | 33989.4918 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
681 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 18297.1411 | 0.2 | 0.3 | 28543.5401 |  |  |  |  | 0 | 9781.6205 | 9781.6205 | 9781.6205 | 9781.6205 | 9781.6205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
682 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 12476.9113 | 0.2 | 0.3 | 19463.9816 |  |  |  |  | 0 | 6503.3727 | 6503.3727 | 6503.3727 | 6503.3727 | 6503.3727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
683 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 7137.5007 | 0.2 | 0.3 | 11134.501 |  |  |  |  | 0 | 5204.6727 | 5204.6727 | 5204.6727 | 5204.6727 | 5204.6727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
684 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17041.4316 | 0.2 | 0.3 | 26584.6333 |  |  |  |  | 0 | 5204.9064 | 5204.9064 | 5204.9064 | 5204.9064 | 5204.9064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
685 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 14096.2276 | 0.2 | 0.3 | 21990.1151 |  |  |  |  | 0 | 6485.4628 | 6485.4628 | 6485.4628 | 6485.4628 | 6485.4628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
686 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 16070.6437 | 0.2 | 0.3 | 25070.2042 |  |  |  |  | 0 | 5200.7405 | 5200.7405 | 5200.7405 | 5200.7405 | 5200.7405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
687 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 1099.9281 | 0.2 | 0.3 | 1715.8878 |  |  |  |  | 0 | 5201.8764 | 5201.8764 | 5201.8764 | 5201.8764 | 5201.8764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
688 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 12296.8057 | 0.2 | 0.3 | 19183.0168 |  |  |  |  | 0 | 5202.9545 | 5202.9545 | 5202.9545 | 5202.9545 | 5202.9545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
689 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 11210.5169 | 0.2 | 0.3 | 17488.4063 |  |  |  |  | 0 | 5201.668 | 5201.668 | 5201.668 | 5201.668 | 5201.668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
690 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 21438.5897 | 0.2 | 0.3 | 33444.1999 |  |  |  |  | 0 | 5200.858 | 5200.858 | 5200.858 | 5200.858 | 5200.858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
691 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 24432.6406 | 0.2 | 0.3 | 38114.9193 |  |  |  |  | 0 | 8106.5657 | 8106.5657 | 8106.5657 | 8106.5657 | 8106.5657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
692 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 1899.461 | 0.2 | 0.3 | 2963.1592 |  |  |  |  | 0 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
693 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 10502.3174 | 0.2 | 0.3 | 16383.6151 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
694 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 17378.5463 | 0.2 | 0.3 | 27110.5323 |  |  |  |  | 0 | 9781.7267 | 9781.7267 | 9781.7267 | 9781.7267 | 9781.7267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
695 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 38039.7749 | 0.2 | 0.3 | 59342.0488 |  |  |  |  | 0 | 6357.8123 | 6357.8123 | 6357.8123 | 6357.8123 | 6357.8123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
696 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 32494.0503 | 0.2 | 0.3 | 50690.7185 |  |  |  |  | 0 | 5204.4996 | 5204.4996 | 5204.4996 | 5204.4996 | 5204.4996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
697 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 15952.7099 | 0.2 | 0.3 | 24886.2274 |  |  |  |  | 0 | 5204.7231 | 5204.7231 | 5204.7231 | 5204.7231 | 5204.7231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
698 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 19275.2286 | 0.2 | 0.3 | 30069.3566 |  |  |  |  | 0 | 6573.858 | 6573.858 | 6573.858 | 6573.858 | 6573.858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
699 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 1219.0853 | 0.2 | 0.3 | 1901.7731 |  |  |  |  | 0 | 5201.7334 | 5201.7334 | 5201.7334 | 5201.7334 | 5201.7334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
700 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 27658.3314 | 0.2 | 0.3 | 43146.997 |  |  |  |  | 0 | 8.8816 | 8.8816 | 8.8816 | 8.8816 | 8.8816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
701 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 37425.6363 | 0.2 | 0.3 | 58383.9926 |  |  |  |  | 0 | 2132.8423 | 2132.8423 | 2132.8423 | 2132.8423 | 2132.8423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
702 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 19010.5367 | 0.2 | 0.3 | 29656.4373 |  |  |  |  | 0 | 9373.8351 | 9373.8351 | 9373.8351 | 9373.8351 | 9373.8351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
703 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 31560.7273 | 0.2 | 0.3 | 49234.7346 |  |  |  |  | 0 | 9791.2135 | 9791.2135 | 9791.2135 | 9791.2135 | 9791.2135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
704 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 29759.4299 | 0.2 | 0.3 | 46424.7106 |  |  |  |  | 0 | 9780.4147 | 9780.4147 | 9780.4147 | 9780.4147 | 9780.4147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
705 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 28559.6962 | 0.2 | 0.3 | 44553.1261 |  |  |  |  | 0 | 9782.1896 | 9782.1896 | 9782.1896 | 9782.1896 | 9782.1896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
706 | WESTON | 70321 | Public | 2036 | 5 | Swales | 66.6667 | 16838.3233 | 0.2 | 0.3 | 26267.7844 |  |  |  |  | 0 | 6468.9997 | 6468.9997 | 6468.9997 | 6468.9997 | 6468.9997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
707 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 23013.623 | 0.2 | 0.3 | 35901.2519 |  |  |  |  | 0 | 9774.229 | 9774.229 | 9774.229 | 9774.229 | 9774.229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
708 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 8789.6065 | 0.2 | 0.3 | 13711.7861 |  |  |  |  | 0 | 5203.5103 | 5203.5103 | 5203.5103 | 5203.5103 | 5203.5103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
709 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 15764.855 | 0.2 | 0.3 | 24593.1738 |  |  |  |  | 0 | 5203.7596 | 5203.7596 | 5203.7596 | 5203.7596 | 5203.7596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
710 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 6945.56 | 6945.56 | 6945.56 | 6945.56 | 6945.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
711 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 13260.3167 | 0.2 | 0.3 | 20686.094 |  |  |  |  | 0 | 5195.8714 | 5195.8714 | 5195.8714 | 5195.8714 | 5195.8714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
712 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4577 | 0.2 | 0.3 | 26001.2341 |  |  |  |  | 0 | 3071.8894 | 3071.8894 | 3071.8894 | 3071.8894 | 3071.8894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
713 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 13186.3453 | 0.2 | 0.3 | 20570.6987 |  |  |  |  | 0 | 5659.5945 | 5659.5945 | 5659.5945 | 5659.5945 | 5659.5945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
714 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 24038.417 | 0.2 | 0.3 | 37499.9305 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
715 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 31591.6045 | 0.2 | 0.3 | 49282.903 |  |  |  |  | 0 | 5202.2673 | 5202.2673 | 5202.2673 | 5202.2673 | 5202.2673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
716 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 19467.8041 | 0.2 | 0.3 | 30369.7743 |  |  |  |  | 0 | 5201.8716 | 5201.8716 | 5201.8716 | 5201.8716 | 5201.8716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
717 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 14685.0392 | 0.2 | 0.3 | 22908.6612 |  |  |  |  | 0 | 9795.0998 | 9795.0998 | 9795.0998 | 9795.0998 | 9795.0998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
718 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 5398.2916 | 0.2 | 0.3 | 8421.3349 |  |  |  |  | 0 | 5203.6189 | 5203.6189 | 5203.6189 | 5203.6189 | 5203.6189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
719 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 19408.7747 | 0.2 | 0.3 | 30277.6885 |  |  |  |  | 0 | 5203.8011 | 5203.8011 | 5203.8011 | 5203.8011 | 5203.8011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
720 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17836.9769 | 0.2 | 0.3 | 27825.6839 |  |  |  |  | 0 | 6175.9562 | 6175.9562 | 6175.9562 | 6175.9562 | 6175.9562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
721 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 18662.521 | 0.2 | 0.3 | 29113.5328 |  |  |  |  | 0 | 5201.3431 | 5201.3431 | 5201.3431 | 5201.3431 | 5201.3431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
722 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17585.6935 | 0.2 | 0.3 | 27433.6818 |  |  |  |  | 0 | 8331.224 | 8331.224 | 8331.224 | 8331.224 | 8331.224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
723 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 2116.5714 | 0.2 | 0.3 | 3301.8514 |  |  |  |  | 0 | 5750.9292 | 5750.9292 | 5750.9292 | 5750.9292 | 5750.9292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
724 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 18269.0815 | 0.2 | 0.3 | 28499.7671 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
725 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 5158.2187 | 0.2 | 0.3 | 8046.8212 |  |  |  |  | 0 | 5203.0481 | 5203.0481 | 5203.0481 | 5203.0481 | 5203.0481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
726 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 15684.8986 | 0.2 | 0.3 | 24468.4418 |  |  |  |  | 0 | 9780.5539 | 9780.5539 | 9780.5539 | 9780.5539 | 9780.5539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
727 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 395.1628 | 0.2 | 0.3 | 616.454 |  |  |  |  | 0 | 4866.3182 | 4866.3182 | 4866.3182 | 4866.3182 | 4866.3182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
728 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 24693.9413 | 0.2 | 0.3 | 38522.5485 |  |  |  |  | 0 | 5378.8831 | 5378.8831 | 5378.8831 | 5378.8831 | 5378.8831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
729 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 20872.0408 | 0.2 | 0.3 | 32560.3836 |  |  |  |  | 0 | 9606.7782 | 9606.7782 | 9606.7782 | 9606.7782 | 9606.7782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
730 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 9149.1496 | 0.2 | 0.3 | 14272.6734 |  |  |  |  | 0 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
731 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 13564.7915 | 0.2 | 0.3 | 21161.0747 |  |  |  |  | 0 | 9781.2472 | 9781.2472 | 9781.2472 | 9781.2472 | 9781.2472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
732 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 28771.8901 | 0.2 | 0.3 | 44884.1485 |  |  |  |  | 0 | 5203.9702 | 5203.9702 | 5203.9702 | 5203.9702 | 5203.9702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
733 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 22550.7328 | 0.2 | 0.3 | 35179.1432 |  |  |  |  | 0 | 5204.0476 | 5204.0476 | 5204.0476 | 5204.0476 | 5204.0476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
734 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 18759.8373 | 0.2 | 0.3 | 29265.3461 |  |  |  |  | 0 | 9779.7692 | 9779.7692 | 9779.7692 | 9779.7692 | 9779.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
735 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 25846.2068 | 0.2 | 0.3 | 40320.0826 |  |  |  |  | 0 | 8963.17 | 8963.17 | 8963.17 | 8963.17 | 8963.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
736 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 23615.6097 | 0.2 | 0.3 | 36840.3512 |  |  |  |  | 0 | 5880.1683 | 5880.1683 | 5880.1683 | 5880.1683 | 5880.1683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
737 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 15366.9128 | 0.2 | 0.3 | 23972.384 |  |  |  |  | 0 | 5824.2687 | 5824.2687 | 5824.2687 | 5824.2687 | 5824.2687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
738 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 35504.9249 | 0.2 | 0.3 | 55387.6828 |  |  |  |  | 0 | 5210.2154 | 5210.2154 | 5210.2154 | 5210.2154 | 5210.2154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
739 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 16675.3877 | 0.2 | 0.3 | 26013.6048 |  |  |  |  | 0 | 5216.2718 | 5216.2718 | 5216.2718 | 5216.2718 | 5216.2718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
740 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 9793.7419 | 9793.7419 | 9793.7419 | 9793.7419 | 9793.7419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
741 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 16666.9803 | 0.2 | 0.3 | 26000.4892 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
742 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 19228.0967 | 0.2 | 0.3 | 29995.8309 |  |  |  |  | 0 | 5204.9345 | 5204.9345 | 5204.9345 | 5204.9345 | 5204.9345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
743 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 24283.7142 | 0.2 | 0.3 | 37882.5942 |  |  |  |  | 0 | 9780.1808 | 9780.1808 | 9780.1808 | 9780.1808 | 9780.1808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
744 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 14562.5887 | 0.2 | 0.3 | 22717.6383 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
745 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 16728.9927 | 0.2 | 0.3 | 26097.2287 |  |  |  |  | 0 | 9789.535 | 9789.535 | 9789.535 | 9789.535 | 9789.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
746 | WESTON | 70321 | Private | 2036 | 5 | Swales | 66.6667 | 16699.4485 | 0.2 | 0.3 | 26051.1396 |  |  |  |  | 0 | 5205.3399 | 5205.3399 | 5205.3399 | 5205.3399 | 5205.3399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
747 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 25138.9928 | 0.2 | 0.3 | 39216.8288 |  |  |  |  | 0 | 5204.862 | 5204.862 | 5204.862 | 5204.862 | 5204.862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
748 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8787 | 0.2 | 0.3 | 26000.3308 |  |  |  |  | 0 | 6436.5336 | 6436.5336 | 6436.5336 | 6436.5336 | 6436.5336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
749 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16821.429 | 0.2 | 0.3 | 26241.4292 |  |  |  |  | 0 | 5683.6644 | 5683.6644 | 5683.6644 | 5683.6644 | 5683.6644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
750 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 15148.0941 | 0.2 | 0.3 | 23631.0268 |  |  |  |  | 0 | 5205.8576 | 5205.8576 | 5205.8576 | 5205.8576 | 5205.8576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
751 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 13203.1362 | 0.2 | 0.3 | 20596.8925 |  |  |  |  | 0 | 5206.0445 | 5206.0445 | 5206.0445 | 5206.0445 | 5206.0445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
752 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 10364.2743 | 0.2 | 0.3 | 16168.2679 |  |  |  |  | 0 | 9793.9429 | 9793.9429 | 9793.9429 | 9793.9429 | 9793.9429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
753 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 11082.4923 | 0.2 | 0.3 | 17288.6879 |  |  |  |  | 0 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
754 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 1877.9179 | 0.2 | 0.3 | 2929.552 |  |  |  |  | 0 | 5205.3533 | 5205.3533 | 5205.3533 | 5205.3533 | 5205.3533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
755 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17036.2304 | 0.2 | 0.3 | 26576.5194 |  |  |  |  | 0 | 9780.1446 | 9780.1446 | 9780.1446 | 9780.1446 | 9780.1446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
756 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16759.3818 | 0.2 | 0.3 | 26144.6356 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
757 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 20846.8061 | 0.2 | 0.3 | 32521.0176 |  |  |  |  | 0 | 9788.2848 | 9788.2848 | 9788.2848 | 9788.2848 | 9788.2848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
758 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 21441.06 | 0.2 | 0.3 | 33448.0536 |  |  |  |  | 0 | 5204.7148 | 5204.7148 | 5204.7148 | 5204.7148 | 5204.7148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
759 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 3612.5082 | 0.2 | 0.3 | 5635.5128 |  |  |  |  | 0 | 5204.1957 | 5204.1957 | 5204.1957 | 5204.1957 | 5204.1957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
760 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 23600.0117 | 0.2 | 0.3 | 36816.0182 |  |  |  |  | 0 | 9662.419 | 9662.419 | 9662.419 | 9662.419 | 9662.419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
761 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 20476.2085 | 0.2 | 0.3 | 31942.8853 |  |  |  |  | 0 | 5204.3945 | 5204.3945 | 5204.3945 | 5204.3945 | 5204.3945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
762 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 11370.8544 | 0.2 | 0.3 | 17738.5329 |  |  |  |  | 0 | 5205.0513 | 5205.0513 | 5205.0513 | 5205.0513 | 5205.0513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
763 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 15264.945 | 0.2 | 0.3 | 23813.3142 |  |  |  |  | 0 | 9780.9576 | 9780.9576 | 9780.9576 | 9780.9576 | 9780.9576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
764 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 8836.4356 | 0.2 | 0.3 | 13784.8395 |  |  |  |  | 0 | 9780.5496 | 9780.5496 | 9780.5496 | 9780.5496 | 9780.5496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
765 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 8771.8453 | 0.2 | 0.3 | 13684.0786 |  |  |  |  | 0 | 5576.2778 | 5576.2778 | 5576.2778 | 5576.2778 | 5576.2778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
766 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 16875.9071 | 0.2 | 0.3 | 26326.415 |  |  |  |  | 0 | 5204.516 | 5204.516 | 5204.516 | 5204.516 | 5204.516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
767 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 2489.4839 | 0.2 | 0.3 | 3883.5948 |  |  |  |  | 0 | 5204.7031 | 5204.7031 | 5204.7031 | 5204.7031 | 5204.7031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
768 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 13534.1899 | 0.2 | 0.3 | 21113.3362 |  |  |  |  | 0 | 9792.2457 | 9792.2457 | 9792.2457 | 9792.2457 | 9792.2457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
769 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 1560.6277 | 0.2 | 0.3 | 2434.5792 |  |  |  |  | 0 | 5204.8646 | 5204.8646 | 5204.8646 | 5204.8646 | 5204.8646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
770 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 520.4643 | 0.2 | 0.3 | 811.9243 |  |  |  |  | 0 | 5205.1435 | 5205.1435 | 5205.1435 | 5205.1435 | 5205.1435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
771 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 12112.5873 | 0.2 | 0.3 | 18895.6361 |  |  |  |  | 0 | 9781.9161 | 9781.9161 | 9781.9161 | 9781.9161 | 9781.9161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
772 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 16675.6223 | 0.2 | 0.3 | 26013.9707 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
773 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 23924.0629 | 0.2 | 0.3 | 37321.5382 |  |  |  |  | 0 | 9790.2606 | 9790.2606 | 9790.2606 | 9790.2606 | 9790.2606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
774 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 27280.6492 | 0.2 | 0.3 | 42557.8128 |  |  |  |  | 0 | 5206.1261 | 5206.1261 | 5206.1261 | 5206.1261 | 5206.1261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
775 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 26610.8524 | 0.2 | 0.3 | 41512.9297 |  |  |  |  | 0 | 5205.1774 | 5205.1774 | 5205.1774 | 5205.1774 | 5205.1774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
776 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 26461.6227 | 0.2 | 0.3 | 41280.1315 |  |  |  |  | 0 | 6701.5339 | 6701.5339 | 6701.5339 | 6701.5339 | 6701.5339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
777 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 26262.7077 | 0.2 | 0.3 | 40969.8241 |  |  |  |  | 0 | 5436.3919 | 5436.3919 | 5436.3919 | 5436.3919 | 5436.3919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
778 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 26106.4106 | 0.2 | 0.3 | 40726.0005 |  |  |  |  | 0 | 5203.4979 | 5203.4979 | 5203.4979 | 5203.4979 | 5203.4979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
779 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 5857.7521 | 0.2 | 0.3 | 9138.0932 |  |  |  |  | 0 | 5203.4728 | 5203.4728 | 5203.4728 | 5203.4728 | 5203.4728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
780 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 9906.6079 | 0.2 | 0.3 | 15454.3084 |  |  |  |  | 0 | 9791.2531 | 9791.2531 | 9791.2531 | 9791.2531 | 9791.2531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
781 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 41199.9209 | 0.2 | 0.3 | 64271.8766 |  |  |  |  | 0 | 5207.474 | 5207.474 | 5207.474 | 5207.474 | 5207.474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
782 | SUNRISE | 70310 | Private | 2036 | 5 | Swales | 66.6667 | 16464.7759 | 0.2 | 0.3 | 25685.0505 |  |  |  |  | 0 | 5207.8162 | 5207.8162 | 5207.8162 | 5207.8162 | 5207.8162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
783 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 14164.4815 | 0.2 | 0.3 | 22096.5912 |  |  |  |  | 0 | 9782.9583 | 9782.9583 | 9782.9583 | 9782.9583 | 9782.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
784 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 16666.8719 | 0.2 | 0.3 | 26000.3201 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
785 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 16678.6349 | 0.2 | 0.3 | 26018.6704 |  |  |  |  | 0 | 9788.1104 | 9788.1104 | 9788.1104 | 9788.1104 | 9788.1104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
786 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 11009.8662 | 0.2 | 0.3 | 17175.3913 |  |  |  |  | 0 | 5204.4975 | 5204.4975 | 5204.4975 | 5204.4975 | 5204.4975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
787 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17007.2607 | 0.2 | 0.3 | 26531.3266 |  |  |  |  | 0 | 5203.7158 | 5203.7158 | 5203.7158 | 5203.7158 | 5203.7158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
788 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 20767.1303 | 0.2 | 0.3 | 32396.7233 |  |  |  |  | 0 | 6878.7972 | 6878.7972 | 6878.7972 | 6878.7972 | 6878.7972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
789 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17135.2545 | 0.2 | 0.3 | 26730.9971 |  |  |  |  | 0 | 3305.3364 | 3305.3364 | 3305.3364 | 3305.3364 | 3305.3364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
790 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 8774.6023 | 0.2 | 0.3 | 13688.3795 |  |  |  |  | 0 | 2675.9643 | 2675.9643 | 2675.9643 | 2675.9643 | 2675.9643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
791 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 5250.5737 | 0.2 | 0.3 | 8190.8949 |  |  |  |  | 0 | 1676.8839 | 1676.8839 | 1676.8839 | 1676.8839 | 1676.8839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
792 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 19020.4149 | 0.2 | 0.3 | 29671.8472 |  |  |  |  | 0 | 1136.1612 | 1136.1612 | 1136.1612 | 1136.1612 | 1136.1612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
793 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 6398.019 | 0.2 | 0.3 | 9980.9096 |  |  |  |  | 0 | 5208.9386 | 5208.9386 | 5208.9386 | 5208.9386 | 5208.9386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
794 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 28126.8365 | 0.2 | 0.3 | 43877.865 |  |  |  |  | 0 | 7521.3238 | 7521.3238 | 7521.3238 | 7521.3238 | 7521.3238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
795 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 2241.1344 | 0.2 | 0.3 | 3496.1697 |  |  |  |  | 0 | 4990.7806 | 4990.7806 | 4990.7806 | 4990.7806 | 4990.7806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
796 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17514.6236 | 0.2 | 0.3 | 27322.8128 |  |  |  |  | 0 | 5205.8072 | 5205.8072 | 5205.8072 | 5205.8072 | 5205.8072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
797 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 29809.1139 | 0.2 | 0.3 | 46502.2176 |  |  |  |  | 0 | 6494.3235 | 6494.3235 | 6494.3235 | 6494.3235 | 6494.3235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
798 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17326.9425 | 0.2 | 0.3 | 27030.0302 |  |  |  |  | 0 | 5440.5027 | 5440.5027 | 5440.5027 | 5440.5027 | 5440.5027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
799 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 22182.7247 | 0.2 | 0.3 | 34605.0506 |  |  |  |  | 0 | 5327.9349 | 5327.9349 | 5327.9349 | 5327.9349 | 5327.9349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
800 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 16701.1357 | 0.2 | 0.3 | 26053.7717 |  |  |  |  | 0 | 4419.758 | 4419.758 | 4419.758 | 4419.758 | 4419.758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
801 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 16809.8339 | 0.2 | 0.3 | 26223.3408 |  |  |  |  | 0 | 8493.4821 | 8493.4821 | 8493.4821 | 8493.4821 | 8493.4821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
802 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 17179.6727 | 0.2 | 0.3 | 26800.2895 |  |  |  |  | 0 | 2848.3745 | 2848.3745 | 2848.3745 | 2848.3745 | 2848.3745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
803 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 25760.6328 | 0.2 | 0.3 | 40186.5872 |  |  |  |  | 0 | 4758.8883 | 4758.8883 | 4758.8883 | 4758.8883 | 4758.8883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
804 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 843.2536 | 0.2 | 0.3 | 1315.4756 |  |  |  |  | 0 | 7356.0078 | 7356.0078 | 7356.0078 | 7356.0078 | 7356.0078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
805 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 8337.3706 | 0.2 | 0.3 | 13006.2981 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
806 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 9283.0316 | 0.2 | 0.3 | 14481.5293 |  |  |  |  | 0 | 5203.9913 | 5203.9913 | 5203.9913 | 5203.9913 | 5203.9913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
807 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 11266.0857 | 0.2 | 0.3 | 17575.0937 |  |  |  |  | 0 | 9786.187 | 9786.187 | 9786.187 | 9786.187 | 9786.187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
808 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 13972.4597 | 0.2 | 0.3 | 21797.0372 |  |  |  |  | 0 | 5205.2836 | 5205.2836 | 5205.2836 | 5205.2836 | 5205.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
809 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 8797.9839 | 0.2 | 0.3 | 13724.8549 |  |  |  |  | 0 | 5205.6512 | 5205.6512 | 5205.6512 | 5205.6512 | 5205.6512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
810 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 9411.0129 | 0.2 | 0.3 | 14681.1801 |  |  |  |  | 0 | 5205.1138 | 5205.1138 | 5205.1138 | 5205.1138 | 5205.1138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
811 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 12071.413 | 0.2 | 0.3 | 18831.4043 |  |  |  |  | 0 | 8769.2728 | 8769.2728 | 8769.2728 | 8769.2728 | 8769.2728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
812 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 16767.2845 | 0.2 | 0.3 | 26156.9638 |  |  |  |  | 0 | 3027.4077 | 3027.4077 | 3027.4077 | 3027.4077 | 3027.4077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
813 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 23908.0185 | 0.2 | 0.3 | 37296.5089 |  |  |  |  | 0 | 3028.4658 | 3028.4658 | 3028.4658 | 3028.4658 | 3028.4658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
814 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 25315.6373 | 0.2 | 0.3 | 39492.3942 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
815 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 19352.9125 | 0.2 | 0.3 | 30190.5434 |  |  |  |  | 0 | 6254.2343 | 6254.2343 | 6254.2343 | 6254.2343 | 6254.2343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
816 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 14353.144 | 0.2 | 0.3 | 22390.9046 |  |  |  |  | 0 | 8734.4017 | 8734.4017 | 8734.4017 | 8734.4017 | 8734.4017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
817 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 16667.4627 | 0.2 | 0.3 | 26001.2419 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
818 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 8042.3754 | 0.2 | 0.3 | 12546.1056 |  |  |  |  | 0 | 5204.4473 | 5204.4473 | 5204.4473 | 5204.4473 | 5204.4473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
819 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 2004.6453 | 0.2 | 0.3 | 3127.2466 |  |  |  |  | 0 | 9784.8693 | 9784.8693 | 9784.8693 | 9784.8693 | 9784.8693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
820 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 3365.2735 | 0.2 | 0.3 | 5249.8266 |  |  |  |  | 0 | 5204.518 | 5204.518 | 5204.518 | 5204.518 | 5204.518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
821 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 12429.3978 | 0.2 | 0.3 | 19389.8606 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
822 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 18261.5413 | 0.2 | 0.3 | 28488.0045 |  |  |  |  | 0 | 5204.7724 | 5204.7724 | 5204.7724 | 5204.7724 | 5204.7724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
823 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 7842.6179 | 0.2 | 0.3 | 12234.4839 |  |  |  |  | 0 | 9795.8552 | 9795.8552 | 9795.8552 | 9795.8552 | 9795.8552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
824 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 3491.7351 | 0.2 | 0.3 | 5447.1067 |  |  |  |  | 0 | 4749.0656 | 4749.0656 | 4749.0656 | 4749.0656 | 4749.0656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
825 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 33706.2003 | 0.2 | 0.3 | 52581.6724 |  |  |  |  | 0 | 2620.3024 | 2620.3024 | 2620.3024 | 2620.3024 | 2620.3024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
826 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 18044.1071 | 0.2 | 0.3 | 28148.8071 |  |  |  |  | 0 | 3309.0049 | 3309.0049 | 3309.0049 | 3309.0049 | 3309.0049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
827 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 12793.6535 | 0.2 | 0.3 | 19958.0994 |  |  |  |  | 0 | 5204.7158 | 5204.7158 | 5204.7158 | 5204.7158 | 5204.7158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
828 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17032.5295 | 0.2 | 0.3 | 26570.746 |  |  |  |  | 0 | 9786.5331 | 9786.5331 | 9786.5331 | 9786.5331 | 9786.5331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
829 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 18005.0845 | 0.2 | 0.3 | 28087.9318 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
830 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 17275.0689 | 0.2 | 0.3 | 26949.1074 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
831 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 15585.9674 | 0.2 | 0.3 | 24314.1091 |  |  |  |  | 0 | 9783.0568 | 9783.0568 | 9783.0568 | 9783.0568 | 9783.0568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
832 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 2256.7745 | 0.2 | 0.3 | 3520.5682 |  |  |  |  | 0 | 5204.1593 | 5204.1593 | 5204.1593 | 5204.1593 | 5204.1593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
833 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 4777.2185 | 0.2 | 0.3 | 7452.4608 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
834 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 27039.8591 | 0.2 | 0.3 | 42182.1801 |  |  |  |  | 0 | 5204.2593 | 5204.2593 | 5204.2593 | 5204.2593 | 5204.2593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
835 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 21933.4763 | 0.2 | 0.3 | 34216.223 |  |  |  |  | 0 | 9794.2744 | 9794.2744 | 9794.2744 | 9794.2744 | 9794.2744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
836 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 22293.0669 | 0.2 | 0.3 | 34777.1843 |  |  |  |  | 0 | 5204.9253 | 5204.9253 | 5204.9253 | 5204.9253 | 5204.9253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
837 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 22405.6111 | 0.2 | 0.3 | 34952.7534 |  |  |  |  | 0 | 5203.5406 | 5203.5406 | 5203.5406 | 5203.5406 | 5203.5406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
838 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 28256.3447 | 0.2 | 0.3 | 44079.8978 |  |  |  |  | 0 | 3607.6997 | 3607.6997 | 3607.6997 | 3607.6997 | 3607.6997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 8338.5591 | 0.2 | 0.3 | 13008.1521 |  |  |  |  | 0 | 3167.2465 | 3167.2465 | 3167.2465 | 3167.2465 | 3167.2465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
840 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 7384.1769 | 0.2 | 0.3 | 11519.3159 |  |  |  |  | 0 | 9782.628 | 9782.628 | 9782.628 | 9782.628 | 9782.628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
841 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 9078.2971 | 0.2 | 0.3 | 14162.1434 |  |  |  |  | 0 | 10895.9705 | 10895.9705 | 10895.9705 | 10895.9705 | 10895.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
842 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 16813.7659 | 0.2 | 0.3 | 26229.4748 |  |  |  |  | 0 | 372.2902 | 372.2902 | 372.2902 | 372.2902 | 372.2902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
843 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 22481.0313 | 0.2 | 0.3 | 35070.4088 |  |  |  |  | 0 | 5205.5238 | 5205.5238 | 5205.5238 | 5205.5238 | 5205.5238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
844 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 19514.29 | 0.2 | 0.3 | 30442.2924 |  |  |  |  | 0 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
845 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 18541.2753 | 0.2 | 0.3 | 28924.3895 |  |  |  |  | 0 | 9786.9228 | 9786.9228 | 9786.9228 | 9786.9228 | 9786.9228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
846 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 26479.0893 | 0.2 | 0.3 | 41307.3794 |  |  |  |  | 0 | 5203.9958 | 5203.9958 | 5203.9958 | 5203.9958 | 5203.9958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
847 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 20437.7819 | 0.2 | 0.3 | 31882.9397 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
848 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 16690.0879 | 0.2 | 0.3 | 26036.5371 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
849 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 29352.1389 | 0.2 | 0.3 | 45789.3366 |  |  |  |  | 0 | 9791.4419 | 9791.4419 | 9791.4419 | 9791.4419 | 9791.4419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
850 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 9545.7845 | 0.2 | 0.3 | 14891.4238 |  |  |  |  | 0 | 5204.5606 | 5204.5606 | 5204.5606 | 5204.5606 | 5204.5606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
851 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 18911.0001 | 0.2 | 0.3 | 29501.1601 |  |  |  |  | 0 | 9507.8699 | 9507.8699 | 9507.8699 | 9507.8699 | 9507.8699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
852 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 14566.1996 | 0.2 | 0.3 | 22723.2714 |  |  |  |  | 0 | 3492.1285 | 3492.1285 | 3492.1285 | 3492.1285 | 3492.1285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
853 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 16671.4834 | 0.2 | 0.3 | 26007.5141 |  |  |  |  | 0 | 3549.8554 | 3549.8554 | 3549.8554 | 3549.8554 | 3549.8554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
854 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 16668.8476 | 0.2 | 0.3 | 26003.4023 |  |  |  |  | 0 | 7727.0251 | 7727.0251 | 7727.0251 | 7727.0251 | 7727.0251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
855 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 16666.6087 | 0.2 | 0.3 | 25999.9096 |  |  |  |  | 0 | 11441.2323 | 11441.2323 | 11441.2323 | 11441.2323 | 11441.2323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
856 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 16767.1197 | 0.2 | 0.3 | 26156.7067 |  |  |  |  | 0 | 1965.6988 | 1965.6988 | 1965.6988 | 1965.6988 | 1965.6988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
857 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 10330.3137 | 0.2 | 0.3 | 16115.2893 |  |  |  |  | 0 | 5282.9184 | 5282.9184 | 5282.9184 | 5282.9184 | 5282.9184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
858 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 18746.4169 | 0.2 | 0.3 | 29244.4104 |  |  |  |  | 0 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
859 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 14520.4925 | 0.2 | 0.3 | 22651.9682 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
860 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16845.9576 | 0.2 | 0.3 | 26279.6939 |  |  |  |  | 0 | 9786.7537 | 9786.7537 | 9786.7537 | 9786.7537 | 9786.7537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
861 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17497.8923 | 0.2 | 0.3 | 27296.7119 |  |  |  |  | 0 | 5204.7526 | 5204.7526 | 5204.7526 | 5204.7526 | 5204.7526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
862 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 30117.3055 | 0.2 | 0.3 | 46982.9966 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
863 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 9211.4873 | 0.2 | 0.3 | 14369.9201 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
864 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 15374.7086 | 0.2 | 0.3 | 23984.5454 |  |  |  |  | 0 | 8907.709 | 8907.709 | 8907.709 | 8907.709 | 8907.709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
865 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 1849.9866 | 0.2 | 0.3 | 2885.9791 |  |  |  |  | 0 | 5203.4434 | 5203.4434 | 5203.4434 | 5203.4434 | 5203.4434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
866 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 15946.9153 | 0.2 | 0.3 | 24877.1878 |  |  |  |  | 0 | 5721.7788 | 5721.7788 | 5721.7788 | 5721.7788 | 5721.7788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
867 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 16914.4797 | 0.2 | 0.3 | 26386.5883 |  |  |  |  | 0 | 5205.7342 | 5205.7342 | 5205.7342 | 5205.7342 | 5205.7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
868 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 11480.2162 | 0.2 | 0.3 | 17909.1373 |  |  |  |  | 0 | 3693.0263 | 3693.0263 | 3693.0263 | 3693.0263 | 3693.0263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
869 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 5564.4514 | 0.2 | 0.3 | 8680.5442 |  |  |  |  | 0 | 6061.1366 | 6061.1366 | 6061.1366 | 6061.1366 | 6061.1366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
870 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 14131.2171 | 0.2 | 0.3 | 22044.6986 |  |  |  |  | 0 | 306.408 | 306.408 | 306.408 | 306.408 | 306.408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
871 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 12180.6609 | 0.2 | 0.3 | 19001.831 |  |  |  |  | 0 | 5213.6786 | 5213.6786 | 5213.6786 | 5213.6786 | 5213.6786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
872 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 19131.2225 | 0.2 | 0.3 | 29844.7072 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
873 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 4087.6586 | 0.2 | 0.3 | 6376.7474 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
874 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 26108.6023 | 0.2 | 0.3 | 40729.4196 |  |  |  |  | 0 | 9224.7378 | 9224.7378 | 9224.7378 | 9224.7378 | 9224.7378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
875 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 30852.1822 | 0.2 | 0.3 | 48129.4042 |  |  |  |  | 0 | 599.1275 | 599.1275 | 599.1275 | 599.1275 | 599.1275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
876 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 15556.4421 | 0.2 | 0.3 | 24268.0497 |  |  |  |  | 0 | 7934.7948 | 7934.7948 | 7934.7948 | 7934.7948 | 7934.7948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
877 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 27675.9327 | 0.2 | 0.3 | 43174.4551 |  |  |  |  | 0 | 5206.8995 | 5206.8995 | 5206.8995 | 5206.8995 | 5206.8995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
878 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 30579.3773 | 0.2 | 0.3 | 47703.8286 |  |  |  |  | 0 | 5201.9163 | 5201.9163 | 5201.9163 | 5201.9163 | 5201.9163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
879 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 16667.7975 | 0.2 | 0.3 | 26001.7642 |  |  |  |  | 0 | 6159.5506 | 6159.5506 | 6159.5506 | 6159.5506 | 6159.5506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
880 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 27546.6455 | 0.2 | 0.3 | 42972.767 |  |  |  |  | 0 | 6119.6926 | 6119.6926 | 6119.6926 | 6119.6926 | 6119.6926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
881 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 23878.5388 | 0.2 | 0.3 | 37250.5205 |  |  |  |  | 0 | 6176.4824 | 6176.4824 | 6176.4824 | 6176.4824 | 6176.4824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
882 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 28535.3008 | 0.2 | 0.3 | 44515.0692 |  |  |  |  | 0 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
883 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 16458.6512 | 0.2 | 0.3 | 25675.4959 |  |  |  |  | 0 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
884 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 28549.5797 | 0.2 | 0.3 | 44537.3444 |  |  |  |  | 0 | 6443.7577 | 6443.7577 | 6443.7577 | 6443.7577 | 6443.7577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
885 | WESTON | 70311 | Public | 2036 | 5 | Swales | 66.6667 | 26988.8024 | 0.2 | 0.3 | 42102.5317 |  |  |  |  | 0 | 3791.2845 | 3791.2845 | 3791.2845 | 3791.2845 | 3791.2845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
886 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 25392.5587 | 0.2 | 0.3 | 39612.3915 |  |  |  |  | 0 | 5203.147 | 5203.147 | 5203.147 | 5203.147 | 5203.147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
887 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 18103.6307 | 0.2 | 0.3 | 28241.6639 |  |  |  |  | 0 | 5203.7834 | 5203.7834 | 5203.7834 | 5203.7834 | 5203.7834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
888 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 18272.6409 | 0.2 | 0.3 | 28505.3198 |  |  |  |  | 0 | 5203.1907 | 5203.1907 | 5203.1907 | 5203.1907 | 5203.1907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
889 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 6771.189 | 0.2 | 0.3 | 10563.0548 |  |  |  |  | 0 | 5204.9365 | 5204.9365 | 5204.9365 | 5204.9365 | 5204.9365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
890 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 15675.8727 | 0.2 | 0.3 | 24454.3615 |  |  |  |  | 0 | 5204.1396 | 5204.1396 | 5204.1396 | 5204.1396 | 5204.1396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
891 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 8169.204 | 0.2 | 0.3 | 12743.9582 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
892 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 10084.5655 | 0.2 | 0.3 | 15731.9222 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
893 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 20133.2175 | 0.2 | 0.3 | 31407.8192 |  |  |  |  | 0 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
894 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 25142.101 | 0.2 | 0.3 | 39221.6776 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
895 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 13116.7195 | 0.2 | 0.3 | 20462.0824 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
896 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 22394.4747 | 0.2 | 0.3 | 34935.3805 |  |  |  |  | 0 | 9064.5087 | 9064.5087 | 9064.5087 | 9064.5087 | 9064.5087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
897 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 20512.1139 | 0.2 | 0.3 | 31998.8976 |  |  |  |  | 0 | 5204.8734 | 5204.8734 | 5204.8734 | 5204.8734 | 5204.8734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
898 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 11880.7186 | 0.2 | 0.3 | 18533.921 |  |  |  |  | 0 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
899 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 28732.1931 | 0.2 | 0.3 | 44822.2212 |  |  |  |  | 0 | 5204.9592 | 5204.9592 | 5204.9592 | 5204.9592 | 5204.9592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
900 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 19373.9761 | 0.2 | 0.3 | 30223.4027 |  |  |  |  | 0 | 6736.2127 | 6736.2127 | 6736.2127 | 6736.2127 | 6736.2127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
901 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 4522.5263 | 0.2 | 0.3 | 7055.1411 |  |  |  |  | 0 | 7769.0181 | 7769.0181 | 7769.0181 | 7769.0181 | 7769.0181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
902 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 2969.3488 | 0.2 | 0.3 | 4632.1841 |  |  |  |  | 0 | 5205.2961 | 5205.2961 | 5205.2961 | 5205.2961 | 5205.2961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
903 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17968.7599 | 0.2 | 0.3 | 28031.2655 |  |  |  |  | 0 | 8218.9948 | 8218.9948 | 8218.9948 | 8218.9948 | 8218.9948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
904 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17946.7689 | 0.2 | 0.3 | 27996.9595 |  |  |  |  | 0 | 8402.4089 | 8402.4089 | 8402.4089 | 8402.4089 | 8402.4089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
905 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 18506.5895 | 0.2 | 0.3 | 28870.2796 |  |  |  |  | 0 | 1297.6411 | 1297.6411 | 1297.6411 | 1297.6411 | 1297.6411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
906 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 1455.9957 | 0.2 | 0.3 | 2271.3533 |  |  |  |  | 0 | 5458.291 | 5458.291 | 5458.291 | 5458.291 | 5458.291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
907 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 16357.7351 | 0.2 | 0.3 | 25518.0668 |  |  |  |  | 0 | 8766.0332 | 8766.0332 | 8766.0332 | 8766.0332 | 8766.0332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
908 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 20583.2021 | 0.2 | 0.3 | 32109.7952 |  |  |  |  | 0 | 3650.2036 | 3650.2036 | 3650.2036 | 3650.2036 | 3650.2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
909 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 21985.1456 | 0.2 | 0.3 | 34296.8271 |  |  |  |  | 0 | 5205.6434 | 5205.6434 | 5205.6434 | 5205.6434 | 5205.6434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
910 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 3507.5237 | 0.2 | 0.3 | 5471.7369 |  |  |  |  | 0 | 4895.9672 | 4895.9672 | 4895.9672 | 4895.9672 | 4895.9672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
911 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 22090.1529 | 0.2 | 0.3 | 34460.6385 |  |  |  |  | 0 | 5204.2272 | 5204.2272 | 5204.2272 | 5204.2272 | 5204.2272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
912 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 21627.0455 | 0.2 | 0.3 | 33738.1909 |  |  |  |  | 0 | 5732.1922 | 5732.1922 | 5732.1922 | 5732.1922 | 5732.1922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
913 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 6395.3699 | 0.2 | 0.3 | 9976.7771 |  |  |  |  | 0 | 5203.7921 | 5203.7921 | 5203.7921 | 5203.7921 | 5203.7921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
914 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 11202.7256 | 0.2 | 0.3 | 17476.2519 |  |  |  |  | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
915 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 21497.6933 | 0.2 | 0.3 | 33536.4016 |  |  |  |  | 0 | 9784.8048 | 9784.8048 | 9784.8048 | 9784.8048 | 9784.8048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
916 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17984.7471 | 0.2 | 0.3 | 28056.2055 |  |  |  |  | 0 | 5204.1058 | 5204.1058 | 5204.1058 | 5204.1058 | 5204.1058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
917 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 26403.7735 | 0.2 | 0.3 | 41189.8867 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
918 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16733.4962 | 0.2 | 0.3 | 26104.2541 |  |  |  |  | 0 | 5204.5299 | 5204.5299 | 5204.5299 | 5204.5299 | 5204.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
919 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 15190.1891 | 0.2 | 0.3 | 23696.695 |  |  |  |  | 0 | 6804.8199 | 6804.8199 | 6804.8199 | 6804.8199 | 6804.8199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
920 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 4576.1558 | 0.2 | 0.3 | 7138.803 |  |  |  |  | 0 | 7347.1282 | 7347.1282 | 7347.1282 | 7347.1282 | 7347.1282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
921 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 385.7574 | 0.2 | 0.3 | 601.7815 |  |  |  |  | 0 | 8778.1126 | 8778.1126 | 8778.1126 | 8778.1126 | 8778.1126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
922 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 15741.9661 | 0.2 | 0.3 | 24557.4671 |  |  |  |  | 0 | 9704.0512 | 9704.0512 | 9704.0512 | 9704.0512 | 9704.0512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
923 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17188.4931 | 0.2 | 0.3 | 26814.0492 |  |  |  |  | 0 | 9486.998 | 9486.998 | 9486.998 | 9486.998 | 9486.998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
924 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 32544.2147 | 0.2 | 0.3 | 50768.9749 |  |  |  |  | 0 | 7991.7692 | 7991.7692 | 7991.7692 | 7991.7692 | 7991.7692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
925 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 18239.8088 | 0.2 | 0.3 | 28454.1017 |  |  |  |  | 0 | 5203.1076 | 5203.1076 | 5203.1076 | 5203.1076 | 5203.1076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
926 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 20897.7224 | 0.2 | 0.3 | 32600.4469 |  |  |  |  | 0 | 5203.7277 | 5203.7277 | 5203.7277 | 5203.7277 | 5203.7277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
927 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 20049.782 | 0.2 | 0.3 | 31277.6599 |  |  |  |  | 0 | 5203.0765 | 5203.0765 | 5203.0765 | 5203.0765 | 5203.0765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
928 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 8039.5143 | 0.2 | 0.3 | 12541.6423 |  |  |  |  | 0 | 5204.9384 | 5204.9384 | 5204.9384 | 5204.9384 | 5204.9384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
929 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 37164.8567 | 0.2 | 0.3 | 57977.1765 |  |  |  |  | 0 | 5204.0243 | 5204.0243 | 5204.0243 | 5204.0243 | 5204.0243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
930 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 18373.4493 | 0.2 | 0.3 | 28662.5809 |  |  |  |  | 0 | 5204.1975 | 5204.1975 | 5204.1975 | 5204.1975 | 5204.1975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
931 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 19889.2512 | 0.2 | 0.3 | 31027.2319 |  |  |  |  | 0 | 5204.2789 | 5204.2789 | 5204.2789 | 5204.2789 | 5204.2789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
932 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 397.9295 | 0.2 | 0.3 | 620.77 |  |  |  |  | 0 | 5204.785 | 5204.785 | 5204.785 | 5204.785 | 5204.785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
933 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 22322.3239 | 0.2 | 0.3 | 34822.8253 |  |  |  |  | 0 | 5203.9579 | 5203.9579 | 5203.9579 | 5203.9579 | 5203.9579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
934 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 153.0851 | 0.2 | 0.3 | 238.8128 |  |  |  |  | 0 | 5393.4812 | 5393.4812 | 5393.4812 | 5393.4812 | 5393.4812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
935 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 36917.5012 | 0.2 | 0.3 | 57591.3019 |  |  |  |  | 0 | 9273.5272 | 9273.5272 | 9273.5272 | 9273.5272 | 9273.5272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
936 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 26010.0283 | 0.2 | 0.3 | 40575.6442 |  |  |  |  | 0 | 5204.5389 | 5204.5389 | 5204.5389 | 5204.5389 | 5204.5389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
937 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 31333.6419 | 0.2 | 0.3 | 48880.4813 |  |  |  |  | 0 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
938 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 30704.9097 | 0.2 | 0.3 | 47899.6591 |  |  |  |  | 0 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
939 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16712.402 | 0.2 | 0.3 | 26071.3471 |  |  |  |  | 0 | 5204.5026 | 5204.5026 | 5204.5026 | 5204.5026 | 5204.5026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
940 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17151.9854 | 0.2 | 0.3 | 26757.0972 |  |  |  |  | 0 | 5557.1242 | 5557.1242 | 5557.1242 | 5557.1242 | 5557.1242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
941 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 1045.2791 | 0.2 | 0.3 | 1630.6353 |  |  |  |  | 0 | 6824.2051 | 6824.2051 | 6824.2051 | 6824.2051 | 6824.2051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
942 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 19118.5077 | 0.2 | 0.3 | 29824.8721 |  |  |  |  | 0 | 5989.0734 | 5989.0734 | 5989.0734 | 5989.0734 | 5989.0734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
943 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 717.2987 | 0.2 | 0.3 | 1118.986 |  |  |  |  | 0 | 8619.0584 | 8619.0584 | 8619.0584 | 8619.0584 | 8619.0584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
944 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 19.4707 | 0.2 | 0.3 | 30.3742 |  |  |  |  | 0 | 4654.6056 | 4654.6056 | 4654.6056 | 4654.6056 | 4654.6056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
945 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 22544.9369 | 0.2 | 0.3 | 35170.1016 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
946 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 10525.4601 | 0.2 | 0.3 | 16419.7178 |  |  |  |  | 0 | 6538.1785 | 6538.1785 | 6538.1785 | 6538.1785 | 6538.1785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
947 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 9913.8127 | 0.2 | 0.3 | 15465.5478 |  |  |  |  | 0 | 1405.227 | 1405.227 | 1405.227 | 1405.227 | 1405.227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
948 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 17909.4489 | 0.2 | 0.3 | 27938.7403 |  |  |  |  | 0 | 5211.5478 | 5211.5478 | 5211.5478 | 5211.5478 | 5211.5478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
949 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 15037.4733 | 0.2 | 0.3 | 23458.4583 |  |  |  |  | 0 | 5204.4304 | 5204.4304 | 5204.4304 | 5204.4304 | 5204.4304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
950 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 4559.5089 | 0.2 | 0.3 | 7112.8339 |  |  |  |  | 0 | 6054.6407 | 6054.6407 | 6054.6407 | 6054.6407 | 6054.6407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
951 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 13696.3433 | 0.2 | 0.3 | 21366.2956 |  |  |  |  | 0 | 5205.1636 | 5205.1636 | 5205.1636 | 5205.1636 | 5205.1636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
952 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 4805.6122 | 0.2 | 0.3 | 7496.755 |  |  |  |  | 0 | 5205.4001 | 5205.4001 | 5205.4001 | 5205.4001 | 5205.4001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
953 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 8476.0101 | 0.2 | 0.3 | 13222.5757 |  |  |  |  | 0 | 7018.9145 | 7018.9145 | 7018.9145 | 7018.9145 | 7018.9145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
954 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 10357.9918 | 0.2 | 0.3 | 16158.4672 |  |  |  |  | 0 | 9790.2593 | 9790.2593 | 9790.2593 | 9790.2593 | 9790.2593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
955 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 6564.2037 | 6564.2037 | 6564.2037 | 6564.2037 | 6564.2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
956 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 16931.0206 | 0.2 | 0.3 | 26412.3921 |  |  |  |  | 0 | 5203.6544 | 5203.6544 | 5203.6544 | 5203.6544 | 5203.6544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
957 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17423.1691 | 0.2 | 0.3 | 27180.1438 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
958 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 26624.6495 | 0.2 | 0.3 | 41534.4532 |  |  |  |  | 0 | 9794.0044 | 9794.0044 | 9794.0044 | 9794.0044 | 9794.0044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
959 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 12876.0657 | 0.2 | 0.3 | 20086.6624 |  |  |  |  | 0 | 5206.1366 | 5206.1366 | 5206.1366 | 5206.1366 | 5206.1366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
960 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 10852.4871 | 0.2 | 0.3 | 16929.8798 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
961 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 5431.5127 | 0.2 | 0.3 | 8473.1598 |  |  |  |  | 0 | 5206.4882 | 5206.4882 | 5206.4882 | 5206.4882 | 5206.4882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
962 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 12857.4249 | 0.2 | 0.3 | 20057.5829 |  |  |  |  | 0 | 4796.2551 | 4796.2551 | 4796.2551 | 4796.2551 | 4796.2551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
963 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 20025.8301 | 0.2 | 0.3 | 31240.2949 |  |  |  |  | 0 | 7641.7774 | 7641.7774 | 7641.7774 | 7641.7774 | 7641.7774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
964 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 432.5942 | 0.2 | 0.3 | 674.847 |  |  |  |  | 0 | 6215.3357 | 6215.3357 | 6215.3357 | 6215.3357 | 6215.3357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
965 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 31209.7591 | 0.2 | 0.3 | 48687.2241 |  |  |  |  | 0 | 1165.6467 | 1165.6467 | 1165.6467 | 1165.6467 | 1165.6467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
966 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 16526.7405 | 0.2 | 0.3 | 25781.7152 |  |  |  |  | 0 | 2659.5714 | 2659.5714 | 2659.5714 | 2659.5714 | 2659.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
967 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17195.09 | 0.2 | 0.3 | 26824.3404 |  |  |  |  | 0 | 4866.2197 | 4866.2197 | 4866.2197 | 4866.2197 | 4866.2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
968 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 23315.5411 | 0.2 | 0.3 | 36372.2442 |  |  |  |  | 0 | 9782.5814 | 9782.5814 | 9782.5814 | 9782.5814 | 9782.5814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
969 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 22750.7011 | 0.2 | 0.3 | 35491.0938 |  |  |  |  | 0 | 9786.5393 | 9786.5393 | 9786.5393 | 9786.5393 | 9786.5393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
970 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 31353.0539 | 0.2 | 0.3 | 48910.764 |  |  |  |  | 0 | 9783.8587 | 9783.8587 | 9783.8587 | 9783.8587 | 9783.8587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
971 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 8293.5096 | 0.2 | 0.3 | 12937.875 |  |  |  |  | 0 | 9786.2476 | 9786.2476 | 9786.2476 | 9786.2476 | 9786.2476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
972 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 14900.6453 | 0.2 | 0.3 | 23245.0067 |  |  |  |  | 0 | 9792.7081 | 9792.7081 | 9792.7081 | 9792.7081 | 9792.7081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
973 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 25795.5044 | 0.2 | 0.3 | 40240.9869 |  |  |  |  | 0 | 9783.6594 | 9783.6594 | 9783.6594 | 9783.6594 | 9783.6594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
974 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 20801.2197 | 0.2 | 0.3 | 32449.9027 |  |  |  |  | 0 | 9783.2928 | 9783.2928 | 9783.2928 | 9783.2928 | 9783.2928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
975 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 11664.5123 | 0.2 | 0.3 | 18196.6391 |  |  |  |  | 0 | 9784.1747 | 9784.1747 | 9784.1747 | 9784.1747 | 9784.1747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
976 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 5157.7244 | 0.2 | 0.3 | 8046.0501 |  |  |  |  | 0 | 9783.4653 | 9783.4653 | 9783.4653 | 9783.4653 | 9783.4653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
977 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 15110.1683 | 0.2 | 0.3 | 23571.8626 |  |  |  |  | 0 | 9594.8615 | 9594.8615 | 9594.8615 | 9594.8615 | 9594.8615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
978 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 14387.9851 | 0.2 | 0.3 | 22445.2567 |  |  |  |  | 0 | 9183.7122 | 9183.7122 | 9183.7122 | 9183.7122 | 9183.7122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
979 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 8552.8988 | 0.2 | 0.3 | 13342.5221 |  |  |  |  | 0 | 5204.6729 | 5204.6729 | 5204.6729 | 5204.6729 | 5204.6729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
980 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 16368.6502 | 0.2 | 0.3 | 25535.0943 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
981 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 23025.4517 | 0.2 | 0.3 | 35919.7046 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
982 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 21804.677 | 0.2 | 0.3 | 34015.2961 |  |  |  |  | 0 | 5204.8828 | 5204.8828 | 5204.8828 | 5204.8828 | 5204.8828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
983 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 10991.3287 | 0.2 | 0.3 | 17146.4728 |  |  |  |  | 0 | 5776.5874 | 5776.5874 | 5776.5874 | 5776.5874 | 5776.5874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
984 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 16838.0168 | 0.2 | 0.3 | 26267.3062 |  |  |  |  | 0 | 5204.561 | 5204.561 | 5204.561 | 5204.561 | 5204.561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
985 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 4572.6929 | 0.2 | 0.3 | 7133.4009 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
986 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16669.7682 | 0.2 | 0.3 | 26004.8384 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
987 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 5279.9711 | 0.2 | 0.3 | 8236.7549 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
988 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 18036.2599 | 0.2 | 0.3 | 28136.5655 |  |  |  |  | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
989 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 8818.727 | 0.2 | 0.3 | 13757.2141 |  |  |  |  | 0 | 5803.3152 | 5803.3152 | 5803.3152 | 5803.3152 | 5803.3152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
990 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 18125.8053 | 0.2 | 0.3 | 28276.2563 |  |  |  |  | 0 | 9184.1019 | 9184.1019 | 9184.1019 | 9184.1019 | 9184.1019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
991 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 18369.5471 | 0.2 | 0.3 | 28656.4935 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
992 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 5896.8891 | 0.2 | 0.3 | 9199.147 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
993 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 34794.6395 | 0.2 | 0.3 | 54279.6377 |  |  |  |  | 0 | 5853.2077 | 5853.2077 | 5853.2077 | 5853.2077 | 5853.2077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
994 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 19002.3403 | 0.2 | 0.3 | 29643.6508 |  |  |  |  | 0 | 5204.8724 | 5204.8724 | 5204.8724 | 5204.8724 | 5204.8724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
995 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 12951.1585 | 0.2 | 0.3 | 20203.8073 |  |  |  |  | 0 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
996 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17023.4288 | 0.2 | 0.3 | 26556.5489 |  |  |  |  | 0 | 5205.026 | 5205.026 | 5205.026 | 5205.026 | 5205.026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
997 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 37948.3041 | 0.2 | 0.3 | 59199.3544 |  |  |  |  | 0 | 9786.5445 | 9786.5445 | 9786.5445 | 9786.5445 | 9786.5445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
998 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 16896.4033 | 0.2 | 0.3 | 26358.3891 |  |  |  |  | 0 | 5204.12 | 5204.12 | 5204.12 | 5204.12 | 5204.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
999 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 19437.4887 | 0.2 | 0.3 | 30322.4824 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1000 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 8184.8522 | 0.2 | 0.3 | 12768.3694 |  |  |  |  | 0 | 5204.1583 | 5204.1583 | 5204.1583 | 5204.1583 | 5204.1583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1001 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 20154.3641 | 0.2 | 0.3 | 31440.8079 |  |  |  |  | 0 | 9783.9001 | 9783.9001 | 9783.9001 | 9783.9001 | 9783.9001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1002 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 8377.0281 | 0.2 | 0.3 | 13068.1639 |  |  |  |  | 0 | 5204.226 | 5204.226 | 5204.226 | 5204.226 | 5204.226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1003 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 2823.7815 | 0.2 | 0.3 | 4405.0991 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1004 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 7933.9313 | 0.2 | 0.3 | 12376.9329 |  |  |  |  | 0 | 5204.6565 | 5204.6565 | 5204.6565 | 5204.6565 | 5204.6565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1005 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 28526.3295 | 0.2 | 0.3 | 44501.074 |  |  |  |  | 0 | 5716.8356 | 5716.8356 | 5716.8356 | 5716.8356 | 5716.8356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1006 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 14073.3023 | 0.2 | 0.3 | 21954.3515 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1007 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 17982.0535 | 0.2 | 0.3 | 28052.0035 |  |  |  |  | 0 | 7603.1822 | 7603.1822 | 7603.1822 | 7603.1822 | 7603.1822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1008 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 22462.3876 | 0.2 | 0.3 | 35041.3247 |  |  |  |  | 0 | 4038.2021 | 4038.2021 | 4038.2021 | 4038.2021 | 4038.2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1009 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16668.5465 | 0.2 | 0.3 | 26002.9326 |  |  |  |  | 0 | 3624.594 | 3624.594 | 3624.594 | 3624.594 | 3624.594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1010 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 6196.8446 | 0.2 | 0.3 | 9667.0776 |  |  |  |  | 0 | 3035.1449 | 3035.1449 | 3035.1449 | 3035.1449 | 3035.1449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1011 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 6723.1965 | 0.2 | 0.3 | 10488.1866 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1012 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 20536.9753 | 0.2 | 0.3 | 32037.6815 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1013 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 16843.455 | 0.2 | 0.3 | 26275.7898 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1014 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 18296.8863 | 0.2 | 0.3 | 28543.1427 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1015 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 37684.7629 | 0.2 | 0.3 | 58788.2301 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1016 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 34619.4183 | 0.2 | 0.3 | 54006.2926 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1017 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 11584.0859 | 0.2 | 0.3 | 18071.174 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1018 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 16702.8341 | 0.2 | 0.3 | 26056.4211 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1019 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 17495.5907 | 0.2 | 0.3 | 27293.1214 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1020 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 21108.3691 | 0.2 | 0.3 | 32929.0557 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1021 | SUNRISE | 70310 | Public | 2036 | 5 | Swales | 66.6667 | 4332.3439 | 0.2 | 0.3 | 6758.4564 |  |  |  |  | 0 | 8373.6155 | 8373.6155 | 8373.6155 | 8373.6155 | 8373.6155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1022 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 23037.3763 | 0.2 | 0.3 | 35938.307 |  |  |  |  | 0 | 5204.4957 | 5204.4957 | 5204.4957 | 5204.4957 | 5204.4957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1023 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 11648.3015 | 0.2 | 0.3 | 18171.3504 |  |  |  |  | 0 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1024 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 15557.6907 | 0.2 | 0.3 | 24269.9974 |  |  |  |  | 0 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1025 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 19945.6726 | 0.2 | 0.3 | 31115.2493 |  |  |  |  | 0 | 5204.8681 | 5204.8681 | 5204.8681 | 5204.8681 | 5204.8681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1026 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 4646.0094 | 0.2 | 0.3 | 7247.7747 |  |  |  |  | 0 | 5979.8069 | 5979.8069 | 5979.8069 | 5979.8069 | 5979.8069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1027 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 2610.498 | 0.2 | 0.3 | 4072.3769 |  |  |  |  | 0 | 5204.5785 | 5204.5785 | 5204.5785 | 5204.5785 | 5204.5785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1028 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 9345.3437 | 0.2 | 0.3 | 14578.7362 |  |  |  |  | 0 | 5204.7363 | 5204.7363 | 5204.7363 | 5204.7363 | 5204.7363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1029 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17191.2087 | 0.2 | 0.3 | 26818.2856 |  |  |  |  | 0 | 5203.0804 | 5203.0804 | 5203.0804 | 5203.0804 | 5203.0804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1030 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 33709.0581 | 0.2 | 0.3 | 52586.1306 |  |  |  |  | 0 | 5202.9598 | 5202.9598 | 5202.9598 | 5202.9598 | 5202.9598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1031 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17673.148 | 0.2 | 0.3 | 27570.1109 |  |  |  |  | 0 | 5499.7644 | 5499.7644 | 5499.7644 | 5499.7644 | 5499.7644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1032 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 6824.844 | 0.2 | 0.3 | 10646.7566 |  |  |  |  | 0 | 5596.2823 | 5596.2823 | 5596.2823 | 5596.2823 | 5596.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1033 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 16851.3894 | 0.2 | 0.3 | 26288.1675 |  |  |  |  | 0 | 7845.6449 | 7845.6449 | 7845.6449 | 7845.6449 | 7845.6449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1034 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 8913.6751 | 0.2 | 0.3 | 13905.3331 |  |  |  |  | 0 | 7680.0241 | 7680.0241 | 7680.0241 | 7680.0241 | 7680.0241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1035 | WESTON | 70311 | Private | 2036 | 5 | Swales | 66.6667 | 12490.9979 | 0.2 | 0.3 | 19485.9568 |  |  |  |  | 0 | 5199.962 | 5199.962 | 5199.962 | 5199.962 | 5199.962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1036 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 14111.0143 | 0.2 | 0.3 | 22013.1823 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1037 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 26540.5419 | 0.2 | 0.3 | 41403.2454 |  |  |  |  | 0 | 5204.7244 | 5204.7244 | 5204.7244 | 5204.7244 | 5204.7244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1038 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 19409.7611 | 0.2 | 0.3 | 30279.2273 |  |  |  |  | 0 | 9796.9961 | 9796.9961 | 9796.9961 | 9796.9961 | 9796.9961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1039 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 12370.7965 | 0.2 | 0.3 | 19298.4426 |  |  |  |  | 0 | 5206.1896 | 5206.1896 | 5206.1896 | 5206.1896 | 5206.1896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1040 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 21297.1468 | 0.2 | 0.3 | 33223.549 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1041 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 4766.4237 | 0.2 | 0.3 | 7435.6209 |  |  |  |  | 0 | 5204.5123 | 5204.5123 | 5204.5123 | 5204.5123 | 5204.5123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1042 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 19396.7516 | 0.2 | 0.3 | 30258.9325 |  |  |  |  | 0 | 9796.3958 | 9796.3958 | 9796.3958 | 9796.3958 | 9796.3958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1043 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 21926.9479 | 0.2 | 0.3 | 34206.0387 |  |  |  |  | 0 | 5206.579 | 5206.579 | 5206.579 | 5206.579 | 5206.579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1044 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 19152.6165 | 0.2 | 0.3 | 29878.0818 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1045 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 3381.7553 | 0.2 | 0.3 | 5275.5383 |  |  |  |  | 0 | 5205.3087 | 5205.3087 | 5205.3087 | 5205.3087 | 5205.3087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1046 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 3402.2278 | 0.2 | 0.3 | 5307.4754 |  |  |  |  | 0 | 1212.6679 | 1212.6679 | 1212.6679 | 1212.6679 | 1212.6679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1047 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17349.1903 | 0.2 | 0.3 | 27064.7369 |  |  |  |  | 0 | 5204.0042 | 5204.0042 | 5204.0042 | 5204.0042 | 5204.0042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1048 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 8519.4179 | 0.2 | 0.3 | 13290.292 |  |  |  |  | 0 | 7427.238 | 7427.238 | 7427.238 | 7427.238 | 7427.238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1049 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 4889.1699 | 0.2 | 0.3 | 7627.105 |  |  |  |  | 0 | 5203.6338 | 5203.6338 | 5203.6338 | 5203.6338 | 5203.6338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1050 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 23709.9766 | 0.2 | 0.3 | 36987.5635 |  |  |  |  | 0 | 4124.1552 | 4124.1552 | 4124.1552 | 4124.1552 | 4124.1552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1051 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 29857.4105 | 0.2 | 0.3 | 46577.5603 |  |  |  |  | 0 | 2506.7996 | 2506.7996 | 2506.7996 | 2506.7996 | 2506.7996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1052 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 20795.1789 | 0.2 | 0.3 | 32440.479 |  |  |  |  | 0 | 9252.4924 | 9252.4924 | 9252.4924 | 9252.4924 | 9252.4924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1053 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 3603.2752 | 0.2 | 0.3 | 5621.1093 |  |  |  |  | 0 | 9786.4017 | 9786.4017 | 9786.4017 | 9786.4017 | 9786.4017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1054 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 16977.6988 | 0.2 | 0.3 | 26485.2101 |  |  |  |  | 0 | 9783.7224 | 9783.7224 | 9783.7224 | 9783.7224 | 9783.7224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1055 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 17414.2781 | 0.2 | 0.3 | 27166.2738 |  |  |  |  | 0 | 9783.3431 | 9783.3431 | 9783.3431 | 9783.3431 | 9783.3431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1056 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 17656.1203 | 0.2 | 0.3 | 27543.5477 |  |  |  |  | 0 | 9787.5273 | 9787.5273 | 9787.5273 | 9787.5273 | 9787.5273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1057 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 32770.8857 | 0.2 | 0.3 | 51122.5816 |  |  |  |  | 0 | 9787.3295 | 9787.3295 | 9787.3295 | 9787.3295 | 9787.3295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1058 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 7015.227 | 0.2 | 0.3 | 10943.7541 |  |  |  |  | 0 | 8510.7832 | 8510.7832 | 8510.7832 | 8510.7832 | 8510.7832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1059 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17107.2428 | 0.2 | 0.3 | 26687.2988 |  |  |  |  | 0 | 8334.4558 | 8334.4558 | 8334.4558 | 8334.4558 | 8334.4558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1060 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 5755.7523 | 0.2 | 0.3 | 8978.9736 |  |  |  |  | 0 | 8085.3239 | 8085.3239 | 8085.3239 | 8085.3239 | 8085.3239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1061 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 19962.9257 | 0.2 | 0.3 | 31142.1641 |  |  |  |  | 0 | 7881.3167 | 7881.3167 | 7881.3167 | 7881.3167 | 7881.3167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1062 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 11892.8119 | 0.2 | 0.3 | 18552.7866 |  |  |  |  | 0 | 9784.7395 | 9784.7395 | 9784.7395 | 9784.7395 | 9784.7395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1063 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17349.6467 | 0.2 | 0.3 | 27065.4489 |  |  |  |  | 0 | 5204.1652 | 5204.1652 | 5204.1652 | 5204.1652 | 5204.1652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1064 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 14325.3522 | 0.2 | 0.3 | 22347.5494 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1065 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 1143.3126 | 0.2 | 0.3 | 1783.5677 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1066 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 6233.7705 | 0.2 | 0.3 | 9724.682 |  |  |  |  | 0 | 5204.4245 | 5204.4245 | 5204.4245 | 5204.4245 | 5204.4245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1067 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 23141.8611 | 0.2 | 0.3 | 36101.3034 |  |  |  |  | 0 | 9786.4513 | 9786.4513 | 9786.4513 | 9786.4513 | 9786.4513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1068 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 1697.931 | 0.2 | 0.3 | 2648.7724 |  |  |  |  | 0 | 6325.4692 | 6325.4692 | 6325.4692 | 6325.4692 | 6325.4692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1069 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 19116.0849 | 0.2 | 0.3 | 29821.0924 |  |  |  |  | 0 | 6089.2511 | 6089.2511 | 6089.2511 | 6089.2511 | 6089.2511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1070 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 29191.8593 | 0.2 | 0.3 | 45539.3006 |  |  |  |  | 0 | 9786.3216 | 9786.3216 | 9786.3216 | 9786.3216 | 9786.3216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1071 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 3897.6605 | 0.2 | 0.3 | 6080.3504 |  |  |  |  | 0 | 5726.4091 | 5726.4091 | 5726.4091 | 5726.4091 | 5726.4091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1072 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 13920.9996 | 0.2 | 0.3 | 21716.7594 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1073 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17888.0402 | 0.2 | 0.3 | 27905.3427 |  |  |  |  | 0 | 5202.3326 | 5202.3326 | 5202.3326 | 5202.3326 | 5202.3326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1074 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 9133.9981 | 0.2 | 0.3 | 14249.037 |  |  |  |  | 0 | 9483.7451 | 9483.7451 | 9483.7451 | 9483.7451 | 9483.7451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1075 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 18582.5119 | 0.2 | 0.3 | 28988.7185 |  |  |  |  | 0 | 5961.4802 | 5961.4802 | 5961.4802 | 5961.4802 | 5961.4802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1076 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 16668.9225 | 0.2 | 0.3 | 26003.519 |  |  |  |  | 0 | 5204.3422 | 5204.3422 | 5204.3422 | 5204.3422 | 5204.3422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1077 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 31115.6617 | 0.2 | 0.3 | 48540.4323 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1078 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 16776.5413 | 0.2 | 0.3 | 26171.4045 |  |  |  |  | 0 | 5204.6146 | 5204.6146 | 5204.6146 | 5204.6146 | 5204.6146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1079 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 16984.2748 | 0.2 | 0.3 | 26495.4687 |  |  |  |  | 0 | 6760.8689 | 6760.8689 | 6760.8689 | 6760.8689 | 6760.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1080 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 14040.2165 | 0.2 | 0.3 | 21902.7377 |  |  |  |  | 0 | 9784.8775 | 9784.8775 | 9784.8775 | 9784.8775 | 9784.8775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1081 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 16889.3537 | 0.2 | 0.3 | 26347.3917 |  |  |  |  | 0 | 5204.9175 | 5204.9175 | 5204.9175 | 5204.9175 | 5204.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1082 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 19210.3257 | 0.2 | 0.3 | 29968.1081 |  |  |  |  | 0 | 5205.1227 | 5205.1227 | 5205.1227 | 5205.1227 | 5205.1227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1083 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 1641.6428 | 0.2 | 0.3 | 2560.9628 |  |  |  |  | 0 | 7612.9979 | 7612.9979 | 7612.9979 | 7612.9979 | 7612.9979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1084 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 20702.0223 | 0.2 | 0.3 | 32295.1548 |  |  |  |  | 0 | 9797.9186 | 9797.9186 | 9797.9186 | 9797.9186 | 9797.9186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1085 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 20967.8199 | 0.2 | 0.3 | 32709.799 |  |  |  |  | 0 | 5205.2471 | 5205.2471 | 5205.2471 | 5205.2471 | 5205.2471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1086 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 3435.3884 | 0.2 | 0.3 | 5359.2059 |  |  |  |  | 0 | 5205.6091 | 5205.6091 | 5205.6091 | 5205.6091 | 5205.6091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1087 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 2684.4444 | 0.2 | 0.3 | 4187.7333 |  |  |  |  | 0 | 8513.1865 | 8513.1865 | 8513.1865 | 8513.1865 | 8513.1865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1088 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 18018.6207 | 0.2 | 0.3 | 28109.0483 |  |  |  |  | 0 | 8690.0096 | 8690.0096 | 8690.0096 | 8690.0096 | 8690.0096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1089 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 16730.8371 | 0.2 | 0.3 | 26100.1058 |  |  |  |  | 0 | 9784.8726 | 9784.8726 | 9784.8726 | 9784.8726 | 9784.8726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1090 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 23264.301 | 0.2 | 0.3 | 36292.3096 |  |  |  |  | 0 | 9783.2868 | 9783.2868 | 9783.2868 | 9783.2868 | 9783.2868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1091 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 21112.8303 | 0.2 | 0.3 | 32936.0153 |  |  |  |  | 0 | 6568.4065 | 6568.4065 | 6568.4065 | 6568.4065 | 6568.4065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1092 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17221.2451 | 0.2 | 0.3 | 26865.1424 |  |  |  |  | 0 | 11136.8435 | 11136.8435 | 11136.8435 | 11136.8435 | 11136.8435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1093 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17540.8327 | 0.2 | 0.3 | 27363.6991 |  |  |  |  | 0 | 6592.986 | 6592.986 | 6592.986 | 6592.986 | 6592.986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1094 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 7432.7628 | 0.2 | 0.3 | 11595.11 |  |  |  |  | 0 | 5735.7852 | 5735.7852 | 5735.7852 | 5735.7852 | 5735.7852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1095 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 7446.4324 | 0.2 | 0.3 | 11616.4345 |  |  |  |  | 0 | 5204.2028 | 5204.2028 | 5204.2028 | 5204.2028 | 5204.2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1096 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 10502.4893 | 0.2 | 0.3 | 16383.8833 |  |  |  |  | 0 | 5203.8168 | 5203.8168 | 5203.8168 | 5203.8168 | 5203.8168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1097 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 16400.3331 | 0.2 | 0.3 | 25584.5197 |  |  |  |  | 0 | 5204.2454 | 5204.2454 | 5204.2454 | 5204.2454 | 5204.2454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1098 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 16953.8232 | 0.2 | 0.3 | 26447.9642 |  |  |  |  | 0 | 5204.0637 | 5204.0637 | 5204.0637 | 5204.0637 | 5204.0637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1099 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 699.4384 | 0.2 | 0.3 | 1091.1239 |  |  |  |  | 0 | 5202.7211 | 5202.7211 | 5202.7211 | 5202.7211 | 5202.7211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1100 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 13862.4186 | 0.2 | 0.3 | 21625.373 |  |  |  |  | 0 | 5845.042 | 5845.042 | 5845.042 | 5845.042 | 5845.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1101 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 8308.2195 | 0.2 | 0.3 | 12960.8224 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1102 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 4013.6914 | 0.2 | 0.3 | 6261.3586 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1103 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 15287.1584 | 0.2 | 0.3 | 23847.9671 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1104 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 16501.7535 | 0.2 | 0.3 | 25742.7355 |  |  |  |  | 0 | 7771.4889 | 7771.4889 | 7771.4889 | 7771.4889 | 7771.4889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1105 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17089.4383 | 0.2 | 0.3 | 26659.5238 |  |  |  |  | 0 | 9785.6529 | 9785.6529 | 9785.6529 | 9785.6529 | 9785.6529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1106 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 3861.9629 | 0.2 | 0.3 | 6024.6622 |  |  |  |  | 0 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1107 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 18582.3018 | 0.2 | 0.3 | 28988.3908 |  |  |  |  | 0 | 5205.0665 | 5205.0665 | 5205.0665 | 5205.0665 | 5205.0665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1108 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 31432.4722 | 0.2 | 0.3 | 49034.6566 |  |  |  |  | 0 | 9784.4414 | 9784.4414 | 9784.4414 | 9784.4414 | 9784.4414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1109 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 1669.7531 | 0.2 | 0.3 | 2604.8148 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1110 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 32970.0023 | 0.2 | 0.3 | 51433.2035 |  |  |  |  | 0 | 5203.0858 | 5203.0858 | 5203.0858 | 5203.0858 | 5203.0858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1111 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 15725.884 | 0.2 | 0.3 | 24532.379 |  |  |  |  | 0 | 5203.1439 | 5203.1439 | 5203.1439 | 5203.1439 | 5203.1439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1112 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 10972.5481 | 0.2 | 0.3 | 17117.1751 |  |  |  |  | 0 | 9784.9646 | 9784.9646 | 9784.9646 | 9784.9646 | 9784.9646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1113 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 6687.9413 | 0.2 | 0.3 | 10433.1885 |  |  |  |  | 0 | 5160.726 | 5160.726 | 5160.726 | 5160.726 | 5160.726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1114 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 12578.5643 | 0.2 | 0.3 | 19622.5603 |  |  |  |  | 0 | 5091.6159 | 5091.6159 | 5091.6159 | 5091.6159 | 5091.6159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1115 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 22184.8191 | 0.2 | 0.3 | 34608.3178 |  |  |  |  | 0 | 5274.4363 | 5274.4363 | 5274.4363 | 5274.4363 | 5274.4363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1116 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 25992.3397 | 0.2 | 0.3 | 40548.05 |  |  |  |  | 0 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1117 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 24638.7633 | 0.2 | 0.3 | 38436.4707 |  |  |  |  | 0 | 5205.2117 | 5205.2117 | 5205.2117 | 5205.2117 | 5205.2117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1118 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 16712.5702 | 0.2 | 0.3 | 26071.6095 |  |  |  |  | 0 | 8305.7478 | 8305.7478 | 8305.7478 | 8305.7478 | 8305.7478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1119 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 16808.5313 | 0.2 | 0.3 | 26221.3089 |  |  |  |  | 0 | 6503.9393 | 6503.9393 | 6503.9393 | 6503.9393 | 6503.9393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1120 | SUNRISE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 17516.4029 | 0.2 | 0.3 | 27325.5886 |  |  |  |  | 0 | 5204.9649 | 5204.9649 | 5204.9649 | 5204.9649 | 5204.9649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1121 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 23922.6357 | 0.2 | 0.3 | 37319.3116 |  |  |  |  | 0 | 5205.0946 | 5205.0946 | 5205.0946 | 5205.0946 | 5205.0946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1122 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 21676.4777 | 0.2 | 0.3 | 33815.3053 |  |  |  |  | 0 | 7722.9641 | 7722.9641 | 7722.9641 | 7722.9641 | 7722.9641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1123 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 249.3065 | 0.2 | 0.3 | 388.9181 |  |  |  |  | 0 | 6677.8008 | 6677.8008 | 6677.8008 | 6677.8008 | 6677.8008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1124 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 7359.9671 | 0.2 | 0.3 | 11481.5487 |  |  |  |  | 0 | 5206.2835 | 5206.2835 | 5206.2835 | 5206.2835 | 5206.2835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1125 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 11163.7337 | 0.2 | 0.3 | 17415.4245 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1126 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 18826.5223 | 0.2 | 0.3 | 29369.3748 |  |  |  |  | 0 | 7999.0236 | 7999.0236 | 7999.0236 | 7999.0236 | 7999.0236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1127 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 4108.2814 | 0.2 | 0.3 | 6408.919 |  |  |  |  | 0 | 5204.701 | 5204.701 | 5204.701 | 5204.701 | 5204.701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1128 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17443.2023 | 0.2 | 0.3 | 27211.3955 |  |  |  |  | 0 | 5204.211 | 5204.211 | 5204.211 | 5204.211 | 5204.211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1129 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 7108.9415 | 0.2 | 0.3 | 11089.9487 |  |  |  |  | 0 | 6973.1034 | 6973.1034 | 6973.1034 | 6973.1034 | 6973.1034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1130 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 16714.6479 | 0.2 | 0.3 | 26074.8507 |  |  |  |  | 0 | 5204.2871 | 5204.2871 | 5204.2871 | 5204.2871 | 5204.2871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1131 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 16741.8985 | 0.2 | 0.3 | 26117.3616 |  |  |  |  | 0 | 5204.7115 | 5204.7115 | 5204.7115 | 5204.7115 | 5204.7115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1132 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 14210.3877 | 0.2 | 0.3 | 22168.2048 |  |  |  |  | 0 | 6243.8622 | 6243.8622 | 6243.8622 | 6243.8622 | 6243.8622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1133 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 28731.884 | 0.2 | 0.3 | 44821.739 |  |  |  |  | 0 | 5204.435 | 5204.435 | 5204.435 | 5204.435 | 5204.435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1134 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 19652.3658 | 0.2 | 0.3 | 30657.6906 |  |  |  |  | 0 | 5205.9039 | 5205.9039 | 5205.9039 | 5205.9039 | 5205.9039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1135 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 24252.3677 | 0.2 | 0.3 | 37833.6937 |  |  |  |  | 0 | 5204.1673 | 5204.1673 | 5204.1673 | 5204.1673 | 5204.1673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1136 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 28291.1911 | 0.2 | 0.3 | 44134.2582 |  |  |  |  | 0 | 5203.7154 | 5203.7154 | 5203.7154 | 5203.7154 | 5203.7154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1137 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 6827.8476 | 0.2 | 0.3 | 10651.4423 |  |  |  |  | 0 | 5204.0541 | 5204.0541 | 5204.0541 | 5204.0541 | 5204.0541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1138 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 1615.968 | 0.2 | 0.3 | 2520.9101 |  |  |  |  | 0 | 5204.0985 | 5204.0985 | 5204.0985 | 5204.0985 | 5204.0985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1139 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 27430.1905 | 0.2 | 0.3 | 42791.0971 |  |  |  |  | 0 | 5201.7319 | 5201.7319 | 5201.7319 | 5201.7319 | 5201.7319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1140 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 8318.8511 | 0.2 | 0.3 | 12977.4078 |  |  |  |  | 0 | 5206.0626 | 5206.0626 | 5206.0626 | 5206.0626 | 5206.0626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1141 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 18612.7391 | 0.2 | 0.3 | 29035.8729 |  |  |  |  | 0 | 8361.2266 | 8361.2266 | 8361.2266 | 8361.2266 | 8361.2266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1142 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 10069.3299 | 0.2 | 0.3 | 15708.1547 |  |  |  |  | 0 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1143 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 18442.4626 | 0.2 | 0.3 | 28770.2417 |  |  |  |  | 0 | 5205.0044 | 5205.0044 | 5205.0044 | 5205.0044 | 5205.0044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1144 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17664.1993 | 0.2 | 0.3 | 27556.1509 |  |  |  |  | 0 | 9782.5756 | 9782.5756 | 9782.5756 | 9782.5756 | 9782.5756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1145 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17331.3734 | 0.2 | 0.3 | 27036.9425 |  |  |  |  | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1146 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 5830.5409 | 0.2 | 0.3 | 9095.6438 |  |  |  |  | 0 | 5202.9734 | 5202.9734 | 5202.9734 | 5202.9734 | 5202.9734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1147 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 27991.7474 | 0.2 | 0.3 | 43667.1259 |  |  |  |  | 0 | 5202.9232 | 5202.9232 | 5202.9232 | 5202.9232 | 5202.9232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1148 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 10076.0379 | 0.2 | 0.3 | 15718.6191 |  |  |  |  | 0 | 9784.3218 | 9784.3218 | 9784.3218 | 9784.3218 | 9784.3218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1149 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 15230.5886 | 0.2 | 0.3 | 23759.7182 |  |  |  |  | 0 | 1017.2404 | 1017.2404 | 1017.2404 | 1017.2404 | 1017.2404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1150 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 13088.8001 | 0.2 | 0.3 | 20418.5281 |  |  |  |  | 0 | 2950.761 | 2950.761 | 2950.761 | 2950.761 | 2950.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1151 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 16741.5233 | 0.2 | 0.3 | 26116.7763 |  |  |  |  | 0 | 5053.824 | 5053.824 | 5053.824 | 5053.824 | 5053.824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1152 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 16739.8987 | 0.2 | 0.3 | 26114.2419 |  |  |  |  | 0 | 7261.9038 | 7261.9038 | 7261.9038 | 7261.9038 | 7261.9038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1153 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 19376.6486 | 0.2 | 0.3 | 30227.5718 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1154 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17584.5864 | 0.2 | 0.3 | 27431.9548 |  |  |  |  | 0 | 5204.5405 | 5204.5405 | 5204.5405 | 5204.5405 | 5204.5405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1155 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17332.9289 | 0.2 | 0.3 | 27039.369 |  |  |  |  | 0 | 8537.5001 | 8537.5001 | 8537.5001 | 8537.5001 | 8537.5001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1156 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 15485.3435 | 0.2 | 0.3 | 24157.1358 |  |  |  |  | 0 | 6275.6852 | 6275.6852 | 6275.6852 | 6275.6852 | 6275.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1157 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 36495.1241 | 0.2 | 0.3 | 56932.3935 |  |  |  |  | 0 | 5205.0339 | 5205.0339 | 5205.0339 | 5205.0339 | 5205.0339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1158 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 2772.0626 | 0.2 | 0.3 | 4324.4177 |  |  |  |  | 0 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1159 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 1914.0231 | 0.2 | 0.3 | 2985.8761 |  |  |  |  | 0 | 7954.6258 | 7954.6258 | 7954.6258 | 7954.6258 | 7954.6258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1160 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 21087.3971 | 0.2 | 0.3 | 32896.3395 |  |  |  |  | 0 | 6975.4938 | 6975.4938 | 6975.4938 | 6975.4938 | 6975.4938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1161 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 16896.2414 | 0.2 | 0.3 | 26358.1366 |  |  |  |  | 0 | 5204.387 | 5204.387 | 5204.387 | 5204.387 | 5204.387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1162 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17372.2433 | 0.2 | 0.3 | 27100.6996 |  |  |  |  | 0 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1163 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 26906.9613 | 0.2 | 0.3 | 41974.8596 |  |  |  |  | 0 | 8256.0838 | 8256.0838 | 8256.0838 | 8256.0838 | 8256.0838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1164 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 5027.1951 | 0.2 | 0.3 | 7842.4243 |  |  |  |  | 0 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1165 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 9513.2053 | 0.2 | 0.3 | 14840.6003 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1166 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 5471.7275 | 0.2 | 0.3 | 8535.895 |  |  |  |  | 0 | 6751.1219 | 6751.1219 | 6751.1219 | 6751.1219 | 6751.1219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1167 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 3983.6908 | 0.2 | 0.3 | 6214.5576 |  |  |  |  | 0 | 5204.1666 | 5204.1666 | 5204.1666 | 5204.1666 | 5204.1666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1168 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 27807.6239 | 0.2 | 0.3 | 43379.8933 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1169 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 16744.2441 | 0.2 | 0.3 | 26121.0208 |  |  |  |  | 0 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1170 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 14330.0923 | 0.2 | 0.3 | 22354.944 |  |  |  |  | 0 | 5204.4008 | 5204.4008 | 5204.4008 | 5204.4008 | 5204.4008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1171 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 13124.5107 | 0.2 | 0.3 | 20474.2366 |  |  |  |  | 0 | 9785.5124 | 9785.5124 | 9785.5124 | 9785.5124 | 9785.5124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1172 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 23627.8801 | 0.2 | 0.3 | 36859.493 |  |  |  |  | 0 | 9783.848 | 9783.848 | 9783.848 | 9783.848 | 9783.848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1173 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 23652.5243 | 0.2 | 0.3 | 36897.938 |  |  |  |  | 0 | 9784.5469 | 9784.5469 | 9784.5469 | 9784.5469 | 9784.5469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1174 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 2910.3681 | 0.2 | 0.3 | 4540.1743 |  |  |  |  | 0 | 9784.7521 | 9784.7521 | 9784.7521 | 9784.7521 | 9784.7521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1175 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 9914.1393 | 0.2 | 0.3 | 15466.0574 |  |  |  |  | 0 | 9787.4264 | 9787.4264 | 9787.4264 | 9787.4264 | 9787.4264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1176 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 21856.0925 | 0.2 | 0.3 | 34095.5044 |  |  |  |  | 0 | 7088.7549 | 7088.7549 | 7088.7549 | 7088.7549 | 7088.7549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1177 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 12738.6565 | 0.2 | 0.3 | 19872.3041 |  |  |  |  | 0 | 5204.5048 | 5204.5048 | 5204.5048 | 5204.5048 | 5204.5048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1178 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 2399.8146 | 0.2 | 0.3 | 3743.7108 |  |  |  |  | 0 | 8154.6791 | 8154.6791 | 8154.6791 | 8154.6791 | 8154.6791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1179 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 7633.3181 | 0.2 | 0.3 | 11907.9763 |  |  |  |  | 0 | 5204.211 | 5204.211 | 5204.211 | 5204.211 | 5204.211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1180 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 25063.8395 | 0.2 | 0.3 | 39099.5896 |  |  |  |  | 0 | 5204.1731 | 5204.1731 | 5204.1731 | 5204.1731 | 5204.1731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1181 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 19812.6937 | 0.2 | 0.3 | 30907.8022 |  |  |  |  | 0 | 9784.27 | 9784.27 | 9784.27 | 9784.27 | 9784.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1182 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 13876.1715 | 0.2 | 0.3 | 21646.8276 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1183 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 8144.0389 | 0.2 | 0.3 | 12704.7006 |  |  |  |  | 0 | 9786.6172 | 9786.6172 | 9786.6172 | 9786.6172 | 9786.6172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1184 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 21682.4197 | 0.2 | 0.3 | 33824.5748 |  |  |  |  | 0 | 1603.7192 | 1603.7192 | 1603.7192 | 1603.7192 | 1603.7192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1185 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 19236.2887 | 0.2 | 0.3 | 30008.6104 |  |  |  |  | 0 | 1590.2504 | 1590.2504 | 1590.2504 | 1590.2504 | 1590.2504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1186 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 20869.2029 | 0.2 | 0.3 | 32555.9566 |  |  |  |  | 0 | 9827.4441 | 9827.4441 | 9827.4441 | 9827.4441 | 9827.4441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1187 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 45461.1075 | 0.2 | 0.3 | 70919.3278 |  |  |  |  | 0 | 7480.3618 | 7480.3618 | 7480.3618 | 7480.3618 | 7480.3618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1188 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 12659.8549 | 0.2 | 0.3 | 19749.3736 |  |  |  |  | 0 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1189 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 254.4252 | 0.2 | 0.3 | 396.9033 |  |  |  |  | 0 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1190 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 3700.6691 | 0.2 | 0.3 | 5773.0438 |  |  |  |  | 0 | 8176.065 | 8176.065 | 8176.065 | 8176.065 | 8176.065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1191 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 11484.1513 | 0.2 | 0.3 | 17915.2761 |  |  |  |  | 0 | 9789.4462 | 9789.4462 | 9789.4462 | 9789.4462 | 9789.4462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1192 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17181.2944 | 0.2 | 0.3 | 26802.8193 |  |  |  |  | 0 | 5206.2873 | 5206.2873 | 5206.2873 | 5206.2873 | 5206.2873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1193 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 31006.2864 | 0.2 | 0.3 | 48369.8068 |  |  |  |  | 0 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1194 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 2889.8377 | 0.2 | 0.3 | 4508.1469 |  |  |  |  | 0 | 8112.6563 | 8112.6563 | 8112.6563 | 8112.6563 | 8112.6563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1195 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 9412.1021 | 0.2 | 0.3 | 14682.8793 |  |  |  |  | 0 | 6740.4983 | 6740.4983 | 6740.4983 | 6740.4983 | 6740.4983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1196 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 7839.9357 | 0.2 | 0.3 | 12230.2997 |  |  |  |  | 0 | 5204.3889 | 5204.3889 | 5204.3889 | 5204.3889 | 5204.3889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1197 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 16774.5162 | 0.2 | 0.3 | 26168.2453 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1198 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 16832.739 | 0.2 | 0.3 | 26259.0728 |  |  |  |  | 0 | 8457.493 | 8457.493 | 8457.493 | 8457.493 | 8457.493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1199 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17284.7925 | 0.2 | 0.3 | 26964.2764 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1200 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 9069.897 | 0.2 | 0.3 | 14149.0393 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1201 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 21905.7481 | 0.2 | 0.3 | 34172.967 |  |  |  |  | 0 | 6466.4411 | 6466.4411 | 6466.4411 | 6466.4411 | 6466.4411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1202 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 21727.9771 | 0.2 | 0.3 | 33895.6443 |  |  |  |  | 0 | 5205.4674 | 5205.4674 | 5205.4674 | 5205.4674 | 5205.4674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1203 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 1545.4801 | 0.2 | 0.3 | 2410.949 |  |  |  |  | 0 | 4543.8824 | 4543.8824 | 4543.8824 | 4543.8824 | 4543.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1204 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 20152.4637 | 0.2 | 0.3 | 31437.8433 |  |  |  |  | 0 | 5203.9803 | 5203.9803 | 5203.9803 | 5203.9803 | 5203.9803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1205 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 23376.4722 | 0.2 | 0.3 | 36467.2966 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1206 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 16859.2083 | 0.2 | 0.3 | 26300.365 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1207 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 2985.6439 | 0.2 | 0.3 | 4657.6044 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1208 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 33339.8109 | 0.2 | 0.3 | 52010.1051 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1209 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 3444.8077 | 0.2 | 0.3 | 5373.9 |  |  |  |  | 0 | 5205.9503 | 5205.9503 | 5205.9503 | 5205.9503 | 5205.9503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1210 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 18731.476 | 0.2 | 0.3 | 29221.1026 |  |  |  |  | 0 | 5204.8501 | 5204.8501 | 5204.8501 | 5204.8501 | 5204.8501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1211 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 2133.8157 | 0.2 | 0.3 | 3328.7525 |  |  |  |  | 0 | 7931.6686 | 7931.6686 | 7931.6686 | 7931.6686 | 7931.6686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1212 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 15145.8035 | 0.2 | 0.3 | 23627.4535 |  |  |  |  | 0 | 5205.1012 | 5205.1012 | 5205.1012 | 5205.1012 | 5205.1012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1213 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 22565.9378 | 0.2 | 0.3 | 35202.863 |  |  |  |  | 0 | 5205.1941 | 5205.1941 | 5205.1941 | 5205.1941 | 5205.1941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1214 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 24537.0607 | 0.2 | 0.3 | 38277.8146 |  |  |  |  | 0 | 9784.6109 | 9784.6109 | 9784.6109 | 9784.6109 | 9784.6109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1215 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 21659.9508 | 0.2 | 0.3 | 33789.5232 |  |  |  |  | 0 | 9780.7702 | 9780.7702 | 9780.7702 | 9780.7702 | 9780.7702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1216 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 9535.3071 | 0.2 | 0.3 | 14875.0791 |  |  |  |  | 0 | 9656.7205 | 9656.7205 | 9656.7205 | 9656.7205 | 9656.7205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1217 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17272.8561 | 0.2 | 0.3 | 26945.6555 |  |  |  |  | 0 | 5205.1579 | 5205.1579 | 5205.1579 | 5205.1579 | 5205.1579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1218 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 18716.5193 | 0.2 | 0.3 | 29197.7701 |  |  |  |  | 0 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1219 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 6821.1117 | 0.2 | 0.3 | 10640.9342 |  |  |  |  | 0 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1220 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 5.5563 | 0.2 | 0.3 | 8.6679 |  |  |  |  | 0 | 5206.1727 | 5206.1727 | 5206.1727 | 5206.1727 | 5206.1727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1221 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 22395.7917 | 0.2 | 0.3 | 34937.435 |  |  |  |  | 0 | 9797.658 | 9797.658 | 9797.658 | 9797.658 | 9797.658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1222 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 3286.7744 | 0.2 | 0.3 | 5127.3681 |  |  |  |  | 0 | 5204.549 | 5204.549 | 5204.549 | 5204.549 | 5204.549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1223 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 21801.2432 | 0.2 | 0.3 | 34009.9394 |  |  |  |  | 0 | 5204.334 | 5204.334 | 5204.334 | 5204.334 | 5204.334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1224 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 16443.5135 | 0.2 | 0.3 | 25651.881 |  |  |  |  | 0 | 8394.4005 | 8394.4005 | 8394.4005 | 8394.4005 | 8394.4005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1225 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 23889.6915 | 0.2 | 0.3 | 37267.9188 |  |  |  |  | 0 | 5967.2111 | 5967.2111 | 5967.2111 | 5967.2111 | 5967.2111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1226 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 16797.2239 | 0.2 | 0.3 | 26203.6693 |  |  |  |  | 0 | 5266.9601 | 5266.9601 | 5266.9601 | 5266.9601 | 5266.9601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1227 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 19521.7645 | 0.2 | 0.3 | 30453.9527 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1228 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 19718.2673 | 0.2 | 0.3 | 30760.4969 |  |  |  |  | 0 | 8682.4433 | 8682.4433 | 8682.4433 | 8682.4433 | 8682.4433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1229 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 713.758 | 0.2 | 0.3 | 1113.4625 |  |  |  |  | 0 | 5204.705 | 5204.705 | 5204.705 | 5204.705 | 5204.705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1230 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 28719.2955 | 0.2 | 0.3 | 44802.101 |  |  |  |  | 0 | 5204.056 | 5204.056 | 5204.056 | 5204.056 | 5204.056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1231 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 594.5157 | 0.2 | 0.3 | 927.4444 |  |  |  |  | 0 | 6254.6683 | 6254.6683 | 6254.6683 | 6254.6683 | 6254.6683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1232 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 29621.8558 | 0.2 | 0.3 | 46210.095 |  |  |  |  | 0 | 5205.8235 | 5205.8235 | 5205.8235 | 5205.8235 | 5205.8235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1233 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 10979.3971 | 0.2 | 0.3 | 17127.8595 |  |  |  |  | 0 | 6511.6945 | 6511.6945 | 6511.6945 | 6511.6945 | 6511.6945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1234 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 5130.7976 | 0.2 | 0.3 | 8004.0443 |  |  |  |  | 0 | 2128.8087 | 2128.8087 | 2128.8087 | 2128.8087 | 2128.8087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1235 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17573.5891 | 0.2 | 0.3 | 27414.799 |  |  |  |  | 0 | 5923.4216 | 5923.4216 | 5923.4216 | 5923.4216 | 5923.4216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1236 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 16891.4582 | 0.2 | 0.3 | 26350.6748 |  |  |  |  | 0 | 9780.8635 | 9780.8635 | 9780.8635 | 9780.8635 | 9780.8635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1237 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 18532.8189 | 0.2 | 0.3 | 28911.1974 |  |  |  |  | 0 | 6296.6387 | 6296.6387 | 6296.6387 | 6296.6387 | 6296.6387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1238 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 1109.4369 | 0.2 | 0.3 | 1730.7216 |  |  |  |  | 0 | 4549.1819 | 4549.1819 | 4549.1819 | 4549.1819 | 4549.1819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1239 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 15630.9947 | 0.2 | 0.3 | 24384.3517 |  |  |  |  | 0 | 6607.4715 | 6607.4715 | 6607.4715 | 6607.4715 | 6607.4715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1240 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 14014.3437 | 0.2 | 0.3 | 21862.3761 |  |  |  |  | 0 | 5203.7982 | 5203.7982 | 5203.7982 | 5203.7982 | 5203.7982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1241 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 16835.4181 | 0.2 | 0.3 | 26263.2523 |  |  |  |  | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1242 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 18891.3125 | 0.2 | 0.3 | 29470.4476 |  |  |  |  | 0 | 5421.6099 | 5421.6099 | 5421.6099 | 5421.6099 | 5421.6099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1243 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17518.9808 | 0.2 | 0.3 | 27329.61 |  |  |  |  | 0 | 486.1268 | 486.1268 | 486.1268 | 486.1268 | 486.1268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1244 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 30692.8053 | 0.2 | 0.3 | 47880.7762 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1245 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 22371.239 | 0.2 | 0.3 | 34899.1328 |  |  |  |  | 0 | 9787.7191 | 9787.7191 | 9787.7191 | 9787.7191 | 9787.7191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1246 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 19755.9431 | 0.2 | 0.3 | 30819.2713 |  |  |  |  | 0 | 5203.424 | 5203.424 | 5203.424 | 5203.424 | 5203.424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1247 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 3670.3117 | 0.2 | 0.3 | 5725.6863 |  |  |  |  | 0 | 5203.6289 | 5203.6289 | 5203.6289 | 5203.6289 | 5203.6289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1248 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 23037.6131 | 0.2 | 0.3 | 35938.6765 |  |  |  |  | 0 | 6547.2228 | 6547.2228 | 6547.2228 | 6547.2228 | 6547.2228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1249 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 27070.1147 | 0.2 | 0.3 | 42229.3789 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1250 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 5730.5717 | 0.2 | 0.3 | 8939.6918 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1251 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 21989.9761 | 0.2 | 0.3 | 34304.3627 |  |  |  |  | 0 | 5207.7416 | 5207.7416 | 5207.7416 | 5207.7416 | 5207.7416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1252 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 18092.6388 | 0.2 | 0.3 | 28224.5165 |  |  |  |  | 0 | 5205.7797 | 5205.7797 | 5205.7797 | 5205.7797 | 5205.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1253 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 4213.3691 | 0.2 | 0.3 | 6572.8558 |  |  |  |  | 0 | 5206.3768 | 5206.3768 | 5206.3768 | 5206.3768 | 5206.3768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1254 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 23203.9141 | 0.2 | 0.3 | 36198.1059 |  |  |  |  | 0 | 5205.7797 | 5205.7797 | 5205.7797 | 5205.7797 | 5205.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1255 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 9851.5214 | 0.2 | 0.3 | 15368.3734 |  |  |  |  | 0 | 5206.3768 | 5206.3768 | 5206.3768 | 5206.3768 | 5206.3768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1256 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 14429.6755 | 0.2 | 0.3 | 22510.2938 |  |  |  |  | 0 | 5206.8886 | 5206.8886 | 5206.8886 | 5206.8886 | 5206.8886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1257 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 18255.4501 | 0.2 | 0.3 | 28478.5022 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1258 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 19176.4763 | 0.2 | 0.3 | 29915.303 |  |  |  |  | 0 | 5208.3387 | 5208.3387 | 5208.3387 | 5208.3387 | 5208.3387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1259 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 28400.5013 | 0.2 | 0.3 | 44304.7821 |  |  |  |  | 0 | 5208.3387 | 5208.3387 | 5208.3387 | 5208.3387 | 5208.3387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1260 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 679.3047 | 0.2 | 0.3 | 1059.7154 |  |  |  |  | 0 | 5207.2298 | 5207.2298 | 5207.2298 | 5207.2298 | 5207.2298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1261 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 22613.4053 | 0.2 | 0.3 | 35276.9122 |  |  |  |  | 0 | 5206.8033 | 5206.8033 | 5206.8033 | 5206.8033 | 5206.8033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1262 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 1270.3914 | 0.2 | 0.3 | 1981.8106 |  |  |  |  | 0 | 5210.9491 | 5210.9491 | 5210.9491 | 5210.9491 | 5210.9491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1263 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 11020.0221 | 0.2 | 0.3 | 17191.2344 |  |  |  |  | 0 | 5205.9977 | 5205.9977 | 5205.9977 | 5205.9977 | 5205.9977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1264 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 8156.4785 | 0.2 | 0.3 | 12724.1065 |  |  |  |  | 0 | 5202.485 | 5202.485 | 5202.485 | 5202.485 | 5202.485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1265 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 3276.8355 | 0.2 | 0.3 | 5111.8634 |  |  |  |  | 0 | 5202.5446 | 5202.5446 | 5202.5446 | 5202.5446 | 5202.5446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1266 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 12108.8381 | 0.2 | 0.3 | 18889.7875 |  |  |  |  | 0 | 5201.6945 | 5201.6945 | 5201.6945 | 5201.6945 | 5201.6945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1267 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 23295.7967 | 0.2 | 0.3 | 36341.4428 |  |  |  |  | 0 | 5204.6356 | 5204.6356 | 5204.6356 | 5204.6356 | 5204.6356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1268 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 20752.4869 | 0.2 | 0.3 | 32373.8795 |  |  |  |  | 0 | 6408.5372 | 6408.5372 | 6408.5372 | 6408.5372 | 6408.5372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1269 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 3429.4187 | 0.2 | 0.3 | 5349.8932 |  |  |  |  | 0 | 5201.5624 | 5201.5624 | 5201.5624 | 5201.5624 | 5201.5624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1270 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 6155.8979 | 0.2 | 0.3 | 9603.2008 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1271 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 26049.4071 | 0.2 | 0.3 | 40637.0751 |  |  |  |  | 0 | 8403.4399 | 8403.4399 | 8403.4399 | 8403.4399 | 8403.4399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1272 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 2381.9033 | 0.2 | 0.3 | 3715.7691 |  |  |  |  | 0 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1273 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17302.1846 | 0.2 | 0.3 | 26991.408 |  |  |  |  | 0 | 5177.7303 | 5177.7303 | 5177.7303 | 5177.7303 | 5177.7303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1274 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 15406.1026 | 0.2 | 0.3 | 24033.5201 |  |  |  |  | 0 | 5204.7268 | 5204.7268 | 5204.7268 | 5204.7268 | 5204.7268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1275 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 22043.9221 | 0.2 | 0.3 | 34388.5184 |  |  |  |  | 0 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1276 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 14075.5503 | 0.2 | 0.3 | 21957.8585 |  |  |  |  | 0 | 5296.3815 | 5296.3815 | 5296.3815 | 5296.3815 | 5296.3815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1277 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 13946.2884 | 0.2 | 0.3 | 21756.2099 |  |  |  |  | 0 | 4050.9621 | 4050.9621 | 4050.9621 | 4050.9621 | 4050.9621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1278 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 22386.7446 | 0.2 | 0.3 | 34923.3216 |  |  |  |  | 0 | 9357.5833 | 9357.5833 | 9357.5833 | 9357.5833 | 9357.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1279 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 10989.106 | 0.2 | 0.3 | 17143.0054 |  |  |  |  | 0 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1280 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17312.311 | 0.2 | 0.3 | 27007.2052 |  |  |  |  | 0 | 9785.3019 | 9785.3019 | 9785.3019 | 9785.3019 | 9785.3019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1281 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17310.8547 | 0.2 | 0.3 | 27004.9333 |  |  |  |  | 0 | 5203.6145 | 5203.6145 | 5203.6145 | 5203.6145 | 5203.6145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1282 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 26087.4976 | 0.2 | 0.3 | 40696.4963 |  |  |  |  | 0 | 5203.7177 | 5203.7177 | 5203.7177 | 5203.7177 | 5203.7177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1283 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 20518.173 | 0.2 | 0.3 | 32008.3499 |  |  |  |  | 0 | 6797.8325 | 6797.8325 | 6797.8325 | 6797.8325 | 6797.8325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1284 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 451.0695 | 0.2 | 0.3 | 703.6685 |  |  |  |  | 0 | 5204.5764 | 5204.5764 | 5204.5764 | 5204.5764 | 5204.5764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1285 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 24753.4838 | 0.2 | 0.3 | 38615.4347 |  |  |  |  | 0 | 5202.4994 | 5202.4994 | 5202.4994 | 5202.4994 | 5202.4994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1286 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 22385.0362 | 0.2 | 0.3 | 34920.6565 |  |  |  |  | 0 | 8302.9955 | 8302.9955 | 8302.9955 | 8302.9955 | 8302.9955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1287 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 2910.4789 | 0.2 | 0.3 | 4540.3471 |  |  |  |  | 0 | 8425.5983 | 8425.5983 | 8425.5983 | 8425.5983 | 8425.5983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1288 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 25617.4662 | 0.2 | 0.3 | 39963.2473 |  |  |  |  | 0 | 5249.2994 | 5249.2994 | 5249.2994 | 5249.2994 | 5249.2994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1289 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 20026.6367 | 0.2 | 0.3 | 31241.5532 |  |  |  |  | 0 | 9787.0307 | 9787.0307 | 9787.0307 | 9787.0307 | 9787.0307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1290 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 1766.7487 | 0.2 | 0.3 | 2756.128 |  |  |  |  | 0 | 9785.9201 | 9785.9201 | 9785.9201 | 9785.9201 | 9785.9201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1291 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 21061.8238 | 0.2 | 0.3 | 32856.4451 |  |  |  |  | 0 | 9787.7389 | 9787.7389 | 9787.7389 | 9787.7389 | 9787.7389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1292 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 16725.1101 | 0.2 | 0.3 | 26091.1717 |  |  |  |  | 0 | 9786.7001 | 9786.7001 | 9786.7001 | 9786.7001 | 9786.7001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1293 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 28188.1526 | 0.2 | 0.3 | 43973.5181 |  |  |  |  | 0 | 9785.833 | 9785.833 | 9785.833 | 9785.833 | 9785.833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1294 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 7046.3285 | 0.2 | 0.3 | 10992.2724 |  |  |  |  | 0 | 9789.4876 | 9789.4876 | 9789.4876 | 9789.4876 | 9789.4876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1295 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 26357.0225 | 0.2 | 0.3 | 41116.9552 |  |  |  |  | 0 | 9789.2756 | 9789.2756 | 9789.2756 | 9789.2756 | 9789.2756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1296 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 8481.3007 | 0.2 | 0.3 | 13230.8291 |  |  |  |  | 0 | 9786.5273 | 9786.5273 | 9786.5273 | 9786.5273 | 9786.5273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1297 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 25211.2901 | 0.2 | 0.3 | 39329.6126 |  |  |  |  | 0 | 9786.7686 | 9786.7686 | 9786.7686 | 9786.7686 | 9786.7686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1298 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 18646.1087 | 0.2 | 0.3 | 29087.9296 |  |  |  |  | 0 | 9788.2626 | 9788.2626 | 9788.2626 | 9788.2626 | 9788.2626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1299 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 7718.6163 | 0.2 | 0.3 | 12041.0414 |  |  |  |  | 0 | 8648.609 | 8648.609 | 8648.609 | 8648.609 | 8648.609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1300 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17111.8813 | 0.2 | 0.3 | 26694.5348 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1301 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 15400.0911 | 0.2 | 0.3 | 24024.1422 |  |  |  |  | 0 | 5202.646 | 5202.646 | 5202.646 | 5202.646 | 5202.646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1302 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 20967.0426 | 0.2 | 0.3 | 32708.5865 |  |  |  |  | 0 | 5201.7067 | 5201.7067 | 5201.7067 | 5201.7067 | 5201.7067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1303 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 2115.1293 | 0.2 | 0.3 | 3299.6017 |  |  |  |  | 0 | 5201.5278 | 5201.5278 | 5201.5278 | 5201.5278 | 5201.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1304 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 7478.8857 | 0.2 | 0.3 | 11667.0616 |  |  |  |  | 0 | 5427.6848 | 5427.6848 | 5427.6848 | 5427.6848 | 5427.6848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1305 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 21076.3577 | 0.2 | 0.3 | 32879.118 |  |  |  |  | 0 | 3578.5864 | 3578.5864 | 3578.5864 | 3578.5864 | 3578.5864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1306 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 1649.4113 | 0.2 | 0.3 | 2573.0817 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1307 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 20419.1729 | 0.2 | 0.3 | 31853.9098 |  |  |  |  | 0 | 8920.6163 | 8920.6163 | 8920.6163 | 8920.6163 | 8920.6163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1308 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17388.5447 | 0.2 | 0.3 | 27126.1298 |  |  |  |  | 0 | 2714.7209 | 2714.7209 | 2714.7209 | 2714.7209 | 2714.7209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1309 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 4143.1123 | 0.2 | 0.3 | 6463.2551 |  |  |  |  | 0 | 6058.2343 | 6058.2343 | 6058.2343 | 6058.2343 | 6058.2343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1310 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 27149.9587 | 0.2 | 0.3 | 42353.9355 |  |  |  |  | 0 | 6434.0514 | 6434.0514 | 6434.0514 | 6434.0514 | 6434.0514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1311 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 6337.2693 | 0.2 | 0.3 | 9886.1401 |  |  |  |  | 0 | 5043.693 | 5043.693 | 5043.693 | 5043.693 | 5043.693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1312 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 21957.9749 | 0.2 | 0.3 | 34254.4408 |  |  |  |  | 0 | 3913.0566 | 3913.0566 | 3913.0566 | 3913.0566 | 3913.0566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1313 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 12038.2149 | 0.2 | 0.3 | 18779.6152 |  |  |  |  | 0 | 6378.8298 | 6378.8298 | 6378.8298 | 6378.8298 | 6378.8298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1314 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 30164.1155 | 0.2 | 0.3 | 47056.0201 |  |  |  |  | 0 | 5205.6091 | 5205.6091 | 5205.6091 | 5205.6091 | 5205.6091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1315 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 24548.9019 | 0.2 | 0.3 | 38296.2869 |  |  |  |  | 0 | 5205.4558 | 5205.4558 | 5205.4558 | 5205.4558 | 5205.4558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1316 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 22339.91 | 0.2 | 0.3 | 34850.2596 |  |  |  |  | 0 | 5228.1257 | 5228.1257 | 5228.1257 | 5228.1257 | 5228.1257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1317 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 5757.6641 | 0.2 | 0.3 | 8981.9559 |  |  |  |  | 0 | 9789.5149 | 9789.5149 | 9789.5149 | 9789.5149 | 9789.5149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1318 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 23417.1949 | 0.2 | 0.3 | 36530.824 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1319 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 16747.2598 | 0.2 | 0.3 | 26125.7253 |  |  |  |  | 0 | 9784.3859 | 9784.3859 | 9784.3859 | 9784.3859 | 9784.3859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1320 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 17453.8161 | 0.2 | 0.3 | 27227.9531 |  |  |  |  | 0 | 5203.89 | 5203.89 | 5203.89 | 5203.89 | 5203.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1321 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 18761.7661 | 0.2 | 0.3 | 29268.3551 |  |  |  |  | 0 | 5204.0562 | 5204.0562 | 5204.0562 | 5204.0562 | 5204.0562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1322 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 20766.0594 | 0.2 | 0.3 | 32395.0527 |  |  |  |  | 0 | 9888.8865 | 9888.8865 | 9888.8865 | 9888.8865 | 9888.8865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1323 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 18088.5345 | 0.2 | 0.3 | 28218.1138 |  |  |  |  | 0 | 5512.6786 | 5512.6786 | 5512.6786 | 5512.6786 | 5512.6786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1324 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 16318.3917 | 0.2 | 0.3 | 25456.6911 |  |  |  |  | 0 | 9372.0781 | 9372.0781 | 9372.0781 | 9372.0781 | 9372.0781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1325 | WESTON | 70318 | Private | 2036 | 5 | Swales | 66.6667 | 18146.2756 | 0.2 | 0.3 | 28308.1899 |  |  |  |  | 0 | 3596.4933 | 3596.4933 | 3596.4933 | 3596.4933 | 3596.4933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1326 | WESTON | 70312 | Private | 2036 | 5 | Swales | 66.6667 | 17790.8836 | 0.2 | 0.3 | 27753.7784 |  |  |  |  | 0 | 6978.9465 | 6978.9465 | 6978.9465 | 6978.9465 | 6978.9465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1327 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 5473.7811 | 0.2 | 0.3 | 8539.0986 |  |  |  |  | 0 | 5206.9776 | 5206.9776 | 5206.9776 | 5206.9776 | 5206.9776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1328 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 39143.3805 | 0.2 | 0.3 | 61063.6736 |  |  |  |  | 0 | 5208.1262 | 5208.1262 | 5208.1262 | 5208.1262 | 5208.1262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1329 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 5306.2555 | 0.2 | 0.3 | 8277.7586 |  |  |  |  | 0 | 5209.6057 | 5209.6057 | 5209.6057 | 5209.6057 | 5209.6057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1330 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 18227.3593 | 0.2 | 0.3 | 28434.6806 |  |  |  |  | 0 | 5207.0714 | 5207.0714 | 5207.0714 | 5207.0714 | 5207.0714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1331 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 5475.6782 | 0.2 | 0.3 | 8542.058 |  |  |  |  | 0 | 5206.2263 | 5206.2263 | 5206.2263 | 5206.2263 | 5206.2263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1332 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 13501.5988 | 0.2 | 0.3 | 21062.4941 |  |  |  |  | 0 | 5207.586 | 5207.586 | 5207.586 | 5207.586 | 5207.586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1333 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17050.7031 | 0.2 | 0.3 | 26599.0969 |  |  |  |  | 0 | 5208.2458 | 5208.2458 | 5208.2458 | 5208.2458 | 5208.2458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1334 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 17249.4801 | 0.2 | 0.3 | 26909.189 |  |  |  |  | 0 | 5206.8379 | 5206.8379 | 5206.8379 | 5206.8379 | 5206.8379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1335 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16837.7656 | 0.2 | 0.3 | 26266.9143 |  |  |  |  | 0 | 5207.4575 | 5207.4575 | 5207.4575 | 5207.4575 | 5207.4575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1336 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16453.9884 | 0.2 | 0.3 | 25668.2219 |  |  |  |  | 0 | 5207.8962 | 5207.8962 | 5207.8962 | 5207.8962 | 5207.8962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1337 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16732.9966 | 0.2 | 0.3 | 26103.4747 |  |  |  |  | 0 | 5202.0664 | 5202.0664 | 5202.0664 | 5202.0664 | 5202.0664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1338 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16672.9997 | 0.2 | 0.3 | 26009.8795 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1339 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 2718.9311 | 0.2 | 0.3 | 4241.5325 |  |  |  |  | 0 | 5202.3225 | 5202.3225 | 5202.3225 | 5202.3225 | 5202.3225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1340 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 34895.7827 | 0.2 | 0.3 | 54437.4211 |  |  |  |  | 0 | 6150.2825 | 6150.2825 | 6150.2825 | 6150.2825 | 6150.2825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1341 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 23712.5563 | 0.2 | 0.3 | 36991.5878 |  |  |  |  | 0 | 6949.1062 | 6949.1062 | 6949.1062 | 6949.1062 | 6949.1062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1342 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 1150.8287 | 0.2 | 0.3 | 1795.2928 |  |  |  |  | 0 | 6836.6769 | 6836.6769 | 6836.6769 | 6836.6769 | 6836.6769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1343 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 18870.406 | 0.2 | 0.3 | 29437.8334 |  |  |  |  | 0 | 5839.1986 | 5839.1986 | 5839.1986 | 5839.1986 | 5839.1986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1344 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 904.0845 | 0.2 | 0.3 | 1410.3718 |  |  |  |  | 0 | 6596.8215 | 6596.8215 | 6596.8215 | 6596.8215 | 6596.8215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1345 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 15684.0156 | 0.2 | 0.3 | 24467.0643 |  |  |  |  | 0 | 5220.5369 | 5220.5369 | 5220.5369 | 5220.5369 | 5220.5369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1346 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16679.8985 | 0.2 | 0.3 | 26020.6417 |  |  |  |  | 0 | 2691.8356 | 2691.8356 | 2691.8356 | 2691.8356 | 2691.8356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1347 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16670.284 | 0.2 | 0.3 | 26005.643 |  |  |  |  | 0 | 6442.2187 | 6442.2187 | 6442.2187 | 6442.2187 | 6442.2187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1348 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16666.4165 | 0.2 | 0.3 | 25999.6098 |  |  |  |  | 0 | 3751.4116 | 3751.4116 | 3751.4116 | 3751.4116 | 3751.4116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1349 | WESTON | 70331 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1687 | 0.2 | 0.3 | 26000.7831 |  |  |  |  | 0 | 9178.0785 | 9178.0785 | 9178.0785 | 9178.0785 | 9178.0785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1350 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 3712.6789 | 0.2 | 0.3 | 5791.779 |  |  |  |  | 0 | 7796.0141 | 7796.0141 | 7796.0141 | 7796.0141 | 7796.0141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1351 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 20407.5871 | 0.2 | 0.3 | 31835.8358 |  |  |  |  | 0 | 5205.6091 | 5205.6091 | 5205.6091 | 5205.6091 | 5205.6091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1352 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 17083.4519 | 0.2 | 0.3 | 26650.185 |  |  |  |  | 0 | 5211.0772 | 5211.0772 | 5211.0772 | 5211.0772 | 5211.0772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1353 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 9892.0673 | 0.2 | 0.3 | 15431.625 |  |  |  |  | 0 | 1403.609 | 1403.609 | 1403.609 | 1403.609 | 1403.609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1354 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 24661.3047 | 0.2 | 0.3 | 38471.6354 |  |  |  |  | 0 | 8891.7272 | 8891.7272 | 8891.7272 | 8891.7272 | 8891.7272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1355 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 8573.8631 | 0.2 | 0.3 | 13375.2264 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1356 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 1504.1572 | 0.2 | 0.3 | 2346.4852 |  |  |  |  | 0 | 9789.278 | 9789.278 | 9789.278 | 9789.278 | 9789.278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1357 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 25182.2185 | 0.2 | 0.3 | 39284.2609 |  |  |  |  | 0 | 5203.7678 | 5203.7678 | 5203.7678 | 5203.7678 | 5203.7678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1358 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 17316.4707 | 0.2 | 0.3 | 27013.6943 |  |  |  |  | 0 | 5204.0094 | 5204.0094 | 5204.0094 | 5204.0094 | 5204.0094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1359 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 14716.7541 | 0.2 | 0.3 | 22958.1364 |  |  |  |  | 0 | 7279.7459 | 7279.7459 | 7279.7459 | 7279.7459 | 7279.7459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1360 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 17798.3462 | 0.2 | 0.3 | 27765.4201 |  |  |  |  | 0 | 3166.9073 | 3166.9073 | 3166.9073 | 3166.9073 | 3166.9073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1361 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 26595.6486 | 0.2 | 0.3 | 41489.2118 |  |  |  |  | 0 | 8816.0114 | 8816.0114 | 8816.0114 | 8816.0114 | 8816.0114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1362 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 15244.0745 | 0.2 | 0.3 | 23780.7563 |  |  |  |  | 0 | 7049.3349 | 7049.3349 | 7049.3349 | 7049.3349 | 7049.3349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1363 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 3467.4448 | 0.2 | 0.3 | 5409.2139 |  |  |  |  | 0 | 4738.7284 | 4738.7284 | 4738.7284 | 4738.7284 | 4738.7284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1364 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 28320.6552 | 0.2 | 0.3 | 44180.2221 |  |  |  |  | 0 | 5206.8033 | 5206.8033 | 5206.8033 | 5206.8033 | 5206.8033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1365 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 27869.2397 | 0.2 | 0.3 | 43476.014 |  |  |  |  | 0 | 5207.8269 | 5207.8269 | 5207.8269 | 5207.8269 | 5207.8269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1366 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 17210.7775 | 0.2 | 0.3 | 26848.813 |  |  |  |  | 0 | 5207.7904 | 5207.7904 | 5207.7904 | 5207.7904 | 5207.7904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1367 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 11107.7781 | 0.2 | 0.3 | 17328.1338 |  |  |  |  | 0 | 5207.0865 | 5207.0865 | 5207.0865 | 5207.0865 | 5207.0865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1368 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 19050.9083 | 0.2 | 0.3 | 29719.417 |  |  |  |  | 0 | 5206.2463 | 5206.2463 | 5206.2463 | 5206.2463 | 5206.2463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1369 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 12591.2984 | 0.2 | 0.3 | 19642.4255 |  |  |  |  | 0 | 5207.545 | 5207.545 | 5207.545 | 5207.545 | 5207.545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1370 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 18052.7559 | 0.2 | 0.3 | 28162.2993 |  |  |  |  | 0 | 5208.1212 | 5208.1212 | 5208.1212 | 5208.1212 | 5208.1212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1371 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 299.8205 | 0.2 | 0.3 | 467.72 |  |  |  |  | 0 | 5206.7635 | 5206.7635 | 5206.7635 | 5206.7635 | 5206.7635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1372 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 17344.5471 | 0.2 | 0.3 | 27057.4935 |  |  |  |  | 0 | 5207.2641 | 5207.2641 | 5207.2641 | 5207.2641 | 5207.2641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1373 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 22854.1289 | 0.2 | 0.3 | 35652.4411 |  |  |  |  | 0 | 5207.5707 | 5207.5707 | 5207.5707 | 5207.5707 | 5207.5707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1374 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16664.3452 | 0.2 | 0.3 | 25996.3785 |  |  |  |  | 0 | 5202.0788 | 5202.0788 | 5202.0788 | 5202.0788 | 5202.0788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1375 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 24760.8499 | 0.2 | 0.3 | 38626.9258 |  |  |  |  | 0 | 2802.8796 | 2802.8796 | 2802.8796 | 2802.8796 | 2802.8796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1376 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 24045.5879 | 0.2 | 0.3 | 37511.1172 |  |  |  |  | 0 | 7321.1292 | 7321.1292 | 7321.1292 | 7321.1292 | 7321.1292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1377 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 31584.3616 | 0.2 | 0.3 | 49271.6041 |  |  |  |  | 0 | 9781.2179 | 9781.2179 | 9781.2179 | 9781.2179 | 9781.2179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1378 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 23503.3393 | 0.2 | 0.3 | 36665.2094 |  |  |  |  | 0 | 5202.1106 | 5202.1106 | 5202.1106 | 5202.1106 | 5202.1106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1379 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 13079.6353 | 0.2 | 0.3 | 20404.2311 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1380 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 18451.7315 | 0.2 | 0.3 | 28784.7012 |  |  |  |  | 0 | 5202.2052 | 5202.2052 | 5202.2052 | 5202.2052 | 5202.2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1381 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 20555.4013 | 0.2 | 0.3 | 32066.426 |  |  |  |  | 0 | 6438.1189 | 6438.1189 | 6438.1189 | 6438.1189 | 6438.1189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1382 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 6353.1397 | 0.2 | 0.3 | 9910.898 |  |  |  |  | 0 | 2072.3275 | 2072.3275 | 2072.3275 | 2072.3275 | 2072.3275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1383 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 27540.0414 | 0.2 | 0.3 | 42962.4646 |  |  |  |  | 0 | 5496.877 | 5496.877 | 5496.877 | 5496.877 | 5496.877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1384 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 24098.5542 | 0.2 | 0.3 | 37593.7446 |  |  |  |  | 0 | 5569.909 | 5569.909 | 5569.909 | 5569.909 | 5569.909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1385 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 19133.7485 | 0.2 | 0.3 | 29848.6476 |  |  |  |  | 0 | 183.7289 | 183.7289 | 183.7289 | 183.7289 | 183.7289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1386 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 17247.0509 | 0.2 | 0.3 | 26905.3994 |  |  |  |  | 0 | 154.6593 | 154.6593 | 154.6593 | 154.6593 | 154.6593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1387 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 18863.6603 | 0.2 | 0.3 | 29427.3101 |  |  |  |  | 0 | 8785.644 | 8785.644 | 8785.644 | 8785.644 | 8785.644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1388 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 27808.6791 | 0.2 | 0.3 | 43381.5394 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1389 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 27665.1927 | 0.2 | 0.3 | 43157.7006 |  |  |  |  | 0 | 5204.5507 | 5204.5507 | 5204.5507 | 5204.5507 | 5204.5507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1390 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 15453.4822 | 0.2 | 0.3 | 24107.4322 |  |  |  |  | 0 | 6009.8663 | 6009.8663 | 6009.8663 | 6009.8663 | 6009.8663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1391 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 18350.0425 | 0.2 | 0.3 | 28626.0662 |  |  |  |  | 0 | 6972.7366 | 6972.7366 | 6972.7366 | 6972.7366 | 6972.7366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1392 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 24182.0411 | 0.2 | 0.3 | 37723.9841 |  |  |  |  | 0 | 4829.889 | 4829.889 | 4829.889 | 4829.889 | 4829.889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1393 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 25297.4619 | 0.2 | 0.3 | 39464.0406 |  |  |  |  | 0 | 9783.2824 | 9783.2824 | 9783.2824 | 9783.2824 | 9783.2824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1394 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16749.5143 | 0.2 | 0.3 | 26129.2424 |  |  |  |  | 0 | 5203.1277 | 5203.1277 | 5203.1277 | 5203.1277 | 5203.1277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1395 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16692.9152 | 0.2 | 0.3 | 26040.9477 |  |  |  |  | 0 | 5203.4226 | 5203.4226 | 5203.4226 | 5203.4226 | 5203.4226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1396 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 33795.9667 | 0.2 | 0.3 | 52721.708 |  |  |  |  | 0 | 10093.2588 | 10093.2588 | 10093.2588 | 10093.2588 | 10093.2588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1397 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 14471.5489 | 0.2 | 0.3 | 22575.6163 |  |  |  |  | 0 | 4484.1306 | 4484.1306 | 4484.1306 | 4484.1306 | 4484.1306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1398 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 33128.1006 | 0.2 | 0.3 | 51679.8369 |  |  |  |  | 0 | 8648.7774 | 8648.7774 | 8648.7774 | 8648.7774 | 8648.7774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1399 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 30729.8706 | 0.2 | 0.3 | 47938.5981 |  |  |  |  | 0 | 8199.7867 | 8199.7867 | 8199.7867 | 8199.7867 | 8199.7867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1400 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 27549.3847 | 0.2 | 0.3 | 42977.0402 |  |  |  |  | 0 | 8911.7038 | 8911.7038 | 8911.7038 | 8911.7038 | 8911.7038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1401 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 21405.5111 | 0.2 | 0.3 | 33392.5974 |  |  |  |  | 0 | 7845.6182 | 7845.6182 | 7845.6182 | 7845.6182 | 7845.6182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1402 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 39721.0053 | 0.2 | 0.3 | 61964.7683 |  |  |  |  | 0 | 9624.5376 | 9624.5376 | 9624.5376 | 9624.5376 | 9624.5376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1403 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 7615.817 | 0.2 | 0.3 | 11880.6745 |  |  |  |  | 0 | 7434.0452 | 7434.0452 | 7434.0452 | 7434.0452 | 7434.0452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1404 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 5646.6445 | 0.2 | 0.3 | 8808.7654 |  |  |  |  | 0 | 9787.6582 | 9787.6582 | 9787.6582 | 9787.6582 | 9787.6582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1405 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 14725.3461 | 0.2 | 0.3 | 22971.5399 |  |  |  |  | 0 | 9805.0649 | 9805.0649 | 9805.0649 | 9805.0649 | 9805.0649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1406 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 141.0911 | 0.2 | 0.3 | 220.1021 |  |  |  |  | 0 | 6882.0438 | 6882.0438 | 6882.0438 | 6882.0438 | 6882.0438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1407 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16671.2479 | 0.2 | 0.3 | 26007.1467 |  |  |  |  | 0 | 9806.6179 | 9806.6179 | 9806.6179 | 9806.6179 | 9806.6179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1408 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 19138.2512 | 0.2 | 0.3 | 29855.6719 |  |  |  |  | 0 | 6515.099 | 6515.099 | 6515.099 | 6515.099 | 6515.099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1409 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16687.7742 | 0.2 | 0.3 | 26032.9278 |  |  |  |  | 0 | 9825.6147 | 9825.6147 | 9825.6147 | 9825.6147 | 9825.6147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1410 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16871.0076 | 0.2 | 0.3 | 26318.7719 |  |  |  |  | 0 | 9829.2985 | 9829.2985 | 9829.2985 | 9829.2985 | 9829.2985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1411 | WESTON | 70330 | Private | 2033 | 5 | Swales | 66.6667 | 20350.2364 | 0.2 | 0.3 | 31746.3688 |  |  |  |  | 0 | 7963.2238 | 7963.2238 | 7963.2238 | 7963.2238 | 7963.2238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1412 | WESTON | 70330 | Private | 2033 | 5 | Swales | 66.6667 | 23189.5577 | 0.2 | 0.3 | 36175.71 |  |  |  |  | 0 | 5212.5488 | 5212.5488 | 5212.5488 | 5212.5488 | 5212.5488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1413 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 24601.1734 | 0.2 | 0.3 | 38377.8305 |  |  |  |  | 0 | 7189.4379 | 7189.4379 | 7189.4379 | 7189.4379 | 7189.4379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1414 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 30914.6684 | 0.2 | 0.3 | 48226.8827 |  |  |  |  | 0 | 5202.3264 | 5202.3264 | 5202.3264 | 5202.3264 | 5202.3264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1415 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 41105.0986 | 0.2 | 0.3 | 64123.9538 |  |  |  |  | 0 | 8033.5556 | 8033.5556 | 8033.5556 | 8033.5556 | 8033.5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1416 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 5149.6765 | 0.2 | 0.3 | 8033.4954 |  |  |  |  | 0 | 5361.5392 | 5361.5392 | 5361.5392 | 5361.5392 | 5361.5392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1417 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 7181.2713 | 0.2 | 0.3 | 11202.7832 |  |  |  |  | 0 | 2837.6092 | 2837.6092 | 2837.6092 | 2837.6092 | 2837.6092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1418 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 27385.3125 | 0.2 | 0.3 | 42721.0876 |  |  |  |  | 0 | 5328.4945 | 5328.4945 | 5328.4945 | 5328.4945 | 5328.4945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1419 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 30823.2113 | 0.2 | 0.3 | 48084.2097 |  |  |  |  | 0 | 4127.7095 | 4127.7095 | 4127.7095 | 4127.7095 | 4127.7095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1420 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16091.2467 | 0.2 | 0.3 | 25102.3449 |  |  |  |  | 0 | 1674.6746 | 1674.6746 | 1674.6746 | 1674.6746 | 1674.6746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1421 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 22146.863 | 0.2 | 0.3 | 34549.1063 |  |  |  |  | 0 | 5206.1888 | 5206.1888 | 5206.1888 | 5206.1888 | 5206.1888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1422 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 21112.0573 | 0.2 | 0.3 | 32934.8093 |  |  |  |  | 0 | 7068.0814 | 7068.0814 | 7068.0814 | 7068.0814 | 7068.0814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1423 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 19856.1193 | 0.2 | 0.3 | 30975.5461 |  |  |  |  | 0 | 2805.8044 | 2805.8044 | 2805.8044 | 2805.8044 | 2805.8044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1424 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 10784.3138 | 0.2 | 0.3 | 16823.5295 |  |  |  |  | 0 | 8232.5509 | 8232.5509 | 8232.5509 | 8232.5509 | 8232.5509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1425 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 24466.7154 | 0.2 | 0.3 | 38168.076 |  |  |  |  | 0 | 5204.4467 | 5204.4467 | 5204.4467 | 5204.4467 | 5204.4467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1426 | WESTON | 70325 | Private | 2036 | 5 | Swales | 66.6667 | 13609.1326 | 0.2 | 0.3 | 21230.2469 |  |  |  |  | 0 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1427 | WESTON | 70325 | Private | 2036 | 5 | Swales | 66.6667 | 16878.0751 | 0.2 | 0.3 | 26329.7972 |  |  |  |  | 0 | 8973.7872 | 8973.7872 | 8973.7872 | 8973.7872 | 8973.7872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1428 | WESTON | 70325 | Private | 2036 | 5 | Swales | 66.6667 | 12691.5447 | 0.2 | 0.3 | 19798.8097 |  |  |  |  | 0 | 6454.6068 | 6454.6068 | 6454.6068 | 6454.6068 | 6454.6068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1429 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 483.6611 | 0.2 | 0.3 | 754.5114 |  |  |  |  | 0 | 6180.0373 | 6180.0373 | 6180.0373 | 6180.0373 | 6180.0373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1430 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 21894.9557 | 0.2 | 0.3 | 34156.1309 |  |  |  |  | 0 | 5200.6947 | 5200.6947 | 5200.6947 | 5200.6947 | 5200.6947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1431 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 2670.0317 | 0.2 | 0.3 | 4165.2495 |  |  |  |  | 0 | 6193.9454 | 6193.9454 | 6193.9454 | 6193.9454 | 6193.9454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1432 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16734.4895 | 0.2 | 0.3 | 26105.8037 |  |  |  |  | 0 | 2118.0439 | 2118.0439 | 2118.0439 | 2118.0439 | 2118.0439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1433 | WESTON | 70330 | Private | 2033 | 5 | Swales | 66.6667 | 26525.9602 | 0.2 | 0.3 | 41380.4979 |  |  |  |  | 0 | 7228.4707 | 7228.4707 | 7228.4707 | 7228.4707 | 7228.4707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1434 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 750.8901 | 0.2 | 0.3 | 1171.3885 |  |  |  |  | 0 | 9935.367 | 9935.367 | 9935.367 | 9935.367 | 9935.367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1435 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 17014.4405 | 0.2 | 0.3 | 26542.5272 |  |  |  |  | 0 | 6859.6767 | 6859.6767 | 6859.6767 | 6859.6767 | 6859.6767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1436 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 19733.9589 | 0.2 | 0.3 | 30784.9758 |  |  |  |  | 0 | 5212.4035 | 5212.4035 | 5212.4035 | 5212.4035 | 5212.4035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1437 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 28345.1779 | 0.2 | 0.3 | 44218.4775 |  |  |  |  | 0 | 5205.1735 | 5205.1735 | 5205.1735 | 5205.1735 | 5205.1735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1438 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 25782.9149 | 0.2 | 0.3 | 40221.3472 |  |  |  |  | 0 | 7909.0022 | 7909.0022 | 7909.0022 | 7909.0022 | 7909.0022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1439 | WESTON | 70325 | Private | 2036 | 5 | Swales | 66.6667 | 8780.7427 | 0.2 | 0.3 | 13697.9587 |  |  |  |  | 0 | 9910.2796 | 9910.2796 | 9910.2796 | 9910.2796 | 9910.2796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1440 | WESTON | 70325 | Private | 2036 | 5 | Swales | 66.6667 | 11188.9945 | 0.2 | 0.3 | 17454.8315 |  |  |  |  | 0 | 8626.0878 | 8626.0878 | 8626.0878 | 8626.0878 | 8626.0878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1441 | WESTON | 70325 | Private | 2036 | 5 | Swales | 66.6667 | 19251.7783 | 0.2 | 0.3 | 30032.7741 |  |  |  |  | 0 | 9592.4325 | 9592.4325 | 9592.4325 | 9592.4325 | 9592.4325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1442 | WESTON | 70325 | Private | 2036 | 5 | Swales | 66.6667 | 12722.3055 | 0.2 | 0.3 | 19846.7966 |  |  |  |  | 0 | 3949.0723 | 3949.0723 | 3949.0723 | 3949.0723 | 3949.0723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1443 | WESTON | 70325 | Private | 2036 | 5 | Swales | 66.6667 | 183.012 | 0.2 | 0.3 | 285.4987 |  |  |  |  | 0 | 5025.9816 | 5025.9816 | 5025.9816 | 5025.9816 | 5025.9816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1444 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 7319.9025 | 0.2 | 0.3 | 11419.0478 |  |  |  |  | 0 | 7951.5441 | 7951.5441 | 7951.5441 | 7951.5441 | 7951.5441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1445 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 15207.9444 | 0.2 | 0.3 | 23724.3933 |  |  |  |  | 0 | 7778.3419 | 7778.3419 | 7778.3419 | 7778.3419 | 7778.3419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1446 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16667.7076 | 0.2 | 0.3 | 26001.6239 |  |  |  |  | 0 | 7969.4662 | 7969.4662 | 7969.4662 | 7969.4662 | 7969.4662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1447 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 9373.9339 | 0.2 | 0.3 | 14623.3369 |  |  |  |  | 0 | 9030.9031 | 9030.9031 | 9030.9031 | 9030.9031 | 9030.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1448 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 6228.3888 | 0.2 | 0.3 | 9716.2865 |  |  |  |  | 0 | 2530.4876 | 2530.4876 | 2530.4876 | 2530.4876 | 2530.4876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1449 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 18414.3375 | 0.2 | 0.3 | 28726.3664 |  |  |  |  | 0 | 5202.7742 | 5202.7742 | 5202.7742 | 5202.7742 | 5202.7742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1450 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 22898.8048 | 0.2 | 0.3 | 35722.1355 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1451 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 1651.4079 | 0.2 | 0.3 | 2576.1963 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1452 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 18298.8584 | 0.2 | 0.3 | 28546.2191 |  |  |  |  | 0 | 5203.1813 | 5203.1813 | 5203.1813 | 5203.1813 | 5203.1813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1453 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 15412.1269 | 0.2 | 0.3 | 24042.9179 |  |  |  |  | 0 | 5772.409 | 5772.409 | 5772.409 | 5772.409 | 5772.409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1454 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 17301.9611 | 0.2 | 0.3 | 26991.0593 |  |  |  |  | 0 | 5346.6413 | 5346.6413 | 5346.6413 | 5346.6413 | 5346.6413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1455 | WESTON | 70325 | Private | 2036 | 5 | Swales | 66.6667 | 16827.296 | 0.2 | 0.3 | 26250.5818 |  |  |  |  | 0 | 4276.1075 | 4276.1075 | 4276.1075 | 4276.1075 | 4276.1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1456 | WESTON | 70325 | Private | 2036 | 5 | Swales | 66.6667 | 21215.0279 | 0.2 | 0.3 | 33095.4436 |  |  |  |  | 0 | 6519.3139 | 6519.3139 | 6519.3139 | 6519.3139 | 6519.3139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1457 | WESTON | 70325 | Private | 2036 | 5 | Swales | 66.6667 | 3028.5557 | 0.2 | 0.3 | 4724.5468 |  |  |  |  | 0 | 7948.2672 | 7948.2672 | 7948.2672 | 7948.2672 | 7948.2672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1458 | WESTON | 70325 | Private | 2036 | 5 | Swales | 66.6667 | 29350.8032 | 0.2 | 0.3 | 45787.253 |  |  |  |  | 0 | 9724.8605 | 9724.8605 | 9724.8605 | 9724.8605 | 9724.8605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1459 | WESTON | 70325 | Private | 2036 | 5 | Swales | 66.6667 | 32951.4983 | 0.2 | 0.3 | 51404.3373 |  |  |  |  | 0 | 2772.0214 | 2772.0214 | 2772.0214 | 2772.0214 | 2772.0214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1460 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 13007.8839 | 0.2 | 0.3 | 20292.2989 |  |  |  |  | 0 | 6978.9527 | 6978.9527 | 6978.9527 | 6978.9527 | 6978.9527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1461 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 21140.3428 | 0.2 | 0.3 | 32978.9348 |  |  |  |  | 0 | 3523.8595 | 3523.8595 | 3523.8595 | 3523.8595 | 3523.8595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1462 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 17251.1721 | 0.2 | 0.3 | 26911.8285 |  |  |  |  | 0 | 4877.5071 | 4877.5071 | 4877.5071 | 4877.5071 | 4877.5071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1463 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 10527.671 | 0.2 | 0.3 | 16423.1668 |  |  |  |  | 0 | 8688.7357 | 8688.7357 | 8688.7357 | 8688.7357 | 8688.7357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1464 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 17349.2418 | 0.2 | 0.3 | 27064.8172 |  |  |  |  | 0 | 3460.8394 | 3460.8394 | 3460.8394 | 3460.8394 | 3460.8394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1465 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 1403.3677 | 0.2 | 0.3 | 2189.2536 |  |  |  |  | 0 | 8098.1061 | 8098.1061 | 8098.1061 | 8098.1061 | 8098.1061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1466 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 27981.6684 | 0.2 | 0.3 | 43651.4027 |  |  |  |  | 0 | 6739.5623 | 6739.5623 | 6739.5623 | 6739.5623 | 6739.5623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1467 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 19608.2468 | 0.2 | 0.3 | 30588.865 |  |  |  |  | 0 | 9020.0298 | 9020.0298 | 9020.0298 | 9020.0298 | 9020.0298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1468 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 1690.5257 | 0.2 | 0.3 | 2637.22 |  |  |  |  | 0 | 5209.3344 | 5209.3344 | 5209.3344 | 5209.3344 | 5209.3344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1469 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 19574.8013 | 0.2 | 0.3 | 30536.69 |  |  |  |  | 0 | 5160.7803 | 5160.7803 | 5160.7803 | 5160.7803 | 5160.7803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1470 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 19733.7651 | 0.2 | 0.3 | 30784.6736 |  |  |  |  | 0 | 5176.7681 | 5176.7681 | 5176.7681 | 5176.7681 | 5176.7681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1471 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16888.4505 | 0.2 | 0.3 | 26345.9828 |  |  |  |  | 0 | 4976.517 | 4976.517 | 4976.517 | 4976.517 | 4976.517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1472 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 11966.0004 | 0.2 | 0.3 | 18666.9606 |  |  |  |  | 0 | 5016.6364 | 5016.6364 | 5016.6364 | 5016.6364 | 5016.6364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1473 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 27489.5015 | 0.2 | 0.3 | 42883.6223 |  |  |  |  | 0 | 3388.7556 | 3388.7556 | 3388.7556 | 3388.7556 | 3388.7556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1474 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 22137.8763 | 0.2 | 0.3 | 34535.087 |  |  |  |  | 0 | 4942.2508 | 4942.2508 | 4942.2508 | 4942.2508 | 4942.2508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1475 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 2840.9629 | 0.2 | 0.3 | 4431.9021 |  |  |  |  | 0 | 5303.5804 | 5303.5804 | 5303.5804 | 5303.5804 | 5303.5804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1476 | WESTON | 70325 | Private | 2036 | 5 | Swales | 66.6667 | 125.6171 | 0.2 | 0.3 | 195.9627 |  |  |  |  | 0 | 5267.0348 | 5267.0348 | 5267.0348 | 5267.0348 | 5267.0348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1477 | WESTON | 70325 | Private | 2036 | 5 | Swales | 66.6667 | 24130.3639 | 0.2 | 0.3 | 37643.3676 |  |  |  |  | 0 | 5012.6264 | 5012.6264 | 5012.6264 | 5012.6264 | 5012.6264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1478 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16812.3525 | 0.2 | 0.3 | 26227.27 |  |  |  |  | 0 | 4178.2291 | 4178.2291 | 4178.2291 | 4178.2291 | 4178.2291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1479 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 27850.2511 | 0.2 | 0.3 | 43446.3917 |  |  |  |  | 0 | 4799.8392 | 4799.8392 | 4799.8392 | 4799.8392 | 4799.8392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1480 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 17209.5156 | 0.2 | 0.3 | 26846.8443 |  |  |  |  | 0 | 4749.1962 | 4749.1962 | 4749.1962 | 4749.1962 | 4749.1962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1481 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16667.6101 | 0.2 | 0.3 | 26001.4717 |  |  |  |  | 0 | 5367.8166 | 5367.8166 | 5367.8166 | 5367.8166 | 5367.8166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1482 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 15713.6269 | 0.2 | 0.3 | 24513.2579 |  |  |  |  | 0 | 4583.5887 | 4583.5887 | 4583.5887 | 4583.5887 | 4583.5887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1483 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 14122.1217 | 0.2 | 0.3 | 22030.5098 |  |  |  |  | 0 | 5286.048 | 5286.048 | 5286.048 | 5286.048 | 5286.048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1484 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 17500.8687 | 0.2 | 0.3 | 27301.3551 |  |  |  |  | 0 | 4901.567 | 4901.567 | 4901.567 | 4901.567 | 4901.567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1485 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 10626.5411 | 0.2 | 0.3 | 16577.4041 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1486 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 30132.0571 | 0.2 | 0.3 | 47006.009 |  |  |  |  | 0 | 7905.2426 | 7905.2426 | 7905.2426 | 7905.2426 | 7905.2426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1487 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 18942.8768 | 0.2 | 0.3 | 29550.8878 |  |  |  |  | 0 | 6859.3841 | 6859.3841 | 6859.3841 | 6859.3841 | 6859.3841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1488 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 15412.0974 | 0.2 | 0.3 | 24042.8719 |  |  |  |  | 0 | 6956.9739 | 6956.9739 | 6956.9739 | 6956.9739 | 6956.9739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1489 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16909.7679 | 0.2 | 0.3 | 26379.2379 |  |  |  |  | 0 | 9934.259 | 9934.259 | 9934.259 | 9934.259 | 9934.259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1490 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 26287.2455 | 0.2 | 0.3 | 41008.103 |  |  |  |  | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1491 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16862.5837 | 0.2 | 0.3 | 26305.6306 |  |  |  |  | 0 | 6098.5224 | 6098.5224 | 6098.5224 | 6098.5224 | 6098.5224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1492 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 18835.6352 | 0.2 | 0.3 | 29383.5909 |  |  |  |  | 0 | 5145.3378 | 5145.3378 | 5145.3378 | 5145.3378 | 5145.3378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1493 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 24447.9535 | 0.2 | 0.3 | 38138.8075 |  |  |  |  | 0 | 326.5661 | 326.5661 | 326.5661 | 326.5661 | 326.5661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1494 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 4288.325 | 0.2 | 0.3 | 6689.787 |  |  |  |  | 0 | 6524.8688 | 6524.8688 | 6524.8688 | 6524.8688 | 6524.8688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1495 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 17155.6484 | 0.2 | 0.3 | 26762.8115 |  |  |  |  | 0 | 7347.0562 | 7347.0562 | 7347.0562 | 7347.0562 | 7347.0562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1496 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16644.5409 | 0.2 | 0.3 | 25965.4839 |  |  |  |  | 0 | 7910.2252 | 7910.2252 | 7910.2252 | 7910.2252 | 7910.2252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1497 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 21527.4175 | 0.2 | 0.3 | 33582.7712 |  |  |  |  | 0 | 8040.3465 | 8040.3465 | 8040.3465 | 8040.3465 | 8040.3465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1498 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 2174.9007 | 0.2 | 0.3 | 3392.8451 |  |  |  |  | 0 | 9784.8456 | 9784.8456 | 9784.8456 | 9784.8456 | 9784.8456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1499 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 13071.1445 | 0.2 | 0.3 | 20390.9854 |  |  |  |  | 0 | 4997.7658 | 4997.7658 | 4997.7658 | 4997.7658 | 4997.7658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1500 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 5139.6468 | 5139.6468 | 5139.6468 | 5139.6468 | 5139.6468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1501 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16659.3723 | 0.2 | 0.3 | 25988.6208 |  |  |  |  | 0 | 4981.5178 | 4981.5178 | 4981.5178 | 4981.5178 | 4981.5178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1502 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16681.2814 | 0.2 | 0.3 | 26022.799 |  |  |  |  | 0 | 4439.0253 | 4439.0253 | 4439.0253 | 4439.0253 | 4439.0253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1503 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16675.0755 | 0.2 | 0.3 | 26013.1177 |  |  |  |  | 0 | 8904.4594 | 8904.4594 | 8904.4594 | 8904.4594 | 8904.4594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1504 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 17504.2621 | 0.2 | 0.3 | 27306.6489 |  |  |  |  | 0 | 4737.9006 | 4737.9006 | 4737.9006 | 4737.9006 | 4737.9006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1505 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16678.7577 | 0.2 | 0.3 | 26018.862 |  |  |  |  | 0 | 5354.6194 | 5354.6194 | 5354.6194 | 5354.6194 | 5354.6194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1506 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16706.2147 | 0.2 | 0.3 | 26061.695 |  |  |  |  | 0 | 5161.2945 | 5161.2945 | 5161.2945 | 5161.2945 | 5161.2945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1507 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16676.6968 | 0.2 | 0.3 | 26015.647 |  |  |  |  | 0 | 5025.7688 | 5025.7688 | 5025.7688 | 5025.7688 | 5025.7688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1508 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16707.8207 | 0.2 | 0.3 | 26064.2003 |  |  |  |  | 0 | 4984.1995 | 4984.1995 | 4984.1995 | 4984.1995 | 4984.1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1509 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 11417.4635 | 0.2 | 0.3 | 17811.243 |  |  |  |  | 0 | 5206.7423 | 5206.7423 | 5206.7423 | 5206.7423 | 5206.7423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1510 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 19648.1519 | 0.2 | 0.3 | 30651.1169 |  |  |  |  | 0 | 5208.3387 | 5208.3387 | 5208.3387 | 5208.3387 | 5208.3387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1511 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16746.7385 | 0.2 | 0.3 | 26124.912 |  |  |  |  | 0 | 5207.4004 | 5207.4004 | 5207.4004 | 5207.4004 | 5207.4004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1512 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 20449.0197 | 0.2 | 0.3 | 31900.4707 |  |  |  |  | 0 | 5208.3387 | 5208.3387 | 5208.3387 | 5208.3387 | 5208.3387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1513 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 4932.5786 | 0.2 | 0.3 | 7694.8226 |  |  |  |  | 0 | 5206.6327 | 5206.6327 | 5206.6327 | 5206.6327 | 5206.6327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1514 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16667.8588 | 0.2 | 0.3 | 26001.8597 |  |  |  |  | 0 | 5207.1287 | 5207.1287 | 5207.1287 | 5207.1287 | 5207.1287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1515 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16674.2815 | 0.2 | 0.3 | 26011.8792 |  |  |  |  | 0 | 5208.2347 | 5208.2347 | 5208.2347 | 5208.2347 | 5208.2347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1516 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 17297.1035 | 0.2 | 0.3 | 26983.4815 |  |  |  |  | 0 | 7420.4217 | 7420.4217 | 7420.4217 | 7420.4217 | 7420.4217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1517 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 6805.9615 | 0.2 | 0.3 | 10617.3 |  |  |  |  | 0 | 9435.3053 | 9435.3053 | 9435.3053 | 9435.3053 | 9435.3053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1518 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16837.8445 | 0.2 | 0.3 | 26267.0375 |  |  |  |  | 0 | 5763.3273 | 5763.3273 | 5763.3273 | 5763.3273 | 5763.3273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1519 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16775.6849 | 0.2 | 0.3 | 26170.0684 |  |  |  |  | 0 | 7825.5342 | 7825.5342 | 7825.5342 | 7825.5342 | 7825.5342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1520 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 18736.6373 | 0.2 | 0.3 | 29229.1541 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1521 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 5332.1108 | 5332.1108 | 5332.1108 | 5332.1108 | 5332.1108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1522 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16651.0161 | 0.2 | 0.3 | 25975.5851 |  |  |  |  | 0 | 9789.5662 | 9789.5662 | 9789.5662 | 9789.5662 | 9789.5662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1523 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 15080.8583 | 0.2 | 0.3 | 23526.1389 |  |  |  |  | 0 | 5467.6799 | 5467.6799 | 5467.6799 | 5467.6799 | 5467.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1524 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16821.4747 | 0.2 | 0.3 | 26241.5006 |  |  |  |  | 0 | 9817.6067 | 9817.6067 | 9817.6067 | 9817.6067 | 9817.6067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1525 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 17640.3612 | 0.2 | 0.3 | 27518.9635 |  |  |  |  | 0 | 5202.9962 | 5202.9962 | 5202.9962 | 5202.9962 | 5202.9962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1526 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 9420.6079 | 0.2 | 0.3 | 14696.1483 |  |  |  |  | 0 | 9346.0781 | 9346.0781 | 9346.0781 | 9346.0781 | 9346.0781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1527 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 10766.6766 | 0.2 | 0.3 | 16796.0155 |  |  |  |  | 0 | 5203.7306 | 5203.7306 | 5203.7306 | 5203.7306 | 5203.7306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1528 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 17272.2465 | 0.2 | 0.3 | 26944.7045 |  |  |  |  | 0 | 5205.7567 | 5205.7567 | 5205.7567 | 5205.7567 | 5205.7567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1529 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 13175.5115 | 0.2 | 0.3 | 20553.798 |  |  |  |  | 0 | 5880.6593 | 5880.6593 | 5880.6593 | 5880.6593 | 5880.6593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1530 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 13592.8365 | 0.2 | 0.3 | 21204.825 |  |  |  |  | 0 | 5656.3454 | 5656.3454 | 5656.3454 | 5656.3454 | 5656.3454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1531 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 5456.261 | 5456.261 | 5456.261 | 5456.261 | 5456.261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1532 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 5327.6313 | 5327.6313 | 5327.6313 | 5327.6313 | 5327.6313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1533 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 14295.7418 | 0.2 | 0.3 | 22301.3572 |  |  |  |  | 0 | 5175.8585 | 5175.8585 | 5175.8585 | 5175.8585 | 5175.8585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1534 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 8150.6075 | 0.2 | 0.3 | 12714.9478 |  |  |  |  | 0 | 7248.0039 | 7248.0039 | 7248.0039 | 7248.0039 | 7248.0039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1535 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 7461.3036 | 7461.3036 | 7461.3036 | 7461.3036 | 7461.3036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1536 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 13429.6988 | 0.2 | 0.3 | 20950.3301 |  |  |  |  | 0 | 8659.6366 | 8659.6366 | 8659.6366 | 8659.6366 | 8659.6366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1537 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 18753.9285 | 0.2 | 0.3 | 29256.1285 |  |  |  |  | 0 | 9777.4246 | 9777.4246 | 9777.4246 | 9777.4246 | 9777.4246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1538 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 13956.6489 | 0.2 | 0.3 | 21772.3723 |  |  |  |  | 0 | 9607.3537 | 9607.3537 | 9607.3537 | 9607.3537 | 9607.3537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1539 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 9674.3643 | 0.2 | 0.3 | 15092.0083 |  |  |  |  | 0 | 9785.6185 | 9785.6185 | 9785.6185 | 9785.6185 | 9785.6185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1540 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16718.8577 | 0.2 | 0.3 | 26081.4181 |  |  |  |  | 0 | 9273.3557 | 9273.3557 | 9273.3557 | 9273.3557 | 9273.3557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1541 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16739.5826 | 0.2 | 0.3 | 26113.7489 |  |  |  |  | 0 | 9097.525 | 9097.525 | 9097.525 | 9097.525 | 9097.525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1542 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 16675.8331 | 0.2 | 0.3 | 26014.2997 |  |  |  |  | 0 | 8951.6508 | 8951.6508 | 8951.6508 | 8951.6508 | 8951.6508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1543 | WESTON | 70326 | Private | 2036 | 5 | Swales | 66.6667 | 8138.2755 | 0.2 | 0.3 | 12695.7097 |  |  |  |  | 0 | 8848.5605 | 8848.5605 | 8848.5605 | 8848.5605 | 8848.5605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1544 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 21489.7773 | 0.2 | 0.3 | 33524.0526 |  |  |  |  | 0 | 4099.5493 | 4099.5493 | 4099.5493 | 4099.5493 | 4099.5493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1545 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16700.1879 | 0.2 | 0.3 | 26052.2931 |  |  |  |  | 0 | 5210.2463 | 5210.2463 | 5210.2463 | 5210.2463 | 5210.2463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1546 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16717.264 | 0.2 | 0.3 | 26078.9318 |  |  |  |  | 0 | 5208.1552 | 5208.1552 | 5208.1552 | 5208.1552 | 5208.1552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1547 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16696.0949 | 0.2 | 0.3 | 26045.908 |  |  |  |  | 0 | 7499.8181 | 7499.8181 | 7499.8181 | 7499.8181 | 7499.8181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1548 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 18257.4867 | 0.2 | 0.3 | 28481.6792 |  |  |  |  | 0 | 5202.2923 | 5202.2923 | 5202.2923 | 5202.2923 | 5202.2923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1549 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 24738.9456 | 0.2 | 0.3 | 38592.7551 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1550 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16847.0977 | 0.2 | 0.3 | 26281.4725 |  |  |  |  | 0 | 5057.1976 | 5057.1976 | 5057.1976 | 5057.1976 | 5057.1976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1551 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16712.6854 | 0.2 | 0.3 | 26071.7892 |  |  |  |  | 0 | 1729.9332 | 1729.9332 | 1729.9332 | 1729.9332 | 1729.9332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1552 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 16670.8754 | 0.2 | 0.3 | 26006.5656 |  |  |  |  | 0 | 6423.9137 | 6423.9137 | 6423.9137 | 6423.9137 | 6423.9137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1553 | WESTON | 70330 | Private | 2036 | 5 | Swales | 66.6667 | 20608.811 | 0.2 | 0.3 | 32149.7452 |  |  |  |  | 0 | 6272.8182 | 6272.8182 | 6272.8182 | 6272.8182 | 6272.8182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1554 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 11686.8054 | 0.2 | 0.3 | 18231.4164 |  |  |  |  | 0 | 5202.8707 | 5202.8707 | 5202.8707 | 5202.8707 | 5202.8707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1555 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4948 | 0.2 | 0.3 | 26001.2919 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1556 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 16678.2896 | 0.2 | 0.3 | 26018.1318 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1557 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 11370.1449 | 0.2 | 0.3 | 17737.4261 |  |  |  |  | 0 | 5203.1041 | 5203.1041 | 5203.1041 | 5203.1041 | 5203.1041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1558 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 2560.7516 | 0.2 | 0.3 | 3994.7725 |  |  |  |  | 0 | 7911.5219 | 7911.5219 | 7911.5219 | 7911.5219 | 7911.5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1559 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 2313.9644 | 0.2 | 0.3 | 3609.7845 |  |  |  |  | 0 | 5368.3943 | 5368.3943 | 5368.3943 | 5368.3943 | 5368.3943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1560 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 110.3677 | 0.2 | 0.3 | 172.1737 |  |  |  |  | 0 | 17.1427 | 17.1427 | 17.1427 | 17.1427 | 17.1427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1561 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 17029.015 | 0.2 | 0.3 | 26565.2634 |  |  |  |  | 0 | 4807.8442 | 4807.8442 | 4807.8442 | 4807.8442 | 4807.8442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1562 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 5378.2328 | 0.2 | 0.3 | 8390.0432 |  |  |  |  | 0 | 5203.718 | 5203.718 | 5203.718 | 5203.718 | 5203.718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1563 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 14111.6529 | 0.2 | 0.3 | 22014.1786 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1564 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 14352.3747 | 0.2 | 0.3 | 22389.7045 |  |  |  |  | 0 | 6298.6754 | 6298.6754 | 6298.6754 | 6298.6754 | 6298.6754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1565 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 24977.0269 | 0.2 | 0.3 | 38964.1619 |  |  |  |  | 0 | 5204.761 | 5204.761 | 5204.761 | 5204.761 | 5204.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1566 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 11756.2959 | 0.2 | 0.3 | 18339.8217 |  |  |  |  | 0 | 6662.4513 | 6662.4513 | 6662.4513 | 6662.4513 | 6662.4513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1567 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 7848.5015 | 0.2 | 0.3 | 12243.6623 |  |  |  |  | 0 | 6693.4246 | 6693.4246 | 6693.4246 | 6693.4246 | 6693.4246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1568 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 16695.0338 | 0.2 | 0.3 | 26044.2527 |  |  |  |  | 0 | 5340.6512 | 5340.6512 | 5340.6512 | 5340.6512 | 5340.6512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1569 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 20881.1673 | 0.2 | 0.3 | 32574.621 |  |  |  |  | 0 | 294.5083 | 294.5083 | 294.5083 | 294.5083 | 294.5083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1570 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 4910.8509 | 0.2 | 0.3 | 7660.9274 |  |  |  |  | 0 | 7481.3794 | 7481.3794 | 7481.3794 | 7481.3794 | 7481.3794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1571 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 20894.179 | 0.2 | 0.3 | 32594.9192 |  |  |  |  | 0 | 4877.2207 | 4877.2207 | 4877.2207 | 4877.2207 | 4877.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1572 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 12917.1638 | 0.2 | 0.3 | 20150.7755 |  |  |  |  | 0 | 9210.6612 | 9210.6612 | 9210.6612 | 9210.6612 | 9210.6612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1573 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 17789.4375 | 0.2 | 0.3 | 27751.5226 |  |  |  |  | 0 | 6301.4287 | 6301.4287 | 6301.4287 | 6301.4287 | 6301.4287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1574 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 18001.5535 | 0.2 | 0.3 | 28082.4235 |  |  |  |  | 0 | 5202.9846 | 5202.9846 | 5202.9846 | 5202.9846 | 5202.9846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1575 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 18002.387 | 0.2 | 0.3 | 28083.7237 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1576 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 22090.8365 | 0.2 | 0.3 | 34461.705 |  |  |  |  | 0 | 8063.6163 | 8063.6163 | 8063.6163 | 8063.6163 | 8063.6163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1577 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1578 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 5266.4224 | 5266.4224 | 5266.4224 | 5266.4224 | 5266.4224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1579 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16756.2671 | 0.2 | 0.3 | 26139.7766 |  |  |  |  | 0 | 2317.8895 | 2317.8895 | 2317.8895 | 2317.8895 | 2317.8895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1580 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16672.662 | 0.2 | 0.3 | 26009.3527 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1581 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16672.0027 | 0.2 | 0.3 | 26008.3243 |  |  |  |  | 0 | 5207.5557 | 5207.5557 | 5207.5557 | 5207.5557 | 5207.5557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1582 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16670.4594 | 0.2 | 0.3 | 26005.9167 |  |  |  |  | 0 | 5204.9569 | 5204.9569 | 5204.9569 | 5204.9569 | 5204.9569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1583 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 16667.7295 | 0.2 | 0.3 | 26001.6581 |  |  |  |  | 0 | 6000.5742 | 6000.5742 | 6000.5742 | 6000.5742 | 6000.5742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1584 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 16666.614 | 0.2 | 0.3 | 25999.9178 |  |  |  |  | 0 | 5203.8203 | 5203.8203 | 5203.8203 | 5203.8203 | 5203.8203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1585 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16676.5909 | 0.2 | 0.3 | 26015.4818 |  |  |  |  | 0 | 6906.5034 | 6906.5034 | 6906.5034 | 6906.5034 | 6906.5034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1586 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16671.8898 | 0.2 | 0.3 | 26008.1481 |  |  |  |  | 0 | 5205.9503 | 5205.9503 | 5205.9503 | 5205.9503 | 5205.9503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1587 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16671.6651 | 0.2 | 0.3 | 26007.7975 |  |  |  |  | 0 | 8061.2636 | 8061.2636 | 8061.2636 | 8061.2636 | 8061.2636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1588 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16673.5831 | 0.2 | 0.3 | 26010.7897 |  |  |  |  | 0 | 9540.0474 | 9540.0474 | 9540.0474 | 9540.0474 | 9540.0474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1589 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 25285.0665 | 0.2 | 0.3 | 39444.7038 |  |  |  |  | 0 | 7517.8816 | 7517.8816 | 7517.8816 | 7517.8816 | 7517.8816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1590 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 5753.796 | 5753.796 | 5753.796 | 5753.796 | 5753.796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1591 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 21509.8605 | 0.2 | 0.3 | 33555.3823 |  |  |  |  | 0 | 5456.5104 | 5456.5104 | 5456.5104 | 5456.5104 | 5456.5104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1592 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 25069.6707 | 0.2 | 0.3 | 39108.6863 |  |  |  |  | 0 | 3465.5038 | 3465.5038 | 3465.5038 | 3465.5038 | 3465.5038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1593 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 29953.6007 | 0.2 | 0.3 | 46727.617 |  |  |  |  | 0 | 9785.7889 | 9785.7889 | 9785.7889 | 9785.7889 | 9785.7889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1594 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 27936.9244 | 0.2 | 0.3 | 43581.6021 |  |  |  |  | 0 | 5657.0712 | 5657.0712 | 5657.0712 | 5657.0712 | 5657.0712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1595 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 24516.412 | 0.2 | 0.3 | 38245.6027 |  |  |  |  | 0 | 7935.6634 | 7935.6634 | 7935.6634 | 7935.6634 | 7935.6634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1596 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 2369.3617 | 0.2 | 0.3 | 3696.2043 |  |  |  |  | 0 | 9783.8941 | 9783.8941 | 9783.8941 | 9783.8941 | 9783.8941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1597 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 21081.6399 | 0.2 | 0.3 | 32887.3582 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1598 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 26819.6705 | 0.2 | 0.3 | 41838.686 |  |  |  |  | 0 | 5204.8558 | 5204.8558 | 5204.8558 | 5204.8558 | 5204.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1599 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 23658.4926 | 0.2 | 0.3 | 36907.2485 |  |  |  |  | 0 | 9784.8813 | 9784.8813 | 9784.8813 | 9784.8813 | 9784.8813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1600 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 23517.3277 | 0.2 | 0.3 | 36687.0312 |  |  |  |  | 0 | 5578.6516 | 5578.6516 | 5578.6516 | 5578.6516 | 5578.6516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1601 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16734.9971 | 0.2 | 0.3 | 26106.5955 |  |  |  |  | 0 | 8434.8046 | 8434.8046 | 8434.8046 | 8434.8046 | 8434.8046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1602 | COOPER CITY | 70402 | Private | 2033 | 5 | Swales | 66.6667 | 31405.0991 | 0.2 | 0.3 | 48991.9546 |  |  |  |  | 0 | 8170.1235 | 8170.1235 | 8170.1235 | 8170.1235 | 8170.1235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1603 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 20077.7367 | 0.2 | 0.3 | 31321.2693 |  |  |  |  | 0 | 5204.4705 | 5204.4705 | 5204.4705 | 5204.4705 | 5204.4705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1604 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 6457.413 | 0.2 | 0.3 | 10073.5643 |  |  |  |  | 0 | 5205.4623 | 5205.4623 | 5205.4623 | 5205.4623 | 5205.4623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1605 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 1310.8003 | 0.2 | 0.3 | 2044.8485 |  |  |  |  | 0 | 7701.5769 | 7701.5769 | 7701.5769 | 7701.5769 | 7701.5769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1606 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 15426.6501 | 0.2 | 0.3 | 24065.5742 |  |  |  |  | 0 | 4358.2053 | 4358.2053 | 4358.2053 | 4358.2053 | 4358.2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1607 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 4693.4696 | 0.2 | 0.3 | 7321.8126 |  |  |  |  | 0 | 5469.8716 | 5469.8716 | 5469.8716 | 5469.8716 | 5469.8716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1608 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 841.7392 | 0.2 | 0.3 | 1313.1132 |  |  |  |  | 0 | 8826.3084 | 8826.3084 | 8826.3084 | 8826.3084 | 8826.3084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1609 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16472.8153 | 0.2 | 0.3 | 25697.5919 |  |  |  |  | 0 | 5335.381 | 5335.381 | 5335.381 | 5335.381 | 5335.381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1610 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16770.3135 | 0.2 | 0.3 | 26161.6891 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1611 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 3308.3255 | 0.2 | 0.3 | 5160.9877 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1612 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 39018.7627 | 0.2 | 0.3 | 60869.2698 |  |  |  |  | 0 | 5203.9767 | 5203.9767 | 5203.9767 | 5203.9767 | 5203.9767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1613 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 27899.6443 | 0.2 | 0.3 | 43523.4451 |  |  |  |  | 0 | 5573.3073 | 5573.3073 | 5573.3073 | 5573.3073 | 5573.3073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1614 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 34055.5583 | 0.2 | 0.3 | 53126.671 |  |  |  |  | 0 | 5205.1602 | 5205.1602 | 5205.1602 | 5205.1602 | 5205.1602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1615 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 31972.8211 | 0.2 | 0.3 | 49877.6009 |  |  |  |  | 0 | 5216.2468 | 5216.2468 | 5216.2468 | 5216.2468 | 5216.2468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1616 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 19860.6547 | 0.2 | 0.3 | 30982.6213 |  |  |  |  | 0 | 3019.0355 | 3019.0355 | 3019.0355 | 3019.0355 | 3019.0355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1617 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 21493.7898 | 0.2 | 0.3 | 33530.3121 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1618 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 19463.5594 | 0.2 | 0.3 | 30363.1527 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1619 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 21726.0881 | 0.2 | 0.3 | 33892.6974 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1620 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 11168.4496 | 0.2 | 0.3 | 17422.7814 |  |  |  |  | 0 | 5643.9764 | 5643.9764 | 5643.9764 | 5643.9764 | 5643.9764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1621 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 17981.0493 | 0.2 | 0.3 | 28050.437 |  |  |  |  | 0 | 5207.276 | 5207.276 | 5207.276 | 5207.276 | 5207.276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1622 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 26705.504 | 0.2 | 0.3 | 41660.5862 |  |  |  |  | 0 | 6708.4181 | 6708.4181 | 6708.4181 | 6708.4181 | 6708.4181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1623 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 33551.7763 | 0.2 | 0.3 | 52340.7711 |  |  |  |  | 0 | 7928.0805 | 7928.0805 | 7928.0805 | 7928.0805 | 7928.0805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1624 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 16769.0265 | 0.2 | 0.3 | 26159.6813 |  |  |  |  | 0 | 7698.2824 | 7698.2824 | 7698.2824 | 7698.2824 | 7698.2824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1625 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 43948.2396 | 0.2 | 0.3 | 68559.2538 |  |  |  |  | 0 | 4292.5413 | 4292.5413 | 4292.5413 | 4292.5413 | 4292.5413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1626 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 29218.7648 | 0.2 | 0.3 | 45581.2731 |  |  |  |  | 0 | 5761.1159 | 5761.1159 | 5761.1159 | 5761.1159 | 5761.1159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1627 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 24947.5103 | 0.2 | 0.3 | 38918.116 |  |  |  |  | 0 | 8709.8086 | 8709.8086 | 8709.8086 | 8709.8086 | 8709.8086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1628 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 13472.6789 | 0.2 | 0.3 | 21017.379 |  |  |  |  | 0 | 8477.8507 | 8477.8507 | 8477.8507 | 8477.8507 | 8477.8507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1629 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 11839.6836 | 0.2 | 0.3 | 18469.9064 |  |  |  |  | 0 | 9787.483 | 9787.483 | 9787.483 | 9787.483 | 9787.483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1630 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 25404.3145 | 0.2 | 0.3 | 39630.7307 |  |  |  |  | 0 | 6858.1811 | 6858.1811 | 6858.1811 | 6858.1811 | 6858.1811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1631 | DAVIE | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 5901.4103 | 0.2 | 0.3 | 9206.2001 |  |  |  |  | 0 | 5204.0703 | 5204.0703 | 5204.0703 | 5204.0703 | 5204.0703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1632 | DAVIE | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 17677.5959 | 0.2 | 0.3 | 27577.0496 |  |  |  |  | 0 | 5202.8558 | 5202.8558 | 5202.8558 | 5202.8558 | 5202.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1633 | DAVIE | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16672.5002 | 0.2 | 0.3 | 26009.1003 |  |  |  |  | 0 | 7397.8716 | 7397.8716 | 7397.8716 | 7397.8716 | 7397.8716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1634 | DAVIE | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 17342.083 | 0.2 | 0.3 | 27053.6495 |  |  |  |  | 0 | 9781.5081 | 9781.5081 | 9781.5081 | 9781.5081 | 9781.5081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1635 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 20318.6497 | 0.2 | 0.3 | 31697.0936 |  |  |  |  | 0 | 7333.9013 | 7333.9013 | 7333.9013 | 7333.9013 | 7333.9013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1636 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 9545.344 | 0.2 | 0.3 | 14890.7366 |  |  |  |  | 0 | 7091.6231 | 7091.6231 | 7091.6231 | 7091.6231 | 7091.6231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1637 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 36109.3739 | 0.2 | 0.3 | 56330.6232 |  |  |  |  | 0 | 9629.6995 | 9629.6995 | 9629.6995 | 9629.6995 | 9629.6995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1638 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 30525.3397 | 0.2 | 0.3 | 47619.5299 |  |  |  |  | 0 | 5198.3257 | 5198.3257 | 5198.3257 | 5198.3257 | 5198.3257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1639 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 34410.1554 | 0.2 | 0.3 | 53679.8424 |  |  |  |  | 0 | 5244.9284 | 5244.9284 | 5244.9284 | 5244.9284 | 5244.9284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1640 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 44183.8885 | 0.2 | 0.3 | 68926.8661 |  |  |  |  | 0 | 5605.376 | 5605.376 | 5605.376 | 5605.376 | 5605.376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1641 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 20578.9885 | 0.2 | 0.3 | 32103.222 |  |  |  |  | 0 | 4677.5291 | 4677.5291 | 4677.5291 | 4677.5291 | 4677.5291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1642 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 27668.3265 | 0.2 | 0.3 | 43162.5893 |  |  |  |  | 0 | 7908.7734 | 7908.7734 | 7908.7734 | 7908.7734 | 7908.7734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1643 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 5594.7486 | 5594.7486 | 5594.7486 | 5594.7486 | 5594.7486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1644 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16816.2245 | 0.2 | 0.3 | 26233.3103 |  |  |  |  | 0 | 5203.1087 | 5203.1087 | 5203.1087 | 5203.1087 | 5203.1087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1645 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 9865.9322 | 0.2 | 0.3 | 15390.8542 |  |  |  |  | 0 | 5131.6919 | 5131.6919 | 5131.6919 | 5131.6919 | 5131.6919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1646 | DAVIE | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16737.2165 | 0.2 | 0.3 | 26110.0578 |  |  |  |  | 0 | 5202.8228 | 5202.8228 | 5202.8228 | 5202.8228 | 5202.8228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1647 | DAVIE | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 17093.9162 | 0.2 | 0.3 | 26666.5093 |  |  |  |  | 0 | 5232.3379 | 5232.3379 | 5232.3379 | 5232.3379 | 5232.3379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1648 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 27266.2518 | 0.2 | 0.3 | 42535.3528 |  |  |  |  | 0 | 3204.3128 | 3204.3128 | 3204.3128 | 3204.3128 | 3204.3128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1649 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 28061.1077 | 0.2 | 0.3 | 43775.3281 |  |  |  |  | 0 | 9040.1162 | 9040.1162 | 9040.1162 | 9040.1162 | 9040.1162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1650 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 31895.3673 | 0.2 | 0.3 | 49756.7729 |  |  |  |  | 0 | 5332.6083 | 5332.6083 | 5332.6083 | 5332.6083 | 5332.6083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1651 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 26105.974 | 0.2 | 0.3 | 40725.3194 |  |  |  |  | 0 | 7910.3101 | 7910.3101 | 7910.3101 | 7910.3101 | 7910.3101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1652 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 21805.7012 | 0.2 | 0.3 | 34016.8939 |  |  |  |  | 0 | 9784.1004 | 9784.1004 | 9784.1004 | 9784.1004 | 9784.1004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1653 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 37077.8549 | 0.2 | 0.3 | 57841.4537 |  |  |  |  | 0 | 8272.3368 | 8272.3368 | 8272.3368 | 8272.3368 | 8272.3368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1654 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16499.7042 | 0.2 | 0.3 | 25739.5386 |  |  |  |  | 0 | 5301.4388 | 5301.4388 | 5301.4388 | 5301.4388 | 5301.4388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1655 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 24363.3601 | 0.2 | 0.3 | 38006.8418 |  |  |  |  | 0 | 5644.2262 | 5644.2262 | 5644.2262 | 5644.2262 | 5644.2262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1656 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 18946.0033 | 0.2 | 0.3 | 29555.7651 |  |  |  |  | 0 | 9208.59 | 9208.59 | 9208.59 | 9208.59 | 9208.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1657 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6975 | 0.2 | 0.3 | 26000.048 |  |  |  |  | 0 | 3809.309 | 3809.309 | 3809.309 | 3809.309 | 3809.309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1658 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16667.21 | 0.2 | 0.3 | 26000.8476 |  |  |  |  | 0 | 8928.0098 | 8928.0098 | 8928.0098 | 8928.0098 | 8928.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1659 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 17494.8512 | 0.2 | 0.3 | 27291.9679 |  |  |  |  | 0 | 9784.8006 | 9784.8006 | 9784.8006 | 9784.8006 | 9784.8006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1660 | DAVIE | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16673.7085 | 0.2 | 0.3 | 26010.9852 |  |  |  |  | 0 | 6862.1992 | 6862.1992 | 6862.1992 | 6862.1992 | 6862.1992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1661 | DAVIE | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 17675.7955 | 0.2 | 0.3 | 27574.241 |  |  |  |  | 0 | 7021.8942 | 7021.8942 | 7021.8942 | 7021.8942 | 7021.8942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1662 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16733.3155 | 0.2 | 0.3 | 26103.9722 |  |  |  |  | 0 | 7231.8532 | 7231.8532 | 7231.8532 | 7231.8532 | 7231.8532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1663 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16674.0297 | 0.2 | 0.3 | 26011.4863 |  |  |  |  | 0 | 8588.5853 | 8588.5853 | 8588.5853 | 8588.5853 | 8588.5853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1664 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 27718.3565 | 0.2 | 0.3 | 43240.6361 |  |  |  |  | 0 | 8536.759 | 8536.759 | 8536.759 | 8536.759 | 8536.759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1665 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 5346.0049 | 5346.0049 | 5346.0049 | 5346.0049 | 5346.0049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1666 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16678.8439 | 0.2 | 0.3 | 26018.9964 |  |  |  |  | 0 | 5204.2232 | 5204.2232 | 5204.2232 | 5204.2232 | 5204.2232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1667 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16678.5714 | 0.2 | 0.3 | 26018.5714 |  |  |  |  | 0 | 5206.3768 | 5206.3768 | 5206.3768 | 5206.3768 | 5206.3768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1668 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 44377.9381 | 0.2 | 0.3 | 69229.5834 |  |  |  |  | 0 | 5272.8371 | 5272.8371 | 5272.8371 | 5272.8371 | 5272.8371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1669 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 23942.8865 | 0.2 | 0.3 | 37350.9029 |  |  |  |  | 0 | 5046.5273 | 5046.5273 | 5046.5273 | 5046.5273 | 5046.5273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1670 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16767.1414 | 0.2 | 0.3 | 26156.7406 |  |  |  |  | 0 | 7549.6394 | 7549.6394 | 7549.6394 | 7549.6394 | 7549.6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1671 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 27572.3281 | 0.2 | 0.3 | 43012.8319 |  |  |  |  | 0 | 4687.3274 | 4687.3274 | 4687.3274 | 4687.3274 | 4687.3274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1672 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 24968.1125 | 0.2 | 0.3 | 38950.2554 |  |  |  |  | 0 | 9682.696 | 9682.696 | 9682.696 | 9682.696 | 9682.696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1673 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 2244.3964 | 0.2 | 0.3 | 3501.2584 |  |  |  |  | 0 | 5203.2389 | 5203.2389 | 5203.2389 | 5203.2389 | 5203.2389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1674 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 23100.8339 | 0.2 | 0.3 | 36037.3008 |  |  |  |  | 0 | 5203.8002 | 5203.8002 | 5203.8002 | 5203.8002 | 5203.8002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1675 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 8333.3323 | 0.2 | 0.3 | 12999.9984 |  |  |  |  | 0 | 5204.434 | 5204.434 | 5204.434 | 5204.434 | 5204.434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1676 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 1857.8516 | 0.2 | 0.3 | 2898.2485 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1677 | DAVIE | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16673.6885 | 0.2 | 0.3 | 26010.9541 |  |  |  |  | 0 | 5200.8223 | 5200.8223 | 5200.8223 | 5200.8223 | 5200.8223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1678 | DAVIE | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 6711.8803 | 0.2 | 0.3 | 10470.5333 |  |  |  |  | 0 | 5203.6593 | 5203.6593 | 5203.6593 | 5203.6593 | 5203.6593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1679 | DAVIE | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 10870.6363 | 0.2 | 0.3 | 16958.1926 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1680 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 6884.8915 | 0.2 | 0.3 | 10740.4308 |  |  |  |  | 0 | 5205.8558 | 5205.8558 | 5205.8558 | 5205.8558 | 5205.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1681 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 14374.7881 | 0.2 | 0.3 | 22424.6694 |  |  |  |  | 0 | 6608.7279 | 6608.7279 | 6608.7279 | 6608.7279 | 6608.7279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1682 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 24695.2539 | 0.2 | 0.3 | 38524.5961 |  |  |  |  | 0 | 4187.8208 | 4187.8208 | 4187.8208 | 4187.8208 | 4187.8208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1683 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 17705.0139 | 0.2 | 0.3 | 27619.8217 |  |  |  |  | 0 | 8268.8485 | 8268.8485 | 8268.8485 | 8268.8485 | 8268.8485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1684 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 35256.0329 | 0.2 | 0.3 | 54999.4114 |  |  |  |  | 0 | 6499.8175 | 6499.8175 | 6499.8175 | 6499.8175 | 6499.8175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1685 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 18056.5493 | 0.2 | 0.3 | 28168.217 |  |  |  |  | 0 | 5966.9925 | 5966.9925 | 5966.9925 | 5966.9925 | 5966.9925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1686 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 28523.8889 | 0.2 | 0.3 | 44497.2667 |  |  |  |  | 0 | 5203.2923 | 5203.2923 | 5203.2923 | 5203.2923 | 5203.2923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1687 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 8333.2968 | 0.2 | 0.3 | 12999.943 |  |  |  |  | 0 | 5203.6896 | 5203.6896 | 5203.6896 | 5203.6896 | 5203.6896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1688 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 19261.6441 | 0.2 | 0.3 | 30048.1648 |  |  |  |  | 0 | 5204.2359 | 5204.2359 | 5204.2359 | 5204.2359 | 5204.2359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1689 | DAVIE | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 17744.2133 | 0.2 | 0.3 | 27680.9728 |  |  |  |  | 0 | 5204.6063 | 5204.6063 | 5204.6063 | 5204.6063 | 5204.6063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1690 | DAVIE | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16674.9755 | 0.2 | 0.3 | 26012.9617 |  |  |  |  | 0 | 5226.2243 | 5226.2243 | 5226.2243 | 5226.2243 | 5226.2243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1691 | DAVIE | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 28838.877 | 0.2 | 0.3 | 44988.6481 |  |  |  |  | 0 | 5203.6651 | 5203.6651 | 5203.6651 | 5203.6651 | 5203.6651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1692 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 24076.9868 | 0.2 | 0.3 | 37560.0994 |  |  |  |  | 0 | 5204.3201 | 5204.3201 | 5204.3201 | 5204.3201 | 5204.3201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1693 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16679.1765 | 0.2 | 0.3 | 26019.5153 |  |  |  |  | 0 | 6759.0755 | 6759.0755 | 6759.0755 | 6759.0755 | 6759.0755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1694 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 17728.4628 | 0.2 | 0.3 | 27656.402 |  |  |  |  | 0 | 3993.5085 | 3993.5085 | 3993.5085 | 3993.5085 | 3993.5085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1695 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 32364.1271 | 0.2 | 0.3 | 50488.0382 |  |  |  |  | 0 | 8690.6836 | 8690.6836 | 8690.6836 | 8690.6836 | 8690.6836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1696 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 2715.4483 | 2715.4483 | 2715.4483 | 2715.4483 | 2715.4483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1697 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6624 |  |  |  |  | 0 | 5296.0178 | 5296.0178 | 5296.0178 | 5296.0178 | 5296.0178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1698 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 16946.7096 | 0.2 | 0.3 | 26436.867 |  |  |  |  | 0 | 8859.9275 | 8859.9275 | 8859.9275 | 8859.9275 | 8859.9275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1699 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 42246.7593 | 0.2 | 0.3 | 65904.9446 |  |  |  |  | 0 | 3324.5588 | 3324.5588 | 3324.5588 | 3324.5588 | 3324.5588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1700 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 31339.0335 | 0.2 | 0.3 | 48888.8922 |  |  |  |  | 0 | 9783.9535 | 9783.9535 | 9783.9535 | 9783.9535 | 9783.9535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1701 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 15325.4006 | 0.2 | 0.3 | 23907.6249 |  |  |  |  | 0 | 6386.655 | 6386.655 | 6386.655 | 6386.655 | 6386.655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1702 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 25993.2502 | 0.2 | 0.3 | 40549.4703 |  |  |  |  | 0 | 6046.8833 | 6046.8833 | 6046.8833 | 6046.8833 | 6046.8833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1703 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16667.0099 | 0.2 | 0.3 | 26000.5355 |  |  |  |  | 0 | 9868.3008 | 9868.3008 | 9868.3008 | 9868.3008 | 9868.3008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1704 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 4435.6841 | 0.2 | 0.3 | 6919.6671 |  |  |  |  | 0 | 5941.4314 | 5941.4314 | 5941.4314 | 5941.4314 | 5941.4314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1705 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 28145.1241 | 0.2 | 0.3 | 43906.3936 |  |  |  |  | 0 | 5761.6076 | 5761.6076 | 5761.6076 | 5761.6076 | 5761.6076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1706 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 24882.6839 | 0.2 | 0.3 | 38816.9869 |  |  |  |  | 0 | 9636.1564 | 9636.1564 | 9636.1564 | 9636.1564 | 9636.1564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1707 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 23174.0985 | 0.2 | 0.3 | 36151.5937 |  |  |  |  | 0 | 4047.2156 | 4047.2156 | 4047.2156 | 4047.2156 | 4047.2156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1708 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 37989.4337 | 0.2 | 0.3 | 59263.5166 |  |  |  |  | 0 | 1765.2709 | 1765.2709 | 1765.2709 | 1765.2709 | 1765.2709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1709 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 44636.7236 | 0.2 | 0.3 | 69633.2888 |  |  |  |  | 0 | 8980.2493 | 8980.2493 | 8980.2493 | 8980.2493 | 8980.2493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1710 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 41412.5419 | 0.2 | 0.3 | 64603.5653 |  |  |  |  | 0 | 6123.8189 | 6123.8189 | 6123.8189 | 6123.8189 | 6123.8189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1711 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 5921.4719 | 0.2 | 0.3 | 9237.4961 |  |  |  |  | 0 | 5206.4795 | 5206.4795 | 5206.4795 | 5206.4795 | 5206.4795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1712 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 30399.2255 | 0.2 | 0.3 | 47422.7918 |  |  |  |  | 0 | 9405.5965 | 9405.5965 | 9405.5965 | 9405.5965 | 9405.5965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1713 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 31344.3563 | 0.2 | 0.3 | 48897.1959 |  |  |  |  | 0 | 5420.4233 | 5420.4233 | 5420.4233 | 5420.4233 | 5420.4233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1714 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 30620.0133 | 0.2 | 0.3 | 47767.2207 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1715 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 31343.1169 | 0.2 | 0.3 | 48895.2624 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1716 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16666.5485 | 0.2 | 0.3 | 25999.8157 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1717 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 20061.8001 | 0.2 | 0.3 | 31296.4081 |  |  |  |  | 0 | 5200.9192 | 5200.9192 | 5200.9192 | 5200.9192 | 5200.9192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1718 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 13649.8939 | 0.2 | 0.3 | 21293.8344 |  |  |  |  | 0 | 5201.2887 | 5201.2887 | 5201.2887 | 5201.2887 | 5201.2887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1719 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16679.3608 | 0.2 | 0.3 | 26019.8028 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1720 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16655.0329 | 0.2 | 0.3 | 25981.8513 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1721 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16680.2831 | 0.2 | 0.3 | 26021.2416 |  |  |  |  | 0 | 5201.2072 | 5201.2072 | 5201.2072 | 5201.2072 | 5201.2072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1722 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 10563.0671 | 0.2 | 0.3 | 16478.3846 |  |  |  |  | 0 | 5201.0799 | 5201.0799 | 5201.0799 | 5201.0799 | 5201.0799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1723 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16673.8717 | 0.2 | 0.3 | 26011.2399 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1724 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16673.1617 | 0.2 | 0.3 | 26010.1322 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1725 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16677.7768 | 0.2 | 0.3 | 26017.3318 |  |  |  |  | 0 | 5201.0741 | 5201.0741 | 5201.0741 | 5201.0741 | 5201.0741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1726 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 21027.4489 | 0.2 | 0.3 | 32802.8203 |  |  |  |  | 0 | 9778.2058 | 9778.2058 | 9778.2058 | 9778.2058 | 9778.2058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1727 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16733.1399 | 0.2 | 0.3 | 26103.6982 |  |  |  |  | 0 | 5201.2 | 5201.2 | 5201.2 | 5201.2 | 5201.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1728 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 14713.1359 | 0.2 | 0.3 | 22952.4921 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1729 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16763.6064 | 0.2 | 0.3 | 26151.226 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1730 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16808.0843 | 0.2 | 0.3 | 26220.6116 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1731 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16673.1617 | 0.2 | 0.3 | 26010.1322 |  |  |  |  | 0 | 5201.3426 | 5201.3426 | 5201.3426 | 5201.3426 | 5201.3426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1732 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16801.9004 | 0.2 | 0.3 | 26210.9646 |  |  |  |  | 0 | 6757.1627 | 6757.1627 | 6757.1627 | 6757.1627 | 6757.1627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1733 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 14968.4419 | 0.2 | 0.3 | 23350.7693 |  |  |  |  | 0 | 5200.7716 | 5200.7716 | 5200.7716 | 5200.7716 | 5200.7716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1734 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 24657.9505 | 0.2 | 0.3 | 38466.4027 |  |  |  |  | 0 | 5203.7727 | 5203.7727 | 5203.7727 | 5203.7727 | 5203.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1735 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 28318.8368 | 0.2 | 0.3 | 44177.3854 |  |  |  |  | 0 | 10884.416 | 10884.416 | 10884.416 | 10884.416 | 10884.416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1736 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16723.9298 | 0.2 | 0.3 | 26089.3305 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1737 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 17049.5977 | 0.2 | 0.3 | 26597.3725 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1738 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 17226.1515 | 0.2 | 0.3 | 26872.7964 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1739 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 18519.6059 | 0.2 | 0.3 | 28890.5853 |  |  |  |  | 0 | 5201.151 | 5201.151 | 5201.151 | 5201.151 | 5201.151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1740 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 27678.8551 | 0.2 | 0.3 | 43179.0139 |  |  |  |  | 0 | 9777.3253 | 9777.3253 | 9777.3253 | 9777.3253 | 9777.3253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1741 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16674.2339 | 0.2 | 0.3 | 26011.8048 |  |  |  |  | 0 | 5200.9977 | 5200.9977 | 5200.9977 | 5200.9977 | 5200.9977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1742 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16681.4117 | 0.2 | 0.3 | 26023.0023 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1743 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 7835.8811 | 0.2 | 0.3 | 12223.9745 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1744 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 16677.8571 | 0.2 | 0.3 | 26017.4571 |  |  |  |  | 0 | 5201.1536 | 5201.1536 | 5201.1536 | 5201.1536 | 5201.1536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1745 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 16858.1736 | 0.2 | 0.3 | 26298.7508 |  |  |  |  | 0 | 5943.6027 | 5943.6027 | 5943.6027 | 5943.6027 | 5943.6027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1746 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 16797.4137 | 0.2 | 0.3 | 26203.9653 |  |  |  |  | 0 | 5201.0731 | 5201.0731 | 5201.0731 | 5201.0731 | 5201.0731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1747 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 13755.2601 | 0.2 | 0.3 | 21458.2058 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1748 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 24091.3716 | 0.2 | 0.3 | 37582.5397 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1749 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16674.8671 | 0.2 | 0.3 | 26012.7927 |  |  |  |  | 0 | 5201.2267 | 5201.2267 | 5201.2267 | 5201.2267 | 5201.2267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1750 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 29430.1983 | 0.2 | 0.3 | 45911.1093 |  |  |  |  | 0 | 9778.7835 | 9778.7835 | 9778.7835 | 9778.7835 | 9778.7835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1751 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16676.4431 | 0.2 | 0.3 | 26015.2513 |  |  |  |  | 0 | 5200.6969 | 5200.6969 | 5200.6969 | 5200.6969 | 5200.6969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1752 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 20149.3761 | 0.2 | 0.3 | 31433.0268 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1753 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16930.6191 | 0.2 | 0.3 | 26411.7658 |  |  |  |  | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1754 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 26079.4593 | 0.2 | 0.3 | 40683.9565 |  |  |  |  | 0 | 5202.333 | 5202.333 | 5202.333 | 5202.333 | 5202.333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1755 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 25346.2324 | 0.2 | 0.3 | 39540.1225 |  |  |  |  | 0 | 7414.2023 | 7414.2023 | 7414.2023 | 7414.2023 | 7414.2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1756 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 20101.2126 | 0.2 | 0.3 | 31357.8917 |  |  |  |  | 0 | 9854.1371 | 9854.1371 | 9854.1371 | 9854.1371 | 9854.1371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1757 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 18565.4512 | 0.2 | 0.3 | 28962.1039 |  |  |  |  | 0 | 9806.077 | 9806.077 | 9806.077 | 9806.077 | 9806.077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1758 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 24652.151 | 0.2 | 0.3 | 38457.3556 |  |  |  |  | 0 | 9126.0244 | 9126.0244 | 9126.0244 | 9126.0244 | 9126.0244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1759 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 19552.4951 | 0.2 | 0.3 | 30501.8923 |  |  |  |  | 0 | 10793.6941 | 10793.6941 | 10793.6941 | 10793.6941 | 10793.6941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1760 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 3942.9074 | 0.2 | 0.3 | 6150.9355 |  |  |  |  | 0 | 5201.0449 | 5201.0449 | 5201.0449 | 5201.0449 | 5201.0449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1761 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 16703.736 | 0.2 | 0.3 | 26057.8282 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1762 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 20568.5109 | 0.2 | 0.3 | 32086.877 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1763 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 18939.1241 | 0.2 | 0.3 | 29545.0335 |  |  |  |  | 0 | 5201.0135 | 5201.0135 | 5201.0135 | 5201.0135 | 5201.0135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1764 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 9694.2714 | 0.2 | 0.3 | 15123.0634 |  |  |  |  | 0 | 9778.67 | 9778.67 | 9778.67 | 9778.67 | 9778.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1765 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 19283.7163 | 0.2 | 0.3 | 30082.5974 |  |  |  |  | 0 | 5200.9949 | 5200.9949 | 5200.9949 | 5200.9949 | 5200.9949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1766 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 21223.2572 | 0.2 | 0.3 | 33108.2812 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1767 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 16777.6645 | 0.2 | 0.3 | 26173.1567 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1768 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 18426.2758 | 0.2 | 0.3 | 28744.9902 |  |  |  |  | 0 | 5201.0518 | 5201.0518 | 5201.0518 | 5201.0518 | 5201.0518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1769 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 17139.6739 | 0.2 | 0.3 | 26737.8913 |  |  |  |  | 0 | 6054.888 | 6054.888 | 6054.888 | 6054.888 | 6054.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1770 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 17776.9949 | 0.2 | 0.3 | 27732.1121 |  |  |  |  | 0 | 5200.9667 | 5200.9667 | 5200.9667 | 5200.9667 | 5200.9667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1771 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 16672.2579 | 0.2 | 0.3 | 26008.7223 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1772 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 18274.5186 | 0.2 | 0.3 | 28508.249 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1773 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 31923.2039 | 0.2 | 0.3 | 49800.1981 |  |  |  |  | 0 | 5201.0862 | 5201.0862 | 5201.0862 | 5201.0862 | 5201.0862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1774 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 33544.6395 | 0.2 | 0.3 | 52329.6376 |  |  |  |  | 0 | 9777.3186 | 9777.3186 | 9777.3186 | 9777.3186 | 9777.3186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1775 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 17878.6102 | 0.2 | 0.3 | 27890.6319 |  |  |  |  | 0 | 5201.0371 | 5201.0371 | 5201.0371 | 5201.0371 | 5201.0371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1776 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 9207.4888 | 0.2 | 0.3 | 14363.6825 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1777 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 9279.6561 | 0.2 | 0.3 | 14476.2636 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1778 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 25995.3755 | 0.2 | 0.3 | 40552.7858 |  |  |  |  | 0 | 5200.9846 | 5200.9846 | 5200.9846 | 5200.9846 | 5200.9846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1779 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 98.0767 | 0.2 | 0.3 | 152.9996 |  |  |  |  | 0 | 9070.8115 | 9070.8115 | 9070.8115 | 9070.8115 | 9070.8115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1780 | COOPER CITY | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 1593.9905 | 0.2 | 0.3 | 2486.6251 |  |  |  |  | 0 | 5202.4895 | 5202.4895 | 5202.4895 | 5202.4895 | 5202.4895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1781 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 13613.0209 | 0.2 | 0.3 | 21236.3127 |  |  |  |  | 0 | 5203.2713 | 5203.2713 | 5203.2713 | 5203.2713 | 5203.2713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1782 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16877.5232 | 0.2 | 0.3 | 26328.9362 |  |  |  |  | 0 | 5203.2006 | 5203.2006 | 5203.2006 | 5203.2006 | 5203.2006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1783 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 8699.0423 | 0.2 | 0.3 | 13570.5059 |  |  |  |  | 0 | 132.7238 | 132.7238 | 132.7238 | 132.7238 | 132.7238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1784 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 11957.3667 | 0.2 | 0.3 | 18653.4921 |  |  |  |  | 0 | 5201.3236 | 5201.3236 | 5201.3236 | 5201.3236 | 5201.3236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1785 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 7150.4585 | 0.2 | 0.3 | 11154.7153 |  |  |  |  | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1786 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 16678.2118 | 0.2 | 0.3 | 26018.0104 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1787 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 5122.2688 | 0.2 | 0.3 | 7990.7393 |  |  |  |  | 0 | 5201.2221 | 5201.2221 | 5201.2221 | 5201.2221 | 5201.2221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1788 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 18747.141 | 0.2 | 0.3 | 29245.54 |  |  |  |  | 0 | 9779.0802 | 9779.0802 | 9779.0802 | 9779.0802 | 9779.0802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1789 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16817.7075 | 0.2 | 0.3 | 26235.6236 |  |  |  |  | 0 | 5200.9257 | 5200.9257 | 5200.9257 | 5200.9257 | 5200.9257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1790 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 30641.6467 | 0.2 | 0.3 | 47800.9688 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1791 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 15173.991 | 0.2 | 0.3 | 23671.426 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1792 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 21551.1821 | 0.2 | 0.3 | 33619.8441 |  |  |  |  | 0 | 5200.9641 | 5200.9641 | 5200.9641 | 5200.9641 | 5200.9641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1793 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 29852.3297 | 0.2 | 0.3 | 46569.6344 |  |  |  |  | 0 | 6166.8415 | 6166.8415 | 6166.8415 | 6166.8415 | 6166.8415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1794 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 24330.8749 | 0.2 | 0.3 | 37956.1649 |  |  |  |  | 0 | 5201.1471 | 5201.1471 | 5201.1471 | 5201.1471 | 5201.1471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1795 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16673.2323 | 0.2 | 0.3 | 26010.2424 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1796 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 23820.9514 | 0.2 | 0.3 | 37160.6842 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1797 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 23852.0481 | 0.2 | 0.3 | 37209.1951 |  |  |  |  | 0 | 5201.2041 | 5201.2041 | 5201.2041 | 5201.2041 | 5201.2041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1798 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 23346.1748 | 0.2 | 0.3 | 36420.0327 |  |  |  |  | 0 | 9778.9752 | 9778.9752 | 9778.9752 | 9778.9752 | 9778.9752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1799 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16667.4163 | 0.2 | 0.3 | 26001.1694 |  |  |  |  | 0 | 5201.0001 | 5201.0001 | 5201.0001 | 5201.0001 | 5201.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1800 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 9433.8208 | 0.2 | 0.3 | 14716.7604 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1801 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 9945.1421 | 0.2 | 0.3 | 15514.4217 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1802 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16711.2357 | 0.2 | 0.3 | 26069.5277 |  |  |  |  | 0 | 5201.0233 | 5201.0233 | 5201.0233 | 5201.0233 | 5201.0233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1803 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 32598.0726 | 0.2 | 0.3 | 50852.9933 |  |  |  |  | 0 | 9328.9633 | 9328.9633 | 9328.9633 | 9328.9633 | 9328.9633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1804 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 10406.2753 | 0.2 | 0.3 | 16233.7895 |  |  |  |  | 0 | 5348.6611 | 5348.6611 | 5348.6611 | 5348.6611 | 5348.6611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1805 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 24216.1973 | 0.2 | 0.3 | 37777.2677 |  |  |  |  | 0 | 5253.6669 | 5253.6669 | 5253.6669 | 5253.6669 | 5253.6669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1806 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 32049.2563 | 0.2 | 0.3 | 49996.8398 |  |  |  |  | 0 | 5206.9272 | 5206.9272 | 5206.9272 | 5206.9272 | 5206.9272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1807 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 33358.0796 | 0.2 | 0.3 | 52038.6042 |  |  |  |  | 0 | 5201.1117 | 5201.1117 | 5201.1117 | 5201.1117 | 5201.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1808 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 33358.9427 | 0.2 | 0.3 | 52039.9507 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1809 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 23322.9747 | 0.2 | 0.3 | 36383.8405 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1810 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16674.2553 | 0.2 | 0.3 | 26011.8382 |  |  |  |  | 0 | 5201.1066 | 5201.1066 | 5201.1066 | 5201.1066 | 5201.1066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1811 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 19558.9861 | 0.2 | 0.3 | 30512.0183 |  |  |  |  | 0 | 9777.8319 | 9777.8319 | 9777.8319 | 9777.8319 | 9777.8319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1812 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 17416.4533 | 0.2 | 0.3 | 27169.6671 |  |  |  |  | 0 | 5200.949 | 5200.949 | 5200.949 | 5200.949 | 5200.949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1813 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 26541.9263 | 0.2 | 0.3 | 41405.405 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1814 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 31353.4727 | 0.2 | 0.3 | 48911.4174 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1815 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 30544.2235 | 0.2 | 0.3 | 47648.9887 |  |  |  |  | 0 | 5201.0771 | 5201.0771 | 5201.0771 | 5201.0771 | 5201.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1816 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 24444.9456 | 0.2 | 0.3 | 38134.1151 |  |  |  |  | 0 | 9777.9499 | 9777.9499 | 9777.9499 | 9777.9499 | 9777.9499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1817 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 11008.3527 | 0.2 | 0.3 | 17173.0302 |  |  |  |  | 0 | 6672.2117 | 6672.2117 | 6672.2117 | 6672.2117 | 6672.2117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1818 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16724.2222 | 0.2 | 0.3 | 26089.7866 |  |  |  |  | 0 | 6730.1686 | 6730.1686 | 6730.1686 | 6730.1686 | 6730.1686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1819 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 35403.3141 | 0.2 | 0.3 | 55229.1699 |  |  |  |  | 0 | 6921.6662 | 6921.6662 | 6921.6662 | 6921.6662 | 6921.6662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1820 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 25068.2411 | 0.2 | 0.3 | 39106.4561 |  |  |  |  | 0 | 6993.461 | 6993.461 | 6993.461 | 6993.461 | 6993.461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1821 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 19744.6193 | 0.2 | 0.3 | 30801.6061 |  |  |  |  | 0 | 9779.9299 | 9779.9299 | 9779.9299 | 9779.9299 | 9779.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1822 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16800.1093 | 0.2 | 0.3 | 26208.1706 |  |  |  |  | 0 | 5201.0921 | 5201.0921 | 5201.0921 | 5201.0921 | 5201.0921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1823 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 3471.6065 | 0.2 | 0.3 | 5415.7062 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1824 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16672.8061 | 0.2 | 0.3 | 26009.5776 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1825 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16695.0573 | 0.2 | 0.3 | 26044.2893 |  |  |  |  | 0 | 5201.1657 | 5201.1657 | 5201.1657 | 5201.1657 | 5201.1657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1826 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16728.069 | 0.2 | 0.3 | 26095.7876 |  |  |  |  | 0 | 10666.6302 | 10666.6302 | 10666.6302 | 10666.6302 | 10666.6302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1827 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 25466.9667 | 0.2 | 0.3 | 39728.468 |  |  |  |  | 0 | 7288.6029 | 7288.6029 | 7288.6029 | 7288.6029 | 7288.6029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1828 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 25253.9775 | 0.2 | 0.3 | 39396.205 |  |  |  |  | 0 | 5723.1049 | 5723.1049 | 5723.1049 | 5723.1049 | 5723.1049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1829 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16673.4351 | 0.2 | 0.3 | 26010.5587 |  |  |  |  | 0 | 5635.7159 | 5635.7159 | 5635.7159 | 5635.7159 | 5635.7159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1830 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16672.8652 | 0.2 | 0.3 | 26009.6697 |  |  |  |  | 0 | 5201.5638 | 5201.5638 | 5201.5638 | 5201.5638 | 5201.5638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1831 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 30268.8624 | 0.2 | 0.3 | 47219.4253 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1832 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 25508.8477 | 0.2 | 0.3 | 39793.8024 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1833 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 29004.6179 | 0.2 | 0.3 | 45247.2039 |  |  |  |  | 0 | 5201.4478 | 5201.4478 | 5201.4478 | 5201.4478 | 5201.4478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1834 | DAVIE | 70402 | Private | 2036 | 5 | Swales | 66.6667 | 24090.3815 | 0.2 | 0.3 | 37580.9952 |  |  |  |  | 0 | 9778.4969 | 9778.4969 | 9778.4969 | 9778.4969 | 9778.4969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1835 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 29988.9798 | 0.2 | 0.3 | 46782.8085 |  |  |  |  | 0 | 5200.9193 | 5200.9193 | 5200.9193 | 5200.9193 | 5200.9193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1836 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 16674.5217 | 0.2 | 0.3 | 26012.2539 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1837 | COOPER CITY | 70402 | Public | 2036 | 5 | Swales | 66.6667 | 21440.2085 | 0.2 | 0.3 | 33446.7252 |  |  |  |  | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1838 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16721.6618 | 0.2 | 0.3 | 26085.7924 |  |  |  |  | 0 | 5200.9952 | 5200.9952 | 5200.9952 | 5200.9952 | 5200.9952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1839 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 18686.5505 | 0.2 | 0.3 | 29151.0187 |  |  |  |  | 0 | 6330.425 | 6330.425 | 6330.425 | 6330.425 | 6330.425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1840 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 23120.267 | 0.2 | 0.3 | 36067.6165 |  |  |  |  | 0 | 5200.9834 | 5200.9834 | 5200.9834 | 5200.9834 | 5200.9834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1841 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 24956.6947 | 0.2 | 0.3 | 38932.4438 |  |  |  |  | 0 | 5201.0417 | 5201.0417 | 5201.0417 | 5201.0417 | 5201.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1842 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 24937.4577 | 0.2 | 0.3 | 38902.4341 |  |  |  |  | 0 | 5200.8447 | 5200.8447 | 5200.8447 | 5200.8447 | 5200.8447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1843 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 31340.4849 | 0.2 | 0.3 | 48891.1564 |  |  |  |  | 0 | 5201.0547 | 5201.0547 | 5201.0547 | 5201.0547 | 5201.0547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1844 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 24574.6575 | 0.2 | 0.3 | 38336.4656 |  |  |  |  | 0 | 7566.1824 | 7566.1824 | 7566.1824 | 7566.1824 | 7566.1824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1845 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 28052.4547 | 0.2 | 0.3 | 43761.8294 |  |  |  |  | 0 | 5200.8382 | 5200.8382 | 5200.8382 | 5200.8382 | 5200.8382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1846 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 42961.7672 | 0.2 | 0.3 | 67020.3568 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1847 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 15997.4689 | 0.2 | 0.3 | 24956.0514 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1848 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 33392.9851 | 0.2 | 0.3 | 52093.0567 |  |  |  |  | 0 | 8149.2003 | 8149.2003 | 8149.2003 | 8149.2003 | 8149.2003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1849 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 21831.2781 | 0.2 | 0.3 | 34056.7938 |  |  |  |  | 0 | 4562.0187 | 4562.0187 | 4562.0187 | 4562.0187 | 4562.0187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1850 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 7922.6682 | 7922.6682 | 7922.6682 | 7922.6682 | 7922.6682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1851 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 20215.2685 | 0.2 | 0.3 | 31535.8188 |  |  |  |  | 0 | 9431.775 | 9431.775 | 9431.775 | 9431.775 | 9431.775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1852 | COOPER CITY | 70401 | Private | 2036 | 5 | Swales | 66.6667 | 7394.7294 | 0.2 | 0.3 | 11535.7779 |  |  |  |  | 0 | 6147.3873 | 6147.3873 | 6147.3873 | 6147.3873 | 6147.3873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1853 | COOPER CITY | 70401 | Public | 2036 | 5 | Swales | 66.6667 | 21689.4998 | 0.2 | 0.3 | 33835.6197 |  |  |  |  | 0 | 5201.1408 | 5201.1408 | 5201.1408 | 5201.1408 | 5201.1408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1854 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 11490.8028 | 0.2 | 0.3 | 17925.6524 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1855 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 15889.6513 | 0.2 | 0.3 | 24787.8561 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1856 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16170.3029 | 0.2 | 0.3 | 25225.6725 |  |  |  |  | 0 | 5201.0299 | 5201.0299 | 5201.0299 | 5201.0299 | 5201.0299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1857 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16697.5254 | 0.2 | 0.3 | 26048.1396 |  |  |  |  | 0 | 9777.1325 | 9777.1325 | 9777.1325 | 9777.1325 | 9777.1325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1858 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 10621.1144 | 0.2 | 0.3 | 16568.9385 |  |  |  |  | 0 | 5200.797 | 5200.797 | 5200.797 | 5200.797 | 5200.797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1859 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 20503.8425 | 0.2 | 0.3 | 31985.9942 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1860 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 30114.1532 | 0.2 | 0.3 | 46978.079 |  |  |  |  | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1861 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 17682.0521 | 0.2 | 0.3 | 27584.0013 |  |  |  |  | 0 | 5200.9124 | 5200.9124 | 5200.9124 | 5200.9124 | 5200.9124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1862 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 23274.1082 | 0.2 | 0.3 | 36307.6088 |  |  |  |  | 0 | 6442.7407 | 6442.7407 | 6442.7407 | 6442.7407 | 6442.7407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1863 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 43246.7453 | 0.2 | 0.3 | 67464.9226 |  |  |  |  | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1864 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 34525.2681 | 0.2 | 0.3 | 53859.4183 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1865 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16744.5874 | 0.2 | 0.3 | 26121.5563 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1866 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 29653.1925 | 0.2 | 0.3 | 46258.9802 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1867 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 20968.4172 | 0.2 | 0.3 | 32710.7308 |  |  |  |  | 0 | 7473.9647 | 7473.9647 | 7473.9647 | 7473.9647 | 7473.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1868 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 779.9936 | 0.2 | 0.3 | 1216.79 |  |  |  |  | 0 | 5201.1169 | 5201.1169 | 5201.1169 | 5201.1169 | 5201.1169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1869 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 3110.3491 | 0.2 | 0.3 | 4852.1445 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1870 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 13691.812 | 0.2 | 0.3 | 21359.2267 |  |  |  |  | 0 | 5201.0861 | 5201.0861 | 5201.0861 | 5201.0861 | 5201.0861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1871 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 25737.7615 | 0.2 | 0.3 | 40150.908 |  |  |  |  | 0 | 8028.2201 | 8028.2201 | 8028.2201 | 8028.2201 | 8028.2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1872 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 18841.501 | 0.2 | 0.3 | 29392.7416 |  |  |  |  | 0 | 5586.079 | 5586.079 | 5586.079 | 5586.079 | 5586.079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1873 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 33798.4085 | 0.2 | 0.3 | 52725.5173 |  |  |  |  | 0 | 5622.4833 | 5622.4833 | 5622.4833 | 5622.4833 | 5622.4833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1874 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 18604.4895 | 0.2 | 0.3 | 29023.0036 |  |  |  |  | 0 | 5133.1314 | 5133.1314 | 5133.1314 | 5133.1314 | 5133.1314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1875 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 28302.4642 | 0.2 | 0.3 | 44151.8442 |  |  |  |  | 0 | 525.5198 | 525.5198 | 525.5198 | 525.5198 | 525.5198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1876 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 33334.7881 | 0.2 | 0.3 | 52002.2695 |  |  |  |  | 0 | 5464.5685 | 5464.5685 | 5464.5685 | 5464.5685 | 5464.5685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1877 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 31330.0901 | 0.2 | 0.3 | 48874.9405 |  |  |  |  | 0 | 5582.7956 | 5582.7956 | 5582.7956 | 5582.7956 | 5582.7956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1878 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16691.2369 | 0.2 | 0.3 | 26038.3296 |  |  |  |  | 0 | 5688.0538 | 5688.0538 | 5688.0538 | 5688.0538 | 5688.0538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1879 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 30699.5573 | 0.2 | 0.3 | 47891.3094 |  |  |  |  | 0 | 5715.6462 | 5715.6462 | 5715.6462 | 5715.6462 | 5715.6462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1880 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16671.1942 | 0.2 | 0.3 | 26007.063 |  |  |  |  | 0 | 9779.5107 | 9779.5107 | 9779.5107 | 9779.5107 | 9779.5107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1881 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 14124.4039 | 0.2 | 0.3 | 22034.0701 |  |  |  |  | 0 | 6020.4864 | 6020.4864 | 6020.4864 | 6020.4864 | 6020.4864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1882 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 5431.6431 | 0.2 | 0.3 | 8473.3632 |  |  |  |  | 0 | 6106.2468 | 6106.2468 | 6106.2468 | 6106.2468 | 6106.2468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1883 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 23288.7142 | 0.2 | 0.3 | 36330.3942 |  |  |  |  | 0 | 6224.6122 | 6224.6122 | 6224.6122 | 6224.6122 | 6224.6122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1884 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 4191.3758 | 0.2 | 0.3 | 6538.5462 |  |  |  |  | 0 | 6337.9935 | 6337.9935 | 6337.9935 | 6337.9935 | 6337.9935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1885 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 22782.0987 | 0.2 | 0.3 | 35540.074 |  |  |  |  | 0 | 6547.8011 | 6547.8011 | 6547.8011 | 6547.8011 | 6547.8011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1886 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 28937.4438 | 0.2 | 0.3 | 45142.4123 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1887 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16677.1623 | 0.2 | 0.3 | 26016.3731 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1888 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 15470.1111 | 0.2 | 0.3 | 24133.3733 |  |  |  |  | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1889 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16680.5643 | 0.2 | 0.3 | 26021.6803 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1890 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16706.7003 | 0.2 | 0.3 | 26062.4525 |  |  |  |  | 0 | 7329.6395 | 7329.6395 | 7329.6395 | 7329.6395 | 7329.6395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1891 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 14294.7249 | 0.2 | 0.3 | 22299.7709 |  |  |  |  | 0 | 7192.2143 | 7192.2143 | 7192.2143 | 7192.2143 | 7192.2143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1892 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 13988.2551 | 0.2 | 0.3 | 21821.6779 |  |  |  |  | 0 | 7301.1129 | 7301.1129 | 7301.1129 | 7301.1129 | 7301.1129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1893 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 17683.1163 | 0.2 | 0.3 | 27585.6614 |  |  |  |  | 0 | 5266.7008 | 5266.7008 | 5266.7008 | 5266.7008 | 5266.7008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1894 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16763.5201 | 0.2 | 0.3 | 26151.0914 |  |  |  |  | 0 | 6064.4331 | 6064.4331 | 6064.4331 | 6064.4331 | 6064.4331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1895 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 19760.7797 | 0.2 | 0.3 | 30826.8164 |  |  |  |  | 0 | 5531.0866 | 5531.0866 | 5531.0866 | 5531.0866 | 5531.0866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1896 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 29334.3322 | 0.2 | 0.3 | 45761.5582 |  |  |  |  | 0 | 5562.6812 | 5562.6812 | 5562.6812 | 5562.6812 | 5562.6812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1897 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 17653.2905 | 0.2 | 0.3 | 27539.1332 |  |  |  |  | 0 | 4787.0718 | 4787.0718 | 4787.0718 | 4787.0718 | 4787.0718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1898 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 3329.8271 | 0.2 | 0.3 | 5194.5302 |  |  |  |  | 0 | 5200.4066 | 5200.4066 | 5200.4066 | 5200.4066 | 5200.4066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1899 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 10050.5651 | 0.2 | 0.3 | 15678.8815 |  |  |  |  | 0 | 5201.0393 | 5201.0393 | 5201.0393 | 5201.0393 | 5201.0393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1900 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 20668.8343 | 0.2 | 0.3 | 32243.3815 |  |  |  |  | 0 | 5200.5648 | 5200.5648 | 5200.5648 | 5200.5648 | 5200.5648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1901 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 30080.1585 | 0.2 | 0.3 | 46925.0472 |  |  |  |  | 0 | 5201.1033 | 5201.1033 | 5201.1033 | 5201.1033 | 5201.1033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1902 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 17968.2249 | 0.2 | 0.3 | 28030.4308 |  |  |  |  | 0 | 5201.4478 | 5201.4478 | 5201.4478 | 5201.4478 | 5201.4478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1903 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 15902.3804 | 0.2 | 0.3 | 24807.7134 |  |  |  |  | 0 | 5200.53 | 5200.53 | 5200.53 | 5200.53 | 5200.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1904 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16296.9266 | 0.2 | 0.3 | 25423.2055 |  |  |  |  | 0 | 5200.818 | 5200.818 | 5200.818 | 5200.818 | 5200.818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1905 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 17104.1988 | 0.2 | 0.3 | 26682.5501 |  |  |  |  | 0 | 5200.6608 | 5200.6608 | 5200.6608 | 5200.6608 | 5200.6608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1906 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16962.7765 | 0.2 | 0.3 | 26461.9314 |  |  |  |  | 0 | 5201.5799 | 5201.5799 | 5201.5799 | 5201.5799 | 5201.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1907 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 27253.3695 | 0.2 | 0.3 | 42515.2565 |  |  |  |  | 0 | 5201.0733 | 5201.0733 | 5201.0733 | 5201.0733 | 5201.0733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1908 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 22786.7289 | 0.2 | 0.3 | 35547.297 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1909 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 9645.8412 | 0.2 | 0.3 | 15047.5123 |  |  |  |  | 0 | 5200.9927 | 5200.9927 | 5200.9927 | 5200.9927 | 5200.9927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1910 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 17985.5043 | 0.2 | 0.3 | 28057.3867 |  |  |  |  | 0 | 5200.8938 | 5200.8938 | 5200.8938 | 5200.8938 | 5200.8938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1911 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16180.6608 | 0.2 | 0.3 | 25241.8308 |  |  |  |  | 0 | 5201.1363 | 5201.1363 | 5201.1363 | 5201.1363 | 5201.1363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1912 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 5200.4336 | 5200.4336 | 5200.4336 | 5200.4336 | 5200.4336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1913 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 745.2133 | 0.2 | 0.3 | 1162.5328 |  |  |  |  | 0 | 5201.3287 | 5201.3287 | 5201.3287 | 5201.3287 | 5201.3287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1914 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 24412.9988 | 0.2 | 0.3 | 38084.2781 |  |  |  |  | 0 | 7198.1413 | 7198.1413 | 7198.1413 | 7198.1413 | 7198.1413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1915 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 4221.6882 | 0.2 | 0.3 | 6585.8336 |  |  |  |  | 0 | 9076.9692 | 9076.9692 | 9076.9692 | 9076.9692 | 9076.9692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1916 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 19586.0102 | 0.2 | 0.3 | 30554.1759 |  |  |  |  | 0 | 4899.6511 | 4899.6511 | 4899.6511 | 4899.6511 | 4899.6511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1917 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 23553.9344 | 0.2 | 0.3 | 36744.1377 |  |  |  |  | 0 | 4619.9523 | 4619.9523 | 4619.9523 | 4619.9523 | 4619.9523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1918 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 23389.049 | 0.2 | 0.3 | 36486.9164 |  |  |  |  | 0 | 3734.8649 | 3734.8649 | 3734.8649 | 3734.8649 | 3734.8649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1919 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 17104.3577 | 0.2 | 0.3 | 26682.798 |  |  |  |  | 0 | 3617.8019 | 3617.8019 | 3617.8019 | 3617.8019 | 3617.8019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1920 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 22669.7272 | 0.2 | 0.3 | 35364.7744 |  |  |  |  | 0 | 5200.3157 | 5200.3157 | 5200.3157 | 5200.3157 | 5200.3157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1921 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 24948.2115 | 0.2 | 0.3 | 38919.2099 |  |  |  |  | 0 | 5200.861 | 5200.861 | 5200.861 | 5200.861 | 5200.861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1922 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 18696.7366 | 0.2 | 0.3 | 29166.9091 |  |  |  |  | 0 | 5200.4973 | 5200.4973 | 5200.4973 | 5200.4973 | 5200.4973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1923 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 25541.6413 | 0.2 | 0.3 | 39844.9604 |  |  |  |  | 0 | 5201.1156 | 5201.1156 | 5201.1156 | 5201.1156 | 5201.1156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1924 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 21855.7239 | 0.2 | 0.3 | 34094.9292 |  |  |  |  | 0 | 5201.4995 | 5201.4995 | 5201.4995 | 5201.4995 | 5201.4995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1925 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 223.2764 | 0.2 | 0.3 | 348.3112 |  |  |  |  | 0 | 5200.6261 | 5200.6261 | 5200.6261 | 5200.6261 | 5200.6261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1926 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 5200.5756 | 5200.5756 | 5200.5756 | 5200.5756 | 5200.5756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1927 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 18068.2963 | 0.2 | 0.3 | 28186.5422 |  |  |  |  | 0 | 5200.7404 | 5200.7404 | 5200.7404 | 5200.7404 | 5200.7404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1928 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 17560.5097 | 0.2 | 0.3 | 27394.3951 |  |  |  |  | 0 | 5201.4353 | 5201.4353 | 5201.4353 | 5201.4353 | 5201.4353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1929 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 17926.4297 | 0.2 | 0.3 | 27965.2303 |  |  |  |  | 0 | 5201.0562 | 5201.0562 | 5201.0562 | 5201.0562 | 5201.0562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1930 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 18536.5222 | 0.2 | 0.3 | 28916.9746 |  |  |  |  | 0 | 5200.761 | 5200.761 | 5200.761 | 5200.761 | 5200.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1931 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 27367.1936 | 0.2 | 0.3 | 42692.822 |  |  |  |  | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1932 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 31330.2705 | 0.2 | 0.3 | 48875.222 |  |  |  |  | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1933 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 19609.2793 | 0.2 | 0.3 | 30590.4757 |  |  |  |  | 0 | 5765.4674 | 5765.4674 | 5765.4674 | 5765.4674 | 5765.4674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1934 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 7786.743 | 0.2 | 0.3 | 12147.3191 |  |  |  |  | 0 | 7448.8139 | 7448.8139 | 7448.8139 | 7448.8139 | 7448.8139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1935 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 19704.6851 | 0.2 | 0.3 | 30739.3087 |  |  |  |  | 0 | 7477.3111 | 7477.3111 | 7477.3111 | 7477.3111 | 7477.3111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1936 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16678.2142 | 0.2 | 0.3 | 26018.0142 |  |  |  |  | 0 | 7942.2598 | 7942.2598 | 7942.2598 | 7942.2598 | 7942.2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1937 | COOPER CITY | 70405 | Public | 2036 | 5 | Swales | 66.6667 | 27444.8827 | 0.2 | 0.3 | 42814.0171 |  |  |  |  | 0 | 9851.8107 | 9851.8107 | 9851.8107 | 9851.8107 | 9851.8107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1938 | COOPER CITY | 70405 | Public | 2036 | 5 | Swales | 66.6667 | 10521.7492 | 0.2 | 0.3 | 16413.9288 |  |  |  |  | 0 | 9950.6091 | 9950.6091 | 9950.6091 | 9950.6091 | 9950.6091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1939 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 7076.6741 | 0.2 | 0.3 | 11039.6115 |  |  |  |  | 0 | 9972.3441 | 9972.3441 | 9972.3441 | 9972.3441 | 9972.3441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1940 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 22463.466 | 0.2 | 0.3 | 35043.007 |  |  |  |  | 0 | 8320.4969 | 8320.4969 | 8320.4969 | 8320.4969 | 8320.4969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1941 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16674.5075 | 0.2 | 0.3 | 26012.2318 |  |  |  |  | 0 | 9780.2848 | 9780.2848 | 9780.2848 | 9780.2848 | 9780.2848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1942 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 6443.1421 | 6443.1421 | 6443.1421 | 6443.1421 | 6443.1421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1943 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16688.5658 | 0.2 | 0.3 | 26034.1626 |  |  |  |  | 0 | 6358.4819 | 6358.4819 | 6358.4819 | 6358.4819 | 6358.4819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1944 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 18259.6444 | 0.2 | 0.3 | 28485.0453 |  |  |  |  | 0 | 6252.5414 | 6252.5414 | 6252.5414 | 6252.5414 | 6252.5414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1945 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 13175.6293 | 0.2 | 0.3 | 20553.9817 |  |  |  |  | 0 | 9778.3207 | 9778.3207 | 9778.3207 | 9778.3207 | 9778.3207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1946 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 21587.8107 | 0.2 | 0.3 | 33676.9847 |  |  |  |  | 0 | 6100.9558 | 6100.9558 | 6100.9558 | 6100.9558 | 6100.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1947 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 28793.0553 | 0.2 | 0.3 | 44917.1662 |  |  |  |  | 0 | 5929.8296 | 5929.8296 | 5929.8296 | 5929.8296 | 5929.8296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1948 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 12259.8196 | 0.2 | 0.3 | 19125.3186 |  |  |  |  | 0 | 5859.4618 | 5859.4618 | 5859.4618 | 5859.4618 | 5859.4618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1949 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 18330.6219 | 0.2 | 0.3 | 28595.7702 |  |  |  |  | 0 | 5776.1678 | 5776.1678 | 5776.1678 | 5776.1678 | 5776.1678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1950 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 5247.2396 | 0.2 | 0.3 | 8185.6938 |  |  |  |  | 0 | 9778.5053 | 9778.5053 | 9778.5053 | 9778.5053 | 9778.5053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1951 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 11223.8599 | 0.2 | 0.3 | 17509.2214 |  |  |  |  | 0 | 9778.3615 | 9778.3615 | 9778.3615 | 9778.3615 | 9778.3615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1952 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 7256.6277 | 0.2 | 0.3 | 11320.3392 |  |  |  |  | 0 | 9777.9755 | 9777.9755 | 9777.9755 | 9777.9755 | 9777.9755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1953 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 22050.0892 | 0.2 | 0.3 | 34398.1392 |  |  |  |  | 0 | 9777.9789 | 9777.9789 | 9777.9789 | 9777.9789 | 9777.9789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1954 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 21407.9211 | 0.2 | 0.3 | 33396.357 |  |  |  |  | 0 | 9213.1193 | 9213.1193 | 9213.1193 | 9213.1193 | 9213.1193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1955 | COOPER CITY | 70405 | Public | 2036 | 5 | Swales | 66.6667 | 14057.0895 | 0.2 | 0.3 | 21929.0597 |  |  |  |  | 0 | 2712.4671 | 2712.4671 | 2712.4671 | 2712.4671 | 2712.4671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1956 | COOPER CITY | 70405 | Public | 2036 | 5 | Swales | 66.6667 | 16676.3146 | 0.2 | 0.3 | 26015.0508 |  |  |  |  | 0 | 3688.1587 | 3688.1587 | 3688.1587 | 3688.1587 | 3688.1587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1957 | COOPER CITY | 70405 | Public | 2036 | 5 | Swales | 66.6667 | 12765.7707 | 0.2 | 0.3 | 19914.6023 |  |  |  |  | 0 | 4610.432 | 4610.432 | 4610.432 | 4610.432 | 4610.432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1958 | COOPER CITY | 70405 | Public | 2036 | 5 | Swales | 66.6667 | 16993.672 | 0.2 | 0.3 | 26510.1283 |  |  |  |  | 0 | 5844.521 | 5844.521 | 5844.521 | 5844.521 | 5844.521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1959 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 6412.4916 | 0.2 | 0.3 | 10003.4869 |  |  |  |  | 0 | 5375.1818 | 5375.1818 | 5375.1818 | 5375.1818 | 5375.1818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1960 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 16800.2404 | 0.2 | 0.3 | 26208.375 |  |  |  |  | 0 | 5379.2732 | 5379.2732 | 5379.2732 | 5379.2732 | 5379.2732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1961 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 9066.0319 | 0.2 | 0.3 | 14143.0097 |  |  |  |  | 0 | 5390.4994 | 5390.4994 | 5390.4994 | 5390.4994 | 5390.4994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1962 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 18502.6179 | 0.2 | 0.3 | 28864.084 |  |  |  |  | 0 | 8014.0244 | 8014.0244 | 8014.0244 | 8014.0244 | 8014.0244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1963 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16674.9487 | 0.2 | 0.3 | 26012.92 |  |  |  |  | 0 | 5200.771 | 5200.771 | 5200.771 | 5200.771 | 5200.771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1964 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1965 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16676.0625 | 0.2 | 0.3 | 26014.6574 |  |  |  |  | 0 | 5200.8024 | 5200.8024 | 5200.8024 | 5200.8024 | 5200.8024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1966 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 18494.6654 | 0.2 | 0.3 | 28851.678 |  |  |  |  | 0 | 9777.5264 | 9777.5264 | 9777.5264 | 9777.5264 | 9777.5264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1967 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 18724.4958 | 0.2 | 0.3 | 29210.2134 |  |  |  |  | 0 | 5201.224 | 5201.224 | 5201.224 | 5201.224 | 5201.224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1968 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 25550.6446 | 0.2 | 0.3 | 39859.0056 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1969 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16753.0325 | 0.2 | 0.3 | 26134.7306 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1970 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 17930.9773 | 0.2 | 0.3 | 27972.3246 |  |  |  |  | 0 | 5201.3274 | 5201.3274 | 5201.3274 | 5201.3274 | 5201.3274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1971 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 30547.8 | 0.2 | 0.3 | 47654.568 |  |  |  |  | 0 | 6925.8268 | 6925.8268 | 6925.8268 | 6925.8268 | 6925.8268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1972 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16679.6096 | 0.2 | 0.3 | 26020.191 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1973 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 12478.4078 | 0.2 | 0.3 | 19466.3162 |  |  |  |  | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1974 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 25046.1886 | 0.2 | 0.3 | 39072.0542 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1975 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 31434.7676 | 0.2 | 0.3 | 49038.2375 |  |  |  |  | 0 | 7021.8812 | 7021.8812 | 7021.8812 | 7021.8812 | 7021.8812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1976 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 30477.6014 | 0.2 | 0.3 | 47545.0582 |  |  |  |  | 0 | 5201.1992 | 5201.1992 | 5201.1992 | 5201.1992 | 5201.1992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1977 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16675.1465 | 0.2 | 0.3 | 26013.2285 |  |  |  |  | 0 | 4113.4086 | 4113.4086 | 4113.4086 | 4113.4086 | 4113.4086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1978 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 18434.9753 | 0.2 | 0.3 | 28758.5614 |  |  |  |  | 0 | 3352.83 | 3352.83 | 3352.83 | 3352.83 | 3352.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1979 | COOPER CITY | 70405 | Public | 2036 | 5 | Swales | 66.6667 | 15165.7913 | 0.2 | 0.3 | 23658.6344 |  |  |  |  | 0 | 5422.5659 | 5422.5659 | 5422.5659 | 5422.5659 | 5422.5659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1980 | COOPER CITY | 70405 | Public | 2036 | 5 | Swales | 66.6667 | 16686.8341 | 0.2 | 0.3 | 26031.4612 |  |  |  |  | 0 | 5160.9959 | 5160.9959 | 5160.9959 | 5160.9959 | 5160.9959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1981 | COOPER CITY | 70405 | Public | 2036 | 5 | Swales | 66.6667 | 25092.1229 | 0.2 | 0.3 | 39143.7118 |  |  |  |  | 0 | 4916.9343 | 4916.9343 | 4916.9343 | 4916.9343 | 4916.9343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1982 | COOPER CITY | 70405 | Public | 2036 | 5 | Swales | 66.6667 | 21489.4294 | 0.2 | 0.3 | 33523.5099 |  |  |  |  | 0 | 5339.8184 | 5339.8184 | 5339.8184 | 5339.8184 | 5339.8184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1983 | COOPER CITY | 70405 | Public | 2036 | 5 | Swales | 66.6667 | 12404.652 | 0.2 | 0.3 | 19351.2571 |  |  |  |  | 0 | 7940.7503 | 7940.7503 | 7940.7503 | 7940.7503 | 7940.7503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1984 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 13446.1241 | 0.2 | 0.3 | 20975.9535 |  |  |  |  | 0 | 8255.9854 | 8255.9854 | 8255.9854 | 8255.9854 | 8255.9854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1985 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 16722.0114 | 0.2 | 0.3 | 26086.3378 |  |  |  |  | 0 | 8339.2996 | 8339.2996 | 8339.2996 | 8339.2996 | 8339.2996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1986 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 24318.1339 | 0.2 | 0.3 | 37936.2889 |  |  |  |  | 0 | 8459.2341 | 8459.2341 | 8459.2341 | 8459.2341 | 8459.2341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1987 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 20335.0957 | 0.2 | 0.3 | 31722.7492 |  |  |  |  | 0 | 9777.6511 | 9777.6511 | 9777.6511 | 9777.6511 | 9777.6511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1988 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 16680.3447 | 0.2 | 0.3 | 26021.3378 |  |  |  |  | 0 | 8679.403 | 8679.403 | 8679.403 | 8679.403 | 8679.403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1989 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16944.4312 | 0.2 | 0.3 | 26433.3127 |  |  |  |  | 0 | 8798.1638 | 8798.1638 | 8798.1638 | 8798.1638 | 8798.1638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1990 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16684.6445 | 0.2 | 0.3 | 26028.0455 |  |  |  |  | 0 | 5200.8118 | 5200.8118 | 5200.8118 | 5200.8118 | 5200.8118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1991 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16689.1171 | 0.2 | 0.3 | 26035.0226 |  |  |  |  | 0 | 5200.9007 | 5200.9007 | 5200.9007 | 5200.9007 | 5200.9007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1992 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 10434.23 | 0.2 | 0.3 | 16277.3988 |  |  |  |  | 0 | 6998.3362 | 6998.3362 | 6998.3362 | 6998.3362 | 6998.3362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1993 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 9278.0308 | 0.2 | 0.3 | 14473.728 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1994 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 20943.164 | 0.2 | 0.3 | 32671.3358 |  |  |  |  | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1995 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16672.8863 | 0.2 | 0.3 | 26009.7026 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1996 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16683.6389 | 0.2 | 0.3 | 26026.4766 |  |  |  |  | 0 | 6868.1469 | 6868.1469 | 6868.1469 | 6868.1469 | 6868.1469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1997 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 19346.8276 | 0.2 | 0.3 | 30181.0511 |  |  |  |  | 0 | 9758.522 | 9758.522 | 9758.522 | 9758.522 | 9758.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1998 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6624 |  |  |  |  | 0 | 8187.7385 | 8187.7385 | 8187.7385 | 8187.7385 | 8187.7385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1999 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16680.3043 | 0.2 | 0.3 | 26021.2748 |  |  |  |  | 0 | 5249.1233 | 5249.1233 | 5249.1233 | 5249.1233 | 5249.1233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2000 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 8672.6981 | 0.2 | 0.3 | 13529.409 |  |  |  |  | 0 | 5126.0634 | 5126.0634 | 5126.0634 | 5126.0634 | 5126.0634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2001 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 20657.0955 | 0.2 | 0.3 | 32225.069 |  |  |  |  | 0 | 5155.5395 | 5155.5395 | 5155.5395 | 5155.5395 | 5155.5395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2002 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 8333.7627 | 0.2 | 0.3 | 13000.6698 |  |  |  |  | 0 | 3837.1587 | 3837.1587 | 3837.1587 | 3837.1587 | 3837.1587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2003 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 4694.5369 | 0.2 | 0.3 | 7323.4775 |  |  |  |  | 0 | 1813.617 | 1813.617 | 1813.617 | 1813.617 | 1813.617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2004 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 14560.5219 | 0.2 | 0.3 | 22714.4142 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2005 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7508 | 0.2 | 0.3 | 26000.1312 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2006 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1519 | 0.2 | 0.3 | 26000.757 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2007 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 10353.6963 | 0.2 | 0.3 | 16151.7663 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2008 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16672.5509 | 0.2 | 0.3 | 26009.1794 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2009 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 20380.0908 | 0.2 | 0.3 | 31792.9416 |  |  |  |  | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2010 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16683.3571 | 0.2 | 0.3 | 26026.0371 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2011 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16676.8329 | 0.2 | 0.3 | 26015.8593 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2012 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 19485.9318 | 0.2 | 0.3 | 30398.0536 |  |  |  |  | 0 | 5201.1461 | 5201.1461 | 5201.1461 | 5201.1461 | 5201.1461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2013 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 10704.0577 | 0.2 | 0.3 | 16698.33 |  |  |  |  | 0 | 5200.8888 | 5200.8888 | 5200.8888 | 5200.8888 | 5200.8888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2014 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16683.1778 | 0.2 | 0.3 | 26025.7574 |  |  |  |  | 0 | 5201.093 | 5201.093 | 5201.093 | 5201.093 | 5201.093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16677.7177 | 0.2 | 0.3 | 26017.2397 |  |  |  |  | 0 | 5201.2627 | 5201.2627 | 5201.2627 | 5201.2627 | 5201.2627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2016 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16676.4425 | 0.2 | 0.3 | 26015.2502 |  |  |  |  | 0 | 5200.1586 | 5200.1586 | 5200.1586 | 5200.1586 | 5200.1586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16676.7755 | 0.2 | 0.3 | 26015.7698 |  |  |  |  | 0 | 5200.6147 | 5200.6147 | 5200.6147 | 5200.6147 | 5200.6147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2018 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16009.1561 | 0.2 | 0.3 | 24974.2836 |  |  |  |  | 0 | 5263.2999 | 5263.2999 | 5263.2999 | 5263.2999 | 5263.2999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2019 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 25746.0525 | 0.2 | 0.3 | 40163.8418 |  |  |  |  | 0 | 5262.775 | 5262.775 | 5262.775 | 5262.775 | 5262.775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 26193.2056 | 0.2 | 0.3 | 40861.4007 |  |  |  |  | 0 | 5257.3309 | 5257.3309 | 5257.3309 | 5257.3309 | 5257.3309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16679.5038 | 0.2 | 0.3 | 26020.0259 |  |  |  |  | 0 | 5274.4433 | 5274.4433 | 5274.4433 | 5274.4433 | 5274.4433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 9779.8434 | 9779.8434 | 9779.8434 | 9779.8434 | 9779.8434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2023 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16680.1003 | 0.2 | 0.3 | 26020.9564 |  |  |  |  | 0 | 8745.8611 | 8745.8611 | 8745.8611 | 8745.8611 | 8745.8611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 22345.2155 | 0.2 | 0.3 | 34858.5362 |  |  |  |  | 0 | 8550.4003 | 8550.4003 | 8550.4003 | 8550.4003 | 8550.4003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 20451.3118 | 0.2 | 0.3 | 31904.0464 |  |  |  |  | 0 | 8434.5672 | 8434.5672 | 8434.5672 | 8434.5672 | 8434.5672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 8333.4701 | 0.2 | 0.3 | 13000.2133 |  |  |  |  | 0 | 8277.7454 | 8277.7454 | 8277.7454 | 8277.7454 | 8277.7454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 22167.5453 | 0.2 | 0.3 | 34581.3706 |  |  |  |  | 0 | 9020.801 | 9020.801 | 9020.801 | 9020.801 | 9020.801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2028 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 20618.2542 | 0.2 | 0.3 | 32164.4766 |  |  |  |  | 0 | 8848.3231 | 8848.3231 | 8848.3231 | 8848.3231 | 8848.3231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2029 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 20116.9309 | 0.2 | 0.3 | 31382.4122 |  |  |  |  | 0 | 5203.098 | 5203.098 | 5203.098 | 5203.098 | 5203.098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2030 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 37795.9458 | 0.2 | 0.3 | 58961.6754 |  |  |  |  | 0 | 5201.5906 | 5201.5906 | 5201.5906 | 5201.5906 | 5201.5906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2031 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 29567.6841 | 0.2 | 0.3 | 46125.5872 |  |  |  |  | 0 | 7557.3218 | 7557.3218 | 7557.3218 | 7557.3218 | 7557.3218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2032 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 33370.1303 | 0.2 | 0.3 | 52057.4033 |  |  |  |  | 0 | 7158.5189 | 7158.5189 | 7158.5189 | 7158.5189 | 7158.5189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2033 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 46032.4824 | 0.2 | 0.3 | 71810.6725 |  |  |  |  | 0 | 7015.3242 | 7015.3242 | 7015.3242 | 7015.3242 | 7015.3242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2034 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 33349.6041 | 0.2 | 0.3 | 52025.3824 |  |  |  |  | 0 | 6863.6037 | 6863.6037 | 6863.6037 | 6863.6037 | 6863.6037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2035 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 33359.1933 | 0.2 | 0.3 | 52040.3416 |  |  |  |  | 0 | 9779.5782 | 9779.5782 | 9779.5782 | 9779.5782 | 9779.5782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2036 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 35391.3956 | 0.2 | 0.3 | 55210.5771 |  |  |  |  | 0 | 6566.5542 | 6566.5542 | 6566.5542 | 6566.5542 | 6566.5542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2037 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 20319.6157 | 0.2 | 0.3 | 31698.6004 |  |  |  |  | 0 | 6372.6801 | 6372.6801 | 6372.6801 | 6372.6801 | 6372.6801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2038 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 4797.4847 | 0.2 | 0.3 | 7484.0761 |  |  |  |  | 0 | 9833.9564 | 9833.9564 | 9833.9564 | 9833.9564 | 9833.9564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2039 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 8680.9756 | 0.2 | 0.3 | 13542.3219 |  |  |  |  | 0 | 9864.6112 | 9864.6112 | 9864.6112 | 9864.6112 | 9864.6112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2040 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16942.3574 | 0.2 | 0.3 | 26430.0775 |  |  |  |  | 0 | 9868.5363 | 9868.5363 | 9868.5363 | 9868.5363 | 9868.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2041 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 27861.4775 | 0.2 | 0.3 | 43463.9048 |  |  |  |  | 0 | 8128.5503 | 8128.5503 | 8128.5503 | 8128.5503 | 8128.5503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2042 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 11696.1558 | 0.2 | 0.3 | 18246.003 |  |  |  |  | 0 | 7499.7854 | 7499.7854 | 7499.7854 | 7499.7854 | 7499.7854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2043 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 25956.5243 | 0.2 | 0.3 | 40492.1779 |  |  |  |  | 0 | 5202.0062 | 5202.0062 | 5202.0062 | 5202.0062 | 5202.0062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2044 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16683.5509 | 0.2 | 0.3 | 26026.3395 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2045 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16683.2142 | 0.2 | 0.3 | 26025.8142 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2046 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 25800.772 | 0.2 | 0.3 | 40249.2043 |  |  |  |  | 0 | 5202.1836 | 5202.1836 | 5202.1836 | 5202.1836 | 5202.1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2047 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 26683.3621 | 0.2 | 0.3 | 41626.0448 |  |  |  |  | 0 | 6598.3504 | 6598.3504 | 6598.3504 | 6598.3504 | 6598.3504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2048 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 16828.8902 | 0.2 | 0.3 | 26253.0687 |  |  |  |  | 0 | 8384.1269 | 8384.1269 | 8384.1269 | 8384.1269 | 8384.1269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2049 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 18766.0315 | 0.2 | 0.3 | 29275.0091 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2050 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 28579.4689 | 0.2 | 0.3 | 44583.9715 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2051 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 22496.0586 | 0.2 | 0.3 | 35093.8514 |  |  |  |  | 0 | 5202.2328 | 5202.2328 | 5202.2328 | 5202.2328 | 5202.2328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2052 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 33355.9154 | 0.2 | 0.3 | 52035.228 |  |  |  |  | 0 | 5200.5604 | 5200.5604 | 5200.5604 | 5200.5604 | 5200.5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2053 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 46412.777 | 0.2 | 0.3 | 72403.9321 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2054 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 33363.2743 | 0.2 | 0.3 | 52046.7079 |  |  |  |  | 0 | 5202.1896 | 5202.1896 | 5202.1896 | 5202.1896 | 5202.1896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2055 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 25616.0879 | 0.2 | 0.3 | 39961.0972 |  |  |  |  | 0 | 9779.5693 | 9779.5693 | 9779.5693 | 9779.5693 | 9779.5693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2056 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16064.4968 | 0.2 | 0.3 | 25060.615 |  |  |  |  | 0 | 5202.0576 | 5202.0576 | 5202.0576 | 5202.0576 | 5202.0576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2057 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16290.8053 | 0.2 | 0.3 | 25413.6562 |  |  |  |  | 0 | 5202.1197 | 5202.1197 | 5202.1197 | 5202.1197 | 5202.1197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2058 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 17735.472 | 0.2 | 0.3 | 27667.3363 |  |  |  |  | 0 | 7358.542 | 7358.542 | 7358.542 | 7358.542 | 7358.542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2059 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 10722.6102 | 0.2 | 0.3 | 16727.2719 |  |  |  |  | 0 | 5234.3464 | 5234.3464 | 5234.3464 | 5234.3464 | 5234.3464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2060 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 30324.5187 | 0.2 | 0.3 | 47306.2491 |  |  |  |  | 0 | 5228.5485 | 5228.5485 | 5228.5485 | 5228.5485 | 5228.5485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2061 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 21402.7985 | 0.2 | 0.3 | 33388.3657 |  |  |  |  | 0 | 5230.6341 | 5230.6341 | 5230.6341 | 5230.6341 | 5230.6341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2062 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 23124.5512 | 0.2 | 0.3 | 36074.2999 |  |  |  |  | 0 | 7325.2814 | 7325.2814 | 7325.2814 | 7325.2814 | 7325.2814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2063 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 24666.8917 | 0.2 | 0.3 | 38480.351 |  |  |  |  | 0 | 5202.17 | 5202.17 | 5202.17 | 5202.17 | 5202.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2064 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 17610.2061 | 0.2 | 0.3 | 27471.9216 |  |  |  |  | 0 | 5202.3378 | 5202.3378 | 5202.3378 | 5202.3378 | 5202.3378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2065 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 2829.2587 | 0.2 | 0.3 | 4413.6435 |  |  |  |  | 0 | 5202.4783 | 5202.4783 | 5202.4783 | 5202.4783 | 5202.4783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2066 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 23234.3738 | 0.2 | 0.3 | 36245.6231 |  |  |  |  | 0 | 5202.2501 | 5202.2501 | 5202.2501 | 5202.2501 | 5202.2501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2067 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 15018.5559 | 0.2 | 0.3 | 23428.9472 |  |  |  |  | 0 | 5202.3767 | 5202.3767 | 5202.3767 | 5202.3767 | 5202.3767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2068 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 467.9973 | 0.2 | 0.3 | 730.0757 |  |  |  |  | 0 | 9781.2395 | 9781.2395 | 9781.2395 | 9781.2395 | 9781.2395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2069 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 20702.2321 | 0.2 | 0.3 | 32295.4821 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2070 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 19480.9997 | 0.2 | 0.3 | 30390.3595 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2071 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 19202.1995 | 0.2 | 0.3 | 29955.4313 |  |  |  |  | 0 | 5202.0161 | 5202.0161 | 5202.0161 | 5202.0161 | 5202.0161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2072 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 23585.0409 | 0.2 | 0.3 | 36792.6639 |  |  |  |  | 0 | 5199.8587 | 5199.8587 | 5199.8587 | 5199.8587 | 5199.8587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2073 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16673.3281 | 0.2 | 0.3 | 26010.3919 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2074 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 39478.3248 | 0.2 | 0.3 | 61586.1867 |  |  |  |  | 0 | 5202.5356 | 5202.5356 | 5202.5356 | 5202.5356 | 5202.5356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2075 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 16931.9837 | 0.2 | 0.3 | 26413.8946 |  |  |  |  | 0 | 9781.4398 | 9781.4398 | 9781.4398 | 9781.4398 | 9781.4398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2076 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 25532.3629 | 0.2 | 0.3 | 39830.4861 |  |  |  |  | 0 | 5202.1591 | 5202.1591 | 5202.1591 | 5202.1591 | 5202.1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2077 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 20625.4177 | 0.2 | 0.3 | 32175.6516 |  |  |  |  | 0 | 5202.3901 | 5202.3901 | 5202.3901 | 5202.3901 | 5202.3901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2078 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 16663.9936 | 0.2 | 0.3 | 25995.83 |  |  |  |  | 0 | 6874.9674 | 6874.9674 | 6874.9674 | 6874.9674 | 6874.9674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2079 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 21550.9919 | 0.2 | 0.3 | 33619.5473 |  |  |  |  | 0 | 5211.4712 | 5211.4712 | 5211.4712 | 5211.4712 | 5211.4712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2080 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 27677.7047 | 0.2 | 0.3 | 43177.2194 |  |  |  |  | 0 | 5214.2611 | 5214.2611 | 5214.2611 | 5214.2611 | 5214.2611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2081 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16699.3343 | 0.2 | 0.3 | 26050.9616 |  |  |  |  | 0 | 5215.287 | 5215.287 | 5215.287 | 5215.287 | 5215.287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2082 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 32128.2138 | 0.2 | 0.3 | 50120.0135 |  |  |  |  | 0 | 7095.2069 | 7095.2069 | 7095.2069 | 7095.2069 | 7095.2069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2083 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 14533.0835 | 0.2 | 0.3 | 22671.6103 |  |  |  |  | 0 | 5202.4247 | 5202.4247 | 5202.4247 | 5202.4247 | 5202.4247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2084 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 27484.0438 | 0.2 | 0.3 | 42875.1083 |  |  |  |  | 0 | 5202.3448 | 5202.3448 | 5202.3448 | 5202.3448 | 5202.3448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2085 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 21485.715 | 0.2 | 0.3 | 33517.7154 |  |  |  |  | 0 | 5202.502 | 5202.502 | 5202.502 | 5202.502 | 5202.502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2086 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 21651.2193 | 0.2 | 0.3 | 33775.9022 |  |  |  |  | 0 | 5202.5071 | 5202.5071 | 5202.5071 | 5202.5071 | 5202.5071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2087 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 23483.3884 | 0.2 | 0.3 | 36634.0859 |  |  |  |  | 0 | 5202.5446 | 5202.5446 | 5202.5446 | 5202.5446 | 5202.5446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2088 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 24946.9846 | 0.2 | 0.3 | 38917.296 |  |  |  |  | 0 | 9781.2374 | 9781.2374 | 9781.2374 | 9781.2374 | 9781.2374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2089 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 29589.0745 | 0.2 | 0.3 | 46158.9562 |  |  |  |  | 0 | 5202.6231 | 5202.6231 | 5202.6231 | 5202.6231 | 5202.6231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2090 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 37032.8229 | 0.2 | 0.3 | 57771.2038 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2091 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 10911.6934 | 0.2 | 0.3 | 17022.2417 |  |  |  |  | 0 | 5202.3162 | 5202.3162 | 5202.3162 | 5202.3162 | 5202.3162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2092 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 17399.9423 | 0.2 | 0.3 | 27143.9099 |  |  |  |  | 0 | 5202.1162 | 5202.1162 | 5202.1162 | 5202.1162 | 5202.1162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2093 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 27408.5059 | 0.2 | 0.3 | 42757.2692 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2094 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 24723.1569 | 0.2 | 0.3 | 38568.1247 |  |  |  |  | 0 | 5202.4759 | 5202.4759 | 5202.4759 | 5202.4759 | 5202.4759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2095 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16673.3735 | 0.2 | 0.3 | 26010.4627 |  |  |  |  | 0 | 9781.4667 | 9781.4667 | 9781.4667 | 9781.4667 | 9781.4667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2096 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 21418.7109 | 0.2 | 0.3 | 33413.1891 |  |  |  |  | 0 | 5201.7361 | 5201.7361 | 5201.7361 | 5201.7361 | 5201.7361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2097 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 31187.5207 | 0.2 | 0.3 | 48652.5322 |  |  |  |  | 0 | 5201.8508 | 5201.8508 | 5201.8508 | 5201.8508 | 5201.8508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2098 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 29030.7863 | 0.2 | 0.3 | 45288.0267 |  |  |  |  | 0 | 6618.0048 | 6618.0048 | 6618.0048 | 6618.0048 | 6618.0048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2099 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 17765.9797 | 0.2 | 0.3 | 27714.9283 |  |  |  |  | 0 | 5203.6563 | 5203.6563 | 5203.6563 | 5203.6563 | 5203.6563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2100 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 9244.4242 | 0.2 | 0.3 | 14421.3018 |  |  |  |  | 0 | 5204.781 | 5204.781 | 5204.781 | 5204.781 | 5204.781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2101 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 33295.312 | 0.2 | 0.3 | 51940.6867 |  |  |  |  | 0 | 5245.8163 | 5245.8163 | 5245.8163 | 5245.8163 | 5245.8163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2102 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 27245.9611 | 0.2 | 0.3 | 42503.6994 |  |  |  |  | 0 | 532.4392 | 532.4392 | 532.4392 | 532.4392 | 532.4392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2103 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 25056.7159 | 0.2 | 0.3 | 39088.4769 |  |  |  |  | 0 | 0.67411 | 0.67411 | 0.67411 | 0.67411 | 0.67411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2104 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 15153.5061 | 0.2 | 0.3 | 23639.4696 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2105 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 21275.8115 | 0.2 | 0.3 | 33190.266 |  |  |  |  | 0 | 5202.2487 | 5202.2487 | 5202.2487 | 5202.2487 | 5202.2487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2106 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16879.5675 | 0.2 | 0.3 | 26332.1254 |  |  |  |  | 0 | 5202.1995 | 5202.1995 | 5202.1995 | 5202.1995 | 5202.1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2107 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 14990.6383 | 0.2 | 0.3 | 23385.3958 |  |  |  |  | 0 | 5202.3145 | 5202.3145 | 5202.3145 | 5202.3145 | 5202.3145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2108 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 20320.1752 | 0.2 | 0.3 | 31699.4733 |  |  |  |  | 0 | 5202.4606 | 5202.4606 | 5202.4606 | 5202.4606 | 5202.4606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2109 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 17244.9908 | 0.2 | 0.3 | 26902.1856 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2110 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 22995.0421 | 0.2 | 0.3 | 35872.2656 |  |  |  |  | 0 | 5202.5577 | 5202.5577 | 5202.5577 | 5202.5577 | 5202.5577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2111 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 22549.8394 | 0.2 | 0.3 | 35177.7495 |  |  |  |  | 0 | 5199.0213 | 5199.0213 | 5199.0213 | 5199.0213 | 5199.0213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2112 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 22748.0885 | 0.2 | 0.3 | 35487.018 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2113 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 20376.2161 | 0.2 | 0.3 | 31786.8972 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2114 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 19669.7794 | 0.2 | 0.3 | 30684.8559 |  |  |  |  | 0 | 7729.9062 | 7729.9062 | 7729.9062 | 7729.9062 | 7729.9062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2115 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 15526.2516 | 0.2 | 0.3 | 24220.9525 |  |  |  |  | 0 | 5202.2081 | 5202.2081 | 5202.2081 | 5202.2081 | 5202.2081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2116 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7599 | 0.2 | 0.3 | 26000.1454 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2117 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 16666.0532 | 0.2 | 0.3 | 25999.043 |  |  |  |  | 0 | 5202.3457 | 5202.3457 | 5202.3457 | 5202.3457 | 5202.3457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2118 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0131 | 0.2 | 0.3 | 26000.5405 |  |  |  |  | 0 | 7176.3329 | 7176.3329 | 7176.3329 | 7176.3329 | 7176.3329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2119 | COOPER CITY | 70405 | Private | 2036 | 5 | Swales | 66.6667 | 17568.0591 | 0.2 | 0.3 | 27406.1722 |  |  |  |  | 0 | 5204.3905 | 5204.3905 | 5204.3905 | 5204.3905 | 5204.3905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2120 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 10730.4709 | 0.2 | 0.3 | 16739.5346 |  |  |  |  | 0 | 234.2167 | 234.2167 | 234.2167 | 234.2167 | 234.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2121 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 2404.8784 | 2404.8784 | 2404.8784 | 2404.8784 | 2404.8784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2122 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16422.3545 | 0.2 | 0.3 | 25618.873 |  |  |  |  | 0 | 2857.148 | 2857.148 | 2857.148 | 2857.148 | 2857.148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2123 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 475.9899 | 0.2 | 0.3 | 742.5443 |  |  |  |  | 0 | 4967.4225 | 4967.4225 | 4967.4225 | 4967.4225 | 4967.4225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2124 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 16749.7915 | 0.2 | 0.3 | 26129.6747 |  |  |  |  | 0 | 5202.2902 | 5202.2902 | 5202.2902 | 5202.2902 | 5202.2902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2125 | COOPER CITY | 70501 | Private | 2036 | 5 | Swales | 66.6667 | 3941.2631 | 0.2 | 0.3 | 6148.3704 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2126 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 11265.4686 | 0.2 | 0.3 | 17574.131 |  |  |  |  | 0 | 5202.575 | 5202.575 | 5202.575 | 5202.575 | 5202.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2127 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 4487.4517 | 0.2 | 0.3 | 7000.4246 |  |  |  |  | 0 | 5240.837 | 5240.837 | 5240.837 | 5240.837 | 5240.837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2128 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 8974.2534 | 0.2 | 0.3 | 13999.8353 |  |  |  |  | 0 | 997.7662 | 997.7662 | 997.7662 | 997.7662 | 997.7662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2129 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16376.4788 | 0.2 | 0.3 | 25547.3069 |  |  |  |  | 0 | 5202.577 | 5202.577 | 5202.577 | 5202.577 | 5202.577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2130 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16674.6896 | 0.2 | 0.3 | 26012.5158 |  |  |  |  | 0 | 6794.5068 | 6794.5068 | 6794.5068 | 6794.5068 | 6794.5068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2131 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 17579.8673 | 0.2 | 0.3 | 27424.5929 |  |  |  |  | 0 | 5201.7045 | 5201.7045 | 5201.7045 | 5201.7045 | 5201.7045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2132 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 18337.4614 | 0.2 | 0.3 | 28606.4398 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2133 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16675.7776 | 0.2 | 0.3 | 26014.2131 |  |  |  |  | 0 | 5201.8933 | 5201.8933 | 5201.8933 | 5201.8933 | 5201.8933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2134 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 19589.9191 | 0.2 | 0.3 | 30560.2738 |  |  |  |  | 0 | 5202.0284 | 5202.0284 | 5202.0284 | 5202.0284 | 5202.0284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2135 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 18499.3543 | 0.2 | 0.3 | 28858.9927 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2136 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 19251.5188 | 0.2 | 0.3 | 30032.3693 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2137 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16822.5689 | 0.2 | 0.3 | 26243.2074 |  |  |  |  | 0 | 5202.2333 | 5202.2333 | 5202.2333 | 5202.2333 | 5202.2333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2138 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 9561.9413 | 0.2 | 0.3 | 14916.6284 |  |  |  |  | 0 | 5739.6254 | 5739.6254 | 5739.6254 | 5739.6254 | 5739.6254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2139 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 16259.6584 | 0.2 | 0.3 | 25365.0671 |  |  |  |  | 0 | 5395.5885 | 5395.5885 | 5395.5885 | 5395.5885 | 5395.5885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2140 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 28044.3523 | 0.2 | 0.3 | 43749.1896 |  |  |  |  | 0 | 5688.0346 | 5688.0346 | 5688.0346 | 5688.0346 | 5688.0346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2141 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 26346.7793 | 0.2 | 0.3 | 41100.9758 |  |  |  |  | 0 | 9959.0376 | 9959.0376 | 9959.0376 | 9959.0376 | 9959.0376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2142 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 12192.5409 | 0.2 | 0.3 | 19020.3639 |  |  |  |  | 0 | 5202.0216 | 5202.0216 | 5202.0216 | 5202.0216 | 5202.0216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2143 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16341.4601 | 0.2 | 0.3 | 25492.6778 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2144 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16027.2036 | 0.2 | 0.3 | 25002.4376 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2145 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 15848.0223 | 0.2 | 0.3 | 24722.9147 |  |  |  |  | 0 | 5202.5309 | 5202.5309 | 5202.5309 | 5202.5309 | 5202.5309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2146 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 18504.5155 | 0.2 | 0.3 | 28867.0441 |  |  |  |  | 0 | 5618.6105 | 5618.6105 | 5618.6105 | 5618.6105 | 5618.6105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2147 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16679.1627 | 0.2 | 0.3 | 26019.4938 |  |  |  |  | 0 | 5202.3553 | 5202.3553 | 5202.3553 | 5202.3553 | 5202.3553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2148 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16671.3015 | 0.2 | 0.3 | 26007.2304 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2149 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 728.1713 | 0.2 | 0.3 | 1135.9473 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2150 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 15948.7801 | 0.2 | 0.3 | 24880.0969 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2151 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16668.2724 | 0.2 | 0.3 | 26002.5049 |  |  |  |  | 0 | 5202.4597 | 5202.4597 | 5202.4597 | 5202.4597 | 5202.4597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2152 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17727.2895 | 0.2 | 0.3 | 27654.5717 |  |  |  |  | 0 | 5202.5697 | 5202.5697 | 5202.5697 | 5202.5697 | 5202.5697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2153 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17254.6019 | 0.2 | 0.3 | 26917.179 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2154 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 16513.5404 | 0.2 | 0.3 | 25761.123 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2155 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 17243.9671 | 0.2 | 0.3 | 26900.5887 |  |  |  |  | 0 | 5202.6148 | 5202.6148 | 5202.6148 | 5202.6148 | 5202.6148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2156 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 27677.8503 | 0.2 | 0.3 | 43177.4464 |  |  |  |  | 0 | 4891.7544 | 4891.7544 | 4891.7544 | 4891.7544 | 4891.7544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2157 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 5135.8612 | 5135.8612 | 5135.8612 | 5135.8612 | 5135.8612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2158 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 4836.8878 | 4836.8878 | 4836.8878 | 4836.8878 | 4836.8878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2159 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16863.4787 | 0.2 | 0.3 | 26307.0267 |  |  |  |  | 0 | 9682.1918 | 9682.1918 | 9682.1918 | 9682.1918 | 9682.1918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2160 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 31140.0889 | 0.2 | 0.3 | 48578.5387 |  |  |  |  | 0 | 5202.3875 | 5202.3875 | 5202.3875 | 5202.3875 | 5202.3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2161 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16667.0709 | 0.2 | 0.3 | 26000.6307 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2162 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8034 | 0.2 | 0.3 | 26000.2133 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2163 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 5202.7909 | 5202.7909 | 5202.7909 | 5202.7909 | 5202.7909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2164 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16675.2312 | 0.2 | 0.3 | 26013.3607 |  |  |  |  | 0 | 5837.8098 | 5837.8098 | 5837.8098 | 5837.8098 | 5837.8098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2165 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16213.4023 | 0.2 | 0.3 | 25292.9076 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2166 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 25717.7147 | 0.2 | 0.3 | 40119.6349 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2167 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16667.0728 | 0.2 | 0.3 | 26000.6336 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2168 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 5202.4839 | 5202.4839 | 5202.4839 | 5202.4839 | 5202.4839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2169 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 5202.417 | 5202.417 | 5202.417 | 5202.417 | 5202.417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2170 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16683.6892 | 0.2 | 0.3 | 26026.5552 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2171 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 17388.5121 | 0.2 | 0.3 | 27126.0788 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2172 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 25176.5351 | 0.2 | 0.3 | 39275.3947 |  |  |  |  | 0 | 5202.5334 | 5202.5334 | 5202.5334 | 5202.5334 | 5202.5334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2173 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 23640.7476 | 0.2 | 0.3 | 36879.5663 |  |  |  |  | 0 | 5381.5098 | 5381.5098 | 5381.5098 | 5381.5098 | 5381.5098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2174 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 16672.4221 | 0.2 | 0.3 | 26008.9784 |  |  |  |  | 0 | 5260.7714 | 5260.7714 | 5260.7714 | 5260.7714 | 5260.7714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2175 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 21282.4515 | 0.2 | 0.3 | 33200.6243 |  |  |  |  | 0 | 5739.5262 | 5739.5262 | 5739.5262 | 5739.5262 | 5739.5262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2176 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 26011.4335 | 0.2 | 0.3 | 40577.8363 |  |  |  |  | 0 | 9885.0397 | 9885.0397 | 9885.0397 | 9885.0397 | 9885.0397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2177 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 16836.5454 | 0.2 | 0.3 | 26265.0108 |  |  |  |  | 0 | 5201.9195 | 5201.9195 | 5201.9195 | 5201.9195 | 5201.9195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2178 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 14548.6259 | 0.2 | 0.3 | 22695.8564 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2179 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 22103.7659 | 0.2 | 0.3 | 34481.8748 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2180 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 16798.9803 | 0.2 | 0.3 | 26206.4092 |  |  |  |  | 0 | 5202.3391 | 5202.3391 | 5202.3391 | 5202.3391 | 5202.3391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2181 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 7759.0341 | 0.2 | 0.3 | 12104.0931 |  |  |  |  | 0 | 6066.1663 | 6066.1663 | 6066.1663 | 6066.1663 | 6066.1663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2182 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 17855.7593 | 0.2 | 0.3 | 27854.9846 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2183 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 11470.3965 | 0.2 | 0.3 | 17893.8186 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2184 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 30335.2341 | 0.2 | 0.3 | 47322.9651 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2185 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 23148.1467 | 0.2 | 0.3 | 36111.1088 |  |  |  |  | 0 | 5202.3693 | 5202.3693 | 5202.3693 | 5202.3693 | 5202.3693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2186 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16678.0077 | 0.2 | 0.3 | 26017.6921 |  |  |  |  | 0 | 5202.413 | 5202.413 | 5202.413 | 5202.413 | 5202.413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2187 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 22638.5438 | 0.2 | 0.3 | 35316.1283 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2188 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 8780.6103 | 0.2 | 0.3 | 13697.7521 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2189 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 19272.3135 | 0.2 | 0.3 | 30064.8091 |  |  |  |  | 0 | 5202.2923 | 5202.2923 | 5202.2923 | 5202.2923 | 5202.2923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2190 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 22711.0516 | 0.2 | 0.3 | 35429.2405 |  |  |  |  | 0 | 2601.0202 | 2601.0202 | 2601.0202 | 2601.0202 | 2601.0202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2191 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16681.492 | 0.2 | 0.3 | 26023.1275 |  |  |  |  | 0 | 3887.7698 | 3887.7698 | 3887.7698 | 3887.7698 | 3887.7698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2192 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 4990.741 | 0.2 | 0.3 | 7785.556 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2193 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 19073.4537 | 0.2 | 0.3 | 29754.5878 |  |  |  |  | 0 | 5202.1926 | 5202.1926 | 5202.1926 | 5202.1926 | 5202.1926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2194 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 5230.3683 | 0.2 | 0.3 | 8159.3745 |  |  |  |  | 0 | 5202.0979 | 5202.0979 | 5202.0979 | 5202.0979 | 5202.0979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2195 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 24049.506 | 0.2 | 0.3 | 37517.2294 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2196 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 29772.777 | 0.2 | 0.3 | 46445.5321 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2197 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 30292.8757 | 0.2 | 0.3 | 47256.8861 |  |  |  |  | 0 | 5202.0226 | 5202.0226 | 5202.0226 | 5202.0226 | 5202.0226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2198 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 28883.7801 | 0.2 | 0.3 | 45058.6969 |  |  |  |  | 0 | 5204.133 | 5204.133 | 5204.133 | 5204.133 | 5204.133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2199 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16864.4747 | 0.2 | 0.3 | 26308.5805 |  |  |  |  | 0 | 8672.0558 | 8672.0558 | 8672.0558 | 8672.0558 | 8672.0558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2200 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 30511.8247 | 0.2 | 0.3 | 47598.4466 |  |  |  |  | 0 | 5202.0366 | 5202.0366 | 5202.0366 | 5202.0366 | 5202.0366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2201 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 26659.4992 | 0.2 | 0.3 | 41588.8188 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2202 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 23392.3174 | 0.2 | 0.3 | 36492.0151 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2203 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 29810.3564 | 0.2 | 0.3 | 46504.156 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2204 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 1252.9251 | 0.2 | 0.3 | 1954.5631 |  |  |  |  | 0 | 5202.4884 | 5202.4884 | 5202.4884 | 5202.4884 | 5202.4884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2205 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 920.7998 | 0.2 | 0.3 | 1436.4477 |  |  |  |  | 0 | 9481.5624 | 9481.5624 | 9481.5624 | 9481.5624 | 9481.5624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2206 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 15102.0615 | 0.2 | 0.3 | 23559.216 |  |  |  |  | 0 | 5201.9743 | 5201.9743 | 5201.9743 | 5201.9743 | 5201.9743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2207 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16675.5573 | 0.2 | 0.3 | 26013.8694 |  |  |  |  | 0 | 4829.8504 | 4829.8504 | 4829.8504 | 4829.8504 | 4829.8504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2208 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 5201.9489 | 5201.9489 | 5201.9489 | 5201.9489 | 5201.9489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2209 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16675.6575 | 0.2 | 0.3 | 26014.0258 |  |  |  |  | 0 | 5202.2945 | 5202.2945 | 5202.2945 | 5202.2945 | 5202.2945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2210 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 31417.7138 | 0.2 | 0.3 | 49011.6335 |  |  |  |  | 0 | 6803.9901 | 6803.9901 | 6803.9901 | 6803.9901 | 6803.9901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2211 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17669.9933 | 0.2 | 0.3 | 27565.1895 |  |  |  |  | 0 | 7958.1901 | 7958.1901 | 7958.1901 | 7958.1901 | 7958.1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2212 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 4271.5047 | 0.2 | 0.3 | 6663.5474 |  |  |  |  | 0 | 5202.3503 | 5202.3503 | 5202.3503 | 5202.3503 | 5202.3503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2213 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 29073.2619 | 0.2 | 0.3 | 45354.2885 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2214 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16674.6563 | 0.2 | 0.3 | 26012.4639 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2215 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 16713.144 | 0.2 | 0.3 | 26072.5046 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2216 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 16776.7088 | 0.2 | 0.3 | 26171.6657 |  |  |  |  | 0 | 5202.4459 | 5202.4459 | 5202.4459 | 5202.4459 | 5202.4459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2217 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 26424.9511 | 0.2 | 0.3 | 41222.9238 |  |  |  |  | 0 | 10130.5388 | 10130.5388 | 10130.5388 | 10130.5388 | 10130.5388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2218 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17256.602 | 0.2 | 0.3 | 26920.2991 |  |  |  |  | 0 | 5201.9225 | 5201.9225 | 5201.9225 | 5201.9225 | 5201.9225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2219 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17442.8821 | 0.2 | 0.3 | 27210.896 |  |  |  |  | 0 | 5518.2675 | 5518.2675 | 5518.2675 | 5518.2675 | 5518.2675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2220 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 772.4576 | 0.2 | 0.3 | 1205.0339 |  |  |  |  | 0 | 5202.0614 | 5202.0614 | 5202.0614 | 5202.0614 | 5202.0614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2221 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17458.6711 | 0.2 | 0.3 | 27235.527 |  |  |  |  | 0 | 5202.0583 | 5202.0583 | 5202.0583 | 5202.0583 | 5202.0583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2222 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16686.6411 | 0.2 | 0.3 | 26031.1601 |  |  |  |  | 0 | 6286.7371 | 6286.7371 | 6286.7371 | 6286.7371 | 6286.7371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2223 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16767.0532 | 0.2 | 0.3 | 26156.603 |  |  |  |  | 0 | 4283.9397 | 4283.9397 | 4283.9397 | 4283.9397 | 4283.9397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2224 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 18932.1992 | 0.2 | 0.3 | 29534.2308 |  |  |  |  | 0 | 5201.9071 | 5201.9071 | 5201.9071 | 5201.9071 | 5201.9071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2225 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 8198.4571 | 0.2 | 0.3 | 12789.5931 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2226 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16593.7057 | 0.2 | 0.3 | 25886.1808 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2227 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16721.2047 | 0.2 | 0.3 | 26085.0794 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2228 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16759.4273 | 0.2 | 0.3 | 26144.7066 |  |  |  |  | 0 | 5203.0355 | 5203.0355 | 5203.0355 | 5203.0355 | 5203.0355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2229 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 9060.9233 | 0.2 | 0.3 | 14135.0403 |  |  |  |  | 0 | 3611.4667 | 3611.4667 | 3611.4667 | 3611.4667 | 3611.4667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2230 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 19934.6931 | 0.2 | 0.3 | 31098.1212 |  |  |  |  | 0 | 2600.8592 | 2600.8592 | 2600.8592 | 2600.8592 | 2600.8592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2231 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 24749.5803 | 0.2 | 0.3 | 38609.3453 |  |  |  |  | 0 | 1370.1685 | 1370.1685 | 1370.1685 | 1370.1685 | 1370.1685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2232 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 12436.5789 | 0.2 | 0.3 | 19401.0631 |  |  |  |  | 0 | 714.6758 | 714.6758 | 714.6758 | 714.6758 | 714.6758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2233 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 32777.9337 | 0.2 | 0.3 | 51133.5765 |  |  |  |  | 0 | 94.2122 | 94.2122 | 94.2122 | 94.2122 | 94.2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2234 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 17600.8732 | 0.2 | 0.3 | 27457.3622 |  |  |  |  | 0 | 1493.0809 | 1493.0809 | 1493.0809 | 1493.0809 | 1493.0809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2235 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 22767.8129 | 0.2 | 0.3 | 35517.7881 |  |  |  |  | 0 | 5059.6083 | 5059.6083 | 5059.6083 | 5059.6083 | 5059.6083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2236 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 22499.1299 | 0.2 | 0.3 | 35098.6427 |  |  |  |  | 0 | 5982.7959 | 5982.7959 | 5982.7959 | 5982.7959 | 5982.7959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2237 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 31329.2475 | 0.2 | 0.3 | 48873.6262 |  |  |  |  | 0 | 6510.2529 | 6510.2529 | 6510.2529 | 6510.2529 | 6510.2529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2238 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 27057.1873 | 0.2 | 0.3 | 42209.2121 |  |  |  |  | 0 | 6454.6632 | 6454.6632 | 6454.6632 | 6454.6632 | 6454.6632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2239 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 24212.1639 | 0.2 | 0.3 | 37770.9756 |  |  |  |  | 0 | 7865.7359 | 7865.7359 | 7865.7359 | 7865.7359 | 7865.7359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2240 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16878.3306 | 0.2 | 0.3 | 26330.1957 |  |  |  |  | 0 | 792.9869 | 792.9869 | 792.9869 | 792.9869 | 792.9869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2241 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 26420.1836 | 0.2 | 0.3 | 41215.4864 |  |  |  |  | 0 | 6722.3274 | 6722.3274 | 6722.3274 | 6722.3274 | 6722.3274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2242 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 20189.6928 | 0.2 | 0.3 | 31495.9208 |  |  |  |  | 0 | 5457.9178 | 5457.9178 | 5457.9178 | 5457.9178 | 5457.9178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2243 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 26698.6976 | 0.2 | 0.3 | 41649.9683 |  |  |  |  | 0 | 5199.8824 | 5199.8824 | 5199.8824 | 5199.8824 | 5199.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2244 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 31358.6015 | 0.2 | 0.3 | 48919.4183 |  |  |  |  | 0 | 7306.082 | 7306.082 | 7306.082 | 7306.082 | 7306.082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2245 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 8165.0139 | 0.2 | 0.3 | 12737.4217 |  |  |  |  | 0 | 7591.0894 | 7591.0894 | 7591.0894 | 7591.0894 | 7591.0894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2246 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 18268.6727 | 0.2 | 0.3 | 28499.1295 |  |  |  |  | 0 | 9324.191 | 9324.191 | 9324.191 | 9324.191 | 9324.191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2247 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 24657.7475 | 0.2 | 0.3 | 38466.0862 |  |  |  |  | 0 | 10606.5427 | 10606.5427 | 10606.5427 | 10606.5427 | 10606.5427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2248 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 17835.8469 | 0.2 | 0.3 | 27823.9212 |  |  |  |  | 0 | 9548.94 | 9548.94 | 9548.94 | 9548.94 | 9548.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2249 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16686.4437 | 0.2 | 0.3 | 26030.8521 |  |  |  |  | 0 | 9042.22 | 9042.22 | 9042.22 | 9042.22 | 9042.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2250 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 14245.8677 | 0.2 | 0.3 | 22223.5536 |  |  |  |  | 0 | 14152.9989 | 14152.9989 | 14152.9989 | 14152.9989 | 14152.9989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2251 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 5991.6041 | 0.2 | 0.3 | 9346.9023 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2252 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16683.7409 | 0.2 | 0.3 | 26026.6358 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2253 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2254 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16666.9522 | 0.2 | 0.3 | 26000.4454 |  |  |  |  | 0 | 3888.2718 | 3888.2718 | 3888.2718 | 3888.2718 | 3888.2718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2255 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 11273.4184 | 0.2 | 0.3 | 17586.5327 |  |  |  |  | 0 | 5945.0369 | 5945.0369 | 5945.0369 | 5945.0369 | 5945.0369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2256 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 8609.6604 | 0.2 | 0.3 | 13431.0702 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2257 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16666.9351 | 0.2 | 0.3 | 26000.4188 |  |  |  |  | 0 | 7187.4365 | 7187.4365 | 7187.4365 | 7187.4365 | 7187.4365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2258 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 5200.2771 | 5200.2771 | 5200.2771 | 5200.2771 | 5200.2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2259 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7214 | 0.2 | 0.3 | 26000.0854 |  |  |  |  | 0 | 6460.0878 | 6460.0878 | 6460.0878 | 6460.0878 | 6460.0878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2260 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 9476.7443 | 0.2 | 0.3 | 14783.7212 |  |  |  |  | 0 | 8904.4838 | 8904.4838 | 8904.4838 | 8904.4838 | 8904.4838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2261 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 26448.1905 | 0.2 | 0.3 | 41259.1771 |  |  |  |  | 0 | 5375.615 | 5375.615 | 5375.615 | 5375.615 | 5375.615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 15416.749 | 0.2 | 0.3 | 24050.1284 |  |  |  |  | 0 | 5621.9865 | 5621.9865 | 5621.9865 | 5621.9865 | 5621.9865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2263 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 19716.8533 | 0.2 | 0.3 | 30758.2911 |  |  |  |  | 0 | 1367.7624 | 1367.7624 | 1367.7624 | 1367.7624 | 1367.7624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2264 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 26596.7809 | 0.2 | 0.3 | 41490.9783 |  |  |  |  | 0 | 1974.8577 | 1974.8577 | 1974.8577 | 1974.8577 | 1974.8577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2265 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.4041 | 0.2 | 0.3 | 26010.5104 |  |  |  |  | 0 | 6336.2664 | 6336.2664 | 6336.2664 | 6336.2664 | 6336.2664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2266 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.1617 | 0.2 | 0.3 | 26010.1322 |  |  |  |  | 0 | 4657.5992 | 4657.5992 | 4657.5992 | 4657.5992 | 4657.5992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2267 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.3152 | 0.2 | 0.3 | 26010.3717 |  |  |  |  | 0 | 7050.8385 | 7050.8385 | 7050.8385 | 7050.8385 | 7050.8385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2268 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 19396.3709 | 0.2 | 0.3 | 30258.3387 |  |  |  |  | 0 | 6528.0466 | 6528.0466 | 6528.0466 | 6528.0466 | 6528.0466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2269 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16674.7773 | 0.2 | 0.3 | 26012.6526 |  |  |  |  | 0 | 4153.0808 | 4153.0808 | 4153.0808 | 4153.0808 | 4153.0808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2270 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 44252.3821 | 0.2 | 0.3 | 69033.716 |  |  |  |  | 0 | 5200.1844 | 5200.1844 | 5200.1844 | 5200.1844 | 5200.1844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2271 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 29337.8795 | 0.2 | 0.3 | 45767.092 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2272 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 25661.6353 | 0.2 | 0.3 | 40032.1511 |  |  |  |  | 0 | 7685.391 | 7685.391 | 7685.391 | 7685.391 | 7685.391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2273 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 25215.4801 | 0.2 | 0.3 | 39336.1489 |  |  |  |  | 0 | 5199.9987 | 5199.9987 | 5199.9987 | 5199.9987 | 5199.9987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2274 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 24135.8681 | 0.2 | 0.3 | 37651.9543 |  |  |  |  | 0 | 7044.7333 | 7044.7333 | 7044.7333 | 7044.7333 | 7044.7333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2275 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 24910.1503 | 0.2 | 0.3 | 38859.8344 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2276 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17218.0523 | 0.2 | 0.3 | 26860.1615 |  |  |  |  | 0 | 6449.6575 | 6449.6575 | 6449.6575 | 6449.6575 | 6449.6575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2277 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 27022.5581 | 0.2 | 0.3 | 42155.1906 |  |  |  |  | 0 | 9271.3637 | 9271.3637 | 9271.3637 | 9271.3637 | 9271.3637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2278 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 13976.1621 | 0.2 | 0.3 | 21802.8129 |  |  |  |  | 0 | 8261.257 | 8261.257 | 8261.257 | 8261.257 | 8261.257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2279 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 24038.2237 | 0.2 | 0.3 | 37499.629 |  |  |  |  | 0 | 1959.0151 | 1959.0151 | 1959.0151 | 1959.0151 | 1959.0151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2280 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 21460.8009 | 0.2 | 0.3 | 33478.8495 |  |  |  |  | 0 | 1569.2988 | 1569.2988 | 1569.2988 | 1569.2988 | 1569.2988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2281 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 27325.6999 | 0.2 | 0.3 | 42628.0918 |  |  |  |  | 0 | 655.9734 | 655.9734 | 655.9734 | 655.9734 | 655.9734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2282 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 23925.6151 | 0.2 | 0.3 | 37323.9595 |  |  |  |  | 0 | 1049.8576 | 1049.8576 | 1049.8576 | 1049.8576 | 1049.8576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2283 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 3572.3655 | 0.2 | 0.3 | 5572.8902 |  |  |  |  | 0 | 8725.4334 | 8725.4334 | 8725.4334 | 8725.4334 | 8725.4334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2284 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 5146.3019 | 0.2 | 0.3 | 8028.231 |  |  |  |  | 0 | 8883.7966 | 8883.7966 | 8883.7966 | 8883.7966 | 8883.7966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2285 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 26587.546 | 0.2 | 0.3 | 41476.5718 |  |  |  |  | 0 | 10561.4163 | 10561.4163 | 10561.4163 | 10561.4163 | 10561.4163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2286 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16677.8395 | 0.2 | 0.3 | 26017.4296 |  |  |  |  | 0 | 5200.0946 | 5200.0946 | 5200.0946 | 5200.0946 | 5200.0946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2287 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 19592.9651 | 0.2 | 0.3 | 30565.0256 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2288 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 24499.8457 | 0.2 | 0.3 | 38219.7593 |  |  |  |  | 0 | 5200.0845 | 5200.0845 | 5200.0845 | 5200.0845 | 5200.0845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2289 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 8629.8685 | 0.2 | 0.3 | 13462.5949 |  |  |  |  | 0 | 5785.8633 | 5785.8633 | 5785.8633 | 5785.8633 | 5785.8633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2290 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 19126.0757 | 0.2 | 0.3 | 29836.6781 |  |  |  |  | 0 | 12225.3906 | 12225.3906 | 12225.3906 | 12225.3906 | 12225.3906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2291 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 10383.4407 | 0.2 | 0.3 | 16198.1675 |  |  |  |  | 0 | 6979.3248 | 6979.3248 | 6979.3248 | 6979.3248 | 6979.3248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2292 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 23709.2485 | 0.2 | 0.3 | 36986.4277 |  |  |  |  | 0 | 5840.9278 | 5840.9278 | 5840.9278 | 5840.9278 | 5840.9278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2293 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 26946.0821 | 0.2 | 0.3 | 42035.8881 |  |  |  |  | 0 | 6233.96 | 6233.96 | 6233.96 | 6233.96 | 6233.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2294 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 18655.9893 | 0.2 | 0.3 | 29103.3433 |  |  |  |  | 0 | 3647.3207 | 3647.3207 | 3647.3207 | 3647.3207 | 3647.3207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2295 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 4911.5145 | 0.2 | 0.3 | 7661.9626 |  |  |  |  | 0 | 6886.5899 | 6886.5899 | 6886.5899 | 6886.5899 | 6886.5899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2296 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 11766.4983 | 0.2 | 0.3 | 18355.7374 |  |  |  |  | 0 | 9728.4783 | 9728.4783 | 9728.4783 | 9728.4783 | 9728.4783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2297 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 33357.9211 | 0.2 | 0.3 | 52038.357 |  |  |  |  | 0 | 1517.8488 | 1517.8488 | 1517.8488 | 1517.8488 | 1517.8488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2298 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 15394.3706 | 0.2 | 0.3 | 24015.2181 |  |  |  |  | 0 | 3167.7225 | 3167.7225 | 3167.7225 | 3167.7225 | 3167.7225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2299 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16671.7941 | 0.2 | 0.3 | 26007.9987 |  |  |  |  | 0 | 5654.3779 | 5654.3779 | 5654.3779 | 5654.3779 | 5654.3779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2300 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 4938.0368 | 0.2 | 0.3 | 7703.3374 |  |  |  |  | 0 | 10400.0437 | 10400.0437 | 10400.0437 | 10400.0437 | 10400.0437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2301 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 30654.0844 | 0.2 | 0.3 | 47820.3717 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2302 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 7508.2592 | 0.2 | 0.3 | 11712.8844 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2303 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 9584.6557 | 0.2 | 0.3 | 14952.0628 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2304 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16991.2267 | 0.2 | 0.3 | 26506.3137 |  |  |  |  | 0 | 5203.575 | 5203.575 | 5203.575 | 5203.575 | 5203.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2305 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 8608.662 | 0.2 | 0.3 | 13429.5127 |  |  |  |  | 0 | 7508.1636 | 7508.1636 | 7508.1636 | 7508.1636 | 7508.1636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2306 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 2739.5125 | 0.2 | 0.3 | 4273.6396 |  |  |  |  | 0 | 7480.806 | 7480.806 | 7480.806 | 7480.806 | 7480.806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2307 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 18565.7705 | 0.2 | 0.3 | 28962.602 |  |  |  |  | 0 | 5309.3883 | 5309.3883 | 5309.3883 | 5309.3883 | 5309.3883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2308 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 9953.6468 | 0.2 | 0.3 | 15527.689 |  |  |  |  | 0 | 5199.9814 | 5199.9814 | 5199.9814 | 5199.9814 | 5199.9814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2309 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16805.1752 | 0.2 | 0.3 | 26216.0733 |  |  |  |  | 0 | 7329.3843 | 7329.3843 | 7329.3843 | 7329.3843 | 7329.3843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2310 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 9192.1511 | 0.2 | 0.3 | 14339.7558 |  |  |  |  | 0 | 5220.4055 | 5220.4055 | 5220.4055 | 5220.4055 | 5220.4055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2311 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 8836.7755 | 0.2 | 0.3 | 13785.3697 |  |  |  |  | 0 | 8979.1449 | 8979.1449 | 8979.1449 | 8979.1449 | 8979.1449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2312 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 18732.9368 | 0.2 | 0.3 | 29223.3814 |  |  |  |  | 0 | 9254.2202 | 9254.2202 | 9254.2202 | 9254.2202 | 9254.2202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2313 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 16788.8026 | 0.2 | 0.3 | 26190.5321 |  |  |  |  | 0 | 14352.2512 | 14352.2512 | 14352.2512 | 14352.2512 | 14352.2512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2314 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 18855.3857 | 0.2 | 0.3 | 29414.4016 |  |  |  |  | 0 | 9776.1408 | 9776.1408 | 9776.1408 | 9776.1408 | 9776.1408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2315 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 1796.7207 | 0.2 | 0.3 | 2802.8843 |  |  |  |  | 0 | 9776.2385 | 9776.2385 | 9776.2385 | 9776.2385 | 9776.2385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2316 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 23230.0213 | 0.2 | 0.3 | 36238.8332 |  |  |  |  | 0 | 9776.0845 | 9776.0845 | 9776.0845 | 9776.0845 | 9776.0845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2317 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 35499.5617 | 0.2 | 0.3 | 55379.3163 |  |  |  |  | 0 | 6038.5627 | 6038.5627 | 6038.5627 | 6038.5627 | 6038.5627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2318 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 25240.1519 | 0.2 | 0.3 | 39374.637 |  |  |  |  | 0 | 5026.1085 | 5026.1085 | 5026.1085 | 5026.1085 | 5026.1085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2319 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 28332.3489 | 0.2 | 0.3 | 44198.4643 |  |  |  |  | 0 | 2600.0421 | 2600.0421 | 2600.0421 | 2600.0421 | 2600.0421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2320 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 17404.8679 | 0.2 | 0.3 | 27151.5939 |  |  |  |  | 0 | 5177.6325 | 5177.6325 | 5177.6325 | 5177.6325 | 5177.6325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2321 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 28247.3184 | 0.2 | 0.3 | 44065.8167 |  |  |  |  | 0 | 7383.4776 | 7383.4776 | 7383.4776 | 7383.4776 | 7383.4776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2322 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 16183.2301 | 0.2 | 0.3 | 25245.839 |  |  |  |  | 0 | 8828.4019 | 8828.4019 | 8828.4019 | 8828.4019 | 8828.4019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2323 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 17537.8414 | 0.2 | 0.3 | 27359.0326 |  |  |  |  | 0 | 5199.9793 | 5199.9793 | 5199.9793 | 5199.9793 | 5199.9793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2324 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 23266.6939 | 0.2 | 0.3 | 36296.0425 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2325 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 37568.4103 | 0.2 | 0.3 | 58606.72 |  |  |  |  | 0 | 5199.9808 | 5199.9808 | 5199.9808 | 5199.9808 | 5199.9808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2326 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 20712.8343 | 0.2 | 0.3 | 32312.0215 |  |  |  |  | 0 | 8458.0322 | 8458.0322 | 8458.0322 | 8458.0322 | 8458.0322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2327 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16691.6459 | 0.2 | 0.3 | 26038.9677 |  |  |  |  | 0 | 10399.9473 | 10399.9473 | 10399.9473 | 10399.9473 | 10399.9473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2328 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 5200.1799 | 5200.1799 | 5200.1799 | 5200.1799 | 5200.1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2329 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 23222.1878 | 0.2 | 0.3 | 36226.613 |  |  |  |  | 0 | 5200.146 | 5200.146 | 5200.146 | 5200.146 | 5200.146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2330 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 17146.8303 | 0.2 | 0.3 | 26749.0552 |  |  |  |  | 0 | 5199.998 | 5199.998 | 5199.998 | 5199.998 | 5199.998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2331 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16676.7894 | 0.2 | 0.3 | 26015.7915 |  |  |  |  | 0 | 7721.8181 | 7721.8181 | 7721.8181 | 7721.8181 | 7721.8181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2332 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16699.1075 | 0.2 | 0.3 | 26050.6078 |  |  |  |  | 0 | 9930.4345 | 9930.4345 | 9930.4345 | 9930.4345 | 9930.4345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2333 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 5647.5549 | 0.2 | 0.3 | 8810.1856 |  |  |  |  | 0 | 2599.9392 | 2599.9392 | 2599.9392 | 2599.9392 | 2599.9392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2334 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 18465.7163 | 0.2 | 0.3 | 28806.5175 |  |  |  |  | 0 | 7319.2116 | 7319.2116 | 7319.2116 | 7319.2116 | 7319.2116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2335 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 8365.2607 | 0.2 | 0.3 | 13049.8067 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2336 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 8265.1718 | 0.2 | 0.3 | 12893.668 |  |  |  |  | 0 | 6365.1423 | 6365.1423 | 6365.1423 | 6365.1423 | 6365.1423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2337 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 8333.7654 | 0.2 | 0.3 | 13000.674 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2338 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 8333.3248 | 0.2 | 0.3 | 12999.9867 |  |  |  |  | 0 | 5714.7151 | 5714.7151 | 5714.7151 | 5714.7151 | 5714.7151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2339 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 3592.5319 | 0.2 | 0.3 | 5604.3498 |  |  |  |  | 0 | 5200.0463 | 5200.0463 | 5200.0463 | 5200.0463 | 5200.0463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2340 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16681.4994 | 0.2 | 0.3 | 26023.1391 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2341 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16691.8096 | 0.2 | 0.3 | 26039.223 |  |  |  |  | 0 | 5200.0232 | 5200.0232 | 5200.0232 | 5200.0232 | 5200.0232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2342 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 26102.9125 | 0.2 | 0.3 | 40720.5434 |  |  |  |  | 0 | 3918.3801 | 3918.3801 | 3918.3801 | 3918.3801 | 3918.3801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2343 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.0929 | 0.2 | 0.3 | 26010.025 |  |  |  |  | 0 | 10399.8954 | 10399.8954 | 10399.8954 | 10399.8954 | 10399.8954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2344 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.1617 | 0.2 | 0.3 | 26010.1322 |  |  |  |  | 0 | 5200.2604 | 5200.2604 | 5200.2604 | 5200.2604 | 5200.2604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2345 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.414 | 0.2 | 0.3 | 26010.5258 |  |  |  |  | 0 | 5200.222 | 5200.222 | 5200.222 | 5200.222 | 5200.222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2346 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 19960.2749 | 0.2 | 0.3 | 31138.0289 |  |  |  |  | 0 | 5200.0561 | 5200.0561 | 5200.0561 | 5200.0561 | 5200.0561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2347 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16721.6898 | 0.2 | 0.3 | 26085.8361 |  |  |  |  | 0 | 6837.6315 | 6837.6315 | 6837.6315 | 6837.6315 | 6837.6315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2348 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 24269.8438 | 0.2 | 0.3 | 37860.9563 |  |  |  |  | 0 | 7520.7395 | 7520.7395 | 7520.7395 | 7520.7395 | 7520.7395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2349 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16676.1686 | 0.2 | 0.3 | 26014.823 |  |  |  |  | 0 | 2600.2049 | 2600.2049 | 2600.2049 | 2600.2049 | 2600.2049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2350 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 22055.3299 | 0.2 | 0.3 | 34406.3146 |  |  |  |  | 0 | 12223.6368 | 12223.6368 | 12223.6368 | 12223.6368 | 12223.6368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2351 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 9202.2976 | 0.2 | 0.3 | 14355.5843 |  |  |  |  | 0 | 10113.0651 | 10113.0651 | 10113.0651 | 10113.0651 | 10113.0651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2352 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 22515.7756 | 0.2 | 0.3 | 35124.6099 |  |  |  |  | 0 | 10400.0437 | 10400.0437 | 10400.0437 | 10400.0437 | 10400.0437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2353 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17073.3606 | 0.2 | 0.3 | 26634.4425 |  |  |  |  | 0 | 10400.0723 | 10400.0723 | 10400.0723 | 10400.0723 | 10400.0723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2354 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16982.8111 | 0.2 | 0.3 | 26493.1853 |  |  |  |  | 0 | 11799.8557 | 11799.8557 | 11799.8557 | 11799.8557 | 11799.8557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2355 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16961.7263 | 0.2 | 0.3 | 26460.2931 |  |  |  |  | 0 | 10400.9978 | 10400.9978 | 10400.9978 | 10400.9978 | 10400.9978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2356 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 3.5977 | 0.2 | 0.3 | 5.6124 |  |  |  |  | 0 | 9584.3791 | 9584.3791 | 9584.3791 | 9584.3791 | 9584.3791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2357 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 26397.0345 | 0.2 | 0.3 | 41179.3738 |  |  |  |  | 0 | 7800.017 | 7800.017 | 7800.017 | 7800.017 | 7800.017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2358 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16695.4882 | 0.2 | 0.3 | 26044.9616 |  |  |  |  | 0 | 7908.1599 | 7908.1599 | 7908.1599 | 7908.1599 | 7908.1599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2359 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 30601.2347 | 0.2 | 0.3 | 47737.9261 |  |  |  |  | 0 | 6723.1464 | 6723.1464 | 6723.1464 | 6723.1464 | 6723.1464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2360 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 6536.334 | 0.2 | 0.3 | 10196.681 |  |  |  |  | 0 | 7727.9245 | 7727.9245 | 7727.9245 | 7727.9245 | 7727.9245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2361 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16820.6559 | 0.2 | 0.3 | 26240.2232 |  |  |  |  | 0 | 5564.6227 | 5564.6227 | 5564.6227 | 5564.6227 | 5564.6227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2362 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16820.3637 | 0.2 | 0.3 | 26239.7674 |  |  |  |  | 0 | 3289.6346 | 3289.6346 | 3289.6346 | 3289.6346 | 3289.6346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2363 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 25627.3312 | 0.2 | 0.3 | 39978.6367 |  |  |  |  | 0 | 4083.508 | 4083.508 | 4083.508 | 4083.508 | 4083.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2364 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 18756.1381 | 0.2 | 0.3 | 29259.5754 |  |  |  |  | 0 | 6855.4471 | 6855.4471 | 6855.4471 | 6855.4471 | 6855.4471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2365 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16967.5336 | 0.2 | 0.3 | 26469.3524 |  |  |  |  | 0 | 7549.3268 | 7549.3268 | 7549.3268 | 7549.3268 | 7549.3268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2366 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 12939.7459 | 0.2 | 0.3 | 20186.0036 |  |  |  |  | 0 | 2600.1504 | 2600.1504 | 2600.1504 | 2600.1504 | 2600.1504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2367 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 12995.047 | 0.2 | 0.3 | 20272.2733 |  |  |  |  | 0 | 8750.4089 | 8750.4089 | 8750.4089 | 8750.4089 | 8750.4089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2368 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 6399.4279 | 0.2 | 0.3 | 9983.1076 |  |  |  |  | 0 | 5486.8187 | 5486.8187 | 5486.8187 | 5486.8187 | 5486.8187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2369 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 31224.0513 | 0.2 | 0.3 | 48709.52 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2370 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 26265.4195 | 0.2 | 0.3 | 40974.0544 |  |  |  |  | 0 | 5199.9637 | 5199.9637 | 5199.9637 | 5199.9637 | 5199.9637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2371 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16668.06 | 0.2 | 0.3 | 26002.1736 |  |  |  |  | 0 | 7268.7481 | 7268.7481 | 7268.7481 | 7268.7481 | 7268.7481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2372 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 19753.2387 | 0.2 | 0.3 | 30815.0523 |  |  |  |  | 0 | 859.6794 | 859.6794 | 859.6794 | 859.6794 | 859.6794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2373 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 28718.5227 | 0.2 | 0.3 | 44800.8954 |  |  |  |  | 0 | 2600.0496 | 2600.0496 | 2600.0496 | 2600.0496 | 2600.0496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2374 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 22435.3647 | 0.2 | 0.3 | 34999.169 |  |  |  |  | 0 | 2491.846 | 2491.846 | 2491.846 | 2491.846 | 2491.846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2375 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 27124.3967 | 0.2 | 0.3 | 42314.0588 |  |  |  |  | 0 | 9265.5957 | 9265.5957 | 9265.5957 | 9265.5957 | 9265.5957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2376 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 18947.7326 | 0.2 | 0.3 | 29558.4629 |  |  |  |  | 0 | 5200.0382 | 5200.0382 | 5200.0382 | 5200.0382 | 5200.0382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2377 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 22628.7627 | 0.2 | 0.3 | 35300.8698 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2378 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 22279.9639 | 0.2 | 0.3 | 34756.7437 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2379 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 26459.1513 | 0.2 | 0.3 | 41276.276 |  |  |  |  | 0 | 5200.0232 | 5200.0232 | 5200.0232 | 5200.0232 | 5200.0232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2380 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16881.7533 | 0.2 | 0.3 | 26335.5352 |  |  |  |  | 0 | 7647.7182 | 7647.7182 | 7647.7182 | 7647.7182 | 7647.7182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2381 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 20463.6802 | 0.2 | 0.3 | 31923.3411 |  |  |  |  | 0 | 10057.108 | 10057.108 | 10057.108 | 10057.108 | 10057.108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2382 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 25481.0445 | 0.2 | 0.3 | 39750.4295 |  |  |  |  | 0 | 2599.947 | 2599.947 | 2599.947 | 2599.947 | 2599.947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2383 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 16789.9044 | 0.2 | 0.3 | 26192.2509 |  |  |  |  | 0 | 6799.0344 | 6799.0344 | 6799.0344 | 6799.0344 | 6799.0344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2384 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 24525.7871 | 0.2 | 0.3 | 38260.2279 |  |  |  |  | 0 | 5199.981 | 5199.981 | 5199.981 | 5199.981 | 5199.981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2385 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 15076.2204 | 0.2 | 0.3 | 23518.9038 |  |  |  |  | 0 | 5200.0786 | 5200.0786 | 5200.0786 | 5200.0786 | 5200.0786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2386 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 1708.5348 | 0.2 | 0.3 | 2665.3143 |  |  |  |  | 0 | 5200.0983 | 5200.0983 | 5200.0983 | 5200.0983 | 5200.0983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2387 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 19157.1503 | 0.2 | 0.3 | 29885.1545 |  |  |  |  | 0 | 5299.09 | 5299.09 | 5299.09 | 5299.09 | 5299.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2388 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 13304.3872 | 0.2 | 0.3 | 20754.844 |  |  |  |  | 0 | 6984.9466 | 6984.9466 | 6984.9466 | 6984.9466 | 6984.9466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2389 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 25893.5241 | 0.2 | 0.3 | 40393.8976 |  |  |  |  | 0 | 5200.0021 | 5200.0021 | 5200.0021 | 5200.0021 | 5200.0021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2390 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 22380.0571 | 0.2 | 0.3 | 34912.889 |  |  |  |  | 0 | 5199.9814 | 5199.9814 | 5199.9814 | 5199.9814 | 5199.9814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2391 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 24909.0197 | 0.2 | 0.3 | 38858.0707 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2392 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 16678.4777 | 0.2 | 0.3 | 26018.4252 |  |  |  |  | 0 | 5199.9857 | 5199.9857 | 5199.9857 | 5199.9857 | 5199.9857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2393 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 21088.8109 | 0.2 | 0.3 | 32898.545 |  |  |  |  | 0 | 13313.6873 | 13313.6873 | 13313.6873 | 13313.6873 | 13313.6873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2394 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 35902.9649 | 0.2 | 0.3 | 56008.6252 |  |  |  |  | 0 | 10400.1544 | 10400.1544 | 10400.1544 | 10400.1544 | 10400.1544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2395 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 3169.7999 | 0.2 | 0.3 | 4944.8879 |  |  |  |  | 0 | 10400.129 | 10400.129 | 10400.129 | 10400.129 | 10400.129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2396 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 26919.2756 | 0.2 | 0.3 | 41994.0699 |  |  |  |  | 0 | 10400.0437 | 10400.0437 | 10400.0437 | 10400.0437 | 10400.0437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2397 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 23078.0209 | 0.2 | 0.3 | 36001.7127 |  |  |  |  | 0 | 10397.6081 | 10397.6081 | 10397.6081 | 10397.6081 | 10397.6081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2398 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16669.5003 | 0.2 | 0.3 | 26004.4204 |  |  |  |  | 0 | 6889.2924 | 6889.2924 | 6889.2924 | 6889.2924 | 6889.2924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2399 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 24477.5978 | 0.2 | 0.3 | 38185.0526 |  |  |  |  | 0 | 9604.5218 | 9604.5218 | 9604.5218 | 9604.5218 | 9604.5218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2400 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 1375.2566 | 0.2 | 0.3 | 2145.4003 |  |  |  |  | 0 | 2356.577 | 2356.577 | 2356.577 | 2356.577 | 2356.577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2401 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16692.5969 | 0.2 | 0.3 | 26040.4512 |  |  |  |  | 0 | 5199.9795 | 5199.9795 | 5199.9795 | 5199.9795 | 5199.9795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2402 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 21354.6143 | 0.2 | 0.3 | 33313.1983 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2403 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 27850.8548 | 0.2 | 0.3 | 43447.3335 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2404 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 6277.4268 | 0.2 | 0.3 | 9792.7858 |  |  |  |  | 0 | 5199.9835 | 5199.9835 | 5199.9835 | 5199.9835 | 5199.9835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2405 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 19328.5331 | 0.2 | 0.3 | 30152.5116 |  |  |  |  | 0 | 9776.3026 | 9776.3026 | 9776.3026 | 9776.3026 | 9776.3026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2406 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16669.4105 | 0.2 | 0.3 | 26004.2803 |  |  |  |  | 0 | 5199.9821 | 5199.9821 | 5199.9821 | 5199.9821 | 5199.9821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2407 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 17981.1637 | 0.2 | 0.3 | 28050.6154 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2408 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 23878.7011 | 0.2 | 0.3 | 37250.7738 |  |  |  |  | 0 | 5199.9952 | 5199.9952 | 5199.9952 | 5199.9952 | 5199.9952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2409 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 8333.8399 | 0.2 | 0.3 | 13000.7902 |  |  |  |  | 0 | 7880.5008 | 7880.5008 | 7880.5008 | 7880.5008 | 7880.5008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2410 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 8333.3248 | 0.2 | 0.3 | 12999.9867 |  |  |  |  | 0 | 9776.4966 | 9776.4966 | 9776.4966 | 9776.4966 | 9776.4966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2411 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 20360.9024 | 0.2 | 0.3 | 31763.0077 |  |  |  |  | 0 | 8677.8701 | 8677.8701 | 8677.8701 | 8677.8701 | 8677.8701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2412 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 18816.7503 | 0.2 | 0.3 | 29354.1304 |  |  |  |  | 0 | 5199.9818 | 5199.9818 | 5199.9818 | 5199.9818 | 5199.9818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2413 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 22646.6282 | 0.2 | 0.3 | 35328.74 |  |  |  |  | 0 | 2400.4046 | 2400.4046 | 2400.4046 | 2400.4046 | 2400.4046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2414 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16682.6589 | 0.2 | 0.3 | 26024.9479 |  |  |  |  | 0 | 2799.5764 | 2799.5764 | 2799.5764 | 2799.5764 | 2799.5764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2415 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 14395.5736 | 0.2 | 0.3 | 22457.0948 |  |  |  |  | 0 | 3285.2689 | 3285.2689 | 3285.2689 | 3285.2689 | 3285.2689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2416 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16052.4105 | 0.2 | 0.3 | 25041.7604 |  |  |  |  | 0 | 8135.4891 | 8135.4891 | 8135.4891 | 8135.4891 | 8135.4891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2417 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 23165.8074 | 0.2 | 0.3 | 36138.6595 |  |  |  |  | 0 | 5201.048 | 5201.048 | 5201.048 | 5201.048 | 5201.048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2418 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 22902.3215 | 0.2 | 0.3 | 35727.6216 |  |  |  |  | 0 | 5218.986 | 5218.986 | 5218.986 | 5218.986 | 5218.986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2419 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 17214.6993 | 0.2 | 0.3 | 26854.931 |  |  |  |  | 0 | 5200.8061 | 5200.8061 | 5200.8061 | 5200.8061 | 5200.8061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2420 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 5584.9765 | 0.2 | 0.3 | 8712.5633 |  |  |  |  | 0 | 5982.6647 | 5982.6647 | 5982.6647 | 5982.6647 | 5982.6647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2421 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 27023.9056 | 0.2 | 0.3 | 42157.2927 |  |  |  |  | 0 | 11913.2995 | 11913.2995 | 11913.2995 | 11913.2995 | 11913.2995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2422 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16680.6475 | 0.2 | 0.3 | 26021.81 |  |  |  |  | 0 | 5200.0033 | 5200.0033 | 5200.0033 | 5200.0033 | 5200.0033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2423 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 7558.9073 | 0.2 | 0.3 | 11791.8954 |  |  |  |  | 0 | 5366.3871 | 5366.3871 | 5366.3871 | 5366.3871 | 5366.3871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2424 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 12793.3573 | 0.2 | 0.3 | 19957.6373 |  |  |  |  | 0 | 7553.0816 | 7553.0816 | 7553.0816 | 7553.0816 | 7553.0816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2425 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 9777.175 | 9777.175 | 9777.175 | 9777.175 | 9777.175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2426 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 29125.8855 | 0.2 | 0.3 | 45436.3814 |  |  |  |  | 0 | 8964.4677 | 8964.4677 | 8964.4677 | 8964.4677 | 8964.4677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2427 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17961.1774 | 0.2 | 0.3 | 28019.4367 |  |  |  |  | 0 | 6851.3732 | 6851.3732 | 6851.3732 | 6851.3732 | 6851.3732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2428 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 12841.0249 | 0.2 | 0.3 | 20031.9988 |  |  |  |  | 0 | 3307.1678 | 3307.1678 | 3307.1678 | 3307.1678 | 3307.1678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2429 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 16485.5168 | 0.2 | 0.3 | 25717.4062 |  |  |  |  | 0 | 2857.0498 | 2857.0498 | 2857.0498 | 2857.0498 | 2857.0498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2430 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 23481.6878 | 0.2 | 0.3 | 36631.433 |  |  |  |  | 0 | 8226.4307 | 8226.4307 | 8226.4307 | 8226.4307 | 8226.4307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2431 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 17161.3594 | 0.2 | 0.3 | 26771.7207 |  |  |  |  | 0 | 5390.4064 | 5390.4064 | 5390.4064 | 5390.4064 | 5390.4064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2432 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 15204.2401 | 0.2 | 0.3 | 23718.6145 |  |  |  |  | 0 | 5200.2278 | 5200.2278 | 5200.2278 | 5200.2278 | 5200.2278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2433 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 30514.7629 | 0.2 | 0.3 | 47603.0301 |  |  |  |  | 0 | 5199.8086 | 5199.8086 | 5199.8086 | 5199.8086 | 5199.8086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2434 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17473.5422 | 0.2 | 0.3 | 27258.7258 |  |  |  |  | 0 | 5199.9468 | 5199.9468 | 5199.9468 | 5199.9468 | 5199.9468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2435 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 23505.6755 | 0.2 | 0.3 | 36668.8538 |  |  |  |  | 0 | 3729.4814 | 3729.4814 | 3729.4814 | 3729.4814 | 3729.4814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2436 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 4995.4704 | 0.2 | 0.3 | 7792.9338 |  |  |  |  | 0 | 5200.0422 | 5200.0422 | 5200.0422 | 5200.0422 | 5200.0422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2437 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 21481.5012 | 0.2 | 0.3 | 33511.1419 |  |  |  |  | 0 | 6783.9148 | 6783.9148 | 6783.9148 | 6783.9148 | 6783.9148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2438 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 8853.917 | 0.2 | 0.3 | 13812.1105 |  |  |  |  | 0 | 6358.8277 | 6358.8277 | 6358.8277 | 6358.8277 | 6358.8277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2439 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 23399.0158 | 0.2 | 0.3 | 36502.4646 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2440 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17505.492 | 0.2 | 0.3 | 27308.5675 |  |  |  |  | 0 | 8195.5682 | 8195.5682 | 8195.5682 | 8195.5682 | 8195.5682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2441 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 12924.0133 | 0.2 | 0.3 | 20161.4607 |  |  |  |  | 0 | 9781.5604 | 9781.5604 | 9781.5604 | 9781.5604 | 9781.5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2442 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16666.7637 | 0.2 | 0.3 | 26000.1513 |  |  |  |  | 0 | 9869.4747 | 9869.4747 | 9869.4747 | 9869.4747 | 9869.4747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2443 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 20230.763 | 0.2 | 0.3 | 31559.9903 |  |  |  |  | 0 | 5946.8945 | 5946.8945 | 5946.8945 | 5946.8945 | 5946.8945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2444 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 5329.7404 | 5329.7404 | 5329.7404 | 5329.7404 | 5329.7404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2445 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 22077.2732 | 0.2 | 0.3 | 34440.5462 |  |  |  |  | 0 | 5405.4446 | 5405.4446 | 5405.4446 | 5405.4446 | 5405.4446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2446 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16808.3081 | 0.2 | 0.3 | 26220.9606 |  |  |  |  | 0 | 7599.2451 | 7599.2451 | 7599.2451 | 7599.2451 | 7599.2451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2447 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16467.3243 | 0.2 | 0.3 | 25689.026 |  |  |  |  | 0 | 6704.6625 | 6704.6625 | 6704.6625 | 6704.6625 | 6704.6625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2448 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 21313.4485 | 0.2 | 0.3 | 33248.9796 |  |  |  |  | 0 | 5201.9325 | 5201.9325 | 5201.9325 | 5201.9325 | 5201.9325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2449 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16118.9926 | 0.2 | 0.3 | 25145.6285 |  |  |  |  | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2450 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 17753.0245 | 0.2 | 0.3 | 27694.7182 |  |  |  |  | 0 | 9607.1036 | 9607.1036 | 9607.1036 | 9607.1036 | 9607.1036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2451 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 24312.1284 | 0.2 | 0.3 | 37926.9203 |  |  |  |  | 0 | 7542.0961 | 7542.0961 | 7542.0961 | 7542.0961 | 7542.0961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2452 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 11695.6565 | 0.2 | 0.3 | 18245.2241 |  |  |  |  | 0 | 5200.0272 | 5200.0272 | 5200.0272 | 5200.0272 | 5200.0272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2453 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 17285.5127 | 0.2 | 0.3 | 26965.3998 |  |  |  |  | 0 | 5200.3019 | 5200.3019 | 5200.3019 | 5200.3019 | 5200.3019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2454 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 26826.6665 | 0.2 | 0.3 | 41849.5998 |  |  |  |  | 0 | 5203.6122 | 5203.6122 | 5203.6122 | 5203.6122 | 5203.6122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2455 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16557.3397 | 0.2 | 0.3 | 25829.4499 |  |  |  |  | 0 | 5200.0855 | 5200.0855 | 5200.0855 | 5200.0855 | 5200.0855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2456 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 237.4493 | 0.2 | 0.3 | 370.4209 |  |  |  |  | 0 | 5200.0701 | 5200.0701 | 5200.0701 | 5200.0701 | 5200.0701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2457 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 16789.4783 | 0.2 | 0.3 | 26191.5862 |  |  |  |  | 0 | 5199.8998 | 5199.8998 | 5199.8998 | 5199.8998 | 5199.8998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2458 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 6220.3873 | 0.2 | 0.3 | 9703.8042 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2459 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 13156.5012 | 0.2 | 0.3 | 20524.1419 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2460 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 14211.5994 | 0.2 | 0.3 | 22170.0951 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2461 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 20729.3801 | 0.2 | 0.3 | 32337.833 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2462 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 6534.315 | 0.2 | 0.3 | 10193.5314 |  |  |  |  | 0 | 9805.6555 | 9805.6555 | 9805.6555 | 9805.6555 | 9805.6555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2463 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 21811.2809 | 0.2 | 0.3 | 34025.5983 |  |  |  |  | 0 | 6431.7164 | 6431.7164 | 6431.7164 | 6431.7164 | 6431.7164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2464 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 22927.2266 | 0.2 | 0.3 | 35766.4735 |  |  |  |  | 0 | 3006.4236 | 3006.4236 | 3006.4236 | 3006.4236 | 3006.4236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2465 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 12295.1414 | 0.2 | 0.3 | 19180.4206 |  |  |  |  | 0 | 3526.1043 | 3526.1043 | 3526.1043 | 3526.1043 | 3526.1043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2466 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 14980.4267 | 0.2 | 0.3 | 23369.4656 |  |  |  |  | 0 | 3812.1453 | 3812.1453 | 3812.1453 | 3812.1453 | 3812.1453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2467 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 23669.5628 | 0.2 | 0.3 | 36924.518 |  |  |  |  | 0 | 8841.6669 | 8841.6669 | 8841.6669 | 8841.6669 | 8841.6669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2468 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 36383.4317 | 0.2 | 0.3 | 56758.1534 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2469 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 13948.2739 | 0.2 | 0.3 | 21759.3072 |  |  |  |  | 0 | 8092.6737 | 8092.6737 | 8092.6737 | 8092.6737 | 8092.6737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2470 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16672.3415 | 0.2 | 0.3 | 26008.8527 |  |  |  |  | 0 | 5238.9323 | 5238.9323 | 5238.9323 | 5238.9323 | 5238.9323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2471 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16672.2767 | 0.2 | 0.3 | 26008.7517 |  |  |  |  | 0 | 5205.2298 | 5205.2298 | 5205.2298 | 5205.2298 | 5205.2298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2472 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 23409.6959 | 0.2 | 0.3 | 36519.1257 |  |  |  |  | 0 | 5435.5451 | 5435.5451 | 5435.5451 | 5435.5451 | 5435.5451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2473 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 25034.0997 | 0.2 | 0.3 | 39053.1955 |  |  |  |  | 0 | 8999.7445 | 8999.7445 | 8999.7445 | 8999.7445 | 8999.7445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2474 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16676.786 | 0.2 | 0.3 | 26015.7862 |  |  |  |  | 0 | 8280.5567 | 8280.5567 | 8280.5567 | 8280.5567 | 8280.5567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2475 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 24020.7791 | 0.2 | 0.3 | 37472.4153 |  |  |  |  | 0 | 6954.2043 | 6954.2043 | 6954.2043 | 6954.2043 | 6954.2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2476 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 27703.5233 | 0.2 | 0.3 | 43217.4963 |  |  |  |  | 0 | 6364.1291 | 6364.1291 | 6364.1291 | 6364.1291 | 6364.1291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2477 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16677.5076 | 0.2 | 0.3 | 26016.9119 |  |  |  |  | 0 | 9286.087 | 9286.087 | 9286.087 | 9286.087 | 9286.087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2478 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16675.2548 | 0.2 | 0.3 | 26013.3975 |  |  |  |  | 0 | 5390.2015 | 5390.2015 | 5390.2015 | 5390.2015 | 5390.2015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2479 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 7816.4174 | 0.2 | 0.3 | 12193.6111 |  |  |  |  | 0 | 1342.3737 | 1342.3737 | 1342.3737 | 1342.3737 | 1342.3737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2480 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16542.6143 | 0.2 | 0.3 | 25806.4784 |  |  |  |  | 0 | 12122.4174 | 12122.4174 | 12122.4174 | 12122.4174 | 12122.4174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2481 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 21507.1989 | 0.2 | 0.3 | 33551.2302 |  |  |  |  | 0 | 10410.6211 | 10410.6211 | 10410.6211 | 10410.6211 | 10410.6211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2482 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 22573.7959 | 0.2 | 0.3 | 35215.1216 |  |  |  |  | 0 | 12258.3167 | 12258.3167 | 12258.3167 | 12258.3167 | 12258.3167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2483 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 18093.5825 | 0.2 | 0.3 | 28225.9886 |  |  |  |  | 0 | 9237.8069 | 9237.8069 | 9237.8069 | 9237.8069 | 9237.8069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2484 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16888.5495 | 0.2 | 0.3 | 26346.1373 |  |  |  |  | 0 | 11552.6354 | 11552.6354 | 11552.6354 | 11552.6354 | 11552.6354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2485 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 17104.064 | 0.2 | 0.3 | 26682.3398 |  |  |  |  | 0 | 6782.64 | 6782.64 | 6782.64 | 6782.64 | 6782.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2486 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 10779.4286 | 0.2 | 0.3 | 16815.9086 |  |  |  |  | 0 | 5028.296 | 5028.296 | 5028.296 | 5028.296 | 5028.296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2487 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16673.1169 | 0.2 | 0.3 | 26010.0623 |  |  |  |  | 0 | 142.5728 | 142.5728 | 142.5728 | 142.5728 | 142.5728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2488 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16670.7493 | 0.2 | 0.3 | 26006.3689 |  |  |  |  | 0 | 8392.783 | 8392.783 | 8392.783 | 8392.783 | 8392.783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2489 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16669.0074 | 0.2 | 0.3 | 26003.6515 |  |  |  |  | 0 | 5205.865 | 5205.865 | 5205.865 | 5205.865 | 5205.865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2490 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16881.2616 | 0.2 | 0.3 | 26334.7681 |  |  |  |  | 0 | 10596.2121 | 10596.2121 | 10596.2121 | 10596.2121 | 10596.2121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2491 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16742.1731 | 0.2 | 0.3 | 26117.79 |  |  |  |  | 0 | 8799.8426 | 8799.8426 | 8799.8426 | 8799.8426 | 8799.8426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2492 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 12173.215 | 12173.215 | 12173.215 | 12173.215 | 12173.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2493 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 5205.179 | 5205.179 | 5205.179 | 5205.179 | 5205.179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2494 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 17009.7419 | 0.2 | 0.3 | 26535.1974 |  |  |  |  | 0 | 5720.3257 | 5720.3257 | 5720.3257 | 5720.3257 | 5720.3257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2495 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 9426.5439 | 0.2 | 0.3 | 14705.4084 |  |  |  |  | 0 | 6240.1379 | 6240.1379 | 6240.1379 | 6240.1379 | 6240.1379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2496 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16677.2083 | 0.2 | 0.3 | 26016.4449 |  |  |  |  | 0 | 8129.799 | 8129.799 | 8129.799 | 8129.799 | 8129.799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2497 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 31350.7085 | 0.2 | 0.3 | 48907.1053 |  |  |  |  | 0 | 5205.3532 | 5205.3532 | 5205.3532 | 5205.3532 | 5205.3532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2498 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.6227 | 0.2 | 0.3 | 26010.8515 |  |  |  |  | 0 | 10519.7877 | 10519.7877 | 10519.7877 | 10519.7877 | 10519.7877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2499 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 6817.276 | 6817.276 | 6817.276 | 6817.276 | 6817.276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2500 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16674.7618 | 0.2 | 0.3 | 26012.6284 |  |  |  |  | 0 | 8880.0692 | 8880.0692 | 8880.0692 | 8880.0692 | 8880.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2501 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 8809.0348 | 0.2 | 0.3 | 13742.0943 |  |  |  |  | 0 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2502 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 11308.6716 | 0.2 | 0.3 | 17641.5277 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2503 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 338.0472 | 0.2 | 0.3 | 527.3536 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2504 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 18447.897 | 0.2 | 0.3 | 28778.7193 |  |  |  |  | 0 | 5201.4929 | 5201.4929 | 5201.4929 | 5201.4929 | 5201.4929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2505 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 1266.4553 | 0.2 | 0.3 | 1975.6703 |  |  |  |  | 0 | 7957.2346 | 7957.2346 | 7957.2346 | 7957.2346 | 7957.2346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2506 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 7806.386 | 0.2 | 0.3 | 12177.9622 |  |  |  |  | 0 | 14191.6005 | 14191.6005 | 14191.6005 | 14191.6005 | 14191.6005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2507 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17043.1959 | 0.2 | 0.3 | 26587.3856 |  |  |  |  | 0 | 10412.9634 | 10412.9634 | 10412.9634 | 10412.9634 | 10412.9634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2508 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16866.9595 | 0.2 | 0.3 | 26312.4569 |  |  |  |  | 0 | 13008.7032 | 13008.7032 | 13008.7032 | 13008.7032 | 13008.7032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2509 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16713.2409 | 0.2 | 0.3 | 26072.6559 |  |  |  |  | 0 | 5204.767 | 5204.767 | 5204.767 | 5204.767 | 5204.767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2510 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 26748.8543 | 0.2 | 0.3 | 41728.2128 |  |  |  |  | 0 | 5203.5394 | 5203.5394 | 5203.5394 | 5203.5394 | 5203.5394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2511 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 4754.6675 | 0.2 | 0.3 | 7417.2812 |  |  |  |  | 0 | 5203.6725 | 5203.6725 | 5203.6725 | 5203.6725 | 5203.6725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2512 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 34414.1993 | 0.2 | 0.3 | 53686.1509 |  |  |  |  | 0 | 7658.9686 | 7658.9686 | 7658.9686 | 7658.9686 | 7658.9686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2513 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 22455.1981 | 0.2 | 0.3 | 35030.1091 |  |  |  |  | 0 | 9957.2805 | 9957.2805 | 9957.2805 | 9957.2805 | 9957.2805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2514 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 26626.4396 | 0.2 | 0.3 | 41537.2458 |  |  |  |  | 0 | 9781.6961 | 9781.6961 | 9781.6961 | 9781.6961 | 9781.6961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2515 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16833.0397 | 0.2 | 0.3 | 26259.542 |  |  |  |  | 0 | 9784.7603 | 9784.7603 | 9784.7603 | 9784.7603 | 9784.7603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2516 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 21181.9965 | 0.2 | 0.3 | 33043.9145 |  |  |  |  | 0 | 9789.9892 | 9789.9892 | 9789.9892 | 9789.9892 | 9789.9892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2517 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 28369.7885 | 0.2 | 0.3 | 44256.87 |  |  |  |  | 0 | 7560.5412 | 7560.5412 | 7560.5412 | 7560.5412 | 7560.5412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2518 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 27440.1626 | 0.2 | 0.3 | 42806.6537 |  |  |  |  | 0 | 7179.787 | 7179.787 | 7179.787 | 7179.787 | 7179.787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2519 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16689.0389 | 0.2 | 0.3 | 26034.9007 |  |  |  |  | 0 | 5205.5336 | 5205.5336 | 5205.5336 | 5205.5336 | 5205.5336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2520 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16850.1794 | 0.2 | 0.3 | 26286.2799 |  |  |  |  | 0 | 9787.2164 | 9787.2164 | 9787.2164 | 9787.2164 | 9787.2164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2521 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 14533.7685 | 0.2 | 0.3 | 22672.6789 |  |  |  |  | 0 | 5204.7194 | 5204.7194 | 5204.7194 | 5204.7194 | 5204.7194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2522 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 13310.9691 | 0.2 | 0.3 | 20765.1118 |  |  |  |  | 0 | 9272.2199 | 9272.2199 | 9272.2199 | 9272.2199 | 9272.2199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2523 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 18145.9795 | 0.2 | 0.3 | 28307.728 |  |  |  |  | 0 | 5205.217 | 5205.217 | 5205.217 | 5205.217 | 5205.217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2524 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 28901.2835 | 0.2 | 0.3 | 45086.0023 |  |  |  |  | 0 | 5205.1763 | 5205.1763 | 5205.1763 | 5205.1763 | 5205.1763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2525 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 17136.647 | 0.2 | 0.3 | 26733.1693 |  |  |  |  | 0 | 5205.7988 | 5205.7988 | 5205.7988 | 5205.7988 | 5205.7988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2526 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 25116.2669 | 0.2 | 0.3 | 39181.3763 |  |  |  |  | 0 | 6993.7131 | 6993.7131 | 6993.7131 | 6993.7131 | 6993.7131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2527 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 7719.303 | 0.2 | 0.3 | 12042.1127 |  |  |  |  | 0 | 7436.0063 | 7436.0063 | 7436.0063 | 7436.0063 | 7436.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2528 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 26981.5579 | 0.2 | 0.3 | 42091.2304 |  |  |  |  | 0 | 13043.3548 | 13043.3548 | 13043.3548 | 13043.3548 | 13043.3548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2529 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 31611.2908 | 0.2 | 0.3 | 49313.6136 |  |  |  |  | 0 | 10487.4885 | 10487.4885 | 10487.4885 | 10487.4885 | 10487.4885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2530 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 31573.2829 | 0.2 | 0.3 | 49254.3213 |  |  |  |  | 0 | 14122.3275 | 14122.3275 | 14122.3275 | 14122.3275 | 14122.3275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2531 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 15072.8711 | 0.2 | 0.3 | 23513.679 |  |  |  |  | 0 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2532 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 28456.1972 | 0.2 | 0.3 | 44391.6676 |  |  |  |  | 0 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2533 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 12482.1114 | 0.2 | 0.3 | 19472.0938 |  |  |  |  | 0 | 5205.6944 | 5205.6944 | 5205.6944 | 5205.6944 | 5205.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2534 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 35711.0521 | 0.2 | 0.3 | 55709.2413 |  |  |  |  | 0 | 10369.3396 | 10369.3396 | 10369.3396 | 10369.3396 | 10369.3396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2535 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 25241.4861 | 0.2 | 0.3 | 39376.7184 |  |  |  |  | 0 | 10901.5317 | 10901.5317 | 10901.5317 | 10901.5317 | 10901.5317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2536 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 283.697 | 0.2 | 0.3 | 442.5673 |  |  |  |  | 0 | 5205.3855 | 5205.3855 | 5205.3855 | 5205.3855 | 5205.3855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2537 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 16249.2305 | 0.2 | 0.3 | 25348.7996 |  |  |  |  | 0 | 10336.2658 | 10336.2658 | 10336.2658 | 10336.2658 | 10336.2658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2538 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 16682.3425 | 0.2 | 0.3 | 26024.4544 |  |  |  |  | 0 | 3337.4666 | 3337.4666 | 3337.4666 | 3337.4666 | 3337.4666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2539 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 18306.2225 | 0.2 | 0.3 | 28557.707 |  |  |  |  | 0 | 11451.2127 | 11451.2127 | 11451.2127 | 11451.2127 | 11451.2127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2540 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 13541.9117 | 0.2 | 0.3 | 21125.3822 |  |  |  |  | 0 | 8378.7777 | 8378.7777 | 8378.7777 | 8378.7777 | 8378.7777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2541 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 22185.3499 | 0.2 | 0.3 | 34609.1459 |  |  |  |  | 0 | 8379.9934 | 8379.9934 | 8379.9934 | 8379.9934 | 8379.9934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2542 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 32646.4173 | 0.2 | 0.3 | 50928.411 |  |  |  |  | 0 | 10184.0849 | 10184.0849 | 10184.0849 | 10184.0849 | 10184.0849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2543 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 25714.4926 | 0.2 | 0.3 | 40114.6085 |  |  |  |  | 0 | 8990.1862 | 8990.1862 | 8990.1862 | 8990.1862 | 8990.1862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2544 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16669.6501 | 0.2 | 0.3 | 26004.6542 |  |  |  |  | 0 | 11389.0004 | 11389.0004 | 11389.0004 | 11389.0004 | 11389.0004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2545 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 17366.1712 | 0.2 | 0.3 | 27091.2271 |  |  |  |  | 0 | 3745.297 | 3745.297 | 3745.297 | 3745.297 | 3745.297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2546 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 17544.3503 | 0.2 | 0.3 | 27369.1864 |  |  |  |  | 0 | 9051.2265 | 9051.2265 | 9051.2265 | 9051.2265 | 9051.2265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2547 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 26720.969 | 0.2 | 0.3 | 41684.7116 |  |  |  |  | 0 | 5205.7537 | 5205.7537 | 5205.7537 | 5205.7537 | 5205.7537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2548 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16676.9893 | 0.2 | 0.3 | 26016.1033 |  |  |  |  | 0 | 8935.6905 | 8935.6905 | 8935.6905 | 8935.6905 | 8935.6905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2549 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 18612.2095 | 0.2 | 0.3 | 29035.0469 |  |  |  |  | 0 | 6961.1936 | 6961.1936 | 6961.1936 | 6961.1936 | 6961.1936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2550 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 19456.153 | 0.2 | 0.3 | 30351.5987 |  |  |  |  | 0 | 6188.6292 | 6188.6292 | 6188.6292 | 6188.6292 | 6188.6292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2551 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16680.558 | 0.2 | 0.3 | 26021.6705 |  |  |  |  | 0 | 4083.5517 | 4083.5517 | 4083.5517 | 4083.5517 | 4083.5517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2552 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 24124.2201 | 0.2 | 0.3 | 37633.7833 |  |  |  |  | 0 | 10411.5594 | 10411.5594 | 10411.5594 | 10411.5594 | 10411.5594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2553 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 177.9172 | 0.2 | 0.3 | 277.5508 |  |  |  |  | 0 | 5205.7797 | 5205.7797 | 5205.7797 | 5205.7797 | 5205.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2554 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 20567.6418 | 0.2 | 0.3 | 32085.5212 |  |  |  |  | 0 | 8867.4532 | 8867.4532 | 8867.4532 | 8867.4532 | 8867.4532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2555 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16690.6631 | 0.2 | 0.3 | 26037.4345 |  |  |  |  | 0 | 6549.8059 | 6549.8059 | 6549.8059 | 6549.8059 | 6549.8059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2556 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 19911.7229 | 0.2 | 0.3 | 31062.2877 |  |  |  |  | 0 | 8362.9063 | 8362.9063 | 8362.9063 | 8362.9063 | 8362.9063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2557 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 28534.5828 | 0.2 | 0.3 | 44513.9492 |  |  |  |  | 0 | 13945.6726 | 13945.6726 | 13945.6726 | 13945.6726 | 13945.6726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2558 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 31358.3515 | 0.2 | 0.3 | 48919.0283 |  |  |  |  | 0 | 8720.3092 | 8720.3092 | 8720.3092 | 8720.3092 | 8720.3092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2559 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 29974.7987 | 0.2 | 0.3 | 46760.6859 |  |  |  |  | 0 | 10201.6522 | 10201.6522 | 10201.6522 | 10201.6522 | 10201.6522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2560 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 17390.9933 | 0.2 | 0.3 | 27129.9495 |  |  |  |  | 0 | 10412.1855 | 10412.1855 | 10412.1855 | 10412.1855 | 10412.1855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2561 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 27982.5861 | 0.2 | 0.3 | 43652.8344 |  |  |  |  | 0 | 14364.0815 | 14364.0815 | 14364.0815 | 14364.0815 | 14364.0815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2562 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 21409.6251 | 0.2 | 0.3 | 33399.0152 |  |  |  |  | 0 | 9064.9564 | 9064.9564 | 9064.9564 | 9064.9564 | 9064.9564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2563 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 132.9189 | 0.2 | 0.3 | 207.3534 |  |  |  |  | 0 | 7119.6601 | 7119.6601 | 7119.6601 | 7119.6601 | 7119.6601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2564 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16687.4927 | 0.2 | 0.3 | 26032.4887 |  |  |  |  | 0 | 4877.5835 | 4877.5835 | 4877.5835 | 4877.5835 | 4877.5835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2565 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 24458.5071 | 0.2 | 0.3 | 38155.271 |  |  |  |  | 0 | 9285.0401 | 9285.0401 | 9285.0401 | 9285.0401 | 9285.0401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2566 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16670.9434 | 0.2 | 0.3 | 26006.6717 |  |  |  |  | 0 | 5415.2697 | 5415.2697 | 5415.2697 | 5415.2697 | 5415.2697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2567 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16706.7797 | 0.2 | 0.3 | 26062.5764 |  |  |  |  | 0 | 5202.5809 | 5202.5809 | 5202.5809 | 5202.5809 | 5202.5809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2568 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 19682.5986 | 0.2 | 0.3 | 30704.8538 |  |  |  |  | 0 | 9786.044 | 9786.044 | 9786.044 | 9786.044 | 9786.044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2569 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16766.3227 | 0.2 | 0.3 | 26155.4635 |  |  |  |  | 0 | 5206.5149 | 5206.5149 | 5206.5149 | 5206.5149 | 5206.5149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2570 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 26893.0304 | 0.2 | 0.3 | 41953.1274 |  |  |  |  | 0 | 5772.7273 | 5772.7273 | 5772.7273 | 5772.7273 | 5772.7273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2571 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 12035.1601 | 0.2 | 0.3 | 18774.8497 |  |  |  |  | 0 | 6036.0675 | 6036.0675 | 6036.0675 | 6036.0675 | 6036.0675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2572 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 23764.0647 | 0.2 | 0.3 | 37071.941 |  |  |  |  | 0 | 9612.8656 | 9612.8656 | 9612.8656 | 9612.8656 | 9612.8656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2573 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 24423.182 | 0.2 | 0.3 | 38100.1639 |  |  |  |  | 0 | 7752.3442 | 7752.3442 | 7752.3442 | 7752.3442 | 7752.3442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2574 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 23986.678 | 0.2 | 0.3 | 37419.2177 |  |  |  |  | 0 | 7917.2922 | 7917.2922 | 7917.2922 | 7917.2922 | 7917.2922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2575 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 7235.7209 | 0.2 | 0.3 | 11287.7246 |  |  |  |  | 0 | 12828.6468 | 12828.6468 | 12828.6468 | 12828.6468 | 12828.6468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2576 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 21944.0924 | 0.2 | 0.3 | 34232.7841 |  |  |  |  | 0 | 8455.1423 | 8455.1423 | 8455.1423 | 8455.1423 | 8455.1423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2577 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 10488.113 | 0.2 | 0.3 | 16361.4563 |  |  |  |  | 0 | 5952.377 | 5952.377 | 5952.377 | 5952.377 | 5952.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2578 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 12381.4268 | 0.2 | 0.3 | 19315.0258 |  |  |  |  | 0 | 5207.0592 | 5207.0592 | 5207.0592 | 5207.0592 | 5207.0592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2579 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 6703.8359 | 0.2 | 0.3 | 10457.984 |  |  |  |  | 0 | 10401.7643 | 10401.7643 | 10401.7643 | 10401.7643 | 10401.7643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2580 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 19551.8493 | 0.2 | 0.3 | 30500.8849 |  |  |  |  | 0 | 11.0837 | 11.0837 | 11.0837 | 11.0837 | 11.0837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2581 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 17466.5005 | 0.2 | 0.3 | 27247.7408 |  |  |  |  | 0 | 8490.3537 | 8490.3537 | 8490.3537 | 8490.3537 | 8490.3537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2582 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 4833.7717 | 0.2 | 0.3 | 7540.6838 |  |  |  |  | 0 | 8912.6486 | 8912.6486 | 8912.6486 | 8912.6486 | 8912.6486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2583 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 10578.7137 | 0.2 | 0.3 | 16502.7934 |  |  |  |  | 0 | 14329.6487 | 14329.6487 | 14329.6487 | 14329.6487 | 14329.6487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2584 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.9729 | 0.2 | 0.3 | 26011.3978 |  |  |  |  | 0 | 9591.5892 | 9591.5892 | 9591.5892 | 9591.5892 | 9591.5892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2585 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 31348.6077 | 0.2 | 0.3 | 48903.8281 |  |  |  |  | 0 | 5537.4148 | 5537.4148 | 5537.4148 | 5537.4148 | 5537.4148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2586 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.644 | 0.2 | 0.3 | 26010.8846 |  |  |  |  | 0 | 5206.9739 | 5206.9739 | 5206.9739 | 5206.9739 | 5206.9739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2587 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 11427.8771 | 11427.8771 | 11427.8771 | 11427.8771 | 11427.8771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2588 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16674.5641 | 0.2 | 0.3 | 26012.3199 |  |  |  |  | 0 | 1184.1085 | 1184.1085 | 1184.1085 | 1184.1085 | 1184.1085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2589 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 21528.8483 | 0.2 | 0.3 | 33585.0034 |  |  |  |  | 0 | 5565.1784 | 5565.1784 | 5565.1784 | 5565.1784 | 5565.1784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2590 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 9695.4257 | 0.2 | 0.3 | 15124.8641 |  |  |  |  | 0 | 6247.4663 | 6247.4663 | 6247.4663 | 6247.4663 | 6247.4663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2591 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 16764.6995 | 0.2 | 0.3 | 26152.9312 |  |  |  |  | 0 | 6706.6426 | 6706.6426 | 6706.6426 | 6706.6426 | 6706.6426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2592 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 19499.0769 | 0.2 | 0.3 | 30418.56 |  |  |  |  | 0 | 5236.0744 | 5236.0744 | 5236.0744 | 5236.0744 | 5236.0744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2593 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 9409.139 | 0.2 | 0.3 | 14678.2568 |  |  |  |  | 0 | 9812.5186 | 9812.5186 | 9812.5186 | 9812.5186 | 9812.5186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2594 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 21777.0669 | 0.2 | 0.3 | 33972.2244 |  |  |  |  | 0 | 7651.3063 | 7651.3063 | 7651.3063 | 7651.3063 | 7651.3063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2595 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17019.3604 | 0.2 | 0.3 | 26550.2022 |  |  |  |  | 0 | 6834.5334 | 6834.5334 | 6834.5334 | 6834.5334 | 6834.5334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2596 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17615.5337 | 0.2 | 0.3 | 27480.2326 |  |  |  |  | 0 | 5997.1914 | 5997.1914 | 5997.1914 | 5997.1914 | 5997.1914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2597 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 10920.9466 | 0.2 | 0.3 | 17036.6767 |  |  |  |  | 0 | 3026.6355 | 3026.6355 | 3026.6355 | 3026.6355 | 3026.6355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2598 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 15450.9562 | 0.2 | 0.3 | 24103.4917 |  |  |  |  | 0 | 7859.7895 | 7859.7895 | 7859.7895 | 7859.7895 | 7859.7895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2599 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 3367.1249 | 0.2 | 0.3 | 5252.7148 |  |  |  |  | 0 | 6079.4502 | 6079.4502 | 6079.4502 | 6079.4502 | 6079.4502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2600 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 15673.3063 | 0.2 | 0.3 | 24450.3579 |  |  |  |  | 0 | 5385.51 | 5385.51 | 5385.51 | 5385.51 | 5385.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2601 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 8541.9363 | 0.2 | 0.3 | 13325.4206 |  |  |  |  | 0 | 2062.2784 | 2062.2784 | 2062.2784 | 2062.2784 | 2062.2784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2602 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 21353.5727 | 0.2 | 0.3 | 33311.5735 |  |  |  |  | 0 | 8885.4712 | 8885.4712 | 8885.4712 | 8885.4712 | 8885.4712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2603 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 19448.8979 | 0.2 | 0.3 | 30340.2808 |  |  |  |  | 0 | 8659.5379 | 8659.5379 | 8659.5379 | 8659.5379 | 8659.5379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2604 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 384.1291 | 0.2 | 0.3 | 599.2413 |  |  |  |  | 0 | 12180.9002 | 12180.9002 | 12180.9002 | 12180.9002 | 12180.9002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2605 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16100.1245 | 0.2 | 0.3 | 25116.1942 |  |  |  |  | 0 | 11934.7058 | 11934.7058 | 11934.7058 | 11934.7058 | 11934.7058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2606 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 8715.9467 | 0.2 | 0.3 | 13596.8768 |  |  |  |  | 0 | 5378.2441 | 5378.2441 | 5378.2441 | 5378.2441 | 5378.2441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2607 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 32365.3137 | 0.2 | 0.3 | 50489.8893 |  |  |  |  | 0 | 5494.8735 | 5494.8735 | 5494.8735 | 5494.8735 | 5494.8735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2608 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 31430.0407 | 0.2 | 0.3 | 49030.8634 |  |  |  |  | 0 | 11290.2476 | 11290.2476 | 11290.2476 | 11290.2476 | 11290.2476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2609 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 25518.5993 | 0.2 | 0.3 | 39809.0149 |  |  |  |  | 0 | 6908.4993 | 6908.4993 | 6908.4993 | 6908.4993 | 6908.4993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2610 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17313.9935 | 0.2 | 0.3 | 27009.8299 |  |  |  |  | 0 | 3405.0351 | 3405.0351 | 3405.0351 | 3405.0351 | 3405.0351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2611 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 14010.3375 | 0.2 | 0.3 | 21856.1264 |  |  |  |  | 0 | 1955.1062 | 1955.1062 | 1955.1062 | 1955.1062 | 1955.1062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2612 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 14288.5359 | 0.2 | 0.3 | 22290.116 |  |  |  |  | 0 | 6799.0676 | 6799.0676 | 6799.0676 | 6799.0676 | 6799.0676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2613 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 22626.6511 | 0.2 | 0.3 | 35297.5757 |  |  |  |  | 0 | 8470.0205 | 8470.0205 | 8470.0205 | 8470.0205 | 8470.0205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2614 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 20293.5867 | 0.2 | 0.3 | 31657.9953 |  |  |  |  | 0 | 6478.602 | 6478.602 | 6478.602 | 6478.602 | 6478.602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2615 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 15346.688 | 0.2 | 0.3 | 23940.8333 |  |  |  |  | 0 | 4737.8473 | 4737.8473 | 4737.8473 | 4737.8473 | 4737.8473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2616 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 30715.2795 | 0.2 | 0.3 | 47915.8361 |  |  |  |  | 0 | 1776.7468 | 1776.7468 | 1776.7468 | 1776.7468 | 1776.7468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2617 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 20512.0205 | 0.2 | 0.3 | 31998.752 |  |  |  |  | 0 | 6588.7377 | 6588.7377 | 6588.7377 | 6588.7377 | 6588.7377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2618 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 16683.7464 | 0.2 | 0.3 | 26026.6444 |  |  |  |  | 0 | 5384.9982 | 5384.9982 | 5384.9982 | 5384.9982 | 5384.9982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2619 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 21575.3642 | 0.2 | 0.3 | 33657.5682 |  |  |  |  | 0 | 5524.4331 | 5524.4331 | 5524.4331 | 5524.4331 | 5524.4331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2620 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 10172.1888 | 0.2 | 0.3 | 15868.6145 |  |  |  |  | 0 | 8626.3139 | 8626.3139 | 8626.3139 | 8626.3139 | 8626.3139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2621 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 7973.6107 | 0.2 | 0.3 | 12438.8327 |  |  |  |  | 0 | 10359.0725 | 10359.0725 | 10359.0725 | 10359.0725 | 10359.0725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2622 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 21642.8801 | 0.2 | 0.3 | 33762.8929 |  |  |  |  | 0 | 6049.308 | 6049.308 | 6049.308 | 6049.308 | 6049.308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2623 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 17840.4708 | 0.2 | 0.3 | 27831.1344 |  |  |  |  | 0 | 5380.5625 | 5380.5625 | 5380.5625 | 5380.5625 | 5380.5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2624 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 23166.6853 | 0.2 | 0.3 | 36140.029 |  |  |  |  | 0 | 1954.7748 | 1954.7748 | 1954.7748 | 1954.7748 | 1954.7748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2625 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 16760.0399 | 0.2 | 0.3 | 26145.6623 |  |  |  |  | 0 | 978.4378 | 978.4378 | 978.4378 | 978.4378 | 978.4378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2626 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 14757.6115 | 0.2 | 0.3 | 23021.8739 |  |  |  |  | 0 | 7814.5928 | 7814.5928 | 7814.5928 | 7814.5928 | 7814.5928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2627 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 16792.6384 | 0.2 | 0.3 | 26196.5159 |  |  |  |  | 0 | 7026.0247 | 7026.0247 | 7026.0247 | 7026.0247 | 7026.0247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2628 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 24309.4029 | 0.2 | 0.3 | 37922.6686 |  |  |  |  | 0 | 561.0657 | 561.0657 | 561.0657 | 561.0657 | 561.0657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2629 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 11654.2714 | 0.2 | 0.3 | 18180.6634 |  |  |  |  | 0 | 5520.5843 | 5520.5843 | 5520.5843 | 5520.5843 | 5520.5843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2630 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 8169.905 | 0.2 | 0.3 | 12745.0518 |  |  |  |  | 0 | 3250.0214 | 3250.0214 | 3250.0214 | 3250.0214 | 3250.0214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2631 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 10922.0345 | 0.2 | 0.3 | 17038.3739 |  |  |  |  | 0 | 2203.9797 | 2203.9797 | 2203.9797 | 2203.9797 | 2203.9797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2632 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 15854.6225 | 0.2 | 0.3 | 24733.2112 |  |  |  |  | 0 | 774.983 | 774.983 | 774.983 | 774.983 | 774.983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2633 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 32915.8121 | 0.2 | 0.3 | 51348.6669 |  |  |  |  | 0 | 7818.9214 | 7818.9214 | 7818.9214 | 7818.9214 | 7818.9214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2634 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 30778.5798 | 0.2 | 0.3 | 48014.5845 |  |  |  |  | 0 | 8418.7311 | 8418.7311 | 8418.7311 | 8418.7311 | 8418.7311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2635 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 19380.2394 | 0.2 | 0.3 | 30233.1735 |  |  |  |  | 0 | 11192.0117 | 11192.0117 | 11192.0117 | 11192.0117 | 11192.0117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2636 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 16688.4979 | 0.2 | 0.3 | 26034.0568 |  |  |  |  | 0 | 681.4326 | 681.4326 | 681.4326 | 681.4326 | 681.4326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2637 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 16692.4756 | 0.2 | 0.3 | 26040.2619 |  |  |  |  | 0 | 6521.6863 | 6521.6863 | 6521.6863 | 6521.6863 | 6521.6863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2638 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 1597.7903 | 0.2 | 0.3 | 2492.5529 |  |  |  |  | 0 | 6766.1791 | 6766.1791 | 6766.1791 | 6766.1791 | 6766.1791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2639 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 20191.8039 | 0.2 | 0.3 | 31499.214 |  |  |  |  | 0 | 514.0467 | 514.0467 | 514.0467 | 514.0467 | 514.0467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2640 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 24141.8737 | 0.2 | 0.3 | 37661.3229 |  |  |  |  | 0 | 4843.8544 | 4843.8544 | 4843.8544 | 4843.8544 | 4843.8544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2641 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 10977.1955 | 0.2 | 0.3 | 17124.425 |  |  |  |  | 0 | 4622.4658 | 4622.4658 | 4622.4658 | 4622.4658 | 4622.4658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2642 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 24014.7919 | 0.2 | 0.3 | 37463.0754 |  |  |  |  | 0 | 2597.1173 | 2597.1173 | 2597.1173 | 2597.1173 | 2597.1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2643 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 19401.9437 | 0.2 | 0.3 | 30267.0322 |  |  |  |  | 0 | 6404.6258 | 6404.6258 | 6404.6258 | 6404.6258 | 6404.6258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2644 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 22406.033 | 0.2 | 0.3 | 34953.4115 |  |  |  |  | 0 | 5888.4835 | 5888.4835 | 5888.4835 | 5888.4835 | 5888.4835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2645 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 28931.055 | 0.2 | 0.3 | 45132.4458 |  |  |  |  | 0 | 325.6959 | 325.6959 | 325.6959 | 325.6959 | 325.6959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2646 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 10319.643 | 0.2 | 0.3 | 16098.6431 |  |  |  |  | 0 | 5431.4482 | 5431.4482 | 5431.4482 | 5431.4482 | 5431.4482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2647 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 6357.2779 | 0.2 | 0.3 | 9917.3535 |  |  |  |  | 0 | 5259.2619 | 5259.2619 | 5259.2619 | 5259.2619 | 5259.2619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2648 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16691.3026 | 0.2 | 0.3 | 26038.4321 |  |  |  |  | 0 | 3707.3425 | 3707.3425 | 3707.3425 | 3707.3425 | 3707.3425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2649 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16680.6616 | 0.2 | 0.3 | 26021.8321 |  |  |  |  | 0 | 9111.5857 | 9111.5857 | 9111.5857 | 9111.5857 | 9111.5857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2650 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16672.3394 | 0.2 | 0.3 | 26008.8495 |  |  |  |  | 0 | 7716.3858 | 7716.3858 | 7716.3858 | 7716.3858 | 7716.3858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2651 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16695.4877 | 0.2 | 0.3 | 26044.9609 |  |  |  |  | 0 | 5241.7411 | 5241.7411 | 5241.7411 | 5241.7411 | 5241.7411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2652 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16982.9321 | 0.2 | 0.3 | 26493.374 |  |  |  |  | 0 | 2625.9941 | 2625.9941 | 2625.9941 | 2625.9941 | 2625.9941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2653 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 1145.4307 | 0.2 | 0.3 | 1786.8719 |  |  |  |  | 0 | 2683.819 | 2683.819 | 2683.819 | 2683.819 | 2683.819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2654 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 24120.3205 | 0.2 | 0.3 | 37627.6999 |  |  |  |  | 0 | 341.2037 | 341.2037 | 341.2037 | 341.2037 | 341.2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2655 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 7311.0212 | 0.2 | 0.3 | 11405.1931 |  |  |  |  | 0 | 995.4157 | 995.4157 | 995.4157 | 995.4157 | 995.4157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2656 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 23774.1565 | 0.2 | 0.3 | 37087.6841 |  |  |  |  | 0 | 10591.7843 | 10591.7843 | 10591.7843 | 10591.7843 | 10591.7843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2657 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16671.2739 | 0.2 | 0.3 | 26007.1872 |  |  |  |  | 0 | 12284.4128 | 12284.4128 | 12284.4128 | 12284.4128 | 12284.4128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2658 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 2516.4905 | 0.2 | 0.3 | 3925.7252 |  |  |  |  | 0 | 2259.9087 | 2259.9087 | 2259.9087 | 2259.9087 | 2259.9087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2659 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 26492.9057 | 0.2 | 0.3 | 41328.9329 |  |  |  |  | 0 | 9738.3308 | 9738.3308 | 9738.3308 | 9738.3308 | 9738.3308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2660 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 17124.2343 | 0.2 | 0.3 | 26713.8055 |  |  |  |  | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2661 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 17594.5777 | 0.2 | 0.3 | 27447.5412 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2662 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 17412.2563 | 0.2 | 0.3 | 27163.1199 |  |  |  |  | 0 | 462.8402 | 462.8402 | 462.8402 | 462.8402 | 462.8402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2663 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 19954.6244 | 0.2 | 0.3 | 31129.2141 |  |  |  |  | 0 | 10107.2679 | 10107.2679 | 10107.2679 | 10107.2679 | 10107.2679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2664 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 8395.3925 | 0.2 | 0.3 | 13096.8122 |  |  |  |  | 0 | 8254.3105 | 8254.3105 | 8254.3105 | 8254.3105 | 8254.3105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2665 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 25802.1991 | 0.2 | 0.3 | 40251.4306 |  |  |  |  | 0 | 5200.5886 | 5200.5886 | 5200.5886 | 5200.5886 | 5200.5886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2666 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 29187.269 | 0.2 | 0.3 | 45532.1396 |  |  |  |  | 0 | 6376.1133 | 6376.1133 | 6376.1133 | 6376.1133 | 6376.1133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2667 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 14254.5993 | 0.2 | 0.3 | 22237.175 |  |  |  |  | 0 | 3909.2485 | 3909.2485 | 3909.2485 | 3909.2485 | 3909.2485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2668 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 17822.0029 | 0.2 | 0.3 | 27802.3245 |  |  |  |  | 0 | 13285.4952 | 13285.4952 | 13285.4952 | 13285.4952 | 13285.4952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2669 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 30624.8401 | 0.2 | 0.3 | 47774.7505 |  |  |  |  | 0 | 9304.6257 | 9304.6257 | 9304.6257 | 9304.6257 | 9304.6257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2670 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 7273.9071 | 0.2 | 0.3 | 11347.2951 |  |  |  |  | 0 | 5672.9833 | 5672.9833 | 5672.9833 | 5672.9833 | 5672.9833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2671 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16990.6166 | 0.2 | 0.3 | 26505.3619 |  |  |  |  | 0 | 5202.5105 | 5202.5105 | 5202.5105 | 5202.5105 | 5202.5105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2672 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 21970.4413 | 0.2 | 0.3 | 34273.8884 |  |  |  |  | 0 | 11003.397 | 11003.397 | 11003.397 | 11003.397 | 11003.397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2673 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 22701.9615 | 0.2 | 0.3 | 35415.0599 |  |  |  |  | 0 | 5200.0769 | 5200.0769 | 5200.0769 | 5200.0769 | 5200.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2674 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 24471.4063 | 0.2 | 0.3 | 38175.3938 |  |  |  |  | 0 | 5641.0449 | 5641.0449 | 5641.0449 | 5641.0449 | 5641.0449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2675 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16669.7669 | 0.2 | 0.3 | 26004.8363 |  |  |  |  | 0 | 80.829 | 80.829 | 80.829 | 80.829 | 80.829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2676 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.4351 | 0.2 | 0.3 | 26010.5587 |  |  |  |  | 0 | 2525.0692 | 2525.0692 | 2525.0692 | 2525.0692 | 2525.0692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2677 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.6465 | 0.2 | 0.3 | 26010.8885 |  |  |  |  | 0 | 2600.3431 | 2600.3431 | 2600.3431 | 2600.3431 | 2600.3431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2678 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 21908.1854 | 0.2 | 0.3 | 34176.7692 |  |  |  |  | 0 | 1010.1078 | 1010.1078 | 1010.1078 | 1010.1078 | 1010.1078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2679 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 10648.1599 | 0.2 | 0.3 | 16611.1294 |  |  |  |  | 0 | 2418.7196 | 2418.7196 | 2418.7196 | 2418.7196 | 2418.7196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2680 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 25041.5374 | 0.2 | 0.3 | 39064.7983 |  |  |  |  | 0 | 5201.005 | 5201.005 | 5201.005 | 5201.005 | 5201.005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2681 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 13621.9378 | 0.2 | 0.3 | 21250.223 |  |  |  |  | 0 | 5202.4307 | 5202.4307 | 5202.4307 | 5202.4307 | 5202.4307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2682 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 12854.9031 | 0.2 | 0.3 | 20053.6488 |  |  |  |  | 0 | 1090.9251 | 1090.9251 | 1090.9251 | 1090.9251 | 1090.9251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2683 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 29398.9393 | 0.2 | 0.3 | 45862.3453 |  |  |  |  | 0 | 5200.0406 | 5200.0406 | 5200.0406 | 5200.0406 | 5200.0406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2684 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17203.4208 | 0.2 | 0.3 | 26837.3364 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2685 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 15909.9826 | 0.2 | 0.3 | 24819.5729 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2686 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17006.1724 | 0.2 | 0.3 | 26529.6289 |  |  |  |  | 0 | 5199.978 | 5199.978 | 5199.978 | 5199.978 | 5199.978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2687 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 23355.2499 | 0.2 | 0.3 | 36434.1898 |  |  |  |  | 0 | 1767.3937 | 1767.3937 | 1767.3937 | 1767.3937 | 1767.3937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2688 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 10554.44 | 0.2 | 0.3 | 16464.9264 |  |  |  |  | 0 | 10085.8822 | 10085.8822 | 10085.8822 | 10085.8822 | 10085.8822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2689 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16898.3824 | 0.2 | 0.3 | 26361.4765 |  |  |  |  | 0 | 7876.469 | 7876.469 | 7876.469 | 7876.469 | 7876.469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2690 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16682.2163 | 0.2 | 0.3 | 26024.2575 |  |  |  |  | 0 | 7800.2377 | 7800.2377 | 7800.2377 | 7800.2377 | 7800.2377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2691 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16676.9311 | 0.2 | 0.3 | 26016.0126 |  |  |  |  | 0 | 8386.4974 | 8386.4974 | 8386.4974 | 8386.4974 | 8386.4974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2692 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16676.3261 | 0.2 | 0.3 | 26015.0687 |  |  |  |  | 0 | 3307.6372 | 3307.6372 | 3307.6372 | 3307.6372 | 3307.6372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2693 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 10387.5629 | 0.2 | 0.3 | 16204.5982 |  |  |  |  | 0 | 5235.3759 | 5235.3759 | 5235.3759 | 5235.3759 | 5235.3759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2694 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16757.2009 | 0.2 | 0.3 | 26141.2334 |  |  |  |  | 0 | 5200.0048 | 5200.0048 | 5200.0048 | 5200.0048 | 5200.0048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2695 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16899.3598 | 0.2 | 0.3 | 26363.0013 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2696 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16761.8725 | 0.2 | 0.3 | 26148.521 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2697 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 3485.8522 | 0.2 | 0.3 | 5437.9294 |  |  |  |  | 0 | 5200.0049 | 5200.0049 | 5200.0049 | 5200.0049 | 5200.0049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2698 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 27746.9635 | 0.2 | 0.3 | 43285.2631 |  |  |  |  | 0 | 7040.0148 | 7040.0148 | 7040.0148 | 7040.0148 | 7040.0148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2699 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 6099.4827 | 0.2 | 0.3 | 9515.193 |  |  |  |  | 0 | 5203.2917 | 5203.2917 | 5203.2917 | 5203.2917 | 5203.2917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2700 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 18708.0531 | 0.2 | 0.3 | 29184.5629 |  |  |  |  | 0 | 2124.6712 | 2124.6712 | 2124.6712 | 2124.6712 | 2124.6712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2701 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 25379.5647 | 0.2 | 0.3 | 39592.121 |  |  |  |  | 0 | 7734.041 | 7734.041 | 7734.041 | 7734.041 | 7734.041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2702 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 46.2869 | 0.2 | 0.3 | 72.2075 |  |  |  |  | 0 | 6760.4103 | 6760.4103 | 6760.4103 | 6760.4103 | 6760.4103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2703 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 741.1731 | 0.2 | 0.3 | 1156.23 |  |  |  |  | 0 | 6056.1903 | 6056.1903 | 6056.1903 | 6056.1903 | 6056.1903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2704 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16420.1149 | 0.2 | 0.3 | 25615.3793 |  |  |  |  | 0 | 9778.242 | 9778.242 | 9778.242 | 9778.242 | 9778.242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2705 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16798.9645 | 0.2 | 0.3 | 26206.3847 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2706 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 18967.6431 | 0.2 | 0.3 | 29589.5233 |  |  |  |  | 0 | 7900.206 | 7900.206 | 7900.206 | 7900.206 | 7900.206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2707 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17094.9481 | 0.2 | 0.3 | 26668.119 |  |  |  |  | 0 | 6834.8044 | 6834.8044 | 6834.8044 | 6834.8044 | 6834.8044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2708 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 22900.3269 | 0.2 | 0.3 | 35724.5099 |  |  |  |  | 0 | 3917.8497 | 3917.8497 | 3917.8497 | 3917.8497 | 3917.8497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2709 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16666.9403 | 0.2 | 0.3 | 26000.4268 |  |  |  |  | 0 | 9822.8827 | 9822.8827 | 9822.8827 | 9822.8827 | 9822.8827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2710 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 15108.01 | 0.2 | 0.3 | 23568.4956 |  |  |  |  | 0 | 9714.7841 | 9714.7841 | 9714.7841 | 9714.7841 | 9714.7841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2711 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 19878.1435 | 0.2 | 0.3 | 31009.9039 |  |  |  |  | 0 | 487.2935 | 487.2935 | 487.2935 | 487.2935 | 487.2935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2712 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 18144.4755 | 0.2 | 0.3 | 28305.3818 |  |  |  |  | 0 | 5201.7875 | 5201.7875 | 5201.7875 | 5201.7875 | 5201.7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2713 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 25542.5658 | 0.2 | 0.3 | 39846.4026 |  |  |  |  | 0 | 8467.8805 | 8467.8805 | 8467.8805 | 8467.8805 | 8467.8805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2714 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 15180.1025 | 0.2 | 0.3 | 23680.9598 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2715 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 10247.857 | 0.2 | 0.3 | 15986.6569 |  |  |  |  | 0 | 8106.4598 | 8106.4598 | 8106.4598 | 8106.4598 | 8106.4598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2716 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 25129.9444 | 0.2 | 0.3 | 39202.7133 |  |  |  |  | 0 | 2700.2667 | 2700.2667 | 2700.2667 | 2700.2667 | 2700.2667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2717 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 15564.4352 | 0.2 | 0.3 | 24280.5189 |  |  |  |  | 0 | 5106.2927 | 5106.2927 | 5106.2927 | 5106.2927 | 5106.2927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2718 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 18183.1949 | 0.2 | 0.3 | 28365.784 |  |  |  |  | 0 | 5246.4077 | 5246.4077 | 5246.4077 | 5246.4077 | 5246.4077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2719 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 14396.6473 | 0.2 | 0.3 | 22458.7698 |  |  |  |  | 0 | 2552.3629 | 2552.3629 | 2552.3629 | 2552.3629 | 2552.3629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2720 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 16791.6971 | 0.2 | 0.3 | 26195.0474 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2721 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 16785.2429 | 0.2 | 0.3 | 26184.9789 |  |  |  |  | 0 | 8319.2228 | 8319.2228 | 8319.2228 | 8319.2228 | 8319.2228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2722 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 12707.1831 | 0.2 | 0.3 | 19823.2057 |  |  |  |  | 0 | 7079.5795 | 7079.5795 | 7079.5795 | 7079.5795 | 7079.5795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2723 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 16407.9087 | 0.2 | 0.3 | 25596.3376 |  |  |  |  | 0 | 9778.3342 | 9778.3342 | 9778.3342 | 9778.3342 | 9778.3342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2724 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 8644.6475 | 0.2 | 0.3 | 13485.65 |  |  |  |  | 0 | 8363.8686 | 8363.8686 | 8363.8686 | 8363.8686 | 8363.8686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2725 | PEMBROKE PINES | 110307 | Private | 2036 | 5 | Swales | 66.6667 | 41266.4393 | 0.2 | 0.3 | 64375.6453 |  |  |  |  | 0 | 9778.1084 | 9778.1084 | 9778.1084 | 9778.1084 | 9778.1084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2726 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 10444.6969 | 0.2 | 0.3 | 16293.7272 |  |  |  |  | 0 | 9297.1889 | 9297.1889 | 9297.1889 | 9297.1889 | 9297.1889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2727 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 16703.7993 | 0.2 | 0.3 | 26057.9269 |  |  |  |  | 0 | 5200.3785 | 5200.3785 | 5200.3785 | 5200.3785 | 5200.3785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2728 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 20947.1527 | 0.2 | 0.3 | 32677.5583 |  |  |  |  | 0 | 5573.3625 | 5573.3625 | 5573.3625 | 5573.3625 | 5573.3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2729 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 16676.5706 | 0.2 | 0.3 | 26015.4501 |  |  |  |  | 0 | 6852.76 | 6852.76 | 6852.76 | 6852.76 | 6852.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2730 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 21821.9068 | 0.2 | 0.3 | 34042.1746 |  |  |  |  | 0 | 9062.3878 | 9062.3878 | 9062.3878 | 9062.3878 | 9062.3878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2731 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 17539.7423 | 0.2 | 0.3 | 27361.998 |  |  |  |  | 0 | 2003.1527 | 2003.1527 | 2003.1527 | 2003.1527 | 2003.1527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2732 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 9633.041 | 0.2 | 0.3 | 15027.544 |  |  |  |  | 0 | 5220.9789 | 5220.9789 | 5220.9789 | 5220.9789 | 5220.9789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2733 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 17085.8039 | 0.2 | 0.3 | 26653.854 |  |  |  |  | 0 | 5266.1684 | 5266.1684 | 5266.1684 | 5266.1684 | 5266.1684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2734 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 13186.0184 | 0.2 | 0.3 | 20570.1887 |  |  |  |  | 0 | 5220.1671 | 5220.1671 | 5220.1671 | 5220.1671 | 5220.1671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2735 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 18295.6232 | 0.2 | 0.3 | 28541.1722 |  |  |  |  | 0 | 8480.5763 | 8480.5763 | 8480.5763 | 8480.5763 | 8480.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2736 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16677.2899 | 0.2 | 0.3 | 26016.5723 |  |  |  |  | 0 | 6546.9456 | 6546.9456 | 6546.9456 | 6546.9456 | 6546.9456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2737 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 19942.2887 | 0.2 | 0.3 | 31109.9703 |  |  |  |  | 0 | 5201.9515 | 5201.9515 | 5201.9515 | 5201.9515 | 5201.9515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2738 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 3540.0257 | 0.2 | 0.3 | 5522.44 |  |  |  |  | 0 | 5226.1266 | 5226.1266 | 5226.1266 | 5226.1266 | 5226.1266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2739 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16067.9663 | 0.2 | 0.3 | 25066.0275 |  |  |  |  | 0 | 4926.502 | 4926.502 | 4926.502 | 4926.502 | 4926.502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2740 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 6322.1225 | 6322.1225 | 6322.1225 | 6322.1225 | 6322.1225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2741 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 16690.2564 | 0.2 | 0.3 | 26036.8 |  |  |  |  | 0 | 3605.3737 | 3605.3737 | 3605.3737 | 3605.3737 | 3605.3737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2742 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 7853.8801 | 0.2 | 0.3 | 12252.053 |  |  |  |  | 0 | 6786.9076 | 6786.9076 | 6786.9076 | 6786.9076 | 6786.9076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2743 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 11717.6127 | 0.2 | 0.3 | 18279.4758 |  |  |  |  | 0 | 5200.1336 | 5200.1336 | 5200.1336 | 5200.1336 | 5200.1336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2744 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 6006.7993 | 6006.7993 | 6006.7993 | 6006.7993 | 6006.7993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2745 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 15534.2093 | 0.2 | 0.3 | 24233.3666 |  |  |  |  | 0 | 5200.6214 | 5200.6214 | 5200.6214 | 5200.6214 | 5200.6214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2746 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 12751.8512 | 0.2 | 0.3 | 19892.8879 |  |  |  |  | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2747 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 15540.146 | 0.2 | 0.3 | 24242.6278 |  |  |  |  | 0 | 8920.1691 | 8920.1691 | 8920.1691 | 8920.1691 | 8920.1691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2748 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 21958.3059 | 0.2 | 0.3 | 34254.9572 |  |  |  |  | 0 | 9558.9064 | 9558.9064 | 9558.9064 | 9558.9064 | 9558.9064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2749 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16673.7761 | 0.2 | 0.3 | 26011.0908 |  |  |  |  | 0 | 5200.1503 | 5200.1503 | 5200.1503 | 5200.1503 | 5200.1503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2750 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 7716.4831 | 0.2 | 0.3 | 12037.7137 |  |  |  |  | 0 | 5200.3145 | 5200.3145 | 5200.3145 | 5200.3145 | 5200.3145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2751 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 31953.8201 | 0.2 | 0.3 | 49847.9593 |  |  |  |  | 0 | 6304.4501 | 6304.4501 | 6304.4501 | 6304.4501 | 6304.4501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2752 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 15759.8175 | 0.2 | 0.3 | 24585.3152 |  |  |  |  | 0 | 2448.0335 | 2448.0335 | 2448.0335 | 2448.0335 | 2448.0335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2753 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 10107.1694 | 0.2 | 0.3 | 15767.1843 |  |  |  |  | 0 | 5200.2495 | 5200.2495 | 5200.2495 | 5200.2495 | 5200.2495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2754 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 11629.0006 | 0.2 | 0.3 | 18141.2409 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2755 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 15196.7547 | 0.2 | 0.3 | 23706.9374 |  |  |  |  | 0 | 9777.7447 | 9777.7447 | 9777.7447 | 9777.7447 | 9777.7447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2756 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 8338.622 | 0.2 | 0.3 | 13008.2503 |  |  |  |  | 0 | 5245.2037 | 5245.2037 | 5245.2037 | 5245.2037 | 5245.2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2757 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16891.8192 | 0.2 | 0.3 | 26351.238 |  |  |  |  | 0 | 5200.9657 | 5200.9657 | 5200.9657 | 5200.9657 | 5200.9657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2758 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16881.8699 | 0.2 | 0.3 | 26335.717 |  |  |  |  | 0 | 5200.3951 | 5200.3951 | 5200.3951 | 5200.3951 | 5200.3951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2759 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 18751.5131 | 0.2 | 0.3 | 29252.3604 |  |  |  |  | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2760 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 621.7794 | 0.2 | 0.3 | 969.9759 |  |  |  |  | 0 | 9132.7452 | 9132.7452 | 9132.7452 | 9132.7452 | 9132.7452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2761 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16102.5581 | 0.2 | 0.3 | 25119.9907 |  |  |  |  | 0 | 5200.6159 | 5200.6159 | 5200.6159 | 5200.6159 | 5200.6159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2762 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16712.7659 | 0.2 | 0.3 | 26071.9148 |  |  |  |  | 0 | 5200.5302 | 5200.5302 | 5200.5302 | 5200.5302 | 5200.5302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2763 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16707.3369 | 0.2 | 0.3 | 26063.4456 |  |  |  |  | 0 | 5246.0827 | 5246.0827 | 5246.0827 | 5246.0827 | 5246.0827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2764 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.2284 | 0.2 | 0.3 | 26010.2363 |  |  |  |  | 0 | 1217.3272 | 1217.3272 | 1217.3272 | 1217.3272 | 1217.3272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2765 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.8947 | 0.2 | 0.3 | 26011.2757 |  |  |  |  | 0 | 6034.8249 | 6034.8249 | 6034.8249 | 6034.8249 | 6034.8249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2766 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17200.2569 | 0.2 | 0.3 | 26832.4008 |  |  |  |  | 0 | 10044.7915 | 10044.7915 | 10044.7915 | 10044.7915 | 10044.7915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2767 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16674.2307 | 0.2 | 0.3 | 26011.7998 |  |  |  |  | 0 | 4265.5158 | 4265.5158 | 4265.5158 | 4265.5158 | 4265.5158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2768 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16674.5233 | 0.2 | 0.3 | 26012.2563 |  |  |  |  | 0 | 4974.591 | 4974.591 | 4974.591 | 4974.591 | 4974.591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2769 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 22367.655 | 0.2 | 0.3 | 34893.5418 |  |  |  |  | 0 | 4697.4505 | 4697.4505 | 4697.4505 | 4697.4505 | 4697.4505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2770 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 14115.5977 | 0.2 | 0.3 | 22020.3324 |  |  |  |  | 0 | 5839.4432 | 5839.4432 | 5839.4432 | 5839.4432 | 5839.4432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2771 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 27474.3327 | 0.2 | 0.3 | 42859.9591 |  |  |  |  | 0 | 10271.4978 | 10271.4978 | 10271.4978 | 10271.4978 | 10271.4978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2772 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 18903.5155 | 0.2 | 0.3 | 29489.4841 |  |  |  |  | 0 | 9604.3606 | 9604.3606 | 9604.3606 | 9604.3606 | 9604.3606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2773 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 20561.8132 | 0.2 | 0.3 | 32076.4286 |  |  |  |  | 0 | 5200.3803 | 5200.3803 | 5200.3803 | 5200.3803 | 5200.3803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2774 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 26161.1536 | 0.2 | 0.3 | 40811.3996 |  |  |  |  | 0 | 4168.4783 | 4168.4783 | 4168.4783 | 4168.4783 | 4168.4783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2775 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 33027.3224 | 0.2 | 0.3 | 51522.6229 |  |  |  |  | 0 | 5644.8915 | 5644.8915 | 5644.8915 | 5644.8915 | 5644.8915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2776 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16685.9838 | 0.2 | 0.3 | 26030.1347 |  |  |  |  | 0 | 6679.2663 | 6679.2663 | 6679.2663 | 6679.2663 | 6679.2663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2777 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16687.6735 | 0.2 | 0.3 | 26032.7706 |  |  |  |  | 0 | 5377.614 | 5377.614 | 5377.614 | 5377.614 | 5377.614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2778 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 5238.8817 | 5238.8817 | 5238.8817 | 5238.8817 | 5238.8817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2779 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 4528.6388 | 4528.6388 | 4528.6388 | 4528.6388 | 4528.6388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2780 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 22631.3803 | 0.2 | 0.3 | 35304.9533 |  |  |  |  | 0 | 5211.271 | 5211.271 | 5211.271 | 5211.271 | 5211.271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2781 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 4947.6901 | 0.2 | 0.3 | 7718.3966 |  |  |  |  | 0 | 3573.9809 | 3573.9809 | 3573.9809 | 3573.9809 | 3573.9809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2782 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 20914.7015 | 0.2 | 0.3 | 32626.9344 |  |  |  |  | 0 | 7540.7026 | 7540.7026 | 7540.7026 | 7540.7026 | 7540.7026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2783 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 29485.3916 | 0.2 | 0.3 | 45997.2109 |  |  |  |  | 0 | 11682.2651 | 11682.2651 | 11682.2651 | 11682.2651 | 11682.2651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2784 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 8385.1514 | 0.2 | 0.3 | 13080.8362 |  |  |  |  | 0 | 1221.0744 | 1221.0744 | 1221.0744 | 1221.0744 | 1221.0744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2785 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16679.5935 | 0.2 | 0.3 | 26020.1658 |  |  |  |  | 0 | 4313.8566 | 4313.8566 | 4313.8566 | 4313.8566 | 4313.8566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2786 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16682.8412 | 0.2 | 0.3 | 26025.2323 |  |  |  |  | 0 | 5199.9802 | 5199.9802 | 5199.9802 | 5199.9802 | 5199.9802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2787 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16697.2619 | 0.2 | 0.3 | 26047.7285 |  |  |  |  | 0 | 9002.6862 | 9002.6862 | 9002.6862 | 9002.6862 | 9002.6862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2788 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 22571.1351 | 0.2 | 0.3 | 35210.9707 |  |  |  |  | 0 | 3800.5636 | 3800.5636 | 3800.5636 | 3800.5636 | 3800.5636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2789 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 12532.7564 | 0.2 | 0.3 | 19551.1 |  |  |  |  | 0 | 2641.3012 | 2641.3012 | 2641.3012 | 2641.3012 | 2641.3012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2790 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 30218.5395 | 0.2 | 0.3 | 47140.9216 |  |  |  |  | 0 | 4424.5283 | 4424.5283 | 4424.5283 | 4424.5283 | 4424.5283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2791 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 29397.4694 | 0.2 | 0.3 | 45860.0523 |  |  |  |  | 0 | 980.0025 | 980.0025 | 980.0025 | 980.0025 | 980.0025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2792 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 14479.5229 | 0.2 | 0.3 | 22588.0557 |  |  |  |  | 0 | 2599.9969 | 2599.9969 | 2599.9969 | 2599.9969 | 2599.9969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2793 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 6270.3093 | 0.2 | 0.3 | 9781.6826 |  |  |  |  | 0 | 7213.1158 | 7213.1158 | 7213.1158 | 7213.1158 | 7213.1158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2794 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 19078.0905 | 0.2 | 0.3 | 29761.8212 |  |  |  |  | 0 | 5838.5959 | 5838.5959 | 5838.5959 | 5838.5959 | 5838.5959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2795 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 14107.0003 | 0.2 | 0.3 | 22006.9205 |  |  |  |  | 0 | 7626.1308 | 7626.1308 | 7626.1308 | 7626.1308 | 7626.1308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2796 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 12981.0053 | 0.2 | 0.3 | 20250.3683 |  |  |  |  | 0 | 7379.4802 | 7379.4802 | 7379.4802 | 7379.4802 | 7379.4802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2797 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 11419.2103 | 0.2 | 0.3 | 17813.9681 |  |  |  |  | 0 | 5200.3515 | 5200.3515 | 5200.3515 | 5200.3515 | 5200.3515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2798 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 30467.9481 | 0.2 | 0.3 | 47529.999 |  |  |  |  | 0 | 8190.0902 | 8190.0902 | 8190.0902 | 8190.0902 | 8190.0902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2799 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 630.0709 | 0.2 | 0.3 | 982.9107 |  |  |  |  | 0 | 8922.6908 | 8922.6908 | 8922.6908 | 8922.6908 | 8922.6908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2800 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 25026.7782 | 0.2 | 0.3 | 39041.774 |  |  |  |  | 0 | 1618.6025 | 1618.6025 | 1618.6025 | 1618.6025 | 1618.6025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2801 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 21735.2065 | 0.2 | 0.3 | 33906.9221 |  |  |  |  | 0 | 5199.9903 | 5199.9903 | 5199.9903 | 5199.9903 | 5199.9903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2802 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 31588.513 | 0.2 | 0.3 | 49278.0803 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2803 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 22426.6185 | 0.2 | 0.3 | 34985.5249 |  |  |  |  | 0 | 9152.2215 | 9152.2215 | 9152.2215 | 9152.2215 | 9152.2215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2804 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 20247.9613 | 0.2 | 0.3 | 31586.8196 |  |  |  |  | 0 | 5200.2349 | 5200.2349 | 5200.2349 | 5200.2349 | 5200.2349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2805 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 16806.6909 | 0.2 | 0.3 | 26218.4378 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2806 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 4826.6693 | 0.2 | 0.3 | 7529.6041 |  |  |  |  | 0 | 6000.1015 | 6000.1015 | 6000.1015 | 6000.1015 | 6000.1015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2807 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 17082.3294 | 0.2 | 0.3 | 26648.4339 |  |  |  |  | 0 | 5598.4001 | 5598.4001 | 5598.4001 | 5598.4001 | 5598.4001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2808 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 16690.9982 | 0.2 | 0.3 | 26037.9572 |  |  |  |  | 0 | 5200.151 | 5200.151 | 5200.151 | 5200.151 | 5200.151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2809 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 16681.8547 | 0.2 | 0.3 | 26023.6933 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2810 | PEMBROKE PINES | 110308 | Private | 2036 | 5 | Swales | 66.6667 | 11857.2645 | 0.2 | 0.3 | 18497.3327 |  |  |  |  | 0 | 9234.7704 | 9234.7704 | 9234.7704 | 9234.7704 | 9234.7704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2811 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 11874.9894 | 0.2 | 0.3 | 18524.9835 |  |  |  |  | 0 | 5200.1434 | 5200.1434 | 5200.1434 | 5200.1434 | 5200.1434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2812 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 9140.1285 | 0.2 | 0.3 | 14258.6005 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2813 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 4450.5897 | 0.2 | 0.3 | 6942.92 |  |  |  |  | 0 | 5199.9638 | 5199.9638 | 5199.9638 | 5199.9638 | 5199.9638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2814 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 8500.8423 | 0.2 | 0.3 | 13261.314 |  |  |  |  | 0 | 8715.8658 | 8715.8658 | 8715.8658 | 8715.8658 | 8715.8658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2815 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 15427.4751 | 0.2 | 0.3 | 24066.8611 |  |  |  |  | 0 | 1162.0414 | 1162.0414 | 1162.0414 | 1162.0414 | 1162.0414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2816 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 16677.7862 | 0.2 | 0.3 | 26017.3465 |  |  |  |  | 0 | 9491.5179 | 9491.5179 | 9491.5179 | 9491.5179 | 9491.5179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2817 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 2571.9377 | 0.2 | 0.3 | 4012.2228 |  |  |  |  | 0 | 5625.9737 | 5625.9737 | 5625.9737 | 5625.9737 | 5625.9737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2818 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 8368.5722 | 0.2 | 0.3 | 13054.9726 |  |  |  |  | 0 | 4683.5349 | 4683.5349 | 4683.5349 | 4683.5349 | 4683.5349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2819 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 19772.3047 | 0.2 | 0.3 | 30844.7954 |  |  |  |  | 0 | 10042.4431 | 10042.4431 | 10042.4431 | 10042.4431 | 10042.4431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2820 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 9198.0162 | 9198.0162 | 9198.0162 | 9198.0162 | 9198.0162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2821 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 19241.8479 | 0.2 | 0.3 | 30017.2827 |  |  |  |  | 0 | 5793.5697 | 5793.5697 | 5793.5697 | 5793.5697 | 5793.5697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2822 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4345 | 0.2 | 0.3 | 26001.1978 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2823 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 26780.0173 | 0.2 | 0.3 | 41776.827 |  |  |  |  | 0 | 8316.1936 | 8316.1936 | 8316.1936 | 8316.1936 | 8316.1936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2824 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 1424.9759 | 0.2 | 0.3 | 2222.9624 |  |  |  |  | 0 | 10009.5203 | 10009.5203 | 10009.5203 | 10009.5203 | 10009.5203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2825 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 31921.3383 | 0.2 | 0.3 | 49797.2878 |  |  |  |  | 0 | 5200.0489 | 5200.0489 | 5200.0489 | 5200.0489 | 5200.0489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2826 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16697.3635 | 0.2 | 0.3 | 26047.8871 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2827 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 17039.6691 | 0.2 | 0.3 | 26581.8837 |  |  |  |  | 0 | 5199.8654 | 5199.8654 | 5199.8654 | 5199.8654 | 5199.8654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2828 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 19566.0432 | 0.2 | 0.3 | 30523.0274 |  |  |  |  | 0 | 8829.6765 | 8829.6765 | 8829.6765 | 8829.6765 | 8829.6765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2829 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 24437.7423 | 0.2 | 0.3 | 38122.878 |  |  |  |  | 0 | 5215.4045 | 5215.4045 | 5215.4045 | 5215.4045 | 5215.4045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2830 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 17407.195 | 0.2 | 0.3 | 27155.2242 |  |  |  |  | 0 | 5201.8759 | 5201.8759 | 5201.8759 | 5201.8759 | 5201.8759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2831 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 17731.2831 | 0.2 | 0.3 | 27660.8016 |  |  |  |  | 0 | 5404.0746 | 5404.0746 | 5404.0746 | 5404.0746 | 5404.0746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2832 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 3431.517 | 0.2 | 0.3 | 5353.1665 |  |  |  |  | 0 | 3041.6911 | 3041.6911 | 3041.6911 | 3041.6911 | 3041.6911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2833 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 1389.4075 | 0.2 | 0.3 | 2167.4756 |  |  |  |  | 0 | 5353.3198 | 5353.3198 | 5353.3198 | 5353.3198 | 5353.3198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2834 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 19871.2899 | 0.2 | 0.3 | 30999.2122 |  |  |  |  | 0 | 10090.488 | 10090.488 | 10090.488 | 10090.488 | 10090.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2835 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 7151.2939 | 0.2 | 0.3 | 11156.0185 |  |  |  |  | 0 | 5833.7615 | 5833.7615 | 5833.7615 | 5833.7615 | 5833.7615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2836 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 15612.5977 | 0.2 | 0.3 | 24355.6525 |  |  |  |  | 0 | 9779.267 | 9779.267 | 9779.267 | 9779.267 | 9779.267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2837 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 14545.6417 | 0.2 | 0.3 | 22691.2011 |  |  |  |  | 0 | 5940.8023 | 5940.8023 | 5940.8023 | 5940.8023 | 5940.8023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2838 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 17718.3934 | 0.2 | 0.3 | 27640.6937 |  |  |  |  | 0 | 5952.2522 | 5952.2522 | 5952.2522 | 5952.2522 | 5952.2522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2839 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 18555.4548 | 0.2 | 0.3 | 28946.5095 |  |  |  |  | 0 | 9780.2252 | 9780.2252 | 9780.2252 | 9780.2252 | 9780.2252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2840 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 5977.3721 | 0.2 | 0.3 | 9324.7005 |  |  |  |  | 0 | 8927.9017 | 8927.9017 | 8927.9017 | 8927.9017 | 8927.9017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2841 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 11258.1586 | 0.2 | 0.3 | 17562.7274 |  |  |  |  | 0 | 5200.4385 | 5200.4385 | 5200.4385 | 5200.4385 | 5200.4385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2842 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 22879.6097 | 0.2 | 0.3 | 35692.1912 |  |  |  |  | 0 | 6155.1099 | 6155.1099 | 6155.1099 | 6155.1099 | 6155.1099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2843 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 18671.3121 | 0.2 | 0.3 | 29127.2468 |  |  |  |  | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2844 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 11671.4352 | 0.2 | 0.3 | 18207.4389 |  |  |  |  | 0 | 8689.7303 | 8689.7303 | 8689.7303 | 8689.7303 | 8689.7303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2845 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 10723.1629 | 0.2 | 0.3 | 16728.1342 |  |  |  |  | 0 | 7471.5304 | 7471.5304 | 7471.5304 | 7471.5304 | 7471.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2846 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 7346.8264 | 0.2 | 0.3 | 11461.0492 |  |  |  |  | 0 | 8849.7216 | 8849.7216 | 8849.7216 | 8849.7216 | 8849.7216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2847 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 13013.3063 | 0.2 | 0.3 | 20300.7578 |  |  |  |  | 0 | 5026.8073 | 5026.8073 | 5026.8073 | 5026.8073 | 5026.8073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2848 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.871 | 0.2 | 0.3 | 26011.2388 |  |  |  |  | 0 | 7348.5828 | 7348.5828 | 7348.5828 | 7348.5828 | 7348.5828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2849 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 8056.5523 | 0.2 | 0.3 | 12568.2215 |  |  |  |  | 0 | 5116.2807 | 5116.2807 | 5116.2807 | 5116.2807 | 5116.2807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2850 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16695.4275 | 0.2 | 0.3 | 26044.8668 |  |  |  |  | 0 | 5406.2637 | 5406.2637 | 5406.2637 | 5406.2637 | 5406.2637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2851 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 8267.933 | 0.2 | 0.3 | 12897.9755 |  |  |  |  | 0 | 9184.0261 | 9184.0261 | 9184.0261 | 9184.0261 | 9184.0261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2852 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 502.4868 | 0.2 | 0.3 | 783.8794 |  |  |  |  | 0 | 5222.1633 | 5222.1633 | 5222.1633 | 5222.1633 | 5222.1633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2853 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 19518.0215 | 0.2 | 0.3 | 30448.1136 |  |  |  |  | 0 | 5217.7899 | 5217.7899 | 5217.7899 | 5217.7899 | 5217.7899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2854 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 26137.6661 | 0.2 | 0.3 | 40774.7591 |  |  |  |  | 0 | 5216.8642 | 5216.8642 | 5216.8642 | 5216.8642 | 5216.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2855 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 17488.8646 | 0.2 | 0.3 | 27282.6288 |  |  |  |  | 0 | 5593.9702 | 5593.9702 | 5593.9702 | 5593.9702 | 5593.9702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2856 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 23074.5033 | 0.2 | 0.3 | 35996.2252 |  |  |  |  | 0 | 5199.9803 | 5199.9803 | 5199.9803 | 5199.9803 | 5199.9803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2857 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 16866.4065 | 0.2 | 0.3 | 26311.5941 |  |  |  |  | 0 | 5199.9799 | 5199.9799 | 5199.9799 | 5199.9799 | 5199.9799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2858 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 22093.353 | 0.2 | 0.3 | 34465.6307 |  |  |  |  | 0 | 7292.3702 | 7292.3702 | 7292.3702 | 7292.3702 | 7292.3702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2859 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 8095.5973 | 0.2 | 0.3 | 12629.1318 |  |  |  |  | 0 | 5599.3836 | 5599.3836 | 5599.3836 | 5599.3836 | 5599.3836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2860 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 18685.4346 | 0.2 | 0.3 | 29149.278 |  |  |  |  | 0 | 5870.4921 | 5870.4921 | 5870.4921 | 5870.4921 | 5870.4921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2861 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 7447.5347 | 0.2 | 0.3 | 11618.1541 |  |  |  |  | 0 | 5478.7533 | 5478.7533 | 5478.7533 | 5478.7533 | 5478.7533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2862 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 21877.2585 | 0.2 | 0.3 | 34128.5232 |  |  |  |  | 0 | 10671.4267 | 10671.4267 | 10671.4267 | 10671.4267 | 10671.4267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2863 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16429.0679 | 0.2 | 0.3 | 25629.3459 |  |  |  |  | 0 | 8846.4546 | 8846.4546 | 8846.4546 | 8846.4546 | 8846.4546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2864 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 5082.317 | 0.2 | 0.3 | 7928.4145 |  |  |  |  | 0 | 5137.8557 | 5137.8557 | 5137.8557 | 5137.8557 | 5137.8557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2865 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 20255.0851 | 0.2 | 0.3 | 31597.9328 |  |  |  |  | 0 | 5394.9403 | 5394.9403 | 5394.9403 | 5394.9403 | 5394.9403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2866 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16691.753 | 0.2 | 0.3 | 26039.1347 |  |  |  |  | 0 | 5345.2088 | 5345.2088 | 5345.2088 | 5345.2088 | 5345.2088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2867 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16695.1906 | 0.2 | 0.3 | 26044.4973 |  |  |  |  | 0 | 5336.5403 | 5336.5403 | 5336.5403 | 5336.5403 | 5336.5403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2868 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 22893.7564 | 0.2 | 0.3 | 35714.26 |  |  |  |  | 0 | 5311.5226 | 5311.5226 | 5311.5226 | 5311.5226 | 5311.5226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2869 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 20543.619 | 0.2 | 0.3 | 32048.0456 |  |  |  |  | 0 | 6447.5376 | 6447.5376 | 6447.5376 | 6447.5376 | 6447.5376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2870 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 21158.9734 | 0.2 | 0.3 | 33007.9985 |  |  |  |  | 0 | 5200.3712 | 5200.3712 | 5200.3712 | 5200.3712 | 5200.3712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2871 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16676.4017 | 0.2 | 0.3 | 26015.1867 |  |  |  |  | 0 | 5199.9812 | 5199.9812 | 5199.9812 | 5199.9812 | 5199.9812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2872 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16726.9202 | 0.2 | 0.3 | 26093.9955 |  |  |  |  | 0 | 7430.7396 | 7430.7396 | 7430.7396 | 7430.7396 | 7430.7396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2873 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16838.8077 | 0.2 | 0.3 | 26268.54 |  |  |  |  | 0 | 5471.4457 | 5471.4457 | 5471.4457 | 5471.4457 | 5471.4457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2874 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17022.2072 | 0.2 | 0.3 | 26554.6432 |  |  |  |  | 0 | 5272.4899 | 5272.4899 | 5272.4899 | 5272.4899 | 5272.4899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2875 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17251.2613 | 0.2 | 0.3 | 26911.9676 |  |  |  |  | 0 | 9188.2213 | 9188.2213 | 9188.2213 | 9188.2213 | 9188.2213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2876 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 14682.1553 | 0.2 | 0.3 | 22904.1622 |  |  |  |  | 0 | 5263.1867 | 5263.1867 | 5263.1867 | 5263.1867 | 5263.1867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2877 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 11057.929 | 0.2 | 0.3 | 17250.3692 |  |  |  |  | 0 | 4067.6265 | 4067.6265 | 4067.6265 | 4067.6265 | 4067.6265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2878 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 26843.0667 | 0.2 | 0.3 | 41875.184 |  |  |  |  | 0 | 6755.4785 | 6755.4785 | 6755.4785 | 6755.4785 | 6755.4785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2879 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 16205.7851 | 0.2 | 0.3 | 25281.0248 |  |  |  |  | 0 | 9479.067 | 9479.067 | 9479.067 | 9479.067 | 9479.067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2880 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 30511.7821 | 0.2 | 0.3 | 47598.3801 |  |  |  |  | 0 | 5102.3735 | 5102.3735 | 5102.3735 | 5102.3735 | 5102.3735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2881 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 13313.1839 | 0.2 | 0.3 | 20768.5668 |  |  |  |  | 0 | 7284.6333 | 7284.6333 | 7284.6333 | 7284.6333 | 7284.6333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2882 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 20581.3253 | 0.2 | 0.3 | 32106.8675 |  |  |  |  | 0 | 8546.8528 | 8546.8528 | 8546.8528 | 8546.8528 | 8546.8528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2883 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 1479.3218 | 0.2 | 0.3 | 2307.742 |  |  |  |  | 0 | 8745.5705 | 8745.5705 | 8745.5705 | 8745.5705 | 8745.5705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2884 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 17418.2587 | 0.2 | 0.3 | 27172.4835 |  |  |  |  | 0 | 7814.315 | 7814.315 | 7814.315 | 7814.315 | 7814.315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2885 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 5200.7343 | 5200.7343 | 5200.7343 | 5200.7343 | 5200.7343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2886 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 16681.2582 | 0.2 | 0.3 | 26022.7628 |  |  |  |  | 0 | 5200.0691 | 5200.0691 | 5200.0691 | 5200.0691 | 5200.0691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2887 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 9001.6297 | 0.2 | 0.3 | 14042.5423 |  |  |  |  | 0 | 7496.7481 | 7496.7481 | 7496.7481 | 7496.7481 | 7496.7481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2888 | PEMBROKE PINES | 110312 | Public | 2036 | 5 | Swales | 66.6667 | 16677.2137 | 0.2 | 0.3 | 26016.4534 |  |  |  |  | 0 | 4798.2142 | 4798.2142 | 4798.2142 | 4798.2142 | 4798.2142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2889 | PEMBROKE PINES | 110312 | Public | 2036 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 5315.1094 | 5315.1094 | 5315.1094 | 5315.1094 | 5315.1094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2890 | PEMBROKE PINES | 110312 | Public | 2036 | 5 | Swales | 66.6667 | 16679.4082 | 0.2 | 0.3 | 26019.8768 |  |  |  |  | 0 | 388.3269 | 388.3269 | 388.3269 | 388.3269 | 388.3269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2891 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 31358.3073 | 0.2 | 0.3 | 48918.9594 |  |  |  |  | 0 | 5199.9538 | 5199.9538 | 5199.9538 | 5199.9538 | 5199.9538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2892 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 16678.9035 | 0.2 | 0.3 | 26019.0894 |  |  |  |  | 0 | 8964.7653 | 8964.7653 | 8964.7653 | 8964.7653 | 8964.7653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2893 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 16678.9031 | 0.2 | 0.3 | 26019.0888 |  |  |  |  | 0 | 5204.866 | 5204.866 | 5204.866 | 5204.866 | 5204.866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2894 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 16679.1765 | 0.2 | 0.3 | 26019.5154 |  |  |  |  | 0 | 5210.1193 | 5210.1193 | 5210.1193 | 5210.1193 | 5210.1193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2895 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 16679.6973 | 0.2 | 0.3 | 26020.3278 |  |  |  |  | 0 | 5211.2775 | 5211.2775 | 5211.2775 | 5211.2775 | 5211.2775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2896 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 31361.4179 | 0.2 | 0.3 | 48923.812 |  |  |  |  | 0 | 5410.9848 | 5410.9848 | 5410.9848 | 5410.9848 | 5410.9848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2897 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 16678.2549 | 0.2 | 0.3 | 26018.0777 |  |  |  |  | 0 | 4333.1963 | 4333.1963 | 4333.1963 | 4333.1963 | 4333.1963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2898 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 5362.688 | 5362.688 | 5362.688 | 5362.688 | 5362.688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2899 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 6215.7913 | 6215.7913 | 6215.7913 | 6215.7913 | 6215.7913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2900 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 16678.6871 | 0.2 | 0.3 | 26018.7519 |  |  |  |  | 0 | 10904.0616 | 10904.0616 | 10904.0616 | 10904.0616 | 10904.0616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2901 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 31358.7723 | 0.2 | 0.3 | 48919.6847 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2902 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 17684.7917 | 0.2 | 0.3 | 27588.2751 |  |  |  |  | 0 | 5567.4176 | 5567.4176 | 5567.4176 | 5567.4176 | 5567.4176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2903 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 17034.9783 | 0.2 | 0.3 | 26574.5662 |  |  |  |  | 0 | 6888.9694 | 6888.9694 | 6888.9694 | 6888.9694 | 6888.9694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2904 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 17285.1058 | 0.2 | 0.3 | 26964.765 |  |  |  |  | 0 | 9049.895 | 9049.895 | 9049.895 | 9049.895 | 9049.895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2905 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.6099 | 0.2 | 0.3 | 26017.0715 |  |  |  |  | 0 | 7493.2468 | 7493.2468 | 7493.2468 | 7493.2468 | 7493.2468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2906 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31372.0256 | 0.2 | 0.3 | 48940.3599 |  |  |  |  | 0 | 2599.7012 | 2599.7012 | 2599.7012 | 2599.7012 | 2599.7012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2907 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 21082.5639 | 0.2 | 0.3 | 32888.7997 |  |  |  |  | 0 | 5245.8912 | 5245.8912 | 5245.8912 | 5245.8912 | 5245.8912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2908 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16332.9164 | 0.2 | 0.3 | 25479.3496 |  |  |  |  | 0 | 7734.5038 | 7734.5038 | 7734.5038 | 7734.5038 | 7734.5038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2909 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 11568.3257 | 0.2 | 0.3 | 18046.5881 |  |  |  |  | 0 | 7673.1344 | 7673.1344 | 7673.1344 | 7673.1344 | 7673.1344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2910 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0183 | 0.2 | 0.3 | 26000.5485 |  |  |  |  | 0 | 9015.5766 | 9015.5766 | 9015.5766 | 9015.5766 | 9015.5766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2911 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6846 | 0.2 | 0.3 | 26000.028 |  |  |  |  | 0 | 5201.3544 | 5201.3544 | 5201.3544 | 5201.3544 | 5201.3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2912 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2913 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 18616.3609 | 0.2 | 0.3 | 29041.5231 |  |  |  |  | 0 | 2698.778 | 2698.778 | 2698.778 | 2698.778 | 2698.778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2914 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 33347.8311 | 0.2 | 0.3 | 52022.6165 |  |  |  |  | 0 | 6251.0323 | 6251.0323 | 6251.0323 | 6251.0323 | 6251.0323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2915 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16672.3989 | 0.2 | 0.3 | 26008.9422 |  |  |  |  | 0 | 5258.0438 | 5258.0438 | 5258.0438 | 5258.0438 | 5258.0438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2916 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16681.0418 | 0.2 | 0.3 | 26022.4252 |  |  |  |  | 0 | 5199.3821 | 5199.3821 | 5199.3821 | 5199.3821 | 5199.3821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2917 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 19125.4209 | 0.2 | 0.3 | 29835.6567 |  |  |  |  | 0 | 1925.7521 | 1925.7521 | 1925.7521 | 1925.7521 | 1925.7521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2918 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 7191.0623 | 0.2 | 0.3 | 11218.0571 |  |  |  |  | 0 | 7709.8897 | 7709.8897 | 7709.8897 | 7709.8897 | 7709.8897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2919 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 21004.4388 | 0.2 | 0.3 | 32766.9245 |  |  |  |  | 0 | 9777.162 | 9777.162 | 9777.162 | 9777.162 | 9777.162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2920 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 17601.87 | 0.2 | 0.3 | 27458.9172 |  |  |  |  | 0 | 7591.1051 | 7591.1051 | 7591.1051 | 7591.1051 | 7591.1051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2921 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 3792.3973 | 0.2 | 0.3 | 5916.1397 |  |  |  |  | 0 | 7559.8999 | 7559.8999 | 7559.8999 | 7559.8999 | 7559.8999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2922 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 8335.8571 | 0.2 | 0.3 | 13003.937 |  |  |  |  | 0 | 5200.2249 | 5200.2249 | 5200.2249 | 5200.2249 | 5200.2249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2923 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 12888.2692 | 0.2 | 0.3 | 20105.7 |  |  |  |  | 0 | 7492.4755 | 7492.4755 | 7492.4755 | 7492.4755 | 7492.4755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2924 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 25285.6335 | 0.2 | 0.3 | 39445.5882 |  |  |  |  | 0 | 5917.0342 | 5917.0342 | 5917.0342 | 5917.0342 | 5917.0342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2925 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 28883.5221 | 0.2 | 0.3 | 45058.2944 |  |  |  |  | 0 | 7426.4175 | 7426.4175 | 7426.4175 | 7426.4175 | 7426.4175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2926 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 32123.7303 | 0.2 | 0.3 | 50113.0193 |  |  |  |  | 0 | 6208.3572 | 6208.3572 | 6208.3572 | 6208.3572 | 6208.3572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2927 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 14110.2638 | 0.2 | 0.3 | 22012.0115 |  |  |  |  | 0 | 3164.6085 | 3164.6085 | 3164.6085 | 3164.6085 | 3164.6085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2928 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 19212.9535 | 0.2 | 0.3 | 29972.2075 |  |  |  |  | 0 | 7614.8014 | 7614.8014 | 7614.8014 | 7614.8014 | 7614.8014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2929 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 17398.8063 | 0.2 | 0.3 | 27142.1379 |  |  |  |  | 0 | 106.3544 | 106.3544 | 106.3544 | 106.3544 | 106.3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2930 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 20317.8763 | 0.2 | 0.3 | 31695.8871 |  |  |  |  | 0 | 8419.2518 | 8419.2518 | 8419.2518 | 8419.2518 | 8419.2518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2931 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 5692.1619 | 0.2 | 0.3 | 8879.7725 |  |  |  |  | 0 | 1897.2314 | 1897.2314 | 1897.2314 | 1897.2314 | 1897.2314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2932 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 14082.7541 | 0.2 | 0.3 | 21969.0964 |  |  |  |  | 0 | 3303.4694 | 3303.4694 | 3303.4694 | 3303.4694 | 3303.4694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2933 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 16618.6027 | 0.2 | 0.3 | 25925.0203 |  |  |  |  | 0 | 1737.8885 | 1737.8885 | 1737.8885 | 1737.8885 | 1737.8885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2934 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 1724.1533 | 0.2 | 0.3 | 2689.6792 |  |  |  |  | 0 | 4965.6215 | 4965.6215 | 4965.6215 | 4965.6215 | 4965.6215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2935 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 2113.8644 | 0.2 | 0.3 | 3297.6285 |  |  |  |  | 0 | 5064.772 | 5064.772 | 5064.772 | 5064.772 | 5064.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2936 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 75.6567 | 0.2 | 0.3 | 118.0245 |  |  |  |  | 0 | 9668.2696 | 9668.2696 | 9668.2696 | 9668.2696 | 9668.2696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2937 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 7763.9743 | 0.2 | 0.3 | 12111.8 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2938 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 511.713 | 0.2 | 0.3 | 798.2723 |  |  |  |  | 0 | 5291.6441 | 5291.6441 | 5291.6441 | 5291.6441 | 5291.6441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2939 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 14395.2783 | 0.2 | 0.3 | 22456.6342 |  |  |  |  | 0 | 9909.9127 | 9909.9127 | 9909.9127 | 9909.9127 | 9909.9127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2940 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 7493.3663 | 0.2 | 0.3 | 11689.6514 |  |  |  |  | 0 | 6768.5428 | 6768.5428 | 6768.5428 | 6768.5428 | 6768.5428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2941 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17338.3374 | 0.2 | 0.3 | 27047.8063 |  |  |  |  | 0 | 6879.9986 | 6879.9986 | 6879.9986 | 6879.9986 | 6879.9986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2942 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 26661.9269 | 0.2 | 0.3 | 41592.6059 |  |  |  |  | 0 | 6112.2984 | 6112.2984 | 6112.2984 | 6112.2984 | 6112.2984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2943 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 20622.5789 | 0.2 | 0.3 | 32171.223 |  |  |  |  | 0 | 6583.036 | 6583.036 | 6583.036 | 6583.036 | 6583.036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2944 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 3147.4518 | 0.2 | 0.3 | 4910.0248 |  |  |  |  | 0 | 5314.9144 | 5314.9144 | 5314.9144 | 5314.9144 | 5314.9144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2945 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 369.6158 | 0.2 | 0.3 | 576.6006 |  |  |  |  | 0 | 966.1727 | 966.1727 | 966.1727 | 966.1727 | 966.1727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2946 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 18094.3944 | 0.2 | 0.3 | 28227.2553 |  |  |  |  | 0 | 7381.6879 | 7381.6879 | 7381.6879 | 7381.6879 | 7381.6879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2947 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 9220.8303 | 0.2 | 0.3 | 14384.4953 |  |  |  |  | 0 | 5785.3286 | 5785.3286 | 5785.3286 | 5785.3286 | 5785.3286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2948 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 16689.6851 | 0.2 | 0.3 | 26035.9088 |  |  |  |  | 0 | 6800.7537 | 6800.7537 | 6800.7537 | 6800.7537 | 6800.7537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2949 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 16673.3569 | 0.2 | 0.3 | 26010.4368 |  |  |  |  | 0 | 1833.0414 | 1833.0414 | 1833.0414 | 1833.0414 | 1833.0414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2950 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 31360.1637 | 0.2 | 0.3 | 48921.8554 |  |  |  |  | 0 | 2600.1727 | 2600.1727 | 2600.1727 | 2600.1727 | 2600.1727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2951 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 16681.4955 | 0.2 | 0.3 | 26023.1329 |  |  |  |  | 0 | 6395.4032 | 6395.4032 | 6395.4032 | 6395.4032 | 6395.4032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2952 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 15629.6904 | 0.2 | 0.3 | 24382.317 |  |  |  |  | 0 | 4794.5518 | 4794.5518 | 4794.5518 | 4794.5518 | 4794.5518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2953 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 17443.6889 | 0.2 | 0.3 | 27212.1546 |  |  |  |  | 0 | 4889.606 | 4889.606 | 4889.606 | 4889.606 | 4889.606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2954 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 6426.2248 | 0.2 | 0.3 | 10024.9107 |  |  |  |  | 0 | 9460.1177 | 9460.1177 | 9460.1177 | 9460.1177 | 9460.1177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2955 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 11455.773 | 0.2 | 0.3 | 17871.0059 |  |  |  |  | 0 | 7800.1829 | 7800.1829 | 7800.1829 | 7800.1829 | 7800.1829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2956 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 20575.6872 | 0.2 | 0.3 | 32098.072 |  |  |  |  | 0 | 10745.6255 | 10745.6255 | 10745.6255 | 10745.6255 | 10745.6255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2957 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 9556.7172 | 0.2 | 0.3 | 14908.4788 |  |  |  |  | 0 | 3597.8868 | 3597.8868 | 3597.8868 | 3597.8868 | 3597.8868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2958 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 29070.3687 | 0.2 | 0.3 | 45349.7752 |  |  |  |  | 0 | 6681.7601 | 6681.7601 | 6681.7601 | 6681.7601 | 6681.7601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2959 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 25264.4891 | 0.2 | 0.3 | 39412.6029 |  |  |  |  | 0 | 9949.7241 | 9949.7241 | 9949.7241 | 9949.7241 | 9949.7241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2960 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 16.9162 | 0.2 | 0.3 | 26.3893 |  |  |  |  | 0 | 6459.9708 | 6459.9708 | 6459.9708 | 6459.9708 | 6459.9708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2961 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 9533.1198 | 0.2 | 0.3 | 14871.6669 |  |  |  |  | 0 | 6141.0448 | 6141.0448 | 6141.0448 | 6141.0448 | 6141.0448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2962 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 7935.4807 | 0.2 | 0.3 | 12379.3498 |  |  |  |  | 0 | 10449.5159 | 10449.5159 | 10449.5159 | 10449.5159 | 10449.5159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2963 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16672.3415 | 0.2 | 0.3 | 26008.8527 |  |  |  |  | 0 | 7800.2247 | 7800.2247 | 7800.2247 | 7800.2247 | 7800.2247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2964 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 16817.1321 | 0.2 | 0.3 | 26234.726 |  |  |  |  | 0 | 7800.3079 | 7800.3079 | 7800.3079 | 7800.3079 | 7800.3079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2965 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 22035.2237 | 0.2 | 0.3 | 34374.9489 |  |  |  |  | 0 | 7948.5637 | 7948.5637 | 7948.5637 | 7948.5637 | 7948.5637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2966 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 15458.3809 | 0.2 | 0.3 | 24115.0743 |  |  |  |  | 0 | 5863.9952 | 5863.9952 | 5863.9952 | 5863.9952 | 5863.9952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2967 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 8112.6671 | 0.2 | 0.3 | 12655.7607 |  |  |  |  | 0 | 5575.9834 | 5575.9834 | 5575.9834 | 5575.9834 | 5575.9834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2968 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 253.2324 | 0.2 | 0.3 | 395.0425 |  |  |  |  | 0 | 581.8793 | 581.8793 | 581.8793 | 581.8793 | 581.8793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2969 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 16675.8882 | 0.2 | 0.3 | 26014.3856 |  |  |  |  | 0 | 4363.4709 | 4363.4709 | 4363.4709 | 4363.4709 | 4363.4709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2970 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 32834.0354 | 0.2 | 0.3 | 51221.0952 |  |  |  |  | 0 | 4016.6951 | 4016.6951 | 4016.6951 | 4016.6951 | 4016.6951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2971 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 35875.694 | 0.2 | 0.3 | 55966.0826 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2972 | PEMBROKE PINES | 110312 | Public | 2036 | 5 | Swales | 66.6667 | 16679.6558 | 0.2 | 0.3 | 26020.263 |  |  |  |  | 0 | 2402.0939 | 2402.0939 | 2402.0939 | 2402.0939 | 2402.0939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2973 | PEMBROKE PINES | 110312 | Public | 2036 | 5 | Swales | 66.6667 | 16683.2775 | 0.2 | 0.3 | 26025.913 |  |  |  |  | 0 | 1345.0817 | 1345.0817 | 1345.0817 | 1345.0817 | 1345.0817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2974 | PEMBROKE PINES | 110312 | Public | 2036 | 5 | Swales | 66.6667 | 16683.5804 | 0.2 | 0.3 | 26026.3854 |  |  |  |  | 0 | 3367.4687 | 3367.4687 | 3367.4687 | 3367.4687 | 3367.4687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2975 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31352.7631 | 0.2 | 0.3 | 48910.3105 |  |  |  |  | 0 | 5200.0009 | 5200.0009 | 5200.0009 | 5200.0009 | 5200.0009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2976 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.2069 | 0.2 | 0.3 | 26018.0028 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2977 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 26288.0059 | 0.2 | 0.3 | 41009.2892 |  |  |  |  | 0 | 5200.1271 | 5200.1271 | 5200.1271 | 5200.1271 | 5200.1271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2978 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.5953 | 0.2 | 0.3 | 26018.6086 |  |  |  |  | 0 | 3115.5518 | 3115.5518 | 3115.5518 | 3115.5518 | 3115.5518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2979 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.5549 | 0.2 | 0.3 | 26018.5457 |  |  |  |  | 0 | 3689.3814 | 3689.3814 | 3689.3814 | 3689.3814 | 3689.3814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2980 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31357.4505 | 0.2 | 0.3 | 48917.6227 |  |  |  |  | 0 | 5200.2442 | 5200.2442 | 5200.2442 | 5200.2442 | 5200.2442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2981 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.7712 | 0.2 | 0.3 | 26020.4431 |  |  |  |  | 0 | 5209.7612 | 5209.7612 | 5209.7612 | 5209.7612 | 5209.7612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2982 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 2528.9536 | 2528.9536 | 2528.9536 | 2528.9536 | 2528.9536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2983 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 30267.3555 | 0.2 | 0.3 | 47217.0745 |  |  |  |  | 0 | 6786.819 | 6786.819 | 6786.819 | 6786.819 | 6786.819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2984 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.4552 | 0.2 | 0.3 | 26018.3901 |  |  |  |  | 0 | 9490.6202 | 9490.6202 | 9490.6202 | 9490.6202 | 9490.6202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2985 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 32090.5182 | 0.2 | 0.3 | 50061.2084 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2986 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 17730.9905 | 0.2 | 0.3 | 27660.3452 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2987 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16957.8373 | 0.2 | 0.3 | 26454.2262 |  |  |  |  | 0 | 5200.2432 | 5200.2432 | 5200.2432 | 5200.2432 | 5200.2432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2988 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16794.18 | 0.2 | 0.3 | 26198.9208 |  |  |  |  | 0 | 9321.3529 | 9321.3529 | 9321.3529 | 9321.3529 | 9321.3529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2989 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16675.3622 | 0.2 | 0.3 | 26013.565 |  |  |  |  | 0 | 9131.8014 | 9131.8014 | 9131.8014 | 9131.8014 | 9131.8014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2990 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 18107.4951 | 0.2 | 0.3 | 28247.6924 |  |  |  |  | 0 | 6670.4839 | 6670.4839 | 6670.4839 | 6670.4839 | 6670.4839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2991 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 22655.2191 | 0.2 | 0.3 | 35342.1418 |  |  |  |  | 0 | 5200.1181 | 5200.1181 | 5200.1181 | 5200.1181 | 5200.1181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2992 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16975.5708 | 0.2 | 0.3 | 26481.8904 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2993 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 18232.2439 | 0.2 | 0.3 | 28442.3004 |  |  |  |  | 0 | 5200.0697 | 5200.0697 | 5200.0697 | 5200.0697 | 5200.0697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2994 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16698.8377 | 0.2 | 0.3 | 26050.1868 |  |  |  |  | 0 | 6429.2613 | 6429.2613 | 6429.2613 | 6429.2613 | 6429.2613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2995 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16699.9482 | 0.2 | 0.3 | 26051.9192 |  |  |  |  | 0 | 4631.2398 | 4631.2398 | 4631.2398 | 4631.2398 | 4631.2398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2996 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 15647.3019 | 0.2 | 0.3 | 24409.791 |  |  |  |  | 0 | 5199.9973 | 5199.9973 | 5199.9973 | 5199.9973 | 5199.9973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2997 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16287.5569 | 0.2 | 0.3 | 25408.5887 |  |  |  |  | 0 | 5200.0419 | 5200.0419 | 5200.0419 | 5200.0419 | 5200.0419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2998 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16700.1717 | 0.2 | 0.3 | 26052.2679 |  |  |  |  | 0 | 7886.1565 | 7886.1565 | 7886.1565 | 7886.1565 | 7886.1565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2999 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16688.3925 | 0.2 | 0.3 | 26033.8924 |  |  |  |  | 0 | 11234.3397 | 11234.3397 | 11234.3397 | 11234.3397 | 11234.3397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3000 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 13048.3958 | 0.2 | 0.3 | 20355.4974 |  |  |  |  | 0 | 13486.5642 | 13486.5642 | 13486.5642 | 13486.5642 | 13486.5642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3001 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 19385.7503 | 0.2 | 0.3 | 30241.7705 |  |  |  |  | 0 | 10400.2996 | 10400.2996 | 10400.2996 | 10400.2996 | 10400.2996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3002 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 10400.4749 | 10400.4749 | 10400.4749 | 10400.4749 | 10400.4749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3003 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 21047.5645 | 0.2 | 0.3 | 32834.2006 |  |  |  |  | 0 | 12916.4837 | 12916.4837 | 12916.4837 | 12916.4837 | 12916.4837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3004 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 26457.9217 | 0.2 | 0.3 | 41274.3579 |  |  |  |  | 0 | 7088.5655 | 7088.5655 | 7088.5655 | 7088.5655 | 7088.5655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3005 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16757.9265 | 0.2 | 0.3 | 26142.3653 |  |  |  |  | 0 | 7568.6998 | 7568.6998 | 7568.6998 | 7568.6998 | 7568.6998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3006 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16937.0631 | 0.2 | 0.3 | 26421.8184 |  |  |  |  | 0 | 5200.0833 | 5200.0833 | 5200.0833 | 5200.0833 | 5200.0833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3007 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 26973.8427 | 0.2 | 0.3 | 42079.1946 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3008 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 22604.8669 | 0.2 | 0.3 | 35263.5923 |  |  |  |  | 0 | 5200.2246 | 5200.2246 | 5200.2246 | 5200.2246 | 5200.2246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3009 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16712.9043 | 0.2 | 0.3 | 26072.1308 |  |  |  |  | 0 | 9776.2365 | 9776.2365 | 9776.2365 | 9776.2365 | 9776.2365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3010 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 9337.2193 | 0.2 | 0.3 | 14566.0621 |  |  |  |  | 0 | 6892.7807 | 6892.7807 | 6892.7807 | 6892.7807 | 6892.7807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3011 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 9485.8239 | 0.2 | 0.3 | 14797.8852 |  |  |  |  | 0 | 5200.0026 | 5200.0026 | 5200.0026 | 5200.0026 | 5200.0026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3012 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 4196.2625 | 0.2 | 0.3 | 6546.1694 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3013 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 7444.1956 | 0.2 | 0.3 | 11612.9451 |  |  |  |  | 0 | 5200.1621 | 5200.1621 | 5200.1621 | 5200.1621 | 5200.1621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3014 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 12903.8365 | 0.2 | 0.3 | 20129.985 |  |  |  |  | 0 | 14349.9954 | 14349.9954 | 14349.9954 | 14349.9954 | 14349.9954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3015 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 8335.9646 | 0.2 | 0.3 | 13004.1048 |  |  |  |  | 0 | 9193.3262 | 9193.3262 | 9193.3262 | 9193.3262 | 9193.3262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3016 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 4868.2896 | 0.2 | 0.3 | 7594.5318 |  |  |  |  | 0 | 5344.2779 | 5344.2779 | 5344.2779 | 5344.2779 | 5344.2779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3017 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 19291.8957 | 0.2 | 0.3 | 30095.3572 |  |  |  |  | 0 | 5908.4246 | 5908.4246 | 5908.4246 | 5908.4246 | 5908.4246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3018 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 11050.0273 | 11050.0273 | 11050.0273 | 11050.0273 | 11050.0273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3019 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 19258.9279 | 0.2 | 0.3 | 30043.9276 |  |  |  |  | 0 | 7990.7931 | 7990.7931 | 7990.7931 | 7990.7931 | 7990.7931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3020 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 5050.7583 | 0.2 | 0.3 | 7879.1829 |  |  |  |  | 0 | 2862.9069 | 2862.9069 | 2862.9069 | 2862.9069 | 2862.9069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3021 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 199.4409 | 0.2 | 0.3 | 311.1278 |  |  |  |  | 0 | 5200.0878 | 5200.0878 | 5200.0878 | 5200.0878 | 5200.0878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3022 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 12062.8318 | 0.2 | 0.3 | 18818.0176 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3023 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17664.3353 | 0.2 | 0.3 | 27556.3631 |  |  |  |  | 0 | 5200.2071 | 5200.2071 | 5200.2071 | 5200.2071 | 5200.2071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3024 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17127.3572 | 0.2 | 0.3 | 26718.6772 |  |  |  |  | 0 | 6503.1604 | 6503.1604 | 6503.1604 | 6503.1604 | 6503.1604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3025 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 24601.0822 | 0.2 | 0.3 | 38377.6882 |  |  |  |  | 0 | 6804.2895 | 6804.2895 | 6804.2895 | 6804.2895 | 6804.2895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3026 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 10458.8968 | 0.2 | 0.3 | 16315.879 |  |  |  |  | 0 | 5200.1178 | 5200.1178 | 5200.1178 | 5200.1178 | 5200.1178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3027 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 4031.002 | 0.2 | 0.3 | 6288.3631 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3028 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 19050.7709 | 0.2 | 0.3 | 29719.2026 |  |  |  |  | 0 | 5200.1593 | 5200.1593 | 5200.1593 | 5200.1593 | 5200.1593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3029 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 23790.1029 | 0.2 | 0.3 | 37112.5605 |  |  |  |  | 0 | 11295.9787 | 11295.9787 | 11295.9787 | 11295.9787 | 11295.9787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3030 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 24054.717 | 0.2 | 0.3 | 37525.3585 |  |  |  |  | 0 | 9087.6917 | 9087.6917 | 9087.6917 | 9087.6917 | 9087.6917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3031 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 160.4046 | 0.2 | 0.3 | 250.2312 |  |  |  |  | 0 | 5437.9809 | 5437.9809 | 5437.9809 | 5437.9809 | 5437.9809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3032 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 796.1635 | 0.2 | 0.3 | 1242.015 |  |  |  |  | 0 | 7557.1028 | 7557.1028 | 7557.1028 | 7557.1028 | 7557.1028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3033 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17777.1632 | 0.2 | 0.3 | 27732.3746 |  |  |  |  | 0 | 7775.091 | 7775.091 | 7775.091 | 7775.091 | 7775.091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3034 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 1976.1975 | 0.2 | 0.3 | 3082.8682 |  |  |  |  | 0 | 6590.1046 | 6590.1046 | 6590.1046 | 6590.1046 | 6590.1046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3035 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 14479.8883 | 0.2 | 0.3 | 22588.6258 |  |  |  |  | 0 | 4614.9186 | 4614.9186 | 4614.9186 | 4614.9186 | 4614.9186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3036 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 15195.4669 | 0.2 | 0.3 | 23704.9284 |  |  |  |  | 0 | 5200.1355 | 5200.1355 | 5200.1355 | 5200.1355 | 5200.1355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3037 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16812.5732 | 0.2 | 0.3 | 26227.6142 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3038 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16930.8087 | 0.2 | 0.3 | 26412.0616 |  |  |  |  | 0 | 5200.0989 | 5200.0989 | 5200.0989 | 5200.0989 | 5200.0989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3039 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 32598.0005 | 0.2 | 0.3 | 50852.8808 |  |  |  |  | 0 | 6545.999 | 6545.999 | 6545.999 | 6545.999 | 6545.999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3040 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 9415.4133 | 0.2 | 0.3 | 14688.0447 |  |  |  |  | 0 | 6768.4526 | 6768.4526 | 6768.4526 | 6768.4526 | 6768.4526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3041 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 19425.1167 | 0.2 | 0.3 | 30303.182 |  |  |  |  | 0 | 5200.2165 | 5200.2165 | 5200.2165 | 5200.2165 | 5200.2165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3042 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 25268.0565 | 0.2 | 0.3 | 39418.1681 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3043 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 6993.265 | 0.2 | 0.3 | 10909.4934 |  |  |  |  | 0 | 5200.1788 | 5200.1788 | 5200.1788 | 5200.1788 | 5200.1788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3044 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17773.2487 | 0.2 | 0.3 | 27726.2679 |  |  |  |  | 0 | 11287.1878 | 11287.1878 | 11287.1878 | 11287.1878 | 11287.1878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3045 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 14386.0449 | 0.2 | 0.3 | 22442.2301 |  |  |  |  | 0 | 8993.5801 | 8993.5801 | 8993.5801 | 8993.5801 | 8993.5801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3046 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16841.4437 | 0.2 | 0.3 | 26272.6521 |  |  |  |  | 0 | 5565.4707 | 5565.4707 | 5565.4707 | 5565.4707 | 5565.4707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3047 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 10288.8868 | 0.2 | 0.3 | 16050.6634 |  |  |  |  | 0 | 7682.4677 | 7682.4677 | 7682.4677 | 7682.4677 | 7682.4677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3048 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 17547.0522 | 0.2 | 0.3 | 27373.4014 |  |  |  |  | 0 | 7107.4673 | 7107.4673 | 7107.4673 | 7107.4673 | 7107.4673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3049 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 2180.4654 | 0.2 | 0.3 | 3401.526 |  |  |  |  | 0 | 6585.7626 | 6585.7626 | 6585.7626 | 6585.7626 | 6585.7626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3050 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 28861.7059 | 0.2 | 0.3 | 45024.2612 |  |  |  |  | 0 | 9776.4319 | 9776.4319 | 9776.4319 | 9776.4319 | 9776.4319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3051 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 8200.9139 | 8200.9139 | 8200.9139 | 8200.9139 | 8200.9139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3052 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 16677.4453 | 0.2 | 0.3 | 26016.8147 |  |  |  |  | 0 | 10620.1618 | 10620.1618 | 10620.1618 | 10620.1618 | 10620.1618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3053 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 31349.3627 | 0.2 | 0.3 | 48905.0059 |  |  |  |  | 0 | 10125.542 | 10125.542 | 10125.542 | 10125.542 | 10125.542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3054 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 16677.1879 | 0.2 | 0.3 | 26016.4132 |  |  |  |  | 0 | 5202.0146 | 5202.0146 | 5202.0146 | 5202.0146 | 5202.0146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3055 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 16680.8908 | 0.2 | 0.3 | 26022.1896 |  |  |  |  | 0 | 9838.1537 | 9838.1537 | 9838.1537 | 9838.1537 | 9838.1537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3056 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 25494.4085 | 0.2 | 0.3 | 39771.2773 |  |  |  |  | 0 | 5744.6839 | 5744.6839 | 5744.6839 | 5744.6839 | 5744.6839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3057 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 10715.4896 | 0.2 | 0.3 | 16716.1638 |  |  |  |  | 0 | 2677.3086 | 2677.3086 | 2677.3086 | 2677.3086 | 2677.3086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3058 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16679.993 | 0.2 | 0.3 | 26020.7891 |  |  |  |  | 0 | 6064.0336 | 6064.0336 | 6064.0336 | 6064.0336 | 6064.0336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3059 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 25241.8553 | 0.2 | 0.3 | 39377.2942 |  |  |  |  | 0 | 5199.9991 | 5199.9991 | 5199.9991 | 5199.9991 | 5199.9991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3060 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 17955.3481 | 0.2 | 0.3 | 28010.343 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3061 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 20149.7953 | 0.2 | 0.3 | 31433.6807 |  |  |  |  | 0 | 5200.1021 | 5200.1021 | 5200.1021 | 5200.1021 | 5200.1021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3062 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 12644.0357 | 0.2 | 0.3 | 19724.6956 |  |  |  |  | 0 | 6618.4114 | 6618.4114 | 6618.4114 | 6618.4114 | 6618.4114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3063 | PEMBROKE PINES | 110307 | Public | 2036 | 5 | Swales | 66.6667 | 27502.0556 | 0.2 | 0.3 | 42903.2067 |  |  |  |  | 0 | 3235.1324 | 3235.1324 | 3235.1324 | 3235.1324 | 3235.1324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3064 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 9224.6107 | 0.2 | 0.3 | 14390.3926 |  |  |  |  | 0 | 5200.102 | 5200.102 | 5200.102 | 5200.102 | 5200.102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3065 | PEMBROKE PINES | 110307 | Public | 2033 | 5 | Swales | 66.6667 | 14579.6041 | 0.2 | 0.3 | 22744.1823 |  |  |  |  | 0 | 5200.1775 | 5200.1775 | 5200.1775 | 5200.1775 | 5200.1775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3066 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 7064.2321 | 0.2 | 0.3 | 11020.202 |  |  |  |  | 0 | 6855.6639 | 6855.6639 | 6855.6639 | 6855.6639 | 6855.6639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3067 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 28855.3722 | 0.2 | 0.3 | 45014.3806 |  |  |  |  | 0 | 9739.4007 | 9739.4007 | 9739.4007 | 9739.4007 | 9739.4007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3068 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 19058.2123 | 0.2 | 0.3 | 29730.8112 |  |  |  |  | 0 | 13659.4094 | 13659.4094 | 13659.4094 | 13659.4094 | 13659.4094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3069 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 31363.6333 | 0.2 | 0.3 | 48927.268 |  |  |  |  | 0 | 10403.373 | 10403.373 | 10403.373 | 10403.373 | 10403.373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3070 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 31360.1745 | 0.2 | 0.3 | 48921.8723 |  |  |  |  | 0 | 7428.707 | 7428.707 | 7428.707 | 7428.707 | 7428.707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3071 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 12786.991 | 0.2 | 0.3 | 19947.706 |  |  |  |  | 0 | 5473.9254 | 5473.9254 | 5473.9254 | 5473.9254 | 5473.9254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3072 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 4951.028 | 0.2 | 0.3 | 7723.6037 |  |  |  |  | 0 | 5668.5634 | 5668.5634 | 5668.5634 | 5668.5634 | 5668.5634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3073 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 25429.7923 | 0.2 | 0.3 | 39670.476 |  |  |  |  | 0 | 4246.0446 | 4246.0446 | 4246.0446 | 4246.0446 | 4246.0446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3074 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 29197.8966 | 0.2 | 0.3 | 45548.7187 |  |  |  |  | 0 | 5200.0834 | 5200.0834 | 5200.0834 | 5200.0834 | 5200.0834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3075 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 16827.6427 | 0.2 | 0.3 | 26251.1227 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3076 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 26500.8758 | 0.2 | 0.3 | 41341.3662 |  |  |  |  | 0 | 5200.1665 | 5200.1665 | 5200.1665 | 5200.1665 | 5200.1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3077 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 18904.1437 | 0.2 | 0.3 | 29490.4641 |  |  |  |  | 0 | 4682.492 | 4682.492 | 4682.492 | 4682.492 | 4682.492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3078 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 24027.8012 | 0.2 | 0.3 | 37483.3699 |  |  |  |  | 0 | 4640.6941 | 4640.6941 | 4640.6941 | 4640.6941 | 4640.6941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3079 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 1463.7613 | 0.2 | 0.3 | 2283.4676 |  |  |  |  | 0 | 5199.9975 | 5199.9975 | 5199.9975 | 5199.9975 | 5199.9975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3080 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 5200.0626 | 5200.0626 | 5200.0626 | 5200.0626 | 5200.0626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3081 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 3819.2855 | 3819.2855 | 3819.2855 | 3819.2855 | 3819.2855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3082 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 9501.4421 | 9501.4421 | 9501.4421 | 9501.4421 | 9501.4421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3083 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 18354.21 | 0.2 | 0.3 | 28632.5676 |  |  |  |  | 0 | 14385.9193 | 14385.9193 | 14385.9193 | 14385.9193 | 14385.9193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3084 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 22709.741 | 0.2 | 0.3 | 35427.196 |  |  |  |  | 0 | 6954.9324 | 6954.9324 | 6954.9324 | 6954.9324 | 6954.9324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3085 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16676.1569 | 0.2 | 0.3 | 26014.8047 |  |  |  |  | 0 | 5623.0157 | 5623.0157 | 5623.0157 | 5623.0157 | 5623.0157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3086 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16676.3859 | 0.2 | 0.3 | 26015.162 |  |  |  |  | 0 | 8552.9271 | 8552.9271 | 8552.9271 | 8552.9271 | 8552.9271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3087 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31354.1909 | 0.2 | 0.3 | 48912.5378 |  |  |  |  | 0 | 8241.6752 | 8241.6752 | 8241.6752 | 8241.6752 | 8241.6752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3088 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.1166 | 0.2 | 0.3 | 26017.8619 |  |  |  |  | 0 | 7469.7474 | 7469.7474 | 7469.7474 | 7469.7474 | 7469.7474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3089 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.4715 | 0.2 | 0.3 | 26018.4156 |  |  |  |  | 0 | 5372.0435 | 5372.0435 | 5372.0435 | 5372.0435 | 5372.0435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3090 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 24698.9446 | 0.2 | 0.3 | 38530.3536 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3091 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 4551.923 | 0.2 | 0.3 | 7100.9999 |  |  |  |  | 0 | 7395.2871 | 7395.2871 | 7395.2871 | 7395.2871 | 7395.2871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3092 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 10167.1513 | 0.2 | 0.3 | 15860.756 |  |  |  |  | 0 | 2219.86 | 2219.86 | 2219.86 | 2219.86 | 2219.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3093 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 7537.0293 | 0.2 | 0.3 | 11757.7658 |  |  |  |  | 0 | 7446.023 | 7446.023 | 7446.023 | 7446.023 | 7446.023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3094 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 522.5195 | 0.2 | 0.3 | 815.1305 |  |  |  |  | 0 | 9625.8694 | 9625.8694 | 9625.8694 | 9625.8694 | 9625.8694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3095 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 19377.5118 | 0.2 | 0.3 | 30228.9184 |  |  |  |  | 0 | 6337.31 | 6337.31 | 6337.31 | 6337.31 | 6337.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3096 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 14475.6944 | 0.2 | 0.3 | 22582.0833 |  |  |  |  | 0 | 7306.6002 | 7306.6002 | 7306.6002 | 7306.6002 | 7306.6002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3097 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16736.9279 | 0.2 | 0.3 | 26109.6076 |  |  |  |  | 0 | 8293.3165 | 8293.3165 | 8293.3165 | 8293.3165 | 8293.3165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3098 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16751.7378 | 0.2 | 0.3 | 26132.711 |  |  |  |  | 0 | 9049.0584 | 9049.0584 | 9049.0584 | 9049.0584 | 9049.0584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3099 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16717.9597 | 0.2 | 0.3 | 26080.0172 |  |  |  |  | 0 | 5160.9532 | 5160.9532 | 5160.9532 | 5160.9532 | 5160.9532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3100 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16718.5161 | 0.2 | 0.3 | 26080.8851 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3101 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 25291.4 | 0.2 | 0.3 | 39454.584 |  |  |  |  | 0 | 5079.5604 | 5079.5604 | 5079.5604 | 5079.5604 | 5079.5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3102 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 22049.7123 | 0.2 | 0.3 | 34397.5511 |  |  |  |  | 0 | 26.8905 | 26.8905 | 26.8905 | 26.8905 | 26.8905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3103 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16780.6916 | 0.2 | 0.3 | 26177.8789 |  |  |  |  | 0 | 2971.7973 | 2971.7973 | 2971.7973 | 2971.7973 | 2971.7973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3104 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16701.4455 | 0.2 | 0.3 | 26054.255 |  |  |  |  | 0 | 5200.205 | 5200.205 | 5200.205 | 5200.205 | 5200.205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3105 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16702.8448 | 0.2 | 0.3 | 26056.4379 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3106 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 13504.8387 | 0.2 | 0.3 | 21067.5484 |  |  |  |  | 0 | 5200.196 | 5200.196 | 5200.196 | 5200.196 | 5200.196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3107 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 15688.9874 | 0.2 | 0.3 | 24474.8203 |  |  |  |  | 0 | 9799.7214 | 9799.7214 | 9799.7214 | 9799.7214 | 9799.7214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3108 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 18412.7892 | 0.2 | 0.3 | 28723.9512 |  |  |  |  | 0 | 8632.3863 | 8632.3863 | 8632.3863 | 8632.3863 | 8632.3863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3109 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 1583.9111 | 0.2 | 0.3 | 2470.9013 |  |  |  |  | 0 | 5185.7141 | 5185.7141 | 5185.7141 | 5185.7141 | 5185.7141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3110 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 8469.0667 | 0.2 | 0.3 | 13211.744 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3111 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17649.7544 | 0.2 | 0.3 | 27533.6169 |  |  |  |  | 0 | 7641.9635 | 7641.9635 | 7641.9635 | 7641.9635 | 7641.9635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3112 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17646.7857 | 0.2 | 0.3 | 27528.9856 |  |  |  |  | 0 | 2628.9818 | 2628.9818 | 2628.9818 | 2628.9818 | 2628.9818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3113 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 21513.3123 | 0.2 | 0.3 | 33560.7671 |  |  |  |  | 0 | 7945.6046 | 7945.6046 | 7945.6046 | 7945.6046 | 7945.6046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3114 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 2868.5161 | 0.2 | 0.3 | 4474.8852 |  |  |  |  | 0 | 5200.2409 | 5200.2409 | 5200.2409 | 5200.2409 | 5200.2409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3115 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 20382.8375 | 0.2 | 0.3 | 31797.2266 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3116 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 17660.7409 | 0.2 | 0.3 | 27550.7559 |  |  |  |  | 0 | 5200.2708 | 5200.2708 | 5200.2708 | 5200.2708 | 5200.2708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3117 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 22710.4681 | 0.2 | 0.3 | 35428.3302 |  |  |  |  | 0 | 9776.5498 | 9776.5498 | 9776.5498 | 9776.5498 | 9776.5498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3118 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 10955.5935 | 0.2 | 0.3 | 17090.7259 |  |  |  |  | 0 | 5200.1912 | 5200.1912 | 5200.1912 | 5200.1912 | 5200.1912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3119 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 20531.1219 | 0.2 | 0.3 | 32028.5501 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3120 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 2549.7917 | 0.2 | 0.3 | 3977.675 |  |  |  |  | 0 | 5200.1864 | 5200.1864 | 5200.1864 | 5200.1864 | 5200.1864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3121 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 15293.6596 | 0.2 | 0.3 | 23858.109 |  |  |  |  | 0 | 5262.5793 | 5262.5793 | 5262.5793 | 5262.5793 | 5262.5793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3122 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 28314.5936 | 0.2 | 0.3 | 44170.766 |  |  |  |  | 0 | 3840.263 | 3840.263 | 3840.263 | 3840.263 | 3840.263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3123 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 19060.4072 | 0.2 | 0.3 | 29734.2352 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3124 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 22717.3051 | 0.2 | 0.3 | 35438.996 |  |  |  |  | 0 | 5202.6421 | 5202.6421 | 5202.6421 | 5202.6421 | 5202.6421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3125 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 21450.1852 | 0.2 | 0.3 | 33462.2889 |  |  |  |  | 0 | 1387.8716 | 1387.8716 | 1387.8716 | 1387.8716 | 1387.8716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3126 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 28244.7591 | 0.2 | 0.3 | 44061.8241 |  |  |  |  | 0 | 8426.7941 | 8426.7941 | 8426.7941 | 8426.7941 | 8426.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3127 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16796.3855 | 0.2 | 0.3 | 26202.3614 |  |  |  |  | 0 | 5234.0542 | 5234.0542 | 5234.0542 | 5234.0542 | 5234.0542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3128 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 23371.8621 | 0.2 | 0.3 | 36460.1048 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3129 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 22612.2422 | 0.2 | 0.3 | 35275.0978 |  |  |  |  | 0 | 6914.4571 | 6914.4571 | 6914.4571 | 6914.4571 | 6914.4571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3130 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16189.5573 | 0.2 | 0.3 | 25255.7093 |  |  |  |  | 0 | 8082.6669 | 8082.6669 | 8082.6669 | 8082.6669 | 8082.6669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3131 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 740.238 | 0.2 | 0.3 | 1154.7713 |  |  |  |  | 0 | 9755.235 | 9755.235 | 9755.235 | 9755.235 | 9755.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3132 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 30485.2689 | 0.2 | 0.3 | 47557.0194 |  |  |  |  | 0 | 9776.4637 | 9776.4637 | 9776.4637 | 9776.4637 | 9776.4637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3133 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 24563.2586 | 0.2 | 0.3 | 38318.6834 |  |  |  |  | 0 | 9800.3353 | 9800.3353 | 9800.3353 | 9800.3353 | 9800.3353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3134 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17638.7354 | 0.2 | 0.3 | 27516.4272 |  |  |  |  | 0 | 9757.611 | 9757.611 | 9757.611 | 9757.611 | 9757.611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3135 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 20121.7564 | 0.2 | 0.3 | 31389.94 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3136 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16669.2752 | 0.2 | 0.3 | 26004.0693 |  |  |  |  | 0 | 5200.2884 | 5200.2884 | 5200.2884 | 5200.2884 | 5200.2884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3137 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 9126.8641 | 0.2 | 0.3 | 14237.908 |  |  |  |  | 0 | 9776.51 | 9776.51 | 9776.51 | 9776.51 | 9776.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3138 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 13479.505 | 0.2 | 0.3 | 21028.0278 |  |  |  |  | 0 | 8201.0047 | 8201.0047 | 8201.0047 | 8201.0047 | 8201.0047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3139 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 23394.5316 | 0.2 | 0.3 | 36495.4693 |  |  |  |  | 0 | 5192.0624 | 5192.0624 | 5192.0624 | 5192.0624 | 5192.0624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3140 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 25553.9928 | 0.2 | 0.3 | 39864.2288 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3141 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 22265.6374 | 0.2 | 0.3 | 34734.3943 |  |  |  |  | 0 | 6254.277 | 6254.277 | 6254.277 | 6254.277 | 6254.277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3142 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 22488.5476 | 0.2 | 0.3 | 35082.1343 |  |  |  |  | 0 | 7253.4653 | 7253.4653 | 7253.4653 | 7253.4653 | 7253.4653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3143 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 19699.6343 | 0.2 | 0.3 | 30731.4295 |  |  |  |  | 0 | 5200.1411 | 5200.1411 | 5200.1411 | 5200.1411 | 5200.1411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3144 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 22002.3115 | 0.2 | 0.3 | 34323.6059 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3145 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16673.9559 | 0.2 | 0.3 | 26011.3712 |  |  |  |  | 0 | 5200.2811 | 5200.2811 | 5200.2811 | 5200.2811 | 5200.2811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3146 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 11394.1315 | 0.2 | 0.3 | 17774.8452 |  |  |  |  | 0 | 9776.4674 | 9776.4674 | 9776.4674 | 9776.4674 | 9776.4674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3147 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 2331.8671 | 0.2 | 0.3 | 3637.7127 |  |  |  |  | 0 | 5200.1064 | 5200.1064 | 5200.1064 | 5200.1064 | 5200.1064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3148 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 31269.4484 | 0.2 | 0.3 | 48780.3395 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3149 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 13649.2229 | 0.2 | 0.3 | 21292.7877 |  |  |  |  | 0 | 5200.2834 | 5200.2834 | 5200.2834 | 5200.2834 | 5200.2834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3150 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 16192.6519 | 0.2 | 0.3 | 25260.537 |  |  |  |  | 0 | 8933.9175 | 8933.9175 | 8933.9175 | 8933.9175 | 8933.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3151 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 28102.9421 | 0.2 | 0.3 | 43840.5896 |  |  |  |  | 0 | 7185.6104 | 7185.6104 | 7185.6104 | 7185.6104 | 7185.6104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3152 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 9.5339 | 0.2 | 0.3 | 14.8729 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3153 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 24698.4565 | 0.2 | 0.3 | 38529.5922 |  |  |  |  | 0 | 5200.3252 | 5200.3252 | 5200.3252 | 5200.3252 | 5200.3252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3154 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 22471.7129 | 0.2 | 0.3 | 35055.8721 |  |  |  |  | 0 | 5810.8318 | 5810.8318 | 5810.8318 | 5810.8318 | 5810.8318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3155 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 18445.4601 | 0.2 | 0.3 | 28774.9178 |  |  |  |  | 0 | 7741.4773 | 7741.4773 | 7741.4773 | 7741.4773 | 7741.4773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3156 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 2505.6169 | 0.2 | 0.3 | 3908.7623 |  |  |  |  | 0 | 4929.6093 | 4929.6093 | 4929.6093 | 4929.6093 | 4929.6093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3157 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 16680.3934 | 0.2 | 0.3 | 26021.4137 |  |  |  |  | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3158 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 16675.6244 | 0.2 | 0.3 | 26013.9741 |  |  |  |  | 0 | 5106.0258 | 5106.0258 | 5106.0258 | 5106.0258 | 5106.0258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3159 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 21322.4003 | 0.2 | 0.3 | 33262.9445 |  |  |  |  | 0 | 105.7748 | 105.7748 | 105.7748 | 105.7748 | 105.7748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3160 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 25950.9741 | 0.2 | 0.3 | 40483.5195 |  |  |  |  | 0 | 4212.6761 | 4212.6761 | 4212.6761 | 4212.6761 | 4212.6761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3161 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 11821.1198 | 0.2 | 0.3 | 18440.9469 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3162 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 9933.1886 | 0.2 | 0.3 | 15495.7742 |  |  |  |  | 0 | 5200.3207 | 5200.3207 | 5200.3207 | 5200.3207 | 5200.3207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3163 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 24656.6733 | 0.2 | 0.3 | 38464.4103 |  |  |  |  | 0 | 9838.9344 | 9838.9344 | 9838.9344 | 9838.9344 | 9838.9344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3164 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 21723.819 | 0.2 | 0.3 | 33889.1576 |  |  |  |  | 0 | 5487.3047 | 5487.3047 | 5487.3047 | 5487.3047 | 5487.3047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3165 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 8151.8064 | 0.2 | 0.3 | 12716.818 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3166 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 18109.9683 | 0.2 | 0.3 | 28251.5506 |  |  |  |  | 0 | 5557.2436 | 5557.2436 | 5557.2436 | 5557.2436 | 5557.2436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3167 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 17011.5129 | 0.2 | 0.3 | 26537.9602 |  |  |  |  | 0 | 4439.7611 | 4439.7611 | 4439.7611 | 4439.7611 | 4439.7611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3168 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 36054.7008 | 0.2 | 0.3 | 56245.3332 |  |  |  |  | 0 | 7665.6693 | 7665.6693 | 7665.6693 | 7665.6693 | 7665.6693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3169 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 23401.0727 | 0.2 | 0.3 | 36505.6734 |  |  |  |  | 0 | 5200.2684 | 5200.2684 | 5200.2684 | 5200.2684 | 5200.2684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3170 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16676.7159 | 0.2 | 0.3 | 26015.6768 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3171 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16676.9893 | 0.2 | 0.3 | 26016.1033 |  |  |  |  | 0 | 5200.3373 | 5200.3373 | 5200.3373 | 5200.3373 | 5200.3373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3172 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 8624.6763 | 8624.6763 | 8624.6763 | 8624.6763 | 8624.6763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3173 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 19103.1234 | 0.2 | 0.3 | 29800.8725 |  |  |  |  | 0 | 8632.1069 | 8632.1069 | 8632.1069 | 8632.1069 | 8632.1069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3174 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 8841.9687 | 0.2 | 0.3 | 13793.4711 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3175 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16681.1303 | 0.2 | 0.3 | 26022.5633 |  |  |  |  | 0 | 5200.3148 | 5200.3148 | 5200.3148 | 5200.3148 | 5200.3148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3176 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 7827.8924 | 7827.8924 | 7827.8924 | 7827.8924 | 7827.8924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3177 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31359.6743 | 0.2 | 0.3 | 48921.092 |  |  |  |  | 0 | 5200.0955 | 5200.0955 | 5200.0955 | 5200.0955 | 5200.0955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3178 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16675.4891 | 0.2 | 0.3 | 26013.7629 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3179 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16676.3125 | 0.2 | 0.3 | 26015.0474 |  |  |  |  | 0 | 4825.2588 | 4825.2588 | 4825.2588 | 4825.2588 | 4825.2588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3180 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 8210.1171 | 0.2 | 0.3 | 12807.7827 |  |  |  |  | 0 | 9220.8465 | 9220.8465 | 9220.8465 | 9220.8465 | 9220.8465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3181 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 2165.1337 | 0.2 | 0.3 | 3377.6085 |  |  |  |  | 0 | 8445.9091 | 8445.9091 | 8445.9091 | 8445.9091 | 8445.9091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3182 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 21801.1485 | 0.2 | 0.3 | 34009.7917 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3183 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 14809.5249 | 0.2 | 0.3 | 23102.8588 |  |  |  |  | 0 | 5200.1897 | 5200.1897 | 5200.1897 | 5200.1897 | 5200.1897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3184 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 23004.5601 | 0.2 | 0.3 | 35887.1137 |  |  |  |  | 0 | 7370.4026 | 7370.4026 | 7370.4026 | 7370.4026 | 7370.4026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3185 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 17243.0895 | 0.2 | 0.3 | 26899.2197 |  |  |  |  | 0 | 9321.9637 | 9321.9637 | 9321.9637 | 9321.9637 | 9321.9637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3186 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16716.0684 | 0.2 | 0.3 | 26077.0667 |  |  |  |  | 0 | 7248.7913 | 7248.7913 | 7248.7913 | 7248.7913 | 7248.7913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3187 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 21223.4553 | 0.2 | 0.3 | 33108.5903 |  |  |  |  | 0 | 4849.6095 | 4849.6095 | 4849.6095 | 4849.6095 | 4849.6095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3188 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 21340.8391 | 0.2 | 0.3 | 33291.709 |  |  |  |  | 0 | 8093.0985 | 8093.0985 | 8093.0985 | 8093.0985 | 8093.0985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3189 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16988.3072 | 0.2 | 0.3 | 26501.7592 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3190 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 3375.6329 | 0.2 | 0.3 | 5265.9874 |  |  |  |  | 0 | 3077.1128 | 3077.1128 | 3077.1128 | 3077.1128 | 3077.1128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3191 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16726.6197 | 0.2 | 0.3 | 26093.5268 |  |  |  |  | 0 | 8968.7429 | 8968.7429 | 8968.7429 | 8968.7429 | 8968.7429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3192 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 23859.4511 | 0.2 | 0.3 | 37220.7438 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3193 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 20479.9011 | 0.2 | 0.3 | 31948.6458 |  |  |  |  | 0 | 7361.6509 | 7361.6509 | 7361.6509 | 7361.6509 | 7361.6509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3194 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 25453.9181 | 0.2 | 0.3 | 39708.1122 |  |  |  |  | 0 | 4297.1419 | 4297.1419 | 4297.1419 | 4297.1419 | 4297.1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3195 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16690.4281 | 0.2 | 0.3 | 26037.0679 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3196 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 19166.8359 | 0.2 | 0.3 | 29900.2641 |  |  |  |  | 0 | 4734.8405 | 4734.8405 | 4734.8405 | 4734.8405 | 4734.8405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3197 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 17353.3864 | 0.2 | 0.3 | 27071.2828 |  |  |  |  | 0 | 7600.9631 | 7600.9631 | 7600.9631 | 7600.9631 | 7600.9631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3198 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 2532.953 | 0.2 | 0.3 | 3951.4067 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3199 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 20939.2181 | 0.2 | 0.3 | 32665.1802 |  |  |  |  | 0 | 7239.2838 | 7239.2838 | 7239.2838 | 7239.2838 | 7239.2838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3200 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 14810.2133 | 0.2 | 0.3 | 23103.9327 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3201 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16820.1065 | 0.2 | 0.3 | 26239.3661 |  |  |  |  | 0 | 5201.6987 | 5201.6987 | 5201.6987 | 5201.6987 | 5201.6987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3202 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 20619.6132 | 0.2 | 0.3 | 32166.5966 |  |  |  |  | 0 | 5287.0267 | 5287.0267 | 5287.0267 | 5287.0267 | 5287.0267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3203 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 12572.9186 | 0.2 | 0.3 | 19613.753 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3204 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 17471.0473 | 0.2 | 0.3 | 27254.8337 |  |  |  |  | 0 | 4615.9856 | 4615.9856 | 4615.9856 | 4615.9856 | 4615.9856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3205 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 14588.8238 | 0.2 | 0.3 | 22758.5651 |  |  |  |  | 0 | 5563.0761 | 5563.0761 | 5563.0761 | 5563.0761 | 5563.0761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3206 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 19088.6179 | 0.2 | 0.3 | 29778.244 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3207 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 24449.7213 | 0.2 | 0.3 | 38141.5652 |  |  |  |  | 0 | 5201.7892 | 5201.7892 | 5201.7892 | 5201.7892 | 5201.7892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3208 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 31199.3207 | 0.2 | 0.3 | 48670.9403 |  |  |  |  | 0 | 4988.7715 | 4988.7715 | 4988.7715 | 4988.7715 | 4988.7715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3209 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 14053.8724 | 0.2 | 0.3 | 21924.0409 |  |  |  |  | 0 | 5201.1694 | 5201.1694 | 5201.1694 | 5201.1694 | 5201.1694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3210 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16586.273 | 0.2 | 0.3 | 25874.5859 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3211 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 12297.5713 | 0.2 | 0.3 | 19184.2113 |  |  |  |  | 0 | 8454.7207 | 8454.7207 | 8454.7207 | 8454.7207 | 8454.7207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3212 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 5732.9855 | 0.2 | 0.3 | 8943.4573 |  |  |  |  | 0 | 5307.1092 | 5307.1092 | 5307.1092 | 5307.1092 | 5307.1092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3213 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17287.2387 | 0.2 | 0.3 | 26968.0924 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3214 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 5629.4793 | 0.2 | 0.3 | 8781.9877 |  |  |  |  | 0 | 7963.887 | 7963.887 | 7963.887 | 7963.887 | 7963.887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3215 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 15829.4996 | 0.2 | 0.3 | 24694.0194 |  |  |  |  | 0 | 5235.3317 | 5235.3317 | 5235.3317 | 5235.3317 | 5235.3317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3216 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 21070.9175 | 0.2 | 0.3 | 32870.6314 |  |  |  |  | 0 | 4733.6533 | 4733.6533 | 4733.6533 | 4733.6533 | 4733.6533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3217 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16934.9383 | 0.2 | 0.3 | 26418.5038 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3218 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 24579.0354 | 0.2 | 0.3 | 38343.2952 |  |  |  |  | 0 | 9779.1018 | 9779.1018 | 9779.1018 | 9779.1018 | 9779.1018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3219 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 6309.4611 | 0.2 | 0.3 | 9842.7594 |  |  |  |  | 0 | 5206.0538 | 5206.0538 | 5206.0538 | 5206.0538 | 5206.0538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3220 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 18671.2229 | 0.2 | 0.3 | 29127.1078 |  |  |  |  | 0 | 6476.1221 | 6476.1221 | 6476.1221 | 6476.1221 | 6476.1221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3221 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 9000.043 | 0.2 | 0.3 | 14040.0671 |  |  |  |  | 0 | 5059.4925 | 5059.4925 | 5059.4925 | 5059.4925 | 5059.4925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3222 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 22101.2905 | 0.2 | 0.3 | 34478.0131 |  |  |  |  | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3223 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 29000.0668 | 0.2 | 0.3 | 45240.1042 |  |  |  |  | 0 | 9779.1822 | 9779.1822 | 9779.1822 | 9779.1822 | 9779.1822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3224 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 18112.808 | 0.2 | 0.3 | 28255.9805 |  |  |  |  | 0 | 5201.518 | 5201.518 | 5201.518 | 5201.518 | 5201.518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3225 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 8933.5343 | 0.2 | 0.3 | 13936.3136 |  |  |  |  | 0 | 5201.6739 | 5201.6739 | 5201.6739 | 5201.6739 | 5201.6739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3226 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 11473.4469 | 0.2 | 0.3 | 17898.5771 |  |  |  |  | 0 | 2998.0075 | 2998.0075 | 2998.0075 | 2998.0075 | 2998.0075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3227 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 19765.2455 | 0.2 | 0.3 | 30833.783 |  |  |  |  | 0 | 4474.8807 | 4474.8807 | 4474.8807 | 4474.8807 | 4474.8807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3228 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 5201.4223 | 5201.4223 | 5201.4223 | 5201.4223 | 5201.4223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3229 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 18952.1058 | 0.2 | 0.3 | 29565.285 |  |  |  |  | 0 | 6884.8467 | 6884.8467 | 6884.8467 | 6884.8467 | 6884.8467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3230 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 16147.569 | 0.2 | 0.3 | 25190.2076 |  |  |  |  | 0 | 5201.597 | 5201.597 | 5201.597 | 5201.597 | 5201.597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3231 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 1315.0615 | 0.2 | 0.3 | 2051.4959 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3232 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 20793.0877 | 0.2 | 0.3 | 32437.2168 |  |  |  |  | 0 | 5378.9891 | 5378.9891 | 5378.9891 | 5378.9891 | 5378.9891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3233 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 17186.7046 | 0.2 | 0.3 | 26811.2592 |  |  |  |  | 0 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3234 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16751.8815 | 0.2 | 0.3 | 26132.9352 |  |  |  |  | 0 | 5697.3302 | 5697.3302 | 5697.3302 | 5697.3302 | 5697.3302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3235 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 31154.4218 | 0.2 | 0.3 | 48600.898 |  |  |  |  | 0 | 6739.477 | 6739.477 | 6739.477 | 6739.477 | 6739.477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3236 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 14419.3041 | 0.2 | 0.3 | 22494.1143 |  |  |  |  | 0 | 6742.2752 | 6742.2752 | 6742.2752 | 6742.2752 | 6742.2752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3237 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 24986.3271 | 0.2 | 0.3 | 38978.6703 |  |  |  |  | 0 | 9802.1379 | 9802.1379 | 9802.1379 | 9802.1379 | 9802.1379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3238 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 27631.4114 | 0.2 | 0.3 | 43105.0018 |  |  |  |  | 0 | 5200.0191 | 5200.0191 | 5200.0191 | 5200.0191 | 5200.0191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3239 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 8029.5203 | 0.2 | 0.3 | 12526.0517 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3240 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 23841.2303 | 0.2 | 0.3 | 37192.3192 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3241 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 22534.2619 | 0.2 | 0.3 | 35153.4486 |  |  |  |  | 0 | 5200.0295 | 5200.0295 | 5200.0295 | 5200.0295 | 5200.0295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3242 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 23584.4793 | 0.2 | 0.3 | 36791.7877 |  |  |  |  | 0 | 9058.6224 | 9058.6224 | 9058.6224 | 9058.6224 | 9058.6224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3243 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 18039.6769 | 0.2 | 0.3 | 28141.8959 |  |  |  |  | 0 | 4356.03 | 4356.03 | 4356.03 | 4356.03 | 4356.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3244 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 19606.6423 | 0.2 | 0.3 | 30586.3619 |  |  |  |  | 0 | 5325.0098 | 5325.0098 | 5325.0098 | 5325.0098 | 5325.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3245 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 16678.1802 | 0.2 | 0.3 | 26017.9611 |  |  |  |  | 0 | 9696.7012 | 9696.7012 | 9696.7012 | 9696.7012 | 9696.7012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3246 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 5200.1942 | 5200.1942 | 5200.1942 | 5200.1942 | 5200.1942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3247 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 10738.1481 | 0.2 | 0.3 | 16751.5111 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3248 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 25361.9303 | 0.2 | 0.3 | 39564.6113 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3249 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 15821.9666 | 0.2 | 0.3 | 24682.2679 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3250 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 22042.9239 | 0.2 | 0.3 | 34386.9612 |  |  |  |  | 0 | 3797.1531 | 3797.1531 | 3797.1531 | 3797.1531 | 3797.1531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3251 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 15056.8489 | 0.2 | 0.3 | 23488.6843 |  |  |  |  | 0 | 4798.2981 | 4798.2981 | 4798.2981 | 4798.2981 | 4798.2981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3252 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 17966.6801 | 0.2 | 0.3 | 28028.0209 |  |  |  |  | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3253 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 16498.9147 | 0.2 | 0.3 | 25738.307 |  |  |  |  | 0 | 9707.4617 | 9707.4617 | 9707.4617 | 9707.4617 | 9707.4617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3254 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 14080.2242 | 0.2 | 0.3 | 21965.1498 |  |  |  |  | 0 | 5200.243 | 5200.243 | 5200.243 | 5200.243 | 5200.243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3255 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 19387.3825 | 0.2 | 0.3 | 30244.3166 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3256 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 29331.5193 | 0.2 | 0.3 | 45757.1702 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3257 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.2935 | 0.2 | 0.3 | 26016.5779 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3258 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.8095 | 0.2 | 0.3 | 26017.3828 |  |  |  |  | 0 | 6619.1935 | 6619.1935 | 6619.1935 | 6619.1935 | 6619.1935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3259 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.7383 | 0.2 | 0.3 | 26017.2718 |  |  |  |  | 0 | 7730.7532 | 7730.7532 | 7730.7532 | 7730.7532 | 7730.7532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3260 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 19772.052 | 0.2 | 0.3 | 30844.4011 |  |  |  |  | 0 | 5499.1586 | 5499.1586 | 5499.1586 | 5499.1586 | 5499.1586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3261 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 14595.9186 | 0.2 | 0.3 | 22769.633 |  |  |  |  | 0 | 9743.5804 | 9743.5804 | 9743.5804 | 9743.5804 | 9743.5804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3262 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16675.7169 | 0.2 | 0.3 | 26014.1184 |  |  |  |  | 0 | 5200.1293 | 5200.1293 | 5200.1293 | 5200.1293 | 5200.1293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3263 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 5200.1928 | 5200.1928 | 5200.1928 | 5200.1928 | 5200.1928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3264 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 6565.8613 | 6565.8613 | 6565.8613 | 6565.8613 | 6565.8613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3265 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.1349 | 0.2 | 0.3 | 26016.3304 |  |  |  |  | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3266 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 28337.9826 | 0.2 | 0.3 | 44207.2529 |  |  |  |  | 0 | 1074.4055 | 1074.4055 | 1074.4055 | 1074.4055 | 1074.4055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3267 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 98.7196 | 0.2 | 0.3 | 154.0026 |  |  |  |  | 0 | 5304.1062 | 5304.1062 | 5304.1062 | 5304.1062 | 5304.1062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3268 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 3692.8686 | 0.2 | 0.3 | 5760.875 |  |  |  |  | 0 | 5201.4539 | 5201.4539 | 5201.4539 | 5201.4539 | 5201.4539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3269 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 12410.7735 | 0.2 | 0.3 | 19360.8067 |  |  |  |  | 0 | 1499.0213 | 1499.0213 | 1499.0213 | 1499.0213 | 1499.0213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3270 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 14678.1112 | 0.2 | 0.3 | 22897.8535 |  |  |  |  | 0 | 3833.6664 | 3833.6664 | 3833.6664 | 3833.6664 | 3833.6664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3271 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 23861.6299 | 0.2 | 0.3 | 37224.1426 |  |  |  |  | 0 | 6030.5048 | 6030.5048 | 6030.5048 | 6030.5048 | 6030.5048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3272 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 13275.9285 | 0.2 | 0.3 | 20710.4484 |  |  |  |  | 0 | 5199.9829 | 5199.9829 | 5199.9829 | 5199.9829 | 5199.9829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3273 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 17332.0823 | 0.2 | 0.3 | 27038.0483 |  |  |  |  | 0 | 5200.0296 | 5200.0296 | 5200.0296 | 5200.0296 | 5200.0296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3274 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 15785.3829 | 0.2 | 0.3 | 24625.1973 |  |  |  |  | 0 | 9777.2641 | 9777.2641 | 9777.2641 | 9777.2641 | 9777.2641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3275 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 9469.9515 | 0.2 | 0.3 | 14773.1243 |  |  |  |  | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3276 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 18900.7797 | 0.2 | 0.3 | 29485.2164 |  |  |  |  | 0 | 5267.4493 | 5267.4493 | 5267.4493 | 5267.4493 | 5267.4493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3277 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 9119.9188 | 0.2 | 0.3 | 14227.0733 |  |  |  |  | 0 | 7305.4114 | 7305.4114 | 7305.4114 | 7305.4114 | 7305.4114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3278 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 3658.268 | 0.2 | 0.3 | 5706.8981 |  |  |  |  | 0 | 5200.2675 | 5200.2675 | 5200.2675 | 5200.2675 | 5200.2675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3279 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 8338.2352 | 0.2 | 0.3 | 13007.6469 |  |  |  |  | 0 | 8951.8479 | 8951.8479 | 8951.8479 | 8951.8479 | 8951.8479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3280 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 23412.4787 | 0.2 | 0.3 | 36523.4667 |  |  |  |  | 0 | 9796.0151 | 9796.0151 | 9796.0151 | 9796.0151 | 9796.0151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3281 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 16705.1953 | 0.2 | 0.3 | 26060.1047 |  |  |  |  | 0 | 5200.5132 | 5200.5132 | 5200.5132 | 5200.5132 | 5200.5132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3282 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 16703.6243 | 0.2 | 0.3 | 26057.654 |  |  |  |  | 0 | 5200.3436 | 5200.3436 | 5200.3436 | 5200.3436 | 5200.3436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3283 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 5557.5331 | 0.2 | 0.3 | 8669.7517 |  |  |  |  | 0 | 8316.7933 | 8316.7933 | 8316.7933 | 8316.7933 | 8316.7933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3284 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 24051.0943 | 0.2 | 0.3 | 37519.7071 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3285 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 19061.3301 | 0.2 | 0.3 | 29735.675 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3286 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 7281.5379 | 0.2 | 0.3 | 11359.1991 |  |  |  |  | 0 | 5201.6283 | 5201.6283 | 5201.6283 | 5201.6283 | 5201.6283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3287 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 11009.5839 | 0.2 | 0.3 | 17174.9508 |  |  |  |  | 0 | 9218.4423 | 9218.4423 | 9218.4423 | 9218.4423 | 9218.4423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3288 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 23086.5575 | 0.2 | 0.3 | 36015.0298 |  |  |  |  | 0 | 9272.8972 | 9272.8972 | 9272.8972 | 9272.8972 | 9272.8972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3289 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 25959.863 | 0.2 | 0.3 | 40497.3863 |  |  |  |  | 0 | 8677.4658 | 8677.4658 | 8677.4658 | 8677.4658 | 8677.4658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3290 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 20529.8328 | 0.2 | 0.3 | 32026.5392 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3291 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 14376.6245 | 0.2 | 0.3 | 22427.5342 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3292 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 21404.3191 | 0.2 | 0.3 | 33390.7377 |  |  |  |  | 0 | 9306.0747 | 9306.0747 | 9306.0747 | 9306.0747 | 9306.0747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3293 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 19095.1751 | 0.2 | 0.3 | 29788.4732 |  |  |  |  | 0 | 5674.4416 | 5674.4416 | 5674.4416 | 5674.4416 | 5674.4416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3294 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 24449.0871 | 0.2 | 0.3 | 38140.5759 |  |  |  |  | 0 | 5200.1223 | 5200.1223 | 5200.1223 | 5200.1223 | 5200.1223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3295 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 1410.071 | 0.2 | 0.3 | 2199.7108 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3296 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 8.3207 | 0.2 | 0.3 | 12.9803 |  |  |  |  | 0 | 7412.1069 | 7412.1069 | 7412.1069 | 7412.1069 | 7412.1069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3297 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 19434.7493 | 0.2 | 0.3 | 30318.2089 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3298 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 21648.661 | 0.2 | 0.3 | 33771.9112 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3299 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 18055.7415 | 0.2 | 0.3 | 28166.9568 |  |  |  |  | 0 | 9713.1902 | 9713.1902 | 9713.1902 | 9713.1902 | 9713.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3300 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 14762.4143 | 0.2 | 0.3 | 23029.3663 |  |  |  |  | 0 | 9849.0562 | 9849.0562 | 9849.0562 | 9849.0562 | 9849.0562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3301 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 30683.1215 | 0.2 | 0.3 | 47865.6696 |  |  |  |  | 0 | 5200.3085 | 5200.3085 | 5200.3085 | 5200.3085 | 5200.3085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3302 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 4376.7338 | 0.2 | 0.3 | 6827.7047 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3303 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 17551.4184 | 0.2 | 0.3 | 27380.2127 |  |  |  |  | 0 | 7165.5919 | 7165.5919 | 7165.5919 | 7165.5919 | 7165.5919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3304 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 16678.0219 | 0.2 | 0.3 | 26017.7142 |  |  |  |  | 0 | 9021.9877 | 9021.9877 | 9021.9877 | 9021.9877 | 9021.9877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3305 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 16677.8095 | 0.2 | 0.3 | 26017.3828 |  |  |  |  | 0 | 9917.8694 | 9917.8694 | 9917.8694 | 9917.8694 | 9917.8694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3306 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 16678.4118 | 0.2 | 0.3 | 26018.3224 |  |  |  |  | 0 | 9528.3097 | 9528.3097 | 9528.3097 | 9528.3097 | 9528.3097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3307 | PEMBROKE PINES | 110309 | Public | 2036 | 5 | Swales | 66.6667 | 12484.1415 | 0.2 | 0.3 | 19475.2607 |  |  |  |  | 0 | 5200.2796 | 5200.2796 | 5200.2796 | 5200.2796 | 5200.2796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3308 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 18231.8497 | 0.2 | 0.3 | 28441.6855 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3309 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16872.5099 | 0.2 | 0.3 | 26321.1155 |  |  |  |  | 0 | 9562.4556 | 9562.4556 | 9562.4556 | 9562.4556 | 9562.4556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3310 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 10276.8819 | 0.2 | 0.3 | 16031.9358 |  |  |  |  | 0 | 5412.2471 | 5412.2471 | 5412.2471 | 5412.2471 | 5412.2471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3311 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 17001.1647 | 0.2 | 0.3 | 26521.817 |  |  |  |  | 0 | 5200.1751 | 5200.1751 | 5200.1751 | 5200.1751 | 5200.1751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3312 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 17242.968 | 0.2 | 0.3 | 26899.0301 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3313 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 6350.6751 | 0.2 | 0.3 | 9907.0531 |  |  |  |  | 0 | 5307.573 | 5307.573 | 5307.573 | 5307.573 | 5307.573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3314 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 13229.7885 | 0.2 | 0.3 | 20638.4701 |  |  |  |  | 0 | 2632.1228 | 2632.1228 | 2632.1228 | 2632.1228 | 2632.1228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3315 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 15153.7662 | 0.2 | 0.3 | 23639.8753 |  |  |  |  | 0 | 5242.5831 | 5242.5831 | 5242.5831 | 5242.5831 | 5242.5831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3316 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 19713.7023 | 0.2 | 0.3 | 30753.3755 |  |  |  |  | 0 | 5507.3899 | 5507.3899 | 5507.3899 | 5507.3899 | 5507.3899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3317 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 2910.7104 | 0.2 | 0.3 | 4540.7082 |  |  |  |  | 0 | 5458.3566 | 5458.3566 | 5458.3566 | 5458.3566 | 5458.3566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3318 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 19569.4987 | 0.2 | 0.3 | 30528.418 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3319 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 8085.3345 | 0.2 | 0.3 | 12613.1219 |  |  |  |  | 0 | 9695.3749 | 9695.3749 | 9695.3749 | 9695.3749 | 9695.3749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3320 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 33285.3383 | 0.2 | 0.3 | 51925.1278 |  |  |  |  | 0 | 5285.3277 | 5285.3277 | 5285.3277 | 5285.3277 | 5285.3277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3321 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 3422.1689 | 0.2 | 0.3 | 5338.5834 |  |  |  |  | 0 | 5200.116 | 5200.116 | 5200.116 | 5200.116 | 5200.116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3322 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 21639.8798 | 0.2 | 0.3 | 33758.2125 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3323 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 14594.7505 | 0.2 | 0.3 | 22767.8107 |  |  |  |  | 0 | 5200.1632 | 5200.1632 | 5200.1632 | 5200.1632 | 5200.1632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3324 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 11941.2925 | 0.2 | 0.3 | 18628.4162 |  |  |  |  | 0 | 5202.9713 | 5202.9713 | 5202.9713 | 5202.9713 | 5202.9713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3325 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 1299.3189 | 0.2 | 0.3 | 2026.9375 |  |  |  |  | 0 | 2593.2621 | 2593.2621 | 2593.2621 | 2593.2621 | 2593.2621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3326 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16181.2437 | 0.2 | 0.3 | 25242.7402 |  |  |  |  | 0 | 16.0865 | 16.0865 | 16.0865 | 16.0865 | 16.0865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3327 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 20643.5515 | 0.2 | 0.3 | 32203.9403 |  |  |  |  | 0 | 5655.4274 | 5655.4274 | 5655.4274 | 5655.4274 | 5655.4274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3328 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16675.4102 | 0.2 | 0.3 | 26013.6399 |  |  |  |  | 0 | 9977.9942 | 9977.9942 | 9977.9942 | 9977.9942 | 9977.9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3329 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16675.6223 | 0.2 | 0.3 | 26013.9707 |  |  |  |  | 0 | 9759.593 | 9759.593 | 9759.593 | 9759.593 | 9759.593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3330 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16675.8453 | 0.2 | 0.3 | 26014.3187 |  |  |  |  | 0 | 7316.563 | 7316.563 | 7316.563 | 7316.563 | 7316.563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3331 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 20613.7774 | 0.2 | 0.3 | 32157.4927 |  |  |  |  | 0 | 7733.6549 | 7733.6549 | 7733.6549 | 7733.6549 | 7733.6549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3332 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 7568.6578 | 0.2 | 0.3 | 11807.1062 |  |  |  |  | 0 | 9389.583 | 9389.583 | 9389.583 | 9389.583 | 9389.583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3333 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16748.2472 | 0.2 | 0.3 | 26127.2656 |  |  |  |  | 0 | 9377.5249 | 9377.5249 | 9377.5249 | 9377.5249 | 9377.5249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3334 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.2627 | 0.2 | 0.3 | 26016.5298 |  |  |  |  | 0 | 5640.711 | 5640.711 | 5640.711 | 5640.711 | 5640.711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3335 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31360.0745 | 0.2 | 0.3 | 48921.7162 |  |  |  |  | 0 | 9932.095 | 9932.095 | 9932.095 | 9932.095 | 9932.095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3336 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.8143 | 0.2 | 0.3 | 26020.5103 |  |  |  |  | 0 | 3699.2802 | 3699.2802 | 3699.2802 | 3699.2802 | 3699.2802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3337 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2479 | 0.2 | 0.3 | 26021.1867 |  |  |  |  | 0 | 3702.9468 | 3702.9468 | 3702.9468 | 3702.9468 | 3702.9468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3338 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 17670.0707 | 0.2 | 0.3 | 27565.3103 |  |  |  |  | 0 | 6890.7525 | 6890.7525 | 6890.7525 | 6890.7525 | 6890.7525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3339 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 19344.4528 | 0.2 | 0.3 | 30177.3464 |  |  |  |  | 0 | 6332.4303 | 6332.4303 | 6332.4303 | 6332.4303 | 6332.4303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3340 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.6137 | 0.2 | 0.3 | 26018.6374 |  |  |  |  | 0 | 5207.0933 | 5207.0933 | 5207.0933 | 5207.0933 | 5207.0933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3341 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16676.7159 | 0.2 | 0.3 | 26015.6768 |  |  |  |  | 0 | 5206.16 | 5206.16 | 5206.16 | 5206.16 | 5206.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3342 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16676.7159 | 0.2 | 0.3 | 26015.6768 |  |  |  |  | 0 | 5203.4837 | 5203.4837 | 5203.4837 | 5203.4837 | 5203.4837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3343 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.4003 | 0.2 | 0.3 | 26016.7445 |  |  |  |  | 0 | 5180.5253 | 5180.5253 | 5180.5253 | 5180.5253 | 5180.5253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3344 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 22562.0654 | 0.2 | 0.3 | 35196.822 |  |  |  |  | 0 | 22.2397 | 22.2397 | 22.2397 | 22.2397 | 22.2397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3345 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 8669.8862 | 0.2 | 0.3 | 13525.0225 |  |  |  |  | 0 | 5206.8277 | 5206.8277 | 5206.8277 | 5206.8277 | 5206.8277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3346 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 16898.1982 | 0.2 | 0.3 | 26361.1892 |  |  |  |  | 0 | 5203.5526 | 5203.5526 | 5203.5526 | 5203.5526 | 5203.5526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3347 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 16671.6685 | 0.2 | 0.3 | 26007.8029 |  |  |  |  | 0 | 5203.2862 | 5203.2862 | 5203.2862 | 5203.2862 | 5203.2862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3348 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 22295.4869 | 0.2 | 0.3 | 34780.9595 |  |  |  |  | 0 | 3168.2185 | 3168.2185 | 3168.2185 | 3168.2185 | 3168.2185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3349 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 8.0955 | 0.2 | 0.3 | 12.629 |  |  |  |  | 0 | 2034.458 | 2034.458 | 2034.458 | 2034.458 | 2034.458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3350 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 4744.3699 | 0.2 | 0.3 | 7401.217 |  |  |  |  | 0 | 9779.653 | 9779.653 | 9779.653 | 9779.653 | 9779.653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3351 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 19891.305 | 0.2 | 0.3 | 31030.4358 |  |  |  |  | 0 | 9780.2923 | 9780.2923 | 9780.2923 | 9780.2923 | 9780.2923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3352 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 17503.6849 | 0.2 | 0.3 | 27305.7484 |  |  |  |  | 0 | 6392.9247 | 6392.9247 | 6392.9247 | 6392.9247 | 6392.9247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3353 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16872.6675 | 0.2 | 0.3 | 26321.3612 |  |  |  |  | 0 | 7510.0757 | 7510.0757 | 7510.0757 | 7510.0757 | 7510.0757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3354 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16856.7217 | 0.2 | 0.3 | 26296.4858 |  |  |  |  | 0 | 7483.8654 | 7483.8654 | 7483.8654 | 7483.8654 | 7483.8654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3355 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 14463.3221 | 0.2 | 0.3 | 22562.7825 |  |  |  |  | 0 | 5211.3146 | 5211.3146 | 5211.3146 | 5211.3146 | 5211.3146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3356 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16590.2056 | 0.2 | 0.3 | 25880.7207 |  |  |  |  | 0 | 5617.9052 | 5617.9052 | 5617.9052 | 5617.9052 | 5617.9052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3357 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 17220.5696 | 0.2 | 0.3 | 26864.0886 |  |  |  |  | 0 | 6261.0383 | 6261.0383 | 6261.0383 | 6261.0383 | 6261.0383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3358 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16132.4337 | 0.2 | 0.3 | 25166.5966 |  |  |  |  | 0 | 5200.2136 | 5200.2136 | 5200.2136 | 5200.2136 | 5200.2136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3359 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 541.0447 | 0.2 | 0.3 | 844.0298 |  |  |  |  | 0 | 6155.0897 | 6155.0897 | 6155.0897 | 6155.0897 | 6155.0897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3360 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 30970.5217 | 0.2 | 0.3 | 48314.0139 |  |  |  |  | 0 | 1421.6505 | 1421.6505 | 1421.6505 | 1421.6505 | 1421.6505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3361 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16674.1219 | 0.2 | 0.3 | 26011.6301 |  |  |  |  | 0 | 5391.7254 | 5391.7254 | 5391.7254 | 5391.7254 | 5391.7254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3362 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.7085 | 0.2 | 0.3 | 26010.9852 |  |  |  |  | 0 | 7711.3294 | 7711.3294 | 7711.3294 | 7711.3294 | 7711.3294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3363 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 6121.2097 | 6121.2097 | 6121.2097 | 6121.2097 | 6121.2097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3364 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16674.3145 | 0.2 | 0.3 | 26011.9306 |  |  |  |  | 0 | 5200.1206 | 5200.1206 | 5200.1206 | 5200.1206 | 5200.1206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3365 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 20042.7074 | 0.2 | 0.3 | 31266.6235 |  |  |  |  | 0 | 5223.8139 | 5223.8139 | 5223.8139 | 5223.8139 | 5223.8139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3366 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 7460.5405 | 0.2 | 0.3 | 11638.4431 |  |  |  |  | 0 | 1889.6092 | 1889.6092 | 1889.6092 | 1889.6092 | 1889.6092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3367 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 13018.0751 | 0.2 | 0.3 | 20308.1971 |  |  |  |  | 0 | 6938.6835 | 6938.6835 | 6938.6835 | 6938.6835 | 6938.6835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3368 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 8338.2787 | 0.2 | 0.3 | 13007.7148 |  |  |  |  | 0 | 8198.1454 | 8198.1454 | 8198.1454 | 8198.1454 | 8198.1454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3369 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 19252.8806 | 0.2 | 0.3 | 30034.4937 |  |  |  |  | 0 | 6765.6926 | 6765.6926 | 6765.6926 | 6765.6926 | 6765.6926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3370 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 16704.5144 | 0.2 | 0.3 | 26059.0425 |  |  |  |  | 0 | 5199.9817 | 5199.9817 | 5199.9817 | 5199.9817 | 5199.9817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3371 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 16703.2359 | 0.2 | 0.3 | 26057.0481 |  |  |  |  | 0 | 5217.0136 | 5217.0136 | 5217.0136 | 5217.0136 | 5217.0136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3372 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 5042.1269 | 0.2 | 0.3 | 7865.7179 |  |  |  |  | 0 | 4257.0641 | 4257.0641 | 4257.0641 | 4257.0641 | 4257.0641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3373 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 381.3118 | 0.2 | 0.3 | 594.8464 |  |  |  |  | 0 | 7185.7861 | 7185.7861 | 7185.7861 | 7185.7861 | 7185.7861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3374 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 18036.0058 | 0.2 | 0.3 | 28136.169 |  |  |  |  | 0 | 7796.599 | 7796.599 | 7796.599 | 7796.599 | 7796.599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3375 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 6599.5172 | 0.2 | 0.3 | 10295.2468 |  |  |  |  | 0 | 9774.7101 | 9774.7101 | 9774.7101 | 9774.7101 | 9774.7101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3376 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17226.201 | 0.2 | 0.3 | 26872.8736 |  |  |  |  | 0 | 5241.2397 | 5241.2397 | 5241.2397 | 5241.2397 | 5241.2397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3377 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 4858.4823 | 0.2 | 0.3 | 7579.2323 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3378 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 8648.5466 | 0.2 | 0.3 | 13491.7327 |  |  |  |  | 0 | 5199.9151 | 5199.9151 | 5199.9151 | 5199.9151 | 5199.9151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3379 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 12713.4964 | 0.2 | 0.3 | 19833.0544 |  |  |  |  | 0 | 8892.3994 | 8892.3994 | 8892.3994 | 8892.3994 | 8892.3994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3380 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 6121.9893 | 0.2 | 0.3 | 9550.3033 |  |  |  |  | 0 | 5448.7667 | 5448.7667 | 5448.7667 | 5448.7667 | 5448.7667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3381 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 19014.7522 | 0.2 | 0.3 | 29663.0134 |  |  |  |  | 0 | 2741.587 | 2741.587 | 2741.587 | 2741.587 | 2741.587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3382 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 28198.1919 | 0.2 | 0.3 | 43989.1793 |  |  |  |  | 0 | 5201.2925 | 5201.2925 | 5201.2925 | 5201.2925 | 5201.2925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3383 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17312.538 | 0.2 | 0.3 | 27007.5593 |  |  |  |  | 0 | 793.6671 | 793.6671 | 793.6671 | 793.6671 | 793.6671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3384 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 7897.9903 | 0.2 | 0.3 | 12320.8649 |  |  |  |  | 0 | 6737.022 | 6737.022 | 6737.022 | 6737.022 | 6737.022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3385 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 23489.5783 | 0.2 | 0.3 | 36643.7422 |  |  |  |  | 0 | 8850.7996 | 8850.7996 | 8850.7996 | 8850.7996 | 8850.7996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3386 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 26590.1255 | 0.2 | 0.3 | 41480.5958 |  |  |  |  | 0 | 7561.1493 | 7561.1493 | 7561.1493 | 7561.1493 | 7561.1493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3387 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 12319.9105 | 0.2 | 0.3 | 19219.0603 |  |  |  |  | 0 | 6143.9428 | 6143.9428 | 6143.9428 | 6143.9428 | 6143.9428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3388 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 12238.3153 | 0.2 | 0.3 | 19091.7718 |  |  |  |  | 0 | 5208.6675 | 5208.6675 | 5208.6675 | 5208.6675 | 5208.6675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3389 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 623.3069 | 0.2 | 0.3 | 972.3588 |  |  |  |  | 0 | 5570.8112 | 5570.8112 | 5570.8112 | 5570.8112 | 5570.8112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3390 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 20485.1269 | 0.2 | 0.3 | 31956.7979 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3391 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 18610.48 | 0.2 | 0.3 | 29032.3488 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3392 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 9532.7566 | 0.2 | 0.3 | 14871.1003 |  |  |  |  | 0 | 9100.7494 | 9100.7494 | 9100.7494 | 9100.7494 | 9100.7494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3393 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 20234.1477 | 0.2 | 0.3 | 31565.2705 |  |  |  |  | 0 | 5383.7797 | 5383.7797 | 5383.7797 | 5383.7797 | 5383.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3394 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 30426.3781 | 0.2 | 0.3 | 47465.1498 |  |  |  |  | 0 | 5431.3126 | 5431.3126 | 5431.3126 | 5431.3126 | 5431.3126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3395 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 97.5533 | 0.2 | 0.3 | 152.1831 |  |  |  |  | 0 | 6519.2801 | 6519.2801 | 6519.2801 | 6519.2801 | 6519.2801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3396 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 778.0479 | 0.2 | 0.3 | 1213.7547 |  |  |  |  | 0 | 9535.5676 | 9535.5676 | 9535.5676 | 9535.5676 | 9535.5676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3397 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 18291.1765 | 0.2 | 0.3 | 28534.2354 |  |  |  |  | 0 | 9776.5203 | 9776.5203 | 9776.5203 | 9776.5203 | 9776.5203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3398 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 20664.8585 | 0.2 | 0.3 | 32237.1792 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3399 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 42685.865 | 0.2 | 0.3 | 66589.9494 |  |  |  |  | 0 | 8465.6774 | 8465.6774 | 8465.6774 | 8465.6774 | 8465.6774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3400 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 26964.0533 | 0.2 | 0.3 | 42063.9232 |  |  |  |  | 0 | 5205.5238 | 5205.5238 | 5205.5238 | 5205.5238 | 5205.5238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3401 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 1708.9575 | 0.2 | 0.3 | 2665.9736 |  |  |  |  | 0 | 8805.4376 | 8805.4376 | 8805.4376 | 8805.4376 | 8805.4376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3402 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 30841.877 | 0.2 | 0.3 | 48113.3281 |  |  |  |  | 0 | 9243.7958 | 9243.7958 | 9243.7958 | 9243.7958 | 9243.7958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3403 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 24603.4985 | 0.2 | 0.3 | 38381.4576 |  |  |  |  | 0 | 5139.9589 | 5139.9589 | 5139.9589 | 5139.9589 | 5139.9589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3404 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 11054.3205 | 0.2 | 0.3 | 17244.74 |  |  |  |  | 0 | 5199.9777 | 5199.9777 | 5199.9777 | 5199.9777 | 5199.9777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3405 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16670.0871 | 0.2 | 0.3 | 26005.3358 |  |  |  |  | 0 | 632.0972 | 632.0972 | 632.0972 | 632.0972 | 632.0972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3406 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16682.1839 | 0.2 | 0.3 | 26024.2069 |  |  |  |  | 0 | 9777.0858 | 9777.0858 | 9777.0858 | 9777.0858 | 9777.0858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3407 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16676.3052 | 0.2 | 0.3 | 26015.0361 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3408 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 8725.5296 | 8725.5296 | 8725.5296 | 8725.5296 | 8725.5296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3409 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16676.4295 | 0.2 | 0.3 | 26015.23 |  |  |  |  | 0 | 5205.4517 | 5205.4517 | 5205.4517 | 5205.4517 | 5205.4517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3410 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 21282.0521 | 0.2 | 0.3 | 33200.0012 |  |  |  |  | 0 | 8078.1905 | 8078.1905 | 8078.1905 | 8078.1905 | 8078.1905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3411 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 19600.3527 | 0.2 | 0.3 | 30576.5502 |  |  |  |  | 0 | 7408.9042 | 7408.9042 | 7408.9042 | 7408.9042 | 7408.9042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3412 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16680.3077 | 0.2 | 0.3 | 26021.2801 |  |  |  |  | 0 | 9776.3977 | 9776.3977 | 9776.3977 | 9776.3977 | 9776.3977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3413 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 7385.3146 | 7385.3146 | 7385.3146 | 7385.3146 | 7385.3146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3414 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31361.7348 | 0.2 | 0.3 | 48924.3063 |  |  |  |  | 0 | 9783.0009 | 9783.0009 | 9783.0009 | 9783.0009 | 9783.0009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3415 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3383 | 0.2 | 0.3 | 26018.2078 |  |  |  |  | 0 | 5200.4533 | 5200.4533 | 5200.4533 | 5200.4533 | 5200.4533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3416 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 5200.1053 | 5200.1053 | 5200.1053 | 5200.1053 | 5200.1053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3417 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 27715.6099 | 0.2 | 0.3 | 43236.3514 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3418 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 18611.6945 | 0.2 | 0.3 | 29034.2435 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3419 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.369 | 0.2 | 0.3 | 26019.8156 |  |  |  |  | 0 | 9788.0824 | 9788.0824 | 9788.0824 | 9788.0824 | 9788.0824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3420 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4499 | 0.2 | 0.3 | 26019.9419 |  |  |  |  | 0 | 5274.8344 | 5274.8344 | 5274.8344 | 5274.8344 | 5274.8344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3421 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.1765 | 0.2 | 0.3 | 26019.5153 |  |  |  |  | 0 | 41.8769 | 41.8769 | 41.8769 | 41.8769 | 41.8769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3422 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16680.3147 | 0.2 | 0.3 | 26021.291 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3423 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 23371.1119 | 0.2 | 0.3 | 36458.9346 |  |  |  |  | 0 | 2633.5772 | 2633.5772 | 2633.5772 | 2633.5772 | 2633.5772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3424 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0251 | 0.2 | 0.3 | 26000.5592 |  |  |  |  | 0 | 3094.9089 | 3094.9089 | 3094.9089 | 3094.9089 | 3094.9089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3425 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 4008.5061 | 4008.5061 | 4008.5061 | 4008.5061 | 4008.5061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3426 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 9441.1813 | 9441.1813 | 9441.1813 | 9441.1813 | 9441.1813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3427 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 18572.793 | 0.2 | 0.3 | 28973.5571 |  |  |  |  | 0 | 5318.0975 | 5318.0975 | 5318.0975 | 5318.0975 | 5318.0975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3428 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 19607.8184 | 0.2 | 0.3 | 30588.1967 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3429 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 1416.8713 | 0.2 | 0.3 | 2210.3192 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3430 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 29522.2304 | 0.2 | 0.3 | 46054.6794 |  |  |  |  | 0 | 8027.5529 | 8027.5529 | 8027.5529 | 8027.5529 | 8027.5529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3431 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 24130.1379 | 0.2 | 0.3 | 37643.0152 |  |  |  |  | 0 | 2271.0423 | 2271.0423 | 2271.0423 | 2271.0423 | 2271.0423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3432 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 16668.1075 | 0.2 | 0.3 | 26002.2478 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3433 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 20310.4486 | 0.2 | 0.3 | 31684.2998 |  |  |  |  | 0 | 3659.5278 | 3659.5278 | 3659.5278 | 3659.5278 | 3659.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3434 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 10714.3191 | 0.2 | 0.3 | 16714.3377 |  |  |  |  | 0 | 2105.2409 | 2105.2409 | 2105.2409 | 2105.2409 | 2105.2409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3435 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 24509.8539 | 0.2 | 0.3 | 38235.3721 |  |  |  |  | 0 | 1191.5352 | 1191.5352 | 1191.5352 | 1191.5352 | 1191.5352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3436 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 8268.2018 | 0.2 | 0.3 | 12898.3948 |  |  |  |  | 0 | 5106.9339 | 5106.9339 | 5106.9339 | 5106.9339 | 5106.9339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3437 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 5988.3937 | 0.2 | 0.3 | 9341.8941 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3438 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 9040.4242 | 0.2 | 0.3 | 14103.0618 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3439 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 7634.8803 | 0.2 | 0.3 | 11910.4133 |  |  |  |  | 0 | 5858.5982 | 5858.5982 | 5858.5982 | 5858.5982 | 5858.5982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3440 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16892.8343 | 0.2 | 0.3 | 26352.8216 |  |  |  |  | 0 | 3874.3812 | 3874.3812 | 3874.3812 | 3874.3812 | 3874.3812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3441 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 30718.7497 | 0.2 | 0.3 | 47921.2495 |  |  |  |  | 0 | 2307.4467 | 2307.4467 | 2307.4467 | 2307.4467 | 2307.4467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3442 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16779.0659 | 0.2 | 0.3 | 26175.3429 |  |  |  |  | 0 | 3403.6698 | 3403.6698 | 3403.6698 | 3403.6698 | 3403.6698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3443 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 16936.7546 | 0.2 | 0.3 | 26421.3372 |  |  |  |  | 0 | 5200.4187 | 5200.4187 | 5200.4187 | 5200.4187 | 5200.4187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3444 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 28803.4725 | 0.2 | 0.3 | 44933.4172 |  |  |  |  | 0 | 7247.5466 | 7247.5466 | 7247.5466 | 7247.5466 | 7247.5466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3445 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 14166.6229 | 0.2 | 0.3 | 22099.9318 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3446 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17732.4119 | 0.2 | 0.3 | 27662.5625 |  |  |  |  | 0 | 5200.0301 | 5200.0301 | 5200.0301 | 5200.0301 | 5200.0301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3447 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 6821.0536 | 0.2 | 0.3 | 10640.8436 |  |  |  |  | 0 | 5451.5395 | 5451.5395 | 5451.5395 | 5451.5395 | 5451.5395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3448 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 21468.8866 | 0.2 | 0.3 | 33491.4631 |  |  |  |  | 0 | 2684.9937 | 2684.9937 | 2684.9937 | 2684.9937 | 2684.9937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3449 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 470.9004 | 0.2 | 0.3 | 734.6046 |  |  |  |  | 0 | 7674.1947 | 7674.1947 | 7674.1947 | 7674.1947 | 7674.1947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3450 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 19652.0161 | 0.2 | 0.3 | 30657.1452 |  |  |  |  | 0 | 6721.6516 | 6721.6516 | 6721.6516 | 6721.6516 | 6721.6516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3451 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 13141.0085 | 0.2 | 0.3 | 20499.9732 |  |  |  |  | 0 | 7396.7898 | 7396.7898 | 7396.7898 | 7396.7898 | 7396.7898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3452 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 22218.3453 | 0.2 | 0.3 | 34660.6186 |  |  |  |  | 0 | 7579.5299 | 7579.5299 | 7579.5299 | 7579.5299 | 7579.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3453 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 12571.1717 | 0.2 | 0.3 | 19611.0279 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3454 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 15005.4809 | 0.2 | 0.3 | 23408.5503 |  |  |  |  | 0 | 5200.1315 | 5200.1315 | 5200.1315 | 5200.1315 | 5200.1315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3455 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 21620.8761 | 0.2 | 0.3 | 33728.5668 |  |  |  |  | 0 | 5491.7342 | 5491.7342 | 5491.7342 | 5491.7342 | 5491.7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3456 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 2124.5405 | 0.2 | 0.3 | 3314.2832 |  |  |  |  | 0 | 8098.5084 | 8098.5084 | 8098.5084 | 8098.5084 | 8098.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3457 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 21888.3315 | 0.2 | 0.3 | 34145.7971 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3458 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16723.7285 | 0.2 | 0.3 | 26089.0164 |  |  |  |  | 0 | 7447.1619 | 7447.1619 | 7447.1619 | 7447.1619 | 7447.1619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3459 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 18781.8161 | 0.2 | 0.3 | 29299.6332 |  |  |  |  | 0 | 7535.1795 | 7535.1795 | 7535.1795 | 7535.1795 | 7535.1795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3460 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 7504.4258 | 0.2 | 0.3 | 11706.9042 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3461 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 19440.8176 | 0.2 | 0.3 | 30327.6755 |  |  |  |  | 0 | 5200.2862 | 5200.2862 | 5200.2862 | 5200.2862 | 5200.2862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3462 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 14903.5476 | 0.2 | 0.3 | 23249.5343 |  |  |  |  | 0 | 5269.5296 | 5269.5296 | 5269.5296 | 5269.5296 | 5269.5296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3463 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 17850.8327 | 0.2 | 0.3 | 27847.299 |  |  |  |  | 0 | 9062.0622 | 9062.0622 | 9062.0622 | 9062.0622 | 9062.0622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3464 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 14401.8661 | 0.2 | 0.3 | 22466.9112 |  |  |  |  | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3465 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 17517.1467 | 0.2 | 0.3 | 27326.7488 |  |  |  |  | 0 | 5399.7131 | 5399.7131 | 5399.7131 | 5399.7131 | 5399.7131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3466 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16854.2684 | 0.2 | 0.3 | 26292.6587 |  |  |  |  | 0 | 9681.7714 | 9681.7714 | 9681.7714 | 9681.7714 | 9681.7714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3467 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 7462.5187 | 0.2 | 0.3 | 11641.5291 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3468 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 24186.605 | 0.2 | 0.3 | 37731.1038 |  |  |  |  | 0 | 5200.1367 | 5200.1367 | 5200.1367 | 5200.1367 | 5200.1367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3469 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 17897.1959 | 0.2 | 0.3 | 27919.6257 |  |  |  |  | 0 | 8480.4173 | 8480.4173 | 8480.4173 | 8480.4173 | 8480.4173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3470 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16774.8357 | 0.2 | 0.3 | 26168.7436 |  |  |  |  | 0 | 4728.4325 | 4728.4325 | 4728.4325 | 4728.4325 | 4728.4325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3471 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 17741.2948 | 0.2 | 0.3 | 27676.4199 |  |  |  |  | 0 | 5195.9786 | 5195.9786 | 5195.9786 | 5195.9786 | 5195.9786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3472 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16554.2199 | 0.2 | 0.3 | 25824.583 |  |  |  |  | 0 | 9831.0672 | 9831.0672 | 9831.0672 | 9831.0672 | 9831.0672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3473 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 16883.3882 | 0.2 | 0.3 | 26338.0856 |  |  |  |  | 0 | 9236.6054 | 9236.6054 | 9236.6054 | 9236.6054 | 9236.6054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3474 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 16714.0304 | 0.2 | 0.3 | 26073.8874 |  |  |  |  | 0 | 8125.1512 | 8125.1512 | 8125.1512 | 8125.1512 | 8125.1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3475 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 1310.0901 | 0.2 | 0.3 | 2043.7406 |  |  |  |  | 0 | 4668.3017 | 4668.3017 | 4668.3017 | 4668.3017 | 4668.3017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3476 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 22918.6634 | 0.2 | 0.3 | 35753.1149 |  |  |  |  | 0 | 1772.1116 | 1772.1116 | 1772.1116 | 1772.1116 | 1772.1116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3477 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 653.6878 | 0.2 | 0.3 | 1019.753 |  |  |  |  | 0 | 471.5467 | 471.5467 | 471.5467 | 471.5467 | 471.5467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3478 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 32359.8238 | 0.2 | 0.3 | 50481.3251 |  |  |  |  | 0 | 4.0302 | 4.0302 | 4.0302 | 4.0302 | 4.0302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3479 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 17621.0998 | 0.2 | 0.3 | 27488.9157 |  |  |  |  | 0 | 5223.8349 | 5223.8349 | 5223.8349 | 5223.8349 | 5223.8349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3480 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 19580.0075 | 0.2 | 0.3 | 30544.8118 |  |  |  |  | 0 | 1077.3163 | 1077.3163 | 1077.3163 | 1077.3163 | 1077.3163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3481 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 1881.3168 | 0.2 | 0.3 | 2934.8542 |  |  |  |  | 0 | 5236.7243 | 5236.7243 | 5236.7243 | 5236.7243 | 5236.7243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3482 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16682.7307 | 0.2 | 0.3 | 26025.0599 |  |  |  |  | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3483 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 22440.5903 | 0.2 | 0.3 | 35007.3209 |  |  |  |  | 0 | 5200.4628 | 5200.4628 | 5200.4628 | 5200.4628 | 5200.4628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3484 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 25246.5393 | 0.2 | 0.3 | 39384.6013 |  |  |  |  | 0 | 5200.0628 | 5200.0628 | 5200.0628 | 5200.0628 | 5200.0628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3485 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16624.8619 | 0.2 | 0.3 | 25934.7845 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3486 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16679.5891 | 0.2 | 0.3 | 26020.159 |  |  |  |  | 0 | 5200.5005 | 5200.5005 | 5200.5005 | 5200.5005 | 5200.5005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3487 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.7773 | 0.2 | 0.3 | 26018.8926 |  |  |  |  | 0 | 1484.0577 | 1484.0577 | 1484.0577 | 1484.0577 | 1484.0577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3488 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4499 | 0.2 | 0.3 | 26019.9419 |  |  |  |  | 0 | 7333.0337 | 7333.0337 | 7333.0337 | 7333.0337 | 7333.0337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3489 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4101 | 0.2 | 0.3 | 26019.8797 |  |  |  |  | 0 | 4214.6697 | 4214.6697 | 4214.6697 | 4214.6697 | 4214.6697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3490 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31364.603 | 0.2 | 0.3 | 48928.7807 |  |  |  |  | 0 | 5200.0616 | 5200.0616 | 5200.0616 | 5200.0616 | 5200.0616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3491 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 5200.5807 | 5200.5807 | 5200.5807 | 5200.5807 | 5200.5807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3492 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 25849.6278 | 0.2 | 0.3 | 40325.4194 |  |  |  |  | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3493 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16673.0429 | 0.2 | 0.3 | 26009.947 |  |  |  |  | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3494 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3495 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31357.5013 | 0.2 | 0.3 | 48917.7021 |  |  |  |  | 0 | 6828.3131 | 6828.3131 | 6828.3131 | 6828.3131 | 6828.3131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3496 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.5163 | 0.2 | 0.3 | 26020.0455 |  |  |  |  | 0 | 7283.7159 | 7283.7159 | 7283.7159 | 7283.7159 | 7283.7159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3497 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 8992.4064 | 8992.4064 | 8992.4064 | 8992.4064 | 8992.4064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3498 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 22034.0824 | 0.2 | 0.3 | 34373.1685 |  |  |  |  | 0 | 9792.1892 | 9792.1892 | 9792.1892 | 9792.1892 | 9792.1892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3499 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16672.4535 | 0.2 | 0.3 | 26009.0275 |  |  |  |  | 0 | 9534.915 | 9534.915 | 9534.915 | 9534.915 | 9534.915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3500 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31361.4433 | 0.2 | 0.3 | 48923.8516 |  |  |  |  | 0 | 9270.35 | 9270.35 | 9270.35 | 9270.35 | 9270.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3501 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.6173 | 0.2 | 0.3 | 26018.6429 |  |  |  |  | 0 | 9777.2461 | 9777.2461 | 9777.2461 | 9777.2461 | 9777.2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3502 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.9031 | 0.2 | 0.3 | 26019.0889 |  |  |  |  | 0 | 9777.2149 | 9777.2149 | 9777.2149 | 9777.2149 | 9777.2149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3503 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2359 |  |  |  |  | 0 | 7119.9254 | 7119.9254 | 7119.9254 | 7119.9254 | 7119.9254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3504 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.4529 | 0.2 | 0.3 | 26018.3866 |  |  |  |  | 0 | 5562.0942 | 5562.0942 | 5562.0942 | 5562.0942 | 5562.0942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3505 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31351.8744 | 0.2 | 0.3 | 48908.9241 |  |  |  |  | 0 | 4860.1619 | 4860.1619 | 4860.1619 | 4860.1619 | 4860.1619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3506 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 17748.3313 | 0.2 | 0.3 | 27687.3969 |  |  |  |  | 0 | 2910.7347 | 2910.7347 | 2910.7347 | 2910.7347 | 2910.7347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3507 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 25430.3355 | 0.2 | 0.3 | 39671.3234 |  |  |  |  | 0 | 2744.084 | 2744.084 | 2744.084 | 2744.084 | 2744.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3508 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 28119.9851 | 0.2 | 0.3 | 43867.1768 |  |  |  |  | 0 | 5200.7721 | 5200.7721 | 5200.7721 | 5200.7721 | 5200.7721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3509 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 24887.3595 | 0.2 | 0.3 | 38824.2808 |  |  |  |  | 0 | 5201.9991 | 5201.9991 | 5201.9991 | 5201.9991 | 5201.9991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3510 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 10584.7079 | 0.2 | 0.3 | 16512.1444 |  |  |  |  | 0 | 9798.0877 | 9798.0877 | 9798.0877 | 9798.0877 | 9798.0877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3511 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 27446.3787 | 0.2 | 0.3 | 42816.3508 |  |  |  |  | 0 | 9822.0869 | 9822.0869 | 9822.0869 | 9822.0869 | 9822.0869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3512 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 10703.2179 | 0.2 | 0.3 | 16697.02 |  |  |  |  | 0 | 4645.6503 | 4645.6503 | 4645.6503 | 4645.6503 | 4645.6503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3513 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 14428.0713 | 0.2 | 0.3 | 22507.7912 |  |  |  |  | 0 | 5200.2859 | 5200.2859 | 5200.2859 | 5200.2859 | 5200.2859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3514 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 12549.9481 | 0.2 | 0.3 | 19577.9191 |  |  |  |  | 0 | 8869.4106 | 8869.4106 | 8869.4106 | 8869.4106 | 8869.4106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3515 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 21496.4789 | 0.2 | 0.3 | 33534.507 |  |  |  |  | 0 | 9777.0974 | 9777.0974 | 9777.0974 | 9777.0974 | 9777.0974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3516 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 6687.7964 | 0.2 | 0.3 | 10432.9624 |  |  |  |  | 0 | 9779.1538 | 9779.1538 | 9779.1538 | 9779.1538 | 9779.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3517 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 10145.7997 | 0.2 | 0.3 | 15827.4475 |  |  |  |  | 0 | 8855.2282 | 8855.2282 | 8855.2282 | 8855.2282 | 8855.2282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3518 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 30090.7607 | 0.2 | 0.3 | 46941.5866 |  |  |  |  | 0 | 1486.5693 | 1486.5693 | 1486.5693 | 1486.5693 | 1486.5693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3519 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 21397.928 | 0.2 | 0.3 | 33380.7677 |  |  |  |  | 0 | 4557.0809 | 4557.0809 | 4557.0809 | 4557.0809 | 4557.0809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3520 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 31386.0994 | 0.2 | 0.3 | 48962.3151 |  |  |  |  | 0 | 8745.2203 | 8745.2203 | 8745.2203 | 8745.2203 | 8745.2203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3521 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 20114.5773 | 0.2 | 0.3 | 31378.7405 |  |  |  |  | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3522 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 23519.1595 | 0.2 | 0.3 | 36689.8888 |  |  |  |  | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3523 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17764.4415 | 0.2 | 0.3 | 27712.5287 |  |  |  |  | 0 | 8466.8056 | 8466.8056 | 8466.8056 | 8466.8056 | 8466.8056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3524 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 24073.4488 | 0.2 | 0.3 | 37554.5801 |  |  |  |  | 0 | 5201.5177 | 5201.5177 | 5201.5177 | 5201.5177 | 5201.5177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3525 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 11173.7703 | 0.2 | 0.3 | 17431.0816 |  |  |  |  | 0 | 5201.9676 | 5201.9676 | 5201.9676 | 5201.9676 | 5201.9676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3526 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 20947.3877 | 0.2 | 0.3 | 32677.9248 |  |  |  |  | 0 | 8667.8274 | 8667.8274 | 8667.8274 | 8667.8274 | 8667.8274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3527 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 7443.003 | 0.2 | 0.3 | 11611.0847 |  |  |  |  | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3528 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 19135.232 | 0.2 | 0.3 | 29850.9619 |  |  |  |  | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3529 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16680.9923 | 0.2 | 0.3 | 26022.3479 |  |  |  |  | 0 | 8576.4143 | 8576.4143 | 8576.4143 | 8576.4143 | 8576.4143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3530 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 15879.5381 | 0.2 | 0.3 | 24772.0794 |  |  |  |  | 0 | 5200.8123 | 5200.8123 | 5200.8123 | 5200.8123 | 5200.8123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3531 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 9284.2485 | 0.2 | 0.3 | 14483.4276 |  |  |  |  | 0 | 5200.7827 | 5200.7827 | 5200.7827 | 5200.7827 | 5200.7827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3532 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 24258.3955 | 0.2 | 0.3 | 37843.0969 |  |  |  |  | 0 | 7278.1481 | 7278.1481 | 7278.1481 | 7278.1481 | 7278.1481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3533 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 20715.1423 | 0.2 | 0.3 | 32315.622 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3534 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17120.7978 | 0.2 | 0.3 | 26708.4446 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3535 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 24770.5214 | 0.2 | 0.3 | 38642.0134 |  |  |  |  | 0 | 9961.7422 | 9961.7422 | 9961.7422 | 9961.7422 | 9961.7422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3536 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16789.0809 | 0.2 | 0.3 | 26190.9662 |  |  |  |  | 0 | 9778.5052 | 9778.5052 | 9778.5052 | 9778.5052 | 9778.5052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3537 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 6802.1594 | 0.2 | 0.3 | 10611.3687 |  |  |  |  | 0 | 9336.7699 | 9336.7699 | 9336.7699 | 9336.7699 | 9336.7699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3538 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 9418.1298 | 0.2 | 0.3 | 14692.2825 |  |  |  |  | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3539 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 18283.1437 | 0.2 | 0.3 | 28521.7042 |  |  |  |  | 0 | 5200.9786 | 5200.9786 | 5200.9786 | 5200.9786 | 5200.9786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3540 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 17415.0411 | 0.2 | 0.3 | 27167.4641 |  |  |  |  | 0 | 5200.5585 | 5200.5585 | 5200.5585 | 5200.5585 | 5200.5585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3541 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 6630.3917 | 0.2 | 0.3 | 10343.4111 |  |  |  |  | 0 | 5201.335 | 5201.335 | 5201.335 | 5201.335 | 5201.335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3542 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 17302.6092 | 0.2 | 0.3 | 26992.0704 |  |  |  |  | 0 | 9777.877 | 9777.877 | 9777.877 | 9777.877 | 9777.877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3543 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 7980.2449 | 0.2 | 0.3 | 12449.1821 |  |  |  |  | 0 | 9786.131 | 9786.131 | 9786.131 | 9786.131 | 9786.131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3544 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 1833.9558 | 0.2 | 0.3 | 2860.971 |  |  |  |  | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3545 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 7066.511 | 0.2 | 0.3 | 11023.7572 |  |  |  |  | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3546 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 28116.8319 | 0.2 | 0.3 | 43862.2578 |  |  |  |  | 0 | 9342.1996 | 9342.1996 | 9342.1996 | 9342.1996 | 9342.1996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3547 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 5643.9103 | 0.2 | 0.3 | 8804.5 |  |  |  |  | 0 | 9778.5667 | 9778.5667 | 9778.5667 | 9778.5667 | 9778.5667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3548 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 9409.9614 | 0.2 | 0.3 | 14679.5398 |  |  |  |  | 0 | 5231.534 | 5231.534 | 5231.534 | 5231.534 | 5231.534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3549 | PEMBROKE PINES | 110339 | Public | 2036 | 5 | Swales | 66.6667 | 34.8179 | 0.2 | 0.3 | 54.3159 |  |  |  |  | 0 | 2282.1905 | 2282.1905 | 2282.1905 | 2282.1905 | 2282.1905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3550 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 28017.1985 | 0.2 | 0.3 | 43706.8296 |  |  |  |  | 0 | 5201.5411 | 5201.5411 | 5201.5411 | 5201.5411 | 5201.5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3551 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 5367.0173 | 0.2 | 0.3 | 8372.547 |  |  |  |  | 0 | 5243.6438 | 5243.6438 | 5243.6438 | 5243.6438 | 5243.6438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3552 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 16701.1562 | 0.2 | 0.3 | 26053.8037 |  |  |  |  | 0 | 1932.1311 | 1932.1311 | 1932.1311 | 1932.1311 | 1932.1311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3553 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 5107.4237 | 0.2 | 0.3 | 7967.581 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3554 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 14367.8284 | 0.2 | 0.3 | 22413.8123 |  |  |  |  | 0 | 2600.5014 | 2600.5014 | 2600.5014 | 2600.5014 | 2600.5014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3555 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16722.7495 | 0.2 | 0.3 | 26087.4892 |  |  |  |  | 0 | 6158.2796 | 6158.2796 | 6158.2796 | 6158.2796 | 6158.2796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3556 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 33791.9629 | 0.2 | 0.3 | 52715.4621 |  |  |  |  | 0 | 7364.3027 | 7364.3027 | 7364.3027 | 7364.3027 | 7364.3027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3557 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 15210.8723 | 0.2 | 0.3 | 23728.9608 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3558 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 15741.3643 | 0.2 | 0.3 | 24556.5283 |  |  |  |  | 0 | 5201.7962 | 5201.7962 | 5201.7962 | 5201.7962 | 5201.7962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3559 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16680.2315 | 0.2 | 0.3 | 26021.1612 |  |  |  |  | 0 | 9557.3842 | 9557.3842 | 9557.3842 | 9557.3842 | 9557.3842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3560 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.0693 | 0.2 | 0.3 | 26019.3482 |  |  |  |  | 0 | 9426.0214 | 9426.0214 | 9426.0214 | 9426.0214 | 9426.0214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3561 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 2784.7646 | 2784.7646 | 2784.7646 | 2784.7646 | 2784.7646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3562 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16680.1661 | 0.2 | 0.3 | 26021.0591 |  |  |  |  | 0 | 2602.5013 | 2602.5013 | 2602.5013 | 2602.5013 | 2602.5013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3563 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31357.7192 | 0.2 | 0.3 | 48918.042 |  |  |  |  | 0 | 9778.977 | 9778.977 | 9778.977 | 9778.977 | 9778.977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3564 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.6196 | 0.2 | 0.3 | 26018.6466 |  |  |  |  | 0 | 5016.1415 | 5016.1415 | 5016.1415 | 5016.1415 | 5016.1415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3565 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.9031 | 0.2 | 0.3 | 26019.0888 |  |  |  |  | 0 | 5692.2672 | 5692.2672 | 5692.2672 | 5692.2672 | 5692.2672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3566 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.1765 | 0.2 | 0.3 | 26019.5154 |  |  |  |  | 0 | 2224.4938 | 2224.4938 | 2224.4938 | 2224.4938 | 2224.4938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3567 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.147 | 0.2 | 0.3 | 26019.4693 |  |  |  |  | 0 | 8120.0383 | 8120.0383 | 8120.0383 | 8120.0383 | 8120.0383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3568 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31356.2902 | 0.2 | 0.3 | 48915.8127 |  |  |  |  | 0 | 3131.9692 | 3131.9692 | 3131.9692 | 3131.9692 | 3131.9692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3569 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.0392 | 0.2 | 0.3 | 26017.7412 |  |  |  |  | 0 | 3281.7734 | 3281.7734 | 3281.7734 | 3281.7734 | 3281.7734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3570 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.9031 | 0.2 | 0.3 | 26019.0888 |  |  |  |  | 0 | 9616.909 | 9616.909 | 9616.909 | 9616.909 | 9616.909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3571 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.1765 | 0.2 | 0.3 | 26019.5153 |  |  |  |  | 0 | 2600.6814 | 2600.6814 | 2600.6814 | 2600.6814 | 2600.6814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3572 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.1291 | 0.2 | 0.3 | 26019.4414 |  |  |  |  | 0 | 2697.257 | 2697.257 | 2697.257 | 2697.257 | 2697.257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3573 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31360.7039 | 0.2 | 0.3 | 48922.6981 |  |  |  |  | 0 | 5100.0639 | 5100.0639 | 5100.0639 | 5100.0639 | 5100.0639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3574 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5279 | 0.2 | 0.3 | 26016.9436 |  |  |  |  | 0 | 569.8338 | 569.8338 | 569.8338 | 569.8338 | 569.8338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3575 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.2627 | 0.2 | 0.3 | 26016.5298 |  |  |  |  | 0 | 5878.5959 | 5878.5959 | 5878.5959 | 5878.5959 | 5878.5959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3576 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.2627 | 0.2 | 0.3 | 26016.5298 |  |  |  |  | 0 | 5184.4064 | 5184.4064 | 5184.4064 | 5184.4064 | 5184.4064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3577 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.8255 | 0.2 | 0.3 | 26017.4077 |  |  |  |  | 0 | 7054.2705 | 7054.2705 | 7054.2705 | 7054.2705 | 7054.2705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3578 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 21900.7977 | 0.2 | 0.3 | 34165.2444 |  |  |  |  | 0 | 9258.1193 | 9258.1193 | 9258.1193 | 9258.1193 | 9258.1193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3579 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 17173.7871 | 0.2 | 0.3 | 26791.1078 |  |  |  |  | 0 | 9764.249 | 9764.249 | 9764.249 | 9764.249 | 9764.249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3580 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 29117.2831 | 0.2 | 0.3 | 45422.9616 |  |  |  |  | 0 | 5081.2825 | 5081.2825 | 5081.2825 | 5081.2825 | 5081.2825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3581 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 2597.8551 | 0.2 | 0.3 | 4052.654 |  |  |  |  | 0 | 5120.0927 | 5120.0927 | 5120.0927 | 5120.0927 | 5120.0927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3582 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 22946.6262 | 0.2 | 0.3 | 35796.7369 |  |  |  |  | 0 | 5342.0052 | 5342.0052 | 5342.0052 | 5342.0052 | 5342.0052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3583 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 14256.7493 | 0.2 | 0.3 | 22240.529 |  |  |  |  | 0 | 5202.3286 | 5202.3286 | 5202.3286 | 5202.3286 | 5202.3286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3584 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 3486.526 | 0.2 | 0.3 | 5438.9806 |  |  |  |  | 0 | 5200.2233 | 5200.2233 | 5200.2233 | 5200.2233 | 5200.2233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3585 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 30497.4151 | 0.2 | 0.3 | 47575.9675 |  |  |  |  | 0 | 9577.7865 | 9577.7865 | 9577.7865 | 9577.7865 | 9577.7865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3586 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 14188.1613 | 0.2 | 0.3 | 22133.5317 |  |  |  |  | 0 | 3942.3152 | 3942.3152 | 3942.3152 | 3942.3152 | 3942.3152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3587 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 32672.3001 | 0.2 | 0.3 | 50968.7881 |  |  |  |  | 0 | 5736.7984 | 5736.7984 | 5736.7984 | 5736.7984 | 5736.7984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3588 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 16675.0933 | 0.2 | 0.3 | 26013.1455 |  |  |  |  | 0 | 1006.0402 | 1006.0402 | 1006.0402 | 1006.0402 | 1006.0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3589 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 28927.6758 | 0.2 | 0.3 | 45127.1742 |  |  |  |  | 0 | 10621.4448 | 10621.4448 | 10621.4448 | 10621.4448 | 10621.4448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3590 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 28108.3673 | 0.2 | 0.3 | 43849.053 |  |  |  |  | 0 | 10114.3952 | 10114.3952 | 10114.3952 | 10114.3952 | 10114.3952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3591 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16706.8839 | 0.2 | 0.3 | 26062.7388 |  |  |  |  | 0 | 5681.4094 | 5681.4094 | 5681.4094 | 5681.4094 | 5681.4094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3592 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16745.5616 | 0.2 | 0.3 | 26123.0761 |  |  |  |  | 0 | 5181.4688 | 5181.4688 | 5181.4688 | 5181.4688 | 5181.4688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3593 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 22724.4399 | 0.2 | 0.3 | 35450.1263 |  |  |  |  | 0 | 2533.8859 | 2533.8859 | 2533.8859 | 2533.8859 | 2533.8859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3594 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 17150.2987 | 0.2 | 0.3 | 26754.4659 |  |  |  |  | 0 | 3532.5559 | 3532.5559 | 3532.5559 | 3532.5559 | 3532.5559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3595 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 14348.0817 | 0.2 | 0.3 | 22383.0075 |  |  |  |  | 0 | 5205.7797 | 5205.7797 | 5205.7797 | 5205.7797 | 5205.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3596 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 2338.1085 | 0.2 | 0.3 | 3647.4492 |  |  |  |  | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3597 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16710.7479 | 0.2 | 0.3 | 26068.7667 |  |  |  |  | 0 | 10809.7553 | 10809.7553 | 10809.7553 | 10809.7553 | 10809.7553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3598 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 2101.6753 | 0.2 | 0.3 | 3278.6134 |  |  |  |  | 0 | 5406.4624 | 5406.4624 | 5406.4624 | 5406.4624 | 5406.4624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3599 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 21691.598 | 0.2 | 0.3 | 33838.8929 |  |  |  |  | 0 | 7851.6332 | 7851.6332 | 7851.6332 | 7851.6332 | 7851.6332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3600 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 22481.0566 | 0.2 | 0.3 | 35070.4483 |  |  |  |  | 0 | 7370.4616 | 7370.4616 | 7370.4616 | 7370.4616 | 7370.4616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3601 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 8872.0963 | 0.2 | 0.3 | 13840.4703 |  |  |  |  | 0 | 6779.0824 | 6779.0824 | 6779.0824 | 6779.0824 | 6779.0824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3602 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17052.9229 | 0.2 | 0.3 | 26602.5597 |  |  |  |  | 0 | 2769.5551 | 2769.5551 | 2769.5551 | 2769.5551 | 2769.5551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3603 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16861.7819 | 0.2 | 0.3 | 26304.3798 |  |  |  |  | 0 | 4216.6969 | 4216.6969 | 4216.6969 | 4216.6969 | 4216.6969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3604 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 22426.5289 | 0.2 | 0.3 | 34985.3851 |  |  |  |  | 0 | 5579.7842 | 5579.7842 | 5579.7842 | 5579.7842 | 5579.7842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3605 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 18987.3411 | 0.2 | 0.3 | 29620.2522 |  |  |  |  | 0 | 8446.5614 | 8446.5614 | 8446.5614 | 8446.5614 | 8446.5614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3606 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 6686.8973 | 0.2 | 0.3 | 10431.5598 |  |  |  |  | 0 | 9783.511 | 9783.511 | 9783.511 | 9783.511 | 9783.511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3607 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 10598.1052 | 0.2 | 0.3 | 16533.0441 |  |  |  |  | 0 | 8611.3538 | 8611.3538 | 8611.3538 | 8611.3538 | 8611.3538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3608 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 21570.7971 | 0.2 | 0.3 | 33650.4435 |  |  |  |  | 0 | 8527.5031 | 8527.5031 | 8527.5031 | 8527.5031 | 8527.5031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3609 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17811.3976 | 0.2 | 0.3 | 27785.7803 |  |  |  |  | 0 | 4859.6165 | 4859.6165 | 4859.6165 | 4859.6165 | 4859.6165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3610 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16255.9308 | 0.2 | 0.3 | 25359.252 |  |  |  |  | 0 | 5339.0374 | 5339.0374 | 5339.0374 | 5339.0374 | 5339.0374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3611 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 10496.5227 | 0.2 | 0.3 | 16374.5754 |  |  |  |  | 0 | 9237.9667 | 9237.9667 | 9237.9667 | 9237.9667 | 9237.9667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3612 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16676.1721 | 0.2 | 0.3 | 26014.8285 |  |  |  |  | 0 | 5369.5089 | 5369.5089 | 5369.5089 | 5369.5089 | 5369.5089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3613 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 1255.4802 | 0.2 | 0.3 | 1958.5491 |  |  |  |  | 0 | 12037.1874 | 12037.1874 | 12037.1874 | 12037.1874 | 12037.1874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3614 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 10028.953 | 0.2 | 0.3 | 15645.1667 |  |  |  |  | 0 | 11282.8636 | 11282.8636 | 11282.8636 | 11282.8636 | 11282.8636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3615 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 18977.5496 | 0.2 | 0.3 | 29604.9774 |  |  |  |  | 0 | 4493.5145 | 4493.5145 | 4493.5145 | 4493.5145 | 4493.5145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3616 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 11904.7454 | 0.2 | 0.3 | 18571.4028 |  |  |  |  | 0 | 8710.8724 | 8710.8724 | 8710.8724 | 8710.8724 | 8710.8724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3617 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 11733.7241 | 0.2 | 0.3 | 18304.6096 |  |  |  |  | 0 | 452.3467 | 452.3467 | 452.3467 | 452.3467 | 452.3467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3618 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 13397.8941 | 0.2 | 0.3 | 20900.7147 |  |  |  |  | 0 | 5537.7557 | 5537.7557 | 5537.7557 | 5537.7557 | 5537.7557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3619 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16818.9323 | 0.2 | 0.3 | 26237.5344 |  |  |  |  | 0 | 5201.0853 | 5201.0853 | 5201.0853 | 5201.0853 | 5201.0853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3620 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 19448.5045 | 0.2 | 0.3 | 30339.6671 |  |  |  |  | 0 | 8565.5718 | 8565.5718 | 8565.5718 | 8565.5718 | 8565.5718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3621 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 26648.7239 | 0.2 | 0.3 | 41572.0093 |  |  |  |  | 0 | 7927.0381 | 7927.0381 | 7927.0381 | 7927.0381 | 7927.0381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3622 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7059 | 0.2 | 0.3 | 26000.0613 |  |  |  |  | 0 | 6686.5385 | 6686.5385 | 6686.5385 | 6686.5385 | 6686.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3623 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 7182.9552 | 0.2 | 0.3 | 11205.4101 |  |  |  |  | 0 | 7569.2101 | 7569.2101 | 7569.2101 | 7569.2101 | 7569.2101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3624 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 21584.5517 | 0.2 | 0.3 | 33671.9006 |  |  |  |  | 0 | 7269.3328 | 7269.3328 | 7269.3328 | 7269.3328 | 7269.3328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3625 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16686.5745 | 0.2 | 0.3 | 26031.0562 |  |  |  |  | 0 | 6962.7132 | 6962.7132 | 6962.7132 | 6962.7132 | 6962.7132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3626 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 14146.2147 | 0.2 | 0.3 | 22068.0949 |  |  |  |  | 0 | 1704.8695 | 1704.8695 | 1704.8695 | 1704.8695 | 1704.8695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3627 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 13021.0146 | 0.2 | 0.3 | 20312.7828 |  |  |  |  | 0 | 8006.2703 | 8006.2703 | 8006.2703 | 8006.2703 | 8006.2703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3628 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 805.3809 | 0.2 | 0.3 | 1256.3942 |  |  |  |  | 0 | 8012.1549 | 8012.1549 | 8012.1549 | 8012.1549 | 8012.1549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3629 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 23848.4631 | 0.2 | 0.3 | 37203.6024 |  |  |  |  | 0 | 5371.0087 | 5371.0087 | 5371.0087 | 5371.0087 | 5371.0087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3630 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 17822.4731 | 0.2 | 0.3 | 27803.0581 |  |  |  |  | 0 | 7217.6126 | 7217.6126 | 7217.6126 | 7217.6126 | 7217.6126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3631 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 31801.379 | 0.2 | 0.3 | 49610.1512 |  |  |  |  | 0 | 6287.9501 | 6287.9501 | 6287.9501 | 6287.9501 | 6287.9501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3632 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 22330.0406 | 0.2 | 0.3 | 34834.8633 |  |  |  |  | 0 | 8601.7 | 8601.7 | 8601.7 | 8601.7 | 8601.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3633 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 4127.7601 | 0.2 | 0.3 | 6439.3057 |  |  |  |  | 0 | 9151.053 | 9151.053 | 9151.053 | 9151.053 | 9151.053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3634 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 20065.9293 | 0.2 | 0.3 | 31302.8497 |  |  |  |  | 0 | 9330.4534 | 9330.4534 | 9330.4534 | 9330.4534 | 9330.4534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3635 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16667.3518 | 0.2 | 0.3 | 26001.0688 |  |  |  |  | 0 | 7690.1925 | 7690.1925 | 7690.1925 | 7690.1925 | 7690.1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3636 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 31158.0919 | 0.2 | 0.3 | 48606.6234 |  |  |  |  | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3637 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7947 | 0.2 | 0.3 | 26000.1997 |  |  |  |  | 0 | 9990.185 | 9990.185 | 9990.185 | 9990.185 | 9990.185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3638 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7495 | 0.2 | 0.3 | 26000.1293 |  |  |  |  | 0 | 6432.7475 | 6432.7475 | 6432.7475 | 6432.7475 | 6432.7475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3639 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 24038.5261 | 0.2 | 0.3 | 37500.1007 |  |  |  |  | 0 | 4273.7502 | 4273.7502 | 4273.7502 | 4273.7502 | 4273.7502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3640 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 24576.4525 | 0.2 | 0.3 | 38339.2658 |  |  |  |  | 0 | 5372.1176 | 5372.1176 | 5372.1176 | 5372.1176 | 5372.1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3641 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 23188.6267 | 0.2 | 0.3 | 36174.2577 |  |  |  |  | 0 | 8376.227 | 8376.227 | 8376.227 | 8376.227 | 8376.227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3642 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 4347.3822 | 0.2 | 0.3 | 6781.9162 |  |  |  |  | 0 | 671.47 | 671.47 | 671.47 | 671.47 | 671.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3643 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16983.5115 | 0.2 | 0.3 | 26494.2779 |  |  |  |  | 0 | 7244.9553 | 7244.9553 | 7244.9553 | 7244.9553 | 7244.9553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3644 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6139 | 0.2 | 0.3 | 25999.9177 |  |  |  |  | 0 | 9411.7144 | 9411.7144 | 9411.7144 | 9411.7144 | 9411.7144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3645 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 9310.6854 | 9310.6854 | 9310.6854 | 9310.6854 | 9310.6854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3646 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16666.9848 | 0.2 | 0.3 | 26000.4963 |  |  |  |  | 0 | 5190.8519 | 5190.8519 | 5190.8519 | 5190.8519 | 5190.8519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3647 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 31422.6943 | 0.2 | 0.3 | 49019.4032 |  |  |  |  | 0 | 5196.4818 | 5196.4818 | 5196.4818 | 5196.4818 | 5196.4818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3648 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 16792.0416 | 0.2 | 0.3 | 26195.5849 |  |  |  |  | 0 | 9793.8696 | 9793.8696 | 9793.8696 | 9793.8696 | 9793.8696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3649 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 19246.6091 | 0.2 | 0.3 | 30024.7101 |  |  |  |  | 0 | 5200.8911 | 5200.8911 | 5200.8911 | 5200.8911 | 5200.8911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3650 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 17278.8806 | 0.2 | 0.3 | 26955.0537 |  |  |  |  | 0 | 8165.5828 | 8165.5828 | 8165.5828 | 8165.5828 | 8165.5828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3651 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 29704.2787 | 0.2 | 0.3 | 46338.6747 |  |  |  |  | 0 | 2911.6947 | 2911.6947 | 2911.6947 | 2911.6947 | 2911.6947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3652 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 116.0889 | 0.2 | 0.3 | 181.0986 |  |  |  |  | 0 | 5202.6966 | 5202.6966 | 5202.6966 | 5202.6966 | 5202.6966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3653 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 20196.6193 | 0.2 | 0.3 | 31506.7262 |  |  |  |  | 0 | 5201.0018 | 5201.0018 | 5201.0018 | 5201.0018 | 5201.0018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3654 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 20529.1726 | 0.2 | 0.3 | 32025.5093 |  |  |  |  | 0 | 3185.0894 | 3185.0894 | 3185.0894 | 3185.0894 | 3185.0894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3655 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 16836.5764 | 0.2 | 0.3 | 26265.0592 |  |  |  |  | 0 | 9811.64 | 9811.64 | 9811.64 | 9811.64 | 9811.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3656 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 19592.3473 | 0.2 | 0.3 | 30564.0618 |  |  |  |  | 0 | 9912.5126 | 9912.5126 | 9912.5126 | 9912.5126 | 9912.5126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3657 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 26473.7901 | 0.2 | 0.3 | 41299.1125 |  |  |  |  | 0 | 9587.3549 | 9587.3549 | 9587.3549 | 9587.3549 | 9587.3549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3658 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 16680.1664 | 0.2 | 0.3 | 26021.0596 |  |  |  |  | 0 | 5194.5199 | 5194.5199 | 5194.5199 | 5194.5199 | 5194.5199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3659 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 6691.8098 | 0.2 | 0.3 | 10439.2233 |  |  |  |  | 0 | 6992.2641 | 6992.2641 | 6992.2641 | 6992.2641 | 6992.2641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3660 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 16666.7422 | 0.2 | 0.3 | 26000.1178 |  |  |  |  | 0 | 7785.6433 | 7785.6433 | 7785.6433 | 7785.6433 | 7785.6433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3661 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 28367.3199 | 0.2 | 0.3 | 44253.0191 |  |  |  |  | 0 | 10287.5509 | 10287.5509 | 10287.5509 | 10287.5509 | 10287.5509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3662 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 21044.3319 | 0.2 | 0.3 | 32829.1577 |  |  |  |  | 0 | 5108.2964 | 5108.2964 | 5108.2964 | 5108.2964 | 5108.2964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3663 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 18085.0598 | 0.2 | 0.3 | 28212.6933 |  |  |  |  | 0 | 5213.9576 | 5213.9576 | 5213.9576 | 5213.9576 | 5213.9576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3664 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 7064.7215 | 0.2 | 0.3 | 11020.9655 |  |  |  |  | 0 | 4221.2111 | 4221.2111 | 4221.2111 | 4221.2111 | 4221.2111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3665 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 24546.9837 | 0.2 | 0.3 | 38293.2946 |  |  |  |  | 0 | 10222.8631 | 10222.8631 | 10222.8631 | 10222.8631 | 10222.8631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3666 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 21579.4724 | 0.2 | 0.3 | 33663.9769 |  |  |  |  | 0 | 7949.257 | 7949.257 | 7949.257 | 7949.257 | 7949.257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3667 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 27616.9509 | 0.2 | 0.3 | 43082.4435 |  |  |  |  | 0 | 9003.0403 | 9003.0403 | 9003.0403 | 9003.0403 | 9003.0403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3668 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 20615.4483 | 0.2 | 0.3 | 32160.0993 |  |  |  |  | 0 | 10404.0501 | 10404.0501 | 10404.0501 | 10404.0501 | 10404.0501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3669 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16679.6873 | 0.2 | 0.3 | 26020.3121 |  |  |  |  | 0 | 10140.3274 | 10140.3274 | 10140.3274 | 10140.3274 | 10140.3274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3670 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 15084.6394 | 0.2 | 0.3 | 23532.0375 |  |  |  |  | 0 | 7656.2454 | 7656.2454 | 7656.2454 | 7656.2454 | 7656.2454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3671 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 1592.3075 | 0.2 | 0.3 | 2483.9998 |  |  |  |  | 0 | 7749.9811 | 7749.9811 | 7749.9811 | 7749.9811 | 7749.9811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3672 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 5403.6594 | 0.2 | 0.3 | 8429.7087 |  |  |  |  | 0 | 10356.7942 | 10356.7942 | 10356.7942 | 10356.7942 | 10356.7942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3673 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16698.0197 | 0.2 | 0.3 | 26048.9108 |  |  |  |  | 0 | 47.2228 | 47.2228 | 47.2228 | 47.2228 | 47.2228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3674 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 10785.6985 | 0.2 | 0.3 | 16825.6897 |  |  |  |  | 0 | 9614.6369 | 9614.6369 | 9614.6369 | 9614.6369 | 9614.6369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3675 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17461.0715 | 0.2 | 0.3 | 27239.2715 |  |  |  |  | 0 | 9690.1734 | 9690.1734 | 9690.1734 | 9690.1734 | 9690.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3676 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16863.0031 | 0.2 | 0.3 | 26306.2848 |  |  |  |  | 0 | 10483.3174 | 10483.3174 | 10483.3174 | 10483.3174 | 10483.3174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3677 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 2706.3506 | 0.2 | 0.3 | 4221.9069 |  |  |  |  | 0 | 10406.317 | 10406.317 | 10406.317 | 10406.317 | 10406.317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3678 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 9266.8529 | 0.2 | 0.3 | 14456.2905 |  |  |  |  | 0 | 10670.3951 | 10670.3951 | 10670.3951 | 10670.3951 | 10670.3951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3679 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 25870.6583 | 0.2 | 0.3 | 40358.2269 |  |  |  |  | 0 | 7623.5902 | 7623.5902 | 7623.5902 | 7623.5902 | 7623.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3680 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17432.0277 | 0.2 | 0.3 | 27193.9633 |  |  |  |  | 0 | 16987.2021 | 16987.2021 | 16987.2021 | 16987.2021 | 16987.2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3681 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 8670.0416 | 0.2 | 0.3 | 13525.2649 |  |  |  |  | 0 | 13466.9021 | 13466.9021 | 13466.9021 | 13466.9021 | 13466.9021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3682 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 19231.0261 | 0.2 | 0.3 | 30000.4008 |  |  |  |  | 0 | 5917.0705 | 5917.0705 | 5917.0705 | 5917.0705 | 5917.0705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3683 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 14107.6341 | 0.2 | 0.3 | 22007.9091 |  |  |  |  | 0 | 8899.7476 | 8899.7476 | 8899.7476 | 8899.7476 | 8899.7476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3684 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 12535.4495 | 0.2 | 0.3 | 19555.3013 |  |  |  |  | 0 | 12777.0924 | 12777.0924 | 12777.0924 | 12777.0924 | 12777.0924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3685 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 8760.844 | 0.2 | 0.3 | 13666.9166 |  |  |  |  | 0 | 7983.0923 | 7983.0923 | 7983.0923 | 7983.0923 | 7983.0923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3686 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 14385.335 | 0.2 | 0.3 | 22441.1226 |  |  |  |  | 0 | 8251.2457 | 8251.2457 | 8251.2457 | 8251.2457 | 8251.2457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3687 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 14126.7182 | 0.2 | 0.3 | 22037.6804 |  |  |  |  | 0 | 11565.3771 | 11565.3771 | 11565.3771 | 11565.3771 | 11565.3771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3688 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17455.2892 | 0.2 | 0.3 | 27230.2512 |  |  |  |  | 0 | 15608.6134 | 15608.6134 | 15608.6134 | 15608.6134 | 15608.6134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3689 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 12743.2265 | 0.2 | 0.3 | 19879.4334 |  |  |  |  | 0 | 17562.6413 | 17562.6413 | 17562.6413 | 17562.6413 | 17562.6413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3690 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 23614.0432 | 0.2 | 0.3 | 36837.9074 |  |  |  |  | 0 | 10408.8866 | 10408.8866 | 10408.8866 | 10408.8866 | 10408.8866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3691 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 10258.5041 | 0.2 | 0.3 | 16003.2663 |  |  |  |  | 0 | 11500.1426 | 11500.1426 | 11500.1426 | 11500.1426 | 11500.1426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3692 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 21661.0851 | 0.2 | 0.3 | 33791.2928 |  |  |  |  | 0 | 12803.7896 | 12803.7896 | 12803.7896 | 12803.7896 | 12803.7896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3693 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17490.9593 | 0.2 | 0.3 | 27285.8966 |  |  |  |  | 0 | 10824.9384 | 10824.9384 | 10824.9384 | 10824.9384 | 10824.9384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3694 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 3094.6267 | 0.2 | 0.3 | 4827.6177 |  |  |  |  | 0 | 9530.1185 | 9530.1185 | 9530.1185 | 9530.1185 | 9530.1185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3695 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16228.3121 | 0.2 | 0.3 | 25316.1669 |  |  |  |  | 0 | 5202.4363 | 5202.4363 | 5202.4363 | 5202.4363 | 5202.4363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3696 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 17801.5476 | 0.2 | 0.3 | 27770.4143 |  |  |  |  | 0 | 5632.831 | 5632.831 | 5632.831 | 5632.831 | 5632.831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3697 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 1789.7811 | 0.2 | 0.3 | 2792.0586 |  |  |  |  | 0 | 8746.0969 | 8746.0969 | 8746.0969 | 8746.0969 | 8746.0969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3698 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17542.4362 | 0.2 | 0.3 | 27366.2005 |  |  |  |  | 0 | 10989.8058 | 10989.8058 | 10989.8058 | 10989.8058 | 10989.8058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3699 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16667.5004 | 0.2 | 0.3 | 26001.3006 |  |  |  |  | 0 | 7993.266 | 7993.266 | 7993.266 | 7993.266 | 7993.266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3700 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 9338.9815 | 0.2 | 0.3 | 14568.8112 |  |  |  |  | 0 | 5821.891 | 5821.891 | 5821.891 | 5821.891 | 5821.891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3701 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 21991.9707 | 0.2 | 0.3 | 34307.4743 |  |  |  |  | 0 | 4231.3869 | 4231.3869 | 4231.3869 | 4231.3869 | 4231.3869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3702 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 5898.3984 | 0.2 | 0.3 | 9201.5015 |  |  |  |  | 0 | 6854.0673 | 6854.0673 | 6854.0673 | 6854.0673 | 6854.0673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3703 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 14323.0015 | 0.2 | 0.3 | 22343.8824 |  |  |  |  | 0 | 6007.6569 | 6007.6569 | 6007.6569 | 6007.6569 | 6007.6569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3704 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 12459.3211 | 0.2 | 0.3 | 19436.541 |  |  |  |  | 0 | 7933.5656 | 7933.5656 | 7933.5656 | 7933.5656 | 7933.5656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3705 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 8258.1475 | 0.2 | 0.3 | 12882.71 |  |  |  |  | 0 | 6150.1697 | 6150.1697 | 6150.1697 | 6150.1697 | 6150.1697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3706 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16706.6353 | 0.2 | 0.3 | 26062.351 |  |  |  |  | 0 | 4886.9689 | 4886.9689 | 4886.9689 | 4886.9689 | 4886.9689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3707 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 12184.5248 | 0.2 | 0.3 | 19007.8587 |  |  |  |  | 0 | 12408.0726 | 12408.0726 | 12408.0726 | 12408.0726 | 12408.0726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3708 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16930.5513 | 0.2 | 0.3 | 26411.66 |  |  |  |  | 0 | 5465.1004 | 5465.1004 | 5465.1004 | 5465.1004 | 5465.1004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3709 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 23520.3629 | 0.2 | 0.3 | 36691.7661 |  |  |  |  | 0 | 5242.0077 | 5242.0077 | 5242.0077 | 5242.0077 | 5242.0077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3710 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 10179.6669 | 0.2 | 0.3 | 15880.2803 |  |  |  |  | 0 | 8001.9153 | 8001.9153 | 8001.9153 | 8001.9153 | 8001.9153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3711 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 13006.2281 | 0.2 | 0.3 | 20289.7159 |  |  |  |  | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3712 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 4691.0119 | 0.2 | 0.3 | 7317.9786 |  |  |  |  | 0 | 5200.7567 | 5200.7567 | 5200.7567 | 5200.7567 | 5200.7567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3713 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 9912.7297 | 0.2 | 0.3 | 15463.8583 |  |  |  |  | 0 | 6243.9987 | 6243.9987 | 6243.9987 | 6243.9987 | 6243.9987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3714 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.6258 | 0.2 | 0.3 | 26020.2162 |  |  |  |  | 0 | 929.0422 | 929.0422 | 929.0422 | 929.0422 | 929.0422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3715 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 6681.9906 | 6681.9906 | 6681.9906 | 6681.9906 | 6681.9906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3716 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16680.5953 | 0.2 | 0.3 | 26021.7286 |  |  |  |  | 0 | 4936.3121 | 4936.3121 | 4936.3121 | 4936.3121 | 4936.3121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3717 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 6668.4157 | 0.2 | 0.3 | 10402.7285 |  |  |  |  | 0 | 7909.1463 | 7909.1463 | 7909.1463 | 7909.1463 | 7909.1463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3718 | PEMBROKE PINES | 110312 | Private | 2026 | 5 | Swales | 66.6667 | 25890.1513 | 0.2 | 0.3 | 40388.6361 |  |  |  |  | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3719 | PEMBROKE PINES | 110312 | Private | 2033 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 5200.7406 | 5200.7406 | 5200.7406 | 5200.7406 | 5200.7406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3720 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 26287.7105 | 0.2 | 0.3 | 41008.8283 |  |  |  |  | 0 | 6398.6485 | 6398.6485 | 6398.6485 | 6398.6485 | 6398.6485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3721 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 439.5512 | 439.5512 | 439.5512 | 439.5512 | 439.5512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3722 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 15650.7235 | 0.2 | 0.3 | 24415.1287 |  |  |  |  | 0 | 5838.4039 | 5838.4039 | 5838.4039 | 5838.4039 | 5838.4039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3723 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 14994.1139 | 0.2 | 0.3 | 23390.8177 |  |  |  |  | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3724 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 8086.823 | 0.2 | 0.3 | 12615.4439 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3725 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 11097.3831 | 0.2 | 0.3 | 17311.9177 |  |  |  |  | 0 | 10737.9011 | 10737.9011 | 10737.9011 | 10737.9011 | 10737.9011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3726 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 36640.9678 | 0.2 | 0.3 | 57159.9098 |  |  |  |  | 0 | 10255.617 | 10255.617 | 10255.617 | 10255.617 | 10255.617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3727 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 18994.0115 | 0.2 | 0.3 | 29630.658 |  |  |  |  | 0 | 13507.7383 | 13507.7383 | 13507.7383 | 13507.7383 | 13507.7383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3728 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16672.4248 | 0.2 | 0.3 | 26008.9827 |  |  |  |  | 0 | 7842.5323 | 7842.5323 | 7842.5323 | 7842.5323 | 7842.5323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3729 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 18363.0787 | 0.2 | 0.3 | 28646.4028 |  |  |  |  | 0 | 7801.7601 | 7801.7601 | 7801.7601 | 7801.7601 | 7801.7601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3730 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 13945.9464 | 0.2 | 0.3 | 21755.6764 |  |  |  |  | 0 | 7282.4677 | 7282.4677 | 7282.4677 | 7282.4677 | 7282.4677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3731 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 16870.0508 | 0.2 | 0.3 | 26317.2792 |  |  |  |  | 0 | 6429.3642 | 6429.3642 | 6429.3642 | 6429.3642 | 6429.3642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3732 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 17018.1506 | 0.2 | 0.3 | 26548.3149 |  |  |  |  | 0 | 9758.7729 | 9758.7729 | 9758.7729 | 9758.7729 | 9758.7729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3733 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 17391.8862 | 0.2 | 0.3 | 27131.3425 |  |  |  |  | 0 | 5349.2498 | 5349.2498 | 5349.2498 | 5349.2498 | 5349.2498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3734 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 20387.0437 | 0.2 | 0.3 | 31803.7882 |  |  |  |  | 0 | 9780.2648 | 9780.2648 | 9780.2648 | 9780.2648 | 9780.2648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3735 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 6052.5395 | 0.2 | 0.3 | 9441.9616 |  |  |  |  | 0 | 5201.0501 | 5201.0501 | 5201.0501 | 5201.0501 | 5201.0501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3736 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 13536.6262 | 0.2 | 0.3 | 21117.1369 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3737 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 14385.0409 | 0.2 | 0.3 | 22440.6638 |  |  |  |  | 0 | 5200.7776 | 5200.7776 | 5200.7776 | 5200.7776 | 5200.7776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3738 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 20380.4031 | 0.2 | 0.3 | 31793.4288 |  |  |  |  | 0 | 9004.9346 | 9004.9346 | 9004.9346 | 9004.9346 | 9004.9346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3739 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 30022.3371 | 0.2 | 0.3 | 46834.8459 |  |  |  |  | 0 | 8345.8813 | 8345.8813 | 8345.8813 | 8345.8813 | 8345.8813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3740 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 23900.9553 | 0.2 | 0.3 | 37285.4902 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3741 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 19204.4762 | 0.2 | 0.3 | 29958.9829 |  |  |  |  | 0 | 9779.5004 | 9779.5004 | 9779.5004 | 9779.5004 | 9779.5004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3742 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 5199.9749 | 0.2 | 0.3 | 8111.9609 |  |  |  |  | 0 | 5200.8861 | 5200.8861 | 5200.8861 | 5200.8861 | 5200.8861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3743 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 19136.4457 | 0.2 | 0.3 | 29852.8553 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3744 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 8373.4179 | 0.2 | 0.3 | 13062.532 |  |  |  |  | 0 | 5200.8851 | 5200.8851 | 5200.8851 | 5200.8851 | 5200.8851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3745 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16609.4995 | 0.2 | 0.3 | 25910.8192 |  |  |  |  | 0 | 7640.1549 | 7640.1549 | 7640.1549 | 7640.1549 | 7640.1549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3746 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16580.2144 | 0.2 | 0.3 | 25865.1345 |  |  |  |  | 0 | 8194.5214 | 8194.5214 | 8194.5214 | 8194.5214 | 8194.5214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3747 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 5972.4923 | 0.2 | 0.3 | 9317.0879 |  |  |  |  | 0 | 9778.8655 | 9778.8655 | 9778.8655 | 9778.8655 | 9778.8655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3748 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 18123.5363 | 0.2 | 0.3 | 28272.7166 |  |  |  |  | 0 | 9843.1112 | 9843.1112 | 9843.1112 | 9843.1112 | 9843.1112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3749 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 23976.0031 | 0.2 | 0.3 | 37402.5649 |  |  |  |  | 0 | 5202.6894 | 5202.6894 | 5202.6894 | 5202.6894 | 5202.6894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3750 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16672.8118 | 0.2 | 0.3 | 26009.5864 |  |  |  |  | 0 | 9782.0485 | 9782.0485 | 9782.0485 | 9782.0485 | 9782.0485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3751 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 21598.2929 | 0.2 | 0.3 | 33693.337 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3752 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 18020.3339 | 0.2 | 0.3 | 28111.7208 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3753 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 13075.8133 | 0.2 | 0.3 | 20398.2688 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3754 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 14100.4907 | 0.2 | 0.3 | 21996.7654 |  |  |  |  | 0 | 7859.4237 | 7859.4237 | 7859.4237 | 7859.4237 | 7859.4237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3755 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 5430.9851 | 0.2 | 0.3 | 8472.3368 |  |  |  |  | 0 | 9781.7472 | 9781.7472 | 9781.7472 | 9781.7472 | 9781.7472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3756 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17298.2691 | 0.2 | 0.3 | 26985.2997 |  |  |  |  | 0 | 9779.092 | 9779.092 | 9779.092 | 9779.092 | 9779.092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3757 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16671.8575 | 0.2 | 0.3 | 26008.0978 |  |  |  |  | 0 | 9780.6274 | 9780.6274 | 9780.6274 | 9780.6274 | 9780.6274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3758 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 22121.3646 | 0.2 | 0.3 | 34509.3288 |  |  |  |  | 0 | 9779.1308 | 9779.1308 | 9779.1308 | 9779.1308 | 9779.1308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3759 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 3398.8357 | 0.2 | 0.3 | 5302.1836 |  |  |  |  | 0 | 7961.9085 | 7961.9085 | 7961.9085 | 7961.9085 | 7961.9085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3760 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 18387.1635 | 0.2 | 0.3 | 28683.975 |  |  |  |  | 0 | 5202.0362 | 5202.0362 | 5202.0362 | 5202.0362 | 5202.0362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3761 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 19160.451 | 0.2 | 0.3 | 29890.3036 |  |  |  |  | 0 | 6161.0727 | 6161.0727 | 6161.0727 | 6161.0727 | 6161.0727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3762 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17979.1149 | 0.2 | 0.3 | 28047.4192 |  |  |  |  | 0 | 8915.6834 | 8915.6834 | 8915.6834 | 8915.6834 | 8915.6834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3763 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 4332.2211 | 0.2 | 0.3 | 6758.2649 |  |  |  |  | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3764 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 5066.7376 | 0.2 | 0.3 | 7904.1107 |  |  |  |  | 0 | 5200.9306 | 5200.9306 | 5200.9306 | 5200.9306 | 5200.9306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3765 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 8264.0423 | 0.2 | 0.3 | 12891.906 |  |  |  |  | 0 | 8397.8442 | 8397.8442 | 8397.8442 | 8397.8442 | 8397.8442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3766 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 13973.4445 | 0.2 | 0.3 | 21798.5735 |  |  |  |  | 0 | 5201.8224 | 5201.8224 | 5201.8224 | 5201.8224 | 5201.8224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3767 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 28365.1232 | 0.2 | 0.3 | 44249.5922 |  |  |  |  | 0 | 5201.212 | 5201.212 | 5201.212 | 5201.212 | 5201.212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3768 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 16838.4843 | 0.2 | 0.3 | 26268.0356 |  |  |  |  | 0 | 5201.7514 | 5201.7514 | 5201.7514 | 5201.7514 | 5201.7514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3769 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 16740.166 | 0.2 | 0.3 | 26114.659 |  |  |  |  | 0 | 5201.9804 | 5201.9804 | 5201.9804 | 5201.9804 | 5201.9804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3770 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 17345.2715 | 0.2 | 0.3 | 27058.6235 |  |  |  |  | 0 | 8750.622 | 8750.622 | 8750.622 | 8750.622 | 8750.622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3771 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 12785.7329 | 0.2 | 0.3 | 19945.7433 |  |  |  |  | 0 | 7803.3039 | 7803.3039 | 7803.3039 | 7803.3039 | 7803.3039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3772 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 3324.2503 | 0.2 | 0.3 | 5185.8304 |  |  |  |  | 0 | 8309.2857 | 8309.2857 | 8309.2857 | 8309.2857 | 8309.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3773 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 14762.3945 | 0.2 | 0.3 | 23029.3355 |  |  |  |  | 0 | 14005.54 | 14005.54 | 14005.54 | 14005.54 | 14005.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3774 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 635.6481 | 0.2 | 0.3 | 991.611 |  |  |  |  | 0 | 10402.0305 | 10402.0305 | 10402.0305 | 10402.0305 | 10402.0305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3775 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 18246.4194 | 0.2 | 0.3 | 28464.4143 |  |  |  |  | 0 | 10402.024 | 10402.024 | 10402.024 | 10402.024 | 10402.024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3776 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 18014.2553 | 0.2 | 0.3 | 28102.2382 |  |  |  |  | 0 | 11677.8879 | 11677.8879 | 11677.8879 | 11677.8879 | 11677.8879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3777 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 6599.2869 | 0.2 | 0.3 | 10294.8875 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3778 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 34803.7712 | 0.2 | 0.3 | 54293.8831 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3779 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 7528.1123 | 0.2 | 0.3 | 11743.8551 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3780 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 11286.6468 | 0.2 | 0.3 | 17607.169 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3781 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 15572.9303 | 0.2 | 0.3 | 24293.7713 |  |  |  |  | 0 | 4222.9879 | 4222.9879 | 4222.9879 | 4222.9879 | 4222.9879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3782 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 7514.4831 | 0.2 | 0.3 | 11722.5937 |  |  |  |  | 0 | 11323.3125 | 11323.3125 | 11323.3125 | 11323.3125 | 11323.3125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3783 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 23438.0322 | 0.2 | 0.3 | 36563.3302 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3784 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 22907.6713 | 0.2 | 0.3 | 35735.9672 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3785 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 27508.2694 | 0.2 | 0.3 | 42912.9003 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3786 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 30723.4137 | 0.2 | 0.3 | 47928.5253 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3787 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 18360.5543 | 0.2 | 0.3 | 28642.4648 |  |  |  |  | 0 | 8066.1755 | 8066.1755 | 8066.1755 | 8066.1755 | 8066.1755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3788 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17922.7295 | 0.2 | 0.3 | 27959.458 |  |  |  |  | 0 | 5201.6628 | 5201.6628 | 5201.6628 | 5201.6628 | 5201.6628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3789 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 5685.9106 | 0.2 | 0.3 | 8870.0205 |  |  |  |  | 0 | 5201.1178 | 5201.1178 | 5201.1178 | 5201.1178 | 5201.1178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3790 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 32595.8586 | 0.2 | 0.3 | 50849.5394 |  |  |  |  | 0 | 5201.8529 | 5201.8529 | 5201.8529 | 5201.8529 | 5201.8529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3791 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16812.2764 | 0.2 | 0.3 | 26227.1512 |  |  |  |  | 0 | 5201.7463 | 5201.7463 | 5201.7463 | 5201.7463 | 5201.7463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3792 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 17097.4222 | 0.2 | 0.3 | 26671.9786 |  |  |  |  | 0 | 9231.9163 | 9231.9163 | 9231.9163 | 9231.9163 | 9231.9163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3793 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 18185.3437 | 0.2 | 0.3 | 28369.1362 |  |  |  |  | 0 | 5648.1991 | 5648.1991 | 5648.1991 | 5648.1991 | 5648.1991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3794 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 32703.6387 | 0.2 | 0.3 | 51017.6764 |  |  |  |  | 0 | 9778.1694 | 9778.1694 | 9778.1694 | 9778.1694 | 9778.1694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3795 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 4936.7313 | 0.2 | 0.3 | 7701.3008 |  |  |  |  | 0 | 9820.4982 | 9820.4982 | 9820.4982 | 9820.4982 | 9820.4982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3796 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 17385.8283 | 0.2 | 0.3 | 27121.8921 |  |  |  |  | 0 | 9789.1484 | 9789.1484 | 9789.1484 | 9789.1484 | 9789.1484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3797 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 16643.4309 | 0.2 | 0.3 | 25963.7522 |  |  |  |  | 0 | 9779.8068 | 9779.8068 | 9779.8068 | 9779.8068 | 9779.8068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3798 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 16677.8095 | 0.2 | 0.3 | 26017.3828 |  |  |  |  | 0 | 9944.8854 | 9944.8854 | 9944.8854 | 9944.8854 | 9944.8854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3799 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 13899.8658 | 0.2 | 0.3 | 21683.7906 |  |  |  |  | 0 | 5200.0488 | 5200.0488 | 5200.0488 | 5200.0488 | 5200.0488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3800 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 8926.808 | 0.2 | 0.3 | 13925.8205 |  |  |  |  | 0 | 5201.561 | 5201.561 | 5201.561 | 5201.561 | 5201.561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3801 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 16678.8846 | 0.2 | 0.3 | 26019.06 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3802 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 20779.2401 | 0.2 | 0.3 | 32415.6145 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3803 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 17281.2525 | 0.2 | 0.3 | 26958.754 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3804 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 21806.5788 | 0.2 | 0.3 | 34018.2629 |  |  |  |  | 0 | 11142.0222 | 11142.0222 | 11142.0222 | 11142.0222 | 11142.0222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3805 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16676.752 | 0.2 | 0.3 | 26015.7331 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3806 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16677.2627 | 0.2 | 0.3 | 26016.5298 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3807 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 6575.4984 | 6575.4984 | 6575.4984 | 6575.4984 | 6575.4984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3808 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16677.4333 | 0.2 | 0.3 | 26016.7959 |  |  |  |  | 0 | 9779.1339 | 9779.1339 | 9779.1339 | 9779.1339 | 9779.1339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3809 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 22450.8356 | 0.2 | 0.3 | 35023.3035 |  |  |  |  | 0 | 9779.7244 | 9779.7244 | 9779.7244 | 9779.7244 | 9779.7244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3810 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16679.1811 | 0.2 | 0.3 | 26019.5226 |  |  |  |  | 0 | 9779.5135 | 9779.5135 | 9779.5135 | 9779.5135 | 9779.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3811 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 18566.6925 | 0.2 | 0.3 | 28964.0402 |  |  |  |  | 0 | 9780.7457 | 9780.7457 | 9780.7457 | 9780.7457 | 9780.7457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3812 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16679.5753 | 0.2 | 0.3 | 26020.1374 |  |  |  |  | 0 | 11373.5323 | 11373.5323 | 11373.5323 | 11373.5323 | 11373.5323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3813 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 3443.3044 | 3443.3044 | 3443.3044 | 3443.3044 | 3443.3044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3814 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16680.6147 | 0.2 | 0.3 | 26021.7589 |  |  |  |  | 0 | 5201.2826 | 5201.2826 | 5201.2826 | 5201.2826 | 5201.2826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3815 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 22587.4005 | 0.2 | 0.3 | 35236.3448 |  |  |  |  | 0 | 5201.4056 | 5201.4056 | 5201.4056 | 5201.4056 | 5201.4056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3816 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 27313.0801 | 0.2 | 0.3 | 42608.4049 |  |  |  |  | 0 | 5201.5763 | 5201.5763 | 5201.5763 | 5201.5763 | 5201.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3817 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 15517.4781 | 0.2 | 0.3 | 24207.2659 |  |  |  |  | 0 | 5202.1539 | 5202.1539 | 5202.1539 | 5202.1539 | 5202.1539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3818 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 30702.8316 | 0.2 | 0.3 | 47896.4173 |  |  |  |  | 0 | 5202.5368 | 5202.5368 | 5202.5368 | 5202.5368 | 5202.5368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3819 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16680.1289 | 0.2 | 0.3 | 26021.0011 |  |  |  |  | 0 | 5201.8471 | 5201.8471 | 5201.8471 | 5201.8471 | 5201.8471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3820 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16680.5435 | 0.2 | 0.3 | 26021.6479 |  |  |  |  | 0 | 9221.8676 | 9221.8676 | 9221.8676 | 9221.8676 | 9221.8676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3821 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16690.7117 | 0.2 | 0.3 | 26037.5102 |  |  |  |  | 0 | 8388.0616 | 8388.0616 | 8388.0616 | 8388.0616 | 8388.0616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3822 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 29007.6197 | 0.2 | 0.3 | 45251.8868 |  |  |  |  | 0 | 5201.5606 | 5201.5606 | 5201.5606 | 5201.5606 | 5201.5606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3823 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31450.9915 | 0.2 | 0.3 | 49063.5467 |  |  |  |  | 0 | 5201.9696 | 5201.9696 | 5201.9696 | 5201.9696 | 5201.9696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3824 | PEMBROKE PINES | 110312 | Private | 2026 | 5 | Swales | 66.6667 | 31467.5339 | 0.2 | 0.3 | 49089.3528 |  |  |  |  | 0 | 5202.345 | 5202.345 | 5202.345 | 5202.345 | 5202.345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3825 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 16679.8621 | 0.2 | 0.3 | 26020.5849 |  |  |  |  | 0 | 5201.704 | 5201.704 | 5201.704 | 5201.704 | 5201.704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3826 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 9143.7895 | 9143.7895 | 9143.7895 | 9143.7895 | 9143.7895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3827 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 16680.3749 | 0.2 | 0.3 | 26021.3848 |  |  |  |  | 0 | 7591.4409 | 7591.4409 | 7591.4409 | 7591.4409 | 7591.4409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3828 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 25943.372 | 0.2 | 0.3 | 40471.6603 |  |  |  |  | 0 | 9902.556 | 9902.556 | 9902.556 | 9902.556 | 9902.556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3829 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 17480.4419 | 0.2 | 0.3 | 27269.4894 |  |  |  |  | 0 | 7241.144 | 7241.144 | 7241.144 | 7241.144 | 7241.144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3830 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 19719.9032 | 0.2 | 0.3 | 30763.049 |  |  |  |  | 0 | 5202.3109 | 5202.3109 | 5202.3109 | 5202.3109 | 5202.3109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3831 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 20370.8586 | 0.2 | 0.3 | 31778.5394 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3832 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 21503.9102 | 0.2 | 0.3 | 33546.0999 |  |  |  |  | 0 | 5202.4691 | 5202.4691 | 5202.4691 | 5202.4691 | 5202.4691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3833 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 17763.4401 | 0.2 | 0.3 | 27710.9665 |  |  |  |  | 0 | 5916.2826 | 5916.2826 | 5916.2826 | 5916.2826 | 5916.2826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3834 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 31089.6979 | 0.2 | 0.3 | 48499.9288 |  |  |  |  | 0 | 9054.0208 | 9054.0208 | 9054.0208 | 9054.0208 | 9054.0208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3835 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 14272.7033 | 0.2 | 0.3 | 22265.4172 |  |  |  |  | 0 | 5201.6839 | 5201.6839 | 5201.6839 | 5201.6839 | 5201.6839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3836 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 16403.6261 | 0.2 | 0.3 | 25589.6567 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3837 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 26994.2573 | 0.2 | 0.3 | 42111.0414 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3838 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 22156.3401 | 0.2 | 0.3 | 34563.8905 |  |  |  |  | 0 | 5201.6576 | 5201.6576 | 5201.6576 | 5201.6576 | 5201.6576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3839 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 15274.2578 | 0.2 | 0.3 | 23827.8422 |  |  |  |  | 0 | 7758.627 | 7758.627 | 7758.627 | 7758.627 | 7758.627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3840 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 7167.9617 | 7167.9617 | 7167.9617 | 7167.9617 | 7167.9617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3841 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 18107.0897 | 0.2 | 0.3 | 28247.06 |  |  |  |  | 0 | 5202.2739 | 5202.2739 | 5202.2739 | 5202.2739 | 5202.2739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3842 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 12327.4593 | 0.2 | 0.3 | 19230.8365 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3843 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 25905.9437 | 0.2 | 0.3 | 40413.2722 |  |  |  |  | 0 | 5202.5432 | 5202.5432 | 5202.5432 | 5202.5432 | 5202.5432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3844 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 15143.2645 | 0.2 | 0.3 | 23623.4926 |  |  |  |  | 0 | 6028.6392 | 6028.6392 | 6028.6392 | 6028.6392 | 6028.6392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3845 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 10084.4052 | 0.2 | 0.3 | 15731.6721 |  |  |  |  | 0 | 8913.8462 | 8913.8462 | 8913.8462 | 8913.8462 | 8913.8462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3846 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16678.4147 | 0.2 | 0.3 | 26018.327 |  |  |  |  | 0 | 5202.0718 | 5202.0718 | 5202.0718 | 5202.0718 | 5202.0718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3847 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 18081.5953 | 0.2 | 0.3 | 28207.2887 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3848 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 5097.6464 | 0.2 | 0.3 | 7952.3284 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3849 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 17960.3131 | 0.2 | 0.3 | 28018.0884 |  |  |  |  | 0 | 5202.1323 | 5202.1323 | 5202.1323 | 5202.1323 | 5202.1323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3850 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 11509.5401 | 0.2 | 0.3 | 17954.8826 |  |  |  |  | 0 | 7897.0699 | 7897.0699 | 7897.0699 | 7897.0699 | 7897.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3851 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 2751.1426 | 0.2 | 0.3 | 4291.7825 |  |  |  |  | 0 | 9584.1167 | 9584.1167 | 9584.1167 | 9584.1167 | 9584.1167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3852 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 3701.1815 | 0.2 | 0.3 | 5773.8431 |  |  |  |  | 0 | 9745.5719 | 9745.5719 | 9745.5719 | 9745.5719 | 9745.5719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3853 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 14124.8529 | 0.2 | 0.3 | 22034.7706 |  |  |  |  | 0 | 9440.9945 | 9440.9945 | 9440.9945 | 9440.9945 | 9440.9945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3854 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 0.1108 | 0.2 | 0.3 | 0.17285 |  |  |  |  | 0 | 5374.0269 | 5374.0269 | 5374.0269 | 5374.0269 | 5374.0269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3855 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16932.0549 | 0.2 | 0.3 | 26414.0056 |  |  |  |  | 0 | 5708.7148 | 5708.7148 | 5708.7148 | 5708.7148 | 5708.7148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3856 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16671.7667 | 0.2 | 0.3 | 26007.956 |  |  |  |  | 0 | 9263.1556 | 9263.1556 | 9263.1556 | 9263.1556 | 9263.1556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3857 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 11333.8232 | 0.2 | 0.3 | 17680.7642 |  |  |  |  | 0 | 5202.8354 | 5202.8354 | 5202.8354 | 5202.8354 | 5202.8354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3858 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 6266.9897 | 0.2 | 0.3 | 9776.504 |  |  |  |  | 0 | 9779.7767 | 9779.7767 | 9779.7767 | 9779.7767 | 9779.7767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3859 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17553.5033 | 0.2 | 0.3 | 27383.4651 |  |  |  |  | 0 | 9342.7734 | 9342.7734 | 9342.7734 | 9342.7734 | 9342.7734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3860 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 8815.3479 | 0.2 | 0.3 | 13751.9428 |  |  |  |  | 0 | 5662.2847 | 5662.2847 | 5662.2847 | 5662.2847 | 5662.2847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3861 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 4685.6495 | 0.2 | 0.3 | 7309.6133 |  |  |  |  | 0 | 5239.756 | 5239.756 | 5239.756 | 5239.756 | 5239.756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3862 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 21244.6524 | 0.2 | 0.3 | 33141.6577 |  |  |  |  | 0 | 8526.4571 | 8526.4571 | 8526.4571 | 8526.4571 | 8526.4571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3863 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 20796.4247 | 0.2 | 0.3 | 32442.4225 |  |  |  |  | 0 | 5393.1165 | 5393.1165 | 5393.1165 | 5393.1165 | 5393.1165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3864 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 19894.7935 | 0.2 | 0.3 | 31035.8778 |  |  |  |  | 0 | 9876.5603 | 9876.5603 | 9876.5603 | 9876.5603 | 9876.5603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3865 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 18158.7044 | 0.2 | 0.3 | 28327.5789 |  |  |  |  | 0 | 741.2115 | 741.2115 | 741.2115 | 741.2115 | 741.2115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3866 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 5804.6513 | 0.2 | 0.3 | 9055.256 |  |  |  |  | 0 | 5662.6214 | 5662.6214 | 5662.6214 | 5662.6214 | 5662.6214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3867 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 21224.4921 | 0.2 | 0.3 | 33110.2077 |  |  |  |  | 0 | 9785.9932 | 9785.9932 | 9785.9932 | 9785.9932 | 9785.9932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3868 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 7860.1849 | 0.2 | 0.3 | 12261.8884 |  |  |  |  | 0 | 2601.7172 | 2601.7172 | 2601.7172 | 2601.7172 | 2601.7172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3869 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 14116.1212 | 0.2 | 0.3 | 22021.1491 |  |  |  |  | 0 | 2601.76 | 2601.76 | 2601.76 | 2601.76 | 2601.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3870 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 21292.2736 | 0.2 | 0.3 | 33215.9468 |  |  |  |  | 0 | 399.4973 | 399.4973 | 399.4973 | 399.4973 | 399.4973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3871 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 16134.9983 | 0.2 | 0.3 | 25170.5973 |  |  |  |  | 0 | 6445.4665 | 6445.4665 | 6445.4665 | 6445.4665 | 6445.4665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3872 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 14194.3183 | 0.2 | 0.3 | 22143.1365 |  |  |  |  | 0 | 5412.2545 | 5412.2545 | 5412.2545 | 5412.2545 | 5412.2545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3873 | PEMBROKE PINES | 110328 | Public | 2036 | 5 | Swales | 66.6667 | 21965.4599 | 0.2 | 0.3 | 34266.1174 |  |  |  |  | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3874 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16674.6982 | 0.2 | 0.3 | 26012.5292 |  |  |  |  | 0 | 5202.1551 | 5202.1551 | 5202.1551 | 5202.1551 | 5202.1551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3875 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 23168.0528 | 0.2 | 0.3 | 36142.1624 |  |  |  |  | 0 | 7697.9427 | 7697.9427 | 7697.9427 | 7697.9427 | 7697.9427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3876 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 23092.5775 | 0.2 | 0.3 | 36024.4208 |  |  |  |  | 0 | 449.0226 | 449.0226 | 449.0226 | 449.0226 | 449.0226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3877 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 22820.9472 | 0.2 | 0.3 | 35600.6776 |  |  |  |  | 0 | 8299.5054 | 8299.5054 | 8299.5054 | 8299.5054 | 8299.5054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3878 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 6202.9905 | 0.2 | 0.3 | 9676.6652 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3879 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 15586.8587 | 0.2 | 0.3 | 24315.4996 |  |  |  |  | 0 | 5202.0229 | 5202.0229 | 5202.0229 | 5202.0229 | 5202.0229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3880 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 16698.968 | 0.2 | 0.3 | 26050.3901 |  |  |  |  | 0 | 7076.9929 | 7076.9929 | 7076.9929 | 7076.9929 | 7076.9929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3881 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 16710.8778 | 0.2 | 0.3 | 26068.9694 |  |  |  |  | 0 | 8070.3361 | 8070.3361 | 8070.3361 | 8070.3361 | 8070.3361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3882 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 4433.1933 | 0.2 | 0.3 | 6915.7816 |  |  |  |  | 0 | 6306.7978 | 6306.7978 | 6306.7978 | 6306.7978 | 6306.7978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3883 | PEMBROKE PINES | 110339 | Private | 2036 | 5 | Swales | 66.6667 | 27849.3098 | 0.2 | 0.3 | 43444.9233 |  |  |  |  | 0 | 5454.4289 | 5454.4289 | 5454.4289 | 5454.4289 | 5454.4289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3884 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 22715.554 | 0.2 | 0.3 | 35436.2642 |  |  |  |  | 0 | 5347.7531 | 5347.7531 | 5347.7531 | 5347.7531 | 5347.7531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3885 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 8487.9938 | 0.2 | 0.3 | 13241.2703 |  |  |  |  | 0 | 6606.7479 | 6606.7479 | 6606.7479 | 6606.7479 | 6606.7479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3886 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 19951.0279 | 0.2 | 0.3 | 31123.6035 |  |  |  |  | 0 | 9778.8707 | 9778.8707 | 9778.8707 | 9778.8707 | 9778.8707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3887 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1807 | 0.2 | 0.3 | 26000.8018 |  |  |  |  | 0 | 463.8522 | 463.8522 | 463.8522 | 463.8522 | 463.8522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3888 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 4881.0936 | 4881.0936 | 4881.0936 | 4881.0936 | 4881.0936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3889 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16678.6597 | 0.2 | 0.3 | 26018.7091 |  |  |  |  | 0 | 5201.9073 | 5201.9073 | 5201.9073 | 5201.9073 | 5201.9073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3890 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 23125.0404 | 0.2 | 0.3 | 36075.063 |  |  |  |  | 0 | 8285.6991 | 8285.6991 | 8285.6991 | 8285.6991 | 8285.6991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3891 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 27259.0689 | 0.2 | 0.3 | 42524.1475 |  |  |  |  | 0 | 3727.2902 | 3727.2902 | 3727.2902 | 3727.2902 | 3727.2902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3892 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16314.5135 | 0.2 | 0.3 | 25450.641 |  |  |  |  | 0 | 5201.8447 | 5201.8447 | 5201.8447 | 5201.8447 | 5201.8447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3893 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 26313.0732 | 0.2 | 0.3 | 41048.3942 |  |  |  |  | 0 | 5202.0318 | 5202.0318 | 5202.0318 | 5202.0318 | 5202.0318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3894 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 23737.4904 | 0.2 | 0.3 | 37030.485 |  |  |  |  | 0 | 9779.9127 | 9779.9127 | 9779.9127 | 9779.9127 | 9779.9127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3895 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9997 | 0.2 | 0.3 | 26020.7996 |  |  |  |  | 0 | 6187.2302 | 6187.2302 | 6187.2302 | 6187.2302 | 6187.2302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3896 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 5201.5408 | 5201.5408 | 5201.5408 | 5201.5408 | 5201.5408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3897 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16681.7638 | 0.2 | 0.3 | 26023.5515 |  |  |  |  | 0 | 5201.6442 | 5201.6442 | 5201.6442 | 5201.6442 | 5201.6442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3898 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 24997.1479 | 0.2 | 0.3 | 38995.5507 |  |  |  |  | 0 | 9779.9102 | 9779.9102 | 9779.9102 | 9779.9102 | 9779.9102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3899 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 19852.6422 | 0.2 | 0.3 | 30970.1218 |  |  |  |  | 0 | 8820.5939 | 8820.5939 | 8820.5939 | 8820.5939 | 8820.5939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3900 | PEMBROKE PINES | 110312 | Public | 2033 | 5 | Swales | 66.6667 | 3288.2798 | 0.2 | 0.3 | 5129.7165 |  |  |  |  | 0 | 7782.8564 | 7782.8564 | 7782.8564 | 7782.8564 | 7782.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3901 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 23003.5423 | 0.2 | 0.3 | 35885.526 |  |  |  |  | 0 | 113.3083 | 113.3083 | 113.3083 | 113.3083 | 113.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3902 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 2225.4612 | 2225.4612 | 2225.4612 | 2225.4612 | 2225.4612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3903 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 16675.2878 | 0.2 | 0.3 | 26013.449 |  |  |  |  | 0 | 3292.873 | 3292.873 | 3292.873 | 3292.873 | 3292.873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3904 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 21585.6707 | 0.2 | 0.3 | 33673.6462 |  |  |  |  | 0 | 5201.0063 | 5201.0063 | 5201.0063 | 5201.0063 | 5201.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3905 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 32354.8225 | 0.2 | 0.3 | 50473.5232 |  |  |  |  | 0 | 5202.5541 | 5202.5541 | 5202.5541 | 5202.5541 | 5202.5541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3906 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 27794.8757 | 0.2 | 0.3 | 43360.006 |  |  |  |  | 0 | 5200.9747 | 5200.9747 | 5200.9747 | 5200.9747 | 5200.9747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3907 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 41.1697 | 0.2 | 0.3 | 64.2248 |  |  |  |  | 0 | 2179.8442 | 2179.8442 | 2179.8442 | 2179.8442 | 2179.8442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3908 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 28256.9737 | 0.2 | 0.3 | 44080.879 |  |  |  |  | 0 | 8877.3527 | 8877.3527 | 8877.3527 | 8877.3527 | 8877.3527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3909 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 31731.8865 | 0.2 | 0.3 | 49501.743 |  |  |  |  | 0 | 14654.7316 | 14654.7316 | 14654.7316 | 14654.7316 | 14654.7316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3910 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 18318.2139 | 0.2 | 0.3 | 28576.4136 |  |  |  |  | 0 | 9736.9749 | 9736.9749 | 9736.9749 | 9736.9749 | 9736.9749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3911 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 22109.1274 | 0.2 | 0.3 | 34490.2387 |  |  |  |  | 0 | 10127.1873 | 10127.1873 | 10127.1873 | 10127.1873 | 10127.1873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3912 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 9911.3331 | 0.2 | 0.3 | 15461.6796 |  |  |  |  | 0 | 4353.6109 | 4353.6109 | 4353.6109 | 4353.6109 | 4353.6109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3913 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 18917.3078 | 0.2 | 0.3 | 29511.0002 |  |  |  |  | 0 | 5201.4305 | 5201.4305 | 5201.4305 | 5201.4305 | 5201.4305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3914 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 23780.1747 | 0.2 | 0.3 | 37097.0725 |  |  |  |  | 0 | 5202.5282 | 5202.5282 | 5202.5282 | 5202.5282 | 5202.5282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3915 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 22575.3061 | 0.2 | 0.3 | 35217.4776 |  |  |  |  | 0 | 7590.9753 | 7590.9753 | 7590.9753 | 7590.9753 | 7590.9753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3916 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 29672.8983 | 0.2 | 0.3 | 46289.7214 |  |  |  |  | 0 | 9869.2149 | 9869.2149 | 9869.2149 | 9869.2149 | 9869.2149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3917 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 16391.9843 | 0.2 | 0.3 | 25571.4956 |  |  |  |  | 0 | 7253.3717 | 7253.3717 | 7253.3717 | 7253.3717 | 7253.3717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3918 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 11288.9697 | 0.2 | 0.3 | 17610.7928 |  |  |  |  | 0 | 11330.4526 | 11330.4526 | 11330.4526 | 11330.4526 | 11330.4526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3919 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 29105.3563 | 0.2 | 0.3 | 45404.3559 |  |  |  |  | 0 | 9706.8424 | 9706.8424 | 9706.8424 | 9706.8424 | 9706.8424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3920 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 24033.0161 | 0.2 | 0.3 | 37491.5051 |  |  |  |  | 0 | 10419.9211 | 10419.9211 | 10419.9211 | 10419.9211 | 10419.9211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3921 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 19515.2021 | 0.2 | 0.3 | 30443.7152 |  |  |  |  | 0 | 1798.3731 | 1798.3731 | 1798.3731 | 1798.3731 | 1798.3731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3922 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 29691.7627 | 0.2 | 0.3 | 46319.1499 |  |  |  |  | 0 | 6783.4641 | 6783.4641 | 6783.4641 | 6783.4641 | 6783.4641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3923 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 9810.7145 | 9810.7145 | 9810.7145 | 9810.7145 | 9810.7145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3924 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 25250.6781 | 0.2 | 0.3 | 39391.0578 |  |  |  |  | 0 | 9780.172 | 9780.172 | 9780.172 | 9780.172 | 9780.172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3925 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16708.6955 | 0.2 | 0.3 | 26065.565 |  |  |  |  | 0 | 5203.2457 | 5203.2457 | 5203.2457 | 5203.2457 | 5203.2457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3926 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 18429.5376 | 0.2 | 0.3 | 28750.0787 |  |  |  |  | 0 | 8381.1098 | 8381.1098 | 8381.1098 | 8381.1098 | 8381.1098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3927 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 12366.1201 | 0.2 | 0.3 | 19291.1473 |  |  |  |  | 0 | 9779.3076 | 9779.3076 | 9779.3076 | 9779.3076 | 9779.3076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3928 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 11607.7389 | 0.2 | 0.3 | 18108.0726 |  |  |  |  | 0 | 5203.605 | 5203.605 | 5203.605 | 5203.605 | 5203.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3929 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16545.0121 | 0.2 | 0.3 | 25810.2188 |  |  |  |  | 0 | 5203.7736 | 5203.7736 | 5203.7736 | 5203.7736 | 5203.7736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3930 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 23027.2069 | 0.2 | 0.3 | 35922.4427 |  |  |  |  | 0 | 9781.8847 | 9781.8847 | 9781.8847 | 9781.8847 | 9781.8847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3931 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 27024.939 | 0.2 | 0.3 | 42158.9048 |  |  |  |  | 0 | 8451.7262 | 8451.7262 | 8451.7262 | 8451.7262 | 8451.7262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3932 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 19058.7137 | 0.2 | 0.3 | 29731.5933 |  |  |  |  | 0 | 10882.3175 | 10882.3175 | 10882.3175 | 10882.3175 | 10882.3175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3933 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16691.0807 | 0.2 | 0.3 | 26038.0858 |  |  |  |  | 0 | 10402.309 | 10402.309 | 10402.309 | 10402.309 | 10402.309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3934 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 26831.4551 | 0.2 | 0.3 | 41857.0699 |  |  |  |  | 0 | 14187.5792 | 14187.5792 | 14187.5792 | 14187.5792 | 14187.5792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3935 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16703.1632 | 0.2 | 0.3 | 26056.9346 |  |  |  |  | 0 | 8696.1819 | 8696.1819 | 8696.1819 | 8696.1819 | 8696.1819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3936 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16719.2237 | 0.2 | 0.3 | 26081.9889 |  |  |  |  | 0 | 5201.7651 | 5201.7651 | 5201.7651 | 5201.7651 | 5201.7651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3937 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 18189.1481 | 0.2 | 0.3 | 28375.0711 |  |  |  |  | 0 | 5201.4213 | 5201.4213 | 5201.4213 | 5201.4213 | 5201.4213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3938 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 14576.8912 | 0.2 | 0.3 | 22739.9503 |  |  |  |  | 0 | 5202.3693 | 5202.3693 | 5202.3693 | 5202.3693 | 5202.3693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3939 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 18460.8559 | 0.2 | 0.3 | 28798.9353 |  |  |  |  | 0 | 8617.5881 | 8617.5881 | 8617.5881 | 8617.5881 | 8617.5881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3940 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 19115.9249 | 0.2 | 0.3 | 29820.8429 |  |  |  |  | 0 | 9778.7869 | 9778.7869 | 9778.7869 | 9778.7869 | 9778.7869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3941 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 16604.1447 | 0.2 | 0.3 | 25902.4657 |  |  |  |  | 0 | 5202.7433 | 5202.7433 | 5202.7433 | 5202.7433 | 5202.7433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3942 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 8257.6693 | 0.2 | 0.3 | 12881.9642 |  |  |  |  | 0 | 5458.1209 | 5458.1209 | 5458.1209 | 5458.1209 | 5458.1209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3943 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 22271.7542 | 0.2 | 0.3 | 34743.9366 |  |  |  |  | 0 | 10932.9347 | 10932.9347 | 10932.9347 | 10932.9347 | 10932.9347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3944 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 12975.1817 | 0.2 | 0.3 | 20241.2834 |  |  |  |  | 0 | 9051.805 | 9051.805 | 9051.805 | 9051.805 | 9051.805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3945 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 13384.8134 | 0.2 | 0.3 | 20880.3089 |  |  |  |  | 0 | 5201.1976 | 5201.1976 | 5201.1976 | 5201.1976 | 5201.1976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3946 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 22975.6028 | 0.2 | 0.3 | 35841.9404 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3947 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 12283.4313 | 0.2 | 0.3 | 19162.1529 |  |  |  |  | 0 | 5201.3547 | 5201.3547 | 5201.3547 | 5201.3547 | 5201.3547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3948 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 10726.0011 | 0.2 | 0.3 | 16732.5618 |  |  |  |  | 0 | 8784.4355 | 8784.4355 | 8784.4355 | 8784.4355 | 8784.4355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3949 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 14466.7059 | 0.2 | 0.3 | 22568.0612 |  |  |  |  | 0 | 5201.7621 | 5201.7621 | 5201.7621 | 5201.7621 | 5201.7621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3950 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 28318.4903 | 0.2 | 0.3 | 44176.8449 |  |  |  |  | 0 | 5527.1116 | 5527.1116 | 5527.1116 | 5527.1116 | 5527.1116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3951 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 13428.8687 | 0.2 | 0.3 | 20949.0352 |  |  |  |  | 0 | 5200.9624 | 5200.9624 | 5200.9624 | 5200.9624 | 5200.9624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3952 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 13389.8607 | 0.2 | 0.3 | 20888.1826 |  |  |  |  | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3953 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 11084.295 | 0.2 | 0.3 | 17291.5002 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3954 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 15749.9911 | 0.2 | 0.3 | 24569.9862 |  |  |  |  | 0 | 5176.1657 | 5176.1657 | 5176.1657 | 5176.1657 | 5176.1657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3955 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 29499.2367 | 0.2 | 0.3 | 46018.8093 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3956 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 4985.5613 | 0.2 | 0.3 | 7777.4756 |  |  |  |  | 0 | 5201.0733 | 5201.0733 | 5201.0733 | 5201.0733 | 5201.0733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3957 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 12794.1387 | 0.2 | 0.3 | 19958.8564 |  |  |  |  | 0 | 9815.4082 | 9815.4082 | 9815.4082 | 9815.4082 | 9815.4082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3958 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 23914.3597 | 0.2 | 0.3 | 37306.4012 |  |  |  |  | 0 | 5922.9227 | 5922.9227 | 5922.9227 | 5922.9227 | 5922.9227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3959 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17151.7931 | 0.2 | 0.3 | 26756.7973 |  |  |  |  | 0 | 5200.2012 | 5200.2012 | 5200.2012 | 5200.2012 | 5200.2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3960 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 15146.9038 | 0.2 | 0.3 | 23629.1699 |  |  |  |  | 0 | 9777.8163 | 9777.8163 | 9777.8163 | 9777.8163 | 9777.8163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3961 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 22966.3583 | 0.2 | 0.3 | 35827.519 |  |  |  |  | 0 | 2387.9625 | 2387.9625 | 2387.9625 | 2387.9625 | 2387.9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3962 | PEMBROKE PINES | 110328 | Public | 2036 | 5 | Swales | 66.6667 | 17800.7116 | 0.2 | 0.3 | 27769.1101 |  |  |  |  | 0 | 2890.0748 | 2890.0748 | 2890.0748 | 2890.0748 | 2890.0748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3963 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0831 | 0.2 | 0.3 | 26000.6497 |  |  |  |  | 0 | 7878.4376 | 7878.4376 | 7878.4376 | 7878.4376 | 7878.4376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3964 | PEMBROKE PINES | 110309 | Private | 2036 | 5 | Swales | 66.6667 | 20424.8275 | 0.2 | 0.3 | 31862.731 |  |  |  |  | 0 | 9777.1707 | 9777.1707 | 9777.1707 | 9777.1707 | 9777.1707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3965 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 16682.902 | 0.2 | 0.3 | 26025.3271 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3966 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 11744.0351 | 0.2 | 0.3 | 18320.6947 |  |  |  |  | 0 | 5201.5335 | 5201.5335 | 5201.5335 | 5201.5335 | 5201.5335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3967 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 27845.0291 | 0.2 | 0.3 | 43438.2454 |  |  |  |  | 0 | 7686.4899 | 7686.4899 | 7686.4899 | 7686.4899 | 7686.4899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3968 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 18494.5439 | 0.2 | 0.3 | 28851.4885 |  |  |  |  | 0 | 5202.9049 | 5202.9049 | 5202.9049 | 5202.9049 | 5202.9049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3969 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 3571.7849 | 0.2 | 0.3 | 5571.9845 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3970 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 20646.9114 | 0.2 | 0.3 | 32209.1818 |  |  |  |  | 0 | 5201.8068 | 5201.8068 | 5201.8068 | 5201.8068 | 5201.8068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3971 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 25747.9241 | 0.2 | 0.3 | 40166.7616 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3972 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 24856.1886 | 0.2 | 0.3 | 38775.6542 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3973 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 23585.2431 | 0.2 | 0.3 | 36792.9792 |  |  |  |  | 0 | 10405.4475 | 10405.4475 | 10405.4475 | 10405.4475 | 10405.4475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3974 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 9331.6576 | 0.2 | 0.3 | 14557.3859 |  |  |  |  | 0 | 5365.0065 | 5365.0065 | 5365.0065 | 5365.0065 | 5365.0065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3975 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16701.3505 | 0.2 | 0.3 | 26054.1068 |  |  |  |  | 0 | 2814.4332 | 2814.4332 | 2814.4332 | 2814.4332 | 2814.4332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3976 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 28140.3767 | 0.2 | 0.3 | 43898.9876 |  |  |  |  | 0 | 2312.3353 | 2312.3353 | 2312.3353 | 2312.3353 | 2312.3353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3977 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16675.8693 | 0.2 | 0.3 | 26014.3562 |  |  |  |  | 0 | 5338.7256 | 5338.7256 | 5338.7256 | 5338.7256 | 5338.7256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3978 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 5178.8781 | 0.2 | 0.3 | 8079.0498 |  |  |  |  | 0 | 5201.5223 | 5201.5223 | 5201.5223 | 5201.5223 | 5201.5223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3979 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 11496.6915 | 0.2 | 0.3 | 17934.8388 |  |  |  |  | 0 | 9773.0018 | 9773.0018 | 9773.0018 | 9773.0018 | 9773.0018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3980 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 13764.9455 | 0.2 | 0.3 | 21473.315 |  |  |  |  | 0 | 5202.1275 | 5202.1275 | 5202.1275 | 5202.1275 | 5202.1275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3981 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 25131.9075 | 0.2 | 0.3 | 39205.7758 |  |  |  |  | 0 | 5200.1752 | 5200.1752 | 5200.1752 | 5200.1752 | 5200.1752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3982 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 30127.1227 | 0.2 | 0.3 | 46998.3115 |  |  |  |  | 0 | 9777.0822 | 9777.0822 | 9777.0822 | 9777.0822 | 9777.0822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3983 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 35028.0415 | 0.2 | 0.3 | 54643.7448 |  |  |  |  | 0 | 5199.5723 | 5199.5723 | 5199.5723 | 5199.5723 | 5199.5723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3984 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 31387.7681 | 0.2 | 0.3 | 48964.9182 |  |  |  |  | 0 | 5199.9962 | 5199.9962 | 5199.9962 | 5199.9962 | 5199.9962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3985 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 17609.2899 | 0.2 | 0.3 | 27470.4923 |  |  |  |  | 0 | 9777.8394 | 9777.8394 | 9777.8394 | 9777.8394 | 9777.8394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3986 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 24258.3009 | 0.2 | 0.3 | 37842.9494 |  |  |  |  | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3987 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 30430.3279 | 0.2 | 0.3 | 47471.3115 |  |  |  |  | 0 | 9816.9133 | 9816.9133 | 9816.9133 | 9816.9133 | 9816.9133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3988 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 25246.2481 | 0.2 | 0.3 | 39384.1471 |  |  |  |  | 0 | 9021.6705 | 9021.6705 | 9021.6705 | 9021.6705 | 9021.6705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3989 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 25460.1565 | 0.2 | 0.3 | 39717.8442 |  |  |  |  | 0 | 9422.0293 | 9422.0293 | 9422.0293 | 9422.0293 | 9422.0293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3990 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 33361.0328 | 0.2 | 0.3 | 52043.2112 |  |  |  |  | 0 | 5201.6094 | 5201.6094 | 5201.6094 | 5201.6094 | 5201.6094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3991 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16671.7947 | 0.2 | 0.3 | 26007.9997 |  |  |  |  | 0 | 1217.2516 | 1217.2516 | 1217.2516 | 1217.2516 | 1217.2516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3992 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16326.7673 | 0.2 | 0.3 | 25469.7569 |  |  |  |  | 0 | 5202.2789 | 5202.2789 | 5202.2789 | 5202.2789 | 5202.2789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3993 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 27432.1676 | 0.2 | 0.3 | 42794.1815 |  |  |  |  | 0 | 4551.3324 | 4551.3324 | 4551.3324 | 4551.3324 | 4551.3324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3994 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 4441.5863 | 0.2 | 0.3 | 6928.8746 |  |  |  |  | 0 | 649.8715 | 649.8715 | 649.8715 | 649.8715 | 649.8715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3995 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16671.1413 | 0.2 | 0.3 | 26006.9805 |  |  |  |  | 0 | 3948.9862 | 3948.9862 | 3948.9862 | 3948.9862 | 3948.9862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3996 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 30564.6529 | 0.2 | 0.3 | 47680.8585 |  |  |  |  | 0 | 8145.7908 | 8145.7908 | 8145.7908 | 8145.7908 | 8145.7908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3997 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 14657.866 | 0.2 | 0.3 | 22866.271 |  |  |  |  | 0 | 5204.1923 | 5204.1923 | 5204.1923 | 5204.1923 | 5204.1923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3998 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 11461.4983 | 0.2 | 0.3 | 17879.9373 |  |  |  |  | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3999 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 18673.6511 | 0.2 | 0.3 | 29130.8958 |  |  |  |  | 0 | 9780.7557 | 9780.7557 | 9780.7557 | 9780.7557 | 9780.7557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4000 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 24308.9037 | 0.2 | 0.3 | 37921.8898 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4001 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 17191.1867 | 0.2 | 0.3 | 26818.2512 |  |  |  |  | 0 | 5200.9389 | 5200.9389 | 5200.9389 | 5200.9389 | 5200.9389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4002 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 16717.7341 | 0.2 | 0.3 | 26079.6651 |  |  |  |  | 0 | 9776.7435 | 9776.7435 | 9776.7435 | 9776.7435 | 9776.7435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4003 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 17099.0648 | 0.2 | 0.3 | 26674.5411 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4004 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 17260.7777 | 0.2 | 0.3 | 26926.8133 |  |  |  |  | 0 | 5201.054 | 5201.054 | 5201.054 | 5201.054 | 5201.054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4005 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 20378.8293 | 0.2 | 0.3 | 31790.9737 |  |  |  |  | 0 | 7907.9603 | 7907.9603 | 7907.9603 | 7907.9603 | 7907.9603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4006 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 11801.2347 | 0.2 | 0.3 | 18409.9261 |  |  |  |  | 0 | 8567.9145 | 8567.9145 | 8567.9145 | 8567.9145 | 8567.9145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4007 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 17484.7658 | 0.2 | 0.3 | 27276.2346 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4008 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 16444.8895 | 0.2 | 0.3 | 25654.0277 |  |  |  |  | 0 | 9719.6134 | 9719.6134 | 9719.6134 | 9719.6134 | 9719.6134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4009 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 23548.3618 | 0.2 | 0.3 | 36735.4444 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4010 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 18128.6359 | 0.2 | 0.3 | 28280.6721 |  |  |  |  | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4011 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 19172.9231 | 0.2 | 0.3 | 29909.7601 |  |  |  |  | 0 | 5201.4666 | 5201.4666 | 5201.4666 | 5201.4666 | 5201.4666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4012 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 20294.4771 | 0.2 | 0.3 | 31659.3842 |  |  |  |  | 0 | 66.1754 | 66.1754 | 66.1754 | 66.1754 | 66.1754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4013 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 31493.4935 | 0.2 | 0.3 | 49129.8498 |  |  |  |  | 0 | 4029.3354 | 4029.3354 | 4029.3354 | 4029.3354 | 4029.3354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4014 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 16676.8364 | 0.2 | 0.3 | 26015.8648 |  |  |  |  | 0 | 5200.5333 | 5200.5333 | 5200.5333 | 5200.5333 | 5200.5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4015 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 28446.1155 | 0.2 | 0.3 | 44375.9401 |  |  |  |  | 0 | 9779.2683 | 9779.2683 | 9779.2683 | 9779.2683 | 9779.2683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4016 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 27617.4961 | 0.2 | 0.3 | 43083.294 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4017 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16666.613 | 0.2 | 0.3 | 25999.9163 |  |  |  |  | 0 | 5202.72 | 5202.72 | 5202.72 | 5202.72 | 5202.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4018 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 31807.98 | 0.2 | 0.3 | 49620.4488 |  |  |  |  | 0 | 7382.5659 | 7382.5659 | 7382.5659 | 7382.5659 | 7382.5659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4019 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 23246.1427 | 0.2 | 0.3 | 36263.9827 |  |  |  |  | 0 | 5148.0873 | 5148.0873 | 5148.0873 | 5148.0873 | 5148.0873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4020 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 521.6789 | 0.2 | 0.3 | 813.819 |  |  |  |  | 0 | 8955.578 | 8955.578 | 8955.578 | 8955.578 | 8955.578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4021 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 17888.9609 | 0.2 | 0.3 | 27906.779 |  |  |  |  | 0 | 9811.2443 | 9811.2443 | 9811.2443 | 9811.2443 | 9811.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4022 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 25856.7355 | 0.2 | 0.3 | 40336.5074 |  |  |  |  | 0 | 60.3422 | 60.3422 | 60.3422 | 60.3422 | 60.3422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4023 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 20648.0578 | 0.2 | 0.3 | 32210.9702 |  |  |  |  | 0 | 5201.6363 | 5201.6363 | 5201.6363 | 5201.6363 | 5201.6363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4024 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 41484.8516 | 0.2 | 0.3 | 64716.3685 |  |  |  |  | 0 | 5199.0709 | 5199.0709 | 5199.0709 | 5199.0709 | 5199.0709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4025 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 18553.2505 | 0.2 | 0.3 | 28943.0707 |  |  |  |  | 0 | 5200.8365 | 5200.8365 | 5200.8365 | 5200.8365 | 5200.8365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4026 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16912.2976 | 0.2 | 0.3 | 26383.1843 |  |  |  |  | 0 | 4213.2263 | 4213.2263 | 4213.2263 | 4213.2263 | 4213.2263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4027 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 14403.2655 | 0.2 | 0.3 | 22469.0941 |  |  |  |  | 0 | 988.3059 | 988.3059 | 988.3059 | 988.3059 | 988.3059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4028 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 19043.0285 | 0.2 | 0.3 | 29707.1245 |  |  |  |  | 0 | 3037.1435 | 3037.1435 | 3037.1435 | 3037.1435 | 3037.1435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4029 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 25937.5171 | 0.2 | 0.3 | 40462.5267 |  |  |  |  | 0 | 2164.3171 | 2164.3171 | 2164.3171 | 2164.3171 | 2164.3171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4030 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 17156.9057 | 0.2 | 0.3 | 26764.7728 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4031 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 25184.91 | 0.2 | 0.3 | 39288.4596 |  |  |  |  | 0 | 3984.4835 | 3984.4835 | 3984.4835 | 3984.4835 | 3984.4835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4032 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 18549.9124 | 0.2 | 0.3 | 28937.8633 |  |  |  |  | 0 | 1217.0394 | 1217.0394 | 1217.0394 | 1217.0394 | 1217.0394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4033 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16906.222 | 0.2 | 0.3 | 26373.7063 |  |  |  |  | 0 | 5200.7454 | 5200.7454 | 5200.7454 | 5200.7454 | 5200.7454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4034 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 7539.7499 | 0.2 | 0.3 | 11762.0098 |  |  |  |  | 0 | 5207.1445 | 5207.1445 | 5207.1445 | 5207.1445 | 5207.1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4035 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 1841.3311 | 0.2 | 0.3 | 2872.4766 |  |  |  |  | 0 | 7356.8571 | 7356.8571 | 7356.8571 | 7356.8571 | 7356.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4036 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 30588.3485 | 0.2 | 0.3 | 47717.8236 |  |  |  |  | 0 | 5208.3282 | 5208.3282 | 5208.3282 | 5208.3282 | 5208.3282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4037 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 13096.768 | 0.2 | 0.3 | 20430.9581 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4038 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 28473.0521 | 0.2 | 0.3 | 44417.9612 |  |  |  |  | 0 | 6585.3124 | 6585.3124 | 6585.3124 | 6585.3124 | 6585.3124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4039 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 200.7513 | 0.2 | 0.3 | 313.172 |  |  |  |  | 0 | 5201.3692 | 5201.3692 | 5201.3692 | 5201.3692 | 5201.3692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4040 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 32547.7001 | 0.2 | 0.3 | 50774.4122 |  |  |  |  | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4041 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 21163.3205 | 0.2 | 0.3 | 33014.78 |  |  |  |  | 0 | 2601.7447 | 2601.7447 | 2601.7447 | 2601.7447 | 2601.7447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4042 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 13886.6007 | 0.2 | 0.3 | 21663.0971 |  |  |  |  | 0 | 2599.587 | 2599.587 | 2599.587 | 2599.587 | 2599.587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4043 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 15144.1788 | 0.2 | 0.3 | 23624.9189 |  |  |  |  | 0 | 2600.437 | 2600.437 | 2600.437 | 2600.437 | 2600.437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4044 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 14517.9945 | 0.2 | 0.3 | 22648.0714 |  |  |  |  | 0 | 2600.3676 | 2600.3676 | 2600.3676 | 2600.3676 | 2600.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4045 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 18533.1393 | 0.2 | 0.3 | 28911.6974 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4046 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 11929.7447 | 0.2 | 0.3 | 18610.4017 |  |  |  |  | 0 | 5329.1095 | 5329.1095 | 5329.1095 | 5329.1095 | 5329.1095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4047 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 4376.1583 | 0.2 | 0.3 | 6826.807 |  |  |  |  | 0 | 2403.8575 | 2403.8575 | 2403.8575 | 2403.8575 | 2403.8575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4048 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 15281.6389 | 0.2 | 0.3 | 23839.3567 |  |  |  |  | 0 | 2785.7509 | 2785.7509 | 2785.7509 | 2785.7509 | 2785.7509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4049 | PEMBROKE PINES | 110327 | Private | 2036 | 5 | Swales | 66.6667 | 7908.5723 | 0.2 | 0.3 | 12337.3728 |  |  |  |  | 0 | 5946.1964 | 5946.1964 | 5946.1964 | 5946.1964 | 5946.1964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4050 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 28290.5744 | 0.2 | 0.3 | 44133.2961 |  |  |  |  | 0 | 1594.5362 | 1594.5362 | 1594.5362 | 1594.5362 | 1594.5362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4051 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 5200.6856 | 5200.6856 | 5200.6856 | 5200.6856 | 5200.6856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4052 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16667.3648 | 0.2 | 0.3 | 26001.0891 |  |  |  |  | 0 | 5200.7168 | 5200.7168 | 5200.7168 | 5200.7168 | 5200.7168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4053 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 5201.3489 | 5201.3489 | 5201.3489 | 5201.3489 | 5201.3489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4054 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17614.8731 | 0.2 | 0.3 | 27479.2021 |  |  |  |  | 0 | 5201.4636 | 5201.4636 | 5201.4636 | 5201.4636 | 5201.4636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4055 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17608.8671 | 0.2 | 0.3 | 27469.8327 |  |  |  |  | 0 | 1616.0602 | 1616.0602 | 1616.0602 | 1616.0602 | 1616.0602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4056 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 18378.2146 | 0.2 | 0.3 | 28670.0148 |  |  |  |  | 0 | 6007.8329 | 6007.8329 | 6007.8329 | 6007.8329 | 6007.8329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4057 | PEMBROKE PINES | 110328 | Public | 2036 | 5 | Swales | 66.6667 | 639.7473 | 0.2 | 0.3 | 998.0058 |  |  |  |  | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4058 | PEMBROKE PINES | 110328 | Public | 2036 | 5 | Swales | 66.6667 | 20090.2169 | 0.2 | 0.3 | 31340.7384 |  |  |  |  | 0 | 5360.5759 | 5360.5759 | 5360.5759 | 5360.5759 | 5360.5759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4059 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 7377.2534 | 7377.2534 | 7377.2534 | 7377.2534 | 7377.2534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4060 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 22786.8798 | 0.2 | 0.3 | 35547.5325 |  |  |  |  | 0 | 1898.9095 | 1898.9095 | 1898.9095 | 1898.9095 | 1898.9095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4061 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 16799.8198 | 0.2 | 0.3 | 26207.7189 |  |  |  |  | 0 | 2599.771 | 2599.771 | 2599.771 | 2599.771 | 2599.771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4062 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 39355.4955 | 0.2 | 0.3 | 61394.573 |  |  |  |  | 0 | 12360.5251 | 12360.5251 | 12360.5251 | 12360.5251 | 12360.5251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4063 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 29185.3637 | 0.2 | 0.3 | 45529.1674 |  |  |  |  | 0 | 10401.6644 | 10401.6644 | 10401.6644 | 10401.6644 | 10401.6644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4064 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 31360.8132 | 0.2 | 0.3 | 48922.8686 |  |  |  |  | 0 | 10401.6375 | 10401.6375 | 10401.6375 | 10401.6375 | 10401.6375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4065 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 31358.146 | 0.2 | 0.3 | 48918.7078 |  |  |  |  | 0 | 11256.8545 | 11256.8545 | 11256.8545 | 11256.8545 | 11256.8545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4066 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 27577.776 | 0.2 | 0.3 | 43021.3306 |  |  |  |  | 0 | 939.9172 | 939.9172 | 939.9172 | 939.9172 | 939.9172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4067 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 19668.2396 | 0.2 | 0.3 | 30682.4538 |  |  |  |  | 0 | 8916.8603 | 8916.8603 | 8916.8603 | 8916.8603 | 8916.8603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4068 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16679.3515 | 0.2 | 0.3 | 26019.7884 |  |  |  |  | 0 | 5655.5588 | 5655.5588 | 5655.5588 | 5655.5588 | 5655.5588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4069 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 17388.5419 | 0.2 | 0.3 | 27126.1254 |  |  |  |  | 0 | 8076.7773 | 8076.7773 | 8076.7773 | 8076.7773 | 8076.7773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4070 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 29578.4929 | 0.2 | 0.3 | 46142.4489 |  |  |  |  | 0 | 8017.5913 | 8017.5913 | 8017.5913 | 8017.5913 | 8017.5913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4071 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 25791.5969 | 0.2 | 0.3 | 40234.8911 |  |  |  |  | 0 | 5202.9367 | 5202.9367 | 5202.9367 | 5202.9367 | 5202.9367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4072 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 27779.682 | 0.2 | 0.3 | 43336.3039 |  |  |  |  | 0 | 3941.5347 | 3941.5347 | 3941.5347 | 3941.5347 | 3941.5347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4073 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.8095 | 0.2 | 0.3 | 26017.3828 |  |  |  |  | 0 | 8390.0125 | 8390.0125 | 8390.0125 | 8390.0125 | 8390.0125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4074 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 21670.3275 | 0.2 | 0.3 | 33805.711 |  |  |  |  | 0 | 5203.1937 | 5203.1937 | 5203.1937 | 5203.1937 | 5203.1937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4075 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16685.5356 | 0.2 | 0.3 | 26029.4355 |  |  |  |  | 0 | 331.2535 | 331.2535 | 331.2535 | 331.2535 | 331.2535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4076 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 2430.367 | 2430.367 | 2430.367 | 2430.367 | 2430.367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4077 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.1703 | 0.2 | 0.3 | 26019.5057 |  |  |  |  | 0 | 2978.9951 | 2978.9951 | 2978.9951 | 2978.9951 | 2978.9951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4078 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.3772 | 0.2 | 0.3 | 26019.8284 |  |  |  |  | 0 | 4786.7995 | 4786.7995 | 4786.7995 | 4786.7995 | 4786.7995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4079 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 16408.9237 | 0.2 | 0.3 | 25597.921 |  |  |  |  | 0 | 179.3458 | 179.3458 | 179.3458 | 179.3458 | 179.3458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4080 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 25122.5784 | 0.2 | 0.3 | 39191.2223 |  |  |  |  | 0 | 9000.7757 | 9000.7757 | 9000.7757 | 9000.7757 | 9000.7757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4081 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 20422.9094 | 0.2 | 0.3 | 31859.7387 |  |  |  |  | 0 | 160.353 | 160.353 | 160.353 | 160.353 | 160.353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4082 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 19310.5077 | 0.2 | 0.3 | 30124.3921 |  |  |  |  | 0 | 7595.7768 | 7595.7768 | 7595.7768 | 7595.7768 | 7595.7768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4083 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 28808.2467 | 0.2 | 0.3 | 44940.8648 |  |  |  |  | 0 | 9187.56 | 9187.56 | 9187.56 | 9187.56 | 9187.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4084 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 34794.2084 | 0.2 | 0.3 | 54278.9651 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4085 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 20848.8907 | 0.2 | 0.3 | 32524.2695 |  |  |  |  | 0 | 5201.7852 | 5201.7852 | 5201.7852 | 5201.7852 | 5201.7852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4086 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 13532.467 | 0.2 | 0.3 | 21110.6485 |  |  |  |  | 0 | 5444.7989 | 5444.7989 | 5444.7989 | 5444.7989 | 5444.7989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4087 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 33360.6656 | 0.2 | 0.3 | 52042.6383 |  |  |  |  | 0 | 5184.5863 | 5184.5863 | 5184.5863 | 5184.5863 | 5184.5863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4088 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16671.5712 | 0.2 | 0.3 | 26007.6511 |  |  |  |  | 0 | 5342.7027 | 5342.7027 | 5342.7027 | 5342.7027 | 5342.7027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4089 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 24332.6431 | 0.2 | 0.3 | 37958.9233 |  |  |  |  | 0 | 5394.2904 | 5394.2904 | 5394.2904 | 5394.2904 | 5394.2904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4090 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 28031.1155 | 0.2 | 0.3 | 43728.5401 |  |  |  |  | 0 | 5195.9194 | 5195.9194 | 5195.9194 | 5195.9194 | 5195.9194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4091 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 5481.1841 | 0.2 | 0.3 | 8550.6472 |  |  |  |  | 0 | 5541.8013 | 5541.8013 | 5541.8013 | 5541.8013 | 5541.8013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4092 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 22393.358 | 0.2 | 0.3 | 34933.6385 |  |  |  |  | 0 | 5201.7474 | 5201.7474 | 5201.7474 | 5201.7474 | 5201.7474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4093 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 1783.1917 | 0.2 | 0.3 | 2781.7791 |  |  |  |  | 0 | 5198.3598 | 5198.3598 | 5198.3598 | 5198.3598 | 5198.3598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4094 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 3888.5986 | 0.2 | 0.3 | 6066.2138 |  |  |  |  | 0 | 6170.6725 | 6170.6725 | 6170.6725 | 6170.6725 | 6170.6725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4095 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 21680.5128 | 0.2 | 0.3 | 33821.6 |  |  |  |  | 0 | 9661.0576 | 9661.0576 | 9661.0576 | 9661.0576 | 9661.0576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4096 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 19662.9367 | 0.2 | 0.3 | 30674.1812 |  |  |  |  | 0 | 3313.1983 | 3313.1983 | 3313.1983 | 3313.1983 | 3313.1983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4097 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 7827.8701 | 0.2 | 0.3 | 12211.4774 |  |  |  |  | 0 | 10327.2632 | 10327.2632 | 10327.2632 | 10327.2632 | 10327.2632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4098 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 16973.4402 | 0.2 | 0.3 | 26478.5667 |  |  |  |  | 0 | 6820.7452 | 6820.7452 | 6820.7452 | 6820.7452 | 6820.7452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4099 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 16700.5256 | 0.2 | 0.3 | 26052.8199 |  |  |  |  | 0 | 7013.6815 | 7013.6815 | 7013.6815 | 7013.6815 | 7013.6815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4100 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 16968.6889 | 0.2 | 0.3 | 26471.1546 |  |  |  |  | 0 | 7154.2533 | 7154.2533 | 7154.2533 | 7154.2533 | 7154.2533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4101 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 24141.8689 | 0.2 | 0.3 | 37661.3154 |  |  |  |  | 0 | 7004.988 | 7004.988 | 7004.988 | 7004.988 | 7004.988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4102 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 21627.3521 | 0.2 | 0.3 | 33738.6692 |  |  |  |  | 0 | 5281.4239 | 5281.4239 | 5281.4239 | 5281.4239 | 5281.4239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4103 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 17256.416 | 0.2 | 0.3 | 26920.009 |  |  |  |  | 0 | 9172.3858 | 9172.3858 | 9172.3858 | 9172.3858 | 9172.3858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4104 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 18169.3333 | 0.2 | 0.3 | 28344.1599 |  |  |  |  | 0 | 9781.2463 | 9781.2463 | 9781.2463 | 9781.2463 | 9781.2463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4105 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 11118.1057 | 0.2 | 0.3 | 17344.2449 |  |  |  |  | 0 | 9033.3309 | 9033.3309 | 9033.3309 | 9033.3309 | 9033.3309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4106 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 21871.2044 | 0.2 | 0.3 | 34119.0789 |  |  |  |  | 0 | 4939.8344 | 4939.8344 | 4939.8344 | 4939.8344 | 4939.8344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4107 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 8591.2157 | 0.2 | 0.3 | 13402.2965 |  |  |  |  | 0 | 6356.4004 | 6356.4004 | 6356.4004 | 6356.4004 | 6356.4004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4108 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 18367.5795 | 0.2 | 0.3 | 28653.424 |  |  |  |  | 0 | 5752.6433 | 5752.6433 | 5752.6433 | 5752.6433 | 5752.6433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4109 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 27786.15 | 0.2 | 0.3 | 43346.394 |  |  |  |  | 0 | 9894.2815 | 9894.2815 | 9894.2815 | 9894.2815 | 9894.2815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4110 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 16672.2557 | 0.2 | 0.3 | 26008.7188 |  |  |  |  | 0 | 4277.1142 | 4277.1142 | 4277.1142 | 4277.1142 | 4277.1142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4111 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 19277.9104 | 0.2 | 0.3 | 30073.5402 |  |  |  |  | 0 | 3352.2745 | 3352.2745 | 3352.2745 | 3352.2745 | 3352.2745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4112 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 13325.6574 | 13325.6574 | 13325.6574 | 13325.6574 | 13325.6574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4113 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 16671.9109 | 0.2 | 0.3 | 26008.181 |  |  |  |  | 0 | 3373.6103 | 3373.6103 | 3373.6103 | 3373.6103 | 3373.6103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4114 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 19557.4453 | 0.2 | 0.3 | 30509.6146 |  |  |  |  | 0 | 3440.7976 | 3440.7976 | 3440.7976 | 3440.7976 | 3440.7976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4115 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 17519.938 | 0.2 | 0.3 | 27331.1033 |  |  |  |  | 0 | 5521.4439 | 5521.4439 | 5521.4439 | 5521.4439 | 5521.4439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4116 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 1371.4543 | 0.2 | 0.3 | 2139.4687 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4117 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16151.1493 | 0.2 | 0.3 | 25195.7929 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4118 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 18780.1198 | 0.2 | 0.3 | 29296.9869 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4119 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 31289.4807 | 0.2 | 0.3 | 48811.5898 |  |  |  |  | 0 | 5194.0327 | 5194.0327 | 5194.0327 | 5194.0327 | 5194.0327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4120 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 21403.9431 | 0.2 | 0.3 | 33390.1513 |  |  |  |  | 0 | 4107.5326 | 4107.5326 | 4107.5326 | 4107.5326 | 4107.5326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4121 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 23859.2887 | 0.2 | 0.3 | 37220.4903 |  |  |  |  | 0 | 4714.4504 | 4714.4504 | 4714.4504 | 4714.4504 | 4714.4504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4122 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 21288.067 | 0.2 | 0.3 | 33209.3845 |  |  |  |  | 0 | 6569.0965 | 6569.0965 | 6569.0965 | 6569.0965 | 6569.0965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4123 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 14610.6154 | 0.2 | 0.3 | 22792.56 |  |  |  |  | 0 | 8799.9932 | 8799.9932 | 8799.9932 | 8799.9932 | 8799.9932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4124 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 19674.54 | 0.2 | 0.3 | 30692.2824 |  |  |  |  | 0 | 6696.1931 | 6696.1931 | 6696.1931 | 6696.1931 | 6696.1931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4125 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 17862.8314 | 0.2 | 0.3 | 27866.017 |  |  |  |  | 0 | 3768.4629 | 3768.4629 | 3768.4629 | 3768.4629 | 3768.4629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4126 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 32586.967 | 0.2 | 0.3 | 50835.6685 |  |  |  |  | 0 | 4972.5901 | 4972.5901 | 4972.5901 | 4972.5901 | 4972.5901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4127 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 12537.5937 | 0.2 | 0.3 | 19558.6462 |  |  |  |  | 0 | 4921.0587 | 4921.0587 | 4921.0587 | 4921.0587 | 4921.0587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4128 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 10397.1795 | 0.2 | 0.3 | 16219.6001 |  |  |  |  | 0 | 9440.0241 | 9440.0241 | 9440.0241 | 9440.0241 | 9440.0241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4129 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 24478.0861 | 0.2 | 0.3 | 38185.8143 |  |  |  |  | 0 | 416.9422 | 416.9422 | 416.9422 | 416.9422 | 416.9422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4130 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 24538.6497 | 0.2 | 0.3 | 38280.2935 |  |  |  |  | 0 | 4913.958 | 4913.958 | 4913.958 | 4913.958 | 4913.958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4131 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 25382.8868 | 0.2 | 0.3 | 39597.3034 |  |  |  |  | 0 | 7446.8708 | 7446.8708 | 7446.8708 | 7446.8708 | 7446.8708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4132 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 28745.4935 | 0.2 | 0.3 | 44842.9698 |  |  |  |  | 0 | 6892.7772 | 6892.7772 | 6892.7772 | 6892.7772 | 6892.7772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4133 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 17559.8051 | 0.2 | 0.3 | 27393.2959 |  |  |  |  | 0 | 4150.6811 | 4150.6811 | 4150.6811 | 4150.6811 | 4150.6811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4134 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 20379.6641 | 0.2 | 0.3 | 31792.276 |  |  |  |  | 0 | 5592.8317 | 5592.8317 | 5592.8317 | 5592.8317 | 5592.8317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4135 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 17843.026 | 0.2 | 0.3 | 27835.1206 |  |  |  |  | 0 | 3838.1114 | 3838.1114 | 3838.1114 | 3838.1114 | 3838.1114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4136 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 34442.9358 | 0.2 | 0.3 | 53730.9798 |  |  |  |  | 0 | 3344.6009 | 3344.6009 | 3344.6009 | 3344.6009 | 3344.6009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4137 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 18558.8785 | 0.2 | 0.3 | 28951.8505 |  |  |  |  | 0 | 3652.6241 | 3652.6241 | 3652.6241 | 3652.6241 | 3652.6241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4138 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17073.3401 | 0.2 | 0.3 | 26634.4106 |  |  |  |  | 0 | 7364.6856 | 7364.6856 | 7364.6856 | 7364.6856 | 7364.6856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4139 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 25201.1099 | 0.2 | 0.3 | 39313.7314 |  |  |  |  | 0 | 10482.9104 | 10482.9104 | 10482.9104 | 10482.9104 | 10482.9104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4140 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 25238.0939 | 0.2 | 0.3 | 39371.4264 |  |  |  |  | 0 | 4585.7835 | 4585.7835 | 4585.7835 | 4585.7835 | 4585.7835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4141 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 14195.9197 | 0.2 | 0.3 | 22145.6348 |  |  |  |  | 0 | 2577.7403 | 2577.7403 | 2577.7403 | 2577.7403 | 2577.7403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4142 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 29280.5406 | 0.2 | 0.3 | 45677.6433 |  |  |  |  | 0 | 2450.3627 | 2450.3627 | 2450.3627 | 2450.3627 | 2450.3627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4143 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 28710.9814 | 0.2 | 0.3 | 44789.131 |  |  |  |  | 0 | 7670.8425 | 7670.8425 | 7670.8425 | 7670.8425 | 7670.8425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4144 | PEMBROKE PINES | 110328 | Public | 2036 | 5 | Swales | 66.6667 | 6895.571 | 0.2 | 0.3 | 10757.0908 |  |  |  |  | 0 | 2782.1241 | 2782.1241 | 2782.1241 | 2782.1241 | 2782.1241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4145 | PEMBROKE PINES | 110328 | Public | 2036 | 5 | Swales | 66.6667 | 18993.5649 | 0.2 | 0.3 | 29629.9613 |  |  |  |  | 0 | 392.1481 | 392.1481 | 392.1481 | 392.1481 | 392.1481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4146 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 16675.9813 | 0.2 | 0.3 | 26014.5309 |  |  |  |  | 0 | 4812.4838 | 4812.4838 | 4812.4838 | 4812.4838 | 4812.4838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4147 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 20474.5576 | 0.2 | 0.3 | 31940.3099 |  |  |  |  | 0 | 4712.9041 | 4712.9041 | 4712.9041 | 4712.9041 | 4712.9041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4148 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 42117.8018 | 0.2 | 0.3 | 65703.7708 |  |  |  |  | 0 | 6562.0712 | 6562.0712 | 6562.0712 | 6562.0712 | 6562.0712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4149 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 20920.3762 | 0.2 | 0.3 | 32635.7869 |  |  |  |  | 0 | 7285.7798 | 7285.7798 | 7285.7798 | 7285.7798 | 7285.7798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4150 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 25861.8799 | 0.2 | 0.3 | 40344.5326 |  |  |  |  | 0 | 5894.9479 | 5894.9479 | 5894.9479 | 5894.9479 | 5894.9479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4151 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 24870.3945 | 0.2 | 0.3 | 38797.8155 |  |  |  |  | 0 | 6376.9747 | 6376.9747 | 6376.9747 | 6376.9747 | 6376.9747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4152 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 20123.0639 | 0.2 | 0.3 | 31391.9797 |  |  |  |  | 0 | 9787.1436 | 9787.1436 | 9787.1436 | 9787.1436 | 9787.1436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4153 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 15488.3906 | 0.2 | 0.3 | 24161.8893 |  |  |  |  | 0 | 4739.4254 | 4739.4254 | 4739.4254 | 4739.4254 | 4739.4254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4154 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 12506.4874 | 0.2 | 0.3 | 19510.1203 |  |  |  |  | 0 | 9353.009 | 9353.009 | 9353.009 | 9353.009 | 9353.009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4155 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 24071.709 | 0.2 | 0.3 | 37551.866 |  |  |  |  | 0 | 7174.8292 | 7174.8292 | 7174.8292 | 7174.8292 | 7174.8292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4156 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 11493.7907 | 0.2 | 0.3 | 17930.3134 |  |  |  |  | 0 | 8385.2215 | 8385.2215 | 8385.2215 | 8385.2215 | 8385.2215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4157 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 8175.665 | 0.2 | 0.3 | 12754.0374 |  |  |  |  | 0 | 7267.7302 | 7267.7302 | 7267.7302 | 7267.7302 | 7267.7302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4158 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16680.8381 | 0.2 | 0.3 | 26022.1075 |  |  |  |  | 0 | 9123.4716 | 9123.4716 | 9123.4716 | 9123.4716 | 9123.4716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4159 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 23166.1785 | 0.2 | 0.3 | 36139.2384 |  |  |  |  | 0 | 7431.8807 | 7431.8807 | 7431.8807 | 7431.8807 | 7431.8807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4160 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 15084.0333 | 0.2 | 0.3 | 23531.0919 |  |  |  |  | 0 | 2420.1863 | 2420.1863 | 2420.1863 | 2420.1863 | 2420.1863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4161 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 12144.5535 | 0.2 | 0.3 | 18945.5034 |  |  |  |  | 0 | 170.212 | 170.212 | 170.212 | 170.212 | 170.212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4162 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16691.7379 | 0.2 | 0.3 | 26039.1111 |  |  |  |  | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4163 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16676.9893 | 0.2 | 0.3 | 26016.1033 |  |  |  |  | 0 | 4909.4658 | 4909.4658 | 4909.4658 | 4909.4658 | 4909.4658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4164 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 31360.5928 | 0.2 | 0.3 | 48922.5248 |  |  |  |  | 0 | 4038.6365 | 4038.6365 | 4038.6365 | 4038.6365 | 4038.6365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4165 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 19352.121 | 0.2 | 0.3 | 30189.3088 |  |  |  |  | 0 | 11758.8024 | 11758.8024 | 11758.8024 | 11758.8024 | 11758.8024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4166 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 24493.8305 | 0.2 | 0.3 | 38210.3756 |  |  |  |  | 0 | 9736.2072 | 9736.2072 | 9736.2072 | 9736.2072 | 9736.2072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4167 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 22319.5924 | 0.2 | 0.3 | 34818.5641 |  |  |  |  | 0 | 4567.3216 | 4567.3216 | 4567.3216 | 4567.3216 | 4567.3216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4168 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 23733.7938 | 0.2 | 0.3 | 37024.7183 |  |  |  |  | 0 | 2789.0833 | 2789.0833 | 2789.0833 | 2789.0833 | 2789.0833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4169 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 25121.2454 | 0.2 | 0.3 | 39189.1428 |  |  |  |  | 0 | 7517.6121 | 7517.6121 | 7517.6121 | 7517.6121 | 7517.6121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4170 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 15923.5743 | 0.2 | 0.3 | 24840.776 |  |  |  |  | 0 | 7394.9421 | 7394.9421 | 7394.9421 | 7394.9421 | 7394.9421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4171 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 27387.2051 | 0.2 | 0.3 | 42724.04 |  |  |  |  | 0 | 5202.3613 | 5202.3613 | 5202.3613 | 5202.3613 | 5202.3613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4172 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 14291.8282 | 0.2 | 0.3 | 22295.252 |  |  |  |  | 0 | 7213.3883 | 7213.3883 | 7213.3883 | 7213.3883 | 7213.3883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4173 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 7843.5655 | 7843.5655 | 7843.5655 | 7843.5655 | 7843.5655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4174 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.4269 | 0.2 | 0.3 | 26018.346 |  |  |  |  | 0 | 7915.9776 | 7915.9776 | 7915.9776 | 7915.9776 | 7915.9776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4175 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31386.8137 | 0.2 | 0.3 | 48963.4293 |  |  |  |  | 0 | 6143.4876 | 6143.4876 | 6143.4876 | 6143.4876 | 6143.4876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4176 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4177 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6623 |  |  |  |  | 0 | 5199.4674 | 5199.4674 | 5199.4674 | 5199.4674 | 5199.4674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4178 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31358.6163 | 0.2 | 0.3 | 48919.4414 |  |  |  |  | 0 | 5199.8086 | 5199.8086 | 5199.8086 | 5199.8086 | 5199.8086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4179 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.523 | 0.2 | 0.3 | 26016.9359 |  |  |  |  | 0 | 4500.9164 | 4500.9164 | 4500.9164 | 4500.9164 | 4500.9164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4180 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.8095 | 0.2 | 0.3 | 26017.3828 |  |  |  |  | 0 | 9225.6692 | 9225.6692 | 9225.6692 | 9225.6692 | 9225.6692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4181 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16679.0749 | 0.2 | 0.3 | 26019.3569 |  |  |  |  | 0 | 5202.0307 | 5202.0307 | 5202.0307 | 5202.0307 | 5202.0307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4182 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 17504.4211 | 0.2 | 0.3 | 27306.8969 |  |  |  |  | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4183 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 10570.6281 | 0.2 | 0.3 | 16490.1799 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4184 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 25617.4989 | 0.2 | 0.3 | 39963.2983 |  |  |  |  | 0 | 5202.658 | 5202.658 | 5202.658 | 5202.658 | 5202.658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4185 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 19373.8551 | 0.2 | 0.3 | 30223.214 |  |  |  |  | 0 | 9242.0592 | 9242.0592 | 9242.0592 | 9242.0592 | 9242.0592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4186 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 29419.3833 | 0.2 | 0.3 | 45894.238 |  |  |  |  | 0 | 7372.3296 | 7372.3296 | 7372.3296 | 7372.3296 | 7372.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4187 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 30119.6465 | 0.2 | 0.3 | 46986.6485 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4188 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 26976.2531 | 0.2 | 0.3 | 42082.9548 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4189 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 24248.9389 | 0.2 | 0.3 | 37828.3446 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4190 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 32363.3532 | 0.2 | 0.3 | 50486.831 |  |  |  |  | 0 | 5200.5544 | 5200.5544 | 5200.5544 | 5200.5544 | 5200.5544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4191 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16671.5879 | 0.2 | 0.3 | 26007.6772 |  |  |  |  | 0 | 6549.3929 | 6549.3929 | 6549.3929 | 6549.3929 | 6549.3929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4192 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 1405.6499 | 0.2 | 0.3 | 2192.8139 |  |  |  |  | 0 | 9693.7649 | 9693.7649 | 9693.7649 | 9693.7649 | 9693.7649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4193 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 7705.7402 | 0.2 | 0.3 | 12020.9547 |  |  |  |  | 0 | 9178.4841 | 9178.4841 | 9178.4841 | 9178.4841 | 9178.4841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4194 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 20034.6039 | 0.2 | 0.3 | 31253.9821 |  |  |  |  | 0 | 6438.294 | 6438.294 | 6438.294 | 6438.294 | 6438.294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4195 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 17999.0379 | 0.2 | 0.3 | 28078.4992 |  |  |  |  | 0 | 5426.5029 | 5426.5029 | 5426.5029 | 5426.5029 | 5426.5029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4196 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 24995.6741 | 0.2 | 0.3 | 38993.2516 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4197 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 12590.9241 | 0.2 | 0.3 | 19641.8416 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4198 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 27993.3774 | 0.2 | 0.3 | 43669.6687 |  |  |  |  | 0 | 5202.0209 | 5202.0209 | 5202.0209 | 5202.0209 | 5202.0209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4199 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 521.9216 | 0.2 | 0.3 | 814.1977 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4200 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 7023.3624 | 0.2 | 0.3 | 10956.4453 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4201 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 20520.2803 | 0.2 | 0.3 | 32011.6373 |  |  |  |  | 0 | 7753.6314 | 7753.6314 | 7753.6314 | 7753.6314 | 7753.6314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4202 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 18166.0396 | 0.2 | 0.3 | 28339.0218 |  |  |  |  | 0 | 7860.3132 | 7860.3132 | 7860.3132 | 7860.3132 | 7860.3132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4203 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 18598.2561 | 0.2 | 0.3 | 29013.2795 |  |  |  |  | 0 | 5202.0764 | 5202.0764 | 5202.0764 | 5202.0764 | 5202.0764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4204 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 18643.5537 | 0.2 | 0.3 | 29083.9438 |  |  |  |  | 0 | 5203.0026 | 5203.0026 | 5203.0026 | 5203.0026 | 5203.0026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4205 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 7037.1469 | 0.2 | 0.3 | 10977.9491 |  |  |  |  | 0 | 5202.6442 | 5202.6442 | 5202.6442 | 5202.6442 | 5202.6442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4206 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 23074.9797 | 0.2 | 0.3 | 35996.9684 |  |  |  |  | 0 | 5201.6472 | 5201.6472 | 5201.6472 | 5201.6472 | 5201.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4207 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 28507.7925 | 0.2 | 0.3 | 44472.1564 |  |  |  |  | 0 | 263.1904 | 263.1904 | 263.1904 | 263.1904 | 263.1904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4208 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 16666.3266 | 0.2 | 0.3 | 25999.4695 |  |  |  |  | 0 | 5160.9798 | 5160.9798 | 5160.9798 | 5160.9798 | 5160.9798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4209 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 16669.0893 | 0.2 | 0.3 | 26003.7794 |  |  |  |  | 0 | 9319.3315 | 9319.3315 | 9319.3315 | 9319.3315 | 9319.3315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4210 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 28384.1639 | 0.2 | 0.3 | 44279.2956 |  |  |  |  | 0 | 6434.2529 | 6434.2529 | 6434.2529 | 6434.2529 | 6434.2529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4211 | PEMBROKE PINES | 110347 | Public | 2036 | 5 | Swales | 66.6667 | 26471.9156 | 0.2 | 0.3 | 41296.1883 |  |  |  |  | 0 | 10011.6774 | 10011.6774 | 10011.6774 | 10011.6774 | 10011.6774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4212 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 20253.1505 | 0.2 | 0.3 | 31594.9148 |  |  |  |  | 0 | 1483.9811 | 1483.9811 | 1483.9811 | 1483.9811 | 1483.9811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4213 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16673.1662 | 0.2 | 0.3 | 26010.1393 |  |  |  |  | 0 | 6107.916 | 6107.916 | 6107.916 | 6107.916 | 6107.916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4214 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 23442.0563 | 0.2 | 0.3 | 36569.6078 |  |  |  |  | 0 | 6223.0332 | 6223.0332 | 6223.0332 | 6223.0332 | 6223.0332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4215 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 18315.9808 | 0.2 | 0.3 | 28572.93 |  |  |  |  | 0 | 7664.3748 | 7664.3748 | 7664.3748 | 7664.3748 | 7664.3748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4216 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 17522.5068 | 0.2 | 0.3 | 27335.1106 |  |  |  |  | 0 | 6581.9994 | 6581.9994 | 6581.9994 | 6581.9994 | 6581.9994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4217 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 19831.3155 | 0.2 | 0.3 | 30936.8522 |  |  |  |  | 0 | 6765.8193 | 6765.8193 | 6765.8193 | 6765.8193 | 6765.8193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4218 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 1985.4227 | 0.2 | 0.3 | 3097.2595 |  |  |  |  | 0 | 6862.085 | 6862.085 | 6862.085 | 6862.085 | 6862.085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4219 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 17462.5417 | 0.2 | 0.3 | 27241.5651 |  |  |  |  | 0 | 9004.2539 | 9004.2539 | 9004.2539 | 9004.2539 | 9004.2539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4220 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 4138.7137 | 0.2 | 0.3 | 6456.3933 |  |  |  |  | 0 | 7282.9503 | 7282.9503 | 7282.9503 | 7282.9503 | 7282.9503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4221 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 33004.6065 | 0.2 | 0.3 | 51487.1862 |  |  |  |  | 0 | 7444.424 | 7444.424 | 7444.424 | 7444.424 | 7444.424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4222 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 32158.693 | 0.2 | 0.3 | 50167.5611 |  |  |  |  | 0 | 3715.6433 | 3715.6433 | 3715.6433 | 3715.6433 | 3715.6433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4223 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 11481.5287 | 0.2 | 0.3 | 17911.1848 |  |  |  |  | 0 | 9779.7946 | 9779.7946 | 9779.7946 | 9779.7946 | 9779.7946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4224 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 5786.0919 | 0.2 | 0.3 | 9026.3033 |  |  |  |  | 0 | 9780.8286 | 9780.8286 | 9780.8286 | 9780.8286 | 9780.8286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4225 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 27526.5103 | 0.2 | 0.3 | 42941.356 |  |  |  |  | 0 | 9780.0924 | 9780.0924 | 9780.0924 | 9780.0924 | 9780.0924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4226 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 19718.2139 | 0.2 | 0.3 | 30760.4137 |  |  |  |  | 0 | 9780.2637 | 9780.2637 | 9780.2637 | 9780.2637 | 9780.2637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4227 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 31313.5713 | 0.2 | 0.3 | 48849.1713 |  |  |  |  | 0 | 9781.406 | 9781.406 | 9781.406 | 9781.406 | 9781.406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4228 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 25246.9009 | 0.2 | 0.3 | 39385.1654 |  |  |  |  | 0 | 5117.6517 | 5117.6517 | 5117.6517 | 5117.6517 | 5117.6517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4229 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 20295.0649 | 0.2 | 0.3 | 31660.3013 |  |  |  |  | 0 | 5323.9098 | 5323.9098 | 5323.9098 | 5323.9098 | 5323.9098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4230 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 27581.464 | 0.2 | 0.3 | 43027.0838 |  |  |  |  | 0 | 581.1001 | 581.1001 | 581.1001 | 581.1001 | 581.1001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4231 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 3005.9285 | 0.2 | 0.3 | 4689.2485 |  |  |  |  | 0 | 5782.3928 | 5782.3928 | 5782.3928 | 5782.3928 | 5782.3928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4232 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 47533.1175 | 0.2 | 0.3 | 74151.6632 |  |  |  |  | 0 | 5196.7719 | 5196.7719 | 5196.7719 | 5196.7719 | 5196.7719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4233 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 9.4588 | 0.2 | 0.3 | 14.7557 |  |  |  |  | 0 | 5385.3954 | 5385.3954 | 5385.3954 | 5385.3954 | 5385.3954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4234 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 184.888 | 0.2 | 0.3 | 288.4253 |  |  |  |  | 0 | 8545.3967 | 8545.3967 | 8545.3967 | 8545.3967 | 8545.3967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4235 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17434.834 | 0.2 | 0.3 | 27198.341 |  |  |  |  | 0 | 9827.776 | 9827.776 | 9827.776 | 9827.776 | 9827.776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4236 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 33980.9879 | 0.2 | 0.3 | 53010.3411 |  |  |  |  | 0 | 13970.2439 | 13970.2439 | 13970.2439 | 13970.2439 | 13970.2439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4237 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 25225.1364 | 0.2 | 0.3 | 39351.2128 |  |  |  |  | 0 | 9531.5189 | 9531.5189 | 9531.5189 | 9531.5189 | 9531.5189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4238 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 6298.0432 | 0.2 | 0.3 | 9824.9474 |  |  |  |  | 0 | 9267.477 | 9267.477 | 9267.477 | 9267.477 | 9267.477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4239 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 278.7827 | 0.2 | 0.3 | 434.901 |  |  |  |  | 0 | 9783.1565 | 9783.1565 | 9783.1565 | 9783.1565 | 9783.1565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4240 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 17194.9568 | 0.2 | 0.3 | 26824.1326 |  |  |  |  | 0 | 12718.597 | 12718.597 | 12718.597 | 12718.597 | 12718.597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4241 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 27528.6679 | 0.2 | 0.3 | 42944.722 |  |  |  |  | 0 | 9785.1838 | 9785.1838 | 9785.1838 | 9785.1838 | 9785.1838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4242 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 23892.8423 | 0.2 | 0.3 | 37272.834 |  |  |  |  | 0 | 8580.1017 | 8580.1017 | 8580.1017 | 8580.1017 | 8580.1017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4243 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 7766.7817 | 0.2 | 0.3 | 12116.1794 |  |  |  |  | 0 | 6478.8244 | 6478.8244 | 6478.8244 | 6478.8244 | 6478.8244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4244 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 8520.0471 | 0.2 | 0.3 | 13291.2734 |  |  |  |  | 0 | 5202.1989 | 5202.1989 | 5202.1989 | 5202.1989 | 5202.1989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4245 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 24835.3693 | 0.2 | 0.3 | 38743.1761 |  |  |  |  | 0 | 5201.8927 | 5201.8927 | 5201.8927 | 5201.8927 | 5201.8927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4246 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 27.2549 | 0.2 | 0.3 | 42.5176 |  |  |  |  | 0 | 5202.0719 | 5202.0719 | 5202.0719 | 5202.0719 | 5202.0719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4247 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 22384.7672 | 0.2 | 0.3 | 34920.2368 |  |  |  |  | 0 | 5202.2808 | 5202.2808 | 5202.2808 | 5202.2808 | 5202.2808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4248 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 540.0408 | 0.2 | 0.3 | 842.4636 |  |  |  |  | 0 | 3311.5305 | 3311.5305 | 3311.5305 | 3311.5305 | 3311.5305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4249 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 28390.2158 | 0.2 | 0.3 | 44288.7366 |  |  |  |  | 0 | 10278.2966 | 10278.2966 | 10278.2966 | 10278.2966 | 10278.2966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4250 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16965.0752 | 0.2 | 0.3 | 26465.5173 |  |  |  |  | 0 | 7906.7557 | 7906.7557 | 7906.7557 | 7906.7557 | 7906.7557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4251 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 20938.6527 | 0.2 | 0.3 | 32664.2983 |  |  |  |  | 0 | 12521.9295 | 12521.9295 | 12521.9295 | 12521.9295 | 12521.9295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4252 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16704.1104 | 0.2 | 0.3 | 26058.4122 |  |  |  |  | 0 | 5668.8487 | 5668.8487 | 5668.8487 | 5668.8487 | 5668.8487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4253 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16700.3351 | 0.2 | 0.3 | 26052.5227 |  |  |  |  | 0 | 10402.0056 | 10402.0056 | 10402.0056 | 10402.0056 | 10402.0056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4254 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16679.6448 | 0.2 | 0.3 | 26020.2459 |  |  |  |  | 0 | 10103.7112 | 10103.7112 | 10103.7112 | 10103.7112 | 10103.7112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4255 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 7747.6279 | 0.2 | 0.3 | 12086.2996 |  |  |  |  | 0 | 5202.8678 | 5202.8678 | 5202.8678 | 5202.8678 | 5202.8678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4256 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 8927.7243 | 0.2 | 0.3 | 13927.25 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4257 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16676.6361 | 0.2 | 0.3 | 26015.5524 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4258 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 7530.8742 | 0.2 | 0.3 | 11748.1638 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4259 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 17127.5926 | 0.2 | 0.3 | 26719.0445 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4260 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 32825.6773 | 0.2 | 0.3 | 51208.0565 |  |  |  |  | 0 | 876.6266 | 876.6266 | 876.6266 | 876.6266 | 876.6266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4261 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.0963 | 0.2 | 0.3 | 26016.2703 |  |  |  |  | 0 | 5992.8371 | 5992.8371 | 5992.8371 | 5992.8371 | 5992.8371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4262 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 30484.0028 | 0.2 | 0.3 | 47555.0444 |  |  |  |  | 0 | 8945.0859 | 8945.0859 | 8945.0859 | 8945.0859 | 8945.0859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4263 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16676.7159 | 0.2 | 0.3 | 26015.6768 |  |  |  |  | 0 | 5201.9884 | 5201.9884 | 5201.9884 | 5201.9884 | 5201.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4264 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.2663 | 0.2 | 0.3 | 26016.5354 |  |  |  |  | 0 | 5202.2678 | 5202.2678 | 5202.2678 | 5202.2678 | 5202.2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4265 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 31358.1937 | 0.2 | 0.3 | 48918.7822 |  |  |  |  | 0 | 5202.2408 | 5202.2408 | 5202.2408 | 5202.2408 | 5202.2408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4266 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.8158 | 0.2 | 0.3 | 26017.3926 |  |  |  |  | 0 | 5202.0525 | 5202.0525 | 5202.0525 | 5202.0525 | 5202.0525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4267 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 5202.2193 | 5202.2193 | 5202.2193 | 5202.2193 | 5202.2193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4268 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 26504.9881 | 0.2 | 0.3 | 41347.7814 |  |  |  |  | 0 | 5202.2357 | 5202.2357 | 5202.2357 | 5202.2357 | 5202.2357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4269 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16672.7927 | 0.2 | 0.3 | 26009.5567 |  |  |  |  | 0 | 5202.4453 | 5202.4453 | 5202.4453 | 5202.4453 | 5202.4453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4270 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 542.488 | 542.488 | 542.488 | 542.488 | 542.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4271 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 16750.1473 | 0.2 | 0.3 | 26130.2297 |  |  |  |  | 0 | 13771.3292 | 13771.3292 | 13771.3292 | 13771.3292 | 13771.3292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4272 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 9535.157 | 0.2 | 0.3 | 14874.8449 |  |  |  |  | 0 | 12997.6003 | 12997.6003 | 12997.6003 | 12997.6003 | 12997.6003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4273 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 23031.7939 | 0.2 | 0.3 | 35929.5984 |  |  |  |  | 0 | 5202.1131 | 5202.1131 | 5202.1131 | 5202.1131 | 5202.1131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4274 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 32425.3035 | 0.2 | 0.3 | 50583.4734 |  |  |  |  | 0 | 5202.2854 | 5202.2854 | 5202.2854 | 5202.2854 | 5202.2854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4275 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 33418.8587 | 0.2 | 0.3 | 52133.4196 |  |  |  |  | 0 | 7510.6294 | 7510.6294 | 7510.6294 | 7510.6294 | 7510.6294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4276 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 37759.8826 | 0.2 | 0.3 | 58905.4169 |  |  |  |  | 0 | 8636.3107 | 8636.3107 | 8636.3107 | 8636.3107 | 8636.3107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4277 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 3661.5684 | 0.2 | 0.3 | 5712.0467 |  |  |  |  | 0 | 8501.6652 | 8501.6652 | 8501.6652 | 8501.6652 | 8501.6652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4278 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 25743.1885 | 0.2 | 0.3 | 40159.374 |  |  |  |  | 0 | 8934.1154 | 8934.1154 | 8934.1154 | 8934.1154 | 8934.1154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4279 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 5159.1556 | 0.2 | 0.3 | 8048.2827 |  |  |  |  | 0 | 5716.785 | 5716.785 | 5716.785 | 5716.785 | 5716.785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4280 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 16861.9101 | 0.2 | 0.3 | 26304.5797 |  |  |  |  | 0 | 6802.9328 | 6802.9328 | 6802.9328 | 6802.9328 | 6802.9328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4281 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 20901.4727 | 0.2 | 0.3 | 32606.2974 |  |  |  |  | 0 | 7235.6312 | 7235.6312 | 7235.6312 | 7235.6312 | 7235.6312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4282 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 1797.6995 | 0.2 | 0.3 | 2804.4112 |  |  |  |  | 0 | 7284.9019 | 7284.9019 | 7284.9019 | 7284.9019 | 7284.9019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4283 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 21847.9129 | 0.2 | 0.3 | 34082.7442 |  |  |  |  | 0 | 3138.0693 | 3138.0693 | 3138.0693 | 3138.0693 | 3138.0693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4284 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 1561.7382 | 0.2 | 0.3 | 2436.3116 |  |  |  |  | 0 | 10021.1556 | 10021.1556 | 10021.1556 | 10021.1556 | 10021.1556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4285 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 5684.174 | 0.2 | 0.3 | 8867.3114 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4286 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 17079.5665 | 0.2 | 0.3 | 26644.1238 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4287 | PEMBROKE PINES | 110368 | Private | 2036 | 5 | Swales | 66.6667 | 16075.1571 | 0.2 | 0.3 | 25077.2451 |  |  |  |  | 0 | 5202.23 | 5202.23 | 5202.23 | 5202.23 | 5202.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4288 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 25874.0236 | 0.2 | 0.3 | 40363.4768 |  |  |  |  | 0 | 16649.9034 | 16649.9034 | 16649.9034 | 16649.9034 | 16649.9034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4289 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 19625.1513 | 0.2 | 0.3 | 30615.236 |  |  |  |  | 0 | 2606.1548 | 2606.1548 | 2606.1548 | 2606.1548 | 2606.1548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4290 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16681.5449 | 0.2 | 0.3 | 26023.2101 |  |  |  |  | 0 | 4604.3762 | 4604.3762 | 4604.3762 | 4604.3762 | 4604.3762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4291 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 26979.9161 | 0.2 | 0.3 | 42088.6692 |  |  |  |  | 0 | 4470.5947 | 4470.5947 | 4470.5947 | 4470.5947 | 4470.5947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4292 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 4581.8679 | 0.2 | 0.3 | 7147.714 |  |  |  |  | 0 | 5201.8646 | 5201.8646 | 5201.8646 | 5201.8646 | 5201.8646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4293 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 8231.2595 | 0.2 | 0.3 | 12840.7648 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4294 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 21255.3573 | 0.2 | 0.3 | 33158.3574 |  |  |  |  | 0 | 5202.0162 | 5202.0162 | 5202.0162 | 5202.0162 | 5202.0162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4295 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16717.8543 | 0.2 | 0.3 | 26079.8528 |  |  |  |  | 0 | 5233.1683 | 5233.1683 | 5233.1683 | 5233.1683 | 5233.1683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4296 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 17372.7159 | 0.2 | 0.3 | 27101.4369 |  |  |  |  | 0 | 3785.8099 | 3785.8099 | 3785.8099 | 3785.8099 | 3785.8099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4297 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 3995.9685 | 0.2 | 0.3 | 6233.7109 |  |  |  |  | 0 | 10086.2191 | 10086.2191 | 10086.2191 | 10086.2191 | 10086.2191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4298 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 21666.7441 | 0.2 | 0.3 | 33800.1208 |  |  |  |  | 0 | 6532.4962 | 6532.4962 | 6532.4962 | 6532.4962 | 6532.4962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4299 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 25006.3819 | 0.2 | 0.3 | 39009.9557 |  |  |  |  | 0 | 9424.8417 | 9424.8417 | 9424.8417 | 9424.8417 | 9424.8417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4300 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 34904.1586 | 0.2 | 0.3 | 54450.4874 |  |  |  |  | 0 | 5559.2318 | 5559.2318 | 5559.2318 | 5559.2318 | 5559.2318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4301 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 24208.0538 | 0.2 | 0.3 | 37764.5639 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4302 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 8723.3848 | 0.2 | 0.3 | 13608.4803 |  |  |  |  | 0 | 3090.9638 | 3090.9638 | 3090.9638 | 3090.9638 | 3090.9638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4303 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 16788.4462 | 0.2 | 0.3 | 26189.9761 |  |  |  |  | 0 | 3206.9336 | 3206.9336 | 3206.9336 | 3206.9336 | 3206.9336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4304 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 30897.1064 | 0.2 | 0.3 | 48199.486 |  |  |  |  | 0 | 9455.5413 | 9455.5413 | 9455.5413 | 9455.5413 | 9455.5413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4305 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 25815.5629 | 0.2 | 0.3 | 40272.2781 |  |  |  |  | 0 | 9784.2686 | 9784.2686 | 9784.2686 | 9784.2686 | 9784.2686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4306 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 29745.9399 | 0.2 | 0.3 | 46403.6662 |  |  |  |  | 0 | 5919.8476 | 5919.8476 | 5919.8476 | 5919.8476 | 5919.8476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4307 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 10324.692 | 0.2 | 0.3 | 16106.5195 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4308 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 28510.3161 | 0.2 | 0.3 | 44476.0931 |  |  |  |  | 0 | 5202.1508 | 5202.1508 | 5202.1508 | 5202.1508 | 5202.1508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4309 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 27246.3423 | 0.2 | 0.3 | 42504.2939 |  |  |  |  | 0 | 9780.5501 | 9780.5501 | 9780.5501 | 9780.5501 | 9780.5501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4310 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 484.9167 | 0.2 | 0.3 | 756.47 |  |  |  |  | 0 | 6589.2511 | 6589.2511 | 6589.2511 | 6589.2511 | 6589.2511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4311 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 9291.5139 | 0.2 | 0.3 | 14494.7617 |  |  |  |  | 0 | 5242.8668 | 5242.8668 | 5242.8668 | 5242.8668 | 5242.8668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4312 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 19990.4993 | 0.2 | 0.3 | 31185.179 |  |  |  |  | 0 | 5204.0573 | 5204.0573 | 5204.0573 | 5204.0573 | 5204.0573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4313 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 19869.9031 | 0.2 | 0.3 | 30997.0489 |  |  |  |  | 0 | 5203.5849 | 5203.5849 | 5203.5849 | 5203.5849 | 5203.5849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4314 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 18914.838 | 0.2 | 0.3 | 29507.1473 |  |  |  |  | 0 | 4711.3951 | 4711.3951 | 4711.3951 | 4711.3951 | 4711.3951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4315 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 6247.8092 | 0.2 | 0.3 | 9746.5824 |  |  |  |  | 0 | 2952.4109 | 2952.4109 | 2952.4109 | 2952.4109 | 2952.4109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4316 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 22284.7255 | 0.2 | 0.3 | 34764.1718 |  |  |  |  | 0 | 6131.2732 | 6131.2732 | 6131.2732 | 6131.2732 | 6131.2732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4317 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 37782.1198 | 0.2 | 0.3 | 58940.1069 |  |  |  |  | 0 | 5202.0007 | 5202.0007 | 5202.0007 | 5202.0007 | 5202.0007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4318 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 4456.5483 | 0.2 | 0.3 | 6952.2153 |  |  |  |  | 0 | 8609.4425 | 8609.4425 | 8609.4425 | 8609.4425 | 8609.4425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4319 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 28895.6365 | 0.2 | 0.3 | 45077.1929 |  |  |  |  | 0 | 6051.4496 | 6051.4496 | 6051.4496 | 6051.4496 | 6051.4496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4320 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 17522.4168 | 0.2 | 0.3 | 27334.9702 |  |  |  |  | 0 | 6597.8102 | 6597.8102 | 6597.8102 | 6597.8102 | 6597.8102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4321 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 24537.6141 | 0.2 | 0.3 | 38278.6779 |  |  |  |  | 0 | 8625.098 | 8625.098 | 8625.098 | 8625.098 | 8625.098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4322 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 17471.5577 | 0.2 | 0.3 | 27255.6301 |  |  |  |  | 0 | 5250.163 | 5250.163 | 5250.163 | 5250.163 | 5250.163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4323 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 17245.566 | 0.2 | 0.3 | 26903.083 |  |  |  |  | 0 | 5258.5558 | 5258.5558 | 5258.5558 | 5258.5558 | 5258.5558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4324 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16695.4985 | 0.2 | 0.3 | 26044.9777 |  |  |  |  | 0 | 9.236 | 9.236 | 9.236 | 9.236 | 9.236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4325 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16009.08 | 0.2 | 0.3 | 24974.1648 |  |  |  |  | 0 | 4848.1529 | 4848.1529 | 4848.1529 | 4848.1529 | 4848.1529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4326 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 19653.0976 | 0.2 | 0.3 | 30658.8323 |  |  |  |  | 0 | 5807.0645 | 5807.0645 | 5807.0645 | 5807.0645 | 5807.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4327 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16679.4019 | 0.2 | 0.3 | 26019.867 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4328 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16680.0302 | 0.2 | 0.3 | 26020.8471 |  |  |  |  | 0 | 5196.6333 | 5196.6333 | 5196.6333 | 5196.6333 | 5196.6333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4329 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 15317.806 | 0.2 | 0.3 | 23895.7774 |  |  |  |  | 0 | 5201.8029 | 5201.8029 | 5201.8029 | 5201.8029 | 5201.8029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4330 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 7580.5189 | 0.2 | 0.3 | 11825.6094 |  |  |  |  | 0 | 5116.4567 | 5116.4567 | 5116.4567 | 5116.4567 | 5116.4567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4331 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16778.1421 | 0.2 | 0.3 | 26173.9017 |  |  |  |  | 0 | 369.2884 | 369.2884 | 369.2884 | 369.2884 | 369.2884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4332 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 16677.7193 | 0.2 | 0.3 | 26017.2421 |  |  |  |  | 0 | 9555.2699 | 9555.2699 | 9555.2699 | 9555.2699 | 9555.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4333 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 14374.1912 | 0.2 | 0.3 | 22423.7383 |  |  |  |  | 0 | 7366.2957 | 7366.2957 | 7366.2957 | 7366.2957 | 7366.2957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4334 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 727.4119 | 0.2 | 0.3 | 1134.7625 |  |  |  |  | 0 | 3213.013 | 3213.013 | 3213.013 | 3213.013 | 3213.013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4335 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 22403.2865 | 0.2 | 0.3 | 34949.127 |  |  |  |  | 0 | 5203.7581 | 5203.7581 | 5203.7581 | 5203.7581 | 5203.7581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4336 | PEMBROKE PINES | 110311 | Public | 2036 | 5 | Swales | 66.6667 | 9200.3712 | 0.2 | 0.3 | 14352.5791 |  |  |  |  | 0 | 6473.2361 | 6473.2361 | 6473.2361 | 6473.2361 | 6473.2361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4337 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 7856.8369 | 0.2 | 0.3 | 12256.6656 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4338 | PEMBROKE PINES | 110312 | Public | 2026 | 5 | Swales | 66.6667 | 480.6667 | 0.2 | 0.3 | 749.84 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4339 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 12047.7136 | 0.2 | 0.3 | 18794.4332 |  |  |  |  | 0 | 5201.6245 | 5201.6245 | 5201.6245 | 5201.6245 | 5201.6245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4340 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 27580.9121 | 0.2 | 0.3 | 43026.2229 |  |  |  |  | 0 | 5379.6987 | 5379.6987 | 5379.6987 | 5379.6987 | 5379.6987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4341 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 2878.3411 | 0.2 | 0.3 | 4490.2121 |  |  |  |  | 0 | 962.5798 | 962.5798 | 962.5798 | 962.5798 | 962.5798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4342 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 33624.2272 | 0.2 | 0.3 | 52453.7944 |  |  |  |  | 0 | 8950.5874 | 8950.5874 | 8950.5874 | 8950.5874 | 8950.5874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4343 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 20504.8433 | 0.2 | 0.3 | 31987.5556 |  |  |  |  | 0 | 6691.0487 | 6691.0487 | 6691.0487 | 6691.0487 | 6691.0487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4344 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 18214.4249 | 0.2 | 0.3 | 28414.5029 |  |  |  |  | 0 | 9678.2788 | 9678.2788 | 9678.2788 | 9678.2788 | 9678.2788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4345 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 24018.0188 | 0.2 | 0.3 | 37468.1093 |  |  |  |  | 0 | 4216.047 | 4216.047 | 4216.047 | 4216.047 | 4216.047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4346 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 8333.3097 | 0.2 | 0.3 | 12999.9632 |  |  |  |  | 0 | 5239.1926 | 5239.1926 | 5239.1926 | 5239.1926 | 5239.1926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4347 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 8333.0693 | 0.2 | 0.3 | 12999.5881 |  |  |  |  | 0 | 5203.906 | 5203.906 | 5203.906 | 5203.906 | 5203.906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4348 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16722.2122 | 0.2 | 0.3 | 26086.651 |  |  |  |  | 0 | 6696.116 | 6696.116 | 6696.116 | 6696.116 | 6696.116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4349 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 18421.3604 | 0.2 | 0.3 | 28737.3222 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4350 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 27035.5348 | 0.2 | 0.3 | 42175.4343 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4351 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 26674.3245 | 0.2 | 0.3 | 41611.9463 |  |  |  |  | 0 | 5201.5923 | 5201.5923 | 5201.5923 | 5201.5923 | 5201.5923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4352 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 15347.2504 | 0.2 | 0.3 | 23941.7106 |  |  |  |  | 0 | 8593.4217 | 8593.4217 | 8593.4217 | 8593.4217 | 8593.4217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4353 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 25756.7353 | 0.2 | 0.3 | 40180.5071 |  |  |  |  | 0 | 5246.5642 | 5246.5642 | 5246.5642 | 5246.5642 | 5246.5642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4354 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 21699.4704 | 0.2 | 0.3 | 33851.1738 |  |  |  |  | 0 | 5270.5364 | 5270.5364 | 5270.5364 | 5270.5364 | 5270.5364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4355 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 4959.0654 | 0.2 | 0.3 | 7736.142 |  |  |  |  | 0 | 8796.6983 | 8796.6983 | 8796.6983 | 8796.6983 | 8796.6983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4356 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 15181.9087 | 0.2 | 0.3 | 23683.7776 |  |  |  |  | 0 | 6235.8002 | 6235.8002 | 6235.8002 | 6235.8002 | 6235.8002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4357 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16668.3079 | 0.2 | 0.3 | 26002.5603 |  |  |  |  | 0 | 7059.0377 | 7059.0377 | 7059.0377 | 7059.0377 | 7059.0377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4358 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 22167.5172 | 0.2 | 0.3 | 34581.3268 |  |  |  |  | 0 | 4126.8829 | 4126.8829 | 4126.8829 | 4126.8829 | 4126.8829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4359 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 689.6343 | 0.2 | 0.3 | 1075.8296 |  |  |  |  | 0 | 5313.6227 | 5313.6227 | 5313.6227 | 5313.6227 | 5313.6227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4360 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 8144.0497 | 0.2 | 0.3 | 12704.7176 |  |  |  |  | 0 | 9561.4276 | 9561.4276 | 9561.4276 | 9561.4276 | 9561.4276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4361 | PEMBROKE PINES | 110356 | Private | 2036 | 5 | Swales | 66.6667 | 4367.2623 | 0.2 | 0.3 | 6812.9292 |  |  |  |  | 0 | 5319.4866 | 5319.4866 | 5319.4866 | 5319.4866 | 5319.4866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4362 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 30653.9051 | 0.2 | 0.3 | 47820.092 |  |  |  |  | 0 | 5280.3332 | 5280.3332 | 5280.3332 | 5280.3332 | 5280.3332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4363 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 26236.5125 | 0.2 | 0.3 | 40928.9596 |  |  |  |  | 0 | 5206.2915 | 5206.2915 | 5206.2915 | 5206.2915 | 5206.2915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4364 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17603.3881 | 0.2 | 0.3 | 27461.2854 |  |  |  |  | 0 | 6843.0406 | 6843.0406 | 6843.0406 | 6843.0406 | 6843.0406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4365 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 26273.9781 | 0.2 | 0.3 | 40987.4059 |  |  |  |  | 0 | 5198.2673 | 5198.2673 | 5198.2673 | 5198.2673 | 5198.2673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4366 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 18337.8863 | 0.2 | 0.3 | 28607.1027 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4367 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 26438.0465 | 0.2 | 0.3 | 41243.3526 |  |  |  |  | 0 | 5201.5372 | 5201.5372 | 5201.5372 | 5201.5372 | 5201.5372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4368 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 28753.6934 | 0.2 | 0.3 | 44855.7617 |  |  |  |  | 0 | 8263.8539 | 8263.8539 | 8263.8539 | 8263.8539 | 8263.8539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4369 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 2839.8787 | 0.2 | 0.3 | 4430.2108 |  |  |  |  | 0 | 5309.3146 | 5309.3146 | 5309.3146 | 5309.3146 | 5309.3146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4370 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 10290.2167 | 0.2 | 0.3 | 16052.7381 |  |  |  |  | 0 | 5352.1714 | 5352.1714 | 5352.1714 | 5352.1714 | 5352.1714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4371 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 6371.8424 | 0.2 | 0.3 | 9940.0741 |  |  |  |  | 0 | 4463.8465 | 4463.8465 | 4463.8465 | 4463.8465 | 4463.8465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4372 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 24218.0803 | 0.2 | 0.3 | 37780.2053 |  |  |  |  | 0 | 12481.5521 | 12481.5521 | 12481.5521 | 12481.5521 | 12481.5521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4373 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 30892.1209 | 0.2 | 0.3 | 48191.7086 |  |  |  |  | 0 | 3951.3605 | 3951.3605 | 3951.3605 | 3951.3605 | 3951.3605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4374 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 893.4189 | 0.2 | 0.3 | 1393.7334 |  |  |  |  | 0 | 3052.6108 | 3052.6108 | 3052.6108 | 3052.6108 | 3052.6108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4375 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 15803.4473 | 0.2 | 0.3 | 24653.3777 |  |  |  |  | 0 | 4689.8006 | 4689.8006 | 4689.8006 | 4689.8006 | 4689.8006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4376 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 11766.8534 | 0.2 | 0.3 | 18356.2913 |  |  |  |  | 0 | 5203.5266 | 5203.5266 | 5203.5266 | 5203.5266 | 5203.5266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4377 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 27288.9721 | 0.2 | 0.3 | 42570.7964 |  |  |  |  | 0 | 10361.448 | 10361.448 | 10361.448 | 10361.448 | 10361.448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4378 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 30716.6204 | 0.2 | 0.3 | 47917.9278 |  |  |  |  | 0 | 6981.3917 | 6981.3917 | 6981.3917 | 6981.3917 | 6981.3917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4379 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 19909.8067 | 0.2 | 0.3 | 31059.2985 |  |  |  |  | 0 | 5203.5363 | 5203.5363 | 5203.5363 | 5203.5363 | 5203.5363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4380 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 20659.1779 | 0.2 | 0.3 | 32228.3175 |  |  |  |  | 0 | 9781.9648 | 9781.9648 | 9781.9648 | 9781.9648 | 9781.9648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4381 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 6951.664 | 6951.664 | 6951.664 | 6951.664 | 6951.664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4382 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 5201.7212 | 5201.7212 | 5201.7212 | 5201.7212 | 5201.7212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4383 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 16675.0755 | 0.2 | 0.3 | 26013.1177 |  |  |  |  | 0 | 5201.541 | 5201.541 | 5201.541 | 5201.541 | 5201.541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4384 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 20201.4107 | 0.2 | 0.3 | 31514.2006 |  |  |  |  | 0 | 8074.7476 | 8074.7476 | 8074.7476 | 8074.7476 | 8074.7476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4385 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 18946.0676 | 0.2 | 0.3 | 29555.8655 |  |  |  |  | 0 | 5353.5647 | 5353.5647 | 5353.5647 | 5353.5647 | 5353.5647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4386 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 20312.2908 | 0.2 | 0.3 | 31687.1736 |  |  |  |  | 0 | 5607.8675 | 5607.8675 | 5607.8675 | 5607.8675 | 5607.8675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4387 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 17886.1989 | 0.2 | 0.3 | 27902.4703 |  |  |  |  | 0 | 10451.5392 | 10451.5392 | 10451.5392 | 10451.5392 | 10451.5392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4388 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 32115.2145 | 0.2 | 0.3 | 50099.7347 |  |  |  |  | 0 | 4670.6532 | 4670.6532 | 4670.6532 | 4670.6532 | 4670.6532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4389 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 29661.238 | 0.2 | 0.3 | 46271.5313 |  |  |  |  | 0 | 10602.5228 | 10602.5228 | 10602.5228 | 10602.5228 | 10602.5228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4390 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 33347.6957 | 0.2 | 0.3 | 52022.4052 |  |  |  |  | 0 | 6490.7245 | 6490.7245 | 6490.7245 | 6490.7245 | 6490.7245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4391 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 45428.0473 | 0.2 | 0.3 | 70867.7537 |  |  |  |  | 0 | 5234.281 | 5234.281 | 5234.281 | 5234.281 | 5234.281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4392 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 34602.2477 | 0.2 | 0.3 | 53979.5064 |  |  |  |  | 0 | 9783.0826 | 9783.0826 | 9783.0826 | 9783.0826 | 9783.0826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4393 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 1844.7215 | 0.2 | 0.3 | 2877.7656 |  |  |  |  | 0 | 538.9974 | 538.9974 | 538.9974 | 538.9974 | 538.9974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4394 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 17632.4795 | 0.2 | 0.3 | 27506.6681 |  |  |  |  | 0 | 10208.3726 | 10208.3726 | 10208.3726 | 10208.3726 | 10208.3726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4395 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 16699.6817 | 0.2 | 0.3 | 26051.5034 |  |  |  |  | 0 | 5304.7919 | 5304.7919 | 5304.7919 | 5304.7919 | 5304.7919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4396 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 27016.1681 | 0.2 | 0.3 | 42145.2223 |  |  |  |  | 0 | 5203.15 | 5203.15 | 5203.15 | 5203.15 | 5203.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4397 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 30468.5151 | 0.2 | 0.3 | 47530.8836 |  |  |  |  | 0 | 7163.4343 | 7163.4343 | 7163.4343 | 7163.4343 | 7163.4343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4398 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 22630.3311 | 0.2 | 0.3 | 35303.3166 |  |  |  |  | 0 | 5202.8266 | 5202.8266 | 5202.8266 | 5202.8266 | 5202.8266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4399 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 15823.4631 | 0.2 | 0.3 | 24684.6025 |  |  |  |  | 0 | 4804.4366 | 4804.4366 | 4804.4366 | 4804.4366 | 4804.4366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4400 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 21093.4294 | 0.2 | 0.3 | 32905.7499 |  |  |  |  | 0 | 9782.8082 | 9782.8082 | 9782.8082 | 9782.8082 | 9782.8082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4401 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 19574.9598 | 0.2 | 0.3 | 30536.9373 |  |  |  |  | 0 | 3018.8594 | 3018.8594 | 3018.8594 | 3018.8594 | 3018.8594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4402 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 18768.1269 | 0.2 | 0.3 | 29278.278 |  |  |  |  | 0 | 2439.0712 | 2439.0712 | 2439.0712 | 2439.0712 | 2439.0712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4403 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 16666.7109 | 0.2 | 0.3 | 26000.069 |  |  |  |  | 0 | 4949.2579 | 4949.2579 | 4949.2579 | 4949.2579 | 4949.2579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4404 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 16667.0709 | 0.2 | 0.3 | 26000.6307 |  |  |  |  | 0 | 0.90948 | 0.90948 | 0.90948 | 0.90948 | 0.90948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4405 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 26819.6663 | 0.2 | 0.3 | 41838.6795 |  |  |  |  | 0 | 6195.9511 | 6195.9511 | 6195.9511 | 6195.9511 | 6195.9511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4406 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 5491.3734 | 5491.3734 | 5491.3734 | 5491.3734 | 5491.3734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4407 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8849 | 0.2 | 0.3 | 26000.3404 |  |  |  |  | 0 | 6922.1404 | 6922.1404 | 6922.1404 | 6922.1404 | 6922.1404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4408 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 17494.3003 | 0.2 | 0.3 | 27291.1085 |  |  |  |  | 0 | 5203.0041 | 5203.0041 | 5203.0041 | 5203.0041 | 5203.0041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4409 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 9890.7305 | 0.2 | 0.3 | 15429.5396 |  |  |  |  | 0 | 5203.0213 | 5203.0213 | 5203.0213 | 5203.0213 | 5203.0213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4410 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 7804.7044 | 0.2 | 0.3 | 12175.3389 |  |  |  |  | 0 | 5948.7554 | 5948.7554 | 5948.7554 | 5948.7554 | 5948.7554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4411 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16131.0109 | 0.2 | 0.3 | 25164.3771 |  |  |  |  | 0 | 1674.6 | 1674.6 | 1674.6 | 1674.6 | 1674.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4412 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 40118.9009 | 0.2 | 0.3 | 62585.4854 |  |  |  |  | 0 | 8925.7964 | 8925.7964 | 8925.7964 | 8925.7964 | 8925.7964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4413 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 25268.4256 | 0.2 | 0.3 | 39418.7439 |  |  |  |  | 0 | 5904.6481 | 5904.6481 | 5904.6481 | 5904.6481 | 5904.6481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4414 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 26774.6176 | 0.2 | 0.3 | 41768.4035 |  |  |  |  | 0 | 9694.2511 | 9694.2511 | 9694.2511 | 9694.2511 | 9694.2511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4415 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 26983.0337 | 0.2 | 0.3 | 42093.5325 |  |  |  |  | 0 | 9444.1286 | 9444.1286 | 9444.1286 | 9444.1286 | 9444.1286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4416 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 15534.9403 | 0.2 | 0.3 | 24234.5069 |  |  |  |  | 0 | 5204.4695 | 5204.4695 | 5204.4695 | 5204.4695 | 5204.4695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4417 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 15379.6943 | 0.2 | 0.3 | 23992.3232 |  |  |  |  | 0 | 7037.1094 | 7037.1094 | 7037.1094 | 7037.1094 | 7037.1094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4418 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 13173.0367 | 0.2 | 0.3 | 20549.9372 |  |  |  |  | 0 | 2556.2925 | 2556.2925 | 2556.2925 | 2556.2925 | 2556.2925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4419 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 19962.4035 | 0.2 | 0.3 | 31141.3495 |  |  |  |  | 0 | 2645.8544 | 2645.8544 | 2645.8544 | 2645.8544 | 2645.8544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4420 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16864.1783 | 0.2 | 0.3 | 26308.1182 |  |  |  |  | 0 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4421 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 23621.7288 | 0.2 | 0.3 | 36849.8969 |  |  |  |  | 0 | 5202.6042 | 5202.6042 | 5202.6042 | 5202.6042 | 5202.6042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4422 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 25955.1625 | 0.2 | 0.3 | 40490.0534 |  |  |  |  | 0 | 373.1755 | 373.1755 | 373.1755 | 373.1755 | 373.1755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4423 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 1427.6764 | 0.2 | 0.3 | 2227.1752 |  |  |  |  | 0 | 9470.3224 | 9470.3224 | 9470.3224 | 9470.3224 | 9470.3224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4424 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 15293.8958 | 0.2 | 0.3 | 23858.4774 |  |  |  |  | 0 | 5314.0397 | 5314.0397 | 5314.0397 | 5314.0397 | 5314.0397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4425 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 19344.9159 | 0.2 | 0.3 | 30178.0688 |  |  |  |  | 0 | 5676.9139 | 5676.9139 | 5676.9139 | 5676.9139 | 5676.9139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4426 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 20301.5947 | 0.2 | 0.3 | 31670.4878 |  |  |  |  | 0 | 6928.4159 | 6928.4159 | 6928.4159 | 6928.4159 | 6928.4159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4427 | PEMBROKE PINES | 110338 | Public | 2036 | 5 | Swales | 66.6667 | 259.4792 | 0.2 | 0.3 | 404.7876 |  |  |  |  | 0 | 9872.7528 | 9872.7528 | 9872.7528 | 9872.7528 | 9872.7528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4428 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 16672.141 | 0.2 | 0.3 | 26008.54 |  |  |  |  | 0 | 802.2579 | 802.2579 | 802.2579 | 802.2579 | 802.2579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4429 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 3214.1161 | 0.2 | 0.3 | 5014.0211 |  |  |  |  | 0 | 2203.687 | 2203.687 | 2203.687 | 2203.687 | 2203.687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4430 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 6076.4896 | 0.2 | 0.3 | 9479.3238 |  |  |  |  | 0 | 3994.4284 | 3994.4284 | 3994.4284 | 3994.4284 | 3994.4284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4431 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 43.9563 | 0.2 | 0.3 | 68.5719 |  |  |  |  | 0 | 5201.572 | 5201.572 | 5201.572 | 5201.572 | 5201.572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4432 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 18407.6445 | 0.2 | 0.3 | 28715.9255 |  |  |  |  | 0 | 5903.0333 | 5903.0333 | 5903.0333 | 5903.0333 | 5903.0333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4433 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 37153.0212 | 0.2 | 0.3 | 57958.7131 |  |  |  |  | 0 | 95.1827 | 95.1827 | 95.1827 | 95.1827 | 95.1827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4434 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 9918.5641 | 0.2 | 0.3 | 15472.9599 |  |  |  |  | 0 | 5231.162 | 5231.162 | 5231.162 | 5231.162 | 5231.162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4435 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 32961.2765 | 0.2 | 0.3 | 51419.5914 |  |  |  |  | 0 | 9219.1835 | 9219.1835 | 9219.1835 | 9219.1835 | 9219.1835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4436 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 44658.609 | 0.2 | 0.3 | 69667.43 |  |  |  |  | 0 | 5204.7466 | 5204.7466 | 5204.7466 | 5204.7466 | 5204.7466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4437 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 12755.2373 | 0.2 | 0.3 | 19898.1702 |  |  |  |  | 0 | 5203.6478 | 5203.6478 | 5203.6478 | 5203.6478 | 5203.6478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4438 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 16667.6854 | 0.2 | 0.3 | 26001.5892 |  |  |  |  | 0 | 6221.3002 | 6221.3002 | 6221.3002 | 6221.3002 | 6221.3002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4439 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 30352.7803 | 0.2 | 0.3 | 47350.3372 |  |  |  |  | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4440 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 7034.3693 | 0.2 | 0.3 | 10973.6161 |  |  |  |  | 0 | 7466.0217 | 7466.0217 | 7466.0217 | 7466.0217 | 7466.0217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4441 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 3288.5215 | 0.2 | 0.3 | 5130.0936 |  |  |  |  | 0 | 5952.2268 | 5952.2268 | 5952.2268 | 5952.2268 | 5952.2268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4442 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 8332.8941 | 0.2 | 0.3 | 12999.3148 |  |  |  |  | 0 | 6354.8429 | 6354.8429 | 6354.8429 | 6354.8429 | 6354.8429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4443 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 33461.3584 | 0.2 | 0.3 | 52199.7191 |  |  |  |  | 0 | 5201.1389 | 5201.1389 | 5201.1389 | 5201.1389 | 5201.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4444 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 26117.4811 | 0.2 | 0.3 | 40743.2705 |  |  |  |  | 0 | 12930.7002 | 12930.7002 | 12930.7002 | 12930.7002 | 12930.7002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4445 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 13765.4203 | 0.2 | 0.3 | 21474.0557 |  |  |  |  | 0 | 13000.7779 | 13000.7779 | 13000.7779 | 13000.7779 | 13000.7779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4446 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 25017.5257 | 0.2 | 0.3 | 39027.34 |  |  |  |  | 0 | 14116.7137 | 14116.7137 | 14116.7137 | 14116.7137 | 14116.7137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4447 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 32659.0185 | 0.2 | 0.3 | 50948.0689 |  |  |  |  | 0 | 12872.9973 | 12872.9973 | 12872.9973 | 12872.9973 | 12872.9973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4448 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 17097.2114 | 0.2 | 0.3 | 26671.6498 |  |  |  |  | 0 | 12131.6802 | 12131.6802 | 12131.6802 | 12131.6802 | 12131.6802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4449 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 29482.8222 | 0.2 | 0.3 | 45993.2026 |  |  |  |  | 0 | 7037.1858 | 7037.1858 | 7037.1858 | 7037.1858 | 7037.1858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4450 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16666.646 | 0.2 | 0.3 | 25999.9678 |  |  |  |  | 0 | 6262.0771 | 6262.0771 | 6262.0771 | 6262.0771 | 6262.0771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4451 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6657 | 0.2 | 0.3 | 25999.9985 |  |  |  |  | 0 | 5418.7456 | 5418.7456 | 5418.7456 | 5418.7456 | 5418.7456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4452 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 9968.4317 | 9968.4317 | 9968.4317 | 9968.4317 | 9968.4317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4453 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6091 | 0.2 | 0.3 | 25999.9102 |  |  |  |  | 0 | 6408.9912 | 6408.9912 | 6408.9912 | 6408.9912 | 6408.9912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4454 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 28083.5915 | 0.2 | 0.3 | 43810.4028 |  |  |  |  | 0 | 5202.0608 | 5202.0608 | 5202.0608 | 5202.0608 | 5202.0608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4455 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16173.9544 | 0.2 | 0.3 | 25231.3689 |  |  |  |  | 0 | 5979.035 | 5979.035 | 5979.035 | 5979.035 | 5979.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4456 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 2609.5194 | 2609.5194 | 2609.5194 | 2609.5194 | 2609.5194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4457 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 9764.5773 | 9764.5773 | 9764.5773 | 9764.5773 | 9764.5773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4458 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 25989.9304 | 0.2 | 0.3 | 40544.2914 |  |  |  |  | 0 | 5203.6549 | 5203.6549 | 5203.6549 | 5203.6549 | 5203.6549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4459 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 16666.7713 | 0.2 | 0.3 | 26000.1633 |  |  |  |  | 0 | 5203.9119 | 5203.9119 | 5203.9119 | 5203.9119 | 5203.9119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4460 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 16666.5973 | 0.2 | 0.3 | 25999.8918 |  |  |  |  | 0 | 9783.8234 | 9783.8234 | 9783.8234 | 9783.8234 | 9783.8234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4461 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 23650.0835 | 0.2 | 0.3 | 36894.1302 |  |  |  |  | 0 | 8388.1687 | 8388.1687 | 8388.1687 | 8388.1687 | 8388.1687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4462 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 17512.4636 | 0.2 | 0.3 | 27319.4432 |  |  |  |  | 0 | 8457.5885 | 8457.5885 | 8457.5885 | 8457.5885 | 8457.5885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4463 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 16676.4707 | 0.2 | 0.3 | 26015.2943 |  |  |  |  | 0 | 8557.0591 | 8557.0591 | 8557.0591 | 8557.0591 | 8557.0591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4464 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 16669.6074 | 0.2 | 0.3 | 26004.5875 |  |  |  |  | 0 | 8591.9375 | 8591.9375 | 8591.9375 | 8591.9375 | 8591.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4465 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 16670.7417 | 0.2 | 0.3 | 26006.357 |  |  |  |  | 0 | 8749.6575 | 8749.6575 | 8749.6575 | 8749.6575 | 8749.6575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4466 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 11622.2895 | 0.2 | 0.3 | 18130.7716 |  |  |  |  | 0 | 8886.3927 | 8886.3927 | 8886.3927 | 8886.3927 | 8886.3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4467 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 6685.7394 | 0.2 | 0.3 | 10429.7535 |  |  |  |  | 0 | 7795.405 | 7795.405 | 7795.405 | 7795.405 | 7795.405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4468 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 26535.8435 | 0.2 | 0.3 | 41395.9159 |  |  |  |  | 0 | 2574.0879 | 2574.0879 | 2574.0879 | 2574.0879 | 2574.0879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4469 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 21393.4641 | 0.2 | 0.3 | 33373.8039 |  |  |  |  | 0 | 2626.8327 | 2626.8327 | 2626.8327 | 2626.8327 | 2626.8327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4470 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 32620.8153 | 0.2 | 0.3 | 50888.4718 |  |  |  |  | 0 | 4721.3388 | 4721.3388 | 4721.3388 | 4721.3388 | 4721.3388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4471 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 22373.4051 | 0.2 | 0.3 | 34902.5119 |  |  |  |  | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4472 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 33408.5163 | 0.2 | 0.3 | 52117.2855 |  |  |  |  | 0 | 4497.3211 | 4497.3211 | 4497.3211 | 4497.3211 | 4497.3211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4473 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 17798.8195 | 0.2 | 0.3 | 27766.1584 |  |  |  |  | 0 | 2726.7302 | 2726.7302 | 2726.7302 | 2726.7302 | 2726.7302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4474 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 16204.9778 | 0.2 | 0.3 | 25279.7654 |  |  |  |  | 0 | 4312.471 | 4312.471 | 4312.471 | 4312.471 | 4312.471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4475 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 27767.9266 | 0.2 | 0.3 | 43317.9655 |  |  |  |  | 0 | 9164.4798 | 9164.4798 | 9164.4798 | 9164.4798 | 9164.4798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4476 | PEMBROKE PINES | 110333 | Private | 2036 | 5 | Swales | 66.6667 | 11427.8299 | 0.2 | 0.3 | 17827.4146 |  |  |  |  | 0 | 6502.0199 | 6502.0199 | 6502.0199 | 6502.0199 | 6502.0199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4477 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 18021.3946 | 0.2 | 0.3 | 28113.3756 |  |  |  |  | 0 | 5200.9628 | 5200.9628 | 5200.9628 | 5200.9628 | 5200.9628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4478 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 19755.9189 | 0.2 | 0.3 | 30819.2335 |  |  |  |  | 0 | 2599.8778 | 2599.8778 | 2599.8778 | 2599.8778 | 2599.8778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4479 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17767.7705 | 0.2 | 0.3 | 27717.7219 |  |  |  |  | 0 | 6881.0901 | 6881.0901 | 6881.0901 | 6881.0901 | 6881.0901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4480 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 8977.7073 | 0.2 | 0.3 | 14005.2233 |  |  |  |  | 0 | 5204.617 | 5204.617 | 5204.617 | 5204.617 | 5204.617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4481 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 16703.5383 | 0.2 | 0.3 | 26057.5198 |  |  |  |  | 0 | 5204.953 | 5204.953 | 5204.953 | 5204.953 | 5204.953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4482 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 16708.1626 | 0.2 | 0.3 | 26064.7337 |  |  |  |  | 0 | 9781.3425 | 9781.3425 | 9781.3425 | 9781.3425 | 9781.3425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4483 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 23808.0627 | 0.2 | 0.3 | 37140.5778 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4484 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 2205.2098 | 0.2 | 0.3 | 3440.1273 |  |  |  |  | 0 | 9584.7322 | 9584.7322 | 9584.7322 | 9584.7322 | 9584.7322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4485 | PEMBROKE PINES | 110338 | Public | 2036 | 5 | Swales | 66.6667 | 26308.7856 | 0.2 | 0.3 | 41041.7055 |  |  |  |  | 0 | 5202.9116 | 5202.9116 | 5202.9116 | 5202.9116 | 5202.9116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4486 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 19688.6561 | 0.2 | 0.3 | 30714.3035 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4487 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 33838.1875 | 0.2 | 0.3 | 52787.5724 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4488 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 33320.5169 | 0.2 | 0.3 | 51980.0063 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4489 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 27447.9133 | 0.2 | 0.3 | 42818.7448 |  |  |  |  | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4490 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 24502.3403 | 0.2 | 0.3 | 38223.6508 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4491 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 33360.4009 | 0.2 | 0.3 | 52042.2254 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4492 | PEMBROKE PINES | 110311 | Private | 2036 | 5 | Swales | 66.6667 | 27307.1215 | 0.2 | 0.3 | 42599.1096 |  |  |  |  | 0 | 1070.5843 | 1070.5843 | 1070.5843 | 1070.5843 | 1070.5843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4493 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 4145.0669 | 0.2 | 0.3 | 6466.3044 |  |  |  |  | 0 | 5394.9551 | 5394.9551 | 5394.9551 | 5394.9551 | 5394.9551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4494 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 16751.8409 | 0.2 | 0.3 | 26132.8718 |  |  |  |  | 0 | 7969.3168 | 7969.3168 | 7969.3168 | 7969.3168 | 7969.3168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4495 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 5701.3652 | 0.2 | 0.3 | 8894.1297 |  |  |  |  | 0 | 8733.2333 | 8733.2333 | 8733.2333 | 8733.2333 | 8733.2333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4496 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 10999.19 | 0.2 | 0.3 | 17158.7364 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4497 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 8332.4798 | 0.2 | 0.3 | 12998.6685 |  |  |  |  | 0 | 5200.9829 | 5200.9829 | 5200.9829 | 5200.9829 | 5200.9829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4498 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 30667.4041 | 0.2 | 0.3 | 47841.1504 |  |  |  |  | 0 | 5614.0068 | 5614.0068 | 5614.0068 | 5614.0068 | 5614.0068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4499 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 24280.2947 | 0.2 | 0.3 | 37877.2597 |  |  |  |  | 0 | 8662.1324 | 8662.1324 | 8662.1324 | 8662.1324 | 8662.1324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4500 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 18728.577 | 0.2 | 0.3 | 29216.5801 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4501 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 20831.3881 | 0.2 | 0.3 | 32496.9655 |  |  |  |  | 0 | 9778.8223 | 9778.8223 | 9778.8223 | 9778.8223 | 9778.8223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4502 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 20747.9642 | 0.2 | 0.3 | 32366.8242 |  |  |  |  | 0 | 4366.2484 | 4366.2484 | 4366.2484 | 4366.2484 | 4366.2484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4503 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 21809.0875 | 0.2 | 0.3 | 34022.1764 |  |  |  |  | 0 | 2341.628 | 2341.628 | 2341.628 | 2341.628 | 2341.628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4504 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 18892.8787 | 0.2 | 0.3 | 29472.8907 |  |  |  |  | 0 | 3012.5694 | 3012.5694 | 3012.5694 | 3012.5694 | 3012.5694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4505 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6151 | 0.2 | 0.3 | 25999.9195 |  |  |  |  | 0 | 6700.8519 | 6700.8519 | 6700.8519 | 6700.8519 | 6700.8519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4506 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4507 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8648 | 0.2 | 0.3 | 26000.3091 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4508 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 16666.4091 | 0.2 | 0.3 | 25999.5981 |  |  |  |  | 0 | 9782.6359 | 9782.6359 | 9782.6359 | 9782.6359 | 9782.6359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4509 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 17047.0849 | 0.2 | 0.3 | 26593.4524 |  |  |  |  | 0 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4510 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 26037.2827 | 0.2 | 0.3 | 40618.1611 |  |  |  |  | 0 | 9735.304 | 9735.304 | 9735.304 | 9735.304 | 9735.304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4511 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 15506.2461 | 0.2 | 0.3 | 24189.7439 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4512 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 16598.4124 | 0.2 | 0.3 | 25893.5233 |  |  |  |  | 0 | 5201.6426 | 5201.6426 | 5201.6426 | 5201.6426 | 5201.6426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4513 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6698 | 0.2 | 0.3 | 26000.0049 |  |  |  |  | 0 | 5207.5402 | 5207.5402 | 5207.5402 | 5207.5402 | 5207.5402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4514 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 16666.835 | 0.2 | 0.3 | 26000.2626 |  |  |  |  | 0 | 5200.8517 | 5200.8517 | 5200.8517 | 5200.8517 | 5200.8517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4515 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 15153.837 | 0.2 | 0.3 | 23639.9857 |  |  |  |  | 0 | 5200.5902 | 5200.5902 | 5200.5902 | 5200.5902 | 5200.5902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4516 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 24200.2215 | 0.2 | 0.3 | 37752.3456 |  |  |  |  | 0 | 6014.9546 | 6014.9546 | 6014.9546 | 6014.9546 | 6014.9546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4517 | PEMBROKE PINES | 110368 | Public | 2036 | 5 | Swales | 66.6667 | 24183.8658 | 0.2 | 0.3 | 37726.8306 |  |  |  |  | 0 | 5323.1822 | 5323.1822 | 5323.1822 | 5323.1822 | 5323.1822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4518 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 22957.5073 | 0.2 | 0.3 | 35813.7114 |  |  |  |  | 0 | 5289.0276 | 5289.0276 | 5289.0276 | 5289.0276 | 5289.0276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4519 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 16749.1784 | 0.2 | 0.3 | 26128.7183 |  |  |  |  | 0 | 5114.6081 | 5114.6081 | 5114.6081 | 5114.6081 | 5114.6081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4520 | PEMBROKE PINES | 110303 | Private | 2036 | 5 | Swales | 66.6667 | 24205.7907 | 0.2 | 0.3 | 37761.0334 |  |  |  |  | 0 | 9782.3863 | 9782.3863 | 9782.3863 | 9782.3863 | 9782.3863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4521 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 9508.7294 | 0.2 | 0.3 | 14833.6179 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4522 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 14052.9275 | 0.2 | 0.3 | 21922.5668 |  |  |  |  | 0 | 5200.9655 | 5200.9655 | 5200.9655 | 5200.9655 | 5200.9655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4523 | PEMBROKE PINES | 110357 | Private | 2036 | 5 | Swales | 66.6667 | 8341.9472 | 0.2 | 0.3 | 13013.4376 |  |  |  |  | 0 | 6087.2695 | 6087.2695 | 6087.2695 | 6087.2695 | 6087.2695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4524 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16680.7237 | 0.2 | 0.3 | 26021.9289 |  |  |  |  | 0 | 8846.8225 | 8846.8225 | 8846.8225 | 8846.8225 | 8846.8225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4525 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 16731.3809 | 0.2 | 0.3 | 26100.9542 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4526 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 17219.7911 | 0.2 | 0.3 | 26862.8742 |  |  |  |  | 0 | 8450.2621 | 8450.2621 | 8450.2621 | 8450.2621 | 8450.2621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4527 | PEMBROKE PINES | 110328 | Private | 2036 | 5 | Swales | 66.6667 | 11892.9406 | 0.2 | 0.3 | 18552.9873 |  |  |  |  | 0 | 16.9336 | 16.9336 | 16.9336 | 16.9336 | 16.9336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4528 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 17716.804 | 0.2 | 0.3 | 27638.2142 |  |  |  |  | 0 | 5622.554 | 5622.554 | 5622.554 | 5622.554 | 5622.554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4529 | PEMBROKE PINES | 110338 | Private | 2036 | 5 | Swales | 66.6667 | 16919.4205 | 0.2 | 0.3 | 26394.296 |  |  |  |  | 0 | 9786.518 | 9786.518 | 9786.518 | 9786.518 | 9786.518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4530 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 22716.7652 | 0.2 | 0.3 | 35438.1537 |  |  |  |  | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4531 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 10911.4731 | 0.2 | 0.3 | 17021.8981 |  |  |  |  | 0 | 9427.1596 | 9427.1596 | 9427.1596 | 9427.1596 | 9427.1596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4532 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 20595.6637 | 0.2 | 0.3 | 32129.2354 |  |  |  |  | 0 | 4388.2895 | 4388.2895 | 4388.2895 | 4388.2895 | 4388.2895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4533 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 9502.8023 | 0.2 | 0.3 | 14824.3715 |  |  |  |  | 0 | 6549.8967 | 6549.8967 | 6549.8967 | 6549.8967 | 6549.8967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4534 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 8333.8799 | 0.2 | 0.3 | 13000.8526 |  |  |  |  | 0 | 8444.8264 | 8444.8264 | 8444.8264 | 8444.8264 | 8444.8264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4535 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 13860.5207 | 0.2 | 0.3 | 21622.4123 |  |  |  |  | 0 | 8193.6564 | 8193.6564 | 8193.6564 | 8193.6564 | 8193.6564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4536 | PEMBROKE PINES | 110301 | Public | 2036 | 5 | Swales | 66.6667 | 1725.8127 | 0.2 | 0.3 | 2692.2679 |  |  |  |  | 0 | 5244.874 | 5244.874 | 5244.874 | 5244.874 | 5244.874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4537 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 8434.9838 | 0.2 | 0.3 | 13158.5747 |  |  |  |  | 0 | 5334.6049 | 5334.6049 | 5334.6049 | 5334.6049 | 5334.6049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4538 | PEMBROKE PINES | 110301 | Private | 2036 | 5 | Swales | 66.6667 | 2956.7871 | 0.2 | 0.3 | 4612.5878 |  |  |  |  | 0 | 5137.6885 | 5137.6885 | 5137.6885 | 5137.6885 | 5137.6885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4539 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 10856.1316 | 0.2 | 0.3 | 16935.5653 |  |  |  |  | 0 | 4217.4365 | 4217.4365 | 4217.4365 | 4217.4365 | 4217.4365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4540 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7983 | 0.2 | 0.3 | 26000.2053 |  |  |  |  | 0 | 8080.361 | 8080.361 | 8080.361 | 8080.361 | 8080.361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4541 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 3996.6475 | 0.2 | 0.3 | 6234.77 |  |  |  |  | 0 | 8336.7545 | 8336.7545 | 8336.7545 | 8336.7545 | 8336.7545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4542 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 58.3067 | 0.2 | 0.3 | 90.9585 |  |  |  |  | 0 | 10197.0448 | 10197.0448 | 10197.0448 | 10197.0448 | 10197.0448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4543 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 23192.4181 | 0.2 | 0.3 | 36180.1723 |  |  |  |  | 0 | 5952.1131 | 5952.1131 | 5952.1131 | 5952.1131 | 5952.1131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4544 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 30123.8621 | 0.2 | 0.3 | 46993.2248 |  |  |  |  | 0 | 8833.8731 | 8833.8731 | 8833.8731 | 8833.8731 | 8833.8731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4545 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 31673.0936 | 0.2 | 0.3 | 49410.026 |  |  |  |  | 0 | 5200.4422 | 5200.4422 | 5200.4422 | 5200.4422 | 5200.4422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4546 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 1363.201 | 0.2 | 0.3 | 2126.5936 |  |  |  |  | 0 | 5623.2601 | 5623.2601 | 5623.2601 | 5623.2601 | 5623.2601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4547 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 26109.0187 | 0.2 | 0.3 | 40730.0691 |  |  |  |  | 0 | 9361.7805 | 9361.7805 | 9361.7805 | 9361.7805 | 9361.7805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4548 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 13254.552 | 0.2 | 0.3 | 20677.1011 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4549 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 31134.925 | 0.2 | 0.3 | 48570.483 |  |  |  |  | 0 | 9361.2102 | 9361.2102 | 9361.2102 | 9361.2102 | 9361.2102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4550 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 7468.6092 | 0.2 | 0.3 | 11651.0304 |  |  |  |  | 0 | 7345.8005 | 7345.8005 | 7345.8005 | 7345.8005 | 7345.8005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4551 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 15403.3999 | 0.2 | 0.3 | 24029.3039 |  |  |  |  | 0 | 2597.0992 | 2597.0992 | 2597.0992 | 2597.0992 | 2597.0992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4552 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 2400.3531 | 0.2 | 0.3 | 3744.5509 |  |  |  |  | 0 | 4473.6224 | 4473.6224 | 4473.6224 | 4473.6224 | 4473.6224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4553 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 1799.6342 | 0.2 | 0.3 | 2807.4294 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4554 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 4432.397 | 0.2 | 0.3 | 6914.5393 |  |  |  |  | 0 | 5196.9084 | 5196.9084 | 5196.9084 | 5196.9084 | 5196.9084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4555 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 2671.9202 | 0.2 | 0.3 | 4168.1955 |  |  |  |  | 0 | 1303.4693 | 1303.4693 | 1303.4693 | 1303.4693 | 1303.4693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4556 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 3856.6518 | 0.2 | 0.3 | 6016.3768 |  |  |  |  | 0 | 1376.6 | 1376.6 | 1376.6 | 1376.6 | 1376.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4557 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 24122.1917 | 0.2 | 0.3 | 37630.6191 |  |  |  |  | 0 | 6405.0879 | 6405.0879 | 6405.0879 | 6405.0879 | 6405.0879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4558 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 24512.0729 | 0.2 | 0.3 | 38238.8337 |  |  |  |  | 0 | 5318.6116 | 5318.6116 | 5318.6116 | 5318.6116 | 5318.6116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4559 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 19669.0665 | 0.2 | 0.3 | 30683.7437 |  |  |  |  | 0 | 4277.2508 | 4277.2508 | 4277.2508 | 4277.2508 | 4277.2508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4560 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16801.6221 | 0.2 | 0.3 | 26210.5305 |  |  |  |  | 0 | 8747.2578 | 8747.2578 | 8747.2578 | 8747.2578 | 8747.2578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4561 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 39226.4992 | 0.2 | 0.3 | 61193.3388 |  |  |  |  | 0 | 5211.9866 | 5211.9866 | 5211.9866 | 5211.9866 | 5211.9866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4562 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 25462.7605 | 0.2 | 0.3 | 39721.9064 |  |  |  |  | 0 | 8487.2954 | 8487.2954 | 8487.2954 | 8487.2954 | 8487.2954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4563 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 2020.251 | 0.2 | 0.3 | 3151.5916 |  |  |  |  | 0 | 4265.9277 | 4265.9277 | 4265.9277 | 4265.9277 | 4265.9277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4564 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 16964.6873 | 0.2 | 0.3 | 26464.9122 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4565 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 29135.0797 | 0.2 | 0.3 | 45450.7244 |  |  |  |  | 0 | 8625.493 | 8625.493 | 8625.493 | 8625.493 | 8625.493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4566 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 38526.1285 | 0.2 | 0.3 | 60100.7605 |  |  |  |  | 0 | 7631.4176 | 7631.4176 | 7631.4176 | 7631.4176 | 7631.4176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4567 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 5813.3035 | 0.2 | 0.3 | 9068.7535 |  |  |  |  | 0 | 2699.3543 | 2699.3543 | 2699.3543 | 2699.3543 | 2699.3543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4568 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 41509.9611 | 0.2 | 0.3 | 64755.5393 |  |  |  |  | 0 | 3096.1952 | 3096.1952 | 3096.1952 | 3096.1952 | 3096.1952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4569 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 6589.9271 | 0.2 | 0.3 | 10280.2863 |  |  |  |  | 0 | 3916.9489 | 3916.9489 | 3916.9489 | 3916.9489 | 3916.9489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4570 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 11057.8507 | 0.2 | 0.3 | 17250.2471 |  |  |  |  | 0 | 8462.7756 | 8462.7756 | 8462.7756 | 8462.7756 | 8462.7756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4571 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 2495.5842 | 0.2 | 0.3 | 3893.1114 |  |  |  |  | 0 | 6748.1586 | 6748.1586 | 6748.1586 | 6748.1586 | 6748.1586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4572 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 14205.2917 | 0.2 | 0.3 | 22160.255 |  |  |  |  | 0 | 5204.047 | 5204.047 | 5204.047 | 5204.047 | 5204.047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4573 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 3449.9822 | 0.2 | 0.3 | 5381.9722 |  |  |  |  | 0 | 5202.3681 | 5202.3681 | 5202.3681 | 5202.3681 | 5202.3681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4574 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 15627.0415 | 0.2 | 0.3 | 24378.1847 |  |  |  |  | 0 | 5690.8537 | 5690.8537 | 5690.8537 | 5690.8537 | 5690.8537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4575 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 6894.9712 | 0.2 | 0.3 | 10756.1551 |  |  |  |  | 0 | 3838.482 | 3838.482 | 3838.482 | 3838.482 | 3838.482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4576 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 22629.9344 | 0.2 | 0.3 | 35302.6977 |  |  |  |  | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4577 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 17378.266 | 0.2 | 0.3 | 27110.095 |  |  |  |  | 0 | 7456.3531 | 7456.3531 | 7456.3531 | 7456.3531 | 7456.3531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4578 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 31132.7922 | 0.2 | 0.3 | 48567.1558 |  |  |  |  | 0 | 9778.413 | 9778.413 | 9778.413 | 9778.413 | 9778.413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4579 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 27147.7444 | 0.2 | 0.3 | 42350.4813 |  |  |  |  | 0 | 7350.8131 | 7350.8131 | 7350.8131 | 7350.8131 | 7350.8131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4580 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 28698.6997 | 0.2 | 0.3 | 44769.9716 |  |  |  |  | 0 | 7007.1948 | 7007.1948 | 7007.1948 | 7007.1948 | 7007.1948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4581 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 31009.8667 | 0.2 | 0.3 | 48375.392 |  |  |  |  | 0 | 2839.215 | 2839.215 | 2839.215 | 2839.215 | 2839.215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4582 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 16774.0493 | 0.2 | 0.3 | 26167.517 |  |  |  |  | 0 | 5201.8957 | 5201.8957 | 5201.8957 | 5201.8957 | 5201.8957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4583 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 25721.9134 | 0.2 | 0.3 | 40126.1849 |  |  |  |  | 0 | 5203.1347 | 5203.1347 | 5203.1347 | 5203.1347 | 5203.1347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4584 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 1834.9928 | 0.2 | 0.3 | 2862.5888 |  |  |  |  | 0 | 5203.0733 | 5203.0733 | 5203.0733 | 5203.0733 | 5203.0733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4585 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 28192.4998 | 0.2 | 0.3 | 43980.2997 |  |  |  |  | 0 | 8131.8326 | 8131.8326 | 8131.8326 | 8131.8326 | 8131.8326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4586 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16969.6361 | 0.2 | 0.3 | 26472.6324 |  |  |  |  | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4587 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 18139.3661 | 0.2 | 0.3 | 28297.4111 |  |  |  |  | 0 | 5204.0529 | 5204.0529 | 5204.0529 | 5204.0529 | 5204.0529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4588 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16671.0821 | 0.2 | 0.3 | 26006.8881 |  |  |  |  | 0 | 4849.9087 | 4849.9087 | 4849.9087 | 4849.9087 | 4849.9087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4589 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 23127.1378 | 0.2 | 0.3 | 36078.335 |  |  |  |  | 0 | 8648.549 | 8648.549 | 8648.549 | 8648.549 | 8648.549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4590 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 12007.718 | 0.2 | 0.3 | 18732.0401 |  |  |  |  | 0 | 9545.2177 | 9545.2177 | 9545.2177 | 9545.2177 | 9545.2177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4591 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 15657.2209 | 0.2 | 0.3 | 24425.2646 |  |  |  |  | 0 | 7503.2253 | 7503.2253 | 7503.2253 | 7503.2253 | 7503.2253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4592 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 28021.2316 | 0.2 | 0.3 | 43713.1213 |  |  |  |  | 0 | 6874.964 | 6874.964 | 6874.964 | 6874.964 | 6874.964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4593 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 8260.1675 | 0.2 | 0.3 | 12885.8614 |  |  |  |  | 0 | 5203.4837 | 5203.4837 | 5203.4837 | 5203.4837 | 5203.4837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4594 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 23109.7249 | 0.2 | 0.3 | 36051.1709 |  |  |  |  | 0 | 9782.3112 | 9782.3112 | 9782.3112 | 9782.3112 | 9782.3112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4595 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 11854.8475 | 0.2 | 0.3 | 18493.562 |  |  |  |  | 0 | 5202.9523 | 5202.9523 | 5202.9523 | 5202.9523 | 5202.9523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4596 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 16892.9423 | 0.2 | 0.3 | 26352.9899 |  |  |  |  | 0 | 5202.9977 | 5202.9977 | 5202.9977 | 5202.9977 | 5202.9977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4597 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 323.5323 | 0.2 | 0.3 | 504.7103 |  |  |  |  | 0 | 13952.47 | 13952.47 | 13952.47 | 13952.47 | 13952.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4598 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 27004.3479 | 0.2 | 0.3 | 42126.7827 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4599 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 15173.1767 | 0.2 | 0.3 | 23670.1556 |  |  |  |  | 0 | 7271.1246 | 7271.1246 | 7271.1246 | 7271.1246 | 7271.1246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4600 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 22661.5355 | 0.2 | 0.3 | 35351.9954 |  |  |  |  | 0 | 254.3403 | 254.3403 | 254.3403 | 254.3403 | 254.3403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4601 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 33363.1455 | 0.2 | 0.3 | 52046.507 |  |  |  |  | 0 | 3438.0101 | 3438.0101 | 3438.0101 | 3438.0101 | 3438.0101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4602 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 24544.4521 | 0.2 | 0.3 | 38289.3453 |  |  |  |  | 0 | 5364.711 | 5364.711 | 5364.711 | 5364.711 | 5364.711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4603 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 18885.6046 | 0.2 | 0.3 | 29461.5432 |  |  |  |  | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4604 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 2593.5765 | 0.2 | 0.3 | 4045.9794 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4605 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16987.0737 | 0.2 | 0.3 | 26499.835 |  |  |  |  | 0 | 0.1982 | 0.1982 | 0.1982 | 0.1982 | 0.1982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4606 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 14920.5227 | 0.2 | 0.3 | 23276.0154 |  |  |  |  | 0 | 2434.3835 | 2434.3835 | 2434.3835 | 2434.3835 | 2434.3835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4607 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16669.9253 | 0.2 | 0.3 | 26005.0835 |  |  |  |  | 0 | 4647.2339 | 4647.2339 | 4647.2339 | 4647.2339 | 4647.2339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4608 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 21325.569 | 0.2 | 0.3 | 33267.8876 |  |  |  |  | 0 | 6419.2884 | 6419.2884 | 6419.2884 | 6419.2884 | 6419.2884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4609 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 9005.323 | 0.2 | 0.3 | 14048.3039 |  |  |  |  | 0 | 5283.7309 | 5283.7309 | 5283.7309 | 5283.7309 | 5283.7309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4610 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 13460.8075 | 0.2 | 0.3 | 20998.8596 |  |  |  |  | 0 | 8021.8401 | 8021.8401 | 8021.8401 | 8021.8401 | 8021.8401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4611 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 23821.4169 | 0.2 | 0.3 | 37161.4104 |  |  |  |  | 0 | 3839.6955 | 3839.6955 | 3839.6955 | 3839.6955 | 3839.6955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4612 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 21772.8961 | 0.2 | 0.3 | 33965.718 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4613 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 31207.8128 | 0.2 | 0.3 | 48684.188 |  |  |  |  | 0 | 4154.2752 | 4154.2752 | 4154.2752 | 4154.2752 | 4154.2752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4614 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 27817.1295 | 0.2 | 0.3 | 43394.7221 |  |  |  |  | 0 | 2893.6387 | 2893.6387 | 2893.6387 | 2893.6387 | 2893.6387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4615 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 15679.3975 | 0.2 | 0.3 | 24459.86 |  |  |  |  | 0 | 5201.5908 | 5201.5908 | 5201.5908 | 5201.5908 | 5201.5908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4616 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 16749.1465 | 0.2 | 0.3 | 26128.6686 |  |  |  |  | 0 | 3517.137 | 3517.137 | 3517.137 | 3517.137 | 3517.137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4617 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 15094.0698 | 0.2 | 0.3 | 23546.7489 |  |  |  |  | 0 | 5201.6803 | 5201.6803 | 5201.6803 | 5201.6803 | 5201.6803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4618 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 27298.9039 | 0.2 | 0.3 | 42586.2901 |  |  |  |  | 0 | 6388.5579 | 6388.5579 | 6388.5579 | 6388.5579 | 6388.5579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4619 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 17603.0222 | 0.2 | 0.3 | 27460.7146 |  |  |  |  | 0 | 4304.3003 | 4304.3003 | 4304.3003 | 4304.3003 | 4304.3003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4620 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 15744.9573 | 0.2 | 0.3 | 24562.1333 |  |  |  |  | 0 | 261.8844 | 261.8844 | 261.8844 | 261.8844 | 261.8844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4621 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 7191.6554 | 0.2 | 0.3 | 11218.9824 |  |  |  |  | 0 | 7505.1624 | 7505.1624 | 7505.1624 | 7505.1624 | 7505.1624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4622 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 13096.9104 | 0.2 | 0.3 | 20431.1802 |  |  |  |  | 0 | 4736.258 | 4736.258 | 4736.258 | 4736.258 | 4736.258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4623 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16733.8439 | 0.2 | 0.3 | 26104.7964 |  |  |  |  | 0 | 4486.21 | 4486.21 | 4486.21 | 4486.21 | 4486.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4624 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 25097.84 | 0.2 | 0.3 | 39152.6304 |  |  |  |  | 0 | 5211.6234 | 5211.6234 | 5211.6234 | 5211.6234 | 5211.6234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4625 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 25100.5384 | 0.2 | 0.3 | 39156.8399 |  |  |  |  | 0 | 8510.2248 | 8510.2248 | 8510.2248 | 8510.2248 | 8510.2248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4626 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 31428.7467 | 0.2 | 0.3 | 49028.8449 |  |  |  |  | 0 | 9780.3616 | 9780.3616 | 9780.3616 | 9780.3616 | 9780.3616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4627 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16676.2841 | 0.2 | 0.3 | 26015.0032 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4628 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 11154.9711 | 0.2 | 0.3 | 17401.755 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4629 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 3782.4025 | 0.2 | 0.3 | 5900.548 |  |  |  |  | 0 | 5202.3106 | 5202.3106 | 5202.3106 | 5202.3106 | 5202.3106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4630 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 24052.8236 | 0.2 | 0.3 | 37522.4048 |  |  |  |  | 0 | 5752.447 | 5752.447 | 5752.447 | 5752.447 | 5752.447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4631 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 25086.8891 | 0.2 | 0.3 | 39135.547 |  |  |  |  | 0 | 5201.8481 | 5201.8481 | 5201.8481 | 5201.8481 | 5201.8481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4632 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 13907.7727 | 0.2 | 0.3 | 21696.1254 |  |  |  |  | 0 | 5188.7645 | 5188.7645 | 5188.7645 | 5188.7645 | 5188.7645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4633 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 8971.0055 | 0.2 | 0.3 | 13994.7685 |  |  |  |  | 0 | 12.7314 | 12.7314 | 12.7314 | 12.7314 | 12.7314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4634 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 13945.3956 | 0.2 | 0.3 | 21754.8171 |  |  |  |  | 0 | 5949.8655 | 5949.8655 | 5949.8655 | 5949.8655 | 5949.8655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4635 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 6334.6121 | 0.2 | 0.3 | 9881.9949 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4636 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 17671.5783 | 0.2 | 0.3 | 27567.6621 |  |  |  |  | 0 | 3446.4839 | 3446.4839 | 3446.4839 | 3446.4839 | 3446.4839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4637 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 19896.7659 | 0.2 | 0.3 | 31038.9549 |  |  |  |  | 0 | 1755.0336 | 1755.0336 | 1755.0336 | 1755.0336 | 1755.0336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4638 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 28386.4425 | 0.2 | 0.3 | 44282.8502 |  |  |  |  | 0 | 5197.2496 | 5197.2496 | 5197.2496 | 5197.2496 | 5197.2496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4639 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 15963.2853 | 0.2 | 0.3 | 24902.7251 |  |  |  |  | 0 | 5202.3527 | 5202.3527 | 5202.3527 | 5202.3527 | 5202.3527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4640 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 16698.0761 | 0.2 | 0.3 | 26048.9987 |  |  |  |  | 0 | 2600.672 | 2600.672 | 2600.672 | 2600.672 | 2600.672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4641 | PEMBROKE PINES | 110312 | Private | 2036 | 5 | Swales | 66.6667 | 19254.2465 | 0.2 | 0.3 | 30036.6246 |  |  |  |  | 0 | 2600.8426 | 2600.8426 | 2600.8426 | 2600.8426 | 2600.8426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4642 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 18161.4505 | 0.2 | 0.3 | 28331.8627 |  |  |  |  | 0 | 6126.6779 | 6126.6779 | 6126.6779 | 6126.6779 | 6126.6779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4643 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16802.8103 | 0.2 | 0.3 | 26212.384 |  |  |  |  | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4644 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16810.5711 | 0.2 | 0.3 | 26224.4909 |  |  |  |  | 0 | 1996.3415 | 1996.3415 | 1996.3415 | 1996.3415 | 1996.3415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4645 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 27693.2165 | 0.2 | 0.3 | 43201.4177 |  |  |  |  | 0 | 3205.1413 | 3205.1413 | 3205.1413 | 3205.1413 | 3205.1413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4646 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16914.3513 | 0.2 | 0.3 | 26386.388 |  |  |  |  | 0 | 5229.984 | 5229.984 | 5229.984 | 5229.984 | 5229.984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4647 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 23664.3874 | 0.2 | 0.3 | 36916.4443 |  |  |  |  | 0 | 5203.7566 | 5203.7566 | 5203.7566 | 5203.7566 | 5203.7566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4648 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 17833.0902 | 0.2 | 0.3 | 27819.6207 |  |  |  |  | 0 | 5202.2439 | 5202.2439 | 5202.2439 | 5202.2439 | 5202.2439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4649 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 19720.9464 | 0.2 | 0.3 | 30764.6764 |  |  |  |  | 0 | 9855.1056 | 9855.1056 | 9855.1056 | 9855.1056 | 9855.1056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4650 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 23095.0327 | 0.2 | 0.3 | 36028.2511 |  |  |  |  | 0 | 7296.1609 | 7296.1609 | 7296.1609 | 7296.1609 | 7296.1609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4651 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 12486.3337 | 0.2 | 0.3 | 19478.6805 |  |  |  |  | 0 | 5204.064 | 5204.064 | 5204.064 | 5204.064 | 5204.064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4652 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 6792.2224 | 0.2 | 0.3 | 10595.8669 |  |  |  |  | 0 | 8292.4313 | 8292.4313 | 8292.4313 | 8292.4313 | 8292.4313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4653 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 3601.2643 | 0.2 | 0.3 | 5617.9723 |  |  |  |  | 0 | 6900.7497 | 6900.7497 | 6900.7497 | 6900.7497 | 6900.7497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4654 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 6417.0777 | 0.2 | 0.3 | 10010.6412 |  |  |  |  | 0 | 7871.4902 | 7871.4902 | 7871.4902 | 7871.4902 | 7871.4902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4655 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 2346.294 | 0.2 | 0.3 | 3660.2186 |  |  |  |  | 0 | 5202.2446 | 5202.2446 | 5202.2446 | 5202.2446 | 5202.2446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4656 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 6909.8388 | 0.2 | 0.3 | 10779.3485 |  |  |  |  | 0 | 5202.4019 | 5202.4019 | 5202.4019 | 5202.4019 | 5202.4019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4657 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17137.9426 | 0.2 | 0.3 | 26735.1905 |  |  |  |  | 0 | 7668.836 | 7668.836 | 7668.836 | 7668.836 | 7668.836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4658 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 12436.3409 | 0.2 | 0.3 | 19400.6918 |  |  |  |  | 0 | 7216.8802 | 7216.8802 | 7216.8802 | 7216.8802 | 7216.8802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4659 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 18867.9111 | 0.2 | 0.3 | 29433.9414 |  |  |  |  | 0 | 5203.4807 | 5203.4807 | 5203.4807 | 5203.4807 | 5203.4807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4660 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 35840.8473 | 0.2 | 0.3 | 55911.7218 |  |  |  |  | 0 | 5202.7025 | 5202.7025 | 5202.7025 | 5202.7025 | 5202.7025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4661 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 32594.0869 | 0.2 | 0.3 | 50846.7755 |  |  |  |  | 0 | 5202.4282 | 5202.4282 | 5202.4282 | 5202.4282 | 5202.4282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4662 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 9006.0189 | 0.2 | 0.3 | 14049.3894 |  |  |  |  | 0 | 5107.8988 | 5107.8988 | 5107.8988 | 5107.8988 | 5107.8988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4663 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 14967.4225 | 0.2 | 0.3 | 23349.1792 |  |  |  |  | 0 | 5523.6401 | 5523.6401 | 5523.6401 | 5523.6401 | 5523.6401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4664 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 17866.3375 | 0.2 | 0.3 | 27871.4866 |  |  |  |  | 0 | 5482.4035 | 5482.4035 | 5482.4035 | 5482.4035 | 5482.4035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4665 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 10649.1889 | 0.2 | 0.3 | 16612.7346 |  |  |  |  | 0 | 5361.89 | 5361.89 | 5361.89 | 5361.89 | 5361.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4666 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 41212.4579 | 0.2 | 0.3 | 64291.4344 |  |  |  |  | 0 | 10000.5098 | 10000.5098 | 10000.5098 | 10000.5098 | 10000.5098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4667 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 19545.3207 | 0.2 | 0.3 | 30490.7002 |  |  |  |  | 0 | 5467.0429 | 5467.0429 | 5467.0429 | 5467.0429 | 5467.0429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4668 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16887.9504 | 0.2 | 0.3 | 26345.2026 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4669 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16320.8041 | 0.2 | 0.3 | 25460.4544 |  |  |  |  | 0 | 7994.969 | 7994.969 | 7994.969 | 7994.969 | 7994.969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4670 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 11500.6006 | 0.2 | 0.3 | 17940.9369 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4671 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 7519.3485 | 0.2 | 0.3 | 11730.1837 |  |  |  |  | 0 | 5531.7961 | 5531.7961 | 5531.7961 | 5531.7961 | 5531.7961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4672 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 8096.078 | 0.2 | 0.3 | 12629.8817 |  |  |  |  | 0 | 5939.2456 | 5939.2456 | 5939.2456 | 5939.2456 | 5939.2456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4673 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16671.085 | 0.2 | 0.3 | 26006.8926 |  |  |  |  | 0 | 9227.6177 | 9227.6177 | 9227.6177 | 9227.6177 | 9227.6177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4674 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 4688.3793 | 0.2 | 0.3 | 7313.8717 |  |  |  |  | 0 | 6520.0536 | 6520.0536 | 6520.0536 | 6520.0536 | 6520.0536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4675 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 20134.8207 | 0.2 | 0.3 | 31410.3202 |  |  |  |  | 0 | 10049.2459 | 10049.2459 | 10049.2459 | 10049.2459 | 10049.2459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4676 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 22925.1169 | 0.2 | 0.3 | 35763.1823 |  |  |  |  | 0 | 1927.8127 | 1927.8127 | 1927.8127 | 1927.8127 | 1927.8127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4677 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 18327.4535 | 0.2 | 0.3 | 28590.8275 |  |  |  |  | 0 | 3515.4974 | 3515.4974 | 3515.4974 | 3515.4974 | 3515.4974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4678 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 18804.8597 | 0.2 | 0.3 | 29335.5811 |  |  |  |  | 0 | 5202.9416 | 5202.9416 | 5202.9416 | 5202.9416 | 5202.9416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4679 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 11950.4989 | 11950.4989 | 11950.4989 | 11950.4989 | 11950.4989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4680 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 5213.2303 | 0.2 | 0.3 | 8132.6392 |  |  |  |  | 0 | 7181.6511 | 7181.6511 | 7181.6511 | 7181.6511 | 7181.6511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4681 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 14603.5653 | 0.2 | 0.3 | 22781.5618 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4682 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 15388.317 | 0.2 | 0.3 | 24005.7745 |  |  |  |  | 0 | 9783.7347 | 9783.7347 | 9783.7347 | 9783.7347 | 9783.7347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4683 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 2673.7011 | 0.2 | 0.3 | 4170.9737 |  |  |  |  | 0 | 5202.6325 | 5202.6325 | 5202.6325 | 5202.6325 | 5202.6325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4684 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16673.7762 | 0.2 | 0.3 | 26011.0909 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4685 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16691.8395 | 0.2 | 0.3 | 26039.2696 |  |  |  |  | 0 | 5202.7675 | 5202.7675 | 5202.7675 | 5202.7675 | 5202.7675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4686 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16763.9891 | 0.2 | 0.3 | 26151.823 |  |  |  |  | 0 | 8209.5181 | 8209.5181 | 8209.5181 | 8209.5181 | 8209.5181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4687 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 9782.5181 | 0.2 | 0.3 | 15260.7282 |  |  |  |  | 0 | 5293.7076 | 5293.7076 | 5293.7076 | 5293.7076 | 5293.7076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4688 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 22572.8333 | 0.2 | 0.3 | 35213.62 |  |  |  |  | 0 | 5200.8653 | 5200.8653 | 5200.8653 | 5200.8653 | 5200.8653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4689 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 21599.5125 | 0.2 | 0.3 | 33695.2396 |  |  |  |  | 0 | 2747.7683 | 2747.7683 | 2747.7683 | 2747.7683 | 2747.7683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4690 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 29274.5316 | 0.2 | 0.3 | 45668.2693 |  |  |  |  | 0 | 5186.3502 | 5186.3502 | 5186.3502 | 5186.3502 | 5186.3502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4691 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 25017.5153 | 0.2 | 0.3 | 39027.3239 |  |  |  |  | 0 | 5335.042 | 5335.042 | 5335.042 | 5335.042 | 5335.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4692 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 26457.9729 | 0.2 | 0.3 | 41274.4377 |  |  |  |  | 0 | 2340.6449 | 2340.6449 | 2340.6449 | 2340.6449 | 2340.6449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4693 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 23449.4482 | 0.2 | 0.3 | 36581.1392 |  |  |  |  | 0 | 5194.616 | 5194.616 | 5194.616 | 5194.616 | 5194.616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4694 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 12755.6597 | 0.2 | 0.3 | 19898.8291 |  |  |  |  | 0 | 5202.9037 | 5202.9037 | 5202.9037 | 5202.9037 | 5202.9037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4695 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 12755.8254 | 0.2 | 0.3 | 19899.0876 |  |  |  |  | 0 | 5202.283 | 5202.283 | 5202.283 | 5202.283 | 5202.283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4696 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 12756.2018 | 0.2 | 0.3 | 19899.6748 |  |  |  |  | 0 | 5204.7285 | 5204.7285 | 5204.7285 | 5204.7285 | 5204.7285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4697 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 12755.7386 | 0.2 | 0.3 | 19898.9522 |  |  |  |  | 0 | 1619.6465 | 1619.6465 | 1619.6465 | 1619.6465 | 1619.6465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4698 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 12755.8643 | 0.2 | 0.3 | 19899.1483 |  |  |  |  | 0 | 2624.2096 | 2624.2096 | 2624.2096 | 2624.2096 | 2624.2096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4699 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 12755.5221 | 0.2 | 0.3 | 19898.6144 |  |  |  |  | 0 | 4661.5632 | 4661.5632 | 4661.5632 | 4661.5632 | 4661.5632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4700 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 12755.9789 | 0.2 | 0.3 | 19899.327 |  |  |  |  | 0 | 9799.1124 | 9799.1124 | 9799.1124 | 9799.1124 | 9799.1124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4701 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 12756.3492 | 0.2 | 0.3 | 19899.9048 |  |  |  |  | 0 | 7078.1143 | 7078.1143 | 7078.1143 | 7078.1143 | 7078.1143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4702 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 12767.917 | 0.2 | 0.3 | 19917.9505 |  |  |  |  | 0 | 6111.5234 | 6111.5234 | 6111.5234 | 6111.5234 | 6111.5234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4703 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 9099.1173 | 0.2 | 0.3 | 14194.6229 |  |  |  |  | 0 | 9663.8562 | 9663.8562 | 9663.8562 | 9663.8562 | 9663.8562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4704 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 9763.8945 | 0.2 | 0.3 | 15231.6755 |  |  |  |  | 0 | 9753.5339 | 9753.5339 | 9753.5339 | 9753.5339 | 9753.5339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4705 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 18359.9709 | 0.2 | 0.3 | 28641.5546 |  |  |  |  | 0 | 7404.1406 | 7404.1406 | 7404.1406 | 7404.1406 | 7404.1406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4706 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 18900.3276 | 0.2 | 0.3 | 29484.5111 |  |  |  |  | 0 | 9045.661 | 9045.661 | 9045.661 | 9045.661 | 9045.661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4707 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 14404.0675 | 0.2 | 0.3 | 22470.3454 |  |  |  |  | 0 | 8304.8005 | 8304.8005 | 8304.8005 | 8304.8005 | 8304.8005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4708 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 18785.1826 | 0.2 | 0.3 | 29304.8849 |  |  |  |  | 0 | 5972.3354 | 5972.3354 | 5972.3354 | 5972.3354 | 5972.3354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4709 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 5887.5759 | 0.2 | 0.3 | 9184.6185 |  |  |  |  | 0 | 5205.5506 | 5205.5506 | 5205.5506 | 5205.5506 | 5205.5506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4710 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 17202.1219 | 0.2 | 0.3 | 26835.3102 |  |  |  |  | 0 | 9543.7748 | 9543.7748 | 9543.7748 | 9543.7748 | 9543.7748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4711 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 18694.2587 | 0.2 | 0.3 | 29163.0436 |  |  |  |  | 0 | 5157.3566 | 5157.3566 | 5157.3566 | 5157.3566 | 5157.3566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4712 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 3580.8529 | 3580.8529 | 3580.8529 | 3580.8529 | 3580.8529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4713 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16668.9377 | 0.2 | 0.3 | 26003.5428 |  |  |  |  | 0 | 2578.7614 | 2578.7614 | 2578.7614 | 2578.7614 | 2578.7614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4714 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 19323.2283 | 0.2 | 0.3 | 30144.2361 |  |  |  |  | 0 | 541.3897 | 541.3897 | 541.3897 | 541.3897 | 541.3897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4715 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 15151.6113 | 0.2 | 0.3 | 23636.5136 |  |  |  |  | 0 | 5202.6267 | 5202.6267 | 5202.6267 | 5202.6267 | 5202.6267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4716 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 22790.7227 | 0.2 | 0.3 | 35553.5274 |  |  |  |  | 0 | 2956.6082 | 2956.6082 | 2956.6082 | 2956.6082 | 2956.6082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4717 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 18322.4256 | 0.2 | 0.3 | 28582.9839 |  |  |  |  | 0 | 6028.6713 | 6028.6713 | 6028.6713 | 6028.6713 | 6028.6713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4718 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16707.6161 | 0.2 | 0.3 | 26063.8812 |  |  |  |  | 0 | 8454.7977 | 8454.7977 | 8454.7977 | 8454.7977 | 8454.7977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4719 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 13005.1509 | 0.2 | 0.3 | 20288.0354 |  |  |  |  | 0 | 6388.9118 | 6388.9118 | 6388.9118 | 6388.9118 | 6388.9118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4720 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17845.7041 | 0.2 | 0.3 | 27839.2983 |  |  |  |  | 0 | 3803.0239 | 3803.0239 | 3803.0239 | 3803.0239 | 3803.0239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4721 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16681.909 | 0.2 | 0.3 | 26023.778 |  |  |  |  | 0 | 3232.9328 | 3232.9328 | 3232.9328 | 3232.9328 | 3232.9328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4722 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 4794.0759 | 0.2 | 0.3 | 7478.7585 |  |  |  |  | 0 | 5201.8388 | 5201.8388 | 5201.8388 | 5201.8388 | 5201.8388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4723 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 3851.8809 | 0.2 | 0.3 | 6008.9343 |  |  |  |  | 0 | 5447.3257 | 5447.3257 | 5447.3257 | 5447.3257 | 5447.3257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4724 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16718.9659 | 0.2 | 0.3 | 26081.5869 |  |  |  |  | 0 | 3055.6921 | 3055.6921 | 3055.6921 | 3055.6921 | 3055.6921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4725 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 32831.9893 | 0.2 | 0.3 | 51217.9033 |  |  |  |  | 0 | 426.6712 | 426.6712 | 426.6712 | 426.6712 | 426.6712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4726 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16666.7191 | 0.2 | 0.3 | 26000.0818 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4727 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 9021.4934 | 9021.4934 | 9021.4934 | 9021.4934 | 9021.4934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4728 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 8539.5811 | 8539.5811 | 8539.5811 | 8539.5811 | 8539.5811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4729 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 5281.7287 | 5281.7287 | 5281.7287 | 5281.7287 | 5281.7287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4730 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 17324.1493 | 0.2 | 0.3 | 27025.6729 |  |  |  |  | 0 | 1563.4286 | 1563.4286 | 1563.4286 | 1563.4286 | 1563.4286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4731 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16871.3123 | 0.2 | 0.3 | 26319.2471 |  |  |  |  | 0 | 5426.6052 | 5426.6052 | 5426.6052 | 5426.6052 | 5426.6052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4732 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 20429.2403 | 0.2 | 0.3 | 31869.6148 |  |  |  |  | 0 | 5202.6197 | 5202.6197 | 5202.6197 | 5202.6197 | 5202.6197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4733 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 29044.9372 | 0.2 | 0.3 | 45310.102 |  |  |  |  | 0 | 6285.0344 | 6285.0344 | 6285.0344 | 6285.0344 | 6285.0344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4734 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 15546.7818 | 0.2 | 0.3 | 24252.9796 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4735 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16676.4425 | 0.2 | 0.3 | 26015.2502 |  |  |  |  | 0 | 5028.8985 | 5028.8985 | 5028.8985 | 5028.8985 | 5028.8985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4736 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16854.8653 | 0.2 | 0.3 | 26293.5898 |  |  |  |  | 0 | 5353.204 | 5353.204 | 5353.204 | 5353.204 | 5353.204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4737 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 23395.6355 | 0.2 | 0.3 | 36497.1914 |  |  |  |  | 0 | 1062.6554 | 1062.6554 | 1062.6554 | 1062.6554 | 1062.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4738 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 11060.5497 | 0.2 | 0.3 | 17254.4575 |  |  |  |  | 0 | 5701.1936 | 5701.1936 | 5701.1936 | 5701.1936 | 5701.1936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4739 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 16672.3415 | 0.2 | 0.3 | 26008.8527 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4740 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 4292.9311 | 0.2 | 0.3 | 6696.9725 |  |  |  |  | 0 | 5203.562 | 5203.562 | 5203.562 | 5203.562 | 5203.562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4741 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 20103.0488 | 0.2 | 0.3 | 31360.7561 |  |  |  |  | 0 | 10005.5562 | 10005.5562 | 10005.5562 | 10005.5562 | 10005.5562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4742 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 3256.6102 | 0.2 | 0.3 | 5080.3119 |  |  |  |  | 0 | 6560.6589 | 6560.6589 | 6560.6589 | 6560.6589 | 6560.6589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4743 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 22405.5349 | 0.2 | 0.3 | 34952.6345 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4744 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 9748.7957 | 0.2 | 0.3 | 15208.1212 |  |  |  |  | 0 | 6496.2637 | 6496.2637 | 6496.2637 | 6496.2637 | 6496.2637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4745 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 42805.2713 | 0.2 | 0.3 | 66776.2233 |  |  |  |  | 0 | 6261.5022 | 6261.5022 | 6261.5022 | 6261.5022 | 6261.5022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4746 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 24847.9779 | 0.2 | 0.3 | 38762.8455 |  |  |  |  | 0 | 5202.5086 | 5202.5086 | 5202.5086 | 5202.5086 | 5202.5086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4747 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 24076.9589 | 0.2 | 0.3 | 37560.0559 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4748 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16672.5183 | 0.2 | 0.3 | 26009.1286 |  |  |  |  | 0 | 5207.4686 | 5207.4686 | 5207.4686 | 5207.4686 | 5207.4686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4749 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16676.4425 | 0.2 | 0.3 | 26015.2502 |  |  |  |  | 0 | 4660.182 | 4660.182 | 4660.182 | 4660.182 | 4660.182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4750 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 12281.177 | 0.2 | 0.3 | 19158.6361 |  |  |  |  | 0 | 9230.4685 | 9230.4685 | 9230.4685 | 9230.4685 | 9230.4685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4751 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16828.8415 | 0.2 | 0.3 | 26252.9927 |  |  |  |  | 0 | 9298.7175 | 9298.7175 | 9298.7175 | 9298.7175 | 9298.7175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4752 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16734.7631 | 0.2 | 0.3 | 26106.2305 |  |  |  |  | 0 | 7380.7414 | 7380.7414 | 7380.7414 | 7380.7414 | 7380.7414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4753 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 21214.7829 | 0.2 | 0.3 | 33095.0613 |  |  |  |  | 0 | 9781.2757 | 9781.2757 | 9781.2757 | 9781.2757 | 9781.2757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4754 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 20055.0655 | 0.2 | 0.3 | 31285.9021 |  |  |  |  | 0 | 5204.1965 | 5204.1965 | 5204.1965 | 5204.1965 | 5204.1965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4755 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 30307.5613 | 0.2 | 0.3 | 47279.7956 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4756 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0081 | 0.2 | 0.3 | 26000.5327 |  |  |  |  | 0 | 3311.5882 | 3311.5882 | 3311.5882 | 3311.5882 | 3311.5882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4757 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 9809.093 | 9809.093 | 9809.093 | 9809.093 | 9809.093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4758 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 16666.9834 | 0.2 | 0.3 | 26000.4941 |  |  |  |  | 0 | 5204.363 | 5204.363 | 5204.363 | 5204.363 | 5204.363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4759 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4760 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4761 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 5204.4932 | 5204.4932 | 5204.4932 | 5204.4932 | 5204.4932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4762 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 13931.6696 | 0.2 | 0.3 | 21733.4046 |  |  |  |  | 0 | 4727.7039 | 4727.7039 | 4727.7039 | 4727.7039 | 4727.7039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4763 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 26685.2311 | 0.2 | 0.3 | 41628.9606 |  |  |  |  | 0 | 5202.5412 | 5202.5412 | 5202.5412 | 5202.5412 | 5202.5412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4764 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 28784.5472 | 0.2 | 0.3 | 44903.8936 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4765 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 28803.2665 | 0.2 | 0.3 | 44933.0957 |  |  |  |  | 0 | 5586.8693 | 5586.8693 | 5586.8693 | 5586.8693 | 5586.8693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4766 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 27200.9147 | 0.2 | 0.3 | 42433.427 |  |  |  |  | 0 | 5204.1354 | 5204.1354 | 5204.1354 | 5204.1354 | 5204.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4767 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 6681.9944 | 0.2 | 0.3 | 10423.9113 |  |  |  |  | 0 | 5840.1257 | 5840.1257 | 5840.1257 | 5840.1257 | 5840.1257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4768 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 17025.0931 | 0.2 | 0.3 | 26559.1453 |  |  |  |  | 0 | 6121.9315 | 6121.9315 | 6121.9315 | 6121.9315 | 6121.9315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4769 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16675.9885 | 0.2 | 0.3 | 26014.5421 |  |  |  |  | 0 | 5203.7303 | 5203.7303 | 5203.7303 | 5203.7303 | 5203.7303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4770 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16731.6804 | 0.2 | 0.3 | 26101.4214 |  |  |  |  | 0 | 5427.3107 | 5427.3107 | 5427.3107 | 5427.3107 | 5427.3107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4771 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 13183.737 | 0.2 | 0.3 | 20566.6297 |  |  |  |  | 0 | 5204.5154 | 5204.5154 | 5204.5154 | 5204.5154 | 5204.5154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4772 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 18443.0309 | 0.2 | 0.3 | 28771.1282 |  |  |  |  | 0 | 5491.5877 | 5491.5877 | 5491.5877 | 5491.5877 | 5491.5877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4773 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 29093.1705 | 0.2 | 0.3 | 45385.346 |  |  |  |  | 0 | 4850.5047 | 4850.5047 | 4850.5047 | 4850.5047 | 4850.5047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4774 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 23740.5435 | 0.2 | 0.3 | 37035.2479 |  |  |  |  | 0 | 9757.3497 | 9757.3497 | 9757.3497 | 9757.3497 | 9757.3497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4775 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 21829.0243 | 0.2 | 0.3 | 34053.2779 |  |  |  |  | 0 | 9657.1793 | 9657.1793 | 9657.1793 | 9657.1793 | 9657.1793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4776 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16668.7475 | 0.2 | 0.3 | 26003.2462 |  |  |  |  | 0 | 9697.5173 | 9697.5173 | 9697.5173 | 9697.5173 | 9697.5173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4777 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 13985.96 | 0.2 | 0.3 | 21818.0976 |  |  |  |  | 0 | 9653.0325 | 9653.0325 | 9653.0325 | 9653.0325 | 9653.0325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4778 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 17631.6785 | 0.2 | 0.3 | 27505.4184 |  |  |  |  | 0 | 4916.1682 | 4916.1682 | 4916.1682 | 4916.1682 | 4916.1682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4779 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 28021.3879 | 0.2 | 0.3 | 43713.3651 |  |  |  |  | 0 | 2800.4292 | 2800.4292 | 2800.4292 | 2800.4292 | 2800.4292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4780 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 4718.1279 | 0.2 | 0.3 | 7360.2795 |  |  |  |  | 0 | 5205.223 | 5205.223 | 5205.223 | 5205.223 | 5205.223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4781 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 17053.518 | 0.2 | 0.3 | 26603.4881 |  |  |  |  | 0 | 9826.8789 | 9826.8789 | 9826.8789 | 9826.8789 | 9826.8789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4782 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 7833.8423 | 0.2 | 0.3 | 12220.7939 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4783 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 18289.3953 | 0.2 | 0.3 | 28531.4566 |  |  |  |  | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4784 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16258.2309 | 0.2 | 0.3 | 25362.8403 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4785 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 24599.4118 | 0.2 | 0.3 | 38375.0824 |  |  |  |  | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4786 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16993.0511 | 0.2 | 0.3 | 26509.1598 |  |  |  |  | 0 | 5200.7607 | 5200.7607 | 5200.7607 | 5200.7607 | 5200.7607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4787 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 9551.0278 | 9551.0278 | 9551.0278 | 9551.0278 | 9551.0278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4788 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16668.5138 | 0.2 | 0.3 | 26002.8815 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4789 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 13008.3472 | 0.2 | 0.3 | 20293.0216 |  |  |  |  | 0 | 6948.8692 | 6948.8692 | 6948.8692 | 6948.8692 | 6948.8692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4790 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17288.9928 | 0.2 | 0.3 | 26970.8288 |  |  |  |  | 0 | 6777.3861 | 6777.3861 | 6777.3861 | 6777.3861 | 6777.3861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4791 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 3534.6165 | 0.2 | 0.3 | 5514.0018 |  |  |  |  | 0 | 329.6591 | 329.6591 | 329.6591 | 329.6591 | 329.6591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4792 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17695.2273 | 0.2 | 0.3 | 27604.5545 |  |  |  |  | 0 | 9487.284 | 9487.284 | 9487.284 | 9487.284 | 9487.284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4793 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16689.1491 | 0.2 | 0.3 | 26035.0726 |  |  |  |  | 0 | 9279.663 | 9279.663 | 9279.663 | 9279.663 | 9279.663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4794 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 25529.1328 | 0.2 | 0.3 | 39825.4472 |  |  |  |  | 0 | 9018.0897 | 9018.0897 | 9018.0897 | 9018.0897 | 9018.0897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4795 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 26089.5855 | 0.2 | 0.3 | 40699.7533 |  |  |  |  | 0 | 9749.074 | 9749.074 | 9749.074 | 9749.074 | 9749.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4796 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 27956.4747 | 0.2 | 0.3 | 43612.1005 |  |  |  |  | 0 | 5203.7196 | 5203.7196 | 5203.7196 | 5203.7196 | 5203.7196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4797 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 28072.9583 | 0.2 | 0.3 | 43793.815 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4798 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 17290.4723 | 0.2 | 0.3 | 26973.1368 |  |  |  |  | 0 | 5203.9025 | 5203.9025 | 5203.9025 | 5203.9025 | 5203.9025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4799 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 21702.0514 | 0.2 | 0.3 | 33855.2002 |  |  |  |  | 0 | 9764.8445 | 9764.8445 | 9764.8445 | 9764.8445 | 9764.8445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4800 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 16671.8021 | 0.2 | 0.3 | 26008.0112 |  |  |  |  | 0 | 5971.0254 | 5971.0254 | 5971.0254 | 5971.0254 | 5971.0254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4801 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 23295.0555 | 0.2 | 0.3 | 36340.2865 |  |  |  |  | 0 | 9445.9124 | 9445.9124 | 9445.9124 | 9445.9124 | 9445.9124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4802 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 29650.8653 | 0.2 | 0.3 | 46255.3499 |  |  |  |  | 0 | 5202.1582 | 5202.1582 | 5202.1582 | 5202.1582 | 5202.1582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4803 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16676.4975 | 0.2 | 0.3 | 26015.336 |  |  |  |  | 0 | 771.0123 | 771.0123 | 771.0123 | 771.0123 | 771.0123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4804 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 18250.742 | 0.2 | 0.3 | 28471.1575 |  |  |  |  | 0 | 2675.6866 | 2675.6866 | 2675.6866 | 2675.6866 | 2675.6866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4805 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 17045.9861 | 0.2 | 0.3 | 26591.7383 |  |  |  |  | 0 | 9700.4381 | 9700.4381 | 9700.4381 | 9700.4381 | 9700.4381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4806 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 10403.6582 | 0.2 | 0.3 | 16229.7068 |  |  |  |  | 0 | 4436.9739 | 4436.9739 | 4436.9739 | 4436.9739 | 4436.9739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4807 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16677.8095 | 0.2 | 0.3 | 26017.3828 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4808 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 25042.9197 | 0.2 | 0.3 | 39066.9548 |  |  |  |  | 0 | 4797.2167 | 4797.2167 | 4797.2167 | 4797.2167 | 4797.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4809 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 8865.1613 | 0.2 | 0.3 | 13829.6516 |  |  |  |  | 0 | 5201.0867 | 5201.0867 | 5201.0867 | 5201.0867 | 5201.0867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4810 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 24534.3275 | 0.2 | 0.3 | 38273.5508 |  |  |  |  | 0 | 9776.8411 | 9776.8411 | 9776.8411 | 9776.8411 | 9776.8411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4811 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 11842.0769 | 0.2 | 0.3 | 18473.6399 |  |  |  |  | 0 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4812 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 5846.5014 | 0.2 | 0.3 | 9120.5422 |  |  |  |  | 0 | 4433.9045 | 4433.9045 | 4433.9045 | 4433.9045 | 4433.9045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4813 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 15165.357 | 0.2 | 0.3 | 23657.9569 |  |  |  |  | 0 | 2529.4188 | 2529.4188 | 2529.4188 | 2529.4188 | 2529.4188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4814 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 16325.6151 | 0.2 | 0.3 | 25467.9595 |  |  |  |  | 0 | 5338.1919 | 5338.1919 | 5338.1919 | 5338.1919 | 5338.1919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4815 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 41694.6279 | 0.2 | 0.3 | 65043.6195 |  |  |  |  | 0 | 0.49718 | 0.49718 | 0.49718 | 0.49718 | 0.49718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4816 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 20835.323 | 0.2 | 0.3 | 32503.1039 |  |  |  |  | 0 | 235.4057 | 235.4057 | 235.4057 | 235.4057 | 235.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4817 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 37137.1908 | 0.2 | 0.3 | 57934.0176 |  |  |  |  | 0 | 7585.757 | 7585.757 | 7585.757 | 7585.757 | 7585.757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4818 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 18666.1873 | 0.2 | 0.3 | 29119.2521 |  |  |  |  | 0 | 6984.5886 | 6984.5886 | 6984.5886 | 6984.5886 | 6984.5886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4819 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 7402.8556 | 0.2 | 0.3 | 11548.4547 |  |  |  |  | 0 | 7394.9861 | 7394.9861 | 7394.9861 | 7394.9861 | 7394.9861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4820 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 22900.6011 | 0.2 | 0.3 | 35724.9378 |  |  |  |  | 0 | 7726.8849 | 7726.8849 | 7726.8849 | 7726.8849 | 7726.8849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4821 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 15444.6078 | 0.2 | 0.3 | 24093.5882 |  |  |  |  | 0 | 24.6747 | 24.6747 | 24.6747 | 24.6747 | 24.6747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4822 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16679.9858 | 0.2 | 0.3 | 26020.7778 |  |  |  |  | 0 | 7300.5694 | 7300.5694 | 7300.5694 | 7300.5694 | 7300.5694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4823 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16687.652 | 0.2 | 0.3 | 26032.7371 |  |  |  |  | 0 | 2771.9807 | 2771.9807 | 2771.9807 | 2771.9807 | 2771.9807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4824 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 34809.5211 | 0.2 | 0.3 | 54302.853 |  |  |  |  | 0 | 8439.6299 | 8439.6299 | 8439.6299 | 8439.6299 | 8439.6299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4825 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 15908.3004 | 0.2 | 0.3 | 24816.9486 |  |  |  |  | 0 | 9398.5191 | 9398.5191 | 9398.5191 | 9398.5191 | 9398.5191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4826 | PEMBROKE PINES | 110341 | Private | 2036 | 5 | Swales | 66.6667 | 16239.6405 | 0.2 | 0.3 | 25333.8392 |  |  |  |  | 0 | 9772.3728 | 9772.3728 | 9772.3728 | 9772.3728 | 9772.3728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4827 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16672.7227 | 0.2 | 0.3 | 26009.4475 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4828 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16676.4425 | 0.2 | 0.3 | 26015.2502 |  |  |  |  | 0 | 5202.5886 | 5202.5886 | 5202.5886 | 5202.5886 | 5202.5886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4829 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 2952.4699 | 0.2 | 0.3 | 4605.853 |  |  |  |  | 0 | 5202.5484 | 5202.5484 | 5202.5484 | 5202.5484 | 5202.5484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4830 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 21985.9771 | 0.2 | 0.3 | 34298.1242 |  |  |  |  | 0 | 5403.9063 | 5403.9063 | 5403.9063 | 5403.9063 | 5403.9063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4831 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 24109.57 | 0.2 | 0.3 | 37610.9292 |  |  |  |  | 0 | 5189.8804 | 5189.8804 | 5189.8804 | 5189.8804 | 5189.8804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4832 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 16764.4369 | 0.2 | 0.3 | 26152.5216 |  |  |  |  | 0 | 7446.4473 | 7446.4473 | 7446.4473 | 7446.4473 | 7446.4473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4833 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 16666.621 | 0.2 | 0.3 | 25999.9288 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4834 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 16702.4963 | 0.2 | 0.3 | 26055.8942 |  |  |  |  | 0 | 9781.5596 | 9781.5596 | 9781.5596 | 9781.5596 | 9781.5596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4835 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 24510.5725 | 0.2 | 0.3 | 38236.493 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4836 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16731.4133 | 0.2 | 0.3 | 26101.0047 |  |  |  |  | 0 | 5304.2836 | 5304.2836 | 5304.2836 | 5304.2836 | 5304.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4837 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 4092.252 | 0.2 | 0.3 | 6383.9131 |  |  |  |  | 0 | 9000.0721 | 9000.0721 | 9000.0721 | 9000.0721 | 9000.0721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4838 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 21225.2767 | 0.2 | 0.3 | 33111.4316 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4839 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 38657.1395 | 0.2 | 0.3 | 60305.1376 |  |  |  |  | 0 | 5202.5097 | 5202.5097 | 5202.5097 | 5202.5097 | 5202.5097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4840 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 19562.0438 | 0.2 | 0.3 | 30516.7883 |  |  |  |  | 0 | 1977.2477 | 1977.2477 | 1977.2477 | 1977.2477 | 1977.2477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4841 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 22507.6425 | 0.2 | 0.3 | 35111.9224 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4842 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 33665.9355 | 0.2 | 0.3 | 52518.8594 |  |  |  |  | 0 | 8788.4125 | 8788.4125 | 8788.4125 | 8788.4125 | 8788.4125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4843 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 26006.4703 | 0.2 | 0.3 | 40570.0937 |  |  |  |  | 0 | 5200.4458 | 5200.4458 | 5200.4458 | 5200.4458 | 5200.4458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4844 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 18904.0309 | 0.2 | 0.3 | 29490.2882 |  |  |  |  | 0 | 9438.3067 | 9438.3067 | 9438.3067 | 9438.3067 | 9438.3067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4845 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 16718.4302 | 0.2 | 0.3 | 26080.7511 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4846 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 5704.9821 | 0.2 | 0.3 | 8899.772 |  |  |  |  | 0 | 5254.4737 | 5254.4737 | 5254.4737 | 5254.4737 | 5254.4737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4847 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 25386.3035 | 0.2 | 0.3 | 39602.6334 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4848 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16157.5629 | 0.2 | 0.3 | 25205.7982 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4849 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 23773.0319 | 0.2 | 0.3 | 37085.9297 |  |  |  |  | 0 | 5201.9641 | 5201.9641 | 5201.9641 | 5201.9641 | 5201.9641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4850 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 17123.9421 | 0.2 | 0.3 | 26713.3496 |  |  |  |  | 0 | 5738.6492 | 5738.6492 | 5738.6492 | 5738.6492 | 5738.6492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4851 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 11402.8643 | 0.2 | 0.3 | 17788.4684 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4852 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 17944.2251 | 0.2 | 0.3 | 27992.9911 |  |  |  |  | 0 | 5393.2103 | 5393.2103 | 5393.2103 | 5393.2103 | 5393.2103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4853 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 17748.1419 | 0.2 | 0.3 | 27687.1013 |  |  |  |  | 0 | 9245.6206 | 9245.6206 | 9245.6206 | 9245.6206 | 9245.6206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4854 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16669.3611 | 0.2 | 0.3 | 26004.2034 |  |  |  |  | 0 | 9031.4553 | 9031.4553 | 9031.4553 | 9031.4553 | 9031.4553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4855 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16667.3621 | 0.2 | 0.3 | 26001.0848 |  |  |  |  | 0 | 5228.5809 | 5228.5809 | 5228.5809 | 5228.5809 | 5228.5809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4856 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16667.5189 | 0.2 | 0.3 | 26001.3294 |  |  |  |  | 0 | 5306.6575 | 5306.6575 | 5306.6575 | 5306.6575 | 5306.6575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4857 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17278.9529 | 0.2 | 0.3 | 26955.1665 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4858 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 15087.8031 | 0.2 | 0.3 | 23536.9728 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4859 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 27510.3685 | 0.2 | 0.3 | 42916.1748 |  |  |  |  | 0 | 5201.6898 | 5201.6898 | 5201.6898 | 5201.6898 | 5201.6898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4860 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17725.7799 | 0.2 | 0.3 | 27652.2166 |  |  |  |  | 0 | 5974.7188 | 5974.7188 | 5974.7188 | 5974.7188 | 5974.7188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4861 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16824.9599 | 0.2 | 0.3 | 26246.9375 |  |  |  |  | 0 | 5201.4122 | 5201.4122 | 5201.4122 | 5201.4122 | 5201.4122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4862 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16722.6886 | 0.2 | 0.3 | 26087.3942 |  |  |  |  | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4863 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16707.3379 | 0.2 | 0.3 | 26063.4471 |  |  |  |  | 0 | 5358.0795 | 5358.0795 | 5358.0795 | 5358.0795 | 5358.0795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4864 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 19844.7792 | 0.2 | 0.3 | 30957.8556 |  |  |  |  | 0 | 9781.0665 | 9781.0665 | 9781.0665 | 9781.0665 | 9781.0665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4865 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17340.3194 | 0.2 | 0.3 | 27050.8983 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4866 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 20003.8787 | 0.2 | 0.3 | 31206.0508 |  |  |  |  | 0 | 5440.5404 | 5440.5404 | 5440.5404 | 5440.5404 | 5440.5404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4867 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 18172.873 | 0.2 | 0.3 | 28349.6819 |  |  |  |  | 0 | 5222.0604 | 5222.0604 | 5222.0604 | 5222.0604 | 5222.0604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4868 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 19125.8563 | 0.2 | 0.3 | 29836.3358 |  |  |  |  | 0 | 1442.0529 | 1442.0529 | 1442.0529 | 1442.0529 | 1442.0529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4869 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 34595.8161 | 0.2 | 0.3 | 53969.4732 |  |  |  |  | 0 | 5203.2192 | 5203.2192 | 5203.2192 | 5203.2192 | 5203.2192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4870 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 23720.846 | 0.2 | 0.3 | 37004.5198 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4871 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 18534.1074 | 0.2 | 0.3 | 28913.2075 |  |  |  |  | 0 | 2403.097 | 2403.097 | 2403.097 | 2403.097 | 2403.097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4872 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 17708.7586 | 0.2 | 0.3 | 27625.6634 |  |  |  |  | 0 | 8625.3403 | 8625.3403 | 8625.3403 | 8625.3403 | 8625.3403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4873 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 3345.642 | 0.2 | 0.3 | 5219.2015 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4874 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 29145.5852 | 0.2 | 0.3 | 45467.1129 |  |  |  |  | 0 | 5259.1597 | 5259.1597 | 5259.1597 | 5259.1597 | 5259.1597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4875 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 9603.7601 | 0.2 | 0.3 | 14981.8657 |  |  |  |  | 0 | 4211.4071 | 4211.4071 | 4211.4071 | 4211.4071 | 4211.4071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4876 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 15998.4492 | 0.2 | 0.3 | 24957.5808 |  |  |  |  | 0 | 5210.222 | 5210.222 | 5210.222 | 5210.222 | 5210.222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4877 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 17816.2327 | 0.2 | 0.3 | 27793.3231 |  |  |  |  | 0 | 4596.4875 | 4596.4875 | 4596.4875 | 4596.4875 | 4596.4875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4878 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 31502.2245 | 0.2 | 0.3 | 49143.4703 |  |  |  |  | 0 | 5460.6569 | 5460.6569 | 5460.6569 | 5460.6569 | 5460.6569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4879 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 6313.4429 | 6313.4429 | 6313.4429 | 6313.4429 | 6313.4429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4880 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16668.3589 | 0.2 | 0.3 | 26002.6398 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4881 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 9256.4593 | 0.2 | 0.3 | 14440.0766 |  |  |  |  | 0 | 7435.1065 | 7435.1065 | 7435.1065 | 7435.1065 | 7435.1065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4882 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 31405.5777 | 0.2 | 0.3 | 48992.7013 |  |  |  |  | 0 | 6964.3851 | 6964.3851 | 6964.3851 | 6964.3851 | 6964.3851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4883 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 33844.7905 | 0.2 | 0.3 | 52797.8731 |  |  |  |  | 0 | 9784.0345 | 9784.0345 | 9784.0345 | 9784.0345 | 9784.0345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4884 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 31388.4827 | 0.2 | 0.3 | 48966.0331 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4885 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 27424.449 | 0.2 | 0.3 | 42782.1404 |  |  |  |  | 0 | 5588.2952 | 5588.2952 | 5588.2952 | 5588.2952 | 5588.2952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4886 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 26606.3307 | 0.2 | 0.3 | 41505.8758 |  |  |  |  | 0 | 1061.0291 | 1061.0291 | 1061.0291 | 1061.0291 | 1061.0291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4887 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 27749.3371 | 0.2 | 0.3 | 43288.9659 |  |  |  |  | 0 | 9782.668 | 9782.668 | 9782.668 | 9782.668 | 9782.668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4888 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 29953.8381 | 0.2 | 0.3 | 46727.9874 |  |  |  |  | 0 | 8383.2878 | 8383.2878 | 8383.2878 | 8383.2878 | 8383.2878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4889 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 21352.151 | 0.2 | 0.3 | 33309.3556 |  |  |  |  | 0 | 6560.7486 | 6560.7486 | 6560.7486 | 6560.7486 | 6560.7486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4890 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 18556.9753 | 0.2 | 0.3 | 28948.8815 |  |  |  |  | 0 | 6646.4761 | 6646.4761 | 6646.4761 | 6646.4761 | 6646.4761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4891 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 7231.079 | 0.2 | 0.3 | 11280.4832 |  |  |  |  | 0 | 5201.7825 | 5201.7825 | 5201.7825 | 5201.7825 | 5201.7825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4892 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 24132.5775 | 0.2 | 0.3 | 37646.8208 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4893 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 1764.6672 | 0.2 | 0.3 | 2752.8808 |  |  |  |  | 0 | 9811.1388 | 9811.1388 | 9811.1388 | 9811.1388 | 9811.1388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4894 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 21880.9082 | 0.2 | 0.3 | 34134.2168 |  |  |  |  | 0 | 8056.6864 | 8056.6864 | 8056.6864 | 8056.6864 | 8056.6864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4895 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 31371.7457 | 0.2 | 0.3 | 48939.9232 |  |  |  |  | 0 | 5202.2925 | 5202.2925 | 5202.2925 | 5202.2925 | 5202.2925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4896 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 24725.547 | 0.2 | 0.3 | 38571.8533 |  |  |  |  | 0 | 5202.3318 | 5202.3318 | 5202.3318 | 5202.3318 | 5202.3318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4897 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 31353.4141 | 0.2 | 0.3 | 48911.326 |  |  |  |  | 0 | 10903.0601 | 10903.0601 | 10903.0601 | 10903.0601 | 10903.0601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4898 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 31418.7542 | 0.2 | 0.3 | 49013.2566 |  |  |  |  | 0 | 4163.8609 | 4163.8609 | 4163.8609 | 4163.8609 | 4163.8609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4899 | PEMBROKE PINES | 110351 | Public | 2036 | 5 | Swales | 66.6667 | 9216.5439 | 0.2 | 0.3 | 14377.8084 |  |  |  |  | 0 | 1229.514 | 1229.514 | 1229.514 | 1229.514 | 1229.514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4900 | PEMBROKE PINES | 110351 | Public | 2036 | 5 | Swales | 66.6667 | 14611.4301 | 0.2 | 0.3 | 22793.8309 |  |  |  |  | 0 | 7505.9269 | 7505.9269 | 7505.9269 | 7505.9269 | 7505.9269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4901 | PEMBROKE PINES | 110351 | Public | 2036 | 5 | Swales | 66.6667 | 16251.6641 | 0.2 | 0.3 | 25352.596 |  |  |  |  | 0 | 9614.2245 | 9614.2245 | 9614.2245 | 9614.2245 | 9614.2245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4902 | PEMBROKE PINES | 110351 | Public | 2036 | 5 | Swales | 66.6667 | 5964.8151 | 0.2 | 0.3 | 9305.1116 |  |  |  |  | 0 | 5202.4894 | 5202.4894 | 5202.4894 | 5202.4894 | 5202.4894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4903 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 16674.5769 | 0.2 | 0.3 | 26012.34 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4904 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 33420.0325 | 0.2 | 0.3 | 52135.2506 |  |  |  |  | 0 | 8844.0285 | 8844.0285 | 8844.0285 | 8844.0285 | 8844.0285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4905 | PEMBROKE PINES | 110341 | Private | 2036 | 5 | Swales | 66.6667 | 26186.4501 | 0.2 | 0.3 | 40850.8622 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4906 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16672.5245 | 0.2 | 0.3 | 26009.1383 |  |  |  |  | 0 | 7824.0579 | 7824.0579 | 7824.0579 | 7824.0579 | 7824.0579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4907 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16678.8221 | 0.2 | 0.3 | 26018.9624 |  |  |  |  | 0 | 5201.9543 | 5201.9543 | 5201.9543 | 5201.9543 | 5201.9543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4908 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 4142.7478 | 0.2 | 0.3 | 6462.6866 |  |  |  |  | 0 | 5201.9745 | 5201.9745 | 5201.9745 | 5201.9745 | 5201.9745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4909 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 17168.4795 | 0.2 | 0.3 | 26782.8281 |  |  |  |  | 0 | 9594.8858 | 9594.8858 | 9594.8858 | 9594.8858 | 9594.8858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4910 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 16712.5694 | 0.2 | 0.3 | 26071.6083 |  |  |  |  | 0 | 6231.8911 | 6231.8911 | 6231.8911 | 6231.8911 | 6231.8911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4911 | PEMBROKE PINES | 110359 | Private | 2033 | 5 | Swales | 66.6667 | 2381.867 | 0.2 | 0.3 | 3715.7125 |  |  |  |  | 0 | 4326.9089 | 4326.9089 | 4326.9089 | 4326.9089 | 4326.9089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4912 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 18723.4585 | 0.2 | 0.3 | 29208.5952 |  |  |  |  | 0 | 2600.2969 | 2600.2969 | 2600.2969 | 2600.2969 | 2600.2969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4913 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 22467.1977 | 0.2 | 0.3 | 35048.8285 |  |  |  |  | 0 | 6548.7232 | 6548.7232 | 6548.7232 | 6548.7232 | 6548.7232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4914 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 25847.5303 | 0.2 | 0.3 | 40322.1472 |  |  |  |  | 0 | 5202.4788 | 5202.4788 | 5202.4788 | 5202.4788 | 5202.4788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4915 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 23273.0997 | 0.2 | 0.3 | 36306.0356 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4916 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16780.0027 | 0.2 | 0.3 | 26176.8043 |  |  |  |  | 0 | 5459.0911 | 5459.0911 | 5459.0911 | 5459.0911 | 5459.0911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4917 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 24424.8176 | 0.2 | 0.3 | 38102.7155 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4918 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16695.5331 | 0.2 | 0.3 | 26045.0316 |  |  |  |  | 0 | 9733.3585 | 9733.3585 | 9733.3585 | 9733.3585 | 9733.3585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4919 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 19465.6503 | 0.2 | 0.3 | 30366.4144 |  |  |  |  | 0 | 5202.5189 | 5202.5189 | 5202.5189 | 5202.5189 | 5202.5189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4920 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 16674.6403 | 0.2 | 0.3 | 26012.4388 |  |  |  |  | 0 | 5202.6027 | 5202.6027 | 5202.6027 | 5202.6027 | 5202.6027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4921 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 16708.112 | 0.2 | 0.3 | 26064.6547 |  |  |  |  | 0 | 5238.9519 | 5238.9519 | 5238.9519 | 5238.9519 | 5238.9519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4922 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 26220.3986 | 0.2 | 0.3 | 40903.8218 |  |  |  |  | 0 | 5272.2903 | 5272.2903 | 5272.2903 | 5272.2903 | 5272.2903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4923 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 31719.3019 | 0.2 | 0.3 | 49482.1109 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4924 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 30597.1057 | 0.2 | 0.3 | 47731.4848 |  |  |  |  | 0 | 6836.866 | 6836.866 | 6836.866 | 6836.866 | 6836.866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4925 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 15623.4082 | 0.2 | 0.3 | 24372.5168 |  |  |  |  | 0 | 5202.5028 | 5202.5028 | 5202.5028 | 5202.5028 | 5202.5028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4926 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16704.2901 | 0.2 | 0.3 | 26058.6925 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4927 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0414 | 0.2 | 0.3 | 26000.5846 |  |  |  |  | 0 | 7603.2244 | 7603.2244 | 7603.2244 | 7603.2244 | 7603.2244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4928 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16757.3171 | 0.2 | 0.3 | 26141.4147 |  |  |  |  | 0 | 5202.0205 | 5202.0205 | 5202.0205 | 5202.0205 | 5202.0205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4929 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 39646.7936 | 0.2 | 0.3 | 61848.998 |  |  |  |  | 0 | 5201.9657 | 5201.9657 | 5201.9657 | 5201.9657 | 5201.9657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4930 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 1662.5835 | 0.2 | 0.3 | 2593.6302 |  |  |  |  | 0 | 5202.9306 | 5202.9306 | 5202.9306 | 5202.9306 | 5202.9306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4931 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 12149.6295 | 0.2 | 0.3 | 18953.4221 |  |  |  |  | 0 | 5352.8018 | 5352.8018 | 5352.8018 | 5352.8018 | 5352.8018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4932 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 40752.5481 | 0.2 | 0.3 | 63573.9751 |  |  |  |  | 0 | 6151.9605 | 6151.9605 | 6151.9605 | 6151.9605 | 6151.9605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4933 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 11203.5713 | 0.2 | 0.3 | 17477.5713 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4934 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 21638.1027 | 0.2 | 0.3 | 33755.4402 |  |  |  |  | 0 | 5260.9669 | 5260.9669 | 5260.9669 | 5260.9669 | 5260.9669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4935 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16698.9835 | 0.2 | 0.3 | 26050.4143 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4936 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 14842.3611 | 0.2 | 0.3 | 23154.0833 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4937 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16765.2495 | 0.2 | 0.3 | 26153.7892 |  |  |  |  | 0 | 7266.1109 | 7266.1109 | 7266.1109 | 7266.1109 | 7266.1109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4938 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16705.0396 | 0.2 | 0.3 | 26059.8618 |  |  |  |  | 0 | 5201.7607 | 5201.7607 | 5201.7607 | 5201.7607 | 5201.7607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4939 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 24798.1708 | 0.2 | 0.3 | 38685.1464 |  |  |  |  | 0 | 5201.8965 | 5201.8965 | 5201.8965 | 5201.8965 | 5201.8965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4940 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 20217.6127 | 0.2 | 0.3 | 31539.4759 |  |  |  |  | 0 | 6437.8536 | 6437.8536 | 6437.8536 | 6437.8536 | 6437.8536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4941 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 29206.0405 | 0.2 | 0.3 | 45561.4231 |  |  |  |  | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4942 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 14203.7419 | 0.2 | 0.3 | 22157.8373 |  |  |  |  | 0 | 6426.6604 | 6426.6604 | 6426.6604 | 6426.6604 | 6426.6604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4943 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 13711.3023 | 0.2 | 0.3 | 21389.6315 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4944 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 19081.3012 | 0.2 | 0.3 | 29766.8299 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4945 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 38792.0301 | 0.2 | 0.3 | 60515.567 |  |  |  |  | 0 | 5202.3217 | 5202.3217 | 5202.3217 | 5202.3217 | 5202.3217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4946 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 15879.4516 | 0.2 | 0.3 | 24771.9445 |  |  |  |  | 0 | 7052.5293 | 7052.5293 | 7052.5293 | 7052.5293 | 7052.5293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4947 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 17713.018 | 0.2 | 0.3 | 27632.3081 |  |  |  |  | 0 | 5202.7992 | 5202.7992 | 5202.7992 | 5202.7992 | 5202.7992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4948 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 8072.8671 | 0.2 | 0.3 | 12593.6727 |  |  |  |  | 0 | 5202.7965 | 5202.7965 | 5202.7965 | 5202.7965 | 5202.7965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4949 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 27129.9069 | 0.2 | 0.3 | 42322.6547 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4950 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 11618.8855 | 0.2 | 0.3 | 18125.4613 |  |  |  |  | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4951 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 17304.2111 | 0.2 | 0.3 | 26994.5694 |  |  |  |  | 0 | 5203.3607 | 5203.3607 | 5203.3607 | 5203.3607 | 5203.3607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4952 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16925.3985 | 0.2 | 0.3 | 26403.6217 |  |  |  |  | 0 | 6688.1542 | 6688.1542 | 6688.1542 | 6688.1542 | 6688.1542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4953 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16754.5543 | 0.2 | 0.3 | 26137.1047 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4954 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 19218.7817 | 0.2 | 0.3 | 29981.2995 |  |  |  |  | 0 | 8576.4035 | 8576.4035 | 8576.4035 | 8576.4035 | 8576.4035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4955 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 15550.768 | 0.2 | 0.3 | 24259.1981 |  |  |  |  | 0 | 2601.3544 | 2601.3544 | 2601.3544 | 2601.3544 | 2601.3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4956 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 13703.5581 | 0.2 | 0.3 | 21377.5506 |  |  |  |  | 0 | 3729.6555 | 3729.6555 | 3729.6555 | 3729.6555 | 3729.6555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4957 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 19998.1691 | 0.2 | 0.3 | 31197.1438 |  |  |  |  | 0 | 5202.6179 | 5202.6179 | 5202.6179 | 5202.6179 | 5202.6179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4958 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 28748.9479 | 0.2 | 0.3 | 44848.3588 |  |  |  |  | 0 | 9076.4056 | 9076.4056 | 9076.4056 | 9076.4056 | 9076.4056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4959 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 25389.1309 | 0.2 | 0.3 | 39607.0443 |  |  |  |  | 0 | 5202.3758 | 5202.3758 | 5202.3758 | 5202.3758 | 5202.3758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4960 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 39366.3143 | 0.2 | 0.3 | 61411.4504 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4961 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 1969.6933 | 0.2 | 0.3 | 3072.7216 |  |  |  |  | 0 | 5202.6676 | 5202.6676 | 5202.6676 | 5202.6676 | 5202.6676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4962 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 21449.2751 | 0.2 | 0.3 | 33460.8692 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4963 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 2702.3681 | 0.2 | 0.3 | 4215.6942 |  |  |  |  | 0 | 5202.4898 | 5202.4898 | 5202.4898 | 5202.4898 | 5202.4898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4964 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 26451.5607 | 0.2 | 0.3 | 41264.4347 |  |  |  |  | 0 | 7342.3411 | 7342.3411 | 7342.3411 | 7342.3411 | 7342.3411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4965 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 25433.1653 | 0.2 | 0.3 | 39675.7378 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4966 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 5482.6481 | 0.2 | 0.3 | 8552.9311 |  |  |  |  | 0 | 5203.1318 | 5203.1318 | 5203.1318 | 5203.1318 | 5203.1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4967 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 18310.1827 | 0.2 | 0.3 | 28563.8851 |  |  |  |  | 0 | 2601.3544 | 2601.3544 | 2601.3544 | 2601.3544 | 2601.3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4968 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 23683.0603 | 0.2 | 0.3 | 36945.5741 |  |  |  |  | 0 | 2419.2348 | 2419.2348 | 2419.2348 | 2419.2348 | 2419.2348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4969 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 28318.117 | 0.2 | 0.3 | 44176.2625 |  |  |  |  | 0 | 2601.3544 | 2601.3544 | 2601.3544 | 2601.3544 | 2601.3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4970 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 17539.5017 | 0.2 | 0.3 | 27361.6227 |  |  |  |  | 0 | 3807.4514 | 3807.4514 | 3807.4514 | 3807.4514 | 3807.4514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4971 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16677.3289 | 0.2 | 0.3 | 26016.633 |  |  |  |  | 0 | 5956.3164 | 5956.3164 | 5956.3164 | 5956.3164 | 5956.3164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4972 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16679.5979 | 0.2 | 0.3 | 26020.1728 |  |  |  |  | 0 | 5201.9935 | 5201.9935 | 5201.9935 | 5201.9935 | 5201.9935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4973 | PEMBROKE PINES | 110351 | Public | 2036 | 5 | Swales | 66.6667 | 18890.9885 | 0.2 | 0.3 | 29469.942 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4974 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 15206.0029 | 0.2 | 0.3 | 23721.3646 |  |  |  |  | 0 | 5200.9854 | 5200.9854 | 5200.9854 | 5200.9854 | 5200.9854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4975 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16926.0949 | 0.2 | 0.3 | 26404.708 |  |  |  |  | 0 | 5202.3377 | 5202.3377 | 5202.3377 | 5202.3377 | 5202.3377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4976 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 18714.3773 | 0.2 | 0.3 | 29194.4285 |  |  |  |  | 0 | 5202.4468 | 5202.4468 | 5202.4468 | 5202.4468 | 5202.4468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4977 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 30178.3987 | 0.2 | 0.3 | 47078.3019 |  |  |  |  | 0 | 6076.7641 | 6076.7641 | 6076.7641 | 6076.7641 | 6076.7641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4978 | PEMBROKE PINES | 110351 | Private | 2036 | 5 | Swales | 66.6667 | 34805.8249 | 0.2 | 0.3 | 54297.0869 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4979 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 17477.8978 | 0.2 | 0.3 | 27265.5206 |  |  |  |  | 0 | 5144.4288 | 5144.4288 | 5144.4288 | 5144.4288 | 5144.4288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4980 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16856.1763 | 0.2 | 0.3 | 26295.635 |  |  |  |  | 0 | 58.6416 | 58.6416 | 58.6416 | 58.6416 | 58.6416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4981 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16771.827 | 0.2 | 0.3 | 26164.0501 |  |  |  |  | 0 | 9778.9482 | 9778.9482 | 9778.9482 | 9778.9482 | 9778.9482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4982 | PEMBROKE PINES | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 17271.8147 | 0.2 | 0.3 | 26944.0309 |  |  |  |  | 0 | 4256.3187 | 4256.3187 | 4256.3187 | 4256.3187 | 4256.3187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4983 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16670.2628 | 0.2 | 0.3 | 26005.61 |  |  |  |  | 0 | 2601.3544 | 2601.3544 | 2601.3544 | 2601.3544 | 2601.3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4984 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 19017.2674 | 0.2 | 0.3 | 29666.9371 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4985 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 26812.0577 | 0.2 | 0.3 | 41826.8101 |  |  |  |  | 0 | 5202.5771 | 5202.5771 | 5202.5771 | 5202.5771 | 5202.5771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4986 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 22199.1871 | 0.2 | 0.3 | 34630.7319 |  |  |  |  | 0 | 5202.5383 | 5202.5383 | 5202.5383 | 5202.5383 | 5202.5383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4987 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 7726.8108 | 0.2 | 0.3 | 12053.8248 |  |  |  |  | 0 | 7112.6416 | 7112.6416 | 7112.6416 | 7112.6416 | 7112.6416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4988 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 26285.4586 | 0.2 | 0.3 | 41005.3154 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4989 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16717.6609 | 0.2 | 0.3 | 26079.551 |  |  |  |  | 0 | 2994.0049 | 2994.0049 | 2994.0049 | 2994.0049 | 2994.0049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4990 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 18986.3843 | 0.2 | 0.3 | 29618.7595 |  |  |  |  | 0 | 2209.061 | 2209.061 | 2209.061 | 2209.061 | 2209.061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4991 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16682.0379 | 0.2 | 0.3 | 26023.9791 |  |  |  |  | 0 | 4199.193 | 4199.193 | 4199.193 | 4199.193 | 4199.193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4992 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 15481.9723 | 0.2 | 0.3 | 24151.8767 |  |  |  |  | 0 | 2188.2701 | 2188.2701 | 2188.2701 | 2188.2701 | 2188.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4993 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 8680.0458 | 0.2 | 0.3 | 13540.8714 |  |  |  |  | 0 | 3015.1488 | 3015.1488 | 3015.1488 | 3015.1488 | 3015.1488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4994 | PEMBROKE PINES | 110330 | Private | 2036 | 5 | Swales | 66.6667 | 20304.7403 | 0.2 | 0.3 | 31675.3948 |  |  |  |  | 0 | 45.054 | 45.054 | 45.054 | 45.054 | 45.054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4995 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16489.0965 | 0.2 | 0.3 | 25722.9906 |  |  |  |  | 0 | 6953.6104 | 6953.6104 | 6953.6104 | 6953.6104 | 6953.6104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4996 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 17338.05 | 0.2 | 0.3 | 27047.358 |  |  |  |  | 0 | 5202.7603 | 5202.7603 | 5202.7603 | 5202.7603 | 5202.7603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4997 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 27551.4935 | 0.2 | 0.3 | 42980.3299 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4998 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 26468.4085 | 0.2 | 0.3 | 41290.7173 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4999 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17200.4347 | 0.2 | 0.3 | 26832.6781 |  |  |  |  | 0 | 5202.8693 | 5202.8693 | 5202.8693 | 5202.8693 | 5202.8693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5000 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16667.686 | 0.2 | 0.3 | 26001.5902 |  |  |  |  | 0 | 9783.4813 | 9783.4813 | 9783.4813 | 9783.4813 | 9783.4813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5001 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17278.2293 | 0.2 | 0.3 | 26954.0378 |  |  |  |  | 0 | 5202.4497 | 5202.4497 | 5202.4497 | 5202.4497 | 5202.4497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5002 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 9051.6951 | 0.2 | 0.3 | 14120.6444 |  |  |  |  | 0 | 7003.171 | 7003.171 | 7003.171 | 7003.171 | 7003.171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5003 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17612.5057 | 0.2 | 0.3 | 27475.5088 |  |  |  |  | 0 | 4834.9394 | 4834.9394 | 4834.9394 | 4834.9394 | 4834.9394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5004 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 24337.3087 | 0.2 | 0.3 | 37966.2016 |  |  |  |  | 0 | 7499.833 | 7499.833 | 7499.833 | 7499.833 | 7499.833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5005 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 23538.0246 | 0.2 | 0.3 | 36719.3184 |  |  |  |  | 0 | 8961.3535 | 8961.3535 | 8961.3535 | 8961.3535 | 8961.3535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5006 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 26125.2825 | 0.2 | 0.3 | 40755.4408 |  |  |  |  | 0 | 6036.9578 | 6036.9578 | 6036.9578 | 6036.9578 | 6036.9578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5007 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 25327.9039 | 0.2 | 0.3 | 39511.5301 |  |  |  |  | 0 | 7963.5646 | 7963.5646 | 7963.5646 | 7963.5646 | 7963.5646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5008 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 43301.4138 | 0.2 | 0.3 | 67550.2055 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5009 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 10066.2463 | 0.2 | 0.3 | 15703.3443 |  |  |  |  | 0 | 5687.7929 | 5687.7929 | 5687.7929 | 5687.7929 | 5687.7929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5010 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 9027.7469 | 0.2 | 0.3 | 14083.2851 |  |  |  |  | 0 | 5205.3164 | 5205.3164 | 5205.3164 | 5205.3164 | 5205.3164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5011 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 9938.6668 | 0.2 | 0.3 | 15504.3202 |  |  |  |  | 0 | 482.4017 | 482.4017 | 482.4017 | 482.4017 | 482.4017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5012 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 20104.9502 | 0.2 | 0.3 | 31363.7223 |  |  |  |  | 0 | 3303.0377 | 3303.0377 | 3303.0377 | 3303.0377 | 3303.0377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5013 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16749.9877 | 0.2 | 0.3 | 26129.9808 |  |  |  |  | 0 | 5005.9521 | 5005.9521 | 5005.9521 | 5005.9521 | 5005.9521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5014 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16749.4603 | 0.2 | 0.3 | 26129.1581 |  |  |  |  | 0 | 3110.3876 | 3110.3876 | 3110.3876 | 3110.3876 | 3110.3876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5015 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 39455.4573 | 0.2 | 0.3 | 61550.5133 |  |  |  |  | 0 | 2847.4862 | 2847.4862 | 2847.4862 | 2847.4862 | 2847.4862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5016 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 26751.5171 | 0.2 | 0.3 | 41732.3667 |  |  |  |  | 0 | 5201.5039 | 5201.5039 | 5201.5039 | 5201.5039 | 5201.5039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5017 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 10628.3108 | 0.2 | 0.3 | 16580.1648 |  |  |  |  | 0 | 2889.0255 | 2889.0255 | 2889.0255 | 2889.0255 | 2889.0255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5018 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 35805.361 | 0.2 | 0.3 | 55856.3632 |  |  |  |  | 0 | 2998.479 | 2998.479 | 2998.479 | 2998.479 | 2998.479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5019 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16699.1519 | 0.2 | 0.3 | 26050.677 |  |  |  |  | 0 | 7895.341 | 7895.341 | 7895.341 | 7895.341 | 7895.341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5020 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16684.8581 | 0.2 | 0.3 | 26028.3786 |  |  |  |  | 0 | 4716.9892 | 4716.9892 | 4716.9892 | 4716.9892 | 4716.9892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5021 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16673.7133 | 0.2 | 0.3 | 26010.9928 |  |  |  |  | 0 | 5104.7278 | 5104.7278 | 5104.7278 | 5104.7278 | 5104.7278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5022 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16667.2711 | 0.2 | 0.3 | 26000.943 |  |  |  |  | 0 | 7063.7037 | 7063.7037 | 7063.7037 | 7063.7037 | 7063.7037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5023 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 23203.5894 | 0.2 | 0.3 | 36197.5995 |  |  |  |  | 0 | 9892.6788 | 9892.6788 | 9892.6788 | 9892.6788 | 9892.6788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5024 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16297.5365 | 0.2 | 0.3 | 25424.157 |  |  |  |  | 0 | 5202.1048 | 5202.1048 | 5202.1048 | 5202.1048 | 5202.1048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5025 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 29334.7155 | 0.2 | 0.3 | 45762.1562 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5026 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 16666.658 | 0.2 | 0.3 | 25999.9865 |  |  |  |  | 0 | 4719.8111 | 4719.8111 | 4719.8111 | 4719.8111 | 4719.8111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5027 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 17368.0211 | 0.2 | 0.3 | 27094.1129 |  |  |  |  | 0 | 2088.6046 | 2088.6046 | 2088.6046 | 2088.6046 | 2088.6046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5028 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 18027.8115 | 0.2 | 0.3 | 28123.3859 |  |  |  |  | 0 | 1993.2006 | 1993.2006 | 1993.2006 | 1993.2006 | 1993.2006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5029 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 23394.5341 | 0.2 | 0.3 | 36495.4732 |  |  |  |  | 0 | 5014.4173 | 5014.4173 | 5014.4173 | 5014.4173 | 5014.4173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5030 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 11165.0562 | 0.2 | 0.3 | 17417.4877 |  |  |  |  | 0 | 5201.641 | 5201.641 | 5201.641 | 5201.641 | 5201.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5031 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 31065.5113 | 0.2 | 0.3 | 48462.1977 |  |  |  |  | 0 | 5449.6916 | 5449.6916 | 5449.6916 | 5449.6916 | 5449.6916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5032 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 14416.9809 | 0.2 | 0.3 | 22490.4903 |  |  |  |  | 0 | 3905.0475 | 3905.0475 | 3905.0475 | 3905.0475 | 3905.0475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5033 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 30261.4889 | 0.2 | 0.3 | 47207.9226 |  |  |  |  | 0 | 9111.0165 | 9111.0165 | 9111.0165 | 9111.0165 | 9111.0165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5034 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 21472.3983 | 0.2 | 0.3 | 33496.9413 |  |  |  |  | 0 | 3678.5555 | 3678.5555 | 3678.5555 | 3678.5555 | 3678.5555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5035 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 20005.9585 | 0.2 | 0.3 | 31209.2953 |  |  |  |  | 0 | 5434.512 | 5434.512 | 5434.512 | 5434.512 | 5434.512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5036 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 25196.868 | 0.2 | 0.3 | 39307.1141 |  |  |  |  | 0 | 9786.5562 | 9786.5562 | 9786.5562 | 9786.5562 | 9786.5562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5037 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 6997.0569 | 0.2 | 0.3 | 10915.4087 |  |  |  |  | 0 | 5202.1899 | 5202.1899 | 5202.1899 | 5202.1899 | 5202.1899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5038 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 18514.0166 | 0.2 | 0.3 | 28881.8659 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5039 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 20152.4134 | 0.2 | 0.3 | 31437.7649 |  |  |  |  | 0 | 5219.4859 | 5219.4859 | 5219.4859 | 5219.4859 | 5219.4859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5040 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 19596.8341 | 0.2 | 0.3 | 30571.0611 |  |  |  |  | 0 | 6505.6667 | 6505.6667 | 6505.6667 | 6505.6667 | 6505.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5041 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 18925.3289 | 0.2 | 0.3 | 29523.5131 |  |  |  |  | 0 | 5756.6362 | 5756.6362 | 5756.6362 | 5756.6362 | 5756.6362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5042 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 20428.5793 | 0.2 | 0.3 | 31868.5837 |  |  |  |  | 0 | 6084.626 | 6084.626 | 6084.626 | 6084.626 | 6084.626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5043 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 8279.7783 | 0.2 | 0.3 | 12916.4542 |  |  |  |  | 0 | 8506.3659 | 8506.3659 | 8506.3659 | 8506.3659 | 8506.3659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5044 | PEMBROKE PINES | 110351 | Public | 2036 | 5 | Swales | 66.6667 | 16496.576 | 0.2 | 0.3 | 25734.6586 |  |  |  |  | 0 | 8723.05 | 8723.05 | 8723.05 | 8723.05 | 8723.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5045 | PEMBROKE PINES | 110351 | Public | 2036 | 5 | Swales | 66.6667 | 16656.8447 | 0.2 | 0.3 | 25984.6778 |  |  |  |  | 0 | 5295.3076 | 5295.3076 | 5295.3076 | 5295.3076 | 5295.3076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5046 | PEMBROKE PINES | 110351 | Public | 2036 | 5 | Swales | 66.6667 | 3396.3983 | 0.2 | 0.3 | 5298.3814 |  |  |  |  | 0 | 5153.5237 | 5153.5237 | 5153.5237 | 5153.5237 | 5153.5237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5047 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 25805.7129 | 0.2 | 0.3 | 40256.9122 |  |  |  |  | 0 | 6235.1282 | 6235.1282 | 6235.1282 | 6235.1282 | 6235.1282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5048 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 15641.7313 | 0.2 | 0.3 | 24401.1008 |  |  |  |  | 0 | 6310.6512 | 6310.6512 | 6310.6512 | 6310.6512 | 6310.6512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5049 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 27296.9188 | 0.2 | 0.3 | 42583.1933 |  |  |  |  | 0 | 4427.127 | 4427.127 | 4427.127 | 4427.127 | 4427.127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5050 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 3666.2602 | 0.2 | 0.3 | 5719.3659 |  |  |  |  | 0 | 9779.4584 | 9779.4584 | 9779.4584 | 9779.4584 | 9779.4584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5051 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 9689.3338 | 0.2 | 0.3 | 15115.3607 |  |  |  |  | 0 | 5200.3764 | 5200.3764 | 5200.3764 | 5200.3764 | 5200.3764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5052 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16672.4733 | 0.2 | 0.3 | 26009.0583 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5053 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 17037.5425 | 0.2 | 0.3 | 26578.5664 |  |  |  |  | 0 | 5299.1318 | 5299.1318 | 5299.1318 | 5299.1318 | 5299.1318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5054 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 33342.8086 | 0.2 | 0.3 | 52014.7814 |  |  |  |  | 0 | 7396.0189 | 7396.0189 | 7396.0189 | 7396.0189 | 7396.0189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5055 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 17527.3727 | 0.2 | 0.3 | 27342.7015 |  |  |  |  | 0 | 5830.0672 | 5830.0672 | 5830.0672 | 5830.0672 | 5830.0672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5056 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16700.0914 | 0.2 | 0.3 | 26052.1426 |  |  |  |  | 0 | 1628.2797 | 1628.2797 | 1628.2797 | 1628.2797 | 1628.2797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5057 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 11743.8149 | 0.2 | 0.3 | 18320.3513 |  |  |  |  | 0 | 5987.514 | 5987.514 | 5987.514 | 5987.514 | 5987.514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5058 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 29536.2 | 0.2 | 0.3 | 46076.472 |  |  |  |  | 0 | 8534.9651 | 8534.9651 | 8534.9651 | 8534.9651 | 8534.9651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5059 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 20290.9465 | 0.2 | 0.3 | 31653.8765 |  |  |  |  | 0 | 3862.9774 | 3862.9774 | 3862.9774 | 3862.9774 | 3862.9774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5060 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 17114.1293 | 0.2 | 0.3 | 26698.0418 |  |  |  |  | 0 | 5719.2083 | 5719.2083 | 5719.2083 | 5719.2083 | 5719.2083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5061 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 17146.1475 | 0.2 | 0.3 | 26747.9902 |  |  |  |  | 0 | 5882.806 | 5882.806 | 5882.806 | 5882.806 | 5882.806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5062 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 9835.1482 | 0.2 | 0.3 | 15342.8312 |  |  |  |  | 0 | 7716.7261 | 7716.7261 | 7716.7261 | 7716.7261 | 7716.7261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5063 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 1416.492 | 0.2 | 0.3 | 2209.7275 |  |  |  |  | 0 | 1305.1112 | 1305.1112 | 1305.1112 | 1305.1112 | 1305.1112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5064 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 23994.1036 | 0.2 | 0.3 | 37430.8016 |  |  |  |  | 0 | 4958.7482 | 4958.7482 | 4958.7482 | 4958.7482 | 4958.7482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5065 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16711.0755 | 0.2 | 0.3 | 26069.2777 |  |  |  |  | 0 | 1967.9894 | 1967.9894 | 1967.9894 | 1967.9894 | 1967.9894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5066 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17833.9227 | 0.2 | 0.3 | 27820.9194 |  |  |  |  | 0 | 9180.0314 | 9180.0314 | 9180.0314 | 9180.0314 | 9180.0314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5067 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 34771.6068 | 0.2 | 0.3 | 54243.7066 |  |  |  |  | 0 | 1695.7136 | 1695.7136 | 1695.7136 | 1695.7136 | 1695.7136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5068 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 22542.4631 | 0.2 | 0.3 | 35166.2425 |  |  |  |  | 0 | 8466.9698 | 8466.9698 | 8466.9698 | 8466.9698 | 8466.9698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5069 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16694.7879 | 0.2 | 0.3 | 26043.8692 |  |  |  |  | 0 | 3223.8861 | 3223.8861 | 3223.8861 | 3223.8861 | 3223.8861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5070 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 23979.1156 | 0.2 | 0.3 | 37407.4203 |  |  |  |  | 0 | 5594.1344 | 5594.1344 | 5594.1344 | 5594.1344 | 5594.1344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5071 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 25678.1046 | 0.2 | 0.3 | 40057.8432 |  |  |  |  | 0 | 5392.7772 | 5392.7772 | 5392.7772 | 5392.7772 | 5392.7772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5072 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 7168.1037 | 0.2 | 0.3 | 11182.2418 |  |  |  |  | 0 | 6230.7351 | 6230.7351 | 6230.7351 | 6230.7351 | 6230.7351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5073 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16656.7575 | 0.2 | 0.3 | 25984.5418 |  |  |  |  | 0 | 3541.123 | 3541.123 | 3541.123 | 3541.123 | 3541.123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5074 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16695.8361 | 0.2 | 0.3 | 26045.5044 |  |  |  |  | 0 | 6224.1817 | 6224.1817 | 6224.1817 | 6224.1817 | 6224.1817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5075 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16669.5985 | 0.2 | 0.3 | 26004.5736 |  |  |  |  | 0 | 3851.3371 | 3851.3371 | 3851.3371 | 3851.3371 | 3851.3371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5076 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 33375.5079 | 0.2 | 0.3 | 52065.7924 |  |  |  |  | 0 | 10300.0341 | 10300.0341 | 10300.0341 | 10300.0341 | 10300.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5077 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 17741.1063 | 0.2 | 0.3 | 27676.1258 |  |  |  |  | 0 | 5209.8456 | 5209.8456 | 5209.8456 | 5209.8456 | 5209.8456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5078 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 591.9999 | 0.2 | 0.3 | 923.5199 |  |  |  |  | 0 | 7207.6762 | 7207.6762 | 7207.6762 | 7207.6762 | 7207.6762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5079 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 19506.7591 | 0.2 | 0.3 | 30430.5442 |  |  |  |  | 0 | 3768.6476 | 3768.6476 | 3768.6476 | 3768.6476 | 3768.6476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5080 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 33708.4127 | 0.2 | 0.3 | 52585.1238 |  |  |  |  | 0 | 5096.9167 | 5096.9167 | 5096.9167 | 5096.9167 | 5096.9167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5081 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 7170.4278 | 0.2 | 0.3 | 11185.8674 |  |  |  |  | 0 | 10015.287 | 10015.287 | 10015.287 | 10015.287 | 10015.287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5082 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 32616.375 | 0.2 | 0.3 | 50881.545 |  |  |  |  | 0 | 5771.2168 | 5771.2168 | 5771.2168 | 5771.2168 | 5771.2168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5083 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 2467.8585 | 0.2 | 0.3 | 3849.8593 |  |  |  |  | 0 | 5253.5965 | 5253.5965 | 5253.5965 | 5253.5965 | 5253.5965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5084 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 41128.6299 | 0.2 | 0.3 | 64160.6626 |  |  |  |  | 0 | 5205.2153 | 5205.2153 | 5205.2153 | 5205.2153 | 5205.2153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5085 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 33210.6167 | 0.2 | 0.3 | 51808.5621 |  |  |  |  | 0 | 6753.4645 | 6753.4645 | 6753.4645 | 6753.4645 | 6753.4645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5086 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 29404.5445 | 0.2 | 0.3 | 45871.0894 |  |  |  |  | 0 | 4410.4548 | 4410.4548 | 4410.4548 | 4410.4548 | 4410.4548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5087 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 29095.9013 | 0.2 | 0.3 | 45389.6061 |  |  |  |  | 0 | 790.9183 | 790.9183 | 790.9183 | 790.9183 | 790.9183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5088 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 25363.6802 | 0.2 | 0.3 | 39567.3411 |  |  |  |  | 0 | 5223.0454 | 5223.0454 | 5223.0454 | 5223.0454 | 5223.0454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5089 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 39846.0579 | 0.2 | 0.3 | 62159.8504 |  |  |  |  | 0 | 5586.4988 | 5586.4988 | 5586.4988 | 5586.4988 | 5586.4988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5090 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 1615.4933 | 0.2 | 0.3 | 2520.1696 |  |  |  |  | 0 | 5256.3724 | 5256.3724 | 5256.3724 | 5256.3724 | 5256.3724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5091 | PEMBROKE PINES | 110352 | Private | 2036 | 5 | Swales | 66.6667 | 26646.7012 | 0.2 | 0.3 | 41568.8539 |  |  |  |  | 0 | 5211.1537 | 5211.1537 | 5211.1537 | 5211.1537 | 5211.1537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5092 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 38472.7841 | 0.2 | 0.3 | 60017.5432 |  |  |  |  | 0 | 5483.7346 | 5483.7346 | 5483.7346 | 5483.7346 | 5483.7346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5093 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 44567.2064 | 0.2 | 0.3 | 69524.842 |  |  |  |  | 0 | 5510.1066 | 5510.1066 | 5510.1066 | 5510.1066 | 5510.1066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5094 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 34247.7002 | 0.2 | 0.3 | 53426.4123 |  |  |  |  | 0 | 5223.1618 | 5223.1618 | 5223.1618 | 5223.1618 | 5223.1618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5095 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 25659.9298 | 0.2 | 0.3 | 40029.4905 |  |  |  |  | 0 | 5205.0852 | 5205.0852 | 5205.0852 | 5205.0852 | 5205.0852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5096 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 24646.8323 | 0.2 | 0.3 | 38449.0584 |  |  |  |  | 0 | 848.2969 | 848.2969 | 848.2969 | 848.2969 | 848.2969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5097 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 25293.3002 | 0.2 | 0.3 | 39457.5483 |  |  |  |  | 0 | 5781.2503 | 5781.2503 | 5781.2503 | 5781.2503 | 5781.2503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5098 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 13440.714 | 0.2 | 0.3 | 20967.5138 |  |  |  |  | 0 | 5203.4046 | 5203.4046 | 5203.4046 | 5203.4046 | 5203.4046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5099 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 24276.7141 | 0.2 | 0.3 | 37871.674 |  |  |  |  | 0 | 2661.2192 | 2661.2192 | 2661.2192 | 2661.2192 | 2661.2192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5100 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16681.3637 | 0.2 | 0.3 | 26022.9274 |  |  |  |  | 0 | 2543.5231 | 2543.5231 | 2543.5231 | 2543.5231 | 2543.5231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5101 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16681.2215 | 0.2 | 0.3 | 26022.7056 |  |  |  |  | 0 | 5201.2306 | 5201.2306 | 5201.2306 | 5201.2306 | 5201.2306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5102 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 36836.7953 | 0.2 | 0.3 | 57465.4007 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5103 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 31360.2035 | 0.2 | 0.3 | 48921.9175 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5104 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 21577.0035 | 0.2 | 0.3 | 33660.1254 |  |  |  |  | 0 | 5211.065 | 5211.065 | 5211.065 | 5211.065 | 5211.065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5105 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16681.0151 | 0.2 | 0.3 | 26022.3835 |  |  |  |  | 0 | 5203.0087 | 5203.0087 | 5203.0087 | 5203.0087 | 5203.0087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5106 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 15457.5825 | 0.2 | 0.3 | 24113.8286 |  |  |  |  | 0 | 5205.7388 | 5205.7388 | 5205.7388 | 5205.7388 | 5205.7388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5107 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 23930.6959 | 0.2 | 0.3 | 37331.8856 |  |  |  |  | 0 | 3983.0247 | 3983.0247 | 3983.0247 | 3983.0247 | 3983.0247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5108 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 18069.8895 | 0.2 | 0.3 | 28189.0277 |  |  |  |  | 0 | 5204.592 | 5204.592 | 5204.592 | 5204.592 | 5204.592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5109 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 38734.9436 | 0.2 | 0.3 | 60426.512 |  |  |  |  | 0 | 5203.1193 | 5203.1193 | 5203.1193 | 5203.1193 | 5203.1193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5110 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 30529.8287 | 0.2 | 0.3 | 47626.5328 |  |  |  |  | 0 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5111 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 43692.4757 | 0.2 | 0.3 | 68160.2621 |  |  |  |  | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5112 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 31357.4044 | 0.2 | 0.3 | 48917.5509 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5113 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 17969.0633 | 0.2 | 0.3 | 28031.7388 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5114 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 21329.2668 | 0.2 | 0.3 | 33273.6562 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5115 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 16186.2006 | 0.2 | 0.3 | 25250.4729 |  |  |  |  | 0 | 5202.1854 | 5202.1854 | 5202.1854 | 5202.1854 | 5202.1854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5116 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 10738.0062 | 0.2 | 0.3 | 16751.2897 |  |  |  |  | 0 | 5122.8386 | 5122.8386 | 5122.8386 | 5122.8386 | 5122.8386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5117 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 18027.8057 | 0.2 | 0.3 | 28123.3769 |  |  |  |  | 0 | 5494.6898 | 5494.6898 | 5494.6898 | 5494.6898 | 5494.6898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5118 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 17088.5438 | 0.2 | 0.3 | 26658.1283 |  |  |  |  | 0 | 5202.3444 | 5202.3444 | 5202.3444 | 5202.3444 | 5202.3444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5119 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 33408.312 | 0.2 | 0.3 | 52116.9667 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5120 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 22599.945 | 0.2 | 0.3 | 35255.9142 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5121 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 10007.2985 | 0.2 | 0.3 | 15611.3857 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5122 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 13443.4125 | 0.2 | 0.3 | 20971.7234 |  |  |  |  | 0 | 8962.8538 | 8962.8538 | 8962.8538 | 8962.8538 | 8962.8538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5123 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 15140.4497 | 0.2 | 0.3 | 23619.1016 |  |  |  |  | 0 | 9682.8352 | 9682.8352 | 9682.8352 | 9682.8352 | 9682.8352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5124 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 13863.1124 | 0.2 | 0.3 | 21626.4553 |  |  |  |  | 0 | 8628.3897 | 8628.3897 | 8628.3897 | 8628.3897 | 8628.3897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5125 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16813.9021 | 0.2 | 0.3 | 26229.6873 |  |  |  |  | 0 | 5212.5093 | 5212.5093 | 5212.5093 | 5212.5093 | 5212.5093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5126 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 15272.9277 | 0.2 | 0.3 | 23825.7673 |  |  |  |  | 0 | 4994.8139 | 4994.8139 | 4994.8139 | 4994.8139 | 4994.8139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5127 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 10109.5837 | 0.2 | 0.3 | 15770.9505 |  |  |  |  | 0 | 6732.0916 | 6732.0916 | 6732.0916 | 6732.0916 | 6732.0916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5128 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 24334.7208 | 0.2 | 0.3 | 37962.1644 |  |  |  |  | 0 | 6043.4151 | 6043.4151 | 6043.4151 | 6043.4151 | 6043.4151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5129 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 26346.6036 | 0.2 | 0.3 | 41100.7016 |  |  |  |  | 0 | 2634.9943 | 2634.9943 | 2634.9943 | 2634.9943 | 2634.9943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5130 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16786.8178 | 0.2 | 0.3 | 26187.4358 |  |  |  |  | 0 | 3092.8157 | 3092.8157 | 3092.8157 | 3092.8157 | 3092.8157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5131 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 18517.9462 | 0.2 | 0.3 | 28887.9961 |  |  |  |  | 0 | 5259.3405 | 5259.3405 | 5259.3405 | 5259.3405 | 5259.3405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5132 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17046.0541 | 0.2 | 0.3 | 26591.8444 |  |  |  |  | 0 | 5202.1518 | 5202.1518 | 5202.1518 | 5202.1518 | 5202.1518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5133 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16779.0214 | 0.2 | 0.3 | 26175.2734 |  |  |  |  | 0 | 5202.3656 | 5202.3656 | 5202.3656 | 5202.3656 | 5202.3656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5134 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 23065.4543 | 0.2 | 0.3 | 35982.1087 |  |  |  |  | 0 | 8015.1788 | 8015.1788 | 8015.1788 | 8015.1788 | 8015.1788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5135 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 13113.4778 | 0.2 | 0.3 | 20457.0254 |  |  |  |  | 0 | 1102.4144 | 1102.4144 | 1102.4144 | 1102.4144 | 1102.4144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5136 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 27009.1565 | 0.2 | 0.3 | 42134.2841 |  |  |  |  | 0 | 4826.2066 | 4826.2066 | 4826.2066 | 4826.2066 | 4826.2066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5137 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 11008.9337 | 0.2 | 0.3 | 17173.9366 |  |  |  |  | 0 | 3229.2964 | 3229.2964 | 3229.2964 | 3229.2964 | 3229.2964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5138 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16769.6305 | 0.2 | 0.3 | 26160.6235 |  |  |  |  | 0 | 4328.0982 | 4328.0982 | 4328.0982 | 4328.0982 | 4328.0982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5139 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 22152.6269 | 0.2 | 0.3 | 34558.098 |  |  |  |  | 0 | 6992.5154 | 6992.5154 | 6992.5154 | 6992.5154 | 6992.5154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5140 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 21947.2479 | 0.2 | 0.3 | 34237.7068 |  |  |  |  | 0 | 5689.404 | 5689.404 | 5689.404 | 5689.404 | 5689.404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5141 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 31338.8715 | 0.2 | 0.3 | 48888.6396 |  |  |  |  | 0 | 3905.8267 | 3905.8267 | 3905.8267 | 3905.8267 | 3905.8267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5142 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 25847.3614 | 0.2 | 0.3 | 40321.8838 |  |  |  |  | 0 | 2757.5691 | 2757.5691 | 2757.5691 | 2757.5691 | 2757.5691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5143 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 26584.7134 | 0.2 | 0.3 | 41472.1529 |  |  |  |  | 0 | 7639.7113 | 7639.7113 | 7639.7113 | 7639.7113 | 7639.7113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5144 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 33094.8998 | 0.2 | 0.3 | 51628.0437 |  |  |  |  | 0 | 9929.1856 | 9929.1856 | 9929.1856 | 9929.1856 | 9929.1856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5145 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 17310.6707 | 0.2 | 0.3 | 27004.6462 |  |  |  |  | 0 | 4569.7917 | 4569.7917 | 4569.7917 | 4569.7917 | 4569.7917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5146 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 24812.6463 | 0.2 | 0.3 | 38707.7283 |  |  |  |  | 0 | 4754.603 | 4754.603 | 4754.603 | 4754.603 | 4754.603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5147 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 20121.9225 | 0.2 | 0.3 | 31390.199 |  |  |  |  | 0 | 8236.5448 | 8236.5448 | 8236.5448 | 8236.5448 | 8236.5448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5148 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 485.2546 | 0.2 | 0.3 | 756.9972 |  |  |  |  | 0 | 3886.867 | 3886.867 | 3886.867 | 3886.867 | 3886.867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5149 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16921.8051 | 0.2 | 0.3 | 26398.0159 |  |  |  |  | 0 | 4136.8682 | 4136.8682 | 4136.8682 | 4136.8682 | 4136.8682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5150 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 22575.5757 | 0.2 | 0.3 | 35217.8981 |  |  |  |  | 0 | 7043.3372 | 7043.3372 | 7043.3372 | 7043.3372 | 7043.3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5151 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 32962.2111 | 0.2 | 0.3 | 51421.0494 |  |  |  |  | 0 | 6345.9657 | 6345.9657 | 6345.9657 | 6345.9657 | 6345.9657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5152 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 38764.98 | 0.2 | 0.3 | 60473.3688 |  |  |  |  | 0 | 3140.4579 | 3140.4579 | 3140.4579 | 3140.4579 | 3140.4579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5153 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 15170.1267 | 0.2 | 0.3 | 23665.3977 |  |  |  |  | 0 | 3864.9499 | 3864.9499 | 3864.9499 | 3864.9499 | 3864.9499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5154 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 9001.2805 | 0.2 | 0.3 | 14041.9976 |  |  |  |  | 0 | 5780.6344 | 5780.6344 | 5780.6344 | 5780.6344 | 5780.6344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5155 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 12826.5779 | 0.2 | 0.3 | 20009.4615 |  |  |  |  | 0 | 1786.8469 | 1786.8469 | 1786.8469 | 1786.8469 | 1786.8469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5156 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 18977.278 | 0.2 | 0.3 | 29604.5537 |  |  |  |  | 0 | 6637.5235 | 6637.5235 | 6637.5235 | 6637.5235 | 6637.5235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5157 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16666.5161 | 0.2 | 0.3 | 25999.7651 |  |  |  |  | 0 | 7263.3517 | 7263.3517 | 7263.3517 | 7263.3517 | 7263.3517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5158 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 7921.2894 | 7921.2894 | 7921.2894 | 7921.2894 | 7921.2894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5159 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 31384.0581 | 0.2 | 0.3 | 48959.1306 |  |  |  |  | 0 | 6869.644 | 6869.644 | 6869.644 | 6869.644 | 6869.644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5160 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16666.5805 | 0.2 | 0.3 | 25999.8656 |  |  |  |  | 0 | 3830.329 | 3830.329 | 3830.329 | 3830.329 | 3830.329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5161 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 14799.8355 | 0.2 | 0.3 | 23087.7433 |  |  |  |  | 0 | 3909.997 | 3909.997 | 3909.997 | 3909.997 | 3909.997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5162 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7288 | 0.2 | 0.3 | 26000.0969 |  |  |  |  | 0 | 5421.4813 | 5421.4813 | 5421.4813 | 5421.4813 | 5421.4813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5163 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16666.5959 | 0.2 | 0.3 | 25999.8897 |  |  |  |  | 0 | 5202.1439 | 5202.1439 | 5202.1439 | 5202.1439 | 5202.1439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5164 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 23328.8443 | 0.2 | 0.3 | 36392.9971 |  |  |  |  | 0 | 4590.5038 | 4590.5038 | 4590.5038 | 4590.5038 | 4590.5038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5165 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16310.8383 | 0.2 | 0.3 | 25444.9078 |  |  |  |  | 0 | 2380.1803 | 2380.1803 | 2380.1803 | 2380.1803 | 2380.1803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5166 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 21302.4427 | 0.2 | 0.3 | 33231.8107 |  |  |  |  | 0 | 4632.984 | 4632.984 | 4632.984 | 4632.984 | 4632.984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5167 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 21380.6918 | 0.2 | 0.3 | 33353.8792 |  |  |  |  | 0 | 4921.5557 | 4921.5557 | 4921.5557 | 4921.5557 | 4921.5557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5168 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 16754.5811 | 0.2 | 0.3 | 26137.1466 |  |  |  |  | 0 | 2094.0292 | 2094.0292 | 2094.0292 | 2094.0292 | 2094.0292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5169 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 16710.1282 | 0.2 | 0.3 | 26067.8 |  |  |  |  | 0 | 4058.3193 | 4058.3193 | 4058.3193 | 4058.3193 | 4058.3193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5170 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 18536.3275 | 0.2 | 0.3 | 28916.671 |  |  |  |  | 0 | 9573.9032 | 9573.9032 | 9573.9032 | 9573.9032 | 9573.9032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5171 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 20620.6822 | 0.2 | 0.3 | 32168.2642 |  |  |  |  | 0 | 3917.2402 | 3917.2402 | 3917.2402 | 3917.2402 | 3917.2402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5172 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 4207.4719 | 4207.4719 | 4207.4719 | 4207.4719 | 4207.4719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5173 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 24885.0292 | 0.2 | 0.3 | 38820.6456 |  |  |  |  | 0 | 7023.6713 | 7023.6713 | 7023.6713 | 7023.6713 | 7023.6713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5174 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16752.83 | 0.2 | 0.3 | 26134.4148 |  |  |  |  | 0 | 3474.0434 | 3474.0434 | 3474.0434 | 3474.0434 | 3474.0434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5175 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 8391.7793 | 0.2 | 0.3 | 13091.1757 |  |  |  |  | 0 | 5318.3484 | 5318.3484 | 5318.3484 | 5318.3484 | 5318.3484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5176 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5177 | PEMBROKE PINES | 110351 | Public | 2036 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 5210.8416 | 5210.8416 | 5210.8416 | 5210.8416 | 5210.8416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5178 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 16676.7211 | 0.2 | 0.3 | 26015.685 |  |  |  |  | 0 | 4099.3714 | 4099.3714 | 4099.3714 | 4099.3714 | 4099.3714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5179 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 16669.6999 | 0.2 | 0.3 | 26004.7319 |  |  |  |  | 0 | 4084.0402 | 4084.0402 | 4084.0402 | 4084.0402 | 4084.0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5180 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 19166.547 | 0.2 | 0.3 | 29899.8133 |  |  |  |  | 0 | 2895.0391 | 2895.0391 | 2895.0391 | 2895.0391 | 2895.0391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5181 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 16686.2405 | 0.2 | 0.3 | 26030.5352 |  |  |  |  | 0 | 5153.3098 | 5153.3098 | 5153.3098 | 5153.3098 | 5153.3098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5182 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 36402.3966 | 0.2 | 0.3 | 56787.7387 |  |  |  |  | 0 | 6415.5703 | 6415.5703 | 6415.5703 | 6415.5703 | 6415.5703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5183 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 17703.4026 | 0.2 | 0.3 | 27617.3081 |  |  |  |  | 0 | 6584.7687 | 6584.7687 | 6584.7687 | 6584.7687 | 6584.7687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5184 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 12438.4446 | 0.2 | 0.3 | 19403.9736 |  |  |  |  | 0 | 3936.1019 | 3936.1019 | 3936.1019 | 3936.1019 | 3936.1019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5185 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 17088.0651 | 0.2 | 0.3 | 26657.3815 |  |  |  |  | 0 | 4052.9814 | 4052.9814 | 4052.9814 | 4052.9814 | 4052.9814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5186 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16687.1947 | 0.2 | 0.3 | 26032.0238 |  |  |  |  | 0 | 6310.1627 | 6310.1627 | 6310.1627 | 6310.1627 | 6310.1627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5187 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 23188.8171 | 0.2 | 0.3 | 36174.5546 |  |  |  |  | 0 | 5212.7033 | 5212.7033 | 5212.7033 | 5212.7033 | 5212.7033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5188 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 19831.4231 | 0.2 | 0.3 | 30937.0201 |  |  |  |  | 0 | 5203.3405 | 5203.3405 | 5203.3405 | 5203.3405 | 5203.3405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5189 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 30825.0489 | 0.2 | 0.3 | 48087.0762 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5190 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 34781.8395 | 0.2 | 0.3 | 54259.6696 |  |  |  |  | 0 | 5202.8497 | 5202.8497 | 5202.8497 | 5202.8497 | 5202.8497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5191 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 19274.19 | 0.2 | 0.3 | 30067.7364 |  |  |  |  | 0 | 5332.3227 | 5332.3227 | 5332.3227 | 5332.3227 | 5332.3227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5192 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 10923.8339 | 0.2 | 0.3 | 17041.1809 |  |  |  |  | 0 | 3226.5215 | 3226.5215 | 3226.5215 | 3226.5215 | 3226.5215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5193 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 18461.0847 | 0.2 | 0.3 | 28799.2922 |  |  |  |  | 0 | 5398.0317 | 5398.0317 | 5398.0317 | 5398.0317 | 5398.0317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5194 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 24296.9706 | 0.2 | 0.3 | 37903.2741 |  |  |  |  | 0 | 3381.0638 | 3381.0638 | 3381.0638 | 3381.0638 | 3381.0638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5195 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 4878.2678 | 0.2 | 0.3 | 7610.0978 |  |  |  |  | 0 | 5934.4236 | 5934.4236 | 5934.4236 | 5934.4236 | 5934.4236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5196 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 1907.0741 | 0.2 | 0.3 | 2975.0355 |  |  |  |  | 0 | 6840.2162 | 6840.2162 | 6840.2162 | 6840.2162 | 6840.2162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5197 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16913.0479 | 0.2 | 0.3 | 26384.3547 |  |  |  |  | 0 | 3907.7881 | 3907.7881 | 3907.7881 | 3907.7881 | 3907.7881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5198 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16781.0045 | 0.2 | 0.3 | 26178.367 |  |  |  |  | 0 | 5859.6249 | 5859.6249 | 5859.6249 | 5859.6249 | 5859.6249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5199 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 14675.5025 | 0.2 | 0.3 | 22893.7838 |  |  |  |  | 0 | 5201.5378 | 5201.5378 | 5201.5378 | 5201.5378 | 5201.5378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5200 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17249.7096 | 0.2 | 0.3 | 26909.547 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5201 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 8982.6917 | 0.2 | 0.3 | 14012.999 |  |  |  |  | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5202 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 23733.6743 | 0.2 | 0.3 | 37024.532 |  |  |  |  | 0 | 5342.9574 | 5342.9574 | 5342.9574 | 5342.9574 | 5342.9574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5203 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16667.2089 | 0.2 | 0.3 | 26000.8459 |  |  |  |  | 0 | 3888.0589 | 3888.0589 | 3888.0589 | 3888.0589 | 3888.0589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5204 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 20907.4809 | 0.2 | 0.3 | 32615.6703 |  |  |  |  | 0 | 4222.3535 | 4222.3535 | 4222.3535 | 4222.3535 | 4222.3535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5205 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16935.6599 | 0.2 | 0.3 | 26419.6295 |  |  |  |  | 0 | 7007.3348 | 7007.3348 | 7007.3348 | 7007.3348 | 7007.3348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5206 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 18323.7061 | 0.2 | 0.3 | 28584.9816 |  |  |  |  | 0 | 141.6539 | 141.6539 | 141.6539 | 141.6539 | 141.6539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5207 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 4028.5475 | 0.2 | 0.3 | 6284.5342 |  |  |  |  | 0 | 5203.6351 | 5203.6351 | 5203.6351 | 5203.6351 | 5203.6351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5208 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 22466.1825 | 0.2 | 0.3 | 35047.2448 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5209 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 29036.4085 | 0.2 | 0.3 | 45296.7973 |  |  |  |  | 0 | 5199.1908 | 5199.1908 | 5199.1908 | 5199.1908 | 5199.1908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5210 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 2676.6231 | 0.2 | 0.3 | 4175.5321 |  |  |  |  | 0 | 6063.7541 | 6063.7541 | 6063.7541 | 6063.7541 | 6063.7541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5211 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 15085.2081 | 0.2 | 0.3 | 23532.9247 |  |  |  |  | 0 | 5560.7816 | 5560.7816 | 5560.7816 | 5560.7816 | 5560.7816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5212 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 6771.8549 | 0.2 | 0.3 | 10564.0936 |  |  |  |  | 0 | 5443.4356 | 5443.4356 | 5443.4356 | 5443.4356 | 5443.4356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5213 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 28483.5851 | 0.2 | 0.3 | 44434.3928 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5214 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 30816.6369 | 0.2 | 0.3 | 48073.9536 |  |  |  |  | 0 | 5203.3177 | 5203.3177 | 5203.3177 | 5203.3177 | 5203.3177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5215 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 21356.6741 | 0.2 | 0.3 | 33316.4115 |  |  |  |  | 0 | 6333.1229 | 6333.1229 | 6333.1229 | 6333.1229 | 6333.1229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5216 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16677.6129 | 0.2 | 0.3 | 26017.0761 |  |  |  |  | 0 | 5204.4264 | 5204.4264 | 5204.4264 | 5204.4264 | 5204.4264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5217 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 31344.2641 | 0.2 | 0.3 | 48897.0519 |  |  |  |  | 0 | 5584.7709 | 5584.7709 | 5584.7709 | 5584.7709 | 5584.7709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5218 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 26196.6725 | 0.2 | 0.3 | 40866.809 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5219 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 14316.4561 | 0.2 | 0.3 | 22333.6716 |  |  |  |  | 0 | 9313.5725 | 9313.5725 | 9313.5725 | 9313.5725 | 9313.5725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5220 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 16849.8143 | 0.2 | 0.3 | 26285.7103 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5221 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 16737.9123 | 0.2 | 0.3 | 26111.1431 |  |  |  |  | 0 | 4506.8982 | 4506.8982 | 4506.8982 | 4506.8982 | 4506.8982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5222 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 45464.5686 | 0.2 | 0.3 | 70924.727 |  |  |  |  | 0 | 9737.4835 | 9737.4835 | 9737.4835 | 9737.4835 | 9737.4835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5223 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 37114.9097 | 0.2 | 0.3 | 57899.2591 |  |  |  |  | 0 | 9700.2981 | 9700.2981 | 9700.2981 | 9700.2981 | 9700.2981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5224 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 20646.6815 | 0.2 | 0.3 | 32208.8231 |  |  |  |  | 0 | 6467.7781 | 6467.7781 | 6467.7781 | 6467.7781 | 6467.7781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5225 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 17031.9951 | 0.2 | 0.3 | 26569.9124 |  |  |  |  | 0 | 11008.9926 | 11008.9926 | 11008.9926 | 11008.9926 | 11008.9926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5226 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 17284.5405 | 0.2 | 0.3 | 26963.8832 |  |  |  |  | 0 | 9243.1421 | 9243.1421 | 9243.1421 | 9243.1421 | 9243.1421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5227 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 22629.0646 | 0.2 | 0.3 | 35301.3408 |  |  |  |  | 0 | 5607.5755 | 5607.5755 | 5607.5755 | 5607.5755 | 5607.5755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5228 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 1173.8853 | 0.2 | 0.3 | 1831.2611 |  |  |  |  | 0 | 3742.0244 | 3742.0244 | 3742.0244 | 3742.0244 | 3742.0244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5229 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 46907.7069 | 0.2 | 0.3 | 73176.0227 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5230 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 22812.5761 | 0.2 | 0.3 | 35587.6188 |  |  |  |  | 0 | 5204.3634 | 5204.3634 | 5204.3634 | 5204.3634 | 5204.3634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5231 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16668.3545 | 0.2 | 0.3 | 26002.6331 |  |  |  |  | 0 | 9929.3611 | 9929.3611 | 9929.3611 | 9929.3611 | 9929.3611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5232 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 5203.177 | 5203.177 | 5203.177 | 5203.177 | 5203.177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5233 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 23254.1092 | 0.2 | 0.3 | 36276.4104 |  |  |  |  | 0 | 6854.1498 | 6854.1498 | 6854.1498 | 6854.1498 | 6854.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5234 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 9324.9053 | 0.2 | 0.3 | 14546.8523 |  |  |  |  | 0 | 5204.0817 | 5204.0817 | 5204.0817 | 5204.0817 | 5204.0817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5235 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16979.0051 | 0.2 | 0.3 | 26487.248 |  |  |  |  | 0 | 9781.799 | 9781.799 | 9781.799 | 9781.799 | 9781.799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5236 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16672.7189 | 0.2 | 0.3 | 26009.4414 |  |  |  |  | 0 | 5204.5134 | 5204.5134 | 5204.5134 | 5204.5134 | 5204.5134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5237 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 27404.9677 | 0.2 | 0.3 | 42751.7496 |  |  |  |  | 0 | 8659.0009 | 8659.0009 | 8659.0009 | 8659.0009 | 8659.0009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5238 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 31527.9685 | 0.2 | 0.3 | 49183.6308 |  |  |  |  | 0 | 5555.4632 | 5555.4632 | 5555.4632 | 5555.4632 | 5555.4632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5239 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 8614.6349 | 0.2 | 0.3 | 13438.8305 |  |  |  |  | 0 | 1520.708 | 1520.708 | 1520.708 | 1520.708 | 1520.708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5240 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 26946.4537 | 0.2 | 0.3 | 42036.4678 |  |  |  |  | 0 | 2311.114 | 2311.114 | 2311.114 | 2311.114 | 2311.114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5241 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 6294.5105 | 0.2 | 0.3 | 9819.4363 |  |  |  |  | 0 | 3910.4356 | 3910.4356 | 3910.4356 | 3910.4356 | 3910.4356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5242 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16674.3901 | 0.2 | 0.3 | 26012.0485 |  |  |  |  | 0 | 9783.6758 | 9783.6758 | 9783.6758 | 9783.6758 | 9783.6758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5243 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 18066.4741 | 0.2 | 0.3 | 28183.6996 |  |  |  |  | 0 | 7225.3838 | 7225.3838 | 7225.3838 | 7225.3838 | 7225.3838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5244 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16734.6051 | 0.2 | 0.3 | 26105.9839 |  |  |  |  | 0 | 4137.6301 | 4137.6301 | 4137.6301 | 4137.6301 | 4137.6301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5245 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 27993.494 | 0.2 | 0.3 | 43669.8506 |  |  |  |  | 0 | 2797.0941 | 2797.0941 | 2797.0941 | 2797.0941 | 2797.0941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5246 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 18193.3198 | 0.2 | 0.3 | 28381.5789 |  |  |  |  | 0 | 5204.3712 | 5204.3712 | 5204.3712 | 5204.3712 | 5204.3712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5247 | PEMBROKE PINES | 110351 | Public | 2036 | 5 | Swales | 66.6667 | 18952.0164 | 0.2 | 0.3 | 29565.1456 |  |  |  |  | 0 | 5202.0596 | 5202.0596 | 5202.0596 | 5202.0596 | 5202.0596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5248 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 28536.0998 | 0.2 | 0.3 | 44516.3157 |  |  |  |  | 0 | 4192.1755 | 4192.1755 | 4192.1755 | 4192.1755 | 4192.1755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5249 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16564.4147 | 0.2 | 0.3 | 25840.487 |  |  |  |  | 0 | 711.5863 | 711.5863 | 711.5863 | 711.5863 | 711.5863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5250 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 22766.0653 | 0.2 | 0.3 | 35515.0618 |  |  |  |  | 0 | 5979.1321 | 5979.1321 | 5979.1321 | 5979.1321 | 5979.1321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5251 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 14503.6909 | 0.2 | 0.3 | 22625.7578 |  |  |  |  | 0 | 7160.633 | 7160.633 | 7160.633 | 7160.633 | 7160.633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5252 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 7778.3795 | 0.2 | 0.3 | 12134.2721 |  |  |  |  | 0 | 9625.05 | 9625.05 | 9625.05 | 9625.05 | 9625.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5253 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 40476.885 | 0.2 | 0.3 | 63143.9406 |  |  |  |  | 0 | 5366.8366 | 5366.8366 | 5366.8366 | 5366.8366 | 5366.8366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5254 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 26152.3671 | 0.2 | 0.3 | 40797.6927 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5255 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 5829.372 | 0.2 | 0.3 | 9093.8203 |  |  |  |  | 0 | 9784.2386 | 9784.2386 | 9784.2386 | 9784.2386 | 9784.2386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5256 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 12890.5678 | 0.2 | 0.3 | 20109.2858 |  |  |  |  | 0 | 5205.7581 | 5205.7581 | 5205.7581 | 5205.7581 | 5205.7581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5257 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 24578.6371 | 0.2 | 0.3 | 38342.6739 |  |  |  |  | 0 | 7981.8596 | 7981.8596 | 7981.8596 | 7981.8596 | 7981.8596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5258 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 28430.6645 | 0.2 | 0.3 | 44351.8367 |  |  |  |  | 0 | 7006.9418 | 7006.9418 | 7006.9418 | 7006.9418 | 7006.9418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5259 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0718 | 0.2 | 0.3 | 26000.632 |  |  |  |  | 0 | 7061.8033 | 7061.8033 | 7061.8033 | 7061.8033 | 7061.8033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5260 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16668.5138 | 0.2 | 0.3 | 26002.8815 |  |  |  |  | 0 | 7927.4115 | 7927.4115 | 7927.4115 | 7927.4115 | 7927.4115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5261 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 22695.051 | 0.2 | 0.3 | 35404.2796 |  |  |  |  | 0 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5262 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 20027.1179 | 0.2 | 0.3 | 31242.304 |  |  |  |  | 0 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5263 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 19764.4249 | 0.2 | 0.3 | 30832.5029 |  |  |  |  | 0 | 9661.3426 | 9661.3426 | 9661.3426 | 9661.3426 | 9661.3426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5264 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 20390.805 | 0.2 | 0.3 | 31809.6558 |  |  |  |  | 0 | 1682.7767 | 1682.7767 | 1682.7767 | 1682.7767 | 1682.7767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5265 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 1986.5143 | 0.2 | 0.3 | 3098.9624 |  |  |  |  | 0 | 8742.0219 | 8742.0219 | 8742.0219 | 8742.0219 | 8742.0219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5266 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 10539.8561 | 0.2 | 0.3 | 16442.1756 |  |  |  |  | 0 | 3648.846 | 3648.846 | 3648.846 | 3648.846 | 3648.846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5267 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 6806.1561 | 0.2 | 0.3 | 10617.6036 |  |  |  |  | 0 | 6965.6606 | 6965.6606 | 6965.6606 | 6965.6606 | 6965.6606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5268 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 6167.6939 | 0.2 | 0.3 | 9621.6024 |  |  |  |  | 0 | 7858.3508 | 7858.3508 | 7858.3508 | 7858.3508 | 7858.3508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5269 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 796.0995 | 0.2 | 0.3 | 1241.9152 |  |  |  |  | 0 | 5214.9387 | 5214.9387 | 5214.9387 | 5214.9387 | 5214.9387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5270 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 8714.2113 | 0.2 | 0.3 | 13594.1697 |  |  |  |  | 0 | 9544.1539 | 9544.1539 | 9544.1539 | 9544.1539 | 9544.1539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5271 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16843.4093 | 0.2 | 0.3 | 26275.7186 |  |  |  |  | 0 | 4067.5818 | 4067.5818 | 4067.5818 | 4067.5818 | 4067.5818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5272 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 7274.872 | 0.2 | 0.3 | 11348.8003 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5273 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 21768.9087 | 0.2 | 0.3 | 33959.4976 |  |  |  |  | 0 | 9812.5907 | 9812.5907 | 9812.5907 | 9812.5907 | 9812.5907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5274 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17058.1395 | 0.2 | 0.3 | 26610.6977 |  |  |  |  | 0 | 5204.1371 | 5204.1371 | 5204.1371 | 5204.1371 | 5204.1371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5275 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17017.3843 | 0.2 | 0.3 | 26547.1195 |  |  |  |  | 0 | 7482.3991 | 7482.3991 | 7482.3991 | 7482.3991 | 7482.3991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5276 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17100.7139 | 0.2 | 0.3 | 26677.1136 |  |  |  |  | 0 | 7572.2146 | 7572.2146 | 7572.2146 | 7572.2146 | 7572.2146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5277 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17268.814 | 0.2 | 0.3 | 26939.3498 |  |  |  |  | 0 | 9546.1826 | 9546.1826 | 9546.1826 | 9546.1826 | 9546.1826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5278 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 7598.1915 | 0.2 | 0.3 | 11853.1787 |  |  |  |  | 0 | 2907.1159 | 2907.1159 | 2907.1159 | 2907.1159 | 2907.1159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5279 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 25752.2036 | 0.2 | 0.3 | 40173.4376 |  |  |  |  | 0 | 2615.9783 | 2615.9783 | 2615.9783 | 2615.9783 | 2615.9783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5280 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 22185.6743 | 0.2 | 0.3 | 34609.6519 |  |  |  |  | 0 | 9791.179 | 9791.179 | 9791.179 | 9791.179 | 9791.179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5281 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16674.6805 | 0.2 | 0.3 | 26012.5015 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5282 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 31340.5111 | 0.2 | 0.3 | 48891.1974 |  |  |  |  | 0 | 9820.847 | 9820.847 | 9820.847 | 9820.847 | 9820.847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5283 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 11608.445 | 0.2 | 0.3 | 18109.1742 |  |  |  |  | 0 | 5203.845 | 5203.845 | 5203.845 | 5203.845 | 5203.845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5284 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 11931.7921 | 0.2 | 0.3 | 18613.5956 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5285 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 8048.6863 | 0.2 | 0.3 | 12555.9507 |  |  |  |  | 0 | 8066.3382 | 8066.3382 | 8066.3382 | 8066.3382 | 8066.3382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5286 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 9769.2208 | 0.2 | 0.3 | 15239.9844 |  |  |  |  | 0 | 6936.9479 | 6936.9479 | 6936.9479 | 6936.9479 | 6936.9479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5287 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 17777.1032 | 0.2 | 0.3 | 27732.281 |  |  |  |  | 0 | 10193.8209 | 10193.8209 | 10193.8209 | 10193.8209 | 10193.8209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5288 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 32928.8185 | 0.2 | 0.3 | 51368.9569 |  |  |  |  | 0 | 4055.2272 | 4055.2272 | 4055.2272 | 4055.2272 | 4055.2272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5289 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 6976.4254 | 0.2 | 0.3 | 10883.2236 |  |  |  |  | 0 | 4413.7841 | 4413.7841 | 4413.7841 | 4413.7841 | 4413.7841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5290 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 851.544 | 0.2 | 0.3 | 1328.4086 |  |  |  |  | 0 | 7628.7505 | 7628.7505 | 7628.7505 | 7628.7505 | 7628.7505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5291 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 172.3841 | 0.2 | 0.3 | 268.9192 |  |  |  |  | 0 | 11281.436 | 11281.436 | 11281.436 | 11281.436 | 11281.436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5292 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 19572.8543 | 0.2 | 0.3 | 30533.6528 |  |  |  |  | 0 | 4348.6149 | 4348.6149 | 4348.6149 | 4348.6149 | 4348.6149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5293 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 31174.919 | 0.2 | 0.3 | 48632.8736 |  |  |  |  | 0 | 1374.3657 | 1374.3657 | 1374.3657 | 1374.3657 | 1374.3657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5294 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16666.5997 | 0.2 | 0.3 | 25999.8956 |  |  |  |  | 0 | 9486.9653 | 9486.9653 | 9486.9653 | 9486.9653 | 9486.9653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5295 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 23782.607 | 0.2 | 0.3 | 37100.8669 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5296 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 8332.2218 | 0.2 | 0.3 | 12998.266 |  |  |  |  | 0 | 8036.3218 | 8036.3218 | 8036.3218 | 8036.3218 | 8036.3218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5297 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 15171.0914 | 0.2 | 0.3 | 23666.9026 |  |  |  |  | 0 | 6969.1851 | 6969.1851 | 6969.1851 | 6969.1851 | 6969.1851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5298 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 24942.2107 | 0.2 | 0.3 | 38909.8486 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5299 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 20533.5709 | 0.2 | 0.3 | 32032.3707 |  |  |  |  | 0 | 8099.4781 | 8099.4781 | 8099.4781 | 8099.4781 | 8099.4781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5300 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 27166.8307 | 0.2 | 0.3 | 42380.2559 |  |  |  |  | 0 | 7131.4567 | 7131.4567 | 7131.4567 | 7131.4567 | 7131.4567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5301 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 31624.4395 | 0.2 | 0.3 | 49334.1256 |  |  |  |  | 0 | 4649.1712 | 4649.1712 | 4649.1712 | 4649.1712 | 4649.1712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5302 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 25919.6873 | 0.2 | 0.3 | 40434.7121 |  |  |  |  | 0 | 5392.4609 | 5392.4609 | 5392.4609 | 5392.4609 | 5392.4609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5303 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 31413.9861 | 0.2 | 0.3 | 49005.8184 |  |  |  |  | 0 | 6208.4303 | 6208.4303 | 6208.4303 | 6208.4303 | 6208.4303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5304 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 3524.2039 | 3524.2039 | 3524.2039 | 3524.2039 | 3524.2039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5305 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 15159.711 | 0.2 | 0.3 | 23649.1492 |  |  |  |  | 0 | 9806.5823 | 9806.5823 | 9806.5823 | 9806.5823 | 9806.5823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5306 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 18098.2068 | 0.2 | 0.3 | 28233.2026 |  |  |  |  | 0 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5307 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16710.3565 | 0.2 | 0.3 | 26068.1561 |  |  |  |  | 0 | 8402.7792 | 8402.7792 | 8402.7792 | 8402.7792 | 8402.7792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5308 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16381.9624 | 0.2 | 0.3 | 25555.8613 |  |  |  |  | 0 | 6607.6609 | 6607.6609 | 6607.6609 | 6607.6609 | 6607.6609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5309 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 28500.8612 | 0.2 | 0.3 | 44461.3435 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5310 | PEMBROKE PINES | 110351 | Public | 2036 | 5 | Swales | 66.6667 | 16672.9713 | 0.2 | 0.3 | 26009.8353 |  |  |  |  | 0 | 9885.2463 | 9885.2463 | 9885.2463 | 9885.2463 | 9885.2463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5311 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 28421.3397 | 0.2 | 0.3 | 44337.2899 |  |  |  |  | 0 | 3997.3125 | 3997.3125 | 3997.3125 | 3997.3125 | 3997.3125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5312 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 5027.4625 | 0.2 | 0.3 | 7842.8414 |  |  |  |  | 0 | 4058.4399 | 4058.4399 | 4058.4399 | 4058.4399 | 4058.4399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5313 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 2550.0127 | 0.2 | 0.3 | 3978.0198 |  |  |  |  | 0 | 4483.8048 | 4483.8048 | 4483.8048 | 4483.8048 | 4483.8048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5314 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 17946.3411 | 0.2 | 0.3 | 27996.2921 |  |  |  |  | 0 | 9089.8696 | 9089.8696 | 9089.8696 | 9089.8696 | 9089.8696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5315 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 16903.3845 | 0.2 | 0.3 | 26369.2799 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5316 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6857 | 0.2 | 0.3 | 26000.0296 |  |  |  |  | 0 | 9801.0358 | 9801.0358 | 9801.0358 | 9801.0358 | 9801.0358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5317 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7764 | 0.2 | 0.3 | 26000.1712 |  |  |  |  | 0 | 5204.0134 | 5204.0134 | 5204.0134 | 5204.0134 | 5204.0134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5318 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16667.3563 | 0.2 | 0.3 | 26001.0759 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5319 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 25365.0435 | 0.2 | 0.3 | 39569.4678 |  |  |  |  | 0 | 9836.4353 | 9836.4353 | 9836.4353 | 9836.4353 | 9836.4353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5320 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16681.5995 | 0.2 | 0.3 | 26023.2953 |  |  |  |  | 0 | 9755.7976 | 9755.7976 | 9755.7976 | 9755.7976 | 9755.7976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5321 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 15977.7236 | 0.2 | 0.3 | 24925.2488 |  |  |  |  | 0 | 10012.5633 | 10012.5633 | 10012.5633 | 10012.5633 | 10012.5633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5322 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 12712.2207 | 0.2 | 0.3 | 19831.0643 |  |  |  |  | 0 | 7843.4959 | 7843.4959 | 7843.4959 | 7843.4959 | 7843.4959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5323 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 18643.9474 | 0.2 | 0.3 | 29084.5579 |  |  |  |  | 0 | 7514.2653 | 7514.2653 | 7514.2653 | 7514.2653 | 7514.2653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5324 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 18080.0195 | 0.2 | 0.3 | 28204.8305 |  |  |  |  | 0 | 5736.0909 | 5736.0909 | 5736.0909 | 5736.0909 | 5736.0909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5325 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 33688.9026 | 0.2 | 0.3 | 52554.6881 |  |  |  |  | 0 | 5250.3654 | 5250.3654 | 5250.3654 | 5250.3654 | 5250.3654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5326 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 23413.5997 | 0.2 | 0.3 | 36525.2155 |  |  |  |  | 0 | 5206.8962 | 5206.8962 | 5206.8962 | 5206.8962 | 5206.8962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5327 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 22772.3003 | 0.2 | 0.3 | 35524.7884 |  |  |  |  | 0 | 8252.1234 | 8252.1234 | 8252.1234 | 8252.1234 | 8252.1234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5328 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 28389.9443 | 0.2 | 0.3 | 44288.3131 |  |  |  |  | 0 | 5204.6954 | 5204.6954 | 5204.6954 | 5204.6954 | 5204.6954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5329 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 10920.0675 | 0.2 | 0.3 | 17035.3052 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5330 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 18399.2141 | 0.2 | 0.3 | 28702.774 |  |  |  |  | 0 | 5204.5854 | 5204.5854 | 5204.5854 | 5204.5854 | 5204.5854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5331 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 27808.914 | 0.2 | 0.3 | 43381.9058 |  |  |  |  | 0 | 6128.1047 | 6128.1047 | 6128.1047 | 6128.1047 | 6128.1047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5332 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16694.6885 | 0.2 | 0.3 | 26043.7141 |  |  |  |  | 0 | 6736.1128 | 6736.1128 | 6736.1128 | 6736.1128 | 6736.1128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5333 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16769.9667 | 0.2 | 0.3 | 26161.1481 |  |  |  |  | 0 | 3363.5822 | 3363.5822 | 3363.5822 | 3363.5822 | 3363.5822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5334 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 18410.2379 | 0.2 | 0.3 | 28719.9712 |  |  |  |  | 0 | 9628.8068 | 9628.8068 | 9628.8068 | 9628.8068 | 9628.8068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5335 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 3693.4863 | 0.2 | 0.3 | 5761.8387 |  |  |  |  | 0 | 5304.9266 | 5304.9266 | 5304.9266 | 5304.9266 | 5304.9266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5336 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 25764.5723 | 0.2 | 0.3 | 40192.7327 |  |  |  |  | 0 | 6445.5517 | 6445.5517 | 6445.5517 | 6445.5517 | 6445.5517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5337 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 18247.7477 | 0.2 | 0.3 | 28466.4864 |  |  |  |  | 0 | 7366.8859 | 7366.8859 | 7366.8859 | 7366.8859 | 7366.8859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5338 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 5518.2864 | 0.2 | 0.3 | 8608.5268 |  |  |  |  | 0 | 7559.0916 | 7559.0916 | 7559.0916 | 7559.0916 | 7559.0916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5339 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 8349.1864 | 0.2 | 0.3 | 13024.7308 |  |  |  |  | 0 | 4917.294 | 4917.294 | 4917.294 | 4917.294 | 4917.294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5340 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 605.8805 | 0.2 | 0.3 | 945.1735 |  |  |  |  | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5341 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 5621.4895 | 0.2 | 0.3 | 8769.5236 |  |  |  |  | 0 | 5203.9871 | 5203.9871 | 5203.9871 | 5203.9871 | 5203.9871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5342 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 1045.3264 | 0.2 | 0.3 | 1630.7092 |  |  |  |  | 0 | 6330.9392 | 6330.9392 | 6330.9392 | 6330.9392 | 6330.9392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5343 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17107.9269 | 0.2 | 0.3 | 26688.366 |  |  |  |  | 0 | 7077.3544 | 7077.3544 | 7077.3544 | 7077.3544 | 7077.3544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5344 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 3251.3817 | 0.2 | 0.3 | 5072.1555 |  |  |  |  | 0 | 6828.0038 | 6828.0038 | 6828.0038 | 6828.0038 | 6828.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5345 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 23142.7375 | 0.2 | 0.3 | 36102.6704 |  |  |  |  | 0 | 5207.0663 | 5207.0663 | 5207.0663 | 5207.0663 | 5207.0663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5346 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 18704.786 | 0.2 | 0.3 | 29179.4662 |  |  |  |  | 0 | 5204.1649 | 5204.1649 | 5204.1649 | 5204.1649 | 5204.1649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5347 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 30940.0472 | 0.2 | 0.3 | 48266.4736 |  |  |  |  | 0 | 4090.348 | 4090.348 | 4090.348 | 4090.348 | 4090.348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5348 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16642.5406 | 0.2 | 0.3 | 25962.3633 |  |  |  |  | 0 | 2825.4882 | 2825.4882 | 2825.4882 | 2825.4882 | 2825.4882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5349 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 7544.2843 | 0.2 | 0.3 | 11769.0835 |  |  |  |  | 0 | 9784.5697 | 9784.5697 | 9784.5697 | 9784.5697 | 9784.5697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5350 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 35281.2837 | 0.2 | 0.3 | 55038.8025 |  |  |  |  | 0 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5351 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 31037.5994 | 0.2 | 0.3 | 48418.6551 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5352 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 22279.1734 | 0.2 | 0.3 | 34755.5105 |  |  |  |  | 0 | 8280.7396 | 8280.7396 | 8280.7396 | 8280.7396 | 8280.7396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5353 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 1823.6389 | 0.2 | 0.3 | 2844.8767 |  |  |  |  | 0 | 7593.6835 | 7593.6835 | 7593.6835 | 7593.6835 | 7593.6835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5354 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 19255.6969 | 0.2 | 0.3 | 30038.8871 |  |  |  |  | 0 | 5203.1185 | 5203.1185 | 5203.1185 | 5203.1185 | 5203.1185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5355 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 18055.0724 | 0.2 | 0.3 | 28165.9129 |  |  |  |  | 0 | 3680.1595 | 3680.1595 | 3680.1595 | 3680.1595 | 3680.1595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5356 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 18527.7089 | 0.2 | 0.3 | 28903.2258 |  |  |  |  | 0 | 3199.9348 | 3199.9348 | 3199.9348 | 3199.9348 | 3199.9348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5357 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 10402.0687 | 0.2 | 0.3 | 16227.2271 |  |  |  |  | 0 | 5214.9955 | 5214.9955 | 5214.9955 | 5214.9955 | 5214.9955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5358 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 8184.1647 | 0.2 | 0.3 | 12767.2969 |  |  |  |  | 0 | 5511.3098 | 5511.3098 | 5511.3098 | 5511.3098 | 5511.3098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5359 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 4901.7699 | 0.2 | 0.3 | 7646.7611 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5360 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 5557.6856 | 0.2 | 0.3 | 8669.9895 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5361 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 31901.7169 | 0.2 | 0.3 | 49766.6783 |  |  |  |  | 0 | 5204.4726 | 5204.4726 | 5204.4726 | 5204.4726 | 5204.4726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5362 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 26334.4506 | 0.2 | 0.3 | 41081.7429 |  |  |  |  | 0 | 1828.2033 | 1828.2033 | 1828.2033 | 1828.2033 | 1828.2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5363 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 10186.5783 | 0.2 | 0.3 | 15891.0622 |  |  |  |  | 0 | 5205.2737 | 5205.2737 | 5205.2737 | 5205.2737 | 5205.2737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5364 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16941.9575 | 0.2 | 0.3 | 26429.4536 |  |  |  |  | 0 | 3856.9104 | 3856.9104 | 3856.9104 | 3856.9104 | 3856.9104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5365 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 3435.1543 | 0.2 | 0.3 | 5358.8408 |  |  |  |  | 0 | 2075.0025 | 2075.0025 | 2075.0025 | 2075.0025 | 2075.0025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5366 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 14972.3245 | 0.2 | 0.3 | 23356.8263 |  |  |  |  | 0 | 2560.6043 | 2560.6043 | 2560.6043 | 2560.6043 | 2560.6043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5367 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 21550.8477 | 0.2 | 0.3 | 33619.3224 |  |  |  |  | 0 | 5203.4816 | 5203.4816 | 5203.4816 | 5203.4816 | 5203.4816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5368 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 13918.9835 | 0.2 | 0.3 | 21713.6143 |  |  |  |  | 0 | 5202.7081 | 5202.7081 | 5202.7081 | 5202.7081 | 5202.7081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5369 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 32022.0795 | 0.2 | 0.3 | 49954.444 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5370 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 26633.9891 | 0.2 | 0.3 | 41549.0229 |  |  |  |  | 0 | 1329.6741 | 1329.6741 | 1329.6741 | 1329.6741 | 1329.6741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5371 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 10268.9167 | 0.2 | 0.3 | 16019.5101 |  |  |  |  | 0 | 5207.4473 | 5207.4473 | 5207.4473 | 5207.4473 | 5207.4473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5372 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 5957.4481 | 0.2 | 0.3 | 9293.619 |  |  |  |  | 0 | 5206.6087 | 5206.6087 | 5206.6087 | 5206.6087 | 5206.6087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5373 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 15143.4628 | 0.2 | 0.3 | 23623.802 |  |  |  |  | 0 | 3877.135 | 3877.135 | 3877.135 | 3877.135 | 3877.135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5374 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16682.1839 | 0.2 | 0.3 | 26024.2069 |  |  |  |  | 0 | 5211.871 | 5211.871 | 5211.871 | 5211.871 | 5211.871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5375 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 16678.566 | 0.2 | 0.3 | 26018.563 |  |  |  |  | 0 | 5204.7369 | 5204.7369 | 5204.7369 | 5204.7369 | 5204.7369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5376 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 18401.7729 | 0.2 | 0.3 | 28706.7657 |  |  |  |  | 0 | 5204.9491 | 5204.9491 | 5204.9491 | 5204.9491 | 5204.9491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5377 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 2062.8703 | 0.2 | 0.3 | 3218.0777 |  |  |  |  | 0 | 5206.0361 | 5206.0361 | 5206.0361 | 5206.0361 | 5206.0361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5378 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 26531.3285 | 0.2 | 0.3 | 41388.8724 |  |  |  |  | 0 | 6076.0779 | 6076.0779 | 6076.0779 | 6076.0779 | 6076.0779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5379 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 31551.5275 | 0.2 | 0.3 | 49220.3828 |  |  |  |  | 0 | 3660.5729 | 3660.5729 | 3660.5729 | 3660.5729 | 3660.5729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5380 | PEMBROKE PINES | 110351 | Public | 2036 | 5 | Swales | 66.6667 | 16852.9279 | 0.2 | 0.3 | 26290.5675 |  |  |  |  | 0 | 6691.1953 | 6691.1953 | 6691.1953 | 6691.1953 | 6691.1953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5381 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 16841.0179 | 0.2 | 0.3 | 26271.9879 |  |  |  |  | 0 | 7759.4774 | 7759.4774 | 7759.4774 | 7759.4774 | 7759.4774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5382 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 3943.8115 | 0.2 | 0.3 | 6152.3459 |  |  |  |  | 0 | 8044.8126 | 8044.8126 | 8044.8126 | 8044.8126 | 8044.8126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5383 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 6.9061 | 0.2 | 0.3 | 10.7736 |  |  |  |  | 0 | 6962.7578 | 6962.7578 | 6962.7578 | 6962.7578 | 6962.7578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5384 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 24300.2275 | 0.2 | 0.3 | 37908.3548 |  |  |  |  | 0 | 4546.1766 | 4546.1766 | 4546.1766 | 4546.1766 | 4546.1766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5385 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 31356.6539 | 0.2 | 0.3 | 48916.38 |  |  |  |  | 0 | 9768.5395 | 9768.5395 | 9768.5395 | 9768.5395 | 9768.5395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5386 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 18760.4829 | 0.2 | 0.3 | 29266.3533 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5387 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6055 | 0.2 | 0.3 | 25999.9046 |  |  |  |  | 0 | 8094.1916 | 8094.1916 | 8094.1916 | 8094.1916 | 8094.1916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5388 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.4006 | 0.2 | 0.3 | 25999.5849 |  |  |  |  | 0 | 435.2121 | 435.2121 | 435.2121 | 435.2121 | 435.2121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5389 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16770.0658 | 0.2 | 0.3 | 26161.3026 |  |  |  |  | 0 | 9610.1368 | 9610.1368 | 9610.1368 | 9610.1368 | 9610.1368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5390 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 19978.0649 | 0.2 | 0.3 | 31165.7813 |  |  |  |  | 0 | 8028.6858 | 8028.6858 | 8028.6858 | 8028.6858 | 8028.6858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5391 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 17082.1289 | 0.2 | 0.3 | 26648.121 |  |  |  |  | 0 | 9462.3497 | 9462.3497 | 9462.3497 | 9462.3497 | 9462.3497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5392 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 28882.7829 | 0.2 | 0.3 | 45057.1414 |  |  |  |  | 0 | 5202.1733 | 5202.1733 | 5202.1733 | 5202.1733 | 5202.1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5393 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 17778.3852 | 0.2 | 0.3 | 27734.2809 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5394 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 37170.3876 | 0.2 | 0.3 | 57985.8047 |  |  |  |  | 0 | 5202.2579 | 5202.2579 | 5202.2579 | 5202.2579 | 5202.2579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5395 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 21552.8087 | 0.2 | 0.3 | 33622.3815 |  |  |  |  | 0 | 10162.5361 | 10162.5361 | 10162.5361 | 10162.5361 | 10162.5361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5396 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 25959.7093 | 0.2 | 0.3 | 40497.1466 |  |  |  |  | 0 | 9790.03 | 9790.03 | 9790.03 | 9790.03 | 9790.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5397 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 22322.3527 | 0.2 | 0.3 | 34822.8702 |  |  |  |  | 0 | 4615.9625 | 4615.9625 | 4615.9625 | 4615.9625 | 4615.9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5398 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 19987.4713 | 0.2 | 0.3 | 31180.4553 |  |  |  |  | 0 | 5201.4077 | 5201.4077 | 5201.4077 | 5201.4077 | 5201.4077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5399 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 22111.2953 | 0.2 | 0.3 | 34493.6206 |  |  |  |  | 0 | 5200.4459 | 5200.4459 | 5200.4459 | 5200.4459 | 5200.4459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5400 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16850.9306 | 0.2 | 0.3 | 26287.4517 |  |  |  |  | 0 | 6699.164 | 6699.164 | 6699.164 | 6699.164 | 6699.164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5401 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 29778.918 | 0.2 | 0.3 | 46455.1121 |  |  |  |  | 0 | 9836.6678 | 9836.6678 | 9836.6678 | 9836.6678 | 9836.6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5402 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16694.9565 | 0.2 | 0.3 | 26044.1321 |  |  |  |  | 0 | 5202.8256 | 5202.8256 | 5202.8256 | 5202.8256 | 5202.8256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5403 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16718.0835 | 0.2 | 0.3 | 26080.2102 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5404 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 20082.3366 | 0.2 | 0.3 | 31328.4451 |  |  |  |  | 0 | 5202.7205 | 5202.7205 | 5202.7205 | 5202.7205 | 5202.7205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5405 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 19405.2915 | 0.2 | 0.3 | 30272.2547 |  |  |  |  | 0 | 9911.5745 | 9911.5745 | 9911.5745 | 9911.5745 | 9911.5745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5406 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 22419.1543 | 0.2 | 0.3 | 34973.8807 |  |  |  |  | 0 | 1058.6803 | 1058.6803 | 1058.6803 | 1058.6803 | 1058.6803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5407 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 20398.6943 | 0.2 | 0.3 | 31821.9632 |  |  |  |  | 0 | 420.5724 | 420.5724 | 420.5724 | 420.5724 | 420.5724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5408 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 22020.4068 | 0.2 | 0.3 | 34351.8346 |  |  |  |  | 0 | 10464.6272 | 10464.6272 | 10464.6272 | 10464.6272 | 10464.6272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5409 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 8352.2214 | 0.2 | 0.3 | 13029.4654 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5410 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 18201.5221 | 0.2 | 0.3 | 28394.3744 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5411 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 7543.2676 | 0.2 | 0.3 | 11767.4975 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5412 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 34790.4743 | 0.2 | 0.3 | 54273.14 |  |  |  |  | 0 | 5824.082 | 5824.082 | 5824.082 | 5824.082 | 5824.082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5413 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 11501.5395 | 0.2 | 0.3 | 17942.4016 |  |  |  |  | 0 | 5707.1037 | 5707.1037 | 5707.1037 | 5707.1037 | 5707.1037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5414 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16652.3831 | 0.2 | 0.3 | 25977.7176 |  |  |  |  | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5415 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 18162.2531 | 0.2 | 0.3 | 28333.1148 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5416 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 3980.0311 | 0.2 | 0.3 | 6208.8486 |  |  |  |  | 0 | 6069.8922 | 6069.8922 | 6069.8922 | 6069.8922 | 6069.8922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5417 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 6655.3239 | 0.2 | 0.3 | 10382.3052 |  |  |  |  | 0 | 11818.2839 | 11818.2839 | 11818.2839 | 11818.2839 | 11818.2839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5418 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 5625.2937 | 0.2 | 0.3 | 8775.4581 |  |  |  |  | 0 | 5202.188 | 5202.188 | 5202.188 | 5202.188 | 5202.188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5419 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 8621.0475 | 0.2 | 0.3 | 13448.834 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5420 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 8055.9739 | 0.2 | 0.3 | 12567.3192 |  |  |  |  | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5421 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 18471.8287 | 0.2 | 0.3 | 28816.0528 |  |  |  |  | 0 | 5521.0545 | 5521.0545 | 5521.0545 | 5521.0545 | 5521.0545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5422 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 15756.2748 | 0.2 | 0.3 | 24579.7887 |  |  |  |  | 0 | 5202.1588 | 5202.1588 | 5202.1588 | 5202.1588 | 5202.1588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5423 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 19728.9575 | 0.2 | 0.3 | 30777.1736 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5424 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 19329.815 | 0.2 | 0.3 | 30154.5114 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5425 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 30475.2891 | 0.2 | 0.3 | 47541.4509 |  |  |  |  | 0 | 5204.3288 | 5204.3288 | 5204.3288 | 5204.3288 | 5204.3288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5426 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 23753.6042 | 0.2 | 0.3 | 37055.6226 |  |  |  |  | 0 | 9791.0062 | 9791.0062 | 9791.0062 | 9791.0062 | 9791.0062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5427 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 25725.3001 | 0.2 | 0.3 | 40131.4681 |  |  |  |  | 0 | 5202.541 | 5202.541 | 5202.541 | 5202.541 | 5202.541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5428 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 10046.7412 | 0.2 | 0.3 | 15672.9163 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5429 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 7708.6716 | 0.2 | 0.3 | 12025.5277 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5430 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 33576.4919 | 0.2 | 0.3 | 52379.3273 |  |  |  |  | 0 | 5249.2341 | 5249.2341 | 5249.2341 | 5249.2341 | 5249.2341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5431 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 15228.683 | 0.2 | 0.3 | 23756.7455 |  |  |  |  | 0 | 5201.6712 | 5201.6712 | 5201.6712 | 5201.6712 | 5201.6712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5432 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 15939.9939 | 0.2 | 0.3 | 24866.3904 |  |  |  |  | 0 | 5201.784 | 5201.784 | 5201.784 | 5201.784 | 5201.784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5433 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 4926.7349 | 0.2 | 0.3 | 7685.7064 |  |  |  |  | 0 | 2403.4489 | 2403.4489 | 2403.4489 | 2403.4489 | 2403.4489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5434 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 12925.6558 | 0.2 | 0.3 | 20164.023 |  |  |  |  | 0 | 2798.2014 | 2798.2014 | 2798.2014 | 2798.2014 | 2798.2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5435 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 4277.8908 | 0.2 | 0.3 | 6673.5096 |  |  |  |  | 0 | 2798.6398 | 2798.6398 | 2798.6398 | 2798.6398 | 2798.6398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5436 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 17796.0268 | 0.2 | 0.3 | 27761.8018 |  |  |  |  | 0 | 5202.5549 | 5202.5549 | 5202.5549 | 5202.5549 | 5202.5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5437 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16696.8906 | 0.2 | 0.3 | 26047.1493 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5438 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 41351.1171 | 0.2 | 0.3 | 64507.7426 |  |  |  |  | 0 | 7787.5969 | 7787.5969 | 7787.5969 | 7787.5969 | 7787.5969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5439 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 25324.3662 | 0.2 | 0.3 | 39506.0113 |  |  |  |  | 0 | 988.1909 | 988.1909 | 988.1909 | 988.1909 | 988.1909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5440 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 18800.1071 | 0.2 | 0.3 | 29328.167 |  |  |  |  | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5441 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 22776.3349 | 0.2 | 0.3 | 35531.0825 |  |  |  |  | 0 | 5202.02 | 5202.02 | 5202.02 | 5202.02 | 5202.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5442 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 4828.7042 | 0.2 | 0.3 | 7532.7786 |  |  |  |  | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5443 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 33656.934 | 0.2 | 0.3 | 52504.817 |  |  |  |  | 0 | 5201.4535 | 5201.4535 | 5201.4535 | 5201.4535 | 5201.4535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5444 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 36833.8666 | 0.2 | 0.3 | 57460.8319 |  |  |  |  | 0 | 9780.062 | 9780.062 | 9780.062 | 9780.062 | 9780.062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5445 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 4460.1953 | 0.2 | 0.3 | 6957.9047 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5446 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 23643.6011 | 0.2 | 0.3 | 36884.0178 |  |  |  |  | 0 | 9780.3846 | 9780.3846 | 9780.3846 | 9780.3846 | 9780.3846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5447 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 28948.4146 | 0.2 | 0.3 | 45159.5268 |  |  |  |  | 0 | 5203.2383 | 5203.2383 | 5203.2383 | 5203.2383 | 5203.2383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5448 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 31308.0216 | 0.2 | 0.3 | 48840.5137 |  |  |  |  | 0 | 5202.9545 | 5202.9545 | 5202.9545 | 5202.9545 | 5202.9545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5449 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 17326.2812 | 0.2 | 0.3 | 27028.9987 |  |  |  |  | 0 | 5204.0794 | 5204.0794 | 5204.0794 | 5204.0794 | 5204.0794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5450 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 17015.2775 | 0.2 | 0.3 | 26543.833 |  |  |  |  | 0 | 5201.9312 | 5201.9312 | 5201.9312 | 5201.9312 | 5201.9312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5451 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 17351.6702 | 0.2 | 0.3 | 27068.6055 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5452 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 29576.7769 | 0.2 | 0.3 | 46139.7719 |  |  |  |  | 0 | 5201.9828 | 5201.9828 | 5201.9828 | 5201.9828 | 5201.9828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5453 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 26447.2156 | 0.2 | 0.3 | 41257.6563 |  |  |  |  | 0 | 9780.061 | 9780.061 | 9780.061 | 9780.061 | 9780.061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5454 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 28638.7771 | 0.2 | 0.3 | 44676.4922 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5455 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 24077.3933 | 0.2 | 0.3 | 37560.7335 |  |  |  |  | 0 | 9780.4264 | 9780.4264 | 9780.4264 | 9780.4264 | 9780.4264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5456 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 24860.7027 | 0.2 | 0.3 | 38782.6962 |  |  |  |  | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5457 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 33359.8362 | 0.2 | 0.3 | 52041.3445 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5458 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 29185.73 | 0.2 | 0.3 | 45529.7388 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5459 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 27369.1967 | 0.2 | 0.3 | 42695.9469 |  |  |  |  | 0 | 8483.5387 | 8483.5387 | 8483.5387 | 8483.5387 | 8483.5387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5460 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 16697.0517 | 0.2 | 0.3 | 26047.4006 |  |  |  |  | 0 | 9781.6871 | 9781.6871 | 9781.6871 | 9781.6871 | 9781.6871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5461 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 11221.784 | 0.2 | 0.3 | 17505.983 |  |  |  |  | 0 | 9829.2676 | 9829.2676 | 9829.2676 | 9829.2676 | 9829.2676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5462 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 23136.898 | 0.2 | 0.3 | 36093.5609 |  |  |  |  | 0 | 16.648 | 16.648 | 16.648 | 16.648 | 16.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5463 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 37241.7661 | 0.2 | 0.3 | 58097.1552 |  |  |  |  | 0 | 5201.4061 | 5201.4061 | 5201.4061 | 5201.4061 | 5201.4061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5464 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 24870.3043 | 0.2 | 0.3 | 38797.6747 |  |  |  |  | 0 | 5203.8381 | 5203.8381 | 5203.8381 | 5203.8381 | 5203.8381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5465 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 33739.5941 | 0.2 | 0.3 | 52633.7668 |  |  |  |  | 0 | 5203.4497 | 5203.4497 | 5203.4497 | 5203.4497 | 5203.4497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5466 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 20410.7478 | 0.2 | 0.3 | 31840.7666 |  |  |  |  | 0 | 5203.2729 | 5203.2729 | 5203.2729 | 5203.2729 | 5203.2729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5467 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16447.2841 | 0.2 | 0.3 | 25657.7632 |  |  |  |  | 0 | 3373.9745 | 3373.9745 | 3373.9745 | 3373.9745 | 3373.9745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5468 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 34559.6101 | 0.2 | 0.3 | 53912.9918 |  |  |  |  | 0 | 5204.514 | 5204.514 | 5204.514 | 5204.514 | 5204.514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5469 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 27880.0884 | 0.2 | 0.3 | 43492.9379 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5470 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 17724.8508 | 0.2 | 0.3 | 27650.7672 |  |  |  |  | 0 | 5201.6022 | 5201.6022 | 5201.6022 | 5201.6022 | 5201.6022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5471 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16706.0819 | 0.2 | 0.3 | 26061.4877 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5472 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 18510.3353 | 0.2 | 0.3 | 28876.1231 |  |  |  |  | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5473 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 3403.5508 | 0.2 | 0.3 | 5309.5392 |  |  |  |  | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5474 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 18899.1537 | 0.2 | 0.3 | 29482.6797 |  |  |  |  | 0 | 7387.8135 | 7387.8135 | 7387.8135 | 7387.8135 | 7387.8135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5475 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16895.7536 | 0.2 | 0.3 | 26357.3756 |  |  |  |  | 0 | 5204.6044 | 5204.6044 | 5204.6044 | 5204.6044 | 5204.6044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5476 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16697.0716 | 0.2 | 0.3 | 26047.4317 |  |  |  |  | 0 | 5203.2975 | 5203.2975 | 5203.2975 | 5203.2975 | 5203.2975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5477 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16712.6335 | 0.2 | 0.3 | 26071.7082 |  |  |  |  | 0 | 5203.2628 | 5203.2628 | 5203.2628 | 5203.2628 | 5203.2628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5478 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 20597.2821 | 0.2 | 0.3 | 32131.76 |  |  |  |  | 0 | 7768.3183 | 7768.3183 | 7768.3183 | 7768.3183 | 7768.3183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5479 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16800.6862 | 0.2 | 0.3 | 26209.0705 |  |  |  |  | 0 | 7411.9558 | 7411.9558 | 7411.9558 | 7411.9558 | 7411.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5480 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 325.8069 | 0.2 | 0.3 | 508.2588 |  |  |  |  | 0 | 8377.0026 | 8377.0026 | 8377.0026 | 8377.0026 | 8377.0026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5481 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16917.7631 | 0.2 | 0.3 | 26391.7104 |  |  |  |  | 0 | 4468.9628 | 4468.9628 | 4468.9628 | 4468.9628 | 4468.9628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5482 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17485.7131 | 0.2 | 0.3 | 27277.7124 |  |  |  |  | 0 | 5203.8179 | 5203.8179 | 5203.8179 | 5203.8179 | 5203.8179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5483 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17202.9037 | 0.2 | 0.3 | 26836.5298 |  |  |  |  | 0 | 5852.6069 | 5852.6069 | 5852.6069 | 5852.6069 | 5852.6069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5484 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 31804.9558 | 0.2 | 0.3 | 49615.731 |  |  |  |  | 0 | 14.7223 | 14.7223 | 14.7223 | 14.7223 | 14.7223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5485 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17389.6941 | 0.2 | 0.3 | 27127.9227 |  |  |  |  | 0 | 5203.1278 | 5203.1278 | 5203.1278 | 5203.1278 | 5203.1278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5486 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 20338.2757 | 0.2 | 0.3 | 31727.7101 |  |  |  |  | 0 | 3038.2661 | 3038.2661 | 3038.2661 | 3038.2661 | 3038.2661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5487 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 2129.2636 | 0.2 | 0.3 | 3321.6512 |  |  |  |  | 0 | 5102.2657 | 5102.2657 | 5102.2657 | 5102.2657 | 5102.2657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5488 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 21120.4867 | 0.2 | 0.3 | 32947.9593 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5489 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16682.8936 | 0.2 | 0.3 | 26025.314 |  |  |  |  | 0 | 9789.5592 | 9789.5592 | 9789.5592 | 9789.5592 | 9789.5592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5490 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 30553.5869 | 0.2 | 0.3 | 47663.5955 |  |  |  |  | 0 | 5209.7515 | 5209.7515 | 5209.7515 | 5209.7515 | 5209.7515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5491 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17023.9135 | 0.2 | 0.3 | 26557.3051 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5492 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 1465.2225 | 0.2 | 0.3 | 2285.7472 |  |  |  |  | 0 | 5202.0112 | 5202.0112 | 5202.0112 | 5202.0112 | 5202.0112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5493 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 34503.1263 | 0.2 | 0.3 | 53824.8771 |  |  |  |  | 0 | 9779.1419 | 9779.1419 | 9779.1419 | 9779.1419 | 9779.1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5494 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 17653.8957 | 0.2 | 0.3 | 27540.0772 |  |  |  |  | 0 | 6255.2703 | 6255.2703 | 6255.2703 | 6255.2703 | 6255.2703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5495 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 5633.3087 | 0.2 | 0.3 | 8787.9616 |  |  |  |  | 0 | 2607.1714 | 2607.1714 | 2607.1714 | 2607.1714 | 2607.1714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5496 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 14251.5257 | 0.2 | 0.3 | 22232.3801 |  |  |  |  | 0 | 3596.9395 | 3596.9395 | 3596.9395 | 3596.9395 | 3596.9395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5497 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 11939.4759 | 0.2 | 0.3 | 18625.5825 |  |  |  |  | 0 | 5202.2276 | 5202.2276 | 5202.2276 | 5202.2276 | 5202.2276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5498 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 37219.5899 | 0.2 | 0.3 | 58062.5602 |  |  |  |  | 0 | 9780.6401 | 9780.6401 | 9780.6401 | 9780.6401 | 9780.6401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5499 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 5694.0174 | 0.2 | 0.3 | 8882.6671 |  |  |  |  | 0 | 5206.0581 | 5206.0581 | 5206.0581 | 5206.0581 | 5206.0581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5500 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 10983.7127 | 0.2 | 0.3 | 17134.5919 |  |  |  |  | 0 | 5214.6671 | 5214.6671 | 5214.6671 | 5214.6671 | 5214.6671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5501 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 27.1949 | 0.2 | 0.3 | 42.424 |  |  |  |  | 0 | 9797.6029 | 9797.6029 | 9797.6029 | 9797.6029 | 9797.6029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5502 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 915.7011 | 0.2 | 0.3 | 1428.4937 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5503 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16671.3691 | 0.2 | 0.3 | 26007.3358 |  |  |  |  | 0 | 8735.2799 | 8735.2799 | 8735.2799 | 8735.2799 | 8735.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5504 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 24202.2213 | 0.2 | 0.3 | 37755.4652 |  |  |  |  | 0 | 8758.9509 | 8758.9509 | 8758.9509 | 8758.9509 | 8758.9509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5505 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 4807.0296 | 0.2 | 0.3 | 7498.9662 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5506 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 4100.0201 | 0.2 | 0.3 | 6396.0313 |  |  |  |  | 0 | 9786.5526 | 9786.5526 | 9786.5526 | 9786.5526 | 9786.5526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5507 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 49903.0772 | 0.2 | 0.3 | 77848.8004 |  |  |  |  | 0 | 1737.633 | 1737.633 | 1737.633 | 1737.633 | 1737.633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5508 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 25881.5818 | 0.2 | 0.3 | 40375.2676 |  |  |  |  | 0 | 7771.4574 | 7771.4574 | 7771.4574 | 7771.4574 | 7771.4574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5509 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 23557.1109 | 0.2 | 0.3 | 36749.0931 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5510 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 14558.0639 | 0.2 | 0.3 | 22710.5797 |  |  |  |  | 0 | 9604.6224 | 9604.6224 | 9604.6224 | 9604.6224 | 9604.6224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5511 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 3068.2308 | 0.2 | 0.3 | 4786.44 |  |  |  |  | 0 | 5398.9923 | 5398.9923 | 5398.9923 | 5398.9923 | 5398.9923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5512 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 16738.4615 | 0.2 | 0.3 | 26111.9999 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5513 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 18171.1341 | 0.2 | 0.3 | 28346.9691 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5514 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 23174.9774 | 0.2 | 0.3 | 36152.9647 |  |  |  |  | 0 | 5201.7337 | 5201.7337 | 5201.7337 | 5201.7337 | 5201.7337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5515 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 35248.3456 | 0.2 | 0.3 | 54987.4191 |  |  |  |  | 0 | 8411.2827 | 8411.2827 | 8411.2827 | 8411.2827 | 8411.2827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5516 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 25013.1567 | 0.2 | 0.3 | 39020.5244 |  |  |  |  | 0 | 6563.1742 | 6563.1742 | 6563.1742 | 6563.1742 | 6563.1742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5517 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 12598.5463 | 0.2 | 0.3 | 19653.7323 |  |  |  |  | 0 | 2928.474 | 2928.474 | 2928.474 | 2928.474 | 2928.474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5518 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 30157.3292 | 0.2 | 0.3 | 47045.4336 |  |  |  |  | 0 | 2272.8542 | 2272.8542 | 2272.8542 | 2272.8542 | 2272.8542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5519 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 18018.9166 | 0.2 | 0.3 | 28109.5099 |  |  |  |  | 0 | 646.4626 | 646.4626 | 646.4626 | 646.4626 | 646.4626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5520 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 210.7596 | 0.2 | 0.3 | 328.785 |  |  |  |  | 0 | 2568.6251 | 2568.6251 | 2568.6251 | 2568.6251 | 2568.6251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5521 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 9348.2017 | 0.2 | 0.3 | 14583.1946 |  |  |  |  | 0 | 5976.2245 | 5976.2245 | 5976.2245 | 5976.2245 | 5976.2245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5522 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 16100.4435 | 0.2 | 0.3 | 25116.6918 |  |  |  |  | 0 | 7984.3597 | 7984.3597 | 7984.3597 | 7984.3597 | 7984.3597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5523 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 18532.0718 | 0.2 | 0.3 | 28910.032 |  |  |  |  | 0 | 5201.7625 | 5201.7625 | 5201.7625 | 5201.7625 | 5201.7625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5524 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 23184.1171 | 0.2 | 0.3 | 36167.2226 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5525 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 30373.5231 | 0.2 | 0.3 | 47382.696 |  |  |  |  | 0 | 5203.5347 | 5203.5347 | 5203.5347 | 5203.5347 | 5203.5347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5526 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 29145.3359 | 0.2 | 0.3 | 45466.7241 |  |  |  |  | 0 | 9803.9741 | 9803.9741 | 9803.9741 | 9803.9741 | 9803.9741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5527 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 31349.4584 | 0.2 | 0.3 | 48905.1551 |  |  |  |  | 0 | 5202.5924 | 5202.5924 | 5202.5924 | 5202.5924 | 5202.5924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5528 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 27520.1062 | 0.2 | 0.3 | 42931.3657 |  |  |  |  | 0 | 5202.0832 | 5202.0832 | 5202.0832 | 5202.0832 | 5202.0832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5529 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 34420.003 | 0.2 | 0.3 | 53695.2047 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5530 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 17943.6391 | 0.2 | 0.3 | 27992.077 |  |  |  |  | 0 | 7450.2677 | 7450.2677 | 7450.2677 | 7450.2677 | 7450.2677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5531 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 11757.8046 | 0.2 | 0.3 | 18342.1752 |  |  |  |  | 0 | 7551.9154 | 7551.9154 | 7551.9154 | 7551.9154 | 7551.9154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5532 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 34550.2952 | 0.2 | 0.3 | 53898.4605 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5533 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 23097.6015 | 0.2 | 0.3 | 36032.2583 |  |  |  |  | 0 | 4555.4828 | 4555.4828 | 4555.4828 | 4555.4828 | 4555.4828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5534 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 25987.88 | 0.2 | 0.3 | 40541.0928 |  |  |  |  | 0 | 341.3565 | 341.3565 | 341.3565 | 341.3565 | 341.3565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5535 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 29090.9958 | 0.2 | 0.3 | 45381.9534 |  |  |  |  | 0 | 1538.0484 | 1538.0484 | 1538.0484 | 1538.0484 | 1538.0484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5536 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 26312.4911 | 0.2 | 0.3 | 41047.4861 |  |  |  |  | 0 | 2965.5114 | 2965.5114 | 2965.5114 | 2965.5114 | 2965.5114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5537 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 12889.9215 | 0.2 | 0.3 | 20108.2775 |  |  |  |  | 0 | 4158.227 | 4158.227 | 4158.227 | 4158.227 | 4158.227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5538 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 21628.0321 | 0.2 | 0.3 | 33739.7301 |  |  |  |  | 0 | 2600.8426 | 2600.8426 | 2600.8426 | 2600.8426 | 2600.8426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5539 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 25969.9702 | 0.2 | 0.3 | 40513.1535 |  |  |  |  | 0 | 8363.1446 | 8363.1446 | 8363.1446 | 8363.1446 | 8363.1446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5540 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 19232.5328 | 0.2 | 0.3 | 30002.7512 |  |  |  |  | 0 | 5204.603 | 5204.603 | 5204.603 | 5204.603 | 5204.603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5541 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 16213.2945 | 0.2 | 0.3 | 25292.7394 |  |  |  |  | 0 | 5202.2621 | 5202.2621 | 5202.2621 | 5202.2621 | 5202.2621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5542 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 14489.9852 | 0.2 | 0.3 | 22604.3769 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5543 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 5162.7622 | 0.2 | 0.3 | 8053.909 |  |  |  |  | 0 | 5207.1647 | 5207.1647 | 5207.1647 | 5207.1647 | 5207.1647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5544 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 21577.6734 | 0.2 | 0.3 | 33661.1705 |  |  |  |  | 0 | 9789.3695 | 9789.3695 | 9789.3695 | 9789.3695 | 9789.3695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5545 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 29544.7597 | 0.2 | 0.3 | 46089.8252 |  |  |  |  | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5546 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 23170.0702 | 0.2 | 0.3 | 36145.3095 |  |  |  |  | 0 | 8247.7601 | 8247.7601 | 8247.7601 | 8247.7601 | 8247.7601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5547 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 1683.8783 | 0.2 | 0.3 | 2626.8502 |  |  |  |  | 0 | 8123.997 | 8123.997 | 8123.997 | 8123.997 | 8123.997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5548 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 27420.2938 | 0.2 | 0.3 | 42775.6583 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5549 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 12884.8787 | 0.2 | 0.3 | 20100.4108 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5550 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 8889.5016 | 0.2 | 0.3 | 13867.6225 |  |  |  |  | 0 | 5202.7979 | 5202.7979 | 5202.7979 | 5202.7979 | 5202.7979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5551 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 12438.1412 | 0.2 | 0.3 | 19403.5003 |  |  |  |  | 0 | 5204.8051 | 5204.8051 | 5204.8051 | 5204.8051 | 5204.8051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5552 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16896.7321 | 0.2 | 0.3 | 26358.9021 |  |  |  |  | 0 | 6070.031 | 6070.031 | 6070.031 | 6070.031 | 6070.031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5553 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 6348.2605 | 0.2 | 0.3 | 9903.2864 |  |  |  |  | 0 | 9544.1952 | 9544.1952 | 9544.1952 | 9544.1952 | 9544.1952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5554 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 11790.777 | 0.2 | 0.3 | 18393.6121 |  |  |  |  | 0 | 7386.7978 | 7386.7978 | 7386.7978 | 7386.7978 | 7386.7978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5555 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 15839.8231 | 0.2 | 0.3 | 24710.124 |  |  |  |  | 0 | 5009.3901 | 5009.3901 | 5009.3901 | 5009.3901 | 5009.3901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5556 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 30864.25 | 0.2 | 0.3 | 48148.23 |  |  |  |  | 0 | 4139.7569 | 4139.7569 | 4139.7569 | 4139.7569 | 4139.7569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5557 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16900.6208 | 0.2 | 0.3 | 26364.9684 |  |  |  |  | 0 | 5202.0365 | 5202.0365 | 5202.0365 | 5202.0365 | 5202.0365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5558 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 24226.2733 | 0.2 | 0.3 | 37792.9863 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5559 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 8039.6615 | 0.2 | 0.3 | 12541.8719 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5560 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 18595.0085 | 0.2 | 0.3 | 29008.2132 |  |  |  |  | 0 | 5205.004 | 5205.004 | 5205.004 | 5205.004 | 5205.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5561 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 6273.1802 | 0.2 | 0.3 | 9786.1611 |  |  |  |  | 0 | 9792.8593 | 9792.8593 | 9792.8593 | 9792.8593 | 9792.8593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5562 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 17608.057 | 0.2 | 0.3 | 27468.5689 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5563 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 14678.7646 | 0.2 | 0.3 | 22898.8728 |  |  |  |  | 0 | 7452.7288 | 7452.7288 | 7452.7288 | 7452.7288 | 7452.7288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5564 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 21221.2983 | 0.2 | 0.3 | 33105.2253 |  |  |  |  | 0 | 5620.9211 | 5620.9211 | 5620.9211 | 5620.9211 | 5620.9211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5565 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16678.9411 | 0.2 | 0.3 | 26019.1481 |  |  |  |  | 0 | 2600.8426 | 2600.8426 | 2600.8426 | 2600.8426 | 2600.8426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5566 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6623 |  |  |  |  | 0 | 6636.6132 | 6636.6132 | 6636.6132 | 6636.6132 | 6636.6132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5567 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 21593.8217 | 0.2 | 0.3 | 33686.3619 |  |  |  |  | 0 | 5204.5818 | 5204.5818 | 5204.5818 | 5204.5818 | 5204.5818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5568 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16669.932 | 0.2 | 0.3 | 26005.0939 |  |  |  |  | 0 | 4356.1456 | 4356.1456 | 4356.1456 | 4356.1456 | 4356.1456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5569 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 22785.0376 | 0.2 | 0.3 | 35544.6587 |  |  |  |  | 0 | 5207.4987 | 5207.4987 | 5207.4987 | 5207.4987 | 5207.4987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5570 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16870.2909 | 0.2 | 0.3 | 26317.6538 |  |  |  |  | 0 | 6364.3579 | 6364.3579 | 6364.3579 | 6364.3579 | 6364.3579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5571 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 22856.3365 | 0.2 | 0.3 | 35655.8849 |  |  |  |  | 0 | 5258.2322 | 5258.2322 | 5258.2322 | 5258.2322 | 5258.2322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5572 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 9064.3027 | 0.2 | 0.3 | 14140.3122 |  |  |  |  | 0 | 7913.6538 | 7913.6538 | 7913.6538 | 7913.6538 | 7913.6538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5573 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 55588.2951 | 0.2 | 0.3 | 86717.7403 |  |  |  |  | 0 | 5229.1281 | 5229.1281 | 5229.1281 | 5229.1281 | 5229.1281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5574 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 32812.0057 | 0.2 | 0.3 | 51186.7289 |  |  |  |  | 0 | 4292.8569 | 4292.8569 | 4292.8569 | 4292.8569 | 4292.8569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5575 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 22482.546 | 0.2 | 0.3 | 35072.7718 |  |  |  |  | 0 | 5204.18 | 5204.18 | 5204.18 | 5204.18 | 5204.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5576 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 34339.2087 | 0.2 | 0.3 | 53569.1655 |  |  |  |  | 0 | 5207.4857 | 5207.4857 | 5207.4857 | 5207.4857 | 5207.4857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5577 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 31907.2603 | 0.2 | 0.3 | 49775.3261 |  |  |  |  | 0 | 5204.2985 | 5204.2985 | 5204.2985 | 5204.2985 | 5204.2985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5578 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 28100.3643 | 0.2 | 0.3 | 43836.5684 |  |  |  |  | 0 | 0.023837 | 0.023837 | 0.023837 | 0.023837 | 0.023837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5579 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 23376.3004 | 0.2 | 0.3 | 36467.0286 |  |  |  |  | 0 | 5628.5483 | 5628.5483 | 5628.5483 | 5628.5483 | 5628.5483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5580 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 8115.7941 | 0.2 | 0.3 | 12660.6387 |  |  |  |  | 0 | 5206.8412 | 5206.8412 | 5206.8412 | 5206.8412 | 5206.8412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5581 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 2601.1351 | 2601.1351 | 2601.1351 | 2601.1351 | 2601.1351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5582 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 18295.6456 | 0.2 | 0.3 | 28541.2071 |  |  |  |  | 0 | 4316.5728 | 4316.5728 | 4316.5728 | 4316.5728 | 4316.5728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5583 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 30906.3825 | 0.2 | 0.3 | 48213.9568 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5584 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 10628.039 | 0.2 | 0.3 | 16579.7408 |  |  |  |  | 0 | 5204.5046 | 5204.5046 | 5204.5046 | 5204.5046 | 5204.5046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5585 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 16667.6067 | 0.2 | 0.3 | 26001.4664 |  |  |  |  | 0 | 9793.3468 | 9793.3468 | 9793.3468 | 9793.3468 | 9793.3468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5586 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 23651.8175 | 0.2 | 0.3 | 36896.8354 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5587 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 19242.8015 | 0.2 | 0.3 | 30018.7704 |  |  |  |  | 0 | 5204.8229 | 5204.8229 | 5204.8229 | 5204.8229 | 5204.8229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5588 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 16500.9158 | 0.2 | 0.3 | 25741.4286 |  |  |  |  | 0 | 9791.6365 | 9791.6365 | 9791.6365 | 9791.6365 | 9791.6365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5589 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16727.5751 | 0.2 | 0.3 | 26095.0171 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5590 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 17614.6144 | 0.2 | 0.3 | 27478.7985 |  |  |  |  | 0 | 9790.0069 | 9790.0069 | 9790.0069 | 9790.0069 | 9790.0069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5591 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 8236.9965 | 0.2 | 0.3 | 12849.7146 |  |  |  |  | 0 | 5206.1178 | 5206.1178 | 5206.1178 | 5206.1178 | 5206.1178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5592 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 8430.0938 | 0.2 | 0.3 | 13150.9463 |  |  |  |  | 0 | 5201.3633 | 5201.3633 | 5201.3633 | 5201.3633 | 5201.3633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5593 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 5202.1352 | 5202.1352 | 5202.1352 | 5202.1352 | 5202.1352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5594 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8751 | 0.2 | 0.3 | 26000.3251 |  |  |  |  | 0 | 5203.3837 | 5203.3837 | 5203.3837 | 5203.3837 | 5203.3837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5595 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8221 | 0.2 | 0.3 | 26000.2424 |  |  |  |  | 0 | 9798.7017 | 9798.7017 | 9798.7017 | 9798.7017 | 9798.7017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5596 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16336.8295 | 0.2 | 0.3 | 25485.4541 |  |  |  |  | 0 | 5202.2881 | 5202.2881 | 5202.2881 | 5202.2881 | 5202.2881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5597 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 31193.4387 | 0.2 | 0.3 | 48661.7643 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5598 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 25122.7823 | 0.2 | 0.3 | 39191.5404 |  |  |  |  | 0 | 5202.1203 | 5202.1203 | 5202.1203 | 5202.1203 | 5202.1203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5599 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 26810.7665 | 0.2 | 0.3 | 41824.7958 |  |  |  |  | 0 | 7704.0057 | 7704.0057 | 7704.0057 | 7704.0057 | 7704.0057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5600 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 22279.0943 | 0.2 | 0.3 | 34755.3872 |  |  |  |  | 0 | 5995.7919 | 5995.7919 | 5995.7919 | 5995.7919 | 5995.7919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5601 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 8876.649 | 0.2 | 0.3 | 13847.5724 |  |  |  |  | 0 | 5203.4069 | 5203.4069 | 5203.4069 | 5203.4069 | 5203.4069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5602 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 18142.9531 | 0.2 | 0.3 | 28303.0068 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5603 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 19564.8141 | 0.2 | 0.3 | 30521.1099 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5604 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 13123.1523 | 0.2 | 0.3 | 20472.1175 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5605 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16699.3581 | 0.2 | 0.3 | 26050.9986 |  |  |  |  | 0 | 5203.4987 | 5203.4987 | 5203.4987 | 5203.4987 | 5203.4987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5606 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16786.2495 | 0.2 | 0.3 | 26186.5493 |  |  |  |  | 0 | 9783.1745 | 9783.1745 | 9783.1745 | 9783.1745 | 9783.1745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5607 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16678.7596 | 0.2 | 0.3 | 26018.865 |  |  |  |  | 0 | 6074.4401 | 6074.4401 | 6074.4401 | 6074.4401 | 6074.4401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5608 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 25908.8331 | 0.2 | 0.3 | 40417.7796 |  |  |  |  | 0 | 5310.0946 | 5310.0946 | 5310.0946 | 5310.0946 | 5310.0946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5609 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16803.3411 | 0.2 | 0.3 | 26213.2122 |  |  |  |  | 0 | 5244.0924 | 5244.0924 | 5244.0924 | 5244.0924 | 5244.0924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5610 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16710.8265 | 0.2 | 0.3 | 26068.8894 |  |  |  |  | 0 | 3331.275 | 3331.275 | 3331.275 | 3331.275 | 3331.275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5611 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16668.795 | 0.2 | 0.3 | 26003.3202 |  |  |  |  | 0 | 9171.548 | 9171.548 | 9171.548 | 9171.548 | 9171.548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5612 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 22019.025 | 0.2 | 0.3 | 34349.679 |  |  |  |  | 0 | 7783.8096 | 7783.8096 | 7783.8096 | 7783.8096 | 7783.8096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5613 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16533.9935 | 0.2 | 0.3 | 25793.0298 |  |  |  |  | 0 | 7143.9883 | 7143.9883 | 7143.9883 | 7143.9883 | 7143.9883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5614 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 22294.5961 | 0.2 | 0.3 | 34779.57 |  |  |  |  | 0 | 2601.0632 | 2601.0632 | 2601.0632 | 2601.0632 | 2601.0632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5615 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 22239.3344 | 0.2 | 0.3 | 34693.3617 |  |  |  |  | 0 | 885.6826 | 885.6826 | 885.6826 | 885.6826 | 885.6826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5616 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 3987.6596 | 0.2 | 0.3 | 6220.749 |  |  |  |  | 0 | 5204.4819 | 5204.4819 | 5204.4819 | 5204.4819 | 5204.4819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5617 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 12761.791 | 0.2 | 0.3 | 19908.394 |  |  |  |  | 0 | 5203.9799 | 5203.9799 | 5203.9799 | 5203.9799 | 5203.9799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5618 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16676.7132 | 0.2 | 0.3 | 26015.6726 |  |  |  |  | 0 | 5201.5221 | 5201.5221 | 5201.5221 | 5201.5221 | 5201.5221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5619 | PEMBROKE PINES | 110334 | Private | 2030 | 5 | Swales | 66.6667 | 11609.7355 | 0.2 | 0.3 | 18111.1874 |  |  |  |  | 0 | 2601.139 | 2601.139 | 2601.139 | 2601.139 | 2601.139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5620 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 16826.6695 | 0.2 | 0.3 | 26249.6045 |  |  |  |  | 0 | 3589.1476 | 3589.1476 | 3589.1476 | 3589.1476 | 3589.1476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5621 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 1814.2161 | 0.2 | 0.3 | 2830.1772 |  |  |  |  | 0 | 9794.5134 | 9794.5134 | 9794.5134 | 9794.5134 | 9794.5134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5622 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 16673.3105 | 0.2 | 0.3 | 26010.3644 |  |  |  |  | 0 | 5202.7972 | 5202.7972 | 5202.7972 | 5202.7972 | 5202.7972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5623 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 6325.6681 | 0.2 | 0.3 | 9868.0423 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5624 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 19845.3553 | 0.2 | 0.3 | 30958.7543 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5625 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 621.5433 | 0.2 | 0.3 | 969.6075 |  |  |  |  | 0 | 8638.748 | 8638.748 | 8638.748 | 8638.748 | 8638.748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5626 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 20621.3365 | 0.2 | 0.3 | 32169.285 |  |  |  |  | 0 | 2701.4276 | 2701.4276 | 2701.4276 | 2701.4276 | 2701.4276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5627 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 31495.815 | 0.2 | 0.3 | 49133.4714 |  |  |  |  | 0 | 5561.5149 | 5561.5149 | 5561.5149 | 5561.5149 | 5561.5149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5628 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 33436.6689 | 0.2 | 0.3 | 52161.2035 |  |  |  |  | 0 | 5203.4367 | 5203.4367 | 5203.4367 | 5203.4367 | 5203.4367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5629 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 37381.4621 | 0.2 | 0.3 | 58315.0808 |  |  |  |  | 0 | 3204.5719 | 3204.5719 | 3204.5719 | 3204.5719 | 3204.5719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5630 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 34559.6306 | 0.2 | 0.3 | 53913.0237 |  |  |  |  | 0 | 5195.4284 | 5195.4284 | 5195.4284 | 5195.4284 | 5195.4284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5631 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 38486.5893 | 0.2 | 0.3 | 60039.0794 |  |  |  |  | 0 | 5204.7034 | 5204.7034 | 5204.7034 | 5204.7034 | 5204.7034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5632 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 33333.3819 | 0.2 | 0.3 | 52000.0757 |  |  |  |  | 0 | 5212.3354 | 5212.3354 | 5212.3354 | 5212.3354 | 5212.3354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5633 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 33384.3475 | 0.2 | 0.3 | 52079.582 |  |  |  |  | 0 | 4172.9205 | 4172.9205 | 4172.9205 | 4172.9205 | 4172.9205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5634 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 8876.8482 | 0.2 | 0.3 | 13847.8832 |  |  |  |  | 0 | 2444.6833 | 2444.6833 | 2444.6833 | 2444.6833 | 2444.6833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5635 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 16718.6859 | 0.2 | 0.3 | 26081.15 |  |  |  |  | 0 | 8494.8895 | 8494.8895 | 8494.8895 | 8494.8895 | 8494.8895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5636 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 12226.1093 | 0.2 | 0.3 | 19072.7306 |  |  |  |  | 0 | 9872.2492 | 9872.2492 | 9872.2492 | 9872.2492 | 9872.2492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5637 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 14552.0736 | 0.2 | 0.3 | 22701.2348 |  |  |  |  | 0 | 8449.0871 | 8449.0871 | 8449.0871 | 8449.0871 | 8449.0871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5638 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 21222.3333 | 0.2 | 0.3 | 33106.84 |  |  |  |  | 0 | 6180.1207 | 6180.1207 | 6180.1207 | 6180.1207 | 6180.1207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5639 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 42481.3413 | 0.2 | 0.3 | 66270.8924 |  |  |  |  | 0 | 5202.2146 | 5202.2146 | 5202.2146 | 5202.2146 | 5202.2146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5640 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 32235.6952 | 0.2 | 0.3 | 50287.6845 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5641 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 2004.3394 | 0.2 | 0.3 | 3126.7695 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5642 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 1386.2849 | 0.2 | 0.3 | 2162.6045 |  |  |  |  | 0 | 5204.3541 | 5204.3541 | 5204.3541 | 5204.3541 | 5204.3541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5643 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 17073.0573 | 0.2 | 0.3 | 26633.9693 |  |  |  |  | 0 | 9794.3956 | 9794.3956 | 9794.3956 | 9794.3956 | 9794.3956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5644 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 24075.6691 | 0.2 | 0.3 | 37558.0437 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5645 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 39842.9087 | 0.2 | 0.3 | 62154.9376 |  |  |  |  | 0 | 5204.1561 | 5204.1561 | 5204.1561 | 5204.1561 | 5204.1561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5646 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 9946.1561 | 0.2 | 0.3 | 15516.0035 |  |  |  |  | 0 | 9785.1903 | 9785.1903 | 9785.1903 | 9785.1903 | 9785.1903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5647 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 16658.9447 | 0.2 | 0.3 | 25987.9538 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5648 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 16672.3415 | 0.2 | 0.3 | 26008.8527 |  |  |  |  | 0 | 9790.2659 | 9790.2659 | 9790.2659 | 9790.2659 | 9790.2659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5649 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 16252.5727 | 0.2 | 0.3 | 25354.0134 |  |  |  |  | 0 | 5206.8684 | 5206.8684 | 5206.8684 | 5206.8684 | 5206.8684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5650 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 24057.9885 | 0.2 | 0.3 | 37530.462 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5651 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 17510.0249 | 0.2 | 0.3 | 27315.6388 |  |  |  |  | 0 | 2600.8912 | 2600.8912 | 2600.8912 | 2600.8912 | 2600.8912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5652 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 20515.9216 | 0.2 | 0.3 | 32004.8377 |  |  |  |  | 0 | 1615.5476 | 1615.5476 | 1615.5476 | 1615.5476 | 1615.5476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5653 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 27860.3074 | 0.2 | 0.3 | 43462.0795 |  |  |  |  | 0 | 5201.7853 | 5201.7853 | 5201.7853 | 5201.7853 | 5201.7853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5654 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 28383.3277 | 0.2 | 0.3 | 44277.9913 |  |  |  |  | 0 | 6189.9494 | 6189.9494 | 6189.9494 | 6189.9494 | 6189.9494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5655 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 12474.8687 | 0.2 | 0.3 | 19460.7951 |  |  |  |  | 0 | 7920.1413 | 7920.1413 | 7920.1413 | 7920.1413 | 7920.1413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5656 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 16667.5259 | 0.2 | 0.3 | 26001.3405 |  |  |  |  | 0 | 5206.9361 | 5206.9361 | 5206.9361 | 5206.9361 | 5206.9361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5657 | PEMBROKE PINES | 110341 | Public | 2036 | 5 | Swales | 66.6667 | 37844.5773 | 0.2 | 0.3 | 59037.5405 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5658 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 26558.3768 | 0.2 | 0.3 | 41431.0678 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5659 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 29579.5181 | 0.2 | 0.3 | 46144.0483 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5660 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 29504.4489 | 0.2 | 0.3 | 46026.9403 |  |  |  |  | 0 | 5203.2326 | 5203.2326 | 5203.2326 | 5203.2326 | 5203.2326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5661 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 19705.3591 | 0.2 | 0.3 | 30740.3601 |  |  |  |  | 0 | 9783.1335 | 9783.1335 | 9783.1335 | 9783.1335 | 9783.1335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5662 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1473 | 0.2 | 0.3 | 26000.7497 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5663 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 5203.4576 | 5203.4576 | 5203.4576 | 5203.4576 | 5203.4576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5664 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 6653.2433 | 0.2 | 0.3 | 10379.0595 |  |  |  |  | 0 | 5135.381 | 5135.381 | 5135.381 | 5135.381 | 5135.381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5665 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 10014.1769 | 0.2 | 0.3 | 15622.116 |  |  |  |  | 0 | 2940.7288 | 2940.7288 | 2940.7288 | 2940.7288 | 2940.7288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5666 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0824 | 0.2 | 0.3 | 26000.6485 |  |  |  |  | 0 | 1998.7192 | 1998.7192 | 1998.7192 | 1998.7192 | 1998.7192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5667 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1478 | 0.2 | 0.3 | 26000.7506 |  |  |  |  | 0 | 7.9645 | 7.9645 | 7.9645 | 7.9645 | 7.9645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5668 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6523 | 0.2 | 0.3 | 25999.9775 |  |  |  |  | 0 | 6958.3688 | 6958.3688 | 6958.3688 | 6958.3688 | 6958.3688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5669 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 6996.0248 | 6996.0248 | 6996.0248 | 6996.0248 | 6996.0248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5670 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 6276.4123 | 6276.4123 | 6276.4123 | 6276.4123 | 6276.4123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5671 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 5243.6232 | 5243.6232 | 5243.6232 | 5243.6232 | 5243.6232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5672 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 5201.0057 | 5201.0057 | 5201.0057 | 5201.0057 | 5201.0057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5673 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 4032.7717 | 4032.7717 | 4032.7717 | 4032.7717 | 4032.7717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5674 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 19588.1321 | 0.2 | 0.3 | 30557.486 |  |  |  |  | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5675 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 6938.3 | 0.2 | 0.3 | 10823.748 |  |  |  |  | 0 | 9787.9325 | 9787.9325 | 9787.9325 | 9787.9325 | 9787.9325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5676 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 8608.2745 | 0.2 | 0.3 | 13428.9083 |  |  |  |  | 0 | 5200.1216 | 5200.1216 | 5200.1216 | 5200.1216 | 5200.1216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5677 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 17692.2651 | 0.2 | 0.3 | 27599.9336 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5678 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 24508.0407 | 0.2 | 0.3 | 38232.5434 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5679 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16732.9992 | 0.2 | 0.3 | 26103.4788 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5680 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16764.0341 | 0.2 | 0.3 | 26151.8931 |  |  |  |  | 0 | 5207.2528 | 5207.2528 | 5207.2528 | 5207.2528 | 5207.2528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5681 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16670.7454 | 0.2 | 0.3 | 26006.3628 |  |  |  |  | 0 | 9795.7357 | 9795.7357 | 9795.7357 | 9795.7357 | 9795.7357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5682 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16671.1799 | 0.2 | 0.3 | 26007.0407 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5683 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 19442.3513 | 0.2 | 0.3 | 30330.068 |  |  |  |  | 0 | 5204.5461 | 5204.5461 | 5204.5461 | 5204.5461 | 5204.5461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5684 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16687.3163 | 0.2 | 0.3 | 26032.2135 |  |  |  |  | 0 | 9785.6019 | 9785.6019 | 9785.6019 | 9785.6019 | 9785.6019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5685 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8427 | 0.2 | 0.3 | 26000.2747 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5686 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 22661.3156 | 0.2 | 0.3 | 35351.6523 |  |  |  |  | 0 | 9788.1378 | 9788.1378 | 9788.1378 | 9788.1378 | 9788.1378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5687 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 23845.1486 | 0.2 | 0.3 | 37198.4318 |  |  |  |  | 0 | 5207.5168 | 5207.5168 | 5207.5168 | 5207.5168 | 5207.5168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5688 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 30813.9935 | 0.2 | 0.3 | 48069.8298 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5689 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 17278.7651 | 0.2 | 0.3 | 26954.8736 |  |  |  |  | 0 | 5202.5214 | 5202.5214 | 5202.5214 | 5202.5214 | 5202.5214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5690 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 12082.6023 | 0.2 | 0.3 | 18848.8595 |  |  |  |  | 0 | 5203.38 | 5203.38 | 5203.38 | 5203.38 | 5203.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5691 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 22748.6195 | 0.2 | 0.3 | 35487.8465 |  |  |  |  | 0 | 9796.1416 | 9796.1416 | 9796.1416 | 9796.1416 | 9796.1416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5692 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16684.1165 | 0.2 | 0.3 | 26027.2218 |  |  |  |  | 0 | 5201.5793 | 5201.5793 | 5201.5793 | 5201.5793 | 5201.5793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5693 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16705.9738 | 0.2 | 0.3 | 26061.3191 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5694 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 5659.9522 | 0.2 | 0.3 | 8829.5254 |  |  |  |  | 0 | 8860.8676 | 8860.8676 | 8860.8676 | 8860.8676 | 8860.8676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5695 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 12960.0631 | 0.2 | 0.3 | 20217.6984 |  |  |  |  | 0 | 5204.2042 | 5204.2042 | 5204.2042 | 5204.2042 | 5204.2042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5696 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16728.8709 | 0.2 | 0.3 | 26097.0386 |  |  |  |  | 0 | 5958.8313 | 5958.8313 | 5958.8313 | 5958.8313 | 5958.8313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5697 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 19510.2871 | 0.2 | 0.3 | 30436.0478 |  |  |  |  | 0 | 5549.6892 | 5549.6892 | 5549.6892 | 5549.6892 | 5549.6892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5698 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 659.765 | 659.765 | 659.765 | 659.765 | 659.765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5699 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 26.9413 | 0.2 | 0.3 | 42.0284 |  |  |  |  | 0 | 2598.9411 | 2598.9411 | 2598.9411 | 2598.9411 | 2598.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5700 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 17020.654 | 0.2 | 0.3 | 26552.2202 |  |  |  |  | 0 | 8621.6411 | 8621.6411 | 8621.6411 | 8621.6411 | 8621.6411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5701 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 16672.8883 | 0.2 | 0.3 | 26009.7057 |  |  |  |  | 0 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5702 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 680.4799 | 0.2 | 0.3 | 1061.5487 |  |  |  |  | 0 | 5205.6863 | 5205.6863 | 5205.6863 | 5205.6863 | 5205.6863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5703 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 17081.4181 | 0.2 | 0.3 | 26647.0123 |  |  |  |  | 0 | 5203.2767 | 5203.2767 | 5203.2767 | 5203.2767 | 5203.2767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5704 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 28279.1332 | 0.2 | 0.3 | 44115.4478 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5705 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 44697.443 | 0.2 | 0.3 | 69728.0111 |  |  |  |  | 0 | 5202.9163 | 5202.9163 | 5202.9163 | 5202.9163 | 5202.9163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5706 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 33340.615 | 0.2 | 0.3 | 52011.3594 |  |  |  |  | 0 | 5202.8298 | 5202.8298 | 5202.8298 | 5202.8298 | 5202.8298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5707 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16751.1143 | 0.2 | 0.3 | 26131.7383 |  |  |  |  | 0 | 10617.9935 | 10617.9935 | 10617.9935 | 10617.9935 | 10617.9935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5708 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 18563.7651 | 0.2 | 0.3 | 28959.4736 |  |  |  |  | 0 | 11949.5338 | 11949.5338 | 11949.5338 | 11949.5338 | 11949.5338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5709 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 21686.9112 | 0.2 | 0.3 | 33831.5815 |  |  |  |  | 0 | 5200.5644 | 5200.5644 | 5200.5644 | 5200.5644 | 5200.5644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5710 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 27458.8757 | 0.2 | 0.3 | 42835.8461 |  |  |  |  | 0 | 7995.0431 | 7995.0431 | 7995.0431 | 7995.0431 | 7995.0431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5711 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 13419.5115 | 0.2 | 0.3 | 20934.4379 |  |  |  |  | 0 | 6434.4447 | 6434.4447 | 6434.4447 | 6434.4447 | 6434.4447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5712 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 8769.3598 | 0.2 | 0.3 | 13680.2013 |  |  |  |  | 0 | 7656.959 | 7656.959 | 7656.959 | 7656.959 | 7656.959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5713 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 12607.2932 | 0.2 | 0.3 | 19667.3774 |  |  |  |  | 0 | 7730.6679 | 7730.6679 | 7730.6679 | 7730.6679 | 7730.6679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5714 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 18360.9141 | 0.2 | 0.3 | 28643.0259 |  |  |  |  | 0 | 81.2075 | 81.2075 | 81.2075 | 81.2075 | 81.2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5715 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 32469.9035 | 0.2 | 0.3 | 50653.0494 |  |  |  |  | 0 | 7127.0185 | 7127.0185 | 7127.0185 | 7127.0185 | 7127.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5716 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 36462.6611 | 0.2 | 0.3 | 56881.7514 |  |  |  |  | 0 | 2652.6148 | 2652.6148 | 2652.6148 | 2652.6148 | 2652.6148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5717 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 33840.8592 | 0.2 | 0.3 | 52791.7404 |  |  |  |  | 0 | 4711.5893 | 4711.5893 | 4711.5893 | 4711.5893 | 4711.5893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5718 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 16677.8095 | 0.2 | 0.3 | 26017.3828 |  |  |  |  | 0 | 9779.9973 | 9779.9973 | 9779.9973 | 9779.9973 | 9779.9973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5719 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 28991.4611 | 0.2 | 0.3 | 45226.6793 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5720 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 24160.6863 | 0.2 | 0.3 | 37690.6706 |  |  |  |  | 0 | 9779.8572 | 9779.8572 | 9779.8572 | 9779.8572 | 9779.8572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5721 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 31542.2235 | 0.2 | 0.3 | 49205.8687 |  |  |  |  | 0 | 5201.7239 | 5201.7239 | 5201.7239 | 5201.7239 | 5201.7239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5722 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 33810.1425 | 0.2 | 0.3 | 52743.8222 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5723 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 21134.2585 | 0.2 | 0.3 | 32969.4433 |  |  |  |  | 0 | 5201.9353 | 5201.9353 | 5201.9353 | 5201.9353 | 5201.9353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5724 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 24707.3503 | 0.2 | 0.3 | 38543.4665 |  |  |  |  | 0 | 5202.049 | 5202.049 | 5202.049 | 5202.049 | 5202.049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5725 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 23416.9099 | 0.2 | 0.3 | 36530.3795 |  |  |  |  | 0 | 9779.9198 | 9779.9198 | 9779.9198 | 9779.9198 | 9779.9198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5726 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 17852.5949 | 0.2 | 0.3 | 27850.0481 |  |  |  |  | 0 | 5201.909 | 5201.909 | 5201.909 | 5201.909 | 5201.909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5727 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 11973.2734 | 0.2 | 0.3 | 18678.3065 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5728 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 13277.1467 | 0.2 | 0.3 | 20712.3489 |  |  |  |  | 0 | 9780.9182 | 9780.9182 | 9780.9182 | 9780.9182 | 9780.9182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5729 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 17114.3111 | 0.2 | 0.3 | 26698.3254 |  |  |  |  | 0 | 5202.6486 | 5202.6486 | 5202.6486 | 5202.6486 | 5202.6486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5730 | PEMBROKE PINES | 110350 | Private | 2036 | 5 | Swales | 66.6667 | 13138.4709 | 0.2 | 0.3 | 20496.0146 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5731 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 18221.6755 | 0.2 | 0.3 | 28425.8137 |  |  |  |  | 0 | 7617.6676 | 7617.6676 | 7617.6676 | 7617.6676 | 7617.6676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5732 | PEMBROKE PINES | 110350 | Public | 2036 | 5 | Swales | 66.6667 | 19368.4839 | 0.2 | 0.3 | 30214.8348 |  |  |  |  | 0 | 7792.0922 | 7792.0922 | 7792.0922 | 7792.0922 | 7792.0922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5733 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16693.5654 | 0.2 | 0.3 | 26041.962 |  |  |  |  | 0 | 5207.2957 | 5207.2957 | 5207.2957 | 5207.2957 | 5207.2957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5734 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16671.7366 | 0.2 | 0.3 | 26007.9091 |  |  |  |  | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5735 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16672.9923 | 0.2 | 0.3 | 26009.8679 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5736 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16677.7297 | 0.2 | 0.3 | 26017.2584 |  |  |  |  | 0 | 4543.3237 | 4543.3237 | 4543.3237 | 4543.3237 | 4543.3237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5737 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 7219.1945 | 0.2 | 0.3 | 11261.9435 |  |  |  |  | 0 | 2604.234 | 2604.234 | 2604.234 | 2604.234 | 2604.234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5738 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 23176.4419 | 0.2 | 0.3 | 36155.2493 |  |  |  |  | 0 | 6364.6979 | 6364.6979 | 6364.6979 | 6364.6979 | 6364.6979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5739 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 18801.5202 | 0.2 | 0.3 | 29330.3715 |  |  |  |  | 0 | 12161.274 | 12161.274 | 12161.274 | 12161.274 | 12161.274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5740 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 4103.0839 | 0.2 | 0.3 | 6400.8109 |  |  |  |  | 0 | 11626.1196 | 11626.1196 | 11626.1196 | 11626.1196 | 11626.1196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5741 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 20868.6882 | 0.2 | 0.3 | 32555.1536 |  |  |  |  | 0 | 5711.2256 | 5711.2256 | 5711.2256 | 5711.2256 | 5711.2256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5742 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 22652.3115 | 0.2 | 0.3 | 35337.606 |  |  |  |  | 0 | 20.8123 | 20.8123 | 20.8123 | 20.8123 | 20.8123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5743 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 8408.4571 | 0.2 | 0.3 | 13117.193 |  |  |  |  | 0 | 9170.1427 | 9170.1427 | 9170.1427 | 9170.1427 | 9170.1427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5744 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 14390.3509 | 0.2 | 0.3 | 22448.9474 |  |  |  |  | 0 | 3715.9864 | 3715.9864 | 3715.9864 | 3715.9864 | 3715.9864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5745 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 24138.927 | 0.2 | 0.3 | 37656.7261 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5746 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 15927.2033 | 0.2 | 0.3 | 24846.4372 |  |  |  |  | 0 | 5393.1786 | 5393.1786 | 5393.1786 | 5393.1786 | 5393.1786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5747 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16081.5582 | 0.2 | 0.3 | 25087.2308 |  |  |  |  | 0 | 5201.1895 | 5201.1895 | 5201.1895 | 5201.1895 | 5201.1895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5748 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 19004.7819 | 0.2 | 0.3 | 29647.4598 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5749 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 13317.4132 | 0.2 | 0.3 | 20775.1646 |  |  |  |  | 0 | 5201.6696 | 5201.6696 | 5201.6696 | 5201.6696 | 5201.6696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5750 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 9729.4663 | 0.2 | 0.3 | 15177.9675 |  |  |  |  | 0 | 9661.8505 | 9661.8505 | 9661.8505 | 9661.8505 | 9661.8505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5751 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 8155.9092 | 0.2 | 0.3 | 12723.2184 |  |  |  |  | 0 | 5120.515 | 5120.515 | 5120.515 | 5120.515 | 5120.515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5752 | PEMBROKE PINES | 110326 | Private | 2036 | 5 | Swales | 66.6667 | 1.9308 | 0.2 | 0.3 | 3.012 |  |  |  |  | 0 | 7855.7026 | 7855.7026 | 7855.7026 | 7855.7026 | 7855.7026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5753 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 21150.3587 | 0.2 | 0.3 | 32994.5596 |  |  |  |  | 0 | 2549.74 | 2549.74 | 2549.74 | 2549.74 | 2549.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5754 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16750.6591 | 0.2 | 0.3 | 26131.0281 |  |  |  |  | 0 | 490.9263 | 490.9263 | 490.9263 | 490.9263 | 490.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5755 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16747.2185 | 0.2 | 0.3 | 26125.6608 |  |  |  |  | 0 | 5201.5951 | 5201.5951 | 5201.5951 | 5201.5951 | 5201.5951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5756 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16680.3268 | 0.2 | 0.3 | 26021.3098 |  |  |  |  | 0 | 5201.9271 | 5201.9271 | 5201.9271 | 5201.9271 | 5201.9271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5757 | PEMBROKE PINES | 110330 | Public | 2036 | 5 | Swales | 66.6667 | 16669.7543 | 0.2 | 0.3 | 26004.8167 |  |  |  |  | 0 | 5201.7323 | 5201.7323 | 5201.7323 | 5201.7323 | 5201.7323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5758 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 27366.3438 | 0.2 | 0.3 | 42691.4963 |  |  |  |  | 0 | 772.28 | 772.28 | 772.28 | 772.28 | 772.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5759 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16688.6806 | 0.2 | 0.3 | 26034.3417 |  |  |  |  | 0 | 7440.7984 | 7440.7984 | 7440.7984 | 7440.7984 | 7440.7984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5760 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0445 | 0.2 | 0.3 | 26000.5894 |  |  |  |  | 0 | 3700.9855 | 3700.9855 | 3700.9855 | 3700.9855 | 3700.9855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5761 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 21592.6523 | 0.2 | 0.3 | 33684.5375 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5762 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 29008.6947 | 0.2 | 0.3 | 45253.5637 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5763 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 30841.8275 | 0.2 | 0.3 | 48113.251 |  |  |  |  | 0 | 7416.2065 | 7416.2065 | 7416.2065 | 7416.2065 | 7416.2065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5764 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 15971.4929 | 0.2 | 0.3 | 24915.5289 |  |  |  |  | 0 | 9499.2312 | 9499.2312 | 9499.2312 | 9499.2312 | 9499.2312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5765 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 11479.9186 | 0.2 | 0.3 | 17908.673 |  |  |  |  | 0 | 6988.0633 | 6988.0633 | 6988.0633 | 6988.0633 | 6988.0633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5766 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 19532.901 | 0.2 | 0.3 | 30471.3256 |  |  |  |  | 0 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5767 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16881.1109 | 0.2 | 0.3 | 26334.5331 |  |  |  |  | 0 | 8015.9104 | 8015.9104 | 8015.9104 | 8015.9104 | 8015.9104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5768 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0819 | 0.2 | 0.3 | 26000.6477 |  |  |  |  | 0 | 6014.8283 | 6014.8283 | 6014.8283 | 6014.8283 | 6014.8283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5769 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 19957.05 | 0.2 | 0.3 | 31132.998 |  |  |  |  | 0 | 8277.0839 | 8277.0839 | 8277.0839 | 8277.0839 | 8277.0839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5770 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 20213.5942 | 0.2 | 0.3 | 31533.207 |  |  |  |  | 0 | 3110.3192 | 3110.3192 | 3110.3192 | 3110.3192 | 3110.3192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5771 | PEMBROKE PINES | 110332 | Private | 2036 | 5 | Swales | 66.6667 | 15402.7709 | 0.2 | 0.3 | 24028.3226 |  |  |  |  | 0 | 2119.3581 | 2119.3581 | 2119.3581 | 2119.3581 | 2119.3581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5772 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 24184.8237 | 0.2 | 0.3 | 37728.3249 |  |  |  |  | 0 | 2337.9822 | 2337.9822 | 2337.9822 | 2337.9822 | 2337.9822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5773 | PEMBROKE PINES | 110355 | Private | 2030 | 5 | Swales | 66.6667 | 31315.9996 | 0.2 | 0.3 | 48852.9594 |  |  |  |  | 0 | 8259.8891 | 8259.8891 | 8259.8891 | 8259.8891 | 8259.8891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5774 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 34122.5743 | 0.2 | 0.3 | 53231.2159 |  |  |  |  | 0 | 9498.5502 | 9498.5502 | 9498.5502 | 9498.5502 | 9498.5502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5775 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16677.4841 | 0.2 | 0.3 | 26016.8752 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5776 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16667.0405 | 0.2 | 0.3 | 26000.5831 |  |  |  |  | 0 | 9779.1581 | 9779.1581 | 9779.1581 | 9779.1581 | 9779.1581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5777 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 44060.8588 | 0.2 | 0.3 | 68734.9397 |  |  |  |  | 0 | 5201.9268 | 5201.9268 | 5201.9268 | 5201.9268 | 5201.9268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5778 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16666.5777 | 0.2 | 0.3 | 25999.8612 |  |  |  |  | 0 | 5202.074 | 5202.074 | 5202.074 | 5202.074 | 5202.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5779 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 9780.2799 | 9780.2799 | 9780.2799 | 9780.2799 | 9780.2799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5780 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5781 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 16669.1232 | 0.2 | 0.3 | 26003.8322 |  |  |  |  | 0 | 9755.2741 | 9755.2741 | 9755.2741 | 9755.2741 | 9755.2741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5782 | PEMBROKE PINES | 110354 | Private | 2030 | 5 | Swales | 66.6667 | 17178.6333 | 0.2 | 0.3 | 26798.6679 |  |  |  |  | 0 | 5226.8191 | 5226.8191 | 5226.8191 | 5226.8191 | 5226.8191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5783 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 18130.7433 | 0.2 | 0.3 | 28283.9595 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5784 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 9829.8691 | 0.2 | 0.3 | 15334.5958 |  |  |  |  | 0 | 8059.8716 | 8059.8716 | 8059.8716 | 8059.8716 | 8059.8716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5785 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 2724.7875 | 0.2 | 0.3 | 4250.6686 |  |  |  |  | 0 | 5202.7028 | 5202.7028 | 5202.7028 | 5202.7028 | 5202.7028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5786 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 20923.2323 | 0.2 | 0.3 | 32640.2424 |  |  |  |  | 0 | 4430.4621 | 4430.4621 | 4430.4621 | 4430.4621 | 4430.4621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5787 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 5159.8172 | 0.2 | 0.3 | 8049.3148 |  |  |  |  | 0 | 1501.6563 | 1501.6563 | 1501.6563 | 1501.6563 | 1501.6563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5788 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 20121.1493 | 0.2 | 0.3 | 31388.9929 |  |  |  |  | 0 | 3762.3695 | 3762.3695 | 3762.3695 | 3762.3695 | 3762.3695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5789 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 20335.7429 | 0.2 | 0.3 | 31723.759 |  |  |  |  | 0 | 5205.1321 | 5205.1321 | 5205.1321 | 5205.1321 | 5205.1321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5790 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 26171.9504 | 0.2 | 0.3 | 40828.2426 |  |  |  |  | 0 | 9784.2708 | 9784.2708 | 9784.2708 | 9784.2708 | 9784.2708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5791 | PEMBROKE PINES | 110353 | Private | 2036 | 5 | Swales | 66.6667 | 15631.2737 | 0.2 | 0.3 | 24384.787 |  |  |  |  | 0 | 5204.0722 | 5204.0722 | 5204.0722 | 5204.0722 | 5204.0722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5792 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 16759.0093 | 0.2 | 0.3 | 26144.0546 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5793 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 27239.486 | 0.2 | 0.3 | 42493.5982 |  |  |  |  | 0 | 1442.7442 | 1442.7442 | 1442.7442 | 1442.7442 | 1442.7442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5794 | PEMBROKE PINES | 110337 | Private | 2036 | 5 | Swales | 66.6667 | 1118.7527 | 0.2 | 0.3 | 1745.2543 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5795 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 3811.1495 | 0.2 | 0.3 | 5945.3933 |  |  |  |  | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5796 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 19613.2497 | 0.2 | 0.3 | 30596.6695 |  |  |  |  | 0 | 2361.6528 | 2361.6528 | 2361.6528 | 2361.6528 | 2361.6528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5797 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 18858.2837 | 0.2 | 0.3 | 29418.9226 |  |  |  |  | 0 | 7097.9368 | 7097.9368 | 7097.9368 | 7097.9368 | 7097.9368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5798 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 14095.2491 | 0.2 | 0.3 | 21988.5886 |  |  |  |  | 0 | 8284.5806 | 8284.5806 | 8284.5806 | 8284.5806 | 8284.5806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5799 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 18593.751 | 0.2 | 0.3 | 29006.2516 |  |  |  |  | 0 | 8920.0762 | 8920.0762 | 8920.0762 | 8920.0762 | 8920.0762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5800 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 19207.4785 | 0.2 | 0.3 | 29963.6664 |  |  |  |  | 0 | 2951.8046 | 2951.8046 | 2951.8046 | 2951.8046 | 2951.8046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5801 | PEMBROKE PINES | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 8283.2311 | 0.2 | 0.3 | 12921.8405 |  |  |  |  | 0 | 6942.0222 | 6942.0222 | 6942.0222 | 6942.0222 | 6942.0222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5802 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 7793.0868 | 0.2 | 0.3 | 12157.2154 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5803 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 5679.7713 | 0.2 | 0.3 | 8860.4432 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5804 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 2224.6842 | 0.2 | 0.3 | 3470.5074 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5805 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 8333.5259 | 0.2 | 0.3 | 13000.3005 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5806 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 2091.3389 | 0.2 | 0.3 | 3262.4886 |  |  |  |  | 0 | 5200.0831 | 5200.0831 | 5200.0831 | 5200.0831 | 5200.0831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5807 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 189.7173 | 0.2 | 0.3 | 295.959 |  |  |  |  | 0 | 5153.1375 | 5153.1375 | 5153.1375 | 5153.1375 | 5153.1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5808 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 19436.4789 | 0.2 | 0.3 | 30320.9071 |  |  |  |  | 0 | 5077.2139 | 5077.2139 | 5077.2139 | 5077.2139 | 5077.2139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5809 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16697.8149 | 0.2 | 0.3 | 26048.5913 |  |  |  |  | 0 | 5760.8516 | 5760.8516 | 5760.8516 | 5760.8516 | 5760.8516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5810 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16259.411 | 0.2 | 0.3 | 25364.6812 |  |  |  |  | 0 | 5204.5258 | 5204.5258 | 5204.5258 | 5204.5258 | 5204.5258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5811 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 5967.4564 | 0.2 | 0.3 | 9309.232 |  |  |  |  | 0 | 5205.1055 | 5205.1055 | 5205.1055 | 5205.1055 | 5205.1055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5812 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 26034.2123 | 0.2 | 0.3 | 40613.3712 |  |  |  |  | 0 | 5205.8803 | 5205.8803 | 5205.8803 | 5205.8803 | 5205.8803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5813 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 33104.3283 | 0.2 | 0.3 | 51642.7521 |  |  |  |  | 0 | 46.4536 | 46.4536 | 46.4536 | 46.4536 | 46.4536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5814 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 20831.3973 | 0.2 | 0.3 | 32496.9798 |  |  |  |  | 0 | 9092.1342 | 9092.1342 | 9092.1342 | 9092.1342 | 9092.1342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5815 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 27191.9733 | 0.2 | 0.3 | 42419.4783 |  |  |  |  | 0 | 15692.4462 | 15692.4462 | 15692.4462 | 15692.4462 | 15692.4462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5816 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 23140.4436 | 0.2 | 0.3 | 36099.092 |  |  |  |  | 0 | 125.3142 | 125.3142 | 125.3142 | 125.3142 | 125.3142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5817 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 22773.6834 | 0.2 | 0.3 | 35526.9461 |  |  |  |  | 0 | 9522.3461 | 9522.3461 | 9522.3461 | 9522.3461 | 9522.3461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5818 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16887.0935 | 0.2 | 0.3 | 26343.8658 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5819 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 24207.4944 | 0.2 | 0.3 | 37763.6913 |  |  |  |  | 0 | 9779.5139 | 9779.5139 | 9779.5139 | 9779.5139 | 9779.5139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5820 | MIRAMAR | 110345 | Public | 2036 | 5 | Swales | 66.6667 | 21697.5127 | 0.2 | 0.3 | 33848.1198 |  |  |  |  | 0 | 5200.0927 | 5200.0927 | 5200.0927 | 5200.0927 | 5200.0927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5821 | MIRAMAR | 110345 | Public | 2036 | 5 | Swales | 66.6667 | 21587.7075 | 0.2 | 0.3 | 33676.8236 |  |  |  |  | 0 | 5200.0076 | 5200.0076 | 5200.0076 | 5200.0076 | 5200.0076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5822 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 16061.3605 | 0.2 | 0.3 | 25055.7224 |  |  |  |  | 0 | 10408.3591 | 10408.3591 | 10408.3591 | 10408.3591 | 10408.3591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5823 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 16668.5742 | 0.2 | 0.3 | 26002.9758 |  |  |  |  | 0 | 15552.6136 | 15552.6136 | 15552.6136 | 15552.6136 | 15552.6136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5824 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 16881.9538 | 0.2 | 0.3 | 26335.8479 |  |  |  |  | 0 | 5257.545 | 5257.545 | 5257.545 | 5257.545 | 5257.545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5825 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 23433.4111 | 0.2 | 0.3 | 36556.1213 |  |  |  |  | 0 | 2289.0505 | 2289.0505 | 2289.0505 | 2289.0505 | 2289.0505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5826 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 26948.9115 | 0.2 | 0.3 | 42040.302 |  |  |  |  | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5827 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 26246.6063 | 0.2 | 0.3 | 40944.7059 |  |  |  |  | 0 | 8976.4928 | 8976.4928 | 8976.4928 | 8976.4928 | 8976.4928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5828 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 26415.2049 | 0.2 | 0.3 | 41207.7196 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5829 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 26451.889 | 0.2 | 0.3 | 41264.9468 |  |  |  |  | 0 | 9778.925 | 9778.925 | 9778.925 | 9778.925 | 9778.925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5830 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 20970.6427 | 0.2 | 0.3 | 32714.2027 |  |  |  |  | 0 | 5200.4664 | 5200.4664 | 5200.4664 | 5200.4664 | 5200.4664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5831 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 26940.0313 | 0.2 | 0.3 | 42026.4489 |  |  |  |  | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5832 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 30298.4471 | 0.2 | 0.3 | 47265.5774 |  |  |  |  | 0 | 8723.1781 | 8723.1781 | 8723.1781 | 8723.1781 | 8723.1781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5833 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 18255.9775 | 0.2 | 0.3 | 28479.325 |  |  |  |  | 0 | 12361.3244 | 12361.3244 | 12361.3244 | 12361.3244 | 12361.3244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5834 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 24104.0143 | 0.2 | 0.3 | 37602.2623 |  |  |  |  | 0 | 5454.2959 | 5454.2959 | 5454.2959 | 5454.2959 | 5454.2959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5835 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 23482.4567 | 0.2 | 0.3 | 36632.6324 |  |  |  |  | 0 | 1721.7569 | 1721.7569 | 1721.7569 | 1721.7569 | 1721.7569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5836 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 18513.3851 | 0.2 | 0.3 | 28880.8807 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5837 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 8333.6775 | 0.2 | 0.3 | 13000.5368 |  |  |  |  | 0 | 4383.3489 | 4383.3489 | 4383.3489 | 4383.3489 | 4383.3489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5838 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 14649.1271 | 0.2 | 0.3 | 22852.6382 |  |  |  |  | 0 | 5546.9798 | 5546.9798 | 5546.9798 | 5546.9798 | 5546.9798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5839 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 16631.509 | 0.2 | 0.3 | 25945.154 |  |  |  |  | 0 | 5204.2751 | 5204.2751 | 5204.2751 | 5204.2751 | 5204.2751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5840 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16410.8349 | 0.2 | 0.3 | 25600.9025 |  |  |  |  | 0 | 5205.5903 | 5205.5903 | 5205.5903 | 5205.5903 | 5205.5903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5841 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16690.119 | 0.2 | 0.3 | 26036.5856 |  |  |  |  | 0 | 7624.2768 | 7624.2768 | 7624.2768 | 7624.2768 | 7624.2768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5842 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 30073.4965 | 0.2 | 0.3 | 46914.6545 |  |  |  |  | 0 | 7234.2323 | 7234.2323 | 7234.2323 | 7234.2323 | 7234.2323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5843 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 22013.553 | 0.2 | 0.3 | 34341.1427 |  |  |  |  | 0 | 10480.4152 | 10480.4152 | 10480.4152 | 10480.4152 | 10480.4152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5844 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 22218.0578 | 0.2 | 0.3 | 34660.1702 |  |  |  |  | 0 | 10401.9793 | 10401.9793 | 10401.9793 | 10401.9793 | 10401.9793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5845 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 16716.5361 | 0.2 | 0.3 | 26077.7964 |  |  |  |  | 0 | 14270.2961 | 14270.2961 | 14270.2961 | 14270.2961 | 14270.2961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5846 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 20052.0756 | 0.2 | 0.3 | 31281.2379 |  |  |  |  | 0 | 10410.1474 | 10410.1474 | 10410.1474 | 10410.1474 | 10410.1474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5847 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 14529.6335 | 0.2 | 0.3 | 22666.2282 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5848 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 19742.9719 | 0.2 | 0.3 | 30799.0361 |  |  |  |  | 0 | 2404.0264 | 2404.0264 | 2404.0264 | 2404.0264 | 2404.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5849 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16667.3275 | 0.2 | 0.3 | 26001.0308 |  |  |  |  | 0 | 9684.373 | 9684.373 | 9684.373 | 9684.373 | 9684.373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5850 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16808.3267 | 0.2 | 0.3 | 26220.9896 |  |  |  |  | 0 | 5238.0245 | 5238.0245 | 5238.0245 | 5238.0245 | 5238.0245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5851 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 5679.3719 | 0.2 | 0.3 | 8859.8202 |  |  |  |  | 0 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5852 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 19648.8468 | 0.2 | 0.3 | 30652.201 |  |  |  |  | 0 | 5205.1826 | 5205.1826 | 5205.1826 | 5205.1826 | 5205.1826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5853 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16667.5595 | 0.2 | 0.3 | 26001.3929 |  |  |  |  | 0 | 5208.469 | 5208.469 | 5208.469 | 5208.469 | 5208.469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5854 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16857.1575 | 0.2 | 0.3 | 26297.1658 |  |  |  |  | 0 | 6087.3848 | 6087.3848 | 6087.3848 | 6087.3848 | 6087.3848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5855 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 7541.5099 | 0.2 | 0.3 | 11764.7554 |  |  |  |  | 0 | 10459.2295 | 10459.2295 | 10459.2295 | 10459.2295 | 10459.2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5856 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 11010.3116 | 0.2 | 0.3 | 17176.0861 |  |  |  |  | 0 | 10404.235 | 10404.235 | 10404.235 | 10404.235 | 10404.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5857 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 11337.0562 | 11337.0562 | 11337.0562 | 11337.0562 | 11337.0562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5858 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16667.6242 | 0.2 | 0.3 | 26001.4938 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5859 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 6046.4008 | 0.2 | 0.3 | 9432.3852 |  |  |  |  | 0 | 5202.5708 | 5202.5708 | 5202.5708 | 5202.5708 | 5202.5708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5860 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 23866.4123 | 0.2 | 0.3 | 37231.6031 |  |  |  |  | 0 | 2403.987 | 2403.987 | 2403.987 | 2403.987 | 2403.987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5861 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 18661.3365 | 0.2 | 0.3 | 29111.685 |  |  |  |  | 0 | 5301.5288 | 5301.5288 | 5301.5288 | 5301.5288 | 5301.5288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5862 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 36477.5642 | 0.2 | 0.3 | 56905.0002 |  |  |  |  | 0 | 3356.518 | 3356.518 | 3356.518 | 3356.518 | 3356.518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5863 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 55668.1076 | 0.2 | 0.3 | 86842.2479 |  |  |  |  | 0 | 9597.3291 | 9597.3291 | 9597.3291 | 9597.3291 | 9597.3291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5864 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 5205.1826 | 5205.1826 | 5205.1826 | 5205.1826 | 5205.1826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5865 | MIRAMAR | 110345 | Public | 2036 | 5 | Swales | 66.6667 | 30042.8099 | 0.2 | 0.3 | 46866.7835 |  |  |  |  | 0 | 5205.7797 | 5205.7797 | 5205.7797 | 5205.7797 | 5205.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5866 | MIRAMAR | 110345 | Public | 2036 | 5 | Swales | 66.6667 | 29814.462 | 0.2 | 0.3 | 46510.5607 |  |  |  |  | 0 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5867 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 2471.544 | 2471.544 | 2471.544 | 2471.544 | 2471.544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5868 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 18392.0279 | 0.2 | 0.3 | 28691.5636 |  |  |  |  | 0 | 2731.8968 | 2731.8968 | 2731.8968 | 2731.8968 | 2731.8968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5869 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 22374.9469 | 0.2 | 0.3 | 34904.9172 |  |  |  |  | 0 | 5203.9664 | 5203.9664 | 5203.9664 | 5203.9664 | 5203.9664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5870 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 30736.9187 | 0.2 | 0.3 | 47949.5932 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5871 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 30689.5859 | 0.2 | 0.3 | 47875.7541 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5872 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 29018.5929 | 0.2 | 0.3 | 45269.005 |  |  |  |  | 0 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5873 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 15759.5284 | 0.2 | 0.3 | 24584.8643 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5874 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 24543.8829 | 0.2 | 0.3 | 38288.4574 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5875 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 25577.7273 | 0.2 | 0.3 | 39901.2545 |  |  |  |  | 0 | 8228.6424 | 8228.6424 | 8228.6424 | 8228.6424 | 8228.6424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5876 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 21771.0011 | 0.2 | 0.3 | 33962.7618 |  |  |  |  | 0 | 10469.1269 | 10469.1269 | 10469.1269 | 10469.1269 | 10469.1269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5877 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 9985.9937 | 0.2 | 0.3 | 15578.1501 |  |  |  |  | 0 | 15381.0067 | 15381.0067 | 15381.0067 | 15381.0067 | 15381.0067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5878 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 16755.4705 | 0.2 | 0.3 | 26138.5339 |  |  |  |  | 0 | 7623.7835 | 7623.7835 | 7623.7835 | 7623.7835 | 7623.7835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5879 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 2191.5315 | 0.2 | 0.3 | 3418.7891 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5880 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 17131.3327 | 0.2 | 0.3 | 26724.8791 |  |  |  |  | 0 | 8130.1371 | 8130.1371 | 8130.1371 | 8130.1371 | 8130.1371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5881 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 27860.1095 | 0.2 | 0.3 | 43461.7709 |  |  |  |  | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5882 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 15464.6322 | 0.2 | 0.3 | 24124.8262 |  |  |  |  | 0 | 5201.7479 | 5201.7479 | 5201.7479 | 5201.7479 | 5201.7479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5883 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 7459.0915 | 0.2 | 0.3 | 11636.1827 |  |  |  |  | 0 | 2403.8293 | 2403.8293 | 2403.8293 | 2403.8293 | 2403.8293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5884 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 9553.1613 | 0.2 | 0.3 | 14902.9317 |  |  |  |  | 0 | 9514.9666 | 9514.9666 | 9514.9666 | 9514.9666 | 9514.9666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5885 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 7159.295 | 0.2 | 0.3 | 11168.5002 |  |  |  |  | 0 | 5202.3391 | 5202.3391 | 5202.3391 | 5202.3391 | 5202.3391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5886 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 11047.5226 | 0.2 | 0.3 | 17234.1353 |  |  |  |  | 0 | 9064.3438 | 9064.3438 | 9064.3438 | 9064.3438 | 9064.3438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5887 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 12499.4887 | 0.2 | 0.3 | 19499.2023 |  |  |  |  | 0 | 10385.4893 | 10385.4893 | 10385.4893 | 10385.4893 | 10385.4893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5888 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 16730.0652 | 0.2 | 0.3 | 26098.9017 |  |  |  |  | 0 | 5302.2317 | 5302.2317 | 5302.2317 | 5302.2317 | 5302.2317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5889 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 16725.3516 | 0.2 | 0.3 | 26091.5485 |  |  |  |  | 0 | 5234.05 | 5234.05 | 5234.05 | 5234.05 | 5234.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5890 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 23953.9459 | 0.2 | 0.3 | 37368.1556 |  |  |  |  | 0 | 7384.4404 | 7384.4404 | 7384.4404 | 7384.4404 | 7384.4404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5891 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 31628.5821 | 0.2 | 0.3 | 49340.588 |  |  |  |  | 0 | 3485.2898 | 3485.2898 | 3485.2898 | 3485.2898 | 3485.2898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5892 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 34431.4014 | 0.2 | 0.3 | 53712.9862 |  |  |  |  | 0 | 5205.6944 | 5205.6944 | 5205.6944 | 5205.6944 | 5205.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5893 | MIRAMAR | 110319 | Public | 2033 | 5 | Swales | 66.6667 | 23498.3111 | 0.2 | 0.3 | 36657.3653 |  |  |  |  | 0 | 5204.0364 | 5204.0364 | 5204.0364 | 5204.0364 | 5204.0364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5894 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 17045.1927 | 0.2 | 0.3 | 26590.5006 |  |  |  |  | 0 | 10406.6665 | 10406.6665 | 10406.6665 | 10406.6665 | 10406.6665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5895 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16681.0903 | 0.2 | 0.3 | 26022.5009 |  |  |  |  | 0 | 9787.9128 | 9787.9128 | 9787.9128 | 9787.9128 | 9787.9128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5896 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 19417.1433 | 0.2 | 0.3 | 30290.7435 |  |  |  |  | 0 | 9796.8297 | 9796.8297 | 9796.8297 | 9796.8297 | 9796.8297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5897 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 20810.1402 | 0.2 | 0.3 | 32463.8187 |  |  |  |  | 0 | 6123.1797 | 6123.1797 | 6123.1797 | 6123.1797 | 6123.1797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5898 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 17072.2693 | 0.2 | 0.3 | 26632.7401 |  |  |  |  | 0 | 5925.8854 | 5925.8854 | 5925.8854 | 5925.8854 | 5925.8854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5899 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 17779.9073 | 0.2 | 0.3 | 27736.6554 |  |  |  |  | 0 | 5204.9779 | 5204.9779 | 5204.9779 | 5204.9779 | 5204.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5900 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16681.1095 | 0.2 | 0.3 | 26022.5308 |  |  |  |  | 0 | 7643.5687 | 7643.5687 | 7643.5687 | 7643.5687 | 7643.5687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5901 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16803.5539 | 0.2 | 0.3 | 26213.5441 |  |  |  |  | 0 | 1578.5335 | 1578.5335 | 1578.5335 | 1578.5335 | 1578.5335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5902 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 29167.9189 | 0.2 | 0.3 | 45501.9534 |  |  |  |  | 0 | 10916.6912 | 10916.6912 | 10916.6912 | 10916.6912 | 10916.6912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5903 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 4117.3713 | 4117.3713 | 4117.3713 | 4117.3713 | 4117.3713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5904 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7199 | 0.2 | 0.3 | 26000.0831 |  |  |  |  | 0 | 6261.8503 | 6261.8503 | 6261.8503 | 6261.8503 | 6261.8503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5905 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 22245.5003 | 0.2 | 0.3 | 34702.9805 |  |  |  |  | 0 | 5203.3747 | 5203.3747 | 5203.3747 | 5203.3747 | 5203.3747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5906 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 8339.9956 | 0.2 | 0.3 | 13010.3931 |  |  |  |  | 0 | 15609.7593 | 15609.7593 | 15609.7593 | 15609.7593 | 15609.7593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5907 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 14042.2117 | 0.2 | 0.3 | 21905.8502 |  |  |  |  | 0 | 5203.8943 | 5203.8943 | 5203.8943 | 5203.8943 | 5203.8943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5908 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 30335.9941 | 0.2 | 0.3 | 47324.1508 |  |  |  |  | 0 | 5203.1853 | 5203.1853 | 5203.1853 | 5203.1853 | 5203.1853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5909 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16684.2525 | 0.2 | 0.3 | 26027.434 |  |  |  |  | 0 | 5203.039 | 5203.039 | 5203.039 | 5203.039 | 5203.039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5910 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 29796.5001 | 0.2 | 0.3 | 46482.5401 |  |  |  |  | 0 | 5204.9109 | 5204.9109 | 5204.9109 | 5204.9109 | 5204.9109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5911 | MIRAMAR | 110345 | Public | 2036 | 5 | Swales | 66.6667 | 29948.8367 | 0.2 | 0.3 | 46720.1853 |  |  |  |  | 0 | 5204.1803 | 5204.1803 | 5204.1803 | 5204.1803 | 5204.1803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5912 | MIRAMAR | 110345 | Public | 2036 | 5 | Swales | 66.6667 | 31347.2429 | 0.2 | 0.3 | 48901.699 |  |  |  |  | 0 | 5203.9713 | 5203.9713 | 5203.9713 | 5203.9713 | 5203.9713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5913 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 11607.2765 | 0.2 | 0.3 | 18107.3514 |  |  |  |  | 0 | 7604.4355 | 7604.4355 | 7604.4355 | 7604.4355 | 7604.4355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5914 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 13061.8313 | 0.2 | 0.3 | 20376.4569 |  |  |  |  | 0 | 6088.0316 | 6088.0316 | 6088.0316 | 6088.0316 | 6088.0316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5915 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 11942.1129 | 0.2 | 0.3 | 18629.6961 |  |  |  |  | 0 | 5433.6659 | 5433.6659 | 5433.6659 | 5433.6659 | 5433.6659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5916 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 14810.7186 | 0.2 | 0.3 | 23104.721 |  |  |  |  | 0 | 7622.4316 | 7622.4316 | 7622.4316 | 7622.4316 | 7622.4316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5917 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 9013.3643 | 0.2 | 0.3 | 14060.8484 |  |  |  |  | 0 | 13191.4838 | 13191.4838 | 13191.4838 | 13191.4838 | 13191.4838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5918 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 16458.9591 | 0.2 | 0.3 | 25675.9761 |  |  |  |  | 0 | 5204.3164 | 5204.3164 | 5204.3164 | 5204.3164 | 5204.3164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5919 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 17045.3367 | 0.2 | 0.3 | 26590.7253 |  |  |  |  | 0 | 7675.7402 | 7675.7402 | 7675.7402 | 7675.7402 | 7675.7402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5920 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 18634.6131 | 0.2 | 0.3 | 29069.9965 |  |  |  |  | 0 | 5200.9469 | 5200.9469 | 5200.9469 | 5200.9469 | 5200.9469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5921 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 271.3775 | 0.2 | 0.3 | 423.349 |  |  |  |  | 0 | 5200.97 | 5200.97 | 5200.97 | 5200.97 | 5200.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5922 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 17435.5741 | 0.2 | 0.3 | 27199.4955 |  |  |  |  | 0 | 5200.9257 | 5200.9257 | 5200.9257 | 5200.9257 | 5200.9257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5923 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 8882.1902 | 8882.1902 | 8882.1902 | 8882.1902 | 8882.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5924 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 18518.9205 | 0.2 | 0.3 | 28889.5159 |  |  |  |  | 0 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5925 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 21057.4068 | 0.2 | 0.3 | 32849.5546 |  |  |  |  | 0 | 5204.6638 | 5204.6638 | 5204.6638 | 5204.6638 | 5204.6638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5926 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 15991.3354 | 0.2 | 0.3 | 24946.4832 |  |  |  |  | 0 | 7799.8123 | 7799.8123 | 7799.8123 | 7799.8123 | 7799.8123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5927 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 31464.8337 | 0.2 | 0.3 | 49085.1405 |  |  |  |  | 0 | 721.3247 | 721.3247 | 721.3247 | 721.3247 | 721.3247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5928 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 570.3371 | 0.2 | 0.3 | 889.7258 |  |  |  |  | 0 | 4922.8447 | 4922.8447 | 4922.8447 | 4922.8447 | 4922.8447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5929 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 305.6194 | 0.2 | 0.3 | 476.7663 |  |  |  |  | 0 | 5203.0605 | 5203.0605 | 5203.0605 | 5203.0605 | 5203.0605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5930 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 1818.1037 | 0.2 | 0.3 | 2836.2417 |  |  |  |  | 0 | 5204.838 | 5204.838 | 5204.838 | 5204.838 | 5204.838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5931 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 2769.4379 | 0.2 | 0.3 | 4320.3232 |  |  |  |  | 0 | 5203.9747 | 5203.9747 | 5203.9747 | 5203.9747 | 5203.9747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5932 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 13986.075 | 0.2 | 0.3 | 21818.277 |  |  |  |  | 0 | 5203.7882 | 5203.7882 | 5203.7882 | 5203.7882 | 5203.7882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5933 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16662.7417 | 0.2 | 0.3 | 25993.877 |  |  |  |  | 0 | 5649.4035 | 5649.4035 | 5649.4035 | 5649.4035 | 5649.4035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5934 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 886.727 | 0.2 | 0.3 | 1383.2941 |  |  |  |  | 0 | 9373.3426 | 9373.3426 | 9373.3426 | 9373.3426 | 9373.3426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5935 | MIRAMAR | 110319 | Public | 2033 | 5 | Swales | 66.6667 | 27262.3289 | 0.2 | 0.3 | 42529.233 |  |  |  |  | 0 | 5499.9764 | 5499.9764 | 5499.9764 | 5499.9764 | 5499.9764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5936 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 4960.5831 | 0.2 | 0.3 | 7738.5096 |  |  |  |  | 0 | 7699.0356 | 7699.0356 | 7699.0356 | 7699.0356 | 7699.0356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5937 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 19857.7348 | 0.2 | 0.3 | 30978.0663 |  |  |  |  | 0 | 1038.5088 | 1038.5088 | 1038.5088 | 1038.5088 | 1038.5088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5938 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 17397.3417 | 0.2 | 0.3 | 27139.853 |  |  |  |  | 0 | 7654.8008 | 7654.8008 | 7654.8008 | 7654.8008 | 7654.8008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5939 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 470.2063 | 0.2 | 0.3 | 733.5219 |  |  |  |  | 0 | 6233.5697 | 6233.5697 | 6233.5697 | 6233.5697 | 6233.5697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5940 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 22896.7391 | 0.2 | 0.3 | 35718.9129 |  |  |  |  | 0 | 9782.7949 | 9782.7949 | 9782.7949 | 9782.7949 | 9782.7949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5941 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 23936.2382 | 0.2 | 0.3 | 37340.5316 |  |  |  |  | 0 | 5203.5103 | 5203.5103 | 5203.5103 | 5203.5103 | 5203.5103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5942 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 22004.9865 | 0.2 | 0.3 | 34327.779 |  |  |  |  | 0 | 6769.758 | 6769.758 | 6769.758 | 6769.758 | 6769.758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5943 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 29905.2401 | 0.2 | 0.3 | 46652.1745 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5944 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 23589.9023 | 0.2 | 0.3 | 36800.2475 |  |  |  |  | 0 | 5202.4752 | 5202.4752 | 5202.4752 | 5202.4752 | 5202.4752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5945 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 2241.8253 | 0.2 | 0.3 | 3497.2474 |  |  |  |  | 0 | 2404.1052 | 2404.1052 | 2404.1052 | 2404.1052 | 2404.1052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5946 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 30750.318 | 0.2 | 0.3 | 47970.4961 |  |  |  |  | 0 | 1119.625 | 1119.625 | 1119.625 | 1119.625 | 1119.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5947 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16688.6378 | 0.2 | 0.3 | 26034.275 |  |  |  |  | 0 | 9366.3826 | 9366.3826 | 9366.3826 | 9366.3826 | 9366.3826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5948 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16668.2667 | 0.2 | 0.3 | 26002.4961 |  |  |  |  | 0 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5949 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 5204.6328 | 5204.6328 | 5204.6328 | 5204.6328 | 5204.6328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5950 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6997 | 0.2 | 0.3 | 26000.0515 |  |  |  |  | 0 | 8051.9725 | 8051.9725 | 8051.9725 | 8051.9725 | 8051.9725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5951 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 8888.7804 | 0.2 | 0.3 | 13866.4974 |  |  |  |  | 0 | 5710.3512 | 5710.3512 | 5710.3512 | 5710.3512 | 5710.3512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5952 | MIRAMAR | 110345 | Public | 2036 | 5 | Swales | 66.6667 | 29733.504 | 0.2 | 0.3 | 46384.2662 |  |  |  |  | 0 | 5203.413 | 5203.413 | 5203.413 | 5203.413 | 5203.413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5953 | MIRAMAR | 110345 | Public | 2036 | 5 | Swales | 66.6667 | 30054.3413 | 0.2 | 0.3 | 46884.7725 |  |  |  |  | 0 | 5204.2014 | 5204.2014 | 5204.2014 | 5204.2014 | 5204.2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5954 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 37200.416 | 0.2 | 0.3 | 58032.649 |  |  |  |  | 0 | 5204.5062 | 5204.5062 | 5204.5062 | 5204.5062 | 5204.5062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5955 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 772.3096 | 0.2 | 0.3 | 1204.803 |  |  |  |  | 0 | 7262.5208 | 7262.5208 | 7262.5208 | 7262.5208 | 7262.5208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5956 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 27024.7979 | 0.2 | 0.3 | 42158.6848 |  |  |  |  | 0 | 5204.3487 | 5204.3487 | 5204.3487 | 5204.3487 | 5204.3487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5957 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 16957.3145 | 0.2 | 0.3 | 26453.4107 |  |  |  |  | 0 | 9754.6648 | 9754.6648 | 9754.6648 | 9754.6648 | 9754.6648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5958 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 16835.9999 | 0.2 | 0.3 | 26264.1598 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5959 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 16758.7257 | 0.2 | 0.3 | 26143.612 |  |  |  |  | 0 | 6690.7914 | 6690.7914 | 6690.7914 | 6690.7914 | 6690.7914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5960 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 14545.2635 | 0.2 | 0.3 | 22690.6111 |  |  |  |  | 0 | 5204.5628 | 5204.5628 | 5204.5628 | 5204.5628 | 5204.5628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5961 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 949.0113 | 0.2 | 0.3 | 1480.4576 |  |  |  |  | 0 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5962 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 23400.9183 | 0.2 | 0.3 | 36505.4325 |  |  |  |  | 0 | 5204.5921 | 5204.5921 | 5204.5921 | 5204.5921 | 5204.5921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5963 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 17336.3166 | 0.2 | 0.3 | 27044.6539 |  |  |  |  | 0 | 8635.1164 | 8635.1164 | 8635.1164 | 8635.1164 | 8635.1164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5964 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 8894.4845 | 0.2 | 0.3 | 13875.3958 |  |  |  |  | 0 | 5204.1118 | 5204.1118 | 5204.1118 | 5204.1118 | 5204.1118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5965 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 31615.695 | 0.2 | 0.3 | 49320.4842 |  |  |  |  | 0 | 9780.2612 | 9780.2612 | 9780.2612 | 9780.2612 | 9780.2612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5966 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 28719.6094 | 0.2 | 0.3 | 44802.5907 |  |  |  |  | 0 | 5262.5434 | 5262.5434 | 5262.5434 | 5262.5434 | 5262.5434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5967 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 119.5168 | 0.2 | 0.3 | 186.4462 |  |  |  |  | 0 | 7041.9984 | 7041.9984 | 7041.9984 | 7041.9984 | 7041.9984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5968 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 15152.6265 | 0.2 | 0.3 | 23638.0973 |  |  |  |  | 0 | 6112.8667 | 6112.8667 | 6112.8667 | 6112.8667 | 6112.8667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5969 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 18576.6895 | 0.2 | 0.3 | 28979.6357 |  |  |  |  | 0 | 5205.1086 | 5205.1086 | 5205.1086 | 5205.1086 | 5205.1086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5970 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 16116.955 | 0.2 | 0.3 | 25142.4498 |  |  |  |  | 0 | 9794.758 | 9794.758 | 9794.758 | 9794.758 | 9794.758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5971 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 16828.7768 | 0.2 | 0.3 | 26252.8918 |  |  |  |  | 0 | 6534.0646 | 6534.0646 | 6534.0646 | 6534.0646 | 6534.0646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5972 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 29320.2762 | 0.2 | 0.3 | 45739.6309 |  |  |  |  | 0 | 5257.0378 | 5257.0378 | 5257.0378 | 5257.0378 | 5257.0378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5973 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 18085.6963 | 0.2 | 0.3 | 28213.6863 |  |  |  |  | 0 | 6294.5603 | 6294.5603 | 6294.5603 | 6294.5603 | 6294.5603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5974 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 5368.9609 | 0.2 | 0.3 | 8375.5791 |  |  |  |  | 0 | 9472.998 | 9472.998 | 9472.998 | 9472.998 | 9472.998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5975 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 19405.0534 | 0.2 | 0.3 | 30271.8833 |  |  |  |  | 0 | 5202.0268 | 5202.0268 | 5202.0268 | 5202.0268 | 5202.0268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5976 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 19372.8481 | 0.2 | 0.3 | 30221.6431 |  |  |  |  | 0 | 7393.1362 | 7393.1362 | 7393.1362 | 7393.1362 | 7393.1362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5977 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16862.8463 | 0.2 | 0.3 | 26306.0403 |  |  |  |  | 0 | 5204.4512 | 5204.4512 | 5204.4512 | 5204.4512 | 5204.4512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5978 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 33638.4447 | 0.2 | 0.3 | 52475.9737 |  |  |  |  | 0 | 7770.9141 | 7770.9141 | 7770.9141 | 7770.9141 | 7770.9141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5979 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 26966.7543 | 0.2 | 0.3 | 42068.1367 |  |  |  |  | 0 | 9665.4071 | 9665.4071 | 9665.4071 | 9665.4071 | 9665.4071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5980 | MIRAMAR | 110319 | Private | 2033 | 5 | Swales | 66.6667 | 38276.3443 | 0.2 | 0.3 | 59711.0971 |  |  |  |  | 0 | 9300.9564 | 9300.9564 | 9300.9564 | 9300.9564 | 9300.9564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5981 | MIRAMAR | 110319 | Private | 2033 | 5 | Swales | 66.6667 | 19786.2021 | 0.2 | 0.3 | 30866.4753 |  |  |  |  | 0 | 5202.934 | 5202.934 | 5202.934 | 5202.934 | 5202.934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5982 | MIRAMAR | 110319 | Public | 2033 | 5 | Swales | 66.6667 | 31601.0946 | 0.2 | 0.3 | 49297.7076 |  |  |  |  | 0 | 6153.7635 | 6153.7635 | 6153.7635 | 6153.7635 | 6153.7635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5983 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 22885.0637 | 0.2 | 0.3 | 35700.6994 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5984 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 11978.8222 | 0.2 | 0.3 | 18686.9626 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5985 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 5686.1144 | 0.2 | 0.3 | 8870.3385 |  |  |  |  | 0 | 7053.2439 | 7053.2439 | 7053.2439 | 7053.2439 | 7053.2439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5986 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 867.9397 | 0.2 | 0.3 | 1353.986 |  |  |  |  | 0 | 5200.7344 | 5200.7344 | 5200.7344 | 5200.7344 | 5200.7344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5987 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 17480.4943 | 0.2 | 0.3 | 27269.5711 |  |  |  |  | 0 | 9791.8133 | 9791.8133 | 9791.8133 | 9791.8133 | 9791.8133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5988 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 12738.8648 | 0.2 | 0.3 | 19872.6291 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5989 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 11718.6309 | 0.2 | 0.3 | 18281.0642 |  |  |  |  | 0 | 6834.2838 | 6834.2838 | 6834.2838 | 6834.2838 | 6834.2838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5990 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 17451.7285 | 0.2 | 0.3 | 27224.6965 |  |  |  |  | 0 | 4427.0755 | 4427.0755 | 4427.0755 | 4427.0755 | 4427.0755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5991 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 15515.7116 | 0.2 | 0.3 | 24204.5101 |  |  |  |  | 0 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5992 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 14991.4038 | 0.2 | 0.3 | 23386.5899 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5993 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 27269.2032 | 0.2 | 0.3 | 42539.957 |  |  |  |  | 0 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5994 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 17660.8503 | 0.2 | 0.3 | 27550.9264 |  |  |  |  | 0 | 5204.6086 | 5204.6086 | 5204.6086 | 5204.6086 | 5204.6086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5995 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 14894.0832 | 0.2 | 0.3 | 23234.7698 |  |  |  |  | 0 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5996 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 8125.3621 | 0.2 | 0.3 | 12675.5649 |  |  |  |  | 0 | 5206.4515 | 5206.4515 | 5206.4515 | 5206.4515 | 5206.4515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5997 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 13529.8147 | 0.2 | 0.3 | 21106.5109 |  |  |  |  | 0 | 9788.3759 | 9788.3759 | 9788.3759 | 9788.3759 | 9788.3759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5998 | MIRAMAR | 110345 | Public | 2036 | 5 | Swales | 66.6667 | 24479.9135 | 0.2 | 0.3 | 38188.6651 |  |  |  |  | 0 | 6101.3633 | 6101.3633 | 6101.3633 | 6101.3633 | 6101.3633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5999 | MIRAMAR | 110345 | Public | 2036 | 5 | Swales | 66.6667 | 24661.9243 | 0.2 | 0.3 | 38472.6019 |  |  |  |  | 0 | 4393.6747 | 4393.6747 | 4393.6747 | 4393.6747 | 4393.6747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6000 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 6966.8121 | 0.2 | 0.3 | 10868.2269 |  |  |  |  | 0 | 6973.2882 | 6973.2882 | 6973.2882 | 6973.2882 | 6973.2882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6001 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 16667.4323 | 0.2 | 0.3 | 26001.1944 |  |  |  |  | 0 | 128.4306 | 128.4306 | 128.4306 | 128.4306 | 128.4306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6002 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 17027.4313 | 0.2 | 0.3 | 26562.7928 |  |  |  |  | 0 | 5337.0933 | 5337.0933 | 5337.0933 | 5337.0933 | 5337.0933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6003 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 7873.6622 | 0.2 | 0.3 | 12282.913 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6004 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 17759.2671 | 0.2 | 0.3 | 27704.4567 |  |  |  |  | 0 | 34.5724 | 34.5724 | 34.5724 | 34.5724 | 34.5724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6005 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 17746.7343 | 0.2 | 0.3 | 27684.9056 |  |  |  |  | 0 | 5168.7018 | 5168.7018 | 5168.7018 | 5168.7018 | 5168.7018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6006 | MIRAMAR | 110344 | Public | 2036 | 5 | Swales | 66.6667 | 14532.5519 | 0.2 | 0.3 | 22670.781 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6007 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 6499.2021 | 0.2 | 0.3 | 10138.7553 |  |  |  |  | 0 | 7441.8187 | 7441.8187 | 7441.8187 | 7441.8187 | 7441.8187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6008 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 34826.9185 | 0.2 | 0.3 | 54329.9928 |  |  |  |  | 0 | 5291.1532 | 5291.1532 | 5291.1532 | 5291.1532 | 5291.1532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6009 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 6654.4283 | 0.2 | 0.3 | 10380.9082 |  |  |  |  | 0 | 6988.8194 | 6988.8194 | 6988.8194 | 6988.8194 | 6988.8194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6010 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 9634.3217 | 0.2 | 0.3 | 15029.5418 |  |  |  |  | 0 | 6409.2731 | 6409.2731 | 6409.2731 | 6409.2731 | 6409.2731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6011 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 20845.0639 | 0.2 | 0.3 | 32518.2997 |  |  |  |  | 0 | 6725.0956 | 6725.0956 | 6725.0956 | 6725.0956 | 6725.0956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6012 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 18334.2067 | 0.2 | 0.3 | 28601.3625 |  |  |  |  | 0 | 5206.1764 | 5206.1764 | 5206.1764 | 5206.1764 | 5206.1764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6013 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 1661.7612 | 0.2 | 0.3 | 2592.3475 |  |  |  |  | 0 | 8813.6381 | 8813.6381 | 8813.6381 | 8813.6381 | 8813.6381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6014 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 20265.7858 | 0.2 | 0.3 | 31614.6258 |  |  |  |  | 0 | 4986.761 | 4986.761 | 4986.761 | 4986.761 | 4986.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6015 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 17289.235 | 0.2 | 0.3 | 26971.2066 |  |  |  |  | 0 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6016 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 19813.8779 | 0.2 | 0.3 | 30909.6496 |  |  |  |  | 0 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6017 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 5296.1554 | 0.2 | 0.3 | 8262.0024 |  |  |  |  | 0 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6018 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 4174.6579 | 0.2 | 0.3 | 6512.4663 |  |  |  |  | 0 | 5204.8156 | 5204.8156 | 5204.8156 | 5204.8156 | 5204.8156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6019 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 26878.0976 | 0.2 | 0.3 | 41929.8323 |  |  |  |  | 0 | 3190.915 | 3190.915 | 3190.915 | 3190.915 | 3190.915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6020 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 17486.7741 | 0.2 | 0.3 | 27279.3675 |  |  |  |  | 0 | 6782.1583 | 6782.1583 | 6782.1583 | 6782.1583 | 6782.1583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6021 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 27482.5542 | 0.2 | 0.3 | 42872.7846 |  |  |  |  | 0 | 7077.4238 | 7077.4238 | 7077.4238 | 7077.4238 | 7077.4238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6022 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16688.6076 | 0.2 | 0.3 | 26034.2279 |  |  |  |  | 0 | 5520.9021 | 5520.9021 | 5520.9021 | 5520.9021 | 5520.9021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6023 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 12460.4659 | 0.2 | 0.3 | 19438.3268 |  |  |  |  | 0 | 10039.4675 | 10039.4675 | 10039.4675 | 10039.4675 | 10039.4675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6024 | MIRAMAR | 110319 | Private | 2033 | 5 | Swales | 66.6667 | 31766.1762 | 0.2 | 0.3 | 49555.2349 |  |  |  |  | 0 | 2575.0079 | 2575.0079 | 2575.0079 | 2575.0079 | 2575.0079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6025 | MIRAMAR | 110319 | Private | 2033 | 5 | Swales | 66.6667 | 14661.834 | 0.2 | 0.3 | 22872.461 |  |  |  |  | 0 | 5504.3629 | 5504.3629 | 5504.3629 | 5504.3629 | 5504.3629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6026 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 18790.492 | 0.2 | 0.3 | 29313.1675 |  |  |  |  | 0 | 5203.6593 | 5203.6593 | 5203.6593 | 5203.6593 | 5203.6593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6027 | MIRAMAR | 110319 | Public | 2033 | 5 | Swales | 66.6667 | 16688.8811 | 0.2 | 0.3 | 26034.6545 |  |  |  |  | 0 | 5201.7029 | 5201.7029 | 5201.7029 | 5201.7029 | 5201.7029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6028 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 24752.3051 | 0.2 | 0.3 | 38613.5959 |  |  |  |  | 0 | 7038.9122 | 7038.9122 | 7038.9122 | 7038.9122 | 7038.9122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6029 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 18648.6254 | 0.2 | 0.3 | 29091.8556 |  |  |  |  | 0 | 6816.9306 | 6816.9306 | 6816.9306 | 6816.9306 | 6816.9306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6030 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 11472.7407 | 0.2 | 0.3 | 17897.4755 |  |  |  |  | 0 | 7543.254 | 7543.254 | 7543.254 | 7543.254 | 7543.254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6031 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 8232.1795 | 0.2 | 0.3 | 12842.2001 |  |  |  |  | 0 | 7513.411 | 7513.411 | 7513.411 | 7513.411 | 7513.411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6032 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 157.0935 | 0.2 | 0.3 | 245.0658 |  |  |  |  | 0 | 9806.9648 | 9806.9648 | 9806.9648 | 9806.9648 | 9806.9648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6033 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 25570.6001 | 0.2 | 0.3 | 39890.1362 |  |  |  |  | 0 | 5212.1084 | 5212.1084 | 5212.1084 | 5212.1084 | 5212.1084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6034 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 25879.7719 | 0.2 | 0.3 | 40372.4442 |  |  |  |  | 0 | 614.0262 | 614.0262 | 614.0262 | 614.0262 | 614.0262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6035 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 8867.5133 | 0.2 | 0.3 | 13833.3207 |  |  |  |  | 0 | 9103.5275 | 9103.5275 | 9103.5275 | 9103.5275 | 9103.5275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6036 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 2784.4217 | 0.2 | 0.3 | 4343.6979 |  |  |  |  | 0 | 4908.3773 | 4908.3773 | 4908.3773 | 4908.3773 | 4908.3773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6037 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 22168.891 | 0.2 | 0.3 | 34583.47 |  |  |  |  | 0 | 5260.4027 | 5260.4027 | 5260.4027 | 5260.4027 | 5260.4027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6038 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 18215.6098 | 0.2 | 0.3 | 28416.3513 |  |  |  |  | 0 | 5205.5411 | 5205.5411 | 5205.5411 | 5205.5411 | 5205.5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6039 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 5071.09 | 0.2 | 0.3 | 7910.9004 |  |  |  |  | 0 | 5205.6944 | 5205.6944 | 5205.6944 | 5205.6944 | 5205.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6040 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 735.1843 | 0.2 | 0.3 | 1146.8876 |  |  |  |  | 0 | 5677.074 | 5677.074 | 5677.074 | 5677.074 | 5677.074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6041 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 17924.1062 | 0.2 | 0.3 | 27961.6057 |  |  |  |  | 0 | 7853.5216 | 7853.5216 | 7853.5216 | 7853.5216 | 7853.5216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6042 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 11384.4787 | 0.2 | 0.3 | 17759.7868 |  |  |  |  | 0 | 4308.9831 | 4308.9831 | 4308.9831 | 4308.9831 | 4308.9831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6043 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 12228.7109 | 0.2 | 0.3 | 19076.789 |  |  |  |  | 0 | 3875.8545 | 3875.8545 | 3875.8545 | 3875.8545 | 3875.8545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6044 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 37047.0671 | 0.2 | 0.3 | 57793.4247 |  |  |  |  | 0 | 3514.9016 | 3514.9016 | 3514.9016 | 3514.9016 | 3514.9016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6045 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 4886.0234 | 0.2 | 0.3 | 7622.1965 |  |  |  |  | 0 | 6064.9838 | 6064.9838 | 6064.9838 | 6064.9838 | 6064.9838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6046 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 24572.3161 | 0.2 | 0.3 | 38332.8132 |  |  |  |  | 0 | 10059.371 | 10059.371 | 10059.371 | 10059.371 | 10059.371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6047 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 52279.4338 | 0.2 | 0.3 | 81555.9167 |  |  |  |  | 0 | 5265.4055 | 5265.4055 | 5265.4055 | 5265.4055 | 5265.4055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6048 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 27853.2715 | 0.2 | 0.3 | 43451.1035 |  |  |  |  | 0 | 2639.4647 | 2639.4647 | 2639.4647 | 2639.4647 | 2639.4647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6049 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 10104.7152 | 0.2 | 0.3 | 15763.3557 |  |  |  |  | 0 | 9464.1517 | 9464.1517 | 9464.1517 | 9464.1517 | 9464.1517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6050 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 17125.5637 | 0.2 | 0.3 | 26715.8794 |  |  |  |  | 0 | 6560.0217 | 6560.0217 | 6560.0217 | 6560.0217 | 6560.0217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6051 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 17530.7977 | 0.2 | 0.3 | 27348.0445 |  |  |  |  | 0 | 3397.0695 | 3397.0695 | 3397.0695 | 3397.0695 | 3397.0695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6052 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 19301.5395 | 0.2 | 0.3 | 30110.4016 |  |  |  |  | 0 | 12407.7831 | 12407.7831 | 12407.7831 | 12407.7831 | 12407.7831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6053 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16084.5927 | 0.2 | 0.3 | 25091.9647 |  |  |  |  | 0 | 10555.0544 | 10555.0544 | 10555.0544 | 10555.0544 | 10555.0544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6054 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16926.0658 | 0.2 | 0.3 | 26404.6626 |  |  |  |  | 0 | 14253.9199 | 14253.9199 | 14253.9199 | 14253.9199 | 14253.9199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6055 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 17058.5055 | 0.2 | 0.3 | 26611.2686 |  |  |  |  | 0 | 9388.476 | 9388.476 | 9388.476 | 9388.476 | 9388.476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6056 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 19533.0834 | 0.2 | 0.3 | 30471.6101 |  |  |  |  | 0 | 9084.223 | 9084.223 | 9084.223 | 9084.223 | 9084.223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6057 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 10542.2271 | 0.2 | 0.3 | 16445.8743 |  |  |  |  | 0 | 355.8738 | 355.8738 | 355.8738 | 355.8738 | 355.8738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6058 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 17295.2062 | 0.2 | 0.3 | 26980.5217 |  |  |  |  | 0 | 5203.8425 | 5203.8425 | 5203.8425 | 5203.8425 | 5203.8425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6059 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 10540.2561 | 0.2 | 0.3 | 16442.7996 |  |  |  |  | 0 | 5488.3304 | 5488.3304 | 5488.3304 | 5488.3304 | 5488.3304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6060 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 20277.1499 | 0.2 | 0.3 | 31632.3538 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6061 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 3459.5293 | 0.2 | 0.3 | 5396.8658 |  |  |  |  | 0 | 5204.1278 | 5204.1278 | 5204.1278 | 5204.1278 | 5204.1278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6062 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 33278.8311 | 0.2 | 0.3 | 51914.9766 |  |  |  |  | 0 | 9783.7214 | 9783.7214 | 9783.7214 | 9783.7214 | 9783.7214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6063 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 24341.2079 | 0.2 | 0.3 | 37972.2844 |  |  |  |  | 0 | 8516.1184 | 8516.1184 | 8516.1184 | 8516.1184 | 8516.1184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6064 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 10996.162 | 0.2 | 0.3 | 17154.0127 |  |  |  |  | 0 | 9782.0262 | 9782.0262 | 9782.0262 | 9782.0262 | 9782.0262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6065 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 12552.912 | 0.2 | 0.3 | 19582.5427 |  |  |  |  | 0 | 9768.8519 | 9768.8519 | 9768.8519 | 9768.8519 | 9768.8519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6066 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 15290.5442 | 0.2 | 0.3 | 23853.249 |  |  |  |  | 0 | 5216.6545 | 5216.6545 | 5216.6545 | 5216.6545 | 5216.6545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6067 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16800.1394 | 0.2 | 0.3 | 26208.2175 |  |  |  |  | 0 | 9783.553 | 9783.553 | 9783.553 | 9783.553 | 9783.553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6068 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 21941.2484 | 0.2 | 0.3 | 34228.3475 |  |  |  |  | 0 | 9784.786 | 9784.786 | 9784.786 | 9784.786 | 9784.786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6069 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 2279.491 | 0.2 | 0.3 | 3556.006 |  |  |  |  | 0 | 5092.4897 | 5092.4897 | 5092.4897 | 5092.4897 | 5092.4897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6070 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 19077.1913 | 0.2 | 0.3 | 29760.4184 |  |  |  |  | 0 | 5172.4088 | 5172.4088 | 5172.4088 | 5172.4088 | 5172.4088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6071 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 17281.2559 | 0.2 | 0.3 | 26958.7593 |  |  |  |  | 0 | 5125.9903 | 5125.9903 | 5125.9903 | 5125.9903 | 5125.9903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6072 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 7476.2143 | 0.2 | 0.3 | 11662.8943 |  |  |  |  | 0 | 9783.1017 | 9783.1017 | 9783.1017 | 9783.1017 | 9783.1017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6073 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16697.4208 | 0.2 | 0.3 | 26047.9764 |  |  |  |  | 0 | 5205.3989 | 5205.3989 | 5205.3989 | 5205.3989 | 5205.3989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6074 | MIRAMAR | 110319 | Private | 2033 | 5 | Swales | 66.6667 | 11038.7555 | 0.2 | 0.3 | 17220.4586 |  |  |  |  | 0 | 5205.6091 | 5205.6091 | 5205.6091 | 5205.6091 | 5205.6091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6075 | MIRAMAR | 110319 | Public | 2033 | 5 | Swales | 66.6667 | 29610.6995 | 0.2 | 0.3 | 46192.6912 |  |  |  |  | 0 | 5951.6547 | 5951.6547 | 5951.6547 | 5951.6547 | 5951.6547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6076 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 27902.803 | 0.2 | 0.3 | 43528.3727 |  |  |  |  | 0 | 4366.1517 | 4366.1517 | 4366.1517 | 4366.1517 | 4366.1517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6077 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 39075.1495 | 0.2 | 0.3 | 60957.2332 |  |  |  |  | 0 | 5202.5498 | 5202.5498 | 5202.5498 | 5202.5498 | 5202.5498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6078 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 14252.3135 | 0.2 | 0.3 | 22233.609 |  |  |  |  | 0 | 7535.3232 | 7535.3232 | 7535.3232 | 7535.3232 | 7535.3232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6079 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 20748.6727 | 0.2 | 0.3 | 32367.9295 |  |  |  |  | 0 | 5100.3747 | 5100.3747 | 5100.3747 | 5100.3747 | 5100.3747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6080 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 30514.9091 | 0.2 | 0.3 | 47603.2582 |  |  |  |  | 0 | 60.7065 | 60.7065 | 60.7065 | 60.7065 | 60.7065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6081 | MIRAMAR | 110367 | Private | 2036 | 5 | Swales | 66.6667 | 31925.3711 | 0.2 | 0.3 | 49803.5789 |  |  |  |  | 0 | 1881.6731 | 1881.6731 | 1881.6731 | 1881.6731 | 1881.6731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6082 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16674.8597 | 0.2 | 0.3 | 26012.7812 |  |  |  |  | 0 | 908.2084 | 908.2084 | 908.2084 | 908.2084 | 908.2084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6083 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 13109.5583 | 0.2 | 0.3 | 20450.911 |  |  |  |  | 0 | 14272.5097 | 14272.5097 | 14272.5097 | 14272.5097 | 14272.5097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6084 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 14081.9292 | 0.2 | 0.3 | 21967.8096 |  |  |  |  | 0 | 12737.6459 | 12737.6459 | 12737.6459 | 12737.6459 | 12737.6459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6085 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 14457.9027 | 0.2 | 0.3 | 22554.3283 |  |  |  |  | 0 | 12529.4322 | 12529.4322 | 12529.4322 | 12529.4322 | 12529.4322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6086 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 10088.0162 | 0.2 | 0.3 | 15737.3053 |  |  |  |  | 0 | 14270.1695 | 14270.1695 | 14270.1695 | 14270.1695 | 14270.1695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6087 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16898.2179 | 0.2 | 0.3 | 26361.22 |  |  |  |  | 0 | 278.454 | 278.454 | 278.454 | 278.454 | 278.454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6088 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16984.2887 | 0.2 | 0.3 | 26495.4903 |  |  |  |  | 0 | 5703.2324 | 5703.2324 | 5703.2324 | 5703.2324 | 5703.2324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6089 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 17153.0794 | 0.2 | 0.3 | 26758.8039 |  |  |  |  | 0 | 10408.3695 | 10408.3695 | 10408.3695 | 10408.3695 | 10408.3695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6090 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 35196.5327 | 0.2 | 0.3 | 54906.591 |  |  |  |  | 0 | 10408.6346 | 10408.6346 | 10408.6346 | 10408.6346 | 10408.6346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6091 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 8797.8151 | 0.2 | 0.3 | 13724.5915 |  |  |  |  | 0 | 5200.9103 | 5200.9103 | 5200.9103 | 5200.9103 | 5200.9103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6092 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16672.9447 | 0.2 | 0.3 | 26009.7938 |  |  |  |  | 0 | 8516.2332 | 8516.2332 | 8516.2332 | 8516.2332 | 8516.2332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6093 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16675.2837 | 0.2 | 0.3 | 26013.4425 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6094 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 2407.9167 | 0.2 | 0.3 | 3756.3501 |  |  |  |  | 0 | 5204.4909 | 5204.4909 | 5204.4909 | 5204.4909 | 5204.4909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6095 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 3762.7933 | 0.2 | 0.3 | 5869.9575 |  |  |  |  | 0 | 5782.833 | 5782.833 | 5782.833 | 5782.833 | 5782.833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6096 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 21371.7591 | 0.2 | 0.3 | 33339.9442 |  |  |  |  | 0 | 5203.506 | 5203.506 | 5203.506 | 5203.506 | 5203.506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6097 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 8517.1266 | 0.2 | 0.3 | 13286.7175 |  |  |  |  | 0 | 3147.858 | 3147.858 | 3147.858 | 3147.858 | 3147.858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6098 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 18091.9251 | 0.2 | 0.3 | 28223.4031 |  |  |  |  | 0 | 2055.4243 | 2055.4243 | 2055.4243 | 2055.4243 | 2055.4243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6099 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 26944.1705 | 0.2 | 0.3 | 42032.9059 |  |  |  |  | 0 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6100 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 15070.413 | 0.2 | 0.3 | 23509.8443 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6101 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 17847.6876 | 0.2 | 0.3 | 27842.3927 |  |  |  |  | 0 | 5822.7045 | 5822.7045 | 5822.7045 | 5822.7045 | 5822.7045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6102 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 19286.7347 | 0.2 | 0.3 | 30087.3062 |  |  |  |  | 0 | 5170.0567 | 5170.0567 | 5170.0567 | 5170.0567 | 5170.0567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6103 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 14678.5641 | 0.2 | 0.3 | 22898.56 |  |  |  |  | 0 | 5241.9105 | 5241.9105 | 5241.9105 | 5241.9105 | 5241.9105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6104 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 15644.2096 | 0.2 | 0.3 | 24404.967 |  |  |  |  | 0 | 9783.5126 | 9783.5126 | 9783.5126 | 9783.5126 | 9783.5126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6105 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 3411.4392 | 0.2 | 0.3 | 5321.8452 |  |  |  |  | 0 | 5205.4975 | 5205.4975 | 5205.4975 | 5205.4975 | 5205.4975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6106 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16679.0948 | 0.2 | 0.3 | 26019.3879 |  |  |  |  | 0 | 5205.6944 | 5205.6944 | 5205.6944 | 5205.6944 | 5205.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6107 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 22628.4077 | 0.2 | 0.3 | 35300.3161 |  |  |  |  | 0 | 5205.4434 | 5205.4434 | 5205.4434 | 5205.4434 | 5205.4434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6108 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 18382.3564 | 0.2 | 0.3 | 28676.476 |  |  |  |  | 0 | 5320.0396 | 5320.0396 | 5320.0396 | 5320.0396 | 5320.0396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6109 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 17230.6399 | 0.2 | 0.3 | 26879.7983 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6110 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16855.9472 | 0.2 | 0.3 | 26295.2776 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6111 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 28464.3057 | 0.2 | 0.3 | 44404.3169 |  |  |  |  | 0 | 8595.8973 | 8595.8973 | 8595.8973 | 8595.8973 | 8595.8973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6112 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 47548.0231 | 0.2 | 0.3 | 74174.916 |  |  |  |  | 0 | 3923.8566 | 3923.8566 | 3923.8566 | 3923.8566 | 3923.8566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6113 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16291.3789 | 0.2 | 0.3 | 25414.551 |  |  |  |  | 0 | 2122.868 | 2122.868 | 2122.868 | 2122.868 | 2122.868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6114 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16678.0959 | 0.2 | 0.3 | 26017.8296 |  |  |  |  | 0 | 2600.5867 | 2600.5867 | 2600.5867 | 2600.5867 | 2600.5867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6115 | MIRAMAR | 110319 | Private | 2033 | 5 | Swales | 66.6667 | 22255.1785 | 0.2 | 0.3 | 34718.0784 |  |  |  |  | 0 | 2907.7907 | 2907.7907 | 2907.7907 | 2907.7907 | 2907.7907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6116 | MIRAMAR | 110319 | Private | 2033 | 5 | Swales | 66.6667 | 11347.4798 | 0.2 | 0.3 | 17702.0685 |  |  |  |  | 0 | 4887.4716 | 4887.4716 | 4887.4716 | 4887.4716 | 4887.4716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6117 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 11236.7623 | 0.2 | 0.3 | 17529.3491 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6118 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16856.9957 | 0.2 | 0.3 | 26296.9133 |  |  |  |  | 0 | 5207.2882 | 5207.2882 | 5207.2882 | 5207.2882 | 5207.2882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6119 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16682.4541 | 0.2 | 0.3 | 26024.6284 |  |  |  |  | 0 | 8925.4582 | 8925.4582 | 8925.4582 | 8925.4582 | 8925.4582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6120 | MIRAMAR | 110319 | Public | 2033 | 5 | Swales | 66.6667 | 16674.2553 | 0.2 | 0.3 | 26011.8382 |  |  |  |  | 0 | 2442.4109 | 2442.4109 | 2442.4109 | 2442.4109 | 2442.4109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6121 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 5471.1872 | 5471.1872 | 5471.1872 | 5471.1872 | 5471.1872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6122 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 10221.9243 | 0.2 | 0.3 | 15946.202 |  |  |  |  | 0 | 2243.0032 | 2243.0032 | 2243.0032 | 2243.0032 | 2243.0032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6123 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 8298.2605 | 0.2 | 0.3 | 12945.2863 |  |  |  |  | 0 | 5704.6626 | 5704.6626 | 5704.6626 | 5704.6626 | 5704.6626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6124 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 20960.8886 | 0.2 | 0.3 | 32698.9862 |  |  |  |  | 0 | 2040.1011 | 2040.1011 | 2040.1011 | 2040.1011 | 2040.1011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6125 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 13716.0252 | 0.2 | 0.3 | 21396.9993 |  |  |  |  | 0 | 6086.384 | 6086.384 | 6086.384 | 6086.384 | 6086.384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6126 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 9341.8764 | 0.2 | 0.3 | 14573.3272 |  |  |  |  | 0 | 1769.6625 | 1769.6625 | 1769.6625 | 1769.6625 | 1769.6625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6127 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 9977.4616 | 0.2 | 0.3 | 15564.8401 |  |  |  |  | 0 | 12621.0797 | 12621.0797 | 12621.0797 | 12621.0797 | 12621.0797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6128 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16791.9236 | 0.2 | 0.3 | 26195.4008 |  |  |  |  | 0 | 10414.7261 | 10414.7261 | 10414.7261 | 10414.7261 | 10414.7261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6129 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 17153.2867 | 0.2 | 0.3 | 26759.1273 |  |  |  |  | 0 | 14781.9942 | 14781.9942 | 14781.9942 | 14781.9942 | 14781.9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6130 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 34885.8853 | 0.2 | 0.3 | 54421.9811 |  |  |  |  | 0 | 12985.7568 | 12985.7568 | 12985.7568 | 12985.7568 | 12985.7568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6131 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 17478.2255 | 0.2 | 0.3 | 27266.0317 |  |  |  |  | 0 | 1709.0393 | 1709.0393 | 1709.0393 | 1709.0393 | 1709.0393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6132 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 20191.9599 | 0.2 | 0.3 | 31499.4574 |  |  |  |  | 0 | 6977.1642 | 6977.1642 | 6977.1642 | 6977.1642 | 6977.1642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6133 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 14304.106 | 0.2 | 0.3 | 22314.4054 |  |  |  |  | 0 | 9423.9492 | 9423.9492 | 9423.9492 | 9423.9492 | 9423.9492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6134 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 13008.036 | 0.2 | 0.3 | 20292.5362 |  |  |  |  | 0 | 10407.2533 | 10407.2533 | 10407.2533 | 10407.2533 | 10407.2533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6135 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16901.1768 | 0.2 | 0.3 | 26365.8358 |  |  |  |  | 0 | 10408.9173 | 10408.9173 | 10408.9173 | 10408.9173 | 10408.9173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6136 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 23310.4229 | 0.2 | 0.3 | 36364.2598 |  |  |  |  | 0 | 5203.1946 | 5203.1946 | 5203.1946 | 5203.1946 | 5203.1946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6137 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 27657.9705 | 0.2 | 0.3 | 43146.4339 |  |  |  |  | 0 | 8368.2549 | 8368.2549 | 8368.2549 | 8368.2549 | 8368.2549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6138 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 23118.7537 | 0.2 | 0.3 | 36065.2557 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6139 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16961.2803 | 0.2 | 0.3 | 26459.5972 |  |  |  |  | 0 | 5204.3042 | 5204.3042 | 5204.3042 | 5204.3042 | 5204.3042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6140 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 17963.1235 | 0.2 | 0.3 | 28022.4727 |  |  |  |  | 0 | 9757.3729 | 9757.3729 | 9757.3729 | 9757.3729 | 9757.3729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6141 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 19498.9393 | 0.2 | 0.3 | 30418.3454 |  |  |  |  | 0 | 5493.3292 | 5493.3292 | 5493.3292 | 5493.3292 | 5493.3292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6142 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 27776.3865 | 0.2 | 0.3 | 43331.163 |  |  |  |  | 0 | 9782.6018 | 9782.6018 | 9782.6018 | 9782.6018 | 9782.6018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6143 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 1406.2585 | 0.2 | 0.3 | 2193.7633 |  |  |  |  | 0 | 7342.6956 | 7342.6956 | 7342.6956 | 7342.6956 | 7342.6956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6144 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 9563.8257 | 0.2 | 0.3 | 14919.5681 |  |  |  |  | 0 | 7643.9865 | 7643.9865 | 7643.9865 | 7643.9865 | 7643.9865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6145 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 28221.2167 | 0.2 | 0.3 | 44025.0981 |  |  |  |  | 0 | 9783.4232 | 9783.4232 | 9783.4232 | 9783.4232 | 9783.4232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6146 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 21982.8299 | 0.2 | 0.3 | 34293.2146 |  |  |  |  | 0 | 9782.7173 | 9782.7173 | 9782.7173 | 9782.7173 | 9782.7173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6147 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 22532.4103 | 0.2 | 0.3 | 35150.5601 |  |  |  |  | 0 | 6453.876 | 6453.876 | 6453.876 | 6453.876 | 6453.876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6148 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 16676.1281 | 0.2 | 0.3 | 26014.7598 |  |  |  |  | 0 | 5299.7701 | 5299.7701 | 5299.7701 | 5299.7701 | 5299.7701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6149 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 21708.8183 | 0.2 | 0.3 | 33865.7565 |  |  |  |  | 0 | 5207.3933 | 5207.3933 | 5207.3933 | 5207.3933 | 5207.3933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6150 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 24361.7413 | 0.2 | 0.3 | 38004.3164 |  |  |  |  | 0 | 8220.8698 | 8220.8698 | 8220.8698 | 8220.8698 | 8220.8698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6151 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 28387.6367 | 0.2 | 0.3 | 44284.7132 |  |  |  |  | 0 | 5203.5327 | 5203.5327 | 5203.5327 | 5203.5327 | 5203.5327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6152 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 26522.1575 | 0.2 | 0.3 | 41374.5658 |  |  |  |  | 0 | 5202.5456 | 5202.5456 | 5202.5456 | 5202.5456 | 5202.5456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6153 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 24573.6291 | 0.2 | 0.3 | 38334.8614 |  |  |  |  | 0 | 5202.2535 | 5202.2535 | 5202.2535 | 5202.2535 | 5202.2535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6154 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 9965.481 | 0.2 | 0.3 | 15546.1504 |  |  |  |  | 0 | 7851.131 | 7851.131 | 7851.131 | 7851.131 | 7851.131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6155 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 16676.3575 | 0.2 | 0.3 | 26015.1178 |  |  |  |  | 0 | 4263.2993 | 4263.2993 | 4263.2993 | 4263.2993 | 4263.2993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6156 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 16675.6741 | 0.2 | 0.3 | 26014.0516 |  |  |  |  | 0 | 6674.0413 | 6674.0413 | 6674.0413 | 6674.0413 | 6674.0413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6157 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 15850.069 | 0.2 | 0.3 | 24726.1076 |  |  |  |  | 0 | 3078.1788 | 3078.1788 | 3078.1788 | 3078.1788 | 3078.1788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6158 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 24031.5505 | 0.2 | 0.3 | 37489.2187 |  |  |  |  | 0 | 2600.5014 | 2600.5014 | 2600.5014 | 2600.5014 | 2600.5014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6159 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 19764.0426 | 0.2 | 0.3 | 30831.9065 |  |  |  |  | 0 | 2293.323 | 2293.323 | 2293.323 | 2293.323 | 2293.323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6160 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 304.6986 | 0.2 | 0.3 | 475.3298 |  |  |  |  | 0 | 313.5926 | 313.5926 | 313.5926 | 313.5926 | 313.5926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6161 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 6042.8294 | 0.2 | 0.3 | 9426.8139 |  |  |  |  | 0 | 3591.6014 | 3591.6014 | 3591.6014 | 3591.6014 | 3591.6014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6162 | MIRAMAR | 110346 | Public | 2036 | 5 | Swales | 66.6667 | 7946.7237 | 0.2 | 0.3 | 12396.8889 |  |  |  |  | 0 | 4485.2605 | 4485.2605 | 4485.2605 | 4485.2605 | 4485.2605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6163 | MIRAMAR | 110346 | Public | 2036 | 5 | Swales | 66.6667 | 35434.2727 | 0.2 | 0.3 | 55277.4655 |  |  |  |  | 0 | 3382.7131 | 3382.7131 | 3382.7131 | 3382.7131 | 3382.7131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6164 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 12077.3504 | 0.2 | 0.3 | 18840.6666 |  |  |  |  | 0 | 4671.7789 | 4671.7789 | 4671.7789 | 4671.7789 | 4671.7789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6165 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 12559.7935 | 0.2 | 0.3 | 19593.2778 |  |  |  |  | 0 | 3170.296 | 3170.296 | 3170.296 | 3170.296 | 3170.296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6166 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16699.1349 | 0.2 | 0.3 | 26050.6504 |  |  |  |  | 0 | 4884.0978 | 4884.0978 | 4884.0978 | 4884.0978 | 4884.0978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6167 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 2990.8207 | 2990.8207 | 2990.8207 | 2990.8207 | 2990.8207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6168 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 4788.0927 | 0.2 | 0.3 | 7469.4247 |  |  |  |  | 0 | 8946.0128 | 8946.0128 | 8946.0128 | 8946.0128 | 8946.0128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6169 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 45252.7637 | 0.2 | 0.3 | 70594.3113 |  |  |  |  | 0 | 9101.5942 | 9101.5942 | 9101.5942 | 9101.5942 | 9101.5942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6170 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16684.5193 | 0.2 | 0.3 | 26027.8501 |  |  |  |  | 0 | 8344.6056 | 8344.6056 | 8344.6056 | 8344.6056 | 8344.6056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6171 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16712.7507 | 0.2 | 0.3 | 26071.8911 |  |  |  |  | 0 | 2403.1573 | 2403.1573 | 2403.1573 | 2403.1573 | 2403.1573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6172 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 23884.6731 | 0.2 | 0.3 | 37260.0901 |  |  |  |  | 0 | 12172.2829 | 12172.2829 | 12172.2829 | 12172.2829 | 12172.2829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6173 | MIRAMAR | 110319 | Private | 2033 | 5 | Swales | 66.6667 | 21563.3977 | 0.2 | 0.3 | 33638.9004 |  |  |  |  | 0 | 11986.2909 | 11986.2909 | 11986.2909 | 11986.2909 | 11986.2909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6174 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 14947.2164 | 0.2 | 0.3 | 23317.6576 |  |  |  |  | 0 | 10974.1401 | 10974.1401 | 10974.1401 | 10974.1401 | 10974.1401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6175 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 28942.7933 | 0.2 | 0.3 | 45150.7576 |  |  |  |  | 0 | 11824.0286 | 11824.0286 | 11824.0286 | 11824.0286 | 11824.0286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6176 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16507.0369 | 0.2 | 0.3 | 25750.9775 |  |  |  |  | 0 | 10109.1146 | 10109.1146 | 10109.1146 | 10109.1146 | 10109.1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6177 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16948.9395 | 0.2 | 0.3 | 26440.3456 |  |  |  |  | 0 | 6692.8709 | 6692.8709 | 6692.8709 | 6692.8709 | 6692.8709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6178 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16672.9386 | 0.2 | 0.3 | 26009.7842 |  |  |  |  | 0 | 119.2254 | 119.2254 | 119.2254 | 119.2254 | 119.2254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6179 | MIRAMAR | 110319 | Public | 2033 | 5 | Swales | 66.6667 | 23623.0957 | 0.2 | 0.3 | 36852.0293 |  |  |  |  | 0 | 6705.1003 | 6705.1003 | 6705.1003 | 6705.1003 | 6705.1003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6180 | MIRAMAR | 110319 | Public | 2033 | 5 | Swales | 66.6667 | 16692.3039 | 0.2 | 0.3 | 26039.994 |  |  |  |  | 0 | 5203.1992 | 5203.1992 | 5203.1992 | 5203.1992 | 5203.1992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6181 | MIRAMAR | 110319 | Public | 2033 | 5 | Swales | 66.6667 | 24304.587 | 0.2 | 0.3 | 37915.1557 |  |  |  |  | 0 | 5287.3672 | 5287.3672 | 5287.3672 | 5287.3672 | 5287.3672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6182 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16674.1115 | 0.2 | 0.3 | 26011.6139 |  |  |  |  | 0 | 5203.6904 | 5203.6904 | 5203.6904 | 5203.6904 | 5203.6904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6183 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16777.4231 | 0.2 | 0.3 | 26172.78 |  |  |  |  | 0 | 5203.1031 | 5203.1031 | 5203.1031 | 5203.1031 | 5203.1031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6184 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 9908.1885 | 0.2 | 0.3 | 15456.774 |  |  |  |  | 0 | 5203.5691 | 5203.5691 | 5203.5691 | 5203.5691 | 5203.5691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6185 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 20932.4441 | 0.2 | 0.3 | 32654.6128 |  |  |  |  | 0 | 61.5848 | 61.5848 | 61.5848 | 61.5848 | 61.5848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6186 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 6166.2243 | 0.2 | 0.3 | 9619.31 |  |  |  |  | 0 | 5142.0398 | 5142.0398 | 5142.0398 | 5142.0398 | 5142.0398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6187 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 12063.5978 | 0.2 | 0.3 | 18819.2126 |  |  |  |  | 0 | 5201.4985 | 5201.4985 | 5201.4985 | 5201.4985 | 5201.4985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6188 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16948.2085 | 0.2 | 0.3 | 26439.2052 |  |  |  |  | 0 | 5205.2312 | 5205.2312 | 5205.2312 | 5205.2312 | 5205.2312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6189 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 17498.8394 | 0.2 | 0.3 | 27298.1895 |  |  |  |  | 0 | 6507.0828 | 6507.0828 | 6507.0828 | 6507.0828 | 6507.0828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6190 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16710.7163 | 0.2 | 0.3 | 26068.7174 |  |  |  |  | 0 | 2768.26 | 2768.26 | 2768.26 | 2768.26 | 2768.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6191 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16815.8105 | 0.2 | 0.3 | 26232.6643 |  |  |  |  | 0 | 1328.9475 | 1328.9475 | 1328.9475 | 1328.9475 | 1328.9475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6192 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 14201.2153 | 0.2 | 0.3 | 22153.8958 |  |  |  |  | 0 | 6385.7632 | 6385.7632 | 6385.7632 | 6385.7632 | 6385.7632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6193 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 7544.2001 | 0.2 | 0.3 | 11768.9521 |  |  |  |  | 0 | 5202.5079 | 5202.5079 | 5202.5079 | 5202.5079 | 5202.5079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6194 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16681.5321 | 0.2 | 0.3 | 26023.1901 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6195 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 10512.8217 | 0.2 | 0.3 | 16400.0018 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6196 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 17059.967 | 0.2 | 0.3 | 26613.5485 |  |  |  |  | 0 | 5202.5135 | 5202.5135 | 5202.5135 | 5202.5135 | 5202.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6197 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 8685.8297 | 0.2 | 0.3 | 13549.8944 |  |  |  |  | 0 | 4932.8007 | 4932.8007 | 4932.8007 | 4932.8007 | 4932.8007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6198 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 36240.4413 | 0.2 | 0.3 | 56535.0885 |  |  |  |  | 0 | 6349.0405 | 6349.0405 | 6349.0405 | 6349.0405 | 6349.0405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6199 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 16677.3026 | 0.2 | 0.3 | 26016.5921 |  |  |  |  | 0 | 4445.6091 | 4445.6091 | 4445.6091 | 4445.6091 | 4445.6091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6200 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 12644.2758 | 0.2 | 0.3 | 19725.0702 |  |  |  |  | 0 | 3546.7949 | 3546.7949 | 3546.7949 | 3546.7949 | 3546.7949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6201 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 6308.0869 | 0.2 | 0.3 | 9840.6155 |  |  |  |  | 0 | 4320.291 | 4320.291 | 4320.291 | 4320.291 | 4320.291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6202 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 16669.6107 | 0.2 | 0.3 | 26004.5926 |  |  |  |  | 0 | 3793.0585 | 3793.0585 | 3793.0585 | 3793.0585 | 3793.0585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6203 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 16684.7399 | 0.2 | 0.3 | 26028.1942 |  |  |  |  | 0 | 4066.7346 | 4066.7346 | 4066.7346 | 4066.7346 | 4066.7346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6204 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 17322.973 | 0.2 | 0.3 | 27023.8379 |  |  |  |  | 0 | 4144.7018 | 4144.7018 | 4144.7018 | 4144.7018 | 4144.7018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6205 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 1512.0479 | 0.2 | 0.3 | 2358.7948 |  |  |  |  | 0 | 3818.6222 | 3818.6222 | 3818.6222 | 3818.6222 | 3818.6222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6206 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 12288.6682 | 0.2 | 0.3 | 19170.3224 |  |  |  |  | 0 | 5839.8539 | 5839.8539 | 5839.8539 | 5839.8539 | 5839.8539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6207 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 28964.0073 | 0.2 | 0.3 | 45183.8514 |  |  |  |  | 0 | 4100.3235 | 4100.3235 | 4100.3235 | 4100.3235 | 4100.3235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6208 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 4179.2585 | 0.2 | 0.3 | 6519.6433 |  |  |  |  | 0 | 2537.5794 | 2537.5794 | 2537.5794 | 2537.5794 | 2537.5794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6209 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 8121.3299 | 0.2 | 0.3 | 12669.2747 |  |  |  |  | 0 | 9761.0477 | 9761.0477 | 9761.0477 | 9761.0477 | 9761.0477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6210 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 5562.0591 | 5562.0591 | 5562.0591 | 5562.0591 | 5562.0591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6211 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 5612.5984 | 5612.5984 | 5612.5984 | 5612.5984 | 5612.5984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6212 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 16691.9498 | 0.2 | 0.3 | 26039.4417 |  |  |  |  | 0 | 5215.6398 | 5215.6398 | 5215.6398 | 5215.6398 | 5215.6398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6213 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 16746.0279 | 0.2 | 0.3 | 26123.8036 |  |  |  |  | 0 | 5647.7828 | 5647.7828 | 5647.7828 | 5647.7828 | 5647.7828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6214 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 895.9325 | 0.2 | 0.3 | 1397.6548 |  |  |  |  | 0 | 2405.3064 | 2405.3064 | 2405.3064 | 2405.3064 | 2405.3064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6215 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 19760.4027 | 0.2 | 0.3 | 30826.2283 |  |  |  |  | 0 | 10405.503 | 10405.503 | 10405.503 | 10405.503 | 10405.503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6216 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 26226.5467 | 0.2 | 0.3 | 40913.4128 |  |  |  |  | 0 | 10798.6281 | 10798.6281 | 10798.6281 | 10798.6281 | 10798.6281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6217 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 963.3263 | 0.2 | 0.3 | 1502.7891 |  |  |  |  | 0 | 6280.1294 | 6280.1294 | 6280.1294 | 6280.1294 | 6280.1294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6218 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 20929.533 | 0.2 | 0.3 | 32650.0715 |  |  |  |  | 0 | 6332.4219 | 6332.4219 | 6332.4219 | 6332.4219 | 6332.4219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6219 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 18754.0519 | 0.2 | 0.3 | 29256.3209 |  |  |  |  | 0 | 11913.7289 | 11913.7289 | 11913.7289 | 11913.7289 | 11913.7289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6220 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 12939.585 | 0.2 | 0.3 | 20185.7526 |  |  |  |  | 0 | 7873.2575 | 7873.2575 | 7873.2575 | 7873.2575 | 7873.2575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6221 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16681.1723 | 0.2 | 0.3 | 26022.6287 |  |  |  |  | 0 | 6356.0668 | 6356.0668 | 6356.0668 | 6356.0668 | 6356.0668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6222 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 7573.3574 | 7573.3574 | 7573.3574 | 7573.3574 | 7573.3574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6223 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 16680.5435 | 0.2 | 0.3 | 26021.6479 |  |  |  |  | 0 | 4472.4459 | 4472.4459 | 4472.4459 | 4472.4459 | 4472.4459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6224 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 17127.1009 | 0.2 | 0.3 | 26718.2775 |  |  |  |  | 0 | 1988.112 | 1988.112 | 1988.112 | 1988.112 | 1988.112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6225 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 17226.6977 | 0.2 | 0.3 | 26873.6485 |  |  |  |  | 0 | 117.7832 | 117.7832 | 117.7832 | 117.7832 | 117.7832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6226 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 13930.1747 | 0.2 | 0.3 | 21731.0725 |  |  |  |  | 0 | 2465.5635 | 2465.5635 | 2465.5635 | 2465.5635 | 2465.5635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6227 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 8335.0965 | 0.2 | 0.3 | 13002.7506 |  |  |  |  | 0 | 9373.7164 | 9373.7164 | 9373.7164 | 9373.7164 | 9373.7164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6228 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 15852.6824 | 0.2 | 0.3 | 24730.1845 |  |  |  |  | 0 | 8960.7198 | 8960.7198 | 8960.7198 | 8960.7198 | 8960.7198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6229 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 22538.9941 | 0.2 | 0.3 | 35160.8307 |  |  |  |  | 0 | 9745.1438 | 9745.1438 | 9745.1438 | 9745.1438 | 9745.1438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6230 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 16745.9116 | 0.2 | 0.3 | 26123.6221 |  |  |  |  | 0 | 5202.1153 | 5202.1153 | 5202.1153 | 5202.1153 | 5202.1153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6231 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 25823.592 | 0.2 | 0.3 | 40284.8035 |  |  |  |  | 0 | 8514.5604 | 8514.5604 | 8514.5604 | 8514.5604 | 8514.5604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6232 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 3183.3169 | 0.2 | 0.3 | 4965.9744 |  |  |  |  | 0 | 9779.5658 | 9779.5658 | 9779.5658 | 9779.5658 | 9779.5658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6233 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 13929.9672 | 0.2 | 0.3 | 21730.7488 |  |  |  |  | 0 | 8089.0371 | 8089.0371 | 8089.0371 | 8089.0371 | 8089.0371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6234 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 13140.0849 | 0.2 | 0.3 | 20498.5325 |  |  |  |  | 0 | 5299.0237 | 5299.0237 | 5299.0237 | 5299.0237 | 5299.0237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6235 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16725.6229 | 0.2 | 0.3 | 26091.9718 |  |  |  |  | 0 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6236 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 14655.0239 | 0.2 | 0.3 | 22861.8372 |  |  |  |  | 0 | 5205.5238 | 5205.5238 | 5205.5238 | 5205.5238 | 5205.5238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6237 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 2041.3292 | 0.2 | 0.3 | 3184.4736 |  |  |  |  | 0 | 272.0223 | 272.0223 | 272.0223 | 272.0223 | 272.0223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6238 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 15369.6498 | 0.2 | 0.3 | 23976.6537 |  |  |  |  | 0 | 5201.2538 | 5201.2538 | 5201.2538 | 5201.2538 | 5201.2538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6239 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 24020.0897 | 0.2 | 0.3 | 37471.34 |  |  |  |  | 0 | 2457.3465 | 2457.3465 | 2457.3465 | 2457.3465 | 2457.3465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6240 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 15594.6597 | 0.2 | 0.3 | 24327.6691 |  |  |  |  | 0 | 5446.1543 | 5446.1543 | 5446.1543 | 5446.1543 | 5446.1543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6241 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 20438.9261 | 0.2 | 0.3 | 31884.7247 |  |  |  |  | 0 | 2609.178 | 2609.178 | 2609.178 | 2609.178 | 2609.178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6242 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8591 | 0.2 | 0.3 | 26000.3002 |  |  |  |  | 0 | 5257.8887 | 5257.8887 | 5257.8887 | 5257.8887 | 5257.8887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6243 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16666.9806 | 0.2 | 0.3 | 26000.4897 |  |  |  |  | 0 | 2973.9783 | 2973.9783 | 2973.9783 | 2973.9783 | 2973.9783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6244 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 28593.3331 | 0.2 | 0.3 | 44605.5996 |  |  |  |  | 0 | 4911.2625 | 4911.2625 | 4911.2625 | 4911.2625 | 4911.2625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6245 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 2351.6697 | 2351.6697 | 2351.6697 | 2351.6697 | 2351.6697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6246 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 28481.0821 | 0.2 | 0.3 | 44430.488 |  |  |  |  | 0 | 6004.6225 | 6004.6225 | 6004.6225 | 6004.6225 | 6004.6225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6247 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 26215.1768 | 0.2 | 0.3 | 40895.6758 |  |  |  |  | 0 | 2792.9838 | 2792.9838 | 2792.9838 | 2792.9838 | 2792.9838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6248 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 13664.1764 | 0.2 | 0.3 | 21316.1152 |  |  |  |  | 0 | 4657.6554 | 4657.6554 | 4657.6554 | 4657.6554 | 4657.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6249 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16667.6985 | 0.2 | 0.3 | 26001.6097 |  |  |  |  | 0 | 5783.6165 | 5783.6165 | 5783.6165 | 5783.6165 | 5783.6165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6250 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0617 | 0.2 | 0.3 | 26000.6163 |  |  |  |  | 0 | 5322.4728 | 5322.4728 | 5322.4728 | 5322.4728 | 5322.4728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6251 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 24612.1885 | 0.2 | 0.3 | 38395.0141 |  |  |  |  | 0 | 119.3766 | 119.3766 | 119.3766 | 119.3766 | 119.3766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6252 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 14599.6021 | 0.2 | 0.3 | 22775.3793 |  |  |  |  | 0 | 10482.7119 | 10482.7119 | 10482.7119 | 10482.7119 | 10482.7119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6253 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 6259.8803 | 0.2 | 0.3 | 9765.4133 |  |  |  |  | 0 | 6896.3043 | 6896.3043 | 6896.3043 | 6896.3043 | 6896.3043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6254 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 20523.6063 | 0.2 | 0.3 | 32016.8259 |  |  |  |  | 0 | 5377.4822 | 5377.4822 | 5377.4822 | 5377.4822 | 5377.4822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6255 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 18742.0699 | 0.2 | 0.3 | 29237.6291 |  |  |  |  | 0 | 5385.4832 | 5385.4832 | 5385.4832 | 5385.4832 | 5385.4832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6256 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 21681.9838 | 0.2 | 0.3 | 33823.8947 |  |  |  |  | 0 | 8856.8268 | 8856.8268 | 8856.8268 | 8856.8268 | 8856.8268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6257 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 7956.1409 | 0.2 | 0.3 | 12411.5798 |  |  |  |  | 0 | 3775.8086 | 3775.8086 | 3775.8086 | 3775.8086 | 3775.8086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6258 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 16675.9723 | 0.2 | 0.3 | 26014.5168 |  |  |  |  | 0 | 7300.8892 | 7300.8892 | 7300.8892 | 7300.8892 | 7300.8892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6259 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 16675.9435 | 0.2 | 0.3 | 26014.4718 |  |  |  |  | 0 | 10374.2962 | 10374.2962 | 10374.2962 | 10374.2962 | 10374.2962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6260 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 18265.6386 | 0.2 | 0.3 | 28494.3962 |  |  |  |  | 0 | 10412.6139 | 10412.6139 | 10412.6139 | 10412.6139 | 10412.6139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6261 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 394.0205 | 0.2 | 0.3 | 614.6719 |  |  |  |  | 0 | 9775.8577 | 9775.8577 | 9775.8577 | 9775.8577 | 9775.8577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6262 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 16844.0667 | 0.2 | 0.3 | 26276.7441 |  |  |  |  | 0 | 6055.7665 | 6055.7665 | 6055.7665 | 6055.7665 | 6055.7665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6263 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 17796.8062 | 0.2 | 0.3 | 27763.0177 |  |  |  |  | 0 | 5088.969 | 5088.969 | 5088.969 | 5088.969 | 5088.969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6264 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 17995.3671 | 0.2 | 0.3 | 28072.7727 |  |  |  |  | 0 | 2741.2156 | 2741.2156 | 2741.2156 | 2741.2156 | 2741.2156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6265 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 5600.8134 | 0.2 | 0.3 | 8737.2689 |  |  |  |  | 0 | 5806.2458 | 5806.2458 | 5806.2458 | 5806.2458 | 5806.2458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6266 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 26483.3828 | 0.2 | 0.3 | 41314.0772 |  |  |  |  | 0 | 5203.7924 | 5203.7924 | 5203.7924 | 5203.7924 | 5203.7924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6267 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 20822.2257 | 0.2 | 0.3 | 32482.672 |  |  |  |  | 0 | 5200.0102 | 5200.0102 | 5200.0102 | 5200.0102 | 5200.0102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6268 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 25232.6557 | 0.2 | 0.3 | 39362.9429 |  |  |  |  | 0 | 4147.7358 | 4147.7358 | 4147.7358 | 4147.7358 | 4147.7358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6269 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 12648.998 | 0.2 | 0.3 | 19732.4369 |  |  |  |  | 0 | 7601.5407 | 7601.5407 | 7601.5407 | 7601.5407 | 7601.5407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6270 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 11792.9594 | 0.2 | 0.3 | 18397.0167 |  |  |  |  | 0 | 1474.4663 | 1474.4663 | 1474.4663 | 1474.4663 | 1474.4663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6271 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 17114.5278 | 0.2 | 0.3 | 26698.6634 |  |  |  |  | 0 | 6444.7855 | 6444.7855 | 6444.7855 | 6444.7855 | 6444.7855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6272 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 11380.2042 | 0.2 | 0.3 | 17753.1186 |  |  |  |  | 0 | 5979.5738 | 5979.5738 | 5979.5738 | 5979.5738 | 5979.5738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6273 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 9186.6952 | 0.2 | 0.3 | 14331.2445 |  |  |  |  | 0 | 2005.3597 | 2005.3597 | 2005.3597 | 2005.3597 | 2005.3597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6274 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6623 |  |  |  |  | 0 | 4233.1463 | 4233.1463 | 4233.1463 | 4233.1463 | 4233.1463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6275 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 26241.1313 | 0.2 | 0.3 | 40936.1648 |  |  |  |  | 0 | 4486.4571 | 4486.4571 | 4486.4571 | 4486.4571 | 4486.4571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6276 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 31087.1603 | 0.2 | 0.3 | 48495.97 |  |  |  |  | 0 | 4568.7472 | 4568.7472 | 4568.7472 | 4568.7472 | 4568.7472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6277 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16677.2328 | 0.2 | 0.3 | 26016.4832 |  |  |  |  | 0 | 2804.3263 | 2804.3263 | 2804.3263 | 2804.3263 | 2804.3263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6278 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 6536.2975 | 0.2 | 0.3 | 10196.624 |  |  |  |  | 0 | 5628.7045 | 5628.7045 | 5628.7045 | 5628.7045 | 5628.7045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6279 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 16661.4053 | 0.2 | 0.3 | 25991.7923 |  |  |  |  | 0 | 4793.0892 | 4793.0892 | 4793.0892 | 4793.0892 | 4793.0892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6280 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 16683.5351 | 0.2 | 0.3 | 26026.3148 |  |  |  |  | 0 | 5740.6618 | 5740.6618 | 5740.6618 | 5740.6618 | 5740.6618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6281 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 16671.2479 | 0.2 | 0.3 | 26007.1467 |  |  |  |  | 0 | 14179.1498 | 14179.1498 | 14179.1498 | 14179.1498 | 14179.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6282 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 11478.672 | 0.2 | 0.3 | 17906.7283 |  |  |  |  | 0 | 10409.546 | 10409.546 | 10409.546 | 10409.546 | 10409.546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6283 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 17879.544 | 0.2 | 0.3 | 27892.0886 |  |  |  |  | 0 | 8211.9491 | 8211.9491 | 8211.9491 | 8211.9491 | 8211.9491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6284 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 16960.4717 | 0.2 | 0.3 | 26458.3358 |  |  |  |  | 0 | 11043.3177 | 11043.3177 | 11043.3177 | 11043.3177 | 11043.3177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6285 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 24419.0623 | 0.2 | 0.3 | 38093.7372 |  |  |  |  | 0 | 5205.9503 | 5205.9503 | 5205.9503 | 5205.9503 | 5205.9503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6286 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 8919.8437 | 0.2 | 0.3 | 13914.9561 |  |  |  |  | 0 | 5205.0535 | 5205.0535 | 5205.0535 | 5205.0535 | 5205.0535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6287 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 8239.8243 | 0.2 | 0.3 | 12854.126 |  |  |  |  | 0 | 9186.4445 | 9186.4445 | 9186.4445 | 9186.4445 | 9186.4445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6288 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 7677.5455 | 0.2 | 0.3 | 11976.9709 |  |  |  |  | 0 | 5732.7226 | 5732.7226 | 5732.7226 | 5732.7226 | 5732.7226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6289 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 18185.3047 | 0.2 | 0.3 | 28369.0754 |  |  |  |  | 0 | 9982.0375 | 9982.0375 | 9982.0375 | 9982.0375 | 9982.0375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6290 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 4611.9487 | 0.2 | 0.3 | 7194.6399 |  |  |  |  | 0 | 10409.2562 | 10409.2562 | 10409.2562 | 10409.2562 | 10409.2562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6291 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 8554.7335 | 0.2 | 0.3 | 13345.3842 |  |  |  |  | 0 | 5203.9635 | 5203.9635 | 5203.9635 | 5203.9635 | 5203.9635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6292 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 27054.8419 | 0.2 | 0.3 | 42205.5534 |  |  |  |  | 0 | 5203.9561 | 5203.9561 | 5203.9561 | 5203.9561 | 5203.9561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6293 | MIRAMAR | 110344 | Private | 2036 | 5 | Swales | 66.6667 | 12839.1425 | 0.2 | 0.3 | 20029.0622 |  |  |  |  | 0 | 9801.9228 | 9801.9228 | 9801.9228 | 9801.9228 | 9801.9228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6294 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 16870.6757 | 0.2 | 0.3 | 26318.2541 |  |  |  |  | 0 | 5252.004 | 5252.004 | 5252.004 | 5252.004 | 5252.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6295 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 22768.5719 | 0.2 | 0.3 | 35518.9721 |  |  |  |  | 0 | 5202.9444 | 5202.9444 | 5202.9444 | 5202.9444 | 5202.9444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6296 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 22123.7294 | 0.2 | 0.3 | 34513.0179 |  |  |  |  | 0 | 9146.1272 | 9146.1272 | 9146.1272 | 9146.1272 | 9146.1272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6297 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 21166.5628 | 0.2 | 0.3 | 33019.838 |  |  |  |  | 0 | 580.9816 | 580.9816 | 580.9816 | 580.9816 | 580.9816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6298 | MIRAMAR | 110346 | Private | 2036 | 5 | Swales | 66.6667 | 7292.8845 | 0.2 | 0.3 | 11376.8999 |  |  |  |  | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6299 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 8803.94 | 0.2 | 0.3 | 13734.1464 |  |  |  |  | 0 | 8621.0378 | 8621.0378 | 8621.0378 | 8621.0378 | 8621.0378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6300 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 19763.0732 | 0.2 | 0.3 | 30830.3942 |  |  |  |  | 0 | 5203.6718 | 5203.6718 | 5203.6718 | 5203.6718 | 5203.6718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6301 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 17533.0421 | 0.2 | 0.3 | 27351.5457 |  |  |  |  | 0 | 5204.7405 | 5204.7405 | 5204.7405 | 5204.7405 | 5204.7405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6302 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 23740.1971 | 0.2 | 0.3 | 37034.7074 |  |  |  |  | 0 | 8921.2268 | 8921.2268 | 8921.2268 | 8921.2268 | 8921.2268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6303 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 10522.9157 | 0.2 | 0.3 | 16415.7485 |  |  |  |  | 0 | 1832.9947 | 1832.9947 | 1832.9947 | 1832.9947 | 1832.9947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6304 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16691.4256 | 0.2 | 0.3 | 26038.6239 |  |  |  |  | 0 | 3795.9771 | 3795.9771 | 3795.9771 | 3795.9771 | 3795.9771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6305 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 24322.1523 | 0.2 | 0.3 | 37942.5575 |  |  |  |  | 0 | 6886.8396 | 6886.8396 | 6886.8396 | 6886.8396 | 6886.8396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6306 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 18797.8567 | 0.2 | 0.3 | 29324.6565 |  |  |  |  | 0 | 1159.9006 | 1159.9006 | 1159.9006 | 1159.9006 | 1159.9006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6307 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 6878.7672 | 6878.7672 | 6878.7672 | 6878.7672 | 6878.7672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6308 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 26890.406 | 0.2 | 0.3 | 41949.0334 |  |  |  |  | 0 | 1212.3199 | 1212.3199 | 1212.3199 | 1212.3199 | 1212.3199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6309 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 27930.0956 | 0.2 | 0.3 | 43570.9491 |  |  |  |  | 0 | 6771.8076 | 6771.8076 | 6771.8076 | 6771.8076 | 6771.8076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6310 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 8344.8161 | 0.2 | 0.3 | 13017.9131 |  |  |  |  | 0 | 2132.9832 | 2132.9832 | 2132.9832 | 2132.9832 | 2132.9832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6311 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 20023.8127 | 0.2 | 0.3 | 31237.1479 |  |  |  |  | 0 | 9490.7818 | 9490.7818 | 9490.7818 | 9490.7818 | 9490.7818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6312 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 18963.3783 | 0.2 | 0.3 | 29582.8702 |  |  |  |  | 0 | 7801.571 | 7801.571 | 7801.571 | 7801.571 | 7801.571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6313 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 23196.8293 | 0.2 | 0.3 | 36187.0538 |  |  |  |  | 0 | 7864.5426 | 7864.5426 | 7864.5426 | 7864.5426 | 7864.5426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6314 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 16638.1019 | 0.2 | 0.3 | 25955.4389 |  |  |  |  | 0 | 1226.5813 | 1226.5813 | 1226.5813 | 1226.5813 | 1226.5813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6315 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 19681.295 | 0.2 | 0.3 | 30702.8202 |  |  |  |  | 0 | 5444.0686 | 5444.0686 | 5444.0686 | 5444.0686 | 5444.0686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6316 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 23991.4626 | 0.2 | 0.3 | 37426.6817 |  |  |  |  | 0 | 5205.8697 | 5205.8697 | 5205.8697 | 5205.8697 | 5205.8697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6317 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 11856.038 | 0.2 | 0.3 | 18495.4193 |  |  |  |  | 0 | 5203.5329 | 5203.5329 | 5203.5329 | 5203.5329 | 5203.5329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6318 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 17184.4044 | 0.2 | 0.3 | 26807.6709 |  |  |  |  | 0 | 10435.9056 | 10435.9056 | 10435.9056 | 10435.9056 | 10435.9056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6319 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 17993.129 | 0.2 | 0.3 | 28069.2812 |  |  |  |  | 0 | 5228.6914 | 5228.6914 | 5228.6914 | 5228.6914 | 5228.6914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6320 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 33064.4776 | 0.2 | 0.3 | 51580.5851 |  |  |  |  | 0 | 12403.3389 | 12403.3389 | 12403.3389 | 12403.3389 | 12403.3389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6321 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 14789.0339 | 0.2 | 0.3 | 23070.8928 |  |  |  |  | 0 | 12112.385 | 12112.385 | 12112.385 | 12112.385 | 12112.385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6322 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 26296.5604 | 0.2 | 0.3 | 41022.6342 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6323 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 28292.8531 | 0.2 | 0.3 | 44136.8509 |  |  |  |  | 0 | 5196.1406 | 5196.1406 | 5196.1406 | 5196.1406 | 5196.1406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6324 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 28549.6716 | 0.2 | 0.3 | 44537.4877 |  |  |  |  | 0 | 7595.4721 | 7595.4721 | 7595.4721 | 7595.4721 | 7595.4721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6325 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.9419 | 0.2 | 0.3 | 26000.4293 |  |  |  |  | 0 | 1812.5493 | 1812.5493 | 1812.5493 | 1812.5493 | 1812.5493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6326 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 8306.4661 | 8306.4661 | 8306.4661 | 8306.4661 | 8306.4661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6327 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 9783.4906 | 9783.4906 | 9783.4906 | 9783.4906 | 9783.4906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6328 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 26932.5959 | 0.2 | 0.3 | 42014.8497 |  |  |  |  | 0 | 5205.5765 | 5205.5765 | 5205.5765 | 5205.5765 | 5205.5765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6329 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 6490.1863 | 0.2 | 0.3 | 10124.6907 |  |  |  |  | 0 | 5207.2845 | 5207.2845 | 5207.2845 | 5207.2845 | 5207.2845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6330 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 39237.7992 | 0.2 | 0.3 | 61210.9668 |  |  |  |  | 0 | 9779.6002 | 9779.6002 | 9779.6002 | 9779.6002 | 9779.6002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6331 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 33261.6161 | 0.2 | 0.3 | 51888.1211 |  |  |  |  | 0 | 7905.9518 | 7905.9518 | 7905.9518 | 7905.9518 | 7905.9518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6332 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 33397.3485 | 0.2 | 0.3 | 52099.8637 |  |  |  |  | 0 | 5205.865 | 5205.865 | 5205.865 | 5205.865 | 5205.865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6333 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 32542.4671 | 0.2 | 0.3 | 50766.2486 |  |  |  |  | 0 | 5203.0263 | 5203.0263 | 5203.0263 | 5203.0263 | 5203.0263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6334 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16391.0427 | 0.2 | 0.3 | 25570.0266 |  |  |  |  | 0 | 4947.3185 | 4947.3185 | 4947.3185 | 4947.3185 | 4947.3185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6335 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16728.3911 | 0.2 | 0.3 | 26096.2901 |  |  |  |  | 0 | 5565.6842 | 5565.6842 | 5565.6842 | 5565.6842 | 5565.6842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6336 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 25920.7445 | 0.2 | 0.3 | 40436.3615 |  |  |  |  | 0 | 5204.0763 | 5204.0763 | 5204.0763 | 5204.0763 | 5204.0763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6337 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 25684.0333 | 0.2 | 0.3 | 40067.0919 |  |  |  |  | 0 | 9161.5237 | 9161.5237 | 9161.5237 | 9161.5237 | 9161.5237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6338 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 19613.1449 | 0.2 | 0.3 | 30596.506 |  |  |  |  | 0 | 11267.7974 | 11267.7974 | 11267.7974 | 11267.7974 | 11267.7974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6339 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 661.8717 | 0.2 | 0.3 | 1032.5199 |  |  |  |  | 0 | 1765.7065 | 1765.7065 | 1765.7065 | 1765.7065 | 1765.7065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6340 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 18369.4896 | 0.2 | 0.3 | 28656.4038 |  |  |  |  | 0 | 6455.8648 | 6455.8648 | 6455.8648 | 6455.8648 | 6455.8648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6341 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 8904.6395 | 0.2 | 0.3 | 13891.2376 |  |  |  |  | 0 | 1430.0786 | 1430.0786 | 1430.0786 | 1430.0786 | 1430.0786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6342 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 20996.9247 | 0.2 | 0.3 | 32755.2026 |  |  |  |  | 0 | 6653.2123 | 6653.2123 | 6653.2123 | 6653.2123 | 6653.2123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6343 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 28474.0545 | 0.2 | 0.3 | 44419.525 |  |  |  |  | 0 | 1327.0969 | 1327.0969 | 1327.0969 | 1327.0969 | 1327.0969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6344 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 21457.2209 | 0.2 | 0.3 | 33473.2646 |  |  |  |  | 0 | 4437.5368 | 4437.5368 | 4437.5368 | 4437.5368 | 4437.5368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6345 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 1185.6099 | 0.2 | 0.3 | 1849.5515 |  |  |  |  | 0 | 9335.6535 | 9335.6535 | 9335.6535 | 9335.6535 | 9335.6535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6346 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 4554.8501 | 0.2 | 0.3 | 7105.5661 |  |  |  |  | 0 | 4416.2554 | 4416.2554 | 4416.2554 | 4416.2554 | 4416.2554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6347 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 5.4228 | 0.2 | 0.3 | 8.4596 |  |  |  |  | 0 | 4460.6215 | 4460.6215 | 4460.6215 | 4460.6215 | 4460.6215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6348 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 13831.7723 | 0.2 | 0.3 | 21577.5647 |  |  |  |  | 0 | 5431.8138 | 5431.8138 | 5431.8138 | 5431.8138 | 5431.8138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6349 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 27372.9145 | 0.2 | 0.3 | 42701.7467 |  |  |  |  | 0 | 2215.5215 | 2215.5215 | 2215.5215 | 2215.5215 | 2215.5215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6350 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 7200.2057 | 7200.2057 | 7200.2057 | 7200.2057 | 7200.2057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6351 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16676.5179 | 0.2 | 0.3 | 26015.368 |  |  |  |  | 0 | 5464.4097 | 5464.4097 | 5464.4097 | 5464.4097 | 5464.4097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6352 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16680.3195 | 0.2 | 0.3 | 26021.2985 |  |  |  |  | 0 | 5205.6944 | 5205.6944 | 5205.6944 | 5205.6944 | 5205.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6353 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 8638.6749 | 0.2 | 0.3 | 13476.3329 |  |  |  |  | 0 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6354 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 15536.6865 | 0.2 | 0.3 | 24237.2309 |  |  |  |  | 0 | 6473.5282 | 6473.5282 | 6473.5282 | 6473.5282 | 6473.5282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6355 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 17166.3329 | 0.2 | 0.3 | 26779.4793 |  |  |  |  | 0 | 5201.7143 | 5201.7143 | 5201.7143 | 5201.7143 | 5201.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6356 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0254 | 0.2 | 0.3 | 26000.5596 |  |  |  |  | 0 | 5621.8325 | 5621.8325 | 5621.8325 | 5621.8325 | 5621.8325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6357 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 19804.6629 | 0.2 | 0.3 | 30895.2741 |  |  |  |  | 0 | 2192.5035 | 2192.5035 | 2192.5035 | 2192.5035 | 2192.5035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6358 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 7580.4753 | 7580.4753 | 7580.4753 | 7580.4753 | 7580.4753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6359 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 16668.2404 | 0.2 | 0.3 | 26002.455 |  |  |  |  | 0 | 8787.0769 | 8787.0769 | 8787.0769 | 8787.0769 | 8787.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6360 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 16807.3255 | 0.2 | 0.3 | 26219.4278 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6361 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 38266.5653 | 0.2 | 0.3 | 59695.8419 |  |  |  |  | 0 | 9097.6347 | 9097.6347 | 9097.6347 | 9097.6347 | 9097.6347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6362 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 16668.8335 | 0.2 | 0.3 | 26003.3802 |  |  |  |  | 0 | 17.5708 | 17.5708 | 17.5708 | 17.5708 | 17.5708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6363 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 17375.4684 | 0.2 | 0.3 | 27105.7307 |  |  |  |  | 0 | 5296.9972 | 5296.9972 | 5296.9972 | 5296.9972 | 5296.9972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6364 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 22886.1493 | 0.2 | 0.3 | 35702.393 |  |  |  |  | 0 | 5204.7756 | 5204.7756 | 5204.7756 | 5204.7756 | 5204.7756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6365 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 35256.4084 | 0.2 | 0.3 | 54999.9971 |  |  |  |  | 0 | 9737.6017 | 9737.6017 | 9737.6017 | 9737.6017 | 9737.6017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6366 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 289.1316 | 0.2 | 0.3 | 451.0453 |  |  |  |  | 0 | 3486.7504 | 3486.7504 | 3486.7504 | 3486.7504 | 3486.7504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6367 | MIRAMAR | 110349 | Private | 2036 | 5 | Swales | 66.6667 | 6396.8561 | 0.2 | 0.3 | 9979.0955 |  |  |  |  | 0 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6368 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16832.8683 | 0.2 | 0.3 | 26259.2745 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6369 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16764.8677 | 0.2 | 0.3 | 26153.1936 |  |  |  |  | 0 | 5204.7569 | 5204.7569 | 5204.7569 | 5204.7569 | 5204.7569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6370 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16768.6178 | 0.2 | 0.3 | 26159.0438 |  |  |  |  | 0 | 6875.1124 | 6875.1124 | 6875.1124 | 6875.1124 | 6875.1124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6371 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 12415.0632 | 0.2 | 0.3 | 19367.4986 |  |  |  |  | 0 | 5291.0054 | 5291.0054 | 5291.0054 | 5291.0054 | 5291.0054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6372 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 8804.5819 | 0.2 | 0.3 | 13735.1477 |  |  |  |  | 0 | 2547.0352 | 2547.0352 | 2547.0352 | 2547.0352 | 2547.0352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6373 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16696.8903 | 0.2 | 0.3 | 26047.1489 |  |  |  |  | 0 | 5561.8222 | 5561.8222 | 5561.8222 | 5561.8222 | 5561.8222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6374 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 30643.7536 | 0.2 | 0.3 | 47804.2556 |  |  |  |  | 0 | 2279.4684 | 2279.4684 | 2279.4684 | 2279.4684 | 2279.4684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6375 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 8135.1061 | 0.2 | 0.3 | 12690.7655 |  |  |  |  | 0 | 5745.9112 | 5745.9112 | 5745.9112 | 5745.9112 | 5745.9112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6376 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4499 | 0.2 | 0.3 | 26019.9419 |  |  |  |  | 0 | 2129.7349 | 2129.7349 | 2129.7349 | 2129.7349 | 2129.7349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6377 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 27672.6696 | 0.2 | 0.3 | 43169.3646 |  |  |  |  | 0 | 10771.0678 | 10771.0678 | 10771.0678 | 10771.0678 | 10771.0678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6378 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 29359.6639 | 0.2 | 0.3 | 45801.0756 |  |  |  |  | 0 | 6338.2315 | 6338.2315 | 6338.2315 | 6338.2315 | 6338.2315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6379 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9105 | 0.2 | 0.3 | 26023.7804 |  |  |  |  | 0 | 4519.7598 | 4519.7598 | 4519.7598 | 4519.7598 | 4519.7598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6380 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 12600.5207 | 0.2 | 0.3 | 19656.8123 |  |  |  |  | 0 | 5839.6551 | 5839.6551 | 5839.6551 | 5839.6551 | 5839.6551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6381 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 18002.6149 | 0.2 | 0.3 | 28084.0792 |  |  |  |  | 0 | 4291.8945 | 4291.8945 | 4291.8945 | 4291.8945 | 4291.8945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6382 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 26497.771 | 0.2 | 0.3 | 41336.5228 |  |  |  |  | 0 | 5204.713 | 5204.713 | 5204.713 | 5204.713 | 5204.713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6383 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 150.0605 | 0.2 | 0.3 | 234.0943 |  |  |  |  | 0 | 5204.8101 | 5204.8101 | 5204.8101 | 5204.8101 | 5204.8101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6384 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 10956.6539 | 0.2 | 0.3 | 17092.3801 |  |  |  |  | 0 | 9783.5687 | 9783.5687 | 9783.5687 | 9783.5687 | 9783.5687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6385 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 19286.3084 | 0.2 | 0.3 | 30086.6411 |  |  |  |  | 0 | 7471.1495 | 7471.1495 | 7471.1495 | 7471.1495 | 7471.1495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6386 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 5767.466 | 0.2 | 0.3 | 8997.247 |  |  |  |  | 0 | 2296.8831 | 2296.8831 | 2296.8831 | 2296.8831 | 2296.8831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6387 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 5201.7303 | 5201.7303 | 5201.7303 | 5201.7303 | 5201.7303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6388 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 20447.6199 | 0.2 | 0.3 | 31898.287 |  |  |  |  | 0 | 6257.4805 | 6257.4805 | 6257.4805 | 6257.4805 | 6257.4805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6389 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 23857.6967 | 0.2 | 0.3 | 37218.0068 |  |  |  |  | 0 | 2290.2706 | 2290.2706 | 2290.2706 | 2290.2706 | 2290.2706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6390 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 17122.6785 | 0.2 | 0.3 | 26711.3784 |  |  |  |  | 0 | 5202.6268 | 5202.6268 | 5202.6268 | 5202.6268 | 5202.6268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6391 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 22062.9371 | 0.2 | 0.3 | 34418.1819 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6392 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 1979.4029 | 0.2 | 0.3 | 3087.8686 |  |  |  |  | 0 | 5202.7452 | 5202.7452 | 5202.7452 | 5202.7452 | 5202.7452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6393 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 11141.7783 | 0.2 | 0.3 | 17381.1742 |  |  |  |  | 0 | 3923.2458 | 3923.2458 | 3923.2458 | 3923.2458 | 3923.2458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6394 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16667.3567 | 0.2 | 0.3 | 26001.0765 |  |  |  |  | 0 | 6334.9737 | 6334.9737 | 6334.9737 | 6334.9737 | 6334.9737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6395 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.3266 | 0.2 | 0.3 | 25999.4695 |  |  |  |  | 0 | 6575.1365 | 6575.1365 | 6575.1365 | 6575.1365 | 6575.1365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6396 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 1718.0216 | 1718.0216 | 1718.0216 | 1718.0216 | 1718.0216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6397 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 30998.8628 | 0.2 | 0.3 | 48358.226 |  |  |  |  | 0 | 4119.2354 | 4119.2354 | 4119.2354 | 4119.2354 | 4119.2354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6398 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 10138.4482 | 0.2 | 0.3 | 15815.9792 |  |  |  |  | 0 | 3773.5176 | 3773.5176 | 3773.5176 | 3773.5176 | 3773.5176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6399 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 23531.2433 | 0.2 | 0.3 | 36708.7395 |  |  |  |  | 0 | 4402.5548 | 4402.5548 | 4402.5548 | 4402.5548 | 4402.5548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6400 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 17887.037 | 0.2 | 0.3 | 27903.7777 |  |  |  |  | 0 | 3468.0992 | 3468.0992 | 3468.0992 | 3468.0992 | 3468.0992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6401 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 14475.7555 | 0.2 | 0.3 | 22582.1785 |  |  |  |  | 0 | 4638.1332 | 4638.1332 | 4638.1332 | 4638.1332 | 4638.1332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6402 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 27030.9929 | 0.2 | 0.3 | 42168.349 |  |  |  |  | 0 | 4812.5575 | 4812.5575 | 4812.5575 | 4812.5575 | 4812.5575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6403 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16674.5465 | 0.2 | 0.3 | 26012.2926 |  |  |  |  | 0 | 8324.0663 | 8324.0663 | 8324.0663 | 8324.0663 | 8324.0663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6404 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 14791.2221 | 0.2 | 0.3 | 23074.3064 |  |  |  |  | 0 | 7901.2769 | 7901.2769 | 7901.2769 | 7901.2769 | 7901.2769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6405 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 11078.1043 | 0.2 | 0.3 | 17281.8427 |  |  |  |  | 0 | 7925.3408 | 7925.3408 | 7925.3408 | 7925.3408 | 7925.3408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6406 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 15296.4229 | 0.2 | 0.3 | 23862.4197 |  |  |  |  | 0 | 4047.1371 | 4047.1371 | 4047.1371 | 4047.1371 | 4047.1371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6407 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 25272.2599 | 0.2 | 0.3 | 39424.7255 |  |  |  |  | 0 | 5823.3009 | 5823.3009 | 5823.3009 | 5823.3009 | 5823.3009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6408 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 485.6814 | 0.2 | 0.3 | 757.663 |  |  |  |  | 0 | 4528.1806 | 4528.1806 | 4528.1806 | 4528.1806 | 4528.1806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6409 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 3838.5972 | 0.2 | 0.3 | 5988.2116 |  |  |  |  | 0 | 5843.242 | 5843.242 | 5843.242 | 5843.242 | 5843.242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6410 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 20402.7159 | 0.2 | 0.3 | 31828.2368 |  |  |  |  | 0 | 3209.9975 | 3209.9975 | 3209.9975 | 3209.9975 | 3209.9975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6411 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 20121.5825 | 0.2 | 0.3 | 31389.6686 |  |  |  |  | 0 | 2621.8672 | 2621.8672 | 2621.8672 | 2621.8672 | 2621.8672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6412 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 22471.9897 | 0.2 | 0.3 | 35056.304 |  |  |  |  | 0 | 4709.6754 | 4709.6754 | 4709.6754 | 4709.6754 | 4709.6754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6413 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 11254.6077 | 0.2 | 0.3 | 17557.1881 |  |  |  |  | 0 | 3621.8692 | 3621.8692 | 3621.8692 | 3621.8692 | 3621.8692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6414 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 23323.482 | 0.2 | 0.3 | 36384.6319 |  |  |  |  | 0 | 1202.0858 | 1202.0858 | 1202.0858 | 1202.0858 | 1202.0858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6415 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16740.9582 | 0.2 | 0.3 | 26115.8948 |  |  |  |  | 0 | 834.8446 | 834.8446 | 834.8446 | 834.8446 | 834.8446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6416 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16680.4943 | 0.2 | 0.3 | 26021.5711 |  |  |  |  | 0 | 5503.8413 | 5503.8413 | 5503.8413 | 5503.8413 | 5503.8413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6417 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 27488.4625 | 0.2 | 0.3 | 42882.0016 |  |  |  |  | 0 | 5813.6683 | 5813.6683 | 5813.6683 | 5813.6683 | 5813.6683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6418 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 21497.043 | 0.2 | 0.3 | 33535.3871 |  |  |  |  | 0 | 5209.7029 | 5209.7029 | 5209.7029 | 5209.7029 | 5209.7029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6419 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 17158.4621 | 0.2 | 0.3 | 26767.2008 |  |  |  |  | 0 | 6834.469 | 6834.469 | 6834.469 | 6834.469 | 6834.469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6420 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 506.0031 | 506.0031 | 506.0031 | 506.0031 | 506.0031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6421 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 17037.0268 | 0.2 | 0.3 | 26577.7618 |  |  |  |  | 0 | 4896.1996 | 4896.1996 | 4896.1996 | 4896.1996 | 4896.1996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6422 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 32030.3197 | 0.2 | 0.3 | 49967.2987 |  |  |  |  | 0 | 5233.6254 | 5233.6254 | 5233.6254 | 5233.6254 | 5233.6254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6423 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16676.1823 | 0.2 | 0.3 | 26014.8443 |  |  |  |  | 0 | 9781.5617 | 9781.5617 | 9781.5617 | 9781.5617 | 9781.5617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6424 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16755.2454 | 0.2 | 0.3 | 26138.1828 |  |  |  |  | 0 | 8665.9636 | 8665.9636 | 8665.9636 | 8665.9636 | 8665.9636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6425 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16770.6017 | 0.2 | 0.3 | 26162.1386 |  |  |  |  | 0 | 6780.4708 | 6780.4708 | 6780.4708 | 6780.4708 | 6780.4708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6426 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 25203.2361 | 0.2 | 0.3 | 39317.0484 |  |  |  |  | 0 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6427 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 28137.7253 | 0.2 | 0.3 | 43894.8514 |  |  |  |  | 0 | 4260.8188 | 4260.8188 | 4260.8188 | 4260.8188 | 4260.8188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6428 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 15666.4746 | 0.2 | 0.3 | 24439.7004 |  |  |  |  | 0 | 13801.4159 | 13801.4159 | 13801.4159 | 13801.4159 | 13801.4159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6429 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 1725.8959 | 0.2 | 0.3 | 2692.3976 |  |  |  |  | 0 | 15600.1935 | 15600.1935 | 15600.1935 | 15600.1935 | 15600.1935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6430 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 27373.1036 | 0.2 | 0.3 | 42702.0416 |  |  |  |  | 0 | 15304.1601 | 15304.1601 | 15304.1601 | 15304.1601 | 15304.1601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6431 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 27305.5047 | 0.2 | 0.3 | 42596.5873 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6432 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16385.3565 | 0.2 | 0.3 | 25561.1561 |  |  |  |  | 0 | 5334.0069 | 5334.0069 | 5334.0069 | 5334.0069 | 5334.0069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6433 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 33885.0736 | 0.2 | 0.3 | 52860.7148 |  |  |  |  | 0 | 3906.4947 | 3906.4947 | 3906.4947 | 3906.4947 | 3906.4947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6434 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 43174.2728 | 0.2 | 0.3 | 67351.8656 |  |  |  |  | 0 | 394.2147 | 394.2147 | 394.2147 | 394.2147 | 394.2147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6435 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 29858.4278 | 0.2 | 0.3 | 46579.1474 |  |  |  |  | 0 | 1021.0341 | 1021.0341 | 1021.0341 | 1021.0341 | 1021.0341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6436 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 25849.2802 | 0.2 | 0.3 | 40324.8771 |  |  |  |  | 0 | 2932.4249 | 2932.4249 | 2932.4249 | 2932.4249 | 2932.4249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6437 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 25699.8225 | 0.2 | 0.3 | 40091.723 |  |  |  |  | 0 | 4932.0772 | 4932.0772 | 4932.0772 | 4932.0772 | 4932.0772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6438 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 27125.0389 | 0.2 | 0.3 | 42315.0607 |  |  |  |  | 0 | 7147.8729 | 7147.8729 | 7147.8729 | 7147.8729 | 7147.8729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6439 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 18463.9463 | 0.2 | 0.3 | 28803.7562 |  |  |  |  | 0 | 9274.1539 | 9274.1539 | 9274.1539 | 9274.1539 | 9274.1539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6440 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 13682.8119 | 0.2 | 0.3 | 21345.1865 |  |  |  |  | 0 | 5012.3532 | 5012.3532 | 5012.3532 | 5012.3532 | 5012.3532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6441 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 16679.4499 | 0.2 | 0.3 | 26019.9419 |  |  |  |  | 0 | 7225.8654 | 7225.8654 | 7225.8654 | 7225.8654 | 7225.8654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6442 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 16679.7703 | 0.2 | 0.3 | 26020.4416 |  |  |  |  | 0 | 4041.1634 | 4041.1634 | 4041.1634 | 4041.1634 | 4041.1634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6443 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 19908.235 | 0.2 | 0.3 | 31056.8466 |  |  |  |  | 0 | 5484.2037 | 5484.2037 | 5484.2037 | 5484.2037 | 5484.2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6444 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 7424.8155 | 7424.8155 | 7424.8155 | 7424.8155 | 7424.8155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6445 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 16679.7331 | 0.2 | 0.3 | 26020.3836 |  |  |  |  | 0 | 7772.7957 | 7772.7957 | 7772.7957 | 7772.7957 | 7772.7957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6446 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 9030.5965 | 9030.5965 | 9030.5965 | 9030.5965 | 9030.5965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6447 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 18148.8909 | 0.2 | 0.3 | 28312.2698 |  |  |  |  | 0 | 5699.2919 | 5699.2919 | 5699.2919 | 5699.2919 | 5699.2919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6448 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 2596.3095 | 0.2 | 0.3 | 4050.2428 |  |  |  |  | 0 | 8228.924 | 8228.924 | 8228.924 | 8228.924 | 8228.924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6449 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 24787.9863 | 0.2 | 0.3 | 38669.2587 |  |  |  |  | 0 | 5183.0547 | 5183.0547 | 5183.0547 | 5183.0547 | 5183.0547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6450 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 738.1158 | 0.2 | 0.3 | 1151.4606 |  |  |  |  | 0 | 800.5348 | 800.5348 | 800.5348 | 800.5348 | 800.5348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6451 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16208.308 | 0.2 | 0.3 | 25284.9605 |  |  |  |  | 0 | 5417.4546 | 5417.4546 | 5417.4546 | 5417.4546 | 5417.4546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6452 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 5586.816 | 0.2 | 0.3 | 8715.433 |  |  |  |  | 0 | 2768.3978 | 2768.3978 | 2768.3978 | 2768.3978 | 2768.3978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6453 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 11291.2865 | 0.2 | 0.3 | 17614.4069 |  |  |  |  | 0 | 5202.7626 | 5202.7626 | 5202.7626 | 5202.7626 | 5202.7626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6454 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 8825.3299 | 0.2 | 0.3 | 13767.5147 |  |  |  |  | 0 | 5203.1079 | 5203.1079 | 5203.1079 | 5203.1079 | 5203.1079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6455 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 17435.0455 | 0.2 | 0.3 | 27198.671 |  |  |  |  | 0 | 5905.1252 | 5905.1252 | 5905.1252 | 5905.1252 | 5905.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6456 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16674.7418 | 0.2 | 0.3 | 26012.5972 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6457 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 28129.6989 | 0.2 | 0.3 | 43882.3303 |  |  |  |  | 0 | 5200.1218 | 5200.1218 | 5200.1218 | 5200.1218 | 5200.1218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6458 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 28650.4705 | 0.2 | 0.3 | 44694.734 |  |  |  |  | 0 | 8050.3531 | 8050.3531 | 8050.3531 | 8050.3531 | 8050.3531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6459 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16675.5617 | 0.2 | 0.3 | 26013.8763 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6460 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 20654.4321 | 0.2 | 0.3 | 32220.9141 |  |  |  |  | 0 | 5202.9108 | 5202.9108 | 5202.9108 | 5202.9108 | 5202.9108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6461 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 17544.6695 | 0.2 | 0.3 | 27369.6844 |  |  |  |  | 0 | 6250.4929 | 6250.4929 | 6250.4929 | 6250.4929 | 6250.4929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6462 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 21752.9015 | 0.2 | 0.3 | 33934.5263 |  |  |  |  | 0 | 9784.6774 | 9784.6774 | 9784.6774 | 9784.6774 | 9784.6774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6463 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 22915.5204 | 0.2 | 0.3 | 35748.2118 |  |  |  |  | 0 | 14259.5928 | 14259.5928 | 14259.5928 | 14259.5928 | 14259.5928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6464 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 16687.9254 | 0.2 | 0.3 | 26033.1636 |  |  |  |  | 0 | 3002.9428 | 3002.9428 | 3002.9428 | 3002.9428 | 3002.9428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6465 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 16686.0115 | 0.2 | 0.3 | 26030.178 |  |  |  |  | 0 | 5196.2328 | 5196.2328 | 5196.2328 | 5196.2328 | 5196.2328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6466 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 13697.0079 | 0.2 | 0.3 | 21367.3324 |  |  |  |  | 0 | 607.4518 | 607.4518 | 607.4518 | 607.4518 | 607.4518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6467 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 25833.9413 | 0.2 | 0.3 | 40300.9485 |  |  |  |  | 0 | 5541.0002 | 5541.0002 | 5541.0002 | 5541.0002 | 5541.0002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6468 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 18934.4631 | 0.2 | 0.3 | 29537.7625 |  |  |  |  | 0 | 1751.0891 | 1751.0891 | 1751.0891 | 1751.0891 | 1751.0891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6469 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 18097.667 | 0.2 | 0.3 | 28232.3605 |  |  |  |  | 0 | 6083.596 | 6083.596 | 6083.596 | 6083.596 | 6083.596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6470 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 7072.4911 | 0.2 | 0.3 | 11033.0862 |  |  |  |  | 0 | 1999.2151 | 1999.2151 | 1999.2151 | 1999.2151 | 1999.2151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6471 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 14853.4648 | 0.2 | 0.3 | 23171.4051 |  |  |  |  | 0 | 7778.0989 | 7778.0989 | 7778.0989 | 7778.0989 | 7778.0989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6472 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 30113.7033 | 0.2 | 0.3 | 46977.3771 |  |  |  |  | 0 | 7064.4178 | 7064.4178 | 7064.4178 | 7064.4178 | 7064.4178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6473 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 11738.1579 | 0.2 | 0.3 | 18311.5263 |  |  |  |  | 0 | 9776.5278 | 9776.5278 | 9776.5278 | 9776.5278 | 9776.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6474 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 15804.1539 | 0.2 | 0.3 | 24654.4801 |  |  |  |  | 0 | 1221.1636 | 1221.1636 | 1221.1636 | 1221.1636 | 1221.1636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6475 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 20112.0049 | 0.2 | 0.3 | 31374.7276 |  |  |  |  | 0 | 4293.585 | 4293.585 | 4293.585 | 4293.585 | 4293.585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6476 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 23893.3853 | 0.2 | 0.3 | 37273.681 |  |  |  |  | 0 | 5211.336 | 5211.336 | 5211.336 | 5211.336 | 5211.336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6477 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 18076.6015 | 0.2 | 0.3 | 28199.4983 |  |  |  |  | 0 | 8921.6931 | 8921.6931 | 8921.6931 | 8921.6931 | 8921.6931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6478 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 24657.9384 | 0.2 | 0.3 | 38466.3839 |  |  |  |  | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6479 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16264.7025 | 0.2 | 0.3 | 25372.9358 |  |  |  |  | 0 | 5200.9223 | 5200.9223 | 5200.9223 | 5200.9223 | 5200.9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6480 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 19961.2886 | 0.2 | 0.3 | 31139.6102 |  |  |  |  | 0 | 13274.176 | 13274.176 | 13274.176 | 13274.176 | 13274.176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6481 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 28373.8316 | 0.2 | 0.3 | 44263.1773 |  |  |  |  | 0 | 7639.173 | 7639.173 | 7639.173 | 7639.173 | 7639.173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6482 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 13469.8291 | 0.2 | 0.3 | 21012.9333 |  |  |  |  | 0 | 5807.502 | 5807.502 | 5807.502 | 5807.502 | 5807.502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6483 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 1224.3528 | 0.2 | 0.3 | 1909.9904 |  |  |  |  | 0 | 5206.4621 | 5206.4621 | 5206.4621 | 5206.4621 | 5206.4621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6484 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 21005.9775 | 0.2 | 0.3 | 32769.3248 |  |  |  |  | 0 | 9786.597 | 9786.597 | 9786.597 | 9786.597 | 9786.597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6485 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16723.2542 | 0.2 | 0.3 | 26088.2766 |  |  |  |  | 0 | 5208.5093 | 5208.5093 | 5208.5093 | 5208.5093 | 5208.5093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6486 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 2299.4271 | 0.2 | 0.3 | 3587.1062 |  |  |  |  | 0 | 5206.4435 | 5206.4435 | 5206.4435 | 5206.4435 | 5206.4435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6487 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16681.3628 | 0.2 | 0.3 | 26022.926 |  |  |  |  | 0 | 5200.9911 | 5200.9911 | 5200.9911 | 5200.9911 | 5200.9911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6488 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16694.0951 | 0.2 | 0.3 | 26042.7884 |  |  |  |  | 0 | 9780.8964 | 9780.8964 | 9780.8964 | 9780.8964 | 9780.8964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6489 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 9389.2333 | 0.2 | 0.3 | 14647.2039 |  |  |  |  | 0 | 8754.3245 | 8754.3245 | 8754.3245 | 8754.3245 | 8754.3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6490 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16667.9558 | 0.2 | 0.3 | 26002.011 |  |  |  |  | 0 | 1220.6986 | 1220.6986 | 1220.6986 | 1220.6986 | 1220.6986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6491 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 9632.9552 | 0.2 | 0.3 | 15027.4101 |  |  |  |  | 0 | 9804.001 | 9804.001 | 9804.001 | 9804.001 | 9804.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6492 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 1040.7787 | 0.2 | 0.3 | 1623.6147 |  |  |  |  | 0 | 5202.2001 | 5202.2001 | 5202.2001 | 5202.2001 | 5202.2001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6493 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 20798.8442 | 0.2 | 0.3 | 32446.197 |  |  |  |  | 0 | 7059.8426 | 7059.8426 | 7059.8426 | 7059.8426 | 7059.8426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6494 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 20376.1655 | 0.2 | 0.3 | 31786.8181 |  |  |  |  | 0 | 7788.1154 | 7788.1154 | 7788.1154 | 7788.1154 | 7788.1154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6495 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 18521.6915 | 0.2 | 0.3 | 28893.8388 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6496 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 20065.0891 | 0.2 | 0.3 | 31301.539 |  |  |  |  | 0 | 1346.7396 | 1346.7396 | 1346.7396 | 1346.7396 | 1346.7396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6497 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 12656.4768 | 0.2 | 0.3 | 19744.1038 |  |  |  |  | 0 | 7366.8427 | 7366.8427 | 7366.8427 | 7366.8427 | 7366.8427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6498 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 15933.4225 | 0.2 | 0.3 | 24856.139 |  |  |  |  | 0 | 6377.769 | 6377.769 | 6377.769 | 6377.769 | 6377.769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6499 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 19741.5472 | 0.2 | 0.3 | 30796.8136 |  |  |  |  | 0 | 714.6904 | 714.6904 | 714.6904 | 714.6904 | 714.6904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6500 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 18422.2342 | 0.2 | 0.3 | 28738.6854 |  |  |  |  | 0 | 6885.2888 | 6885.2888 | 6885.2888 | 6885.2888 | 6885.2888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6501 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 1148.5538 | 1148.5538 | 1148.5538 | 1148.5538 | 1148.5538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6502 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 26203.2692 | 0.2 | 0.3 | 40877.1 |  |  |  |  | 0 | 6803.936 | 6803.936 | 6803.936 | 6803.936 | 6803.936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6503 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 24894.4566 | 0.2 | 0.3 | 38835.3523 |  |  |  |  | 0 | 6792.003 | 6792.003 | 6792.003 | 6792.003 | 6792.003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6504 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 31132.014 | 0.2 | 0.3 | 48565.9418 |  |  |  |  | 0 | 2685.6179 | 2685.6179 | 2685.6179 | 2685.6179 | 2685.6179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6505 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 38990.3387 | 0.2 | 0.3 | 60824.9284 |  |  |  |  | 0 | 3743.5168 | 3743.5168 | 3743.5168 | 3743.5168 | 3743.5168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6506 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 47795.766 | 0.2 | 0.3 | 74561.395 |  |  |  |  | 0 | 5203.1154 | 5203.1154 | 5203.1154 | 5203.1154 | 5203.1154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6507 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 25138.5535 | 0.2 | 0.3 | 39216.1435 |  |  |  |  | 0 | 9332.5456 | 9332.5456 | 9332.5456 | 9332.5456 | 9332.5456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6508 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 7948.3379 | 0.2 | 0.3 | 12399.4072 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6509 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 18145.6557 | 0.2 | 0.3 | 28307.2229 |  |  |  |  | 0 | 5207.7687 | 5207.7687 | 5207.7687 | 5207.7687 | 5207.7687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6510 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 12846.1416 | 0.2 | 0.3 | 20039.9809 |  |  |  |  | 0 | 9786.0437 | 9786.0437 | 9786.0437 | 9786.0437 | 9786.0437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6511 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 5382.8569 | 0.2 | 0.3 | 8397.2567 |  |  |  |  | 0 | 5205.0002 | 5205.0002 | 5205.0002 | 5205.0002 | 5205.0002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6512 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 16682.1826 | 0.2 | 0.3 | 26024.2049 |  |  |  |  | 0 | 2405.0965 | 2405.0965 | 2405.0965 | 2405.0965 | 2405.0965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6513 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 16859.8431 | 0.2 | 0.3 | 26301.3552 |  |  |  |  | 0 | 4764.3799 | 4764.3799 | 4764.3799 | 4764.3799 | 4764.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6514 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 26770.2651 | 0.2 | 0.3 | 41761.6135 |  |  |  |  | 0 | 7589.3721 | 7589.3721 | 7589.3721 | 7589.3721 | 7589.3721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6515 | MIRAMAR | 110319 | Private | 2036 | 5 | Swales | 66.6667 | 18735.1827 | 0.2 | 0.3 | 29226.8851 |  |  |  |  | 0 | 4574.1013 | 4574.1013 | 4574.1013 | 4574.1013 | 4574.1013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6516 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 3163.8557 | 0.2 | 0.3 | 4935.6149 |  |  |  |  | 0 | 2799.9311 | 2799.9311 | 2799.9311 | 2799.9311 | 2799.9311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6517 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 15360.703 | 0.2 | 0.3 | 23962.6967 |  |  |  |  | 0 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6518 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16552.8986 | 0.2 | 0.3 | 25822.5218 |  |  |  |  | 0 | 9676.4591 | 9676.4591 | 9676.4591 | 9676.4591 | 9676.4591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6519 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 11637.8448 | 0.2 | 0.3 | 18155.0379 |  |  |  |  | 0 | 5311.1722 | 5311.1722 | 5311.1722 | 5311.1722 | 5311.1722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6520 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 28583.6221 | 0.2 | 0.3 | 44590.4505 |  |  |  |  | 0 | 9779.7279 | 9779.7279 | 9779.7279 | 9779.7279 | 9779.7279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6521 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 21944.609 | 0.2 | 0.3 | 34233.59 |  |  |  |  | 0 | 5477.4219 | 5477.4219 | 5477.4219 | 5477.4219 | 5477.4219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6522 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 22386.6586 | 0.2 | 0.3 | 34923.1874 |  |  |  |  | 0 | 1874.9704 | 1874.9704 | 1874.9704 | 1874.9704 | 1874.9704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6523 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 23431.6714 | 0.2 | 0.3 | 36553.4074 |  |  |  |  | 0 | 12387.5497 | 12387.5497 | 12387.5497 | 12387.5497 | 12387.5497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6524 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 7298.6403 | 0.2 | 0.3 | 11385.8789 |  |  |  |  | 0 | 5202.8043 | 5202.8043 | 5202.8043 | 5202.8043 | 5202.8043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6525 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 19159.1636 | 0.2 | 0.3 | 29888.2952 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6526 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 28922.6863 | 0.2 | 0.3 | 45119.3906 |  |  |  |  | 0 | 5203.031 | 5203.031 | 5203.031 | 5203.031 | 5203.031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6527 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 28802.2631 | 0.2 | 0.3 | 44931.5305 |  |  |  |  | 0 | 6275.1088 | 6275.1088 | 6275.1088 | 6275.1088 | 6275.1088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6528 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 28047.8765 | 0.2 | 0.3 | 43754.6874 |  |  |  |  | 0 | 802.4169 | 802.4169 | 802.4169 | 802.4169 | 802.4169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6529 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16676.4425 | 0.2 | 0.3 | 26015.2502 |  |  |  |  | 0 | 5427.6094 | 5427.6094 | 5427.6094 | 5427.6094 | 5427.6094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6530 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 13829.9119 | 0.2 | 0.3 | 21574.6625 |  |  |  |  | 0 | 4182.0172 | 4182.0172 | 4182.0172 | 4182.0172 | 4182.0172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6531 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 4837.311 | 0.2 | 0.3 | 7546.2052 |  |  |  |  | 0 | 5204.5061 | 5204.5061 | 5204.5061 | 5204.5061 | 5204.5061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6532 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 11079.6927 | 0.2 | 0.3 | 17284.3207 |  |  |  |  | 0 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6533 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 10030.6215 | 0.2 | 0.3 | 15647.7696 |  |  |  |  | 0 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6534 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 16683.0041 | 0.2 | 0.3 | 26025.4864 |  |  |  |  | 0 | 5204.799 | 5204.799 | 5204.799 | 5204.799 | 5204.799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6535 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 9966.2001 | 0.2 | 0.3 | 15547.2722 |  |  |  |  | 0 | 36.7174 | 36.7174 | 36.7174 | 36.7174 | 36.7174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6536 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 13872.2443 | 0.2 | 0.3 | 21640.7012 |  |  |  |  | 0 | 6644.545 | 6644.545 | 6644.545 | 6644.545 | 6644.545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6537 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 16712.0471 | 0.2 | 0.3 | 26070.7935 |  |  |  |  | 0 | 1325.3701 | 1325.3701 | 1325.3701 | 1325.3701 | 1325.3701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6538 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 19451.5891 | 0.2 | 0.3 | 30344.479 |  |  |  |  | 0 | 10305.5928 | 10305.5928 | 10305.5928 | 10305.5928 | 10305.5928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6539 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 9837.5588 | 0.2 | 0.3 | 15346.5917 |  |  |  |  | 0 | 9835.0306 | 9835.0306 | 9835.0306 | 9835.0306 | 9835.0306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6540 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 4644.6782 | 0.2 | 0.3 | 7245.698 |  |  |  |  | 0 | 3777.9249 | 3777.9249 | 3777.9249 | 3777.9249 | 3777.9249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6541 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 11011.0265 | 0.2 | 0.3 | 17177.2014 |  |  |  |  | 0 | 10657.0278 | 10657.0278 | 10657.0278 | 10657.0278 | 10657.0278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6542 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 18468.6013 | 0.2 | 0.3 | 28811.0181 |  |  |  |  | 0 | 5204.0376 | 5204.0376 | 5204.0376 | 5204.0376 | 5204.0376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6543 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 34262.3181 | 0.2 | 0.3 | 53449.2162 |  |  |  |  | 0 | 5204.0486 | 5204.0486 | 5204.0486 | 5204.0486 | 5204.0486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6544 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 24946.1912 | 0.2 | 0.3 | 38916.0583 |  |  |  |  | 0 | 9783.5689 | 9783.5689 | 9783.5689 | 9783.5689 | 9783.5689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6545 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 6465.0083 | 0.2 | 0.3 | 10085.413 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6546 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 7254.0057 | 0.2 | 0.3 | 11316.2489 |  |  |  |  | 0 | 5202.3564 | 5202.3564 | 5202.3564 | 5202.3564 | 5202.3564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6547 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 5207.3707 | 0.2 | 0.3 | 8123.4983 |  |  |  |  | 0 | 7303.7534 | 7303.7534 | 7303.7534 | 7303.7534 | 7303.7534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6548 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 26370.2891 | 0.2 | 0.3 | 41137.651 |  |  |  |  | 0 | 5205.548 | 5205.548 | 5205.548 | 5205.548 | 5205.548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6549 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 29935.3521 | 0.2 | 0.3 | 46699.1492 |  |  |  |  | 0 | 5204.4577 | 5204.4577 | 5204.4577 | 5204.4577 | 5204.4577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6550 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 9147.8797 | 0.2 | 0.3 | 14270.6923 |  |  |  |  | 0 | 2304.8528 | 2304.8528 | 2304.8528 | 2304.8528 | 2304.8528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6551 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 8774.0277 | 0.2 | 0.3 | 13687.4833 |  |  |  |  | 0 | 5906.1868 | 5906.1868 | 5906.1868 | 5906.1868 | 5906.1868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6552 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 862.5215 | 0.2 | 0.3 | 1345.5336 |  |  |  |  | 0 | 5206.5474 | 5206.5474 | 5206.5474 | 5206.5474 | 5206.5474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6553 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 22580.5957 | 0.2 | 0.3 | 35225.7292 |  |  |  |  | 0 | 7712.5794 | 7712.5794 | 7712.5794 | 7712.5794 | 7712.5794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6554 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 27014.2255 | 0.2 | 0.3 | 42142.1918 |  |  |  |  | 0 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6555 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16692.2789 | 0.2 | 0.3 | 26039.955 |  |  |  |  | 0 | 7457.0158 | 7457.0158 | 7457.0158 | 7457.0158 | 7457.0158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6556 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16679.2845 | 0.2 | 0.3 | 26019.6838 |  |  |  |  | 0 | 6825.1665 | 6825.1665 | 6825.1665 | 6825.1665 | 6825.1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6557 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 31081.1673 | 0.2 | 0.3 | 48486.621 |  |  |  |  | 0 | 9801.6267 | 9801.6267 | 9801.6267 | 9801.6267 | 9801.6267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6558 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 10941.0911 | 0.2 | 0.3 | 17068.1022 |  |  |  |  | 0 | 5202.6005 | 5202.6005 | 5202.6005 | 5202.6005 | 5202.6005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6559 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 10681.8549 | 0.2 | 0.3 | 16663.6936 |  |  |  |  | 0 | 4193.9987 | 4193.9987 | 4193.9987 | 4193.9987 | 4193.9987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6560 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 13461.5548 | 0.2 | 0.3 | 21000.0255 |  |  |  |  | 0 | 7330.6312 | 7330.6312 | 7330.6312 | 7330.6312 | 7330.6312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6561 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 5438.9646 | 0.2 | 0.3 | 8484.7848 |  |  |  |  | 0 | 5202.9315 | 5202.9315 | 5202.9315 | 5202.9315 | 5202.9315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6562 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 2892.7458 | 0.2 | 0.3 | 4512.6834 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6563 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 23093.6447 | 0.2 | 0.3 | 36026.0858 |  |  |  |  | 0 | 5203.1792 | 5203.1792 | 5203.1792 | 5203.1792 | 5203.1792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6564 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 2986.2675 | 0.2 | 0.3 | 4658.5772 |  |  |  |  | 0 | 2854.6124 | 2854.6124 | 2854.6124 | 2854.6124 | 2854.6124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6565 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 10185.4337 | 0.2 | 0.3 | 15889.2766 |  |  |  |  | 0 | 5205.2811 | 5205.2811 | 5205.2811 | 5205.2811 | 5205.2811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6566 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 23031.4412 | 0.2 | 0.3 | 35929.0483 |  |  |  |  | 0 | 5206.7303 | 5206.7303 | 5206.7303 | 5206.7303 | 5206.7303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6567 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 11993.5795 | 0.2 | 0.3 | 18709.9841 |  |  |  |  | 0 | 6221.8865 | 6221.8865 | 6221.8865 | 6221.8865 | 6221.8865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6568 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 5591.8298 | 5591.8298 | 5591.8298 | 5591.8298 | 5591.8298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6569 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 11354.1287 | 0.2 | 0.3 | 17712.4408 |  |  |  |  | 0 | 5733.1504 | 5733.1504 | 5733.1504 | 5733.1504 | 5733.1504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6570 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 32795.6711 | 0.2 | 0.3 | 51161.2469 |  |  |  |  | 0 | 7342.3587 | 7342.3587 | 7342.3587 | 7342.3587 | 7342.3587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6571 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 24659.1723 | 0.2 | 0.3 | 38468.3087 |  |  |  |  | 0 | 6395.0866 | 6395.0866 | 6395.0866 | 6395.0866 | 6395.0866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6572 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 61045.2025 | 0.2 | 0.3 | 95230.5158 |  |  |  |  | 0 | 1220.9106 | 1220.9106 | 1220.9106 | 1220.9106 | 1220.9106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6573 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 48236.0217 | 0.2 | 0.3 | 75248.1939 |  |  |  |  | 0 | 1036.2678 | 1036.2678 | 1036.2678 | 1036.2678 | 1036.2678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6574 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 26414.9396 | 0.2 | 0.3 | 41207.3058 |  |  |  |  | 0 | 7281.127 | 7281.127 | 7281.127 | 7281.127 | 7281.127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6575 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 1919.8772 | 0.2 | 0.3 | 2995.0084 |  |  |  |  | 0 | 5202.7825 | 5202.7825 | 5202.7825 | 5202.7825 | 5202.7825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6576 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 41026.4181 | 0.2 | 0.3 | 64001.2123 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6577 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 26407.0094 | 0.2 | 0.3 | 41194.9347 |  |  |  |  | 0 | 5202.3428 | 5202.3428 | 5202.3428 | 5202.3428 | 5202.3428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6578 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 3301.4485 | 0.2 | 0.3 | 5150.2597 |  |  |  |  | 0 | 6384.4396 | 6384.4396 | 6384.4396 | 6384.4396 | 6384.4396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6579 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 13697.1666 | 0.2 | 0.3 | 21367.5799 |  |  |  |  | 0 | 8105.4853 | 8105.4853 | 8105.4853 | 8105.4853 | 8105.4853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6580 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 3012.8389 | 0.2 | 0.3 | 4700.0287 |  |  |  |  | 0 | 4195.6348 | 4195.6348 | 4195.6348 | 4195.6348 | 4195.6348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6581 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 16780.3673 | 0.2 | 0.3 | 26177.373 |  |  |  |  | 0 | 4439.3776 | 4439.3776 | 4439.3776 | 4439.3776 | 4439.3776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6582 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 16681.6371 | 0.2 | 0.3 | 26023.3539 |  |  |  |  | 0 | 4276.0038 | 4276.0038 | 4276.0038 | 4276.0038 | 4276.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6583 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 17045.9383 | 0.2 | 0.3 | 26591.6638 |  |  |  |  | 0 | 6043.9181 | 6043.9181 | 6043.9181 | 6043.9181 | 6043.9181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6584 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 17015.3693 | 0.2 | 0.3 | 26543.9761 |  |  |  |  | 0 | 6850.9354 | 6850.9354 | 6850.9354 | 6850.9354 | 6850.9354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6585 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 234.815 | 0.2 | 0.3 | 366.3114 |  |  |  |  | 0 | 6191.0846 | 6191.0846 | 6191.0846 | 6191.0846 | 6191.0846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6586 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 19967.57 | 0.2 | 0.3 | 31149.4092 |  |  |  |  | 0 | 10580.1021 | 10580.1021 | 10580.1021 | 10580.1021 | 10580.1021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6587 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 29256.6524 | 0.2 | 0.3 | 45640.3777 |  |  |  |  | 0 | 13060.8224 | 13060.8224 | 13060.8224 | 13060.8224 | 13060.8224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6588 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 28996.5037 | 0.2 | 0.3 | 45234.5458 |  |  |  |  | 0 | 5203.1202 | 5203.1202 | 5203.1202 | 5203.1202 | 5203.1202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6589 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16679.7202 | 0.2 | 0.3 | 26020.3635 |  |  |  |  | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6590 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 21186.8454 | 0.2 | 0.3 | 33051.4788 |  |  |  |  | 0 | 5203.2639 | 5203.2639 | 5203.2639 | 5203.2639 | 5203.2639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6591 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16682.7307 | 0.2 | 0.3 | 26025.0599 |  |  |  |  | 0 | 7817.2074 | 7817.2074 | 7817.2074 | 7817.2074 | 7817.2074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6592 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16678.5565 | 0.2 | 0.3 | 26018.5482 |  |  |  |  | 0 | 5204.6574 | 5204.6574 | 5204.6574 | 5204.6574 | 5204.6574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6593 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16677.6623 | 0.2 | 0.3 | 26017.1531 |  |  |  |  | 0 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 5205.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6594 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 6128.4495 | 0.2 | 0.3 | 9560.3813 |  |  |  |  | 0 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6595 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16680.0731 | 0.2 | 0.3 | 26020.914 |  |  |  |  | 0 | 5208.4135 | 5208.4135 | 5208.4135 | 5208.4135 | 5208.4135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6596 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 27496.0177 | 0.2 | 0.3 | 42893.7877 |  |  |  |  | 0 | 5942.3728 | 5942.3728 | 5942.3728 | 5942.3728 | 5942.3728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6597 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16676.6673 | 0.2 | 0.3 | 26015.601 |  |  |  |  | 0 | 5201.7043 | 5201.7043 | 5201.7043 | 5201.7043 | 5201.7043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6598 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16676.7159 | 0.2 | 0.3 | 26015.6768 |  |  |  |  | 0 | 6004.5365 | 6004.5365 | 6004.5365 | 6004.5365 | 6004.5365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6599 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16676.7159 | 0.2 | 0.3 | 26015.6768 |  |  |  |  | 0 | 10403.5411 | 10403.5411 | 10403.5411 | 10403.5411 | 10403.5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6600 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16667.4233 | 0.2 | 0.3 | 26001.1804 |  |  |  |  | 0 | 8826.1181 | 8826.1181 | 8826.1181 | 8826.1181 | 8826.1181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6601 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 18439.3381 | 0.2 | 0.3 | 28765.3674 |  |  |  |  | 0 | 7449.4795 | 7449.4795 | 7449.4795 | 7449.4795 | 7449.4795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6602 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 11949.8142 | 0.2 | 0.3 | 18641.7102 |  |  |  |  | 0 | 3691.4884 | 3691.4884 | 3691.4884 | 3691.4884 | 3691.4884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6603 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 22171.7907 | 0.2 | 0.3 | 34587.9935 |  |  |  |  | 0 | 2342.6319 | 2342.6319 | 2342.6319 | 2342.6319 | 2342.6319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6604 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 23064.8245 | 0.2 | 0.3 | 35981.1262 |  |  |  |  | 0 | 6158.9798 | 6158.9798 | 6158.9798 | 6158.9798 | 6158.9798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6605 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 10637.6543 | 0.2 | 0.3 | 16594.7407 |  |  |  |  | 0 | 5199.9806 | 5199.9806 | 5199.9806 | 5199.9806 | 5199.9806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6606 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 19520.9828 | 0.2 | 0.3 | 30452.7332 |  |  |  |  | 0 | 8517.2983 | 8517.2983 | 8517.2983 | 8517.2983 | 8517.2983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6607 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 13548.2069 | 0.2 | 0.3 | 21135.2028 |  |  |  |  | 0 | 8527.3048 | 8527.3048 | 8527.3048 | 8527.3048 | 8527.3048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6608 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 12543.4247 | 0.2 | 0.3 | 19567.7425 |  |  |  |  | 0 | 8608.0638 | 8608.0638 | 8608.0638 | 8608.0638 | 8608.0638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6609 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 4712.3953 | 0.2 | 0.3 | 7351.3366 |  |  |  |  | 0 | 8694.6752 | 8694.6752 | 8694.6752 | 8694.6752 | 8694.6752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6610 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 12427.9732 | 0.2 | 0.3 | 19387.6382 |  |  |  |  | 0 | 8811.8472 | 8811.8472 | 8811.8472 | 8811.8472 | 8811.8472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6611 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 9566.8173 | 0.2 | 0.3 | 14924.2349 |  |  |  |  | 0 | 8843.9706 | 8843.9706 | 8843.9706 | 8843.9706 | 8843.9706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6612 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 30678.8933 | 0.2 | 0.3 | 47859.0735 |  |  |  |  | 0 | 2912.5924 | 2912.5924 | 2912.5924 | 2912.5924 | 2912.5924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6613 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 15666.9779 | 0.2 | 0.3 | 24440.4855 |  |  |  |  | 0 | 7303.6828 | 7303.6828 | 7303.6828 | 7303.6828 | 7303.6828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6614 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 19373.8667 | 0.2 | 0.3 | 30223.232 |  |  |  |  | 0 | 5199.98 | 5199.98 | 5199.98 | 5199.98 | 5199.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6615 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 1355.0705 | 0.2 | 0.3 | 2113.91 |  |  |  |  | 0 | 6296.2696 | 6296.2696 | 6296.2696 | 6296.2696 | 6296.2696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6616 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 26061.2076 | 0.2 | 0.3 | 40655.4839 |  |  |  |  | 0 | 5200.6379 | 5200.6379 | 5200.6379 | 5200.6379 | 5200.6379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6617 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 28031.4031 | 0.2 | 0.3 | 43728.9889 |  |  |  |  | 0 | 5201.067 | 5201.067 | 5201.067 | 5201.067 | 5201.067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6618 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16746.8439 | 0.2 | 0.3 | 26125.0764 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6619 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 13706.7749 | 0.2 | 0.3 | 21382.5689 |  |  |  |  | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6620 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8253 | 0.2 | 0.3 | 26000.2475 |  |  |  |  | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6621 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 2598.1299 | 2598.1299 | 2598.1299 | 2598.1299 | 2598.1299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6622 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 28774.4927 | 0.2 | 0.3 | 44888.2086 |  |  |  |  | 0 | 7479.2031 | 7479.2031 | 7479.2031 | 7479.2031 | 7479.2031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6623 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16935.2361 | 0.2 | 0.3 | 26418.9683 |  |  |  |  | 0 | 8087.6468 | 8087.6468 | 8087.6468 | 8087.6468 | 8087.6468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6624 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 9742.5561 | 0.2 | 0.3 | 15198.3876 |  |  |  |  | 0 | 6409.44 | 6409.44 | 6409.44 | 6409.44 | 6409.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6625 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 23295.0313 | 0.2 | 0.3 | 36340.2488 |  |  |  |  | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6626 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 2793.4791 | 0.2 | 0.3 | 4357.8274 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6627 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 30500.967 | 0.2 | 0.3 | 47581.5085 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6628 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 36946.0003 | 0.2 | 0.3 | 57635.7604 |  |  |  |  | 0 | 5200.8036 | 5200.8036 | 5200.8036 | 5200.8036 | 5200.8036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6629 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 19170.835 | 0.2 | 0.3 | 29906.5026 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6630 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16730.4327 | 0.2 | 0.3 | 26099.4751 |  |  |  |  | 0 | 1455.2444 | 1455.2444 | 1455.2444 | 1455.2444 | 1455.2444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6631 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 10449.5329 | 0.2 | 0.3 | 16301.2713 |  |  |  |  | 0 | 3746.347 | 3746.347 | 3746.347 | 3746.347 | 3746.347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6632 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 10825.8254 | 0.2 | 0.3 | 16888.2876 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6633 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16986.7863 | 0.2 | 0.3 | 26499.3867 |  |  |  |  | 0 | 8409.8353 | 8409.8353 | 8409.8353 | 8409.8353 | 8409.8353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6634 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 9026.2183 | 0.2 | 0.3 | 14080.9006 |  |  |  |  | 0 | 9777.8599 | 9777.8599 | 9777.8599 | 9777.8599 | 9777.8599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6635 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 12594.3657 | 0.2 | 0.3 | 19647.2105 |  |  |  |  | 0 | 9778.4469 | 9778.4469 | 9778.4469 | 9778.4469 | 9778.4469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6636 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 17359.6292 | 0.2 | 0.3 | 27081.0216 |  |  |  |  | 0 | 9593.1508 | 9593.1508 | 9593.1508 | 9593.1508 | 9593.1508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6637 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 7694.4452 | 0.2 | 0.3 | 12003.3345 |  |  |  |  | 0 | 9569.3532 | 9569.3532 | 9569.3532 | 9569.3532 | 9569.3532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6638 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 31041.0205 | 0.2 | 0.3 | 48423.992 |  |  |  |  | 0 | 9144.2256 | 9144.2256 | 9144.2256 | 9144.2256 | 9144.2256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6639 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 34844.3945 | 0.2 | 0.3 | 54357.2555 |  |  |  |  | 0 | 9070.6365 | 9070.6365 | 9070.6365 | 9070.6365 | 9070.6365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6640 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 48143.5172 | 0.2 | 0.3 | 75103.8868 |  |  |  |  | 0 | 9552.4213 | 9552.4213 | 9552.4213 | 9552.4213 | 9552.4213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6641 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 1191.4132 | 0.2 | 0.3 | 1858.6046 |  |  |  |  | 0 | 6661.6918 | 6661.6918 | 6661.6918 | 6661.6918 | 6661.6918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6642 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 23130.5307 | 0.2 | 0.3 | 36083.6279 |  |  |  |  | 0 | 5206.1843 | 5206.1843 | 5206.1843 | 5206.1843 | 5206.1843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6643 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 33644.9383 | 0.2 | 0.3 | 52486.1037 |  |  |  |  | 0 | 5201.5172 | 5201.5172 | 5201.5172 | 5201.5172 | 5201.5172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6644 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 1126.3885 | 0.2 | 0.3 | 1757.1661 |  |  |  |  | 0 | 4961.8913 | 4961.8913 | 4961.8913 | 4961.8913 | 4961.8913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6645 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 18727.4618 | 0.2 | 0.3 | 29214.8404 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6646 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 9087.8111 | 0.2 | 0.3 | 14176.9854 |  |  |  |  | 0 | 5199.9883 | 5199.9883 | 5199.9883 | 5199.9883 | 5199.9883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6647 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 11433.5585 | 0.2 | 0.3 | 17836.3513 |  |  |  |  | 0 | 6818.2258 | 6818.2258 | 6818.2258 | 6818.2258 | 6818.2258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6648 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 4574.7461 | 0.2 | 0.3 | 7136.604 |  |  |  |  | 0 | 5201.2593 | 5201.2593 | 5201.2593 | 5201.2593 | 5201.2593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6649 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 13493.7422 | 0.2 | 0.3 | 21050.2378 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6650 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16681.6592 | 0.2 | 0.3 | 26023.3884 |  |  |  |  | 0 | 3132.1872 | 3132.1872 | 3132.1872 | 3132.1872 | 3132.1872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6651 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16696.4301 | 0.2 | 0.3 | 26046.4309 |  |  |  |  | 0 | 2216.3798 | 2216.3798 | 2216.3798 | 2216.3798 | 2216.3798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6652 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 12884.3423 | 0.2 | 0.3 | 20099.574 |  |  |  |  | 0 | 7548.0875 | 7548.0875 | 7548.0875 | 7548.0875 | 7548.0875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6653 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 21310.6691 | 0.2 | 0.3 | 33244.6438 |  |  |  |  | 0 | 7763.4956 | 7763.4956 | 7763.4956 | 7763.4956 | 7763.4956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6654 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 19894.5907 | 0.2 | 0.3 | 31035.5615 |  |  |  |  | 0 | 3418.8881 | 3418.8881 | 3418.8881 | 3418.8881 | 3418.8881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6655 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16676.7452 | 0.2 | 0.3 | 26015.7225 |  |  |  |  | 0 | 4283.8299 | 4283.8299 | 4283.8299 | 4283.8299 | 4283.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6656 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 21957.2492 | 0.2 | 0.3 | 34253.3088 |  |  |  |  | 0 | 6003.0141 | 6003.0141 | 6003.0141 | 6003.0141 | 6003.0141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6657 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16682.7307 | 0.2 | 0.3 | 26025.0599 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6658 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16678.2995 | 0.2 | 0.3 | 26018.1473 |  |  |  |  | 0 | 5201.0198 | 5201.0198 | 5201.0198 | 5201.0198 | 5201.0198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6659 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 16674.3319 | 0.2 | 0.3 | 26011.9577 |  |  |  |  | 0 | 10061.1975 | 10061.1975 | 10061.1975 | 10061.1975 | 10061.1975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6660 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 22568.3061 | 0.2 | 0.3 | 35206.5576 |  |  |  |  | 0 | 8846.6175 | 8846.6175 | 8846.6175 | 8846.6175 | 8846.6175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6661 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4063 | 0.2 | 0.3 | 26019.8738 |  |  |  |  | 0 | 9245.1202 | 9245.1202 | 9245.1202 | 9245.1202 | 9245.1202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6662 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 26790.5576 | 0.2 | 0.3 | 41793.2699 |  |  |  |  | 0 | 9776.8465 | 9776.8465 | 9776.8465 | 9776.8465 | 9776.8465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6663 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16677.7079 | 0.2 | 0.3 | 26017.2244 |  |  |  |  | 0 | 8727.8016 | 8727.8016 | 8727.8016 | 8727.8016 | 8727.8016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6664 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 9727.461 | 9727.461 | 9727.461 | 9727.461 | 9727.461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6665 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16677.8095 | 0.2 | 0.3 | 26017.3828 |  |  |  |  | 0 | 5459.6475 | 5459.6475 | 5459.6475 | 5459.6475 | 5459.6475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6666 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 16678.2462 | 0.2 | 0.3 | 26018.0641 |  |  |  |  | 0 | 5303.0834 | 5303.0834 | 5303.0834 | 5303.0834 | 5303.0834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6667 | MIRAMAR | 110366 | Public | 2026 | 5 | Swales | 66.6667 | 21466.1552 | 0.2 | 0.3 | 33487.2021 |  |  |  |  | 0 | 5200.5113 | 5200.5113 | 5200.5113 | 5200.5113 | 5200.5113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6668 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 14997.1832 | 0.2 | 0.3 | 23395.6058 |  |  |  |  | 0 | 7763.1945 | 7763.1945 | 7763.1945 | 7763.1945 | 7763.1945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6669 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 14142.815 | 0.2 | 0.3 | 22062.7914 |  |  |  |  | 0 | 4941.2817 | 4941.2817 | 4941.2817 | 4941.2817 | 4941.2817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6670 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 20060.5279 | 0.2 | 0.3 | 31294.4236 |  |  |  |  | 0 | 3439.7683 | 3439.7683 | 3439.7683 | 3439.7683 | 3439.7683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6671 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 8784.0593 | 0.2 | 0.3 | 13703.1325 |  |  |  |  | 0 | 9777.0867 | 9777.0867 | 9777.0867 | 9777.0867 | 9777.0867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6672 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 17172.7165 | 0.2 | 0.3 | 26789.4378 |  |  |  |  | 0 | 9780.5547 | 9780.5547 | 9780.5547 | 9780.5547 | 9780.5547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6673 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 17191.0305 | 0.2 | 0.3 | 26818.0076 |  |  |  |  | 0 | 9598.775 | 9598.775 | 9598.775 | 9598.775 | 9598.775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6674 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16680.2635 | 0.2 | 0.3 | 26021.211 |  |  |  |  | 0 | 9708.0648 | 9708.0648 | 9708.0648 | 9708.0648 | 9708.0648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6675 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 15720.4131 | 0.2 | 0.3 | 24523.8445 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6676 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 13491.6438 | 0.2 | 0.3 | 21046.9643 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6677 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 30297.7641 | 0.2 | 0.3 | 47264.5119 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6678 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 1083.8041 | 0.2 | 0.3 | 1690.7343 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6679 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 22546.7651 | 0.2 | 0.3 | 35172.9535 |  |  |  |  | 0 | 2774.3818 | 2774.3818 | 2774.3818 | 2774.3818 | 2774.3818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6680 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 20336.6382 | 0.2 | 0.3 | 31725.1556 |  |  |  |  | 0 | 9777.6215 | 9777.6215 | 9777.6215 | 9777.6215 | 9777.6215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6681 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 18430.2455 | 0.2 | 0.3 | 28751.183 |  |  |  |  | 0 | 9779.5829 | 9779.5829 | 9779.5829 | 9779.5829 | 9779.5829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6682 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 37413.3809 | 0.2 | 0.3 | 58364.8742 |  |  |  |  | 0 | 8803.6145 | 8803.6145 | 8803.6145 | 8803.6145 | 8803.6145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6683 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 1551.207 | 0.2 | 0.3 | 2419.8829 |  |  |  |  | 0 | 9727.4252 | 9727.4252 | 9727.4252 | 9727.4252 | 9727.4252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6684 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 8355.0841 | 0.2 | 0.3 | 13033.9311 |  |  |  |  | 0 | 5202.352 | 5202.352 | 5202.352 | 5202.352 | 5202.352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6685 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 8331.6728 | 0.2 | 0.3 | 12997.4096 |  |  |  |  | 0 | 5201.3894 | 5201.3894 | 5201.3894 | 5201.3894 | 5201.3894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6686 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 9396.3501 | 0.2 | 0.3 | 14658.3062 |  |  |  |  | 0 | 5202.2934 | 5202.2934 | 5202.2934 | 5202.2934 | 5202.2934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6687 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 18456.3329 | 0.2 | 0.3 | 28791.8794 |  |  |  |  | 0 | 812.5337 | 812.5337 | 812.5337 | 812.5337 | 812.5337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6688 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 4661.4716 | 0.2 | 0.3 | 7271.8957 |  |  |  |  | 0 | 5202.222 | 5202.222 | 5202.222 | 5202.222 | 5202.222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6689 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 9513.6611 | 0.2 | 0.3 | 14841.3114 |  |  |  |  | 0 | 5201.105 | 5201.105 | 5201.105 | 5201.105 | 5201.105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6690 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 9554.2391 | 0.2 | 0.3 | 14904.613 |  |  |  |  | 0 | 5202.0832 | 5202.0832 | 5202.0832 | 5202.0832 | 5202.0832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6691 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 21732.5761 | 0.2 | 0.3 | 33902.8187 |  |  |  |  | 0 | 5201.5974 | 5201.5974 | 5201.5974 | 5201.5974 | 5201.5974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6692 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 34868.6902 | 0.2 | 0.3 | 54395.1567 |  |  |  |  | 0 | 5201.5216 | 5201.5216 | 5201.5216 | 5201.5216 | 5201.5216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6693 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 31874.8791 | 0.2 | 0.3 | 49724.8114 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6694 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 22721.2433 | 0.2 | 0.3 | 35445.1396 |  |  |  |  | 0 | 38.5534 | 38.5534 | 38.5534 | 38.5534 | 38.5534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6695 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 39674.7211 | 0.2 | 0.3 | 61892.5649 |  |  |  |  | 0 | 5162.4773 | 5162.4773 | 5162.4773 | 5162.4773 | 5162.4773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6696 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 27592.4238 | 0.2 | 0.3 | 43044.1811 |  |  |  |  | 0 | 5201.6493 | 5201.6493 | 5201.6493 | 5201.6493 | 5201.6493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6697 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 22252.9193 | 0.2 | 0.3 | 34714.5542 |  |  |  |  | 0 | 5200.6376 | 5200.6376 | 5200.6376 | 5200.6376 | 5200.6376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6698 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 35052.305 | 0.2 | 0.3 | 54681.5958 |  |  |  |  | 0 | 5201.1834 | 5201.1834 | 5201.1834 | 5201.1834 | 5201.1834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6699 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 29161.8892 | 0.2 | 0.3 | 45492.5472 |  |  |  |  | 0 | 5200.9063 | 5200.9063 | 5200.9063 | 5200.9063 | 5200.9063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6700 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 28992.6881 | 0.2 | 0.3 | 45228.5934 |  |  |  |  | 0 | 9779.8154 | 9779.8154 | 9779.8154 | 9779.8154 | 9779.8154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6701 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 28893.8729 | 0.2 | 0.3 | 45074.4417 |  |  |  |  | 0 | 9781.5863 | 9781.5863 | 9781.5863 | 9781.5863 | 9781.5863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6702 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 28787.2289 | 0.2 | 0.3 | 44908.077 |  |  |  |  | 0 | 9776.5121 | 9776.5121 | 9776.5121 | 9776.5121 | 9776.5121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6703 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 28670.2841 | 0.2 | 0.3 | 44725.6431 |  |  |  |  | 0 | 5200.8514 | 5200.8514 | 5200.8514 | 5200.8514 | 5200.8514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6704 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 28615.0689 | 0.2 | 0.3 | 44639.5075 |  |  |  |  | 0 | 9777.6897 | 9777.6897 | 9777.6897 | 9777.6897 | 9777.6897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6705 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 28369.6628 | 0.2 | 0.3 | 44256.674 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6706 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 13474.1925 | 0.2 | 0.3 | 21019.7402 |  |  |  |  | 0 | 5203.0654 | 5203.0654 | 5203.0654 | 5203.0654 | 5203.0654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6707 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 22826.022 | 0.2 | 0.3 | 35608.5943 |  |  |  |  | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6708 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 44676.9034 | 0.2 | 0.3 | 69695.9693 |  |  |  |  | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6709 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 22196.4339 | 0.2 | 0.3 | 34626.4369 |  |  |  |  | 0 | 2773.9244 | 2773.9244 | 2773.9244 | 2773.9244 | 2773.9244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6710 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 6202.7484 | 0.2 | 0.3 | 9676.2875 |  |  |  |  | 0 | 3492.5199 | 3492.5199 | 3492.5199 | 3492.5199 | 3492.5199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6711 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 20125.6137 | 0.2 | 0.3 | 31395.9574 |  |  |  |  | 0 | 2145.9606 | 2145.9606 | 2145.9606 | 2145.9606 | 2145.9606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6712 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 31989.3851 | 0.2 | 0.3 | 49903.4407 |  |  |  |  | 0 | 2144.8376 | 2144.8376 | 2144.8376 | 2144.8376 | 2144.8376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6713 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 17869.7704 | 0.2 | 0.3 | 27876.8418 |  |  |  |  | 0 | 2147.3675 | 2147.3675 | 2147.3675 | 2147.3675 | 2147.3675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6714 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 11664.2933 | 0.2 | 0.3 | 18196.2976 |  |  |  |  | 0 | 2144.7647 | 2144.7647 | 2144.7647 | 2144.7647 | 2144.7647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6715 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 7458.4063 | 0.2 | 0.3 | 11635.1138 |  |  |  |  | 0 | 2145.3978 | 2145.3978 | 2145.3978 | 2145.3978 | 2145.3978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6716 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 18839.2787 | 0.2 | 0.3 | 29389.2748 |  |  |  |  | 0 | 2144.835 | 2144.835 | 2144.835 | 2144.835 | 2144.835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6717 | MIRAMAR | 110349 | Public | 2036 | 5 | Swales | 66.6667 | 18092.8345 | 0.2 | 0.3 | 28224.8218 |  |  |  |  | 0 | 2145.1164 | 2145.1164 | 2145.1164 | 2145.1164 | 2145.1164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6718 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 11413.2857 | 0.2 | 0.3 | 17804.7256 |  |  |  |  | 0 | 2144.5454 | 2144.5454 | 2144.5454 | 2144.5454 | 2144.5454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6719 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 23662.9425 | 0.2 | 0.3 | 36914.1904 |  |  |  |  | 0 | 5205.4804 | 5205.4804 | 5205.4804 | 5205.4804 | 5205.4804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6720 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 22873.7844 | 0.2 | 0.3 | 35683.1037 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6721 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 12882.6014 | 0.2 | 0.3 | 20096.8582 |  |  |  |  | 0 | 5205.072 | 5205.072 | 5205.072 | 5205.072 | 5205.072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6722 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 19839.5565 | 0.2 | 0.3 | 30949.7082 |  |  |  |  | 0 | 8487.7829 | 8487.7829 | 8487.7829 | 8487.7829 | 8487.7829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6723 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 18899.4085 | 0.2 | 0.3 | 29483.0773 |  |  |  |  | 0 | 2797.4225 | 2797.4225 | 2797.4225 | 2797.4225 | 2797.4225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6724 | MIRAMAR | 110319 | Public | 2036 | 5 | Swales | 66.6667 | 5151.2581 | 0.2 | 0.3 | 8035.9626 |  |  |  |  | 0 | 2403.9286 | 2403.9286 | 2403.9286 | 2403.9286 | 2403.9286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6725 | MIRAMAR | 110366 | Private | 2026 | 5 | Swales | 66.6667 | 13247.9654 | 0.2 | 0.3 | 20666.826 |  |  |  |  | 0 | 4090.0079 | 4090.0079 | 4090.0079 | 4090.0079 | 4090.0079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6726 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 26856.0581 | 0.2 | 0.3 | 41895.4506 |  |  |  |  | 0 | 7478.6705 | 7478.6705 | 7478.6705 | 7478.6705 | 7478.6705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6727 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 25399.1942 | 0.2 | 0.3 | 39622.743 |  |  |  |  | 0 | 7117.1736 | 7117.1736 | 7117.1736 | 7117.1736 | 7117.1736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6728 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 20235.7336 | 0.2 | 0.3 | 31567.7444 |  |  |  |  | 0 | 7955.4164 | 7955.4164 | 7955.4164 | 7955.4164 | 7955.4164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6729 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16679.3273 | 0.2 | 0.3 | 26019.7505 |  |  |  |  | 0 | 5202.6667 | 5202.6667 | 5202.6667 | 5202.6667 | 5202.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6730 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 10576.2407 | 0.2 | 0.3 | 16498.9354 |  |  |  |  | 0 | 5204.9516 | 5204.9516 | 5204.9516 | 5204.9516 | 5204.9516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6731 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 10625.9852 | 0.2 | 0.3 | 16576.5369 |  |  |  |  | 0 | 6364.405 | 6364.405 | 6364.405 | 6364.405 | 6364.405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6732 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 19621.1781 | 0.2 | 0.3 | 30609.0378 |  |  |  |  | 0 | 7561.2885 | 7561.2885 | 7561.2885 | 7561.2885 | 7561.2885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6733 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 19586.2798 | 0.2 | 0.3 | 30554.5965 |  |  |  |  | 0 | 9659.555 | 9659.555 | 9659.555 | 9659.555 | 9659.555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6734 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 75.9566 | 0.2 | 0.3 | 118.4923 |  |  |  |  | 0 | 2068.1744 | 2068.1744 | 2068.1744 | 2068.1744 | 2068.1744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6735 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 25722.1646 | 0.2 | 0.3 | 40126.5768 |  |  |  |  | 0 | 3510.0178 | 3510.0178 | 3510.0178 | 3510.0178 | 3510.0178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6736 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 29480.0841 | 0.2 | 0.3 | 45988.9311 |  |  |  |  | 0 | 7092.1057 | 7092.1057 | 7092.1057 | 7092.1057 | 7092.1057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6737 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 19224.1983 | 0.2 | 0.3 | 29989.7494 |  |  |  |  | 0 | 2012.3734 | 2012.3734 | 2012.3734 | 2012.3734 | 2012.3734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6738 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 19175.7621 | 0.2 | 0.3 | 29914.1889 |  |  |  |  | 0 | 3985.3903 | 3985.3903 | 3985.3903 | 3985.3903 | 3985.3903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6739 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 18179.4116 | 0.2 | 0.3 | 28359.8821 |  |  |  |  | 0 | 5203.7847 | 5203.7847 | 5203.7847 | 5203.7847 | 5203.7847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6740 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 8354.8776 | 0.2 | 0.3 | 13033.6091 |  |  |  |  | 0 | 8047.6427 | 8047.6427 | 8047.6427 | 8047.6427 | 8047.6427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6741 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 8333.9439 | 0.2 | 0.3 | 13000.9525 |  |  |  |  | 0 | 7205.5667 | 7205.5667 | 7205.5667 | 7205.5667 | 7205.5667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6742 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 8367.1035 | 0.2 | 0.3 | 13052.6814 |  |  |  |  | 0 | 5387.4596 | 5387.4596 | 5387.4596 | 5387.4596 | 5387.4596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6743 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 17466.8535 | 0.2 | 0.3 | 27248.2914 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6744 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 14208.6355 | 0.2 | 0.3 | 22165.4714 |  |  |  |  | 0 | 1218.3085 | 1218.3085 | 1218.3085 | 1218.3085 | 1218.3085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6745 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 7836.1524 | 7836.1524 | 7836.1524 | 7836.1524 | 7836.1524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6746 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16674.0335 | 0.2 | 0.3 | 26011.4923 |  |  |  |  | 0 | 1219.0211 | 1219.0211 | 1219.0211 | 1219.0211 | 1219.0211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6747 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 10816.4557 | 0.2 | 0.3 | 16873.6709 |  |  |  |  | 0 | 1218.3117 | 1218.3117 | 1218.3117 | 1218.3117 | 1218.3117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6748 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 2184.6906 | 0.2 | 0.3 | 3408.1173 |  |  |  |  | 0 | 11411.0177 | 11411.0177 | 11411.0177 | 11411.0177 | 11411.0177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6749 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 34160.4351 | 0.2 | 0.3 | 53290.2788 |  |  |  |  | 0 | 5203.5571 | 5203.5571 | 5203.5571 | 5203.5571 | 5203.5571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6750 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 38096.7013 | 0.2 | 0.3 | 59430.8541 |  |  |  |  | 0 | 4899.0215 | 4899.0215 | 4899.0215 | 4899.0215 | 4899.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6751 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 15789.1927 | 0.2 | 0.3 | 24631.1407 |  |  |  |  | 0 | 2922.4937 | 2922.4937 | 2922.4937 | 2922.4937 | 2922.4937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6752 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 41780.5789 | 0.2 | 0.3 | 65177.7031 |  |  |  |  | 0 | 5202.4623 | 5202.4623 | 5202.4623 | 5202.4623 | 5202.4623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6753 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 34005.5489 | 0.2 | 0.3 | 53048.6562 |  |  |  |  | 0 | 5202.4161 | 5202.4161 | 5202.4161 | 5202.4161 | 5202.4161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6754 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 24756.71 | 0.2 | 0.3 | 38620.4676 |  |  |  |  | 0 | 5203.2139 | 5203.2139 | 5203.2139 | 5203.2139 | 5203.2139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6755 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 20634.9565 | 0.2 | 0.3 | 32190.5321 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6756 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 22350.7805 | 0.2 | 0.3 | 34867.2175 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6757 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 18790.7403 | 0.2 | 0.3 | 29313.5549 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6758 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 19881.9615 | 0.2 | 0.3 | 31015.86 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6759 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16680.5075 | 0.2 | 0.3 | 26021.5918 |  |  |  |  | 0 | 5227.2833 | 5227.2833 | 5227.2833 | 5227.2833 | 5227.2833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6760 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16679.7192 | 0.2 | 0.3 | 26020.362 |  |  |  |  | 0 | 5461.8866 | 5461.8866 | 5461.8866 | 5461.8866 | 5461.8866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6761 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16673.7085 | 0.2 | 0.3 | 26010.9852 |  |  |  |  | 0 | 11531.4795 | 11531.4795 | 11531.4795 | 11531.4795 | 11531.4795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6762 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 27062.6566 | 0.2 | 0.3 | 42217.7443 |  |  |  |  | 0 | 2751.7105 | 2751.7105 | 2751.7105 | 2751.7105 | 2751.7105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6763 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 13048.1468 | 0.2 | 0.3 | 20355.109 |  |  |  |  | 0 | 4074.6874 | 4074.6874 | 4074.6874 | 4074.6874 | 4074.6874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6764 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 3636.8671 | 0.2 | 0.3 | 5673.5126 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6765 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 18487.6353 | 0.2 | 0.3 | 28840.711 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6766 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6767 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 31358.9157 | 0.2 | 0.3 | 48919.9084 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6768 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16680.5435 | 0.2 | 0.3 | 26021.6479 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6769 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16681.0903 | 0.2 | 0.3 | 26022.5009 |  |  |  |  | 0 | 5202.4288 | 5202.4288 | 5202.4288 | 5202.4288 | 5202.4288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6770 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16681.6371 | 0.2 | 0.3 | 26023.3539 |  |  |  |  | 0 | 5203.1494 | 5203.1494 | 5203.1494 | 5203.1494 | 5203.1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6771 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16682.4573 | 0.2 | 0.3 | 26024.6334 |  |  |  |  | 0 | 948.5975 | 948.5975 | 948.5975 | 948.5975 | 948.5975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6772 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16683.2775 | 0.2 | 0.3 | 26025.913 |  |  |  |  | 0 | 2855.2167 | 2855.2167 | 2855.2167 | 2855.2167 | 2855.2167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6773 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16684.0977 | 0.2 | 0.3 | 26027.1925 |  |  |  |  | 0 | 11577.3386 | 11577.3386 | 11577.3386 | 11577.3386 | 11577.3386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6774 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 10330.1474 | 0.2 | 0.3 | 16115.0299 |  |  |  |  | 0 | 795.9755 | 795.9755 | 795.9755 | 795.9755 | 795.9755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6775 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 23588.2929 | 0.2 | 0.3 | 36797.737 |  |  |  |  | 0 | 608.9921 | 608.9921 | 608.9921 | 608.9921 | 608.9921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6776 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 22361.0785 | 0.2 | 0.3 | 34883.2824 |  |  |  |  | 0 | 5275.4672 | 5275.4672 | 5275.4672 | 5275.4672 | 5275.4672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6777 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 14581.6883 | 0.2 | 0.3 | 22747.4338 |  |  |  |  | 0 | 5218.2105 | 5218.2105 | 5218.2105 | 5218.2105 | 5218.2105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6778 | MIRAMAR | 110359 | Private | 2036 | 5 | Swales | 66.6667 | 49.8369 | 0.2 | 0.3 | 77.7456 |  |  |  |  | 0 | 7449.5729 | 7449.5729 | 7449.5729 | 7449.5729 | 7449.5729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6779 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 5527.0445 | 0.2 | 0.3 | 8622.1894 |  |  |  |  | 0 | 7308.8266 | 7308.8266 | 7308.8266 | 7308.8266 | 7308.8266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6780 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16752.0454 | 0.2 | 0.3 | 26133.1908 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6781 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 17337.6134 | 0.2 | 0.3 | 27046.6769 |  |  |  |  | 0 | 6042.0047 | 6042.0047 | 6042.0047 | 6042.0047 | 6042.0047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6782 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 23630.3607 | 0.2 | 0.3 | 36863.3627 |  |  |  |  | 0 | 5713.9045 | 5713.9045 | 5713.9045 | 5713.9045 | 5713.9045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6783 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 8333.6194 | 0.2 | 0.3 | 13000.4463 |  |  |  |  | 0 | 5210.9456 | 5210.9456 | 5210.9456 | 5210.9456 | 5210.9456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6784 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 8333.5734 | 0.2 | 0.3 | 13000.3745 |  |  |  |  | 0 | 5120.2885 | 5120.2885 | 5120.2885 | 5120.2885 | 5120.2885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6785 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 23612.173 | 0.2 | 0.3 | 36834.9899 |  |  |  |  | 0 | 8075.256 | 8075.256 | 8075.256 | 8075.256 | 8075.256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6786 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 1984.2102 | 0.2 | 0.3 | 3095.3679 |  |  |  |  | 0 | 2328.3288 | 2328.3288 | 2328.3288 | 2328.3288 | 2328.3288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6787 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 18641.8302 | 0.2 | 0.3 | 29081.2551 |  |  |  |  | 0 | 3097.3288 | 3097.3288 | 3097.3288 | 3097.3288 | 3097.3288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6788 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7968 | 0.2 | 0.3 | 26000.203 |  |  |  |  | 0 | 5120.7748 | 5120.7748 | 5120.7748 | 5120.7748 | 5120.7748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6789 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 7532.7551 | 7532.7551 | 7532.7551 | 7532.7551 | 7532.7551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6790 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6879 | 0.2 | 0.3 | 26000.0332 |  |  |  |  | 0 | 5785.0401 | 5785.0401 | 5785.0401 | 5785.0401 | 5785.0401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6791 | MIRAMAR | 110360 | Private | 2036 | 5 | Swales | 66.6667 | 18846.5406 | 0.2 | 0.3 | 29400.6033 |  |  |  |  | 0 | 6644.8818 | 6644.8818 | 6644.8818 | 6644.8818 | 6644.8818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6792 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 23871.8641 | 0.2 | 0.3 | 37240.1079 |  |  |  |  | 0 | 8224.1933 | 8224.1933 | 8224.1933 | 8224.1933 | 8224.1933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6793 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 12783.548 | 0.2 | 0.3 | 19942.3349 |  |  |  |  | 0 | 9785.6465 | 9785.6465 | 9785.6465 | 9785.6465 | 9785.6465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6794 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 20183.509 | 0.2 | 0.3 | 31486.274 |  |  |  |  | 0 | 7760.704 | 7760.704 | 7760.704 | 7760.704 | 7760.704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6795 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 25593.4816 | 0.2 | 0.3 | 39925.8313 |  |  |  |  | 0 | 7462.2705 | 7462.2705 | 7462.2705 | 7462.2705 | 7462.2705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6796 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 31362.2672 | 0.2 | 0.3 | 48925.1368 |  |  |  |  | 0 | 5201.9666 | 5201.9666 | 5201.9666 | 5201.9666 | 5201.9666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6797 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16668.5138 | 0.2 | 0.3 | 26002.8815 |  |  |  |  | 0 | 5957.2973 | 5957.2973 | 5957.2973 | 5957.2973 | 5957.2973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6798 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 21836.1412 | 0.2 | 0.3 | 34064.3803 |  |  |  |  | 0 | 5204.5579 | 5204.5579 | 5204.5579 | 5204.5579 | 5204.5579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6799 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 20680.6854 | 0.2 | 0.3 | 32261.8692 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6800 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16667.7887 | 0.2 | 0.3 | 26001.7503 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6801 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 21695.7399 | 0.2 | 0.3 | 33845.3542 |  |  |  |  | 0 | 5864.3275 | 5864.3275 | 5864.3275 | 5864.3275 | 5864.3275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6802 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 37520.8109 | 0.2 | 0.3 | 58532.465 |  |  |  |  | 0 | 9215.0288 | 9215.0288 | 9215.0288 | 9215.0288 | 9215.0288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6803 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 26092.2265 | 0.2 | 0.3 | 40703.8733 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6804 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 18532.1275 | 0.2 | 0.3 | 28910.1188 |  |  |  |  | 0 | 9958.4126 | 9958.4126 | 9958.4126 | 9958.4126 | 9958.4126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6805 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 26685.8922 | 0.2 | 0.3 | 41629.9918 |  |  |  |  | 0 | 5377.6846 | 5377.6846 | 5377.6846 | 5377.6846 | 5377.6846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6806 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 21358.5529 | 0.2 | 0.3 | 33319.3426 |  |  |  |  | 0 | 4717.2688 | 4717.2688 | 4717.2688 | 4717.2688 | 4717.2688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6807 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 33854.1212 | 0.2 | 0.3 | 52812.4291 |  |  |  |  | 0 | 586.1828 | 586.1828 | 586.1828 | 586.1828 | 586.1828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6808 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 20359.3955 | 0.2 | 0.3 | 31760.657 |  |  |  |  | 0 | 6885.5106 | 6885.5106 | 6885.5106 | 6885.5106 | 6885.5106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6809 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 17534.0873 | 0.2 | 0.3 | 27353.1761 |  |  |  |  | 0 | 7545.2674 | 7545.2674 | 7545.2674 | 7545.2674 | 7545.2674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6810 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 25761.3549 | 0.2 | 0.3 | 40187.7136 |  |  |  |  | 0 | 7266.9432 | 7266.9432 | 7266.9432 | 7266.9432 | 7266.9432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6811 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 6335.1768 | 6335.1768 | 6335.1768 | 6335.1768 | 6335.1768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6812 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16678.6741 | 0.2 | 0.3 | 26018.7316 |  |  |  |  | 0 | 9404.3599 | 9404.3599 | 9404.3599 | 9404.3599 | 9404.3599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6813 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 22044.5711 | 0.2 | 0.3 | 34389.5309 |  |  |  |  | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6814 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 29437.4177 | 0.2 | 0.3 | 45922.3716 |  |  |  |  | 0 | 8684.0408 | 8684.0408 | 8684.0408 | 8684.0408 | 8684.0408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6815 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 27144.3396 | 0.2 | 0.3 | 42345.1698 |  |  |  |  | 0 | 5202.3933 | 5202.3933 | 5202.3933 | 5202.3933 | 5202.3933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6816 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16677.1275 | 0.2 | 0.3 | 26016.319 |  |  |  |  | 0 | 6115.3581 | 6115.3581 | 6115.3581 | 6115.3581 | 6115.3581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6817 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16681.4778 | 0.2 | 0.3 | 26023.1054 |  |  |  |  | 0 | 5203.7288 | 5203.7288 | 5203.7288 | 5203.7288 | 5203.7288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6818 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9105 | 0.2 | 0.3 | 26023.7804 |  |  |  |  | 0 | 6572.5531 | 6572.5531 | 6572.5531 | 6572.5531 | 6572.5531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6819 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 21254.515 | 0.2 | 0.3 | 33157.0434 |  |  |  |  | 0 | 5204.2098 | 5204.2098 | 5204.2098 | 5204.2098 | 5204.2098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6820 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 4740.9639 | 0.2 | 0.3 | 7395.9036 |  |  |  |  | 0 | 5204.199 | 5204.199 | 5204.199 | 5204.199 | 5204.199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6821 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 4076.8873 | 0.2 | 0.3 | 6359.9442 |  |  |  |  | 0 | 3438.2477 | 3438.2477 | 3438.2477 | 3438.2477 | 3438.2477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6822 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 13793.4665 | 0.2 | 0.3 | 21517.8077 |  |  |  |  | 0 | 5202.4034 | 5202.4034 | 5202.4034 | 5202.4034 | 5202.4034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6823 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 31279.9766 | 0.2 | 0.3 | 48796.7635 |  |  |  |  | 0 | 5204.2726 | 5204.2726 | 5204.2726 | 5204.2726 | 5204.2726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6824 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16758.2999 | 0.2 | 0.3 | 26142.9478 |  |  |  |  | 0 | 5203.6164 | 5203.6164 | 5203.6164 | 5203.6164 | 5203.6164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6825 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16677.0704 | 0.2 | 0.3 | 26016.2298 |  |  |  |  | 0 | 5492.9311 | 5492.9311 | 5492.9311 | 5492.9311 | 5492.9311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6826 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16676.9893 | 0.2 | 0.3 | 26016.1033 |  |  |  |  | 0 | 7499.9391 | 7499.9391 | 7499.9391 | 7499.9391 | 7499.9391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6827 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16677.2627 | 0.2 | 0.3 | 26016.5298 |  |  |  |  | 0 | 5877.6631 | 5877.6631 | 5877.6631 | 5877.6631 | 5877.6631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6828 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5312 | 0.2 | 0.3 | 26016.9487 |  |  |  |  | 0 | 5705.6485 | 5705.6485 | 5705.6485 | 5705.6485 | 5705.6485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6829 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16708.5613 | 0.2 | 0.3 | 26065.3557 |  |  |  |  | 0 | 8653.5466 | 8653.5466 | 8653.5466 | 8653.5466 | 8653.5466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6830 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 5880.2933 | 0.2 | 0.3 | 9173.2576 |  |  |  |  | 0 | 2949.093 | 2949.093 | 2949.093 | 2949.093 | 2949.093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6831 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16682.8403 | 0.2 | 0.3 | 26025.2309 |  |  |  |  | 0 | 7534.0828 | 7534.0828 | 7534.0828 | 7534.0828 | 7534.0828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6832 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9254 | 0.2 | 0.3 | 26020.6836 |  |  |  |  | 0 | 9355.0961 | 9355.0961 | 9355.0961 | 9355.0961 | 9355.0961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6833 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 19904.3513 | 0.2 | 0.3 | 31050.7881 |  |  |  |  | 0 | 5201.5186 | 5201.5186 | 5201.5186 | 5201.5186 | 5201.5186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6834 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 13619.6805 | 0.2 | 0.3 | 21246.7015 |  |  |  |  | 0 | 10361.6714 | 10361.6714 | 10361.6714 | 10361.6714 | 10361.6714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6835 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 6885.2528 | 6885.2528 | 6885.2528 | 6885.2528 | 6885.2528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6836 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 16667.2627 | 0.2 | 0.3 | 26000.9298 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6837 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 7714.138 | 0.2 | 0.3 | 12034.0553 |  |  |  |  | 0 | 7511.2104 | 7511.2104 | 7511.2104 | 7511.2104 | 7511.2104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6838 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 3790.0279 | 0.2 | 0.3 | 5912.4436 |  |  |  |  | 0 | 6665.3128 | 6665.3128 | 6665.3128 | 6665.3128 | 6665.3128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6839 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 8333.1391 | 0.2 | 0.3 | 12999.6969 |  |  |  |  | 0 | 6824.2255 | 6824.2255 | 6824.2255 | 6824.2255 | 6824.2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6840 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 8333.5734 | 0.2 | 0.3 | 13000.3745 |  |  |  |  | 0 | 6896.6127 | 6896.6127 | 6896.6127 | 6896.6127 | 6896.6127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6841 | MIRAMAR | 110358 | Private | 2036 | 5 | Swales | 66.6667 | 6932.7003 | 0.2 | 0.3 | 10815.0124 |  |  |  |  | 0 | 8155.0065 | 8155.0065 | 8155.0065 | 8155.0065 | 8155.0065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6842 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 7219.9473 | 0.2 | 0.3 | 11263.1177 |  |  |  |  | 0 | 5201.3995 | 5201.3995 | 5201.3995 | 5201.3995 | 5201.3995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6843 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 20362.2531 | 0.2 | 0.3 | 31765.1148 |  |  |  |  | 0 | 5201.5511 | 5201.5511 | 5201.5511 | 5201.5511 | 5201.5511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6844 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16770.2506 | 0.2 | 0.3 | 26161.5909 |  |  |  |  | 0 | 8330.4151 | 8330.4151 | 8330.4151 | 8330.4151 | 8330.4151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6845 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16770.4929 | 0.2 | 0.3 | 26161.9689 |  |  |  |  | 0 | 9780.8559 | 9780.8559 | 9780.8559 | 9780.8559 | 9780.8559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6846 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 22389.9241 | 0.2 | 0.3 | 34928.2815 |  |  |  |  | 0 | 5200.6623 | 5200.6623 | 5200.6623 | 5200.6623 | 5200.6623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6847 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 2463.4953 | 0.2 | 0.3 | 3843.0526 |  |  |  |  | 0 | 5200.6664 | 5200.6664 | 5200.6664 | 5200.6664 | 5200.6664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6848 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 17950.3043 | 0.2 | 0.3 | 28002.4747 |  |  |  |  | 0 | 201.3673 | 201.3673 | 201.3673 | 201.3673 | 201.3673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6849 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 2498.9696 | 2498.9696 | 2498.9696 | 2498.9696 | 2498.9696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6850 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8797 | 0.2 | 0.3 | 26000.3323 |  |  |  |  | 0 | 3791.4552 | 3791.4552 | 3791.4552 | 3791.4552 | 3791.4552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6851 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 12797.6058 | 0.2 | 0.3 | 19964.265 |  |  |  |  | 0 | 2404.4416 | 2404.4416 | 2404.4416 | 2404.4416 | 2404.4416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6852 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16329.8785 | 0.2 | 0.3 | 25474.6105 |  |  |  |  | 0 | 2800.1248 | 2800.1248 | 2800.1248 | 2800.1248 | 2800.1248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6853 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 5004.2546 | 5004.2546 | 5004.2546 | 5004.2546 | 5004.2546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6854 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 13657.3197 | 0.2 | 0.3 | 21305.4187 |  |  |  |  | 0 | 7537.8319 | 7537.8319 | 7537.8319 | 7537.8319 | 7537.8319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6855 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 12058.0725 | 0.2 | 0.3 | 18810.5932 |  |  |  |  | 0 | 1412.0346 | 1412.0346 | 1412.0346 | 1412.0346 | 1412.0346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6856 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 16667.6299 | 0.2 | 0.3 | 26001.5027 |  |  |  |  | 0 | 63.5896 | 63.5896 | 63.5896 | 63.5896 | 63.5896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6857 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 8054.5761 | 0.2 | 0.3 | 12565.1387 |  |  |  |  | 0 | 7855.331 | 7855.331 | 7855.331 | 7855.331 | 7855.331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6858 | MIRAMAR | 110345 | Private | 2036 | 5 | Swales | 66.6667 | 19003.9247 | 0.2 | 0.3 | 29646.1225 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6859 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 21474.9744 | 0.2 | 0.3 | 33500.9601 |  |  |  |  | 0 | 2403.7322 | 2403.7322 | 2403.7322 | 2403.7322 | 2403.7322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6860 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 25344.7226 | 0.2 | 0.3 | 39537.7673 |  |  |  |  | 0 | 6783.5689 | 6783.5689 | 6783.5689 | 6783.5689 | 6783.5689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6861 | MIRAMAR | 110348 | Private | 2036 | 5 | Swales | 66.6667 | 20967.7417 | 0.2 | 0.3 | 32709.677 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6862 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 20678.6348 | 0.2 | 0.3 | 32258.6703 |  |  |  |  | 0 | 5140.5452 | 5140.5452 | 5140.5452 | 5140.5452 | 5140.5452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6863 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 18374.2491 | 0.2 | 0.3 | 28663.8285 |  |  |  |  | 0 | 4571.5795 | 4571.5795 | 4571.5795 | 4571.5795 | 4571.5795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6864 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 6514.3514 | 0.2 | 0.3 | 10162.3882 |  |  |  |  | 0 | 8107.9795 | 8107.9795 | 8107.9795 | 8107.9795 | 8107.9795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6865 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 18001.4165 | 0.2 | 0.3 | 28082.2097 |  |  |  |  | 0 | 5203.839 | 5203.839 | 5203.839 | 5203.839 | 5203.839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6866 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16679.2147 | 0.2 | 0.3 | 26019.5749 |  |  |  |  | 0 | 5362.5719 | 5362.5719 | 5362.5719 | 5362.5719 | 5362.5719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6867 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 31357.6243 | 0.2 | 0.3 | 48917.8939 |  |  |  |  | 0 | 5434.6433 | 5434.6433 | 5434.6433 | 5434.6433 | 5434.6433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6868 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16679.0233 | 0.2 | 0.3 | 26019.2764 |  |  |  |  | 0 | 7836.3975 | 7836.3975 | 7836.3975 | 7836.3975 | 7836.3975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6869 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16679.1402 | 0.2 | 0.3 | 26019.4587 |  |  |  |  | 0 | 6870.4357 | 6870.4357 | 6870.4357 | 6870.4357 | 6870.4357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6870 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 22713.9479 | 0.2 | 0.3 | 35433.7588 |  |  |  |  | 0 | 7102.9112 | 7102.9112 | 7102.9112 | 7102.9112 | 7102.9112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6871 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16685.9176 | 0.2 | 0.3 | 26030.0315 |  |  |  |  | 0 | 1327.7628 | 1327.7628 | 1327.7628 | 1327.7628 | 1327.7628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6872 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 1798.4797 | 0.2 | 0.3 | 2805.6283 |  |  |  |  | 0 | 4059.5169 | 4059.5169 | 4059.5169 | 4059.5169 | 4059.5169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6873 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 27852.3247 | 0.2 | 0.3 | 43449.6266 |  |  |  |  | 0 | 4193.5609 | 4193.5609 | 4193.5609 | 4193.5609 | 4193.5609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6874 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16669.2659 | 0.2 | 0.3 | 26004.0548 |  |  |  |  | 0 | 1590.5266 | 1590.5266 | 1590.5266 | 1590.5266 | 1590.5266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6875 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 25275.8818 | 0.2 | 0.3 | 39430.3756 |  |  |  |  | 0 | 2587.0856 | 2587.0856 | 2587.0856 | 2587.0856 | 2587.0856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6876 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 22726.2426 | 0.2 | 0.3 | 35452.9385 |  |  |  |  | 0 | 2965.1731 | 2965.1731 | 2965.1731 | 2965.1731 | 2965.1731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6877 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16676.7766 | 0.2 | 0.3 | 26015.7715 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6878 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 6598.7509 | 6598.7509 | 6598.7509 | 6598.7509 | 6598.7509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6879 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16677.8095 | 0.2 | 0.3 | 26017.3828 |  |  |  |  | 0 | 1982.581 | 1982.581 | 1982.581 | 1982.581 | 1982.581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6880 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16677.9886 | 0.2 | 0.3 | 26017.6622 |  |  |  |  | 0 | 5201.409 | 5201.409 | 5201.409 | 5201.409 | 5201.409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6881 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 7879.815 | 7879.815 | 7879.815 | 7879.815 | 7879.815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6882 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 18449.1965 | 0.2 | 0.3 | 28780.7465 |  |  |  |  | 0 | 2905.5209 | 2905.5209 | 2905.5209 | 2905.5209 | 2905.5209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6883 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16682.5629 | 0.2 | 0.3 | 26024.7982 |  |  |  |  | 0 | 4416.1092 | 4416.1092 | 4416.1092 | 4416.1092 | 4416.1092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6884 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9755 | 0.2 | 0.3 | 26020.7617 |  |  |  |  | 0 | 6271.0234 | 6271.0234 | 6271.0234 | 6271.0234 | 6271.0234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6885 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 13948.7232 | 0.2 | 0.3 | 21760.0082 |  |  |  |  | 0 | 11808.5719 | 11808.5719 | 11808.5719 | 11808.5719 | 11808.5719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6886 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 9264.0562 | 0.2 | 0.3 | 14451.9277 |  |  |  |  | 0 | 1601.4612 | 1601.4612 | 1601.4612 | 1601.4612 | 1601.4612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6887 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 20614.5151 | 0.2 | 0.3 | 32158.6435 |  |  |  |  | 0 | 8871.0298 | 8871.0298 | 8871.0298 | 8871.0298 | 8871.0298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6888 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 24520.6919 | 0.2 | 0.3 | 38252.2794 |  |  |  |  | 0 | 4232.8515 | 4232.8515 | 4232.8515 | 4232.8515 | 4232.8515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6889 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 32911.1751 | 0.2 | 0.3 | 51341.4332 |  |  |  |  | 0 | 7297.3112 | 7297.3112 | 7297.3112 | 7297.3112 | 7297.3112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6890 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 21936.8274 | 0.2 | 0.3 | 34221.4507 |  |  |  |  | 0 | 11978.8673 | 11978.8673 | 11978.8673 | 11978.8673 | 11978.8673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6891 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 27261.0803 | 0.2 | 0.3 | 42527.2853 |  |  |  |  | 0 | 10406.2707 | 10406.2707 | 10406.2707 | 10406.2707 | 10406.2707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6892 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16672.9166 | 0.2 | 0.3 | 26009.7499 |  |  |  |  | 0 | 4170.6111 | 4170.6111 | 4170.6111 | 4170.6111 | 4170.6111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6893 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 25219.7956 | 0.2 | 0.3 | 39342.8811 |  |  |  |  | 0 | 5203.2121 | 5203.2121 | 5203.2121 | 5203.2121 | 5203.2121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6894 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16676.9892 | 0.2 | 0.3 | 26016.1032 |  |  |  |  | 0 | 9781.5722 | 9781.5722 | 9781.5722 | 9781.5722 | 9781.5722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6895 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16678.0053 | 0.2 | 0.3 | 26017.6882 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6896 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 22930.7421 | 0.2 | 0.3 | 35771.9576 |  |  |  |  | 0 | 3130.8002 | 3130.8002 | 3130.8002 | 3130.8002 | 3130.8002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6897 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16676.595 | 0.2 | 0.3 | 26015.4882 |  |  |  |  | 0 | 5201.1682 | 5201.1682 | 5201.1682 | 5201.1682 | 5201.1682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6898 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 22942.1549 | 0.2 | 0.3 | 35789.7616 |  |  |  |  | 0 | 3525.9009 | 3525.9009 | 3525.9009 | 3525.9009 | 3525.9009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6899 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 19588.6063 | 0.2 | 0.3 | 30558.2258 |  |  |  |  | 0 | 2797.9985 | 2797.9985 | 2797.9985 | 2797.9985 | 2797.9985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6900 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8757 | 0.2 | 0.3 | 26022.166 |  |  |  |  | 0 | 4640.1236 | 4640.1236 | 4640.1236 | 4640.1236 | 4640.1236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6901 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 2798.2734 | 2798.2734 | 2798.2734 | 2798.2734 | 2798.2734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6902 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 15943.7848 | 0.2 | 0.3 | 24872.3043 |  |  |  |  | 0 | 9231.9022 | 9231.9022 | 9231.9022 | 9231.9022 | 9231.9022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6903 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16441.5641 | 0.2 | 0.3 | 25648.8399 |  |  |  |  | 0 | 9798.3664 | 9798.3664 | 9798.3664 | 9798.3664 | 9798.3664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6904 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 15079.5132 | 0.2 | 0.3 | 23524.0406 |  |  |  |  | 0 | 6359.1721 | 6359.1721 | 6359.1721 | 6359.1721 | 6359.1721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6905 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 22708.123 | 0.2 | 0.3 | 35424.6719 |  |  |  |  | 0 | 7625.0364 | 7625.0364 | 7625.0364 | 7625.0364 | 7625.0364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6906 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 24912.2989 | 0.2 | 0.3 | 38863.1862 |  |  |  |  | 0 | 3.1847 | 3.1847 | 3.1847 | 3.1847 | 3.1847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6907 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3481 | 0.2 | 0.3 | 26018.223 |  |  |  |  | 0 | 7935.7385 | 7935.7385 | 7935.7385 | 7935.7385 | 7935.7385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6908 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2359 |  |  |  |  | 0 | 6720.3313 | 6720.3313 | 6720.3313 | 6720.3313 | 6720.3313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6909 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 7971.9858 | 7971.9858 | 7971.9858 | 7971.9858 | 7971.9858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6910 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16678.2026 | 0.2 | 0.3 | 26017.9961 |  |  |  |  | 0 | 5592.771 | 5592.771 | 5592.771 | 5592.771 | 5592.771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6911 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16683.4803 | 0.2 | 0.3 | 26026.2293 |  |  |  |  | 0 | 5200.1187 | 5200.1187 | 5200.1187 | 5200.1187 | 5200.1187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6912 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 13421.3018 | 0.2 | 0.3 | 20937.2308 |  |  |  |  | 0 | 5200.8915 | 5200.8915 | 5200.8915 | 5200.8915 | 5200.8915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6913 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 19542.4802 | 0.2 | 0.3 | 30486.2691 |  |  |  |  | 0 | 2980.7332 | 2980.7332 | 2980.7332 | 2980.7332 | 2980.7332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6914 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 12337.2487 | 0.2 | 0.3 | 19246.108 |  |  |  |  | 0 | 540.8592 | 540.8592 | 540.8592 | 540.8592 | 540.8592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6915 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 2010.711 | 0.2 | 0.3 | 3136.7092 |  |  |  |  | 0 | 6844.0086 | 6844.0086 | 6844.0086 | 6844.0086 | 6844.0086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6916 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 28566.3323 | 0.2 | 0.3 | 44563.4784 |  |  |  |  | 0 | 4696.3433 | 4696.3433 | 4696.3433 | 4696.3433 | 4696.3433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6917 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 21177.0365 | 0.2 | 0.3 | 33036.1769 |  |  |  |  | 0 | 9093.8025 | 9093.8025 | 9093.8025 | 9093.8025 | 9093.8025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6918 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 18987.2588 | 0.2 | 0.3 | 29620.1237 |  |  |  |  | 0 | 5440.8023 | 5440.8023 | 5440.8023 | 5440.8023 | 5440.8023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6919 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 13114.7381 | 0.2 | 0.3 | 20458.9914 |  |  |  |  | 0 | 9714.9908 | 9714.9908 | 9714.9908 | 9714.9908 | 9714.9908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6920 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 6275.8938 | 0.2 | 0.3 | 9790.3943 |  |  |  |  | 0 | 4338.7271 | 4338.7271 | 4338.7271 | 4338.7271 | 4338.7271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6921 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16683.2421 | 0.2 | 0.3 | 26025.8577 |  |  |  |  | 0 | 402.5489 | 402.5489 | 402.5489 | 402.5489 | 402.5489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6922 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6205 | 0.2 | 0.3 | 25999.9279 |  |  |  |  | 0 | 5233.0682 | 5233.0682 | 5233.0682 | 5233.0682 | 5233.0682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6923 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 19021.8541 | 0.2 | 0.3 | 29674.0924 |  |  |  |  | 0 | 10516.3197 | 10516.3197 | 10516.3197 | 10516.3197 | 10516.3197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6924 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16606.3751 | 0.2 | 0.3 | 25905.9451 |  |  |  |  | 0 | 7973.2701 | 7973.2701 | 7973.2701 | 7973.2701 | 7973.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6925 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 14227.3866 | 0.2 | 0.3 | 22194.7231 |  |  |  |  | 0 | 1382.0236 | 1382.0236 | 1382.0236 | 1382.0236 | 1382.0236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6926 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16675.7047 | 0.2 | 0.3 | 26014.0994 |  |  |  |  | 0 | 3294.4242 | 3294.4242 | 3294.4242 | 3294.4242 | 3294.4242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6927 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16671.2479 | 0.2 | 0.3 | 26007.1467 |  |  |  |  | 0 | 5401.9722 | 5401.9722 | 5401.9722 | 5401.9722 | 5401.9722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6928 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 6395.7178 | 6395.7178 | 6395.7178 | 6395.7178 | 6395.7178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6929 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17275.5135 | 0.2 | 0.3 | 26949.8011 |  |  |  |  | 0 | 1432.4816 | 1432.4816 | 1432.4816 | 1432.4816 | 1432.4816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6930 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 4917.8529 | 0.2 | 0.3 | 7671.8506 |  |  |  |  | 0 | 5258.6221 | 5258.6221 | 5258.6221 | 5258.6221 | 5258.6221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6931 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 22506.4116 | 0.2 | 0.3 | 35110.0021 |  |  |  |  | 0 | 5361.2114 | 5361.2114 | 5361.2114 | 5361.2114 | 5361.2114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6932 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 18938.4327 | 0.2 | 0.3 | 29543.955 |  |  |  |  | 0 | 912.0779 | 912.0779 | 912.0779 | 912.0779 | 912.0779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6933 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 3420.6453 | 0.2 | 0.3 | 5336.2067 |  |  |  |  | 0 | 3984.0421 | 3984.0421 | 3984.0421 | 3984.0421 | 3984.0421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6934 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 12007.3511 | 0.2 | 0.3 | 18731.4677 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6935 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 25302.1825 | 0.2 | 0.3 | 39471.4048 |  |  |  |  | 0 | 5204.1134 | 5204.1134 | 5204.1134 | 5204.1134 | 5204.1134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6936 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 13448.9595 | 0.2 | 0.3 | 20980.3769 |  |  |  |  | 0 | 6708.9818 | 6708.9818 | 6708.9818 | 6708.9818 | 6708.9818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6937 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 2945.8417 | 0.2 | 0.3 | 4595.513 |  |  |  |  | 0 | 9782.4834 | 9782.4834 | 9782.4834 | 9782.4834 | 9782.4834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6938 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 3321.8483 | 0.2 | 0.3 | 5182.0834 |  |  |  |  | 0 | 9782.7769 | 9782.7769 | 9782.7769 | 9782.7769 | 9782.7769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6939 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 17860.7381 | 0.2 | 0.3 | 27862.7515 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6940 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16751.3009 | 0.2 | 0.3 | 26132.0294 |  |  |  |  | 0 | 73.888 | 73.888 | 73.888 | 73.888 | 73.888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6941 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 6697.0887 | 0.2 | 0.3 | 10447.4583 |  |  |  |  | 0 | 3910.3797 | 3910.3797 | 3910.3797 | 3910.3797 | 3910.3797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6942 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 18211.7715 | 0.2 | 0.3 | 28410.3636 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6943 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4499 | 0.2 | 0.3 | 26019.9419 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6944 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4499 | 0.2 | 0.3 | 26019.9419 |  |  |  |  | 0 | 2799.0989 | 2799.0989 | 2799.0989 | 2799.0989 | 2799.0989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6945 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 15617.7323 | 0.2 | 0.3 | 24363.6623 |  |  |  |  | 0 | 6323.4911 | 6323.4911 | 6323.4911 | 6323.4911 | 6323.4911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6946 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 8569.0637 | 0.2 | 0.3 | 13367.7393 |  |  |  |  | 0 | 2600.7504 | 2600.7504 | 2600.7504 | 2600.7504 | 2600.7504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6947 | MIRAMAR | 110323 | Public | 2026 | 5 | Swales | 66.6667 | 4493.6311 | 0.2 | 0.3 | 7010.0645 |  |  |  |  | 0 | 8461.8545 | 8461.8545 | 8461.8545 | 8461.8545 | 8461.8545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6948 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 13019.5643 | 0.2 | 0.3 | 20310.5203 |  |  |  |  | 0 | 9783.2795 | 9783.2795 | 9783.2795 | 9783.2795 | 9783.2795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6949 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16788.9482 | 0.2 | 0.3 | 26190.7592 |  |  |  |  | 0 | 9782.2064 | 9782.2064 | 9782.2064 | 9782.2064 | 9782.2064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6950 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 3860.4007 | 3860.4007 | 3860.4007 | 3860.4007 | 3860.4007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6951 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16996.9349 | 0.2 | 0.3 | 26515.2185 |  |  |  |  | 0 | 2600.8236 | 2600.8236 | 2600.8236 | 2600.8236 | 2600.8236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6952 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 11301.7249 | 0.2 | 0.3 | 17630.6909 |  |  |  |  | 0 | 6524.0849 | 6524.0849 | 6524.0849 | 6524.0849 | 6524.0849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6953 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 373.7757 | 0.2 | 0.3 | 583.0901 |  |  |  |  | 0 | 5204.0255 | 5204.0255 | 5204.0255 | 5204.0255 | 5204.0255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6954 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 25596.8297 | 0.2 | 0.3 | 39931.0544 |  |  |  |  | 0 | 5203.8454 | 5203.8454 | 5203.8454 | 5203.8454 | 5203.8454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6955 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 14311.9011 | 0.2 | 0.3 | 22326.5658 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6956 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 17092.3407 | 0.2 | 0.3 | 26664.0514 |  |  |  |  | 0 | 5204.0193 | 5204.0193 | 5204.0193 | 5204.0193 | 5204.0193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6957 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 20364.4833 | 0.2 | 0.3 | 31768.594 |  |  |  |  | 0 | 5203.8435 | 5203.8435 | 5203.8435 | 5203.8435 | 5203.8435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6958 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16667.387 | 0.2 | 0.3 | 26001.1237 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6959 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 41954.2652 | 0.2 | 0.3 | 65448.6537 |  |  |  |  | 0 | 2601.6956 | 2601.6956 | 2601.6956 | 2601.6956 | 2601.6956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6960 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 31352.7657 | 0.2 | 0.3 | 48910.3144 |  |  |  |  | 0 | 2601.6956 | 2601.6956 | 2601.6956 | 2601.6956 | 2601.6956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6961 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17186.9329 | 0.2 | 0.3 | 26811.6153 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6962 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17390.1084 | 0.2 | 0.3 | 27128.5691 |  |  |  |  | 0 | 5206.6327 | 5206.6327 | 5206.6327 | 5206.6327 | 5206.6327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6963 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16674.5399 | 0.2 | 0.3 | 26012.2823 |  |  |  |  | 0 | 4044.8576 | 4044.8576 | 4044.8576 | 4044.8576 | 4044.8576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6964 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 922.9097 | 0.2 | 0.3 | 1439.7391 |  |  |  |  | 0 | 5202.3479 | 5202.3479 | 5202.3479 | 5202.3479 | 5202.3479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6965 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 15749.1687 | 0.2 | 0.3 | 24568.7032 |  |  |  |  | 0 | 1954.5639 | 1954.5639 | 1954.5639 | 1954.5639 | 1954.5639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6966 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 26317.7313 | 0.2 | 0.3 | 41055.6609 |  |  |  |  | 0 | 5546.6033 | 5546.6033 | 5546.6033 | 5546.6033 | 5546.6033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6967 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 17299.1273 | 0.2 | 0.3 | 26986.6385 |  |  |  |  | 0 | 9783.3337 | 9783.3337 | 9783.3337 | 9783.3337 | 9783.3337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6968 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 28787.1857 | 0.2 | 0.3 | 44908.0096 |  |  |  |  | 0 | 9782.9227 | 9782.9227 | 9782.9227 | 9782.9227 | 9782.9227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6969 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 15305.9618 | 0.2 | 0.3 | 23877.3004 |  |  |  |  | 0 | 9783.9061 | 9783.9061 | 9783.9061 | 9783.9061 | 9783.9061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6970 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 32325.866 | 0.2 | 0.3 | 50428.351 |  |  |  |  | 0 | 9786.1738 | 9786.1738 | 9786.1738 | 9786.1738 | 9786.1738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6971 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 19832.8009 | 0.2 | 0.3 | 30939.1694 |  |  |  |  | 0 | 6033.6333 | 6033.6333 | 6033.6333 | 6033.6333 | 6033.6333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6972 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 27283.2201 | 0.2 | 0.3 | 42561.8233 |  |  |  |  | 0 | 8948.475 | 8948.475 | 8948.475 | 8948.475 | 8948.475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6973 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 15835.0657 | 0.2 | 0.3 | 24702.7024 |  |  |  |  | 0 | 9780.5164 | 9780.5164 | 9780.5164 | 9780.5164 | 9780.5164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6974 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 18427.4183 | 0.2 | 0.3 | 28746.7725 |  |  |  |  | 0 | 9782.4306 | 9782.4306 | 9782.4306 | 9782.4306 | 9782.4306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6975 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 20194.7615 | 0.2 | 0.3 | 31503.8279 |  |  |  |  | 0 | 9780.3705 | 9780.3705 | 9780.3705 | 9780.3705 | 9780.3705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6976 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 1121.4765 | 0.2 | 0.3 | 1749.5034 |  |  |  |  | 0 | 9784.1448 | 9784.1448 | 9784.1448 | 9784.1448 | 9784.1448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6977 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 4903.8595 | 0.2 | 0.3 | 7650.0209 |  |  |  |  | 0 | 6490.6969 | 6490.6969 | 6490.6969 | 6490.6969 | 6490.6969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6978 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 23217.6112 | 0.2 | 0.3 | 36219.4735 |  |  |  |  | 0 | 3802.7939 | 3802.7939 | 3802.7939 | 3802.7939 | 3802.7939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6979 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16425.0686 | 0.2 | 0.3 | 25623.107 |  |  |  |  | 0 | 2663.6722 | 2663.6722 | 2663.6722 | 2663.6722 | 2663.6722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6980 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 44680.4623 | 0.2 | 0.3 | 69701.5212 |  |  |  |  | 0 | 2539.8552 | 2539.8552 | 2539.8552 | 2539.8552 | 2539.8552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6981 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 1460.8555 | 0.2 | 0.3 | 2278.9345 |  |  |  |  | 0 | 5203.5228 | 5203.5228 | 5203.5228 | 5203.5228 | 5203.5228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6982 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6983 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 10435.643 | 0.2 | 0.3 | 16279.6031 |  |  |  |  | 0 | 4419.7291 | 4419.7291 | 4419.7291 | 4419.7291 | 4419.7291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6984 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 10866.1754 | 0.2 | 0.3 | 16951.2336 |  |  |  |  | 0 | 5203.4873 | 5203.4873 | 5203.4873 | 5203.4873 | 5203.4873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6985 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16351.8819 | 0.2 | 0.3 | 25508.9358 |  |  |  |  | 0 | 5202.842 | 5202.842 | 5202.842 | 5202.842 | 5202.842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6986 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 325.705 | 0.2 | 0.3 | 508.0998 |  |  |  |  | 0 | 5204.6717 | 5204.6717 | 5204.6717 | 5204.6717 | 5204.6717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6987 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 5203.3827 | 5203.3827 | 5203.3827 | 5203.3827 | 5203.3827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6988 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 14528.6727 | 0.2 | 0.3 | 22664.7295 |  |  |  |  | 0 | 5205.1972 | 5205.1972 | 5205.1972 | 5205.1972 | 5205.1972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6989 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 26114.2629 | 0.2 | 0.3 | 40738.2501 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6990 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 28562.7639 | 0.2 | 0.3 | 44557.9117 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6991 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 27833.3577 | 0.2 | 0.3 | 43420.0381 |  |  |  |  | 0 | 589.8222 | 589.8222 | 589.8222 | 589.8222 | 589.8222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6992 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16684.0518 | 0.2 | 0.3 | 26027.1208 |  |  |  |  | 0 | 1372.6228 | 1372.6228 | 1372.6228 | 1372.6228 | 1372.6228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6993 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 17150.9644 | 0.2 | 0.3 | 26755.5045 |  |  |  |  | 0 | 5203.2213 | 5203.2213 | 5203.2213 | 5203.2213 | 5203.2213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6994 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 15110.7925 | 0.2 | 0.3 | 23572.8364 |  |  |  |  | 0 | 5202.8218 | 5202.8218 | 5202.8218 | 5202.8218 | 5202.8218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6995 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 17143.7792 | 0.2 | 0.3 | 26744.2956 |  |  |  |  | 0 | 5204.5785 | 5204.5785 | 5204.5785 | 5204.5785 | 5204.5785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6996 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 27365.1622 | 0.2 | 0.3 | 42689.653 |  |  |  |  | 0 | 5203.3209 | 5203.3209 | 5203.3209 | 5203.3209 | 5203.3209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6997 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16673.9405 | 0.2 | 0.3 | 26011.3471 |  |  |  |  | 0 | 5205.0627 | 5205.0627 | 5205.0627 | 5205.0627 | 5205.0627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6998 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 31459.6286 | 0.2 | 0.3 | 49077.0206 |  |  |  |  | 0 | 7473.8158 | 7473.8158 | 7473.8158 | 7473.8158 | 7473.8158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6999 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 21812.7312 | 0.2 | 0.3 | 34027.8607 |  |  |  |  | 0 | 9789.2926 | 9789.2926 | 9789.2926 | 9789.2926 | 9789.2926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7000 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 9033.5853 | 0.2 | 0.3 | 14092.393 |  |  |  |  | 0 | 9783.2506 | 9783.2506 | 9783.2506 | 9783.2506 | 9783.2506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7001 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 11521.648 | 0.2 | 0.3 | 17973.7709 |  |  |  |  | 0 | 5203.3571 | 5203.3571 | 5203.3571 | 5203.3571 | 5203.3571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7002 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17592.7772 | 0.2 | 0.3 | 27444.7324 |  |  |  |  | 0 | 9782.7856 | 9782.7856 | 9782.7856 | 9782.7856 | 9782.7856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7003 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 9043.0461 | 0.2 | 0.3 | 14107.1519 |  |  |  |  | 0 | 2799.4804 | 2799.4804 | 2799.4804 | 2799.4804 | 2799.4804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7004 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 24493.8975 | 0.2 | 0.3 | 38210.4802 |  |  |  |  | 0 | 5185.4879 | 5185.4879 | 5185.4879 | 5185.4879 | 5185.4879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7005 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 26589.4751 | 0.2 | 0.3 | 41479.5812 |  |  |  |  | 0 | 6472.999 | 6472.999 | 6472.999 | 6472.999 | 6472.999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7006 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 6875.9093 | 0.2 | 0.3 | 10726.4185 |  |  |  |  | 0 | 9784.2526 | 9784.2526 | 9784.2526 | 9784.2526 | 9784.2526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7007 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 21316.8387 | 0.2 | 0.3 | 33254.2684 |  |  |  |  | 0 | 5201.441 | 5201.441 | 5201.441 | 5201.441 | 5201.441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7008 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 12570.2079 | 0.2 | 0.3 | 19609.5243 |  |  |  |  | 0 | 9780.7568 | 9780.7568 | 9780.7568 | 9780.7568 | 9780.7568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7009 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 23780.7521 | 0.2 | 0.3 | 37097.9733 |  |  |  |  | 0 | 9780.0674 | 9780.0674 | 9780.0674 | 9780.0674 | 9780.0674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7010 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16677.9449 | 0.2 | 0.3 | 26017.5941 |  |  |  |  | 0 | 9781.9161 | 9781.9161 | 9781.9161 | 9781.9161 | 9781.9161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7011 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 19871.9448 | 0.2 | 0.3 | 31000.2339 |  |  |  |  | 0 | 9782.306 | 9782.306 | 9782.306 | 9782.306 | 9782.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7012 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 15824.2145 | 0.2 | 0.3 | 24685.7747 |  |  |  |  | 0 | 3839.4211 | 3839.4211 | 3839.4211 | 3839.4211 | 3839.4211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7013 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16684.9439 | 0.2 | 0.3 | 26028.5124 |  |  |  |  | 0 | 7511.8877 | 7511.8877 | 7511.8877 | 7511.8877 | 7511.8877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7014 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 25559.0112 | 0.2 | 0.3 | 39872.0575 |  |  |  |  | 0 | 5205.9107 | 5205.9107 | 5205.9107 | 5205.9107 | 5205.9107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7015 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 29769.3249 | 0.2 | 0.3 | 46440.1469 |  |  |  |  | 0 | 5204.1439 | 5204.1439 | 5204.1439 | 5204.1439 | 5204.1439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7016 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 19171.2904 | 0.2 | 0.3 | 29907.213 |  |  |  |  | 0 | 5202.3687 | 5202.3687 | 5202.3687 | 5202.3687 | 5202.3687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7017 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 12210.0233 | 0.2 | 0.3 | 19047.6364 |  |  |  |  | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7018 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16870.4357 | 0.2 | 0.3 | 26317.8796 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7019 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 17551.2566 | 0.2 | 0.3 | 27379.9603 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7020 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 12352.2385 | 0.2 | 0.3 | 19269.4921 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7021 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 17539.8828 | 0.2 | 0.3 | 27362.2172 |  |  |  |  | 0 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7022 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 18639.6041 | 0.2 | 0.3 | 29077.7824 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7023 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 19361.5267 | 0.2 | 0.3 | 30203.9817 |  |  |  |  | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7024 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 19004.7459 | 0.2 | 0.3 | 29647.4037 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7025 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 24170.0903 | 0.2 | 0.3 | 37705.3408 |  |  |  |  | 0 | 4132.8588 | 4132.8588 | 4132.8588 | 4132.8588 | 4132.8588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7026 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 29957.5727 | 0.2 | 0.3 | 46733.8134 |  |  |  |  | 0 | 1071.2184 | 1071.2184 | 1071.2184 | 1071.2184 | 1071.2184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7027 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 24765.1414 | 0.2 | 0.3 | 38633.6206 |  |  |  |  | 0 | 5204.9409 | 5204.9409 | 5204.9409 | 5204.9409 | 5204.9409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7028 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 18389.4638 | 0.2 | 0.3 | 28687.5635 |  |  |  |  | 0 | 5205.7514 | 5205.7514 | 5205.7514 | 5205.7514 | 5205.7514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7029 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16785.1863 | 0.2 | 0.3 | 26184.8907 |  |  |  |  | 0 | 5204.1225 | 5204.1225 | 5204.1225 | 5204.1225 | 5204.1225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7030 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 16687.248 | 0.2 | 0.3 | 26032.1069 |  |  |  |  | 0 | 5202.4077 | 5202.4077 | 5202.4077 | 5202.4077 | 5202.4077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7031 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 11539.8783 | 0.2 | 0.3 | 18002.2102 |  |  |  |  | 0 | 632.9266 | 632.9266 | 632.9266 | 632.9266 | 632.9266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7032 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 31707.0765 | 0.2 | 0.3 | 49463.0393 |  |  |  |  | 0 | 5203.9791 | 5203.9791 | 5203.9791 | 5203.9791 | 5203.9791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7033 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 8380.6329 | 0.2 | 0.3 | 13073.7873 |  |  |  |  | 0 | 368.3457 | 368.3457 | 368.3457 | 368.3457 | 368.3457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7034 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 38630.8993 | 0.2 | 0.3 | 60264.203 |  |  |  |  | 0 | 4835.4313 | 4835.4313 | 4835.4313 | 4835.4313 | 4835.4313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7035 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 21902.3204 | 0.2 | 0.3 | 34167.6198 |  |  |  |  | 0 | 5201.4537 | 5201.4537 | 5201.4537 | 5201.4537 | 5201.4537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7036 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 31252.1877 | 0.2 | 0.3 | 48753.4128 |  |  |  |  | 0 | 5202.4589 | 5202.4589 | 5202.4589 | 5202.4589 | 5202.4589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7037 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 18626.3685 | 0.2 | 0.3 | 29057.1348 |  |  |  |  | 0 | 2554.4858 | 2554.4858 | 2554.4858 | 2554.4858 | 2554.4858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7038 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 23935.6904 | 0.2 | 0.3 | 37339.677 |  |  |  |  | 0 | 2649.5387 | 2649.5387 | 2649.5387 | 2649.5387 | 2649.5387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7039 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 22476.3303 | 0.2 | 0.3 | 35063.0753 |  |  |  |  | 0 | 5205.6944 | 5205.6944 | 5205.6944 | 5205.6944 | 5205.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7040 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 6005.4293 | 0.2 | 0.3 | 9368.4698 |  |  |  |  | 0 | 3774.6219 | 3774.6219 | 3774.6219 | 3774.6219 | 3774.6219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7041 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 15191.2438 | 0.2 | 0.3 | 23698.3403 |  |  |  |  | 0 | 8674.57 | 8674.57 | 8674.57 | 8674.57 | 8674.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7042 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 7074.8504 | 0.2 | 0.3 | 11036.7666 |  |  |  |  | 0 | 5203.3339 | 5203.3339 | 5203.3339 | 5203.3339 | 5203.3339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7043 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 11830.3975 | 0.2 | 0.3 | 18455.42 |  |  |  |  | 0 | 5204.9335 | 5204.9335 | 5204.9335 | 5204.9335 | 5204.9335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7044 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 3945.9175 | 0.2 | 0.3 | 6155.6314 |  |  |  |  | 0 | 5205.5344 | 5205.5344 | 5205.5344 | 5205.5344 | 5205.5344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7045 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 26400.5453 | 0.2 | 0.3 | 41184.8507 |  |  |  |  | 0 | 2607.7015 | 2607.7015 | 2607.7015 | 2607.7015 | 2607.7015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7046 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 35002.9233 | 0.2 | 0.3 | 54604.5604 |  |  |  |  | 0 | 2595.3065 | 2595.3065 | 2595.3065 | 2595.3065 | 2595.3065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7047 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16666.5992 | 0.2 | 0.3 | 25999.8948 |  |  |  |  | 0 | 5203.4669 | 5203.4669 | 5203.4669 | 5203.4669 | 5203.4669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7048 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 21849.3869 | 0.2 | 0.3 | 34085.0435 |  |  |  |  | 0 | 5204.4677 | 5204.4677 | 5204.4677 | 5204.4677 | 5204.4677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7049 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 23210.0548 | 0.2 | 0.3 | 36207.6855 |  |  |  |  | 0 | 5203.9245 | 5203.9245 | 5203.9245 | 5203.9245 | 5203.9245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7050 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 26041.311 | 0.2 | 0.3 | 40624.4452 |  |  |  |  | 0 | 5203.8429 | 5203.8429 | 5203.8429 | 5203.8429 | 5203.8429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7051 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 26863.3482 | 0.2 | 0.3 | 41906.8232 |  |  |  |  | 0 | 5201.2901 | 5201.2901 | 5201.2901 | 5201.2901 | 5201.2901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7052 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 47271.4457 | 0.2 | 0.3 | 73743.4553 |  |  |  |  | 0 | 5482.6604 | 5482.6604 | 5482.6604 | 5482.6604 | 5482.6604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7053 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 35771.9585 | 0.2 | 0.3 | 55804.2552 |  |  |  |  | 0 | 2888.2497 | 2888.2497 | 2888.2497 | 2888.2497 | 2888.2497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7054 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17507.9338 | 0.2 | 0.3 | 27312.3767 |  |  |  |  | 0 | 8646.6399 | 8646.6399 | 8646.6399 | 8646.6399 | 8646.6399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7055 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17202.5058 | 0.2 | 0.3 | 26835.909 |  |  |  |  | 0 | 9785.5248 | 9785.5248 | 9785.5248 | 9785.5248 | 9785.5248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7056 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16900.0707 | 0.2 | 0.3 | 26364.1102 |  |  |  |  | 0 | 7719.1575 | 7719.1575 | 7719.1575 | 7719.1575 | 7719.1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7057 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 19404.319 | 0.2 | 0.3 | 30270.7376 |  |  |  |  | 0 | 7580.3959 | 7580.3959 | 7580.3959 | 7580.3959 | 7580.3959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7058 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 1303.995 | 0.2 | 0.3 | 2034.2322 |  |  |  |  | 0 | 13292.834 | 13292.834 | 13292.834 | 13292.834 | 13292.834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7059 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 28135.8373 | 0.2 | 0.3 | 43891.9061 |  |  |  |  | 0 | 8172.1163 | 8172.1163 | 8172.1163 | 8172.1163 | 8172.1163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7060 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 15780.2319 | 0.2 | 0.3 | 24617.1617 |  |  |  |  | 0 | 6815.2681 | 6815.2681 | 6815.2681 | 6815.2681 | 6815.2681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7061 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 8334.3936 | 0.2 | 0.3 | 13001.654 |  |  |  |  | 0 | 9782.6199 | 9782.6199 | 9782.6199 | 9782.6199 | 9782.6199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7062 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 26773.1691 | 0.2 | 0.3 | 41766.1437 |  |  |  |  | 0 | 9782.4748 | 9782.4748 | 9782.4748 | 9782.4748 | 9782.4748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7063 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 14312.7005 | 0.2 | 0.3 | 22327.8128 |  |  |  |  | 0 | 9783.2979 | 9783.2979 | 9783.2979 | 9783.2979 | 9783.2979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7064 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 26476.154 | 0.2 | 0.3 | 41302.8002 |  |  |  |  | 0 | 9782.7723 | 9782.7723 | 9782.7723 | 9782.7723 | 9782.7723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7065 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 7344.8279 | 0.2 | 0.3 | 11457.9316 |  |  |  |  | 0 | 9782.8059 | 9782.8059 | 9782.8059 | 9782.8059 | 9782.8059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7066 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 1103.7814 | 0.2 | 0.3 | 1721.899 |  |  |  |  | 0 | 8628.1622 | 8628.1622 | 8628.1622 | 8628.1622 | 8628.1622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7067 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 23291.9875 | 0.2 | 0.3 | 36335.5004 |  |  |  |  | 0 | 9781.8963 | 9781.8963 | 9781.8963 | 9781.8963 | 9781.8963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7068 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 23123.2665 | 0.2 | 0.3 | 36072.2957 |  |  |  |  | 0 | 9781.2551 | 9781.2551 | 9781.2551 | 9781.2551 | 9781.2551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7069 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 23104.52 | 0.2 | 0.3 | 36043.0512 |  |  |  |  | 0 | 9781.9143 | 9781.9143 | 9781.9143 | 9781.9143 | 9781.9143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7070 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 18439.7217 | 0.2 | 0.3 | 28765.9658 |  |  |  |  | 0 | 5203.7297 | 5203.7297 | 5203.7297 | 5203.7297 | 5203.7297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7071 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 2991.6975 | 0.2 | 0.3 | 4667.0482 |  |  |  |  | 0 | 9780.1635 | 9780.1635 | 9780.1635 | 9780.1635 | 9780.1635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7072 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 24987.5391 | 0.2 | 0.3 | 38980.561 |  |  |  |  | 0 | 9791.6218 | 9791.6218 | 9791.6218 | 9791.6218 | 9791.6218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7073 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 3201.197 | 0.2 | 0.3 | 4993.8673 |  |  |  |  | 0 | 9503.4798 | 9503.4798 | 9503.4798 | 9503.4798 | 9503.4798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7074 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 19518.2883 | 0.2 | 0.3 | 30448.5298 |  |  |  |  | 0 | 2664.022 | 2664.022 | 2664.022 | 2664.022 | 2664.022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7075 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 5742.1917 | 5742.1917 | 5742.1917 | 5742.1917 | 5742.1917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7076 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 59179.4925 | 0.2 | 0.3 | 92320.0082 |  |  |  |  | 0 | 8115.753 | 8115.753 | 8115.753 | 8115.753 | 8115.753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7077 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 37642.9939 | 0.2 | 0.3 | 58723.0704 |  |  |  |  | 0 | 5205.6944 | 5205.6944 | 5205.6944 | 5205.6944 | 5205.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7078 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 32983.3854 | 0.2 | 0.3 | 51454.0812 |  |  |  |  | 0 | 5203.1423 | 5203.1423 | 5203.1423 | 5203.1423 | 5203.1423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7079 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 15133.585 | 0.2 | 0.3 | 23608.3926 |  |  |  |  | 0 | 2393.532 | 2393.532 | 2393.532 | 2393.532 | 2393.532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7080 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17996.2722 | 0.2 | 0.3 | 28074.1846 |  |  |  |  | 0 | 2809.0453 | 2809.0453 | 2809.0453 | 2809.0453 | 2809.0453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7081 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 3420.8362 | 0.2 | 0.3 | 5336.5045 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7082 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 12412.6799 | 0.2 | 0.3 | 19363.7806 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7083 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17449.1698 | 0.2 | 0.3 | 27220.7049 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7084 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 146.3429 | 0.2 | 0.3 | 228.295 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7085 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 19008.7631 | 0.2 | 0.3 | 29653.6705 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7086 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 30606.1893 | 0.2 | 0.3 | 47745.6554 |  |  |  |  | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7087 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16971.9741 | 0.2 | 0.3 | 26476.2795 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7088 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 13545.7713 | 0.2 | 0.3 | 21131.4033 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7089 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 18347.4191 | 0.2 | 0.3 | 28621.9737 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7090 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 21229.4269 | 0.2 | 0.3 | 33117.9059 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7091 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 27325.0449 | 0.2 | 0.3 | 42627.07 |  |  |  |  | 0 | 5207.1445 | 5207.1445 | 5207.1445 | 5207.1445 | 5207.1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7092 | MIRAMAR | 110323 | Private | 2036 | 5 | Swales | 66.6667 | 15942.9847 | 0.2 | 0.3 | 24871.0562 |  |  |  |  | 0 | 5205.1826 | 5205.1826 | 5205.1826 | 5205.1826 | 5205.1826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7093 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 8332.1589 | 0.2 | 0.3 | 12998.1678 |  |  |  |  | 0 | 9781.4936 | 9781.4936 | 9781.4936 | 9781.4936 | 9781.4936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7094 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 30792.4608 | 0.2 | 0.3 | 48036.2388 |  |  |  |  | 0 | 9782.063 | 9782.063 | 9782.063 | 9782.063 | 9782.063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7095 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 46183.9925 | 0.2 | 0.3 | 72047.0282 |  |  |  |  | 0 | 9779.8965 | 9779.8965 | 9779.8965 | 9779.8965 | 9779.8965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7096 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 8337.0837 | 0.2 | 0.3 | 13005.8506 |  |  |  |  | 0 | 9455.5072 | 9455.5072 | 9455.5072 | 9455.5072 | 9455.5072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7097 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 8335.8447 | 0.2 | 0.3 | 13003.9178 |  |  |  |  | 0 | 5532.4203 | 5532.4203 | 5532.4203 | 5532.4203 | 5532.4203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7098 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 4918.2301 | 0.2 | 0.3 | 7672.4389 |  |  |  |  | 0 | 9782.2327 | 9782.2327 | 9782.2327 | 9782.2327 | 9782.2327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7099 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 22995.0792 | 0.2 | 0.3 | 35872.3236 |  |  |  |  | 0 | 9784.7761 | 9784.7761 | 9784.7761 | 9784.7761 | 9784.7761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7100 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 27476.5961 | 0.2 | 0.3 | 42863.4899 |  |  |  |  | 0 | 7946.5141 | 7946.5141 | 7946.5141 | 7946.5141 | 7946.5141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7101 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 31411.1697 | 0.2 | 0.3 | 49001.4247 |  |  |  |  | 0 | 5200.0674 | 5200.0674 | 5200.0674 | 5200.0674 | 5200.0674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7102 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 3951.9948 | 0.2 | 0.3 | 6165.1119 |  |  |  |  | 0 | 9788.5775 | 9788.5775 | 9788.5775 | 9788.5775 | 9788.5775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7103 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 24930.4873 | 0.2 | 0.3 | 38891.5601 |  |  |  |  | 0 | 5203.6758 | 5203.6758 | 5203.6758 | 5203.6758 | 5203.6758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7104 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 28207.0322 | 0.2 | 0.3 | 44002.9702 |  |  |  |  | 0 | 5202.4263 | 5202.4263 | 5202.4263 | 5202.4263 | 5202.4263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7105 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 38746.7217 | 0.2 | 0.3 | 60444.8859 |  |  |  |  | 0 | 5202.3391 | 5202.3391 | 5202.3391 | 5202.3391 | 5202.3391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7106 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 32543.4109 | 0.2 | 0.3 | 50767.721 |  |  |  |  | 0 | 2660.2918 | 2660.2918 | 2660.2918 | 2660.2918 | 2660.2918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7107 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 31030.9307 | 0.2 | 0.3 | 48408.2519 |  |  |  |  | 0 | 2542.1725 | 2542.1725 | 2542.1725 | 2542.1725 | 2542.1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7108 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16682.1839 | 0.2 | 0.3 | 26024.2069 |  |  |  |  | 0 | 5202.8043 | 5202.8043 | 5202.8043 | 5202.8043 | 5202.8043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7109 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 11541.1 | 0.2 | 0.3 | 18004.116 |  |  |  |  | 0 | 5204.2951 | 5204.2951 | 5204.2951 | 5204.2951 | 5204.2951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7110 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 20866.2719 | 0.2 | 0.3 | 32551.3841 |  |  |  |  | 0 | 5204.5524 | 5204.5524 | 5204.5524 | 5204.5524 | 5204.5524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7111 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 21420.8691 | 0.2 | 0.3 | 33416.5557 |  |  |  |  | 0 | 4493.9519 | 4493.9519 | 4493.9519 | 4493.9519 | 4493.9519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7112 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16675.5607 | 0.2 | 0.3 | 26013.8747 |  |  |  |  | 0 | 2312.035 | 2312.035 | 2312.035 | 2312.035 | 2312.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7113 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17000.3507 | 0.2 | 0.3 | 26520.547 |  |  |  |  | 0 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7114 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16868.7289 | 0.2 | 0.3 | 26315.2171 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7115 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 8431.7408 | 0.2 | 0.3 | 13153.5156 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7116 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 19312.7468 | 0.2 | 0.3 | 30127.885 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7117 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 2186.1389 | 0.2 | 0.3 | 3410.3766 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7118 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 1305.4717 | 0.2 | 0.3 | 2036.5358 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7119 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16189.2575 | 0.2 | 0.3 | 25255.2416 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7120 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 1726.7585 | 0.2 | 0.3 | 2693.7432 |  |  |  |  | 0 | 5203.2504 | 5203.2504 | 5203.2504 | 5203.2504 | 5203.2504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7121 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 18758.1861 | 0.2 | 0.3 | 29262.7703 |  |  |  |  | 0 | 5205.638 | 5205.638 | 5205.638 | 5205.638 | 5205.638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7122 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0293 | 0.2 | 0.3 | 26000.5657 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7123 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16588.5693 | 0.2 | 0.3 | 25878.1682 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7124 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 6039.1767 | 0.2 | 0.3 | 9421.1156 |  |  |  |  | 0 | 5202.2205 | 5202.2205 | 5202.2205 | 5202.2205 | 5202.2205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7125 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 10828.4641 | 0.2 | 0.3 | 16892.4039 |  |  |  |  | 0 | 2017.9323 | 2017.9323 | 2017.9323 | 2017.9323 | 2017.9323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7126 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 163.2031 | 0.2 | 0.3 | 254.5968 |  |  |  |  | 0 | 3184.4677 | 3184.4677 | 3184.4677 | 3184.4677 | 3184.4677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7127 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 18204.955 | 0.2 | 0.3 | 28399.7298 |  |  |  |  | 0 | 5202.761 | 5202.761 | 5202.761 | 5202.761 | 5202.761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7128 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 45294.279 | 0.2 | 0.3 | 70659.0752 |  |  |  |  | 0 | 5204.2446 | 5204.2446 | 5204.2446 | 5204.2446 | 5204.2446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7129 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 25796.421 | 0.2 | 0.3 | 40242.4168 |  |  |  |  | 0 | 3565.3931 | 3565.3931 | 3565.3931 | 3565.3931 | 3565.3931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7130 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 39312.1283 | 0.2 | 0.3 | 61326.9201 |  |  |  |  | 0 | 21.0626 | 21.0626 | 21.0626 | 21.0626 | 21.0626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7131 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 39940.692 | 0.2 | 0.3 | 62307.4795 |  |  |  |  | 0 | 2199.339 | 2199.339 | 2199.339 | 2199.339 | 2199.339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7132 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16672.3415 | 0.2 | 0.3 | 26008.8527 |  |  |  |  | 0 | 6871.3649 | 6871.3649 | 6871.3649 | 6871.3649 | 6871.3649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7133 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 4164.5298 | 0.2 | 0.3 | 6496.6665 |  |  |  |  | 0 | 658.6133 | 658.6133 | 658.6133 | 658.6133 | 658.6133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7134 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 19603.6543 | 0.2 | 0.3 | 30581.7008 |  |  |  |  | 0 | 3958.9504 | 3958.9504 | 3958.9504 | 3958.9504 | 3958.9504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7135 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 19757.3955 | 0.2 | 0.3 | 30821.5369 |  |  |  |  | 0 | 6608.6538 | 6608.6538 | 6608.6538 | 6608.6538 | 6608.6538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7136 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16974.9656 | 0.2 | 0.3 | 26480.9463 |  |  |  |  | 0 | 5203.7676 | 5203.7676 | 5203.7676 | 5203.7676 | 5203.7676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7137 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16675.9035 | 0.2 | 0.3 | 26014.4095 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7138 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16676.252 | 0.2 | 0.3 | 26014.9531 |  |  |  |  | 0 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7139 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16671.4071 | 0.2 | 0.3 | 26007.3951 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7140 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7141 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16672.5421 | 0.2 | 0.3 | 26009.1656 |  |  |  |  | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7142 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 17975.6638 | 0.2 | 0.3 | 28042.0355 |  |  |  |  | 0 | 6567.2919 | 6567.2919 | 6567.2919 | 6567.2919 | 6567.2919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7143 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16955.6997 | 0.2 | 0.3 | 26450.8916 |  |  |  |  | 0 | 5204.9153 | 5204.9153 | 5204.9153 | 5204.9153 | 5204.9153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7144 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16849.5506 | 0.2 | 0.3 | 26285.2989 |  |  |  |  | 0 | 5204.944 | 5204.944 | 5204.944 | 5204.944 | 5204.944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7145 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 9723.6068 | 9723.6068 | 9723.6068 | 9723.6068 | 9723.6068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7146 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16671.4521 | 0.2 | 0.3 | 26007.4653 |  |  |  |  | 0 | 5205.6091 | 5205.6091 | 5205.6091 | 5205.6091 | 5205.6091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7147 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 20814.0096 | 0.2 | 0.3 | 32469.855 |  |  |  |  | 0 | 9782.9214 | 9782.9214 | 9782.9214 | 9782.9214 | 9782.9214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7148 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 23830.4565 | 0.2 | 0.3 | 37175.5122 |  |  |  |  | 0 | 5204.4171 | 5204.4171 | 5204.4171 | 5204.4171 | 5204.4171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7149 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 15442.6893 | 0.2 | 0.3 | 24090.5953 |  |  |  |  | 0 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7150 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 18039.5131 | 0.2 | 0.3 | 28141.6404 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7151 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 28291.2881 | 0.2 | 0.3 | 44134.4094 |  |  |  |  | 0 | 6535.6935 | 6535.6935 | 6535.6935 | 6535.6935 | 6535.6935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7152 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 22820.2769 | 0.2 | 0.3 | 35599.632 |  |  |  |  | 0 | 5310.7555 | 5310.7555 | 5310.7555 | 5310.7555 | 5310.7555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7153 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16079.8424 | 0.2 | 0.3 | 25084.5541 |  |  |  |  | 0 | 4685.0262 | 4685.0262 | 4685.0262 | 4685.0262 | 4685.0262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7154 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 17055.2984 | 0.2 | 0.3 | 26606.2655 |  |  |  |  | 0 | 5112.6853 | 5112.6853 | 5112.6853 | 5112.6853 | 5112.6853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7155 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 828.8959 | 0.2 | 0.3 | 1293.0777 |  |  |  |  | 0 | 9791.6133 | 9791.6133 | 9791.6133 | 9791.6133 | 9791.6133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7156 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 22872.1795 | 0.2 | 0.3 | 35680.6001 |  |  |  |  | 0 | 7038.0012 | 7038.0012 | 7038.0012 | 7038.0012 | 7038.0012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7157 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 10546.2063 | 0.2 | 0.3 | 16452.0818 |  |  |  |  | 0 | 7248.3326 | 7248.3326 | 7248.3326 | 7248.3326 | 7248.3326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7158 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 27352.3052 | 0.2 | 0.3 | 42669.5961 |  |  |  |  | 0 | 9779.3742 | 9779.3742 | 9779.3742 | 9779.3742 | 9779.3742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7159 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 25802.6459 | 0.2 | 0.3 | 40252.1277 |  |  |  |  | 0 | 5201.9613 | 5201.9613 | 5201.9613 | 5201.9613 | 5201.9613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7160 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17905.1833 | 0.2 | 0.3 | 27932.086 |  |  |  |  | 0 | 12023.2913 | 12023.2913 | 12023.2913 | 12023.2913 | 12023.2913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7161 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17260.8725 | 0.2 | 0.3 | 26926.961 |  |  |  |  | 0 | 6583.7639 | 6583.7639 | 6583.7639 | 6583.7639 | 6583.7639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7162 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17929.9742 | 0.2 | 0.3 | 27970.7598 |  |  |  |  | 0 | 1682.308 | 1682.308 | 1682.308 | 1682.308 | 1682.308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7163 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 1438.2805 | 0.2 | 0.3 | 2243.7175 |  |  |  |  | 0 | 8893.8926 | 8893.8926 | 8893.8926 | 8893.8926 | 8893.8926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7164 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16671.4117 | 0.2 | 0.3 | 26007.4023 |  |  |  |  | 0 | 7424.0221 | 7424.0221 | 7424.0221 | 7424.0221 | 7424.0221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7165 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 18858.6917 | 0.2 | 0.3 | 29419.5591 |  |  |  |  | 0 | 5461.9326 | 5461.9326 | 5461.9326 | 5461.9326 | 5461.9326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7166 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 22492.7897 | 0.2 | 0.3 | 35088.7519 |  |  |  |  | 0 | 5205.7367 | 5205.7367 | 5205.7367 | 5205.7367 | 5205.7367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7167 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 15954.5545 | 0.2 | 0.3 | 24889.105 |  |  |  |  | 0 | 5204.121 | 5204.121 | 5204.121 | 5204.121 | 5204.121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7168 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 28813.4705 | 0.2 | 0.3 | 44949.0139 |  |  |  |  | 0 | 4845.8649 | 4845.8649 | 4845.8649 | 4845.8649 | 4845.8649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7169 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 7179.9132 | 0.2 | 0.3 | 11200.6646 |  |  |  |  | 0 | 359.985 | 359.985 | 359.985 | 359.985 | 359.985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7170 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 17056.0083 | 0.2 | 0.3 | 26607.373 |  |  |  |  | 0 | 7266.2924 | 7266.2924 | 7266.2924 | 7266.2924 | 7266.2924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7171 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16802.2721 | 0.2 | 0.3 | 26211.5445 |  |  |  |  | 0 | 9189.5452 | 9189.5452 | 9189.5452 | 9189.5452 | 9189.5452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7172 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 22752.3096 | 0.2 | 0.3 | 35493.603 |  |  |  |  | 0 | 9783.1022 | 9783.1022 | 9783.1022 | 9783.1022 | 9783.1022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7173 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16670.5603 | 0.2 | 0.3 | 26006.0741 |  |  |  |  | 0 | 5786.7201 | 5786.7201 | 5786.7201 | 5786.7201 | 5786.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7174 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 19494.8685 | 0.2 | 0.3 | 30411.9949 |  |  |  |  | 0 | 9785.8915 | 9785.8915 | 9785.8915 | 9785.8915 | 9785.8915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7175 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 13231.1652 | 0.2 | 0.3 | 20640.6177 |  |  |  |  | 0 | 9785.4855 | 9785.4855 | 9785.4855 | 9785.4855 | 9785.4855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7176 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 24721.2807 | 0.2 | 0.3 | 38565.1979 |  |  |  |  | 0 | 7196.9065 | 7196.9065 | 7196.9065 | 7196.9065 | 7196.9065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7177 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 23867.9583 | 0.2 | 0.3 | 37234.0149 |  |  |  |  | 0 | 6985.7529 | 6985.7529 | 6985.7529 | 6985.7529 | 6985.7529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7178 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 25208.1034 | 0.2 | 0.3 | 39324.6413 |  |  |  |  | 0 | 5205.569 | 5205.569 | 5205.569 | 5205.569 | 5205.569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7179 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 36746.2752 | 0.2 | 0.3 | 57324.1893 |  |  |  |  | 0 | 5205.7174 | 5205.7174 | 5205.7174 | 5205.7174 | 5205.7174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7180 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 24733.9797 | 0.2 | 0.3 | 38585.0084 |  |  |  |  | 0 | 9782.0357 | 9782.0357 | 9782.0357 | 9782.0357 | 9782.0357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7181 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16671.2479 | 0.2 | 0.3 | 26007.1467 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7182 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 23282.5994 | 0.2 | 0.3 | 36320.8551 |  |  |  |  | 0 | 9783.6473 | 9783.6473 | 9783.6473 | 9783.6473 | 9783.6473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7183 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17008.0979 | 0.2 | 0.3 | 26532.6328 |  |  |  |  | 0 | 5204.8752 | 5204.8752 | 5204.8752 | 5204.8752 | 5204.8752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7184 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16668.986 | 0.2 | 0.3 | 26003.6182 |  |  |  |  | 0 | 5205.3532 | 5205.3532 | 5205.3532 | 5205.3532 | 5205.3532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7185 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 22639.4921 | 0.2 | 0.3 | 35317.6076 |  |  |  |  | 0 | 5205.3532 | 5205.3532 | 5205.3532 | 5205.3532 | 5205.3532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7186 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 4657.2442 | 0.2 | 0.3 | 7265.301 |  |  |  |  | 0 | 4279.5437 | 4279.5437 | 4279.5437 | 4279.5437 | 4279.5437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7187 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17057.5474 | 0.2 | 0.3 | 26609.7739 |  |  |  |  | 0 | 6300.2838 | 6300.2838 | 6300.2838 | 6300.2838 | 6300.2838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7188 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 2658.7989 | 0.2 | 0.3 | 4147.7263 |  |  |  |  | 0 | 5132.7682 | 5132.7682 | 5132.7682 | 5132.7682 | 5132.7682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7189 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 1427.02 | 0.2 | 0.3 | 2226.1512 |  |  |  |  | 0 | 9042.8938 | 9042.8938 | 9042.8938 | 9042.8938 | 9042.8938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7190 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 13967.4249 | 0.2 | 0.3 | 21789.1828 |  |  |  |  | 0 | 7858.0155 | 7858.0155 | 7858.0155 | 7858.0155 | 7858.0155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7191 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 14807.9603 | 0.2 | 0.3 | 23100.418 |  |  |  |  | 0 | 2322.3149 | 2322.3149 | 2322.3149 | 2322.3149 | 2322.3149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7192 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 8977.8163 | 0.2 | 0.3 | 14005.3935 |  |  |  |  | 0 | 5429.5668 | 5429.5668 | 5429.5668 | 5429.5668 | 5429.5668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7193 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 33204.6124 | 0.2 | 0.3 | 51799.1953 |  |  |  |  | 0 | 11704.3393 | 11704.3393 | 11704.3393 | 11704.3393 | 11704.3393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7194 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17072.1229 | 0.2 | 0.3 | 26632.5118 |  |  |  |  | 0 | 14354.9079 | 14354.9079 | 14354.9079 | 14354.9079 | 14354.9079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7195 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16855.5207 | 0.2 | 0.3 | 26294.6122 |  |  |  |  | 0 | 10406.434 | 10406.434 | 10406.434 | 10406.434 | 10406.434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7196 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 23492.2553 | 0.2 | 0.3 | 36647.9182 |  |  |  |  | 0 | 12468.5617 | 12468.5617 | 12468.5617 | 12468.5617 | 12468.5617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7197 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 33561.9181 | 0.2 | 0.3 | 52356.5922 |  |  |  |  | 0 | 12354.4712 | 12354.4712 | 12354.4712 | 12354.4712 | 12354.4712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7198 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 24980.8905 | 0.2 | 0.3 | 38970.1891 |  |  |  |  | 0 | 6669.3166 | 6669.3166 | 6669.3166 | 6669.3166 | 6669.3166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7199 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 22904.3334 | 0.2 | 0.3 | 35730.7601 |  |  |  |  | 0 | 5201.2163 | 5201.2163 | 5201.2163 | 5201.2163 | 5201.2163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7200 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16717.6685 | 0.2 | 0.3 | 26079.5629 |  |  |  |  | 0 | 6982.201 | 6982.201 | 6982.201 | 6982.201 | 6982.201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7201 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 25860.6815 | 0.2 | 0.3 | 40342.6632 |  |  |  |  | 0 | 9795.2492 | 9795.2492 | 9795.2492 | 9795.2492 | 9795.2492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7202 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 13169.9623 | 0.2 | 0.3 | 20545.1412 |  |  |  |  | 0 | 9759.3886 | 9759.3886 | 9759.3886 | 9759.3886 | 9759.3886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7203 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16738.2507 | 0.2 | 0.3 | 26111.6711 |  |  |  |  | 0 | 9780.4201 | 9780.4201 | 9780.4201 | 9780.4201 | 9780.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7204 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 13871.7552 | 0.2 | 0.3 | 21639.9381 |  |  |  |  | 0 | 9783.924 | 9783.924 | 9783.924 | 9783.924 | 9783.924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7205 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 15808.3469 | 0.2 | 0.3 | 24661.0211 |  |  |  |  | 0 | 9783.9957 | 9783.9957 | 9783.9957 | 9783.9957 | 9783.9957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7206 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 7485.2467 | 7485.2467 | 7485.2467 | 7485.2467 | 7485.2467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7207 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 21699.8011 | 0.2 | 0.3 | 33851.6898 |  |  |  |  | 0 | 8055.4897 | 8055.4897 | 8055.4897 | 8055.4897 | 8055.4897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7208 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 12939.0145 | 0.2 | 0.3 | 20184.8627 |  |  |  |  | 0 | 7199.2832 | 7199.2832 | 7199.2832 | 7199.2832 | 7199.2832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7209 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16749.9075 | 0.2 | 0.3 | 26129.8556 |  |  |  |  | 0 | 5795.6373 | 5795.6373 | 5795.6373 | 5795.6373 | 5795.6373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7210 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 35460.0411 | 0.2 | 0.3 | 55317.6641 |  |  |  |  | 0 | 5202.6525 | 5202.6525 | 5202.6525 | 5202.6525 | 5202.6525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7211 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 2153.5798 | 0.2 | 0.3 | 3359.5845 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7212 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 678.5957 | 0.2 | 0.3 | 1058.6092 |  |  |  |  | 0 | 5203.4542 | 5203.4542 | 5203.4542 | 5203.4542 | 5203.4542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7213 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 16649.0804 | 0.2 | 0.3 | 25972.5654 |  |  |  |  | 0 | 3111.4108 | 3111.4108 | 3111.4108 | 3111.4108 | 3111.4108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7214 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17352.1868 | 0.2 | 0.3 | 27069.4114 |  |  |  |  | 0 | 4432.3144 | 4432.3144 | 4432.3144 | 4432.3144 | 4432.3144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7215 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 15955.1541 | 0.2 | 0.3 | 24890.0404 |  |  |  |  | 0 | 5213.135 | 5213.135 | 5213.135 | 5213.135 | 5213.135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7216 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 13934.3855 | 0.2 | 0.3 | 21737.6414 |  |  |  |  | 0 | 6471.4227 | 6471.4227 | 6471.4227 | 6471.4227 | 6471.4227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7217 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 11500.3241 | 0.2 | 0.3 | 17940.5055 |  |  |  |  | 0 | 5208.5681 | 5208.5681 | 5208.5681 | 5208.5681 | 5208.5681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7218 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16889.4228 | 0.2 | 0.3 | 26347.4996 |  |  |  |  | 0 | 11969.9109 | 11969.9109 | 11969.9109 | 11969.9109 | 11969.9109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7219 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16672.0647 | 0.2 | 0.3 | 26008.4209 |  |  |  |  | 0 | 5306.8321 | 5306.8321 | 5306.8321 | 5306.8321 | 5306.8321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7220 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16675.687 | 0.2 | 0.3 | 26014.0717 |  |  |  |  | 0 | 5204.0815 | 5204.0815 | 5204.0815 | 5204.0815 | 5204.0815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7221 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16674.2553 | 0.2 | 0.3 | 26011.8382 |  |  |  |  | 0 | 8253.0321 | 8253.0321 | 8253.0321 | 8253.0321 | 8253.0321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7222 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16672.8883 | 0.2 | 0.3 | 26009.7057 |  |  |  |  | 0 | 4481.6301 | 4481.6301 | 4481.6301 | 4481.6301 | 4481.6301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7223 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 33339.2149 | 0.2 | 0.3 | 52009.1752 |  |  |  |  | 0 | 4256.6506 | 4256.6506 | 4256.6506 | 4256.6506 | 4256.6506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7224 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 346.1499 | 0.2 | 0.3 | 539.9938 |  |  |  |  | 0 | 11135.6269 | 11135.6269 | 11135.6269 | 11135.6269 | 11135.6269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7225 | MIRAMAR | 110362 | Private | 2036 | 5 | Swales | 66.6667 | 17032.6602 | 0.2 | 0.3 | 26570.9499 |  |  |  |  | 0 | 6842.3573 | 6842.3573 | 6842.3573 | 6842.3573 | 6842.3573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7226 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16450.4401 | 0.2 | 0.3 | 25662.6866 |  |  |  |  | 0 | 6901.1382 | 6901.1382 | 6901.1382 | 6901.1382 | 6901.1382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7227 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 21348.0863 | 0.2 | 0.3 | 33303.0146 |  |  |  |  | 0 | 4272.6335 | 4272.6335 | 4272.6335 | 4272.6335 | 4272.6335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7228 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 7627.5396 | 0.2 | 0.3 | 11898.9618 |  |  |  |  | 0 | 5201.4863 | 5201.4863 | 5201.4863 | 5201.4863 | 5201.4863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7229 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 19170.4649 | 0.2 | 0.3 | 29905.9253 |  |  |  |  | 0 | 6946.2116 | 6946.2116 | 6946.2116 | 6946.2116 | 6946.2116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7230 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 3846.9975 | 0.2 | 0.3 | 6001.316 |  |  |  |  | 0 | 9777.8096 | 9777.8096 | 9777.8096 | 9777.8096 | 9777.8096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7231 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 15086.3956 | 0.2 | 0.3 | 23534.7771 |  |  |  |  | 0 | 5203.1292 | 5203.1292 | 5203.1292 | 5203.1292 | 5203.1292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7232 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 3776.3331 | 0.2 | 0.3 | 5891.0797 |  |  |  |  | 0 | 6168.2804 | 6168.2804 | 6168.2804 | 6168.2804 | 6168.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7233 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 13654.9693 | 0.2 | 0.3 | 21301.7521 |  |  |  |  | 0 | 8959.9087 | 8959.9087 | 8959.9087 | 8959.9087 | 8959.9087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7234 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 17212.7879 | 0.2 | 0.3 | 26851.9491 |  |  |  |  | 0 | 1325.6724 | 1325.6724 | 1325.6724 | 1325.6724 | 1325.6724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7235 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 19045.4261 | 0.2 | 0.3 | 29710.8648 |  |  |  |  | 0 | 5205.351 | 5205.351 | 5205.351 | 5205.351 | 5205.351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7236 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16674.3144 | 0.2 | 0.3 | 26011.9305 |  |  |  |  | 0 | 5202.2517 | 5202.2517 | 5202.2517 | 5202.2517 | 5202.2517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7237 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 17375.8473 | 0.2 | 0.3 | 27106.3217 |  |  |  |  | 0 | 5314.7111 | 5314.7111 | 5314.7111 | 5314.7111 | 5314.7111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7238 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 18910.1545 | 0.2 | 0.3 | 29499.8411 |  |  |  |  | 0 | 4496.3818 | 4496.3818 | 4496.3818 | 4496.3818 | 4496.3818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7239 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16770.6951 | 0.2 | 0.3 | 26162.2844 |  |  |  |  | 0 | 5203.1015 | 5203.1015 | 5203.1015 | 5203.1015 | 5203.1015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7240 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 38542.5893 | 0.2 | 0.3 | 60126.4393 |  |  |  |  | 0 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7241 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 8914.5008 | 0.2 | 0.3 | 13906.6212 |  |  |  |  | 0 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7242 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 19319.1485 | 0.2 | 0.3 | 30137.8716 |  |  |  |  | 0 | 1079.8801 | 1079.8801 | 1079.8801 | 1079.8801 | 1079.8801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7243 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 17597.5899 | 0.2 | 0.3 | 27452.2402 |  |  |  |  | 0 | 4123.1514 | 4123.1514 | 4123.1514 | 4123.1514 | 4123.1514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7244 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 9352.5658 | 0.2 | 0.3 | 14590.0026 |  |  |  |  | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7245 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 22563.5087 | 0.2 | 0.3 | 35199.0735 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7246 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 24950.125 | 0.2 | 0.3 | 38922.195 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7247 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 26837.8101 | 0.2 | 0.3 | 41866.9837 |  |  |  |  | 0 | 5202.6475 | 5202.6475 | 5202.6475 | 5202.6475 | 5202.6475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7248 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 30552.5697 | 0.2 | 0.3 | 47662.0087 |  |  |  |  | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7249 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 31598.0867 | 0.2 | 0.3 | 49293.0153 |  |  |  |  | 0 | 9022.8941 | 9022.8941 | 9022.8941 | 9022.8941 | 9022.8941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7250 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16718.4279 | 0.2 | 0.3 | 26080.7476 |  |  |  |  | 0 | 9147.3664 | 9147.3664 | 9147.3664 | 9147.3664 | 9147.3664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7251 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 5456.5806 | 5456.5806 | 5456.5806 | 5456.5806 | 5456.5806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7252 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 15524.9742 | 0.2 | 0.3 | 24218.9598 |  |  |  |  | 0 | 5204.2237 | 5204.2237 | 5204.2237 | 5204.2237 | 5204.2237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7253 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 17147.2529 | 0.2 | 0.3 | 26749.7146 |  |  |  |  | 0 | 5374.2563 | 5374.2563 | 5374.2563 | 5374.2563 | 5374.2563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7254 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 29523.7669 | 0.2 | 0.3 | 46057.0764 |  |  |  |  | 0 | 5313.8853 | 5313.8853 | 5313.8853 | 5313.8853 | 5313.8853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7255 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 39398.9831 | 0.2 | 0.3 | 61462.4137 |  |  |  |  | 0 | 5773.3791 | 5773.3791 | 5773.3791 | 5773.3791 | 5773.3791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7256 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 19931.3631 | 0.2 | 0.3 | 31092.9264 |  |  |  |  | 0 | 5205.4078 | 5205.4078 | 5205.4078 | 5205.4078 | 5205.4078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7257 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16978.2789 | 0.2 | 0.3 | 26486.1151 |  |  |  |  | 0 | 6896.946 | 6896.946 | 6896.946 | 6896.946 | 6896.946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7258 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 23053.314 | 0.2 | 0.3 | 35963.1698 |  |  |  |  | 0 | 8450.7966 | 8450.7966 | 8450.7966 | 8450.7966 | 8450.7966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7259 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 9797.8503 | 0.2 | 0.3 | 15284.6464 |  |  |  |  | 0 | 6734.5433 | 6734.5433 | 6734.5433 | 6734.5433 | 6734.5433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7260 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16881.6125 | 0.2 | 0.3 | 26335.3154 |  |  |  |  | 0 | 6954.1337 | 6954.1337 | 6954.1337 | 6954.1337 | 6954.1337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7261 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 33323.0053 | 0.2 | 0.3 | 51983.8882 |  |  |  |  | 0 | 5264.495 | 5264.495 | 5264.495 | 5264.495 | 5264.495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7262 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 23296.5527 | 0.2 | 0.3 | 36342.6223 |  |  |  |  | 0 | 4593.5695 | 4593.5695 | 4593.5695 | 4593.5695 | 4593.5695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7263 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 20880.8617 | 0.2 | 0.3 | 32574.1442 |  |  |  |  | 0 | 5201.5237 | 5201.5237 | 5201.5237 | 5201.5237 | 5201.5237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7264 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 11190.6627 | 0.2 | 0.3 | 17457.4339 |  |  |  |  | 0 | 6844.5293 | 6844.5293 | 6844.5293 | 6844.5293 | 6844.5293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7265 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 19289.373 | 0.2 | 0.3 | 30091.4219 |  |  |  |  | 0 | 9779.6814 | 9779.6814 | 9779.6814 | 9779.6814 | 9779.6814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7266 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 17110.5156 | 0.2 | 0.3 | 26692.4043 |  |  |  |  | 0 | 5201.1434 | 5201.1434 | 5201.1434 | 5201.1434 | 5201.1434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7267 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 18720.4504 | 0.2 | 0.3 | 29203.9026 |  |  |  |  | 0 | 6204.5282 | 6204.5282 | 6204.5282 | 6204.5282 | 6204.5282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7268 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 21149.0203 | 0.2 | 0.3 | 32992.4717 |  |  |  |  | 0 | 7803.1725 | 7803.1725 | 7803.1725 | 7803.1725 | 7803.1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7269 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 7836.0608 | 0.2 | 0.3 | 12224.2548 |  |  |  |  | 0 | 7747.932 | 7747.932 | 7747.932 | 7747.932 | 7747.932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7270 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 21300.9739 | 0.2 | 0.3 | 33229.5193 |  |  |  |  | 0 | 5205.2343 | 5205.2343 | 5205.2343 | 5205.2343 | 5205.2343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7271 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16673.1392 | 0.2 | 0.3 | 26010.0972 |  |  |  |  | 0 | 5202.0463 | 5202.0463 | 5202.0463 | 5202.0463 | 5202.0463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7272 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16676.0245 | 0.2 | 0.3 | 26014.5982 |  |  |  |  | 0 | 5201.6599 | 5201.6599 | 5201.6599 | 5201.6599 | 5201.6599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7273 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 15736.7154 | 0.2 | 0.3 | 24549.276 |  |  |  |  | 0 | 0.42736 | 0.42736 | 0.42736 | 0.42736 | 0.42736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7274 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 33276.4723 | 0.2 | 0.3 | 51911.2967 |  |  |  |  | 0 | 5203.1014 | 5203.1014 | 5203.1014 | 5203.1014 | 5203.1014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7275 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 24428.9731 | 0.2 | 0.3 | 38109.198 |  |  |  |  | 0 | 5433.8649 | 5433.8649 | 5433.8649 | 5433.8649 | 5433.8649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7276 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 12976.6653 | 0.2 | 0.3 | 20243.5979 |  |  |  |  | 0 | 7356.3196 | 7356.3196 | 7356.3196 | 7356.3196 | 7356.3196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7277 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 21911.4347 | 0.2 | 0.3 | 34181.8381 |  |  |  |  | 0 | 4331.0818 | 4331.0818 | 4331.0818 | 4331.0818 | 4331.0818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7278 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16506.1245 | 0.2 | 0.3 | 25749.5543 |  |  |  |  | 0 | 9781.8354 | 9781.8354 | 9781.8354 | 9781.8354 | 9781.8354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7279 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 23646.4685 | 0.2 | 0.3 | 36888.4909 |  |  |  |  | 0 | 9784.3644 | 9784.3644 | 9784.3644 | 9784.3644 | 9784.3644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7280 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 7973.9674 | 0.2 | 0.3 | 12439.3891 |  |  |  |  | 0 | 9783.2755 | 9783.2755 | 9783.2755 | 9783.2755 | 9783.2755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7281 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16794.5059 | 0.2 | 0.3 | 26199.4292 |  |  |  |  | 0 | 8601.8713 | 8601.8713 | 8601.8713 | 8601.8713 | 8601.8713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7282 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16721.2375 | 0.2 | 0.3 | 26085.1306 |  |  |  |  | 0 | 8721.8677 | 8721.8677 | 8721.8677 | 8721.8677 | 8721.8677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7283 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16789.3541 | 0.2 | 0.3 | 26191.3924 |  |  |  |  | 0 | 9780.7227 | 9780.7227 | 9780.7227 | 9780.7227 | 9780.7227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7284 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16721.7761 | 0.2 | 0.3 | 26085.9708 |  |  |  |  | 0 | 9781.8378 | 9781.8378 | 9781.8378 | 9781.8378 | 9781.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7285 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16799.0309 | 0.2 | 0.3 | 26206.4883 |  |  |  |  | 0 | 12406.6904 | 12406.6904 | 12406.6904 | 12406.6904 | 12406.6904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7286 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16732.8817 | 0.2 | 0.3 | 26103.2954 |  |  |  |  | 0 | 5205.5892 | 5205.5892 | 5205.5892 | 5205.5892 | 5205.5892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7287 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 35.4804 | 0.2 | 0.3 | 55.3494 |  |  |  |  | 0 | 9783.6532 | 9783.6532 | 9783.6532 | 9783.6532 | 9783.6532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7288 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 23195.2536 | 0.2 | 0.3 | 36184.5956 |  |  |  |  | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7289 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 23939.7101 | 0.2 | 0.3 | 37345.9477 |  |  |  |  | 0 | 5204.2921 | 5204.2921 | 5204.2921 | 5204.2921 | 5204.2921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7290 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 39493.0605 | 0.2 | 0.3 | 61609.1744 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7291 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 26627.8921 | 0.2 | 0.3 | 41539.5117 |  |  |  |  | 0 | 5204.096 | 5204.096 | 5204.096 | 5204.096 | 5204.096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7292 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 23374.5963 | 0.2 | 0.3 | 36464.3703 |  |  |  |  | 0 | 9131.6929 | 9131.6929 | 9131.6929 | 9131.6929 | 9131.6929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7293 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16674.6361 | 0.2 | 0.3 | 26012.4323 |  |  |  |  | 0 | 2439.7721 | 2439.7721 | 2439.7721 | 2439.7721 | 2439.7721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7294 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16671.6467 | 0.2 | 0.3 | 26007.7689 |  |  |  |  | 0 | 4145.4985 | 4145.4985 | 4145.4985 | 4145.4985 | 4145.4985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7295 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 1802.3599 | 0.2 | 0.3 | 2811.6815 |  |  |  |  | 0 | 11650.3461 | 11650.3461 | 11650.3461 | 11650.3461 | 11650.3461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7296 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 5387.9197 | 0.2 | 0.3 | 8405.1548 |  |  |  |  | 0 | 8703.5299 | 8703.5299 | 8703.5299 | 8703.5299 | 8703.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7297 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 24658.0469 | 0.2 | 0.3 | 38466.5532 |  |  |  |  | 0 | 5913.9211 | 5913.9211 | 5913.9211 | 5913.9211 | 5913.9211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7298 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17188.4945 | 0.2 | 0.3 | 26814.0515 |  |  |  |  | 0 | 12307.0084 | 12307.0084 | 12307.0084 | 12307.0084 | 12307.0084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7299 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 23398.1085 | 0.2 | 0.3 | 36501.0493 |  |  |  |  | 0 | 5297.8625 | 5297.8625 | 5297.8625 | 5297.8625 | 5297.8625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7300 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 17618.9032 | 0.2 | 0.3 | 27485.489 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7301 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 4156.4487 | 0.2 | 0.3 | 6484.06 |  |  |  |  | 0 | 5202.9674 | 5202.9674 | 5202.9674 | 5202.9674 | 5202.9674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7302 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 17036.9446 | 0.2 | 0.3 | 26577.6336 |  |  |  |  | 0 | 2403.951 | 2403.951 | 2403.951 | 2403.951 | 2403.951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7303 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16929.9997 | 0.2 | 0.3 | 26410.7995 |  |  |  |  | 0 | 7499.4189 | 7499.4189 | 7499.4189 | 7499.4189 | 7499.4189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7304 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16751.8035 | 0.2 | 0.3 | 26132.8135 |  |  |  |  | 0 | 9766.377 | 9766.377 | 9766.377 | 9766.377 | 9766.377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7305 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16727.3051 | 0.2 | 0.3 | 26094.5959 |  |  |  |  | 0 | 8268.768 | 8268.768 | 8268.768 | 8268.768 | 8268.768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7306 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16704.2517 | 0.2 | 0.3 | 26058.6327 |  |  |  |  | 0 | 1186.787 | 1186.787 | 1186.787 | 1186.787 | 1186.787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7307 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 17770.0141 | 0.2 | 0.3 | 27721.2219 |  |  |  |  | 0 | 32.5378 | 32.5378 | 32.5378 | 32.5378 | 32.5378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7308 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 19591.0453 | 0.2 | 0.3 | 30562.0307 |  |  |  |  | 0 | 5202.821 | 5202.821 | 5202.821 | 5202.821 | 5202.821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7309 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 8298.1995 | 0.2 | 0.3 | 12945.1912 |  |  |  |  | 0 | 7552.5072 | 7552.5072 | 7552.5072 | 7552.5072 | 7552.5072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7310 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 36474.2265 | 0.2 | 0.3 | 56899.7934 |  |  |  |  | 0 | 10145.1446 | 10145.1446 | 10145.1446 | 10145.1446 | 10145.1446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7311 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 23544.8132 | 0.2 | 0.3 | 36729.9086 |  |  |  |  | 0 | 8808.1591 | 8808.1591 | 8808.1591 | 8808.1591 | 8808.1591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7312 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 36821.8351 | 0.2 | 0.3 | 57442.0628 |  |  |  |  | 0 | 9781.1099 | 9781.1099 | 9781.1099 | 9781.1099 | 9781.1099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7313 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 36465.3678 | 0.2 | 0.3 | 56885.9738 |  |  |  |  | 0 | 9213.4769 | 9213.4769 | 9213.4769 | 9213.4769 | 9213.4769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7314 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16674.4403 | 0.2 | 0.3 | 26012.1268 |  |  |  |  | 0 | 1400.5203 | 1400.5203 | 1400.5203 | 1400.5203 | 1400.5203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7315 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 23560.6341 | 0.2 | 0.3 | 36754.5891 |  |  |  |  | 0 | 4306.3265 | 4306.3265 | 4306.3265 | 4306.3265 | 4306.3265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7316 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 17994.8287 | 0.2 | 0.3 | 28071.9327 |  |  |  |  | 0 | 5215.8863 | 5215.8863 | 5215.8863 | 5215.8863 | 5215.8863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7317 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 26190.1057 | 0.2 | 0.3 | 40856.5648 |  |  |  |  | 0 | 9781.8736 | 9781.8736 | 9781.8736 | 9781.8736 | 9781.8736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7318 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 34271.9741 | 0.2 | 0.3 | 53464.2796 |  |  |  |  | 0 | 9553.4151 | 9553.4151 | 9553.4151 | 9553.4151 | 9553.4151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7319 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 28175.0612 | 0.2 | 0.3 | 43953.0955 |  |  |  |  | 0 | 7633.3791 | 7633.3791 | 7633.3791 | 7633.3791 | 7633.3791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7320 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16904.7467 | 0.2 | 0.3 | 26371.4048 |  |  |  |  | 0 | 870.7542 | 870.7542 | 870.7542 | 870.7542 | 870.7542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7321 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16791.774 | 0.2 | 0.3 | 26195.1674 |  |  |  |  | 0 | 5203.8491 | 5203.8491 | 5203.8491 | 5203.8491 | 5203.8491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7322 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17740.5629 | 0.2 | 0.3 | 27675.2781 |  |  |  |  | 0 | 5203.4376 | 5203.4376 | 5203.4376 | 5203.4376 | 5203.4376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7323 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 21362.1662 | 0.2 | 0.3 | 33324.9793 |  |  |  |  | 0 | 5202.8245 | 5202.8245 | 5202.8245 | 5202.8245 | 5202.8245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7324 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 27803.5035 | 0.2 | 0.3 | 43373.4655 |  |  |  |  | 0 | 5204.1258 | 5204.1258 | 5204.1258 | 5204.1258 | 5204.1258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7325 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 23437.3854 | 0.2 | 0.3 | 36562.3212 |  |  |  |  | 0 | 5203.5685 | 5203.5685 | 5203.5685 | 5203.5685 | 5203.5685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7326 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16694.5247 | 0.2 | 0.3 | 26043.4586 |  |  |  |  | 0 | 5206.0454 | 5206.0454 | 5206.0454 | 5206.0454 | 5206.0454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7327 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16661.6479 | 0.2 | 0.3 | 25992.1708 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7328 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 25653.418 | 0.2 | 0.3 | 40019.3321 |  |  |  |  | 0 | 5203.3291 | 5203.3291 | 5203.3291 | 5203.3291 | 5203.3291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7329 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6635 | 0.2 | 0.3 | 25999.9951 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7330 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 14753.2661 | 0.2 | 0.3 | 23015.0952 |  |  |  |  | 0 | 5203.4112 | 5203.4112 | 5203.4112 | 5203.4112 | 5203.4112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7331 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 14799.4545 | 0.2 | 0.3 | 23087.149 |  |  |  |  | 0 | 9783.0501 | 9783.0501 | 9783.0501 | 9783.0501 | 9783.0501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7332 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16740.4387 | 0.2 | 0.3 | 26115.0844 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7333 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16735.2558 | 0.2 | 0.3 | 26106.999 |  |  |  |  | 0 | 2404.241 | 2404.241 | 2404.241 | 2404.241 | 2404.241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7334 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16681.3574 | 0.2 | 0.3 | 26022.9175 |  |  |  |  | 0 | 4856.1037 | 4856.1037 | 4856.1037 | 4856.1037 | 4856.1037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7335 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 24093.4973 | 0.2 | 0.3 | 37585.8557 |  |  |  |  | 0 | 2330.3902 | 2330.3902 | 2330.3902 | 2330.3902 | 2330.3902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7336 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 12859.5127 | 0.2 | 0.3 | 20060.8399 |  |  |  |  | 0 | 2802.3299 | 2802.3299 | 2802.3299 | 2802.3299 | 2802.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7337 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 1898.8456 | 0.2 | 0.3 | 2962.1991 |  |  |  |  | 0 | 218.1066 | 218.1066 | 218.1066 | 218.1066 | 218.1066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7338 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 20530.5151 | 0.2 | 0.3 | 32027.6035 |  |  |  |  | 0 | 8473.8448 | 8473.8448 | 8473.8448 | 8473.8448 | 8473.8448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7339 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 9501.1593 | 0.2 | 0.3 | 14821.8085 |  |  |  |  | 0 | 5567.1683 | 5567.1683 | 5567.1683 | 5567.1683 | 5567.1683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7340 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16665.1591 | 0.2 | 0.3 | 25997.6481 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7341 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16674.3819 | 0.2 | 0.3 | 26012.0358 |  |  |  |  | 0 | 2404.2653 | 2404.2653 | 2404.2653 | 2404.2653 | 2404.2653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7342 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 4656.2353 | 0.2 | 0.3 | 7263.727 |  |  |  |  | 0 | 5383.76 | 5383.76 | 5383.76 | 5383.76 | 5383.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7343 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 13311.0401 | 0.2 | 0.3 | 20765.2225 |  |  |  |  | 0 | 9782.7409 | 9782.7409 | 9782.7409 | 9782.7409 | 9782.7409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7344 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 18255.1957 | 0.2 | 0.3 | 28478.1052 |  |  |  |  | 0 | 9782.9559 | 9782.9559 | 9782.9559 | 9782.9559 | 9782.9559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7345 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 24084.3777 | 0.2 | 0.3 | 37571.6292 |  |  |  |  | 0 | 6859.2202 | 6859.2202 | 6859.2202 | 6859.2202 | 6859.2202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7346 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16426.2125 | 0.2 | 0.3 | 25624.8914 |  |  |  |  | 0 | 6912.1187 | 6912.1187 | 6912.1187 | 6912.1187 | 6912.1187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7347 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16686.9933 | 0.2 | 0.3 | 26031.7095 |  |  |  |  | 0 | 6484.3128 | 6484.3128 | 6484.3128 | 6484.3128 | 6484.3128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7348 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16711.9397 | 0.2 | 0.3 | 26070.626 |  |  |  |  | 0 | 5202.7274 | 5202.7274 | 5202.7274 | 5202.7274 | 5202.7274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7349 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17015.2727 | 0.2 | 0.3 | 26543.8254 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7350 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 29967.9127 | 0.2 | 0.3 | 46749.9438 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7351 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 18431.4753 | 0.2 | 0.3 | 28753.1015 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7352 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 23767.5953 | 0.2 | 0.3 | 37077.4486 |  |  |  |  | 0 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7353 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 0.1808 | 0.2 | 0.3 | 0.28205 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7354 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 19715.3133 | 0.2 | 0.3 | 30755.8888 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7355 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16676.3089 | 0.2 | 0.3 | 26015.0419 |  |  |  |  | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7356 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16672.4536 | 0.2 | 0.3 | 26009.0276 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7357 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 14732.4683 | 0.2 | 0.3 | 22982.6505 |  |  |  |  | 0 | 5203.3834 | 5203.3834 | 5203.3834 | 5203.3834 | 5203.3834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7358 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 17300.6603 | 0.2 | 0.3 | 26989.03 |  |  |  |  | 0 | 5202.6802 | 5202.6802 | 5202.6802 | 5202.6802 | 5202.6802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7359 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 15959.1515 | 0.2 | 0.3 | 24896.2763 |  |  |  |  | 0 | 5204.0446 | 5204.0446 | 5204.0446 | 5204.0446 | 5204.0446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7360 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 1674.8277 | 0.2 | 0.3 | 2612.7313 |  |  |  |  | 0 | 5203.5741 | 5203.5741 | 5203.5741 | 5203.5741 | 5203.5741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7361 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 24411.233 | 0.2 | 0.3 | 38081.5235 |  |  |  |  | 0 | 5205.7204 | 5205.7204 | 5205.7204 | 5205.7204 | 5205.7204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7362 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16687.1051 | 0.2 | 0.3 | 26031.884 |  |  |  |  | 0 | 5391.0596 | 5391.0596 | 5391.0596 | 5391.0596 | 5391.0596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7363 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17591.3619 | 0.2 | 0.3 | 27442.5246 |  |  |  |  | 0 | 9785.5976 | 9785.5976 | 9785.5976 | 9785.5976 | 9785.5976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7364 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17397.9959 | 0.2 | 0.3 | 27140.8736 |  |  |  |  | 0 | 5188.173 | 5188.173 | 5188.173 | 5188.173 | 5188.173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7365 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 21463.5983 | 0.2 | 0.3 | 33483.2134 |  |  |  |  | 0 | 9783.0776 | 9783.0776 | 9783.0776 | 9783.0776 | 9783.0776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7366 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 25174.6115 | 0.2 | 0.3 | 39272.3939 |  |  |  |  | 0 | 7221.6496 | 7221.6496 | 7221.6496 | 7221.6496 | 7221.6496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7367 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 25617.5511 | 0.2 | 0.3 | 39963.3798 |  |  |  |  | 0 | 5204.2374 | 5204.2374 | 5204.2374 | 5204.2374 | 5204.2374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7368 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 19902.3446 | 0.2 | 0.3 | 31047.6576 |  |  |  |  | 0 | 7942.6046 | 7942.6046 | 7942.6046 | 7942.6046 | 7942.6046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7369 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 5686.2471 | 5686.2471 | 5686.2471 | 5686.2471 | 5686.2471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7370 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16666.4377 | 0.2 | 0.3 | 25999.6428 |  |  |  |  | 0 | 5203.6206 | 5203.6206 | 5203.6206 | 5203.6206 | 5203.6206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7371 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 7385.8931 | 0.2 | 0.3 | 11521.9933 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7372 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16802.9084 | 0.2 | 0.3 | 26212.5371 |  |  |  |  | 0 | 5203.619 | 5203.619 | 5203.619 | 5203.619 | 5203.619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7373 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16693.751 | 0.2 | 0.3 | 26042.2516 |  |  |  |  | 0 | 9780.6903 | 9780.6903 | 9780.6903 | 9780.6903 | 9780.6903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7374 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16176.8529 | 0.2 | 0.3 | 25235.8905 |  |  |  |  | 0 | 5204.2009 | 5204.2009 | 5204.2009 | 5204.2009 | 5204.2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7375 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 4956.0291 | 0.2 | 0.3 | 7731.4054 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7376 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 27923.0413 | 0.2 | 0.3 | 43559.9444 |  |  |  |  | 0 | 5203.9071 | 5203.9071 | 5203.9071 | 5203.9071 | 5203.9071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7377 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 18525.6815 | 0.2 | 0.3 | 28900.0631 |  |  |  |  | 0 | 7999.8806 | 7999.8806 | 7999.8806 | 7999.8806 | 7999.8806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7378 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16811.4356 | 0.2 | 0.3 | 26225.8395 |  |  |  |  | 0 | 4060.7087 | 4060.7087 | 4060.7087 | 4060.7087 | 4060.7087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7379 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 11347.5795 | 0.2 | 0.3 | 17702.224 |  |  |  |  | 0 | 5357.447 | 5357.447 | 5357.447 | 5357.447 | 5357.447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7380 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 3870.4122 | 0.2 | 0.3 | 6037.843 |  |  |  |  | 0 | 5208.4594 | 5208.4594 | 5208.4594 | 5208.4594 | 5208.4594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7381 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 12237.9055 | 0.2 | 0.3 | 19091.1325 |  |  |  |  | 0 | 11286.9265 | 11286.9265 | 11286.9265 | 11286.9265 | 11286.9265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7382 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 29588.2525 | 0.2 | 0.3 | 46157.6738 |  |  |  |  | 0 | 5659.7852 | 5659.7852 | 5659.7852 | 5659.7852 | 5659.7852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7383 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 17091.7569 | 0.2 | 0.3 | 26663.1408 |  |  |  |  | 0 | 5844.4633 | 5844.4633 | 5844.4633 | 5844.4633 | 5844.4633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7384 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 14110.9539 | 0.2 | 0.3 | 22013.0881 |  |  |  |  | 0 | 5269.4392 | 5269.4392 | 5269.4392 | 5269.4392 | 5269.4392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7385 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 29914.0065 | 0.2 | 0.3 | 46665.8502 |  |  |  |  | 0 | 7443.9156 | 7443.9156 | 7443.9156 | 7443.9156 | 7443.9156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7386 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 29573.9547 | 0.2 | 0.3 | 46135.3694 |  |  |  |  | 0 | 9781.2701 | 9781.2701 | 9781.2701 | 9781.2701 | 9781.2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7387 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 44094.242 | 0.2 | 0.3 | 68787.0175 |  |  |  |  | 0 | 6631.0699 | 6631.0699 | 6631.0699 | 6631.0699 | 6631.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7388 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 2996.8745 | 0.2 | 0.3 | 4675.1242 |  |  |  |  | 0 | 2800.6929 | 2800.6929 | 2800.6929 | 2800.6929 | 2800.6929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7389 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 14117.1153 | 0.2 | 0.3 | 22022.6999 |  |  |  |  | 0 | 5201.553 | 5201.553 | 5201.553 | 5201.553 | 5201.553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7390 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 27017.7391 | 0.2 | 0.3 | 42147.6729 |  |  |  |  | 0 | 9781.7388 | 9781.7388 | 9781.7388 | 9781.7388 | 9781.7388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7391 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 20088.2588 | 0.2 | 0.3 | 31337.6837 |  |  |  |  | 0 | 9089.9658 | 9089.9658 | 9089.9658 | 9089.9658 | 9089.9658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7392 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 26966.7208 | 0.2 | 0.3 | 42068.0844 |  |  |  |  | 0 | 9784.607 | 9784.607 | 9784.607 | 9784.607 | 9784.607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7393 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 34230.3307 | 0.2 | 0.3 | 53399.3158 |  |  |  |  | 0 | 5203.7057 | 5203.7057 | 5203.7057 | 5203.7057 | 5203.7057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7394 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 17651.0874 | 0.2 | 0.3 | 27535.6963 |  |  |  |  | 0 | 9167.4996 | 9167.4996 | 9167.4996 | 9167.4996 | 9167.4996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7395 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16943.2905 | 0.2 | 0.3 | 26431.5331 |  |  |  |  | 0 | 9783.3147 | 9783.3147 | 9783.3147 | 9783.3147 | 9783.3147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7396 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 31380.9296 | 0.2 | 0.3 | 48954.2502 |  |  |  |  | 0 | 9784.0171 | 9784.0171 | 9784.0171 | 9784.0171 | 9784.0171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7397 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 46816.5828 | 0.2 | 0.3 | 73033.8692 |  |  |  |  | 0 | 9596.27 | 9596.27 | 9596.27 | 9596.27 | 9596.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7398 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 23638.1871 | 0.2 | 0.3 | 36875.5718 |  |  |  |  | 0 | 5203.1876 | 5203.1876 | 5203.1876 | 5203.1876 | 5203.1876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7399 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 20713.0331 | 0.2 | 0.3 | 32312.3316 |  |  |  |  | 0 | 4405.5909 | 4405.5909 | 4405.5909 | 4405.5909 | 4405.5909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7400 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 9459.9249 | 0.2 | 0.3 | 14757.4828 |  |  |  |  | 0 | 797.4539 | 797.4539 | 797.4539 | 797.4539 | 797.4539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7401 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 12576.9621 | 0.2 | 0.3 | 19620.0608 |  |  |  |  | 0 | 5203.0459 | 5203.0459 | 5203.0459 | 5203.0459 | 5203.0459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7402 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 18568.5537 | 0.2 | 0.3 | 28966.9438 |  |  |  |  | 0 | 5203.6654 | 5203.6654 | 5203.6654 | 5203.6654 | 5203.6654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7403 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 29464.2959 | 0.2 | 0.3 | 45964.3016 |  |  |  |  | 0 | 5203.7165 | 5203.7165 | 5203.7165 | 5203.7165 | 5203.7165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7404 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 23891.0498 | 0.2 | 0.3 | 37270.0377 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7405 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16670.5014 | 0.2 | 0.3 | 26005.9822 |  |  |  |  | 0 | 5203.8315 | 5203.8315 | 5203.8315 | 5203.8315 | 5203.8315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7406 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16667.2267 | 0.2 | 0.3 | 26000.8737 |  |  |  |  | 0 | 9781.2746 | 9781.2746 | 9781.2746 | 9781.2746 | 9781.2746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7407 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 14770.7612 | 0.2 | 0.3 | 23042.3875 |  |  |  |  | 0 | 5203.9345 | 5203.9345 | 5203.9345 | 5203.9345 | 5203.9345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7408 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 24175.5309 | 0.2 | 0.3 | 37713.8283 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7409 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 7313.6227 | 0.2 | 0.3 | 11409.2515 |  |  |  |  | 0 | 5204.1391 | 5204.1391 | 5204.1391 | 5204.1391 | 5204.1391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7410 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 26478.0595 | 0.2 | 0.3 | 41305.7729 |  |  |  |  | 0 | 9782.048 | 9782.048 | 9782.048 | 9782.048 | 9782.048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7411 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 6604.131 | 0.2 | 0.3 | 10302.4444 |  |  |  |  | 0 | 3543.7898 | 3543.7898 | 3543.7898 | 3543.7898 | 3543.7898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7412 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 29751.1819 | 0.2 | 0.3 | 46411.8437 |  |  |  |  | 0 | 982.3485 | 982.3485 | 982.3485 | 982.3485 | 982.3485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7413 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 19795.7496 | 0.2 | 0.3 | 30881.3694 |  |  |  |  | 0 | 9248.7708 | 9248.7708 | 9248.7708 | 9248.7708 | 9248.7708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7414 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 5203.7137 | 5203.7137 | 5203.7137 | 5203.7137 | 5203.7137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7415 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 22836.8038 | 0.2 | 0.3 | 35625.4139 |  |  |  |  | 0 | 5203.5932 | 5203.5932 | 5203.5932 | 5203.5932 | 5203.5932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7416 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 13095.8154 | 0.2 | 0.3 | 20429.472 |  |  |  |  | 0 | 14019.1623 | 14019.1623 | 14019.1623 | 14019.1623 | 14019.1623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7417 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 15084.7697 | 0.2 | 0.3 | 23532.2408 |  |  |  |  | 0 | 7045.233 | 7045.233 | 7045.233 | 7045.233 | 7045.233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7418 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 18974.0359 | 0.2 | 0.3 | 29599.496 |  |  |  |  | 0 | 414.443 | 414.443 | 414.443 | 414.443 | 414.443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7419 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16673.9973 | 0.2 | 0.3 | 26011.4357 |  |  |  |  | 0 | 2670.4531 | 2670.4531 | 2670.4531 | 2670.4531 | 2670.4531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7420 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 22740.0005 | 0.2 | 0.3 | 35474.4007 |  |  |  |  | 0 | 5204.8245 | 5204.8245 | 5204.8245 | 5204.8245 | 5204.8245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7421 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 6472.7446 | 0.2 | 0.3 | 10097.4816 |  |  |  |  | 0 | 5202.8187 | 5202.8187 | 5202.8187 | 5202.8187 | 5202.8187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7422 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16711.2863 | 0.2 | 0.3 | 26069.6066 |  |  |  |  | 0 | 5205.3284 | 5205.3284 | 5205.3284 | 5205.3284 | 5205.3284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7423 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16671.7503 | 0.2 | 0.3 | 26007.9304 |  |  |  |  | 0 | 5201.2001 | 5201.2001 | 5201.2001 | 5201.2001 | 5201.2001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7424 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16675.3017 | 0.2 | 0.3 | 26013.4707 |  |  |  |  | 0 | 2495.8907 | 2495.8907 | 2495.8907 | 2495.8907 | 2495.8907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7425 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 20330.7727 | 0.2 | 0.3 | 31716.0054 |  |  |  |  | 0 | 2709.7392 | 2709.7392 | 2709.7392 | 2709.7392 | 2709.7392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7426 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16829.0812 | 0.2 | 0.3 | 26253.3667 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7427 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 19319.9744 | 0.2 | 0.3 | 30139.1601 |  |  |  |  | 0 | 6731.8431 | 6731.8431 | 6731.8431 | 6731.8431 | 6731.8431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7428 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 2311.7217 | 0.2 | 0.3 | 3606.2859 |  |  |  |  | 0 | 6336.3643 | 6336.3643 | 6336.3643 | 6336.3643 | 6336.3643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7429 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16680.3525 | 0.2 | 0.3 | 26021.35 |  |  |  |  | 0 | 5203.1578 | 5203.1578 | 5203.1578 | 5203.1578 | 5203.1578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7430 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16673.7613 | 0.2 | 0.3 | 26011.0676 |  |  |  |  | 0 | 2601.5275 | 2601.5275 | 2601.5275 | 2601.5275 | 2601.5275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7431 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16724.2879 | 0.2 | 0.3 | 26089.8891 |  |  |  |  | 0 | 2601.5335 | 2601.5335 | 2601.5335 | 2601.5335 | 2601.5335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7432 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 17407.3441 | 0.2 | 0.3 | 27155.4568 |  |  |  |  | 0 | 5204.0354 | 5204.0354 | 5204.0354 | 5204.0354 | 5204.0354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7433 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 29207.4864 | 0.2 | 0.3 | 45563.6788 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7434 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 26196.2545 | 0.2 | 0.3 | 40866.157 |  |  |  |  | 0 | 5204.0753 | 5204.0753 | 5204.0753 | 5204.0753 | 5204.0753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7435 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 37074.0267 | 0.2 | 0.3 | 57835.4816 |  |  |  |  | 0 | 9783.7111 | 9783.7111 | 9783.7111 | 9783.7111 | 9783.7111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7436 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 21154.6445 | 0.2 | 0.3 | 33001.2455 |  |  |  |  | 0 | 5203.7252 | 5203.7252 | 5203.7252 | 5203.7252 | 5203.7252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7437 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 22535.0994 | 0.2 | 0.3 | 35154.7551 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7438 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 24324.3753 | 0.2 | 0.3 | 37946.0255 |  |  |  |  | 0 | 5203.6914 | 5203.6914 | 5203.6914 | 5203.6914 | 5203.6914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7439 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 20820.7499 | 0.2 | 0.3 | 32480.3698 |  |  |  |  | 0 | 9782.2664 | 9782.2664 | 9782.2664 | 9782.2664 | 9782.2664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7440 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 27448.2931 | 0.2 | 0.3 | 42819.3373 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7441 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 19311.6736 | 0.2 | 0.3 | 30126.2108 |  |  |  |  | 0 | 2572.5891 | 2572.5891 | 2572.5891 | 2572.5891 | 2572.5891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7442 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 31358.0073 | 0.2 | 0.3 | 48918.4914 |  |  |  |  | 0 | 7423.9722 | 7423.9722 | 7423.9722 | 7423.9722 | 7423.9722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7443 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16635.4044 | 0.2 | 0.3 | 25951.2309 |  |  |  |  | 0 | 5204.6265 | 5204.6265 | 5204.6265 | 5204.6265 | 5204.6265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7444 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 15606.0677 | 0.2 | 0.3 | 24345.4657 |  |  |  |  | 0 | 5204.7144 | 5204.7144 | 5204.7144 | 5204.7144 | 5204.7144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7445 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 20950.4595 | 0.2 | 0.3 | 32682.7168 |  |  |  |  | 0 | 9789.1189 | 9789.1189 | 9789.1189 | 9789.1189 | 9789.1189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7446 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 17918.5441 | 0.2 | 0.3 | 27952.9287 |  |  |  |  | 0 | 12623.4754 | 12623.4754 | 12623.4754 | 12623.4754 | 12623.4754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7447 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 17564.9495 | 0.2 | 0.3 | 27401.3212 |  |  |  |  | 0 | 926.1441 | 926.1441 | 926.1441 | 926.1441 | 926.1441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7448 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16723.4559 | 0.2 | 0.3 | 26088.5913 |  |  |  |  | 0 | 5204.7347 | 5204.7347 | 5204.7347 | 5204.7347 | 5204.7347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7449 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7635 | 0.2 | 0.3 | 26000.1511 |  |  |  |  | 0 | 5203.3619 | 5203.3619 | 5203.3619 | 5203.3619 | 5203.3619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7450 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 9675.1567 | 0.2 | 0.3 | 15093.2444 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7451 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 31367.2363 | 0.2 | 0.3 | 48932.8886 |  |  |  |  | 0 | 5203.553 | 5203.553 | 5203.553 | 5203.553 | 5203.553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7452 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 1162.3958 | 0.2 | 0.3 | 1813.3374 |  |  |  |  | 0 | 9783.7635 | 9783.7635 | 9783.7635 | 9783.7635 | 9783.7635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7453 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16080.0623 | 0.2 | 0.3 | 25084.8972 |  |  |  |  | 0 | 5204.1354 | 5204.1354 | 5204.1354 | 5204.1354 | 5204.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7454 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 46085.3965 | 0.2 | 0.3 | 71893.2186 |  |  |  |  | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7455 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 45815.1153 | 0.2 | 0.3 | 71471.5798 |  |  |  |  | 0 | 5204.2867 | 5204.2867 | 5204.2867 | 5204.2867 | 5204.2867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7456 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 30367.2287 | 0.2 | 0.3 | 47372.8767 |  |  |  |  | 0 | 5203.3526 | 5203.3526 | 5203.3526 | 5203.3526 | 5203.3526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7457 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 3769.9433 | 0.2 | 0.3 | 5881.1116 |  |  |  |  | 0 | 5203.7097 | 5203.7097 | 5203.7097 | 5203.7097 | 5203.7097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7458 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 17204.1723 | 0.2 | 0.3 | 26838.5087 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7459 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 18867.6319 | 0.2 | 0.3 | 29433.5057 |  |  |  |  | 0 | 2135.6489 | 2135.6489 | 2135.6489 | 2135.6489 | 2135.6489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7460 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16673.7522 | 0.2 | 0.3 | 26011.0534 |  |  |  |  | 0 | 3067.4931 | 3067.4931 | 3067.4931 | 3067.4931 | 3067.4931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7461 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 26755.1948 | 0.2 | 0.3 | 41738.1039 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7462 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16672.9329 | 0.2 | 0.3 | 26009.7754 |  |  |  |  | 0 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7463 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 14309.3116 | 0.2 | 0.3 | 22322.5261 |  |  |  |  | 0 | 2176.8099 | 2176.8099 | 2176.8099 | 2176.8099 | 2176.8099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7464 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 17086.3457 | 0.2 | 0.3 | 26654.6993 |  |  |  |  | 0 | 3026.6701 | 3026.6701 | 3026.6701 | 3026.6701 | 3026.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7465 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16712.2115 | 0.2 | 0.3 | 26071.05 |  |  |  |  | 0 | 5205.5238 | 5205.5238 | 5205.5238 | 5205.5238 | 5205.5238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7466 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16673.78 | 0.2 | 0.3 | 26011.0968 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7467 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16674.2656 | 0.2 | 0.3 | 26011.8543 |  |  |  |  | 0 | 2922.2466 | 2922.2466 | 2922.2466 | 2922.2466 | 2922.2466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7468 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 15614.4419 | 0.2 | 0.3 | 24358.5294 |  |  |  |  | 0 | 2280.3812 | 2280.3812 | 2280.3812 | 2280.3812 | 2280.3812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7469 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 1580.1462 | 0.2 | 0.3 | 2465.0281 |  |  |  |  | 0 | 8461.2636 | 8461.2636 | 8461.2636 | 8461.2636 | 8461.2636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7470 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 18906.5681 | 0.2 | 0.3 | 29494.2463 |  |  |  |  | 0 | 4424.6091 | 4424.6091 | 4424.6091 | 4424.6091 | 4424.6091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7471 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16667.7574 | 0.2 | 0.3 | 26001.7015 |  |  |  |  | 0 | 779.456 | 779.456 | 779.456 | 779.456 | 779.456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7472 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8724 | 0.2 | 0.3 | 26000.3209 |  |  |  |  | 0 | 5202.7835 | 5202.7835 | 5202.7835 | 5202.7835 | 5202.7835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7473 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 10302.7607 | 0.2 | 0.3 | 16072.3066 |  |  |  |  | 0 | 5203.1499 | 5203.1499 | 5203.1499 | 5203.1499 | 5203.1499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7474 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 13757.4929 | 0.2 | 0.3 | 21461.689 |  |  |  |  | 0 | 5205.0128 | 5205.0128 | 5205.0128 | 5205.0128 | 5205.0128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7475 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 20564.6157 | 0.2 | 0.3 | 32080.8005 |  |  |  |  | 0 | 5202.147 | 5202.147 | 5202.147 | 5202.147 | 5202.147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7476 | MIRAMAR | 110321 | Private | 2036 | 5 | Swales | 66.6667 | 7966.3644 | 0.2 | 0.3 | 12427.5285 |  |  |  |  | 0 | 3210.9516 | 3210.9516 | 3210.9516 | 3210.9516 | 3210.9516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7477 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 9990.4998 | 0.2 | 0.3 | 15585.1797 |  |  |  |  | 0 | 3983.7661 | 3983.7661 | 3983.7661 | 3983.7661 | 3983.7661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7478 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 25812.3995 | 0.2 | 0.3 | 40267.3432 |  |  |  |  | 0 | 720.4527 | 720.4527 | 720.4527 | 720.4527 | 720.4527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7479 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 17129.867 | 0.2 | 0.3 | 26722.5925 |  |  |  |  | 0 | 4481.8429 | 4481.8429 | 4481.8429 | 4481.8429 | 4481.8429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7480 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 27299.928 | 0.2 | 0.3 | 42587.8877 |  |  |  |  | 0 | 9572.9408 | 9572.9408 | 9572.9408 | 9572.9408 | 9572.9408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7481 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 24454.4641 | 0.2 | 0.3 | 38148.9639 |  |  |  |  | 0 | 5202.0643 | 5202.0643 | 5202.0643 | 5202.0643 | 5202.0643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7482 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 15133.5497 | 0.2 | 0.3 | 23608.3375 |  |  |  |  | 0 | 9781.1756 | 9781.1756 | 9781.1756 | 9781.1756 | 9781.1756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7483 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 11.0237 | 0.2 | 0.3 | 17.197 |  |  |  |  | 0 | 5204.241 | 5204.241 | 5204.241 | 5204.241 | 5204.241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7484 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 27617.5364 | 0.2 | 0.3 | 43083.3568 |  |  |  |  | 0 | 9782.8364 | 9782.8364 | 9782.8364 | 9782.8364 | 9782.8364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7485 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16888.0571 | 0.2 | 0.3 | 26345.3691 |  |  |  |  | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7486 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 25697.8903 | 0.2 | 0.3 | 40088.7088 |  |  |  |  | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7487 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 17959.0787 | 0.2 | 0.3 | 28016.1628 |  |  |  |  | 0 | 5203.6421 | 5203.6421 | 5203.6421 | 5203.6421 | 5203.6421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7488 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 14370.2893 | 0.2 | 0.3 | 22417.6513 |  |  |  |  | 0 | 5203.9375 | 5203.9375 | 5203.9375 | 5203.9375 | 5203.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7489 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16961.4971 | 0.2 | 0.3 | 26459.9355 |  |  |  |  | 0 | 33.9946 | 33.9946 | 33.9946 | 33.9946 | 33.9946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7490 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 23433.5181 | 0.2 | 0.3 | 36556.2882 |  |  |  |  | 0 | 3290.4878 | 3290.4878 | 3290.4878 | 3290.4878 | 3290.4878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7491 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 28456.0149 | 0.2 | 0.3 | 44391.3832 |  |  |  |  | 0 | 9705.3654 | 9705.3654 | 9705.3654 | 9705.3654 | 9705.3654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7492 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16732.0527 | 0.2 | 0.3 | 26102.0022 |  |  |  |  | 0 | 9782.0881 | 9782.0881 | 9782.0881 | 9782.0881 | 9782.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7493 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16668.4375 | 0.2 | 0.3 | 26002.7624 |  |  |  |  | 0 | 5236.4625 | 5236.4625 | 5236.4625 | 5236.4625 | 5236.4625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7494 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 30379.073 | 0.2 | 0.3 | 47391.3539 |  |  |  |  | 0 | 9747.7423 | 9747.7423 | 9747.7423 | 9747.7423 | 9747.7423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7495 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 35274.2797 | 0.2 | 0.3 | 55027.8763 |  |  |  |  | 0 | 9784.328 | 9784.328 | 9784.328 | 9784.328 | 9784.328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7496 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 22950.7988 | 0.2 | 0.3 | 35803.2461 |  |  |  |  | 0 | 9780.8681 | 9780.8681 | 9780.8681 | 9780.8681 | 9780.8681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7497 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 802.6395 | 0.2 | 0.3 | 1252.1176 |  |  |  |  | 0 | 7355.2704 | 7355.2704 | 7355.2704 | 7355.2704 | 7355.2704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7498 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 29731.8265 | 0.2 | 0.3 | 46381.6493 |  |  |  |  | 0 | 7626.8607 | 7626.8607 | 7626.8607 | 7626.8607 | 7626.8607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7499 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 25232.2197 | 0.2 | 0.3 | 39362.2628 |  |  |  |  | 0 | 9854.8215 | 9854.8215 | 9854.8215 | 9854.8215 | 9854.8215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7500 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 26913.8026 | 0.2 | 0.3 | 41985.5321 |  |  |  |  | 0 | 765.1199 | 765.1199 | 765.1199 | 765.1199 | 765.1199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7501 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 687.4526 | 0.2 | 0.3 | 1072.4261 |  |  |  |  | 0 | 2601.9063 | 2601.9063 | 2601.9063 | 2601.9063 | 2601.9063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7502 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16669.0029 | 0.2 | 0.3 | 26003.6446 |  |  |  |  | 0 | 2602.1521 | 2602.1521 | 2602.1521 | 2602.1521 | 2602.1521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7503 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 22721.0744 | 0.2 | 0.3 | 35444.8761 |  |  |  |  | 0 | 5202.5933 | 5202.5933 | 5202.5933 | 5202.5933 | 5202.5933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7504 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 18651.8557 | 0.2 | 0.3 | 29096.8948 |  |  |  |  | 0 | 5202.9386 | 5202.9386 | 5202.9386 | 5202.9386 | 5202.9386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7505 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16775.3075 | 0.2 | 0.3 | 26169.4796 |  |  |  |  | 0 | 5204.8846 | 5204.8846 | 5204.8846 | 5204.8846 | 5204.8846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7506 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 20767.1511 | 0.2 | 0.3 | 32396.7557 |  |  |  |  | 0 | 4420.8821 | 4420.8821 | 4420.8821 | 4420.8821 | 4420.8821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7507 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 26336.3213 | 0.2 | 0.3 | 41084.6612 |  |  |  |  | 0 | 3570.7918 | 3570.7918 | 3570.7918 | 3570.7918 | 3570.7918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7508 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16673.6633 | 0.2 | 0.3 | 26010.9147 |  |  |  |  | 0 | 5202.8039 | 5202.8039 | 5202.8039 | 5202.8039 | 5202.8039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7509 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 10911.9325 | 0.2 | 0.3 | 17022.6146 |  |  |  |  | 0 | 114.6429 | 114.6429 | 114.6429 | 114.6429 | 114.6429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7510 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 10853.698 | 0.2 | 0.3 | 16931.7689 |  |  |  |  | 0 | 2265.8937 | 2265.8937 | 2265.8937 | 2265.8937 | 2265.8937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7511 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 12991.2018 | 0.2 | 0.3 | 20266.2748 |  |  |  |  | 0 | 9674.1051 | 9674.1051 | 9674.1051 | 9674.1051 | 9674.1051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7512 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16560.4559 | 0.2 | 0.3 | 25834.3113 |  |  |  |  | 0 | 9844.4353 | 9844.4353 | 9844.4353 | 9844.4353 | 9844.4353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7513 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 25463.2349 | 0.2 | 0.3 | 39722.6465 |  |  |  |  | 0 | 5202.5054 | 5202.5054 | 5202.5054 | 5202.5054 | 5202.5054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7514 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 34800.3035 | 0.2 | 0.3 | 54288.4735 |  |  |  |  | 0 | 9468.7029 | 9468.7029 | 9468.7029 | 9468.7029 | 9468.7029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7515 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 13122.8905 | 0.2 | 0.3 | 20471.7092 |  |  |  |  | 0 | 5202.7387 | 5202.7387 | 5202.7387 | 5202.7387 | 5202.7387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7516 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 20314.1919 | 0.2 | 0.3 | 31690.1393 |  |  |  |  | 0 | 9782.1089 | 9782.1089 | 9782.1089 | 9782.1089 | 9782.1089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7517 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 5909.3955 | 0.2 | 0.3 | 9218.657 |  |  |  |  | 0 | 9781.7028 | 9781.7028 | 9781.7028 | 9781.7028 | 9781.7028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7518 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 28182.9404 | 0.2 | 0.3 | 43965.387 |  |  |  |  | 0 | 5204.3169 | 5204.3169 | 5204.3169 | 5204.3169 | 5204.3169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7519 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 19120.4519 | 0.2 | 0.3 | 29827.905 |  |  |  |  | 0 | 9781.306 | 9781.306 | 9781.306 | 9781.306 | 9781.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7520 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 5091.6363 | 0.2 | 0.3 | 7942.9526 |  |  |  |  | 0 | 9783.0069 | 9783.0069 | 9783.0069 | 9783.0069 | 9783.0069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7521 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 29596.3478 | 0.2 | 0.3 | 46170.3026 |  |  |  |  | 0 | 5203.7343 | 5203.7343 | 5203.7343 | 5203.7343 | 5203.7343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7522 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 20412.4235 | 0.2 | 0.3 | 31843.3806 |  |  |  |  | 0 | 9782.1366 | 9782.1366 | 9782.1366 | 9782.1366 | 9782.1366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7523 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 852.228 | 0.2 | 0.3 | 1329.4757 |  |  |  |  | 0 | 4676.1006 | 4676.1006 | 4676.1006 | 4676.1006 | 4676.1006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7524 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 17229.2611 | 0.2 | 0.3 | 26877.6473 |  |  |  |  | 0 | 5277.3935 | 5277.3935 | 5277.3935 | 5277.3935 | 5277.3935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7525 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 32620.5501 | 0.2 | 0.3 | 50888.0581 |  |  |  |  | 0 | 5202.0984 | 5202.0984 | 5202.0984 | 5202.0984 | 5202.0984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7526 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 27736.7346 | 0.2 | 0.3 | 43269.306 |  |  |  |  | 0 | 5201.3109 | 5201.3109 | 5201.3109 | 5201.3109 | 5201.3109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7527 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 2702.2318 | 0.2 | 0.3 | 4215.4816 |  |  |  |  | 0 | 5202.3643 | 5202.3643 | 5202.3643 | 5202.3643 | 5202.3643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7528 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 14803.7211 | 0.2 | 0.3 | 23093.8049 |  |  |  |  | 0 | 5202.386 | 5202.386 | 5202.386 | 5202.386 | 5202.386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7529 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16674.3962 | 0.2 | 0.3 | 26012.0581 |  |  |  |  | 0 | 190.7005 | 190.7005 | 190.7005 | 190.7005 | 190.7005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7530 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16257.7192 | 0.2 | 0.3 | 25362.042 |  |  |  |  | 0 | 5011.1721 | 5011.1721 | 5011.1721 | 5011.1721 | 5011.1721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7531 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 23818.8168 | 0.2 | 0.3 | 37157.3542 |  |  |  |  | 0 | 8125.7292 | 8125.7292 | 8125.7292 | 8125.7292 | 8125.7292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7532 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 22782.5864 | 0.2 | 0.3 | 35540.8348 |  |  |  |  | 0 | 515.573 | 515.573 | 515.573 | 515.573 | 515.573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7533 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 23351.4391 | 0.2 | 0.3 | 36428.245 |  |  |  |  | 0 | 707.4042 | 707.4042 | 707.4042 | 707.4042 | 707.4042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7534 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 29906.1709 | 0.2 | 0.3 | 46653.6266 |  |  |  |  | 0 | 9214.7537 | 9214.7537 | 9214.7537 | 9214.7537 | 9214.7537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7535 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 3406.8247 | 0.2 | 0.3 | 5314.6466 |  |  |  |  | 0 | 9780.63 | 9780.63 | 9780.63 | 9780.63 | 9780.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7536 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 8836.9206 | 0.2 | 0.3 | 13785.5961 |  |  |  |  | 0 | 9778.7673 | 9778.7673 | 9778.7673 | 9778.7673 | 9778.7673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7537 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 19672.4974 | 0.2 | 0.3 | 30689.0959 |  |  |  |  | 0 | 9783.3789 | 9783.3789 | 9783.3789 | 9783.3789 | 9783.3789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7538 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 9703.4533 | 0.2 | 0.3 | 15137.3871 |  |  |  |  | 0 | 6611.0616 | 6611.0616 | 6611.0616 | 6611.0616 | 6611.0616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7539 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16708.5074 | 0.2 | 0.3 | 26065.2715 |  |  |  |  | 0 | 7442.2335 | 7442.2335 | 7442.2335 | 7442.2335 | 7442.2335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7540 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 2403.0623 | 2403.0623 | 2403.0623 | 2403.0623 | 2403.0623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7541 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 27977.3635 | 0.2 | 0.3 | 43644.687 |  |  |  |  | 0 | 6453.6242 | 6453.6242 | 6453.6242 | 6453.6242 | 6453.6242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7542 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 29870.6535 | 0.2 | 0.3 | 46598.2194 |  |  |  |  | 0 | 2933.8115 | 2933.8115 | 2933.8115 | 2933.8115 | 2933.8115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7543 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 22126.7472 | 0.2 | 0.3 | 34517.7256 |  |  |  |  | 0 | 850.5628 | 850.5628 | 850.5628 | 850.5628 | 850.5628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7544 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 24677.2561 | 0.2 | 0.3 | 38496.5195 |  |  |  |  | 0 | 3133.6521 | 3133.6521 | 3133.6521 | 3133.6521 | 3133.6521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7545 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 14548.1012 | 0.2 | 0.3 | 22695.0379 |  |  |  |  | 0 | 5199.7944 | 5199.7944 | 5199.7944 | 5199.7944 | 5199.7944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7546 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 22993.0231 | 0.2 | 0.3 | 35869.116 |  |  |  |  | 0 | 9791.9174 | 9791.9174 | 9791.9174 | 9791.9174 | 9791.9174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7547 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 27617.3305 | 0.2 | 0.3 | 43083.0356 |  |  |  |  | 0 | 612.2882 | 612.2882 | 612.2882 | 612.2882 | 612.2882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7548 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 28995.4549 | 0.2 | 0.3 | 45232.9097 |  |  |  |  | 0 | 5202.4208 | 5202.4208 | 5202.4208 | 5202.4208 | 5202.4208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7549 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 21095.0526 | 0.2 | 0.3 | 32908.2821 |  |  |  |  | 0 | 4754.862 | 4754.862 | 4754.862 | 4754.862 | 4754.862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7550 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 17679.9447 | 0.2 | 0.3 | 27580.7137 |  |  |  |  | 0 | 448.7154 | 448.7154 | 448.7154 | 448.7154 | 448.7154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7551 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 7606.215 | 0.2 | 0.3 | 11865.6954 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7552 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 23435.0229 | 0.2 | 0.3 | 36558.6357 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7553 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 20862.4145 | 0.2 | 0.3 | 32545.3666 |  |  |  |  | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7554 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 29064.9934 | 0.2 | 0.3 | 45341.3897 |  |  |  |  | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7555 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 27185.8217 | 0.2 | 0.3 | 42409.8818 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7556 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 21530.9491 | 0.2 | 0.3 | 33588.2806 |  |  |  |  | 0 | 5202.1362 | 5202.1362 | 5202.1362 | 5202.1362 | 5202.1362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7557 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 29550.8375 | 0.2 | 0.3 | 46099.3064 |  |  |  |  | 0 | 5201.1389 | 5201.1389 | 5201.1389 | 5201.1389 | 5201.1389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7558 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 25219.4615 | 0.2 | 0.3 | 39342.3599 |  |  |  |  | 0 | 5202.136 | 5202.136 | 5202.136 | 5202.136 | 5202.136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7559 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 33147.6257 | 0.2 | 0.3 | 51710.296 |  |  |  |  | 0 | 5202.1357 | 5202.1357 | 5202.1357 | 5202.1357 | 5202.1357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7560 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 33333.9774 | 0.2 | 0.3 | 52001.0047 |  |  |  |  | 0 | 5201.7187 | 5201.7187 | 5201.7187 | 5201.7187 | 5201.7187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7561 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 30618.8537 | 0.2 | 0.3 | 47765.4117 |  |  |  |  | 0 | 7973.7485 | 7973.7485 | 7973.7485 | 7973.7485 | 7973.7485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7562 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16826.759 | 0.2 | 0.3 | 26249.744 |  |  |  |  | 0 | 266.3212 | 266.3212 | 266.3212 | 266.3212 | 266.3212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7563 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16766.1277 | 0.2 | 0.3 | 26155.1592 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7564 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16747.5483 | 0.2 | 0.3 | 26126.1753 |  |  |  |  | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7565 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16726.1574 | 0.2 | 0.3 | 26092.8055 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7566 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 35814.745 | 0.2 | 0.3 | 55871.0022 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7567 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16721.3765 | 0.2 | 0.3 | 26085.3473 |  |  |  |  | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7568 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16717.8639 | 0.2 | 0.3 | 26079.8676 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7569 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 23399.9385 | 0.2 | 0.3 | 36503.904 |  |  |  |  | 0 | 7882.8354 | 7882.8354 | 7882.8354 | 7882.8354 | 7882.8354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7570 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 10293.3224 | 0.2 | 0.3 | 16057.5829 |  |  |  |  | 0 | 2521.3829 | 2521.3829 | 2521.3829 | 2521.3829 | 2521.3829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7571 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 7679.1619 | 0.2 | 0.3 | 11979.4925 |  |  |  |  | 0 | 5202.3982 | 5202.3982 | 5202.3982 | 5202.3982 | 5202.3982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7572 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 24357.7915 | 0.2 | 0.3 | 37998.1547 |  |  |  |  | 0 | 2630.4285 | 2630.4285 | 2630.4285 | 2630.4285 | 2630.4285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7573 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 31795.0263 | 0.2 | 0.3 | 49600.2411 |  |  |  |  | 0 | 2572.9724 | 2572.9724 | 2572.9724 | 2572.9724 | 2572.9724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7574 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 10059.3263 | 0.2 | 0.3 | 15692.5491 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7575 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 17974.9372 | 0.2 | 0.3 | 28040.902 |  |  |  |  | 0 | 1219.0169 | 1219.0169 | 1219.0169 | 1219.0169 | 1219.0169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7576 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 21009.1916 | 0.2 | 0.3 | 32774.3389 |  |  |  |  | 0 | 1219.0169 | 1219.0169 | 1219.0169 | 1219.0169 | 1219.0169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7577 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 9645.2166 | 9645.2166 | 9645.2166 | 9645.2166 | 9645.2166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7578 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 3332.9002 | 0.2 | 0.3 | 5199.3243 |  |  |  |  | 0 | 9.9592 | 9.9592 | 9.9592 | 9.9592 | 9.9592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7579 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 629.8213 | 0.2 | 0.3 | 982.5213 |  |  |  |  | 0 | 7638.7616 | 7638.7616 | 7638.7616 | 7638.7616 | 7638.7616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7580 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 19185.1645 | 0.2 | 0.3 | 29928.8567 |  |  |  |  | 0 | 9579.591 | 9579.591 | 9579.591 | 9579.591 | 9579.591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7581 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 33786.0461 | 0.2 | 0.3 | 52706.2319 |  |  |  |  | 0 | 9422.1342 | 9422.1342 | 9422.1342 | 9422.1342 | 9422.1342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7582 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 24889.461 | 0.2 | 0.3 | 38827.5592 |  |  |  |  | 0 | 5203.2233 | 5203.2233 | 5203.2233 | 5203.2233 | 5203.2233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7583 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 26218.0381 | 0.2 | 0.3 | 40900.1395 |  |  |  |  | 0 | 3622.8537 | 3622.8537 | 3622.8537 | 3622.8537 | 3622.8537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7584 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 18292.1779 | 0.2 | 0.3 | 28535.7976 |  |  |  |  | 0 | 1219.0412 | 1219.0412 | 1219.0412 | 1219.0412 | 1219.0412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7585 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 24571.3245 | 0.2 | 0.3 | 38331.2663 |  |  |  |  | 0 | 8928.166 | 8928.166 | 8928.166 | 8928.166 | 8928.166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7586 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 7440.0143 | 0.2 | 0.3 | 11606.4224 |  |  |  |  | 0 | 9784.4722 | 9784.4722 | 9784.4722 | 9784.4722 | 9784.4722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7587 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16561.5309 | 0.2 | 0.3 | 25835.9883 |  |  |  |  | 0 | 9779.8617 | 9779.8617 | 9779.8617 | 9779.8617 | 9779.8617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7588 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 24323.1462 | 0.2 | 0.3 | 37944.1081 |  |  |  |  | 0 | 5200.9521 | 5200.9521 | 5200.9521 | 5200.9521 | 5200.9521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7589 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 13389.9784 | 0.2 | 0.3 | 20888.3663 |  |  |  |  | 0 | 9780.0697 | 9780.0697 | 9780.0697 | 9780.0697 | 9780.0697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7590 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 17431.4796 | 0.2 | 0.3 | 27193.1082 |  |  |  |  | 0 | 9779.6068 | 9779.6068 | 9779.6068 | 9779.6068 | 9779.6068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7591 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 17435.4731 | 0.2 | 0.3 | 27199.338 |  |  |  |  | 0 | 9779.124 | 9779.124 | 9779.124 | 9779.124 | 9779.124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7592 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 17289.2528 | 0.2 | 0.3 | 26971.2344 |  |  |  |  | 0 | 5202.2871 | 5202.2871 | 5202.2871 | 5202.2871 | 5202.2871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7593 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 17168.8188 | 0.2 | 0.3 | 26783.3573 |  |  |  |  | 0 | 9777.9731 | 9777.9731 | 9777.9731 | 9777.9731 | 9777.9731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7594 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 33344.0834 | 0.2 | 0.3 | 52016.7701 |  |  |  |  | 0 | 7178.7733 | 7178.7733 | 7178.7733 | 7178.7733 | 7178.7733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7595 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16731.1229 | 0.2 | 0.3 | 26100.5518 |  |  |  |  | 0 | 5202.9888 | 5202.9888 | 5202.9888 | 5202.9888 | 5202.9888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7596 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16717.9996 | 0.2 | 0.3 | 26080.0794 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7597 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 6418.4058 | 0.2 | 0.3 | 10012.713 |  |  |  |  | 0 | 5204.6027 | 5204.6027 | 5204.6027 | 5204.6027 | 5204.6027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7598 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 8992.6943 | 0.2 | 0.3 | 14028.6032 |  |  |  |  | 0 | 13413.1718 | 13413.1718 | 13413.1718 | 13413.1718 | 13413.1718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7599 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 22707.3065 | 0.2 | 0.3 | 35423.3981 |  |  |  |  | 0 | 5202.1326 | 5202.1326 | 5202.1326 | 5202.1326 | 5202.1326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7600 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 33370.1093 | 0.2 | 0.3 | 52057.3706 |  |  |  |  | 0 | 5202.3365 | 5202.3365 | 5202.3365 | 5202.3365 | 5202.3365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7601 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 8057.6804 | 0.2 | 0.3 | 12569.9814 |  |  |  |  | 0 | 5203.5414 | 5203.5414 | 5203.5414 | 5203.5414 | 5203.5414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7602 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 8997.1805 | 0.2 | 0.3 | 14035.6015 |  |  |  |  | 0 | 5200.6938 | 5200.6938 | 5200.6938 | 5200.6938 | 5200.6938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7603 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 15324.5808 | 0.2 | 0.3 | 23906.346 |  |  |  |  | 0 | 5204.3028 | 5204.3028 | 5204.3028 | 5204.3028 | 5204.3028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7604 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 25837.9023 | 0.2 | 0.3 | 40307.1275 |  |  |  |  | 0 | 7916.6161 | 7916.6161 | 7916.6161 | 7916.6161 | 7916.6161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7605 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 21031.8333 | 0.2 | 0.3 | 32809.66 |  |  |  |  | 0 | 5205.6238 | 5205.6238 | 5205.6238 | 5205.6238 | 5205.6238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7606 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 15495.7627 | 0.2 | 0.3 | 24173.3899 |  |  |  |  | 0 | 9779.5182 | 9779.5182 | 9779.5182 | 9779.5182 | 9779.5182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7607 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 19807.8687 | 0.2 | 0.3 | 30900.2752 |  |  |  |  | 0 | 9780.2052 | 9780.2052 | 9780.2052 | 9780.2052 | 9780.2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7608 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 11442.8521 | 0.2 | 0.3 | 17850.8492 |  |  |  |  | 0 | 9779.6469 | 9779.6469 | 9779.6469 | 9779.6469 | 9779.6469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7609 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 13985.7096 | 0.2 | 0.3 | 21817.707 |  |  |  |  | 0 | 5202.2425 | 5202.2425 | 5202.2425 | 5202.2425 | 5202.2425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7610 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 29978.9517 | 0.2 | 0.3 | 46767.1647 |  |  |  |  | 0 | 9781.524 | 9781.524 | 9781.524 | 9781.524 | 9781.524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7611 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 31335.0752 | 0.2 | 0.3 | 48882.7173 |  |  |  |  | 0 | 9789.1607 | 9789.1607 | 9789.1607 | 9789.1607 | 9789.1607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7612 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 31337.8362 | 0.2 | 0.3 | 48887.0245 |  |  |  |  | 0 | 2612.4842 | 2612.4842 | 2612.4842 | 2612.4842 | 2612.4842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7613 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 19121.6107 | 0.2 | 0.3 | 29829.7126 |  |  |  |  | 0 | 2799.2431 | 2799.2431 | 2799.2431 | 2799.2431 | 2799.2431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7614 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 19940.1756 | 0.2 | 0.3 | 31106.6739 |  |  |  |  | 0 | 5203.668 | 5203.668 | 5203.668 | 5203.668 | 5203.668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7615 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 25003.7519 | 0.2 | 0.3 | 39005.8529 |  |  |  |  | 0 | 9817.3315 | 9817.3315 | 9817.3315 | 9817.3315 | 9817.3315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7616 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 30682.0847 | 0.2 | 0.3 | 47864.0522 |  |  |  |  | 0 | 2798.7516 | 2798.7516 | 2798.7516 | 2798.7516 | 2798.7516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7617 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 17405.4447 | 0.2 | 0.3 | 27152.4937 |  |  |  |  | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7618 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 28829.1545 | 0.2 | 0.3 | 44973.4811 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7619 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 17243.2571 | 0.2 | 0.3 | 26899.481 |  |  |  |  | 0 | 7194.7328 | 7194.7328 | 7194.7328 | 7194.7328 | 7194.7328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7620 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 21330.8971 | 0.2 | 0.3 | 33276.1994 |  |  |  |  | 0 | 9782.4807 | 9782.4807 | 9782.4807 | 9782.4807 | 9782.4807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7621 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 21888.5177 | 0.2 | 0.3 | 34146.0877 |  |  |  |  | 0 | 5201.2291 | 5201.2291 | 5201.2291 | 5201.2291 | 5201.2291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7622 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 21336.3409 | 0.2 | 0.3 | 33284.6919 |  |  |  |  | 0 | 9779.8116 | 9779.8116 | 9779.8116 | 9779.8116 | 9779.8116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7623 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 23662.8259 | 0.2 | 0.3 | 36914.0085 |  |  |  |  | 0 | 7709.3647 | 7709.3647 | 7709.3647 | 7709.3647 | 7709.3647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7624 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 19706.1884 | 0.2 | 0.3 | 30741.6539 |  |  |  |  | 0 | 2542.3746 | 2542.3746 | 2542.3746 | 2542.3746 | 2542.3746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7625 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 28462.4331 | 0.2 | 0.3 | 44401.3956 |  |  |  |  | 0 | 5197.2496 | 5197.2496 | 5197.2496 | 5197.2496 | 5197.2496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7626 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 18833.2123 | 0.2 | 0.3 | 29379.8112 |  |  |  |  | 0 | 9674.0162 | 9674.0162 | 9674.0162 | 9674.0162 | 9674.0162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7627 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 38209.3261 | 0.2 | 0.3 | 59606.5488 |  |  |  |  | 0 | 9784.7079 | 9784.7079 | 9784.7079 | 9784.7079 | 9784.7079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7628 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 25255.9769 | 0.2 | 0.3 | 39399.3239 |  |  |  |  | 0 | 2662.5237 | 2662.5237 | 2662.5237 | 2662.5237 | 2662.5237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7629 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16770.2243 | 0.2 | 0.3 | 26161.5499 |  |  |  |  | 0 | 756.915 | 756.915 | 756.915 | 756.915 | 756.915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7630 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16669.6797 | 0.2 | 0.3 | 26004.7004 |  |  |  |  | 0 | 9778.3274 | 9778.3274 | 9778.3274 | 9778.3274 | 9778.3274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7631 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6027 | 0.2 | 0.3 | 25999.9002 |  |  |  |  | 0 | 9146.2748 | 9146.2748 | 9146.2748 | 9146.2748 | 9146.2748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7632 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 5466.6641 | 0.2 | 0.3 | 8527.996 |  |  |  |  | 0 | 9294.3575 | 9294.3575 | 9294.3575 | 9294.3575 | 9294.3575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7633 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16696.2297 | 0.2 | 0.3 | 26046.1184 |  |  |  |  | 0 | 5605.9579 | 5605.9579 | 5605.9579 | 5605.9579 | 5605.9579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7634 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 21547.7259 | 0.2 | 0.3 | 33614.4524 |  |  |  |  | 0 | 9907.925 | 9907.925 | 9907.925 | 9907.925 | 9907.925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7635 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16667.304 | 0.2 | 0.3 | 26000.9942 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7636 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16667.2375 | 0.2 | 0.3 | 26000.8904 |  |  |  |  | 0 | 4172.6181 | 4172.6181 | 4172.6181 | 4172.6181 | 4172.6181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7637 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0051 | 0.2 | 0.3 | 26000.5279 |  |  |  |  | 0 | 5484.5005 | 5484.5005 | 5484.5005 | 5484.5005 | 5484.5005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7638 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7007 | 0.2 | 0.3 | 26000.053 |  |  |  |  | 0 | 9776.6575 | 9776.6575 | 9776.6575 | 9776.6575 | 9776.6575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7639 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 30154.6907 | 0.2 | 0.3 | 47041.3175 |  |  |  |  | 0 | 5200.9331 | 5200.9331 | 5200.9331 | 5200.9331 | 5200.9331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7640 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 28136.1797 | 0.2 | 0.3 | 43892.4403 |  |  |  |  | 0 | 9728.3471 | 9728.3471 | 9728.3471 | 9728.3471 | 9728.3471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7641 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 5234.0152 | 0.2 | 0.3 | 8165.0637 |  |  |  |  | 0 | 7455.3035 | 7455.3035 | 7455.3035 | 7455.3035 | 7455.3035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7642 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 27197.9739 | 0.2 | 0.3 | 42428.8392 |  |  |  |  | 0 | 5202.3207 | 5202.3207 | 5202.3207 | 5202.3207 | 5202.3207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7643 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 11884.5532 | 0.2 | 0.3 | 18539.903 |  |  |  |  | 0 | 9779.2622 | 9779.2622 | 9779.2622 | 9779.2622 | 9779.2622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7644 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 17286.9335 | 0.2 | 0.3 | 26967.6162 |  |  |  |  | 0 | 5200.7508 | 5200.7508 | 5200.7508 | 5200.7508 | 5200.7508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7645 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 13311.2841 | 0.2 | 0.3 | 20765.6032 |  |  |  |  | 0 | 6425.0382 | 6425.0382 | 6425.0382 | 6425.0382 | 6425.0382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7646 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 28297.5131 | 0.2 | 0.3 | 44144.1205 |  |  |  |  | 0 | 6525.7836 | 6525.7836 | 6525.7836 | 6525.7836 | 6525.7836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7647 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 9413.5354 | 0.2 | 0.3 | 14685.1152 |  |  |  |  | 0 | 5860.4036 | 5860.4036 | 5860.4036 | 5860.4036 | 5860.4036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7648 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16796.6767 | 0.2 | 0.3 | 26202.8157 |  |  |  |  | 0 | 9004.8639 | 9004.8639 | 9004.8639 | 9004.8639 | 9004.8639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7649 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 17727.8324 | 0.2 | 0.3 | 27655.4185 |  |  |  |  | 0 | 5201.2986 | 5201.2986 | 5201.2986 | 5201.2986 | 5201.2986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7650 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 2019.6316 | 0.2 | 0.3 | 3150.6253 |  |  |  |  | 0 | 9777.5335 | 9777.5335 | 9777.5335 | 9777.5335 | 9777.5335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7651 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 11584.2429 | 0.2 | 0.3 | 18071.419 |  |  |  |  | 0 | 5201.0622 | 5201.0622 | 5201.0622 | 5201.0622 | 5201.0622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7652 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 28318.1414 | 0.2 | 0.3 | 44176.3006 |  |  |  |  | 0 | 9778.2823 | 9778.2823 | 9778.2823 | 9778.2823 | 9778.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7653 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7838 | 0.2 | 0.3 | 26000.1827 |  |  |  |  | 0 | 10767.5804 | 10767.5804 | 10767.5804 | 10767.5804 | 10767.5804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7654 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16669.8114 | 0.2 | 0.3 | 26004.9058 |  |  |  |  | 0 | 8729.6374 | 8729.6374 | 8729.6374 | 8729.6374 | 8729.6374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7655 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16669.6479 | 0.2 | 0.3 | 26004.6507 |  |  |  |  | 0 | 4587.2984 | 4587.2984 | 4587.2984 | 4587.2984 | 4587.2984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7656 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 11189.8358 | 0.2 | 0.3 | 17456.1438 |  |  |  |  | 0 | 4701.1056 | 4701.1056 | 4701.1056 | 4701.1056 | 4701.1056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7657 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 8751.2789 | 0.2 | 0.3 | 13651.995 |  |  |  |  | 0 | 4034.4028 | 4034.4028 | 4034.4028 | 4034.4028 | 4034.4028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7658 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 19801.8039 | 0.2 | 0.3 | 30890.814 |  |  |  |  | 0 | 6792.4038 | 6792.4038 | 6792.4038 | 6792.4038 | 6792.4038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7659 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 17027.4749 | 0.2 | 0.3 | 26562.8609 |  |  |  |  | 0 | 5200.6142 | 5200.6142 | 5200.6142 | 5200.6142 | 5200.6142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7660 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 17239.9705 | 0.2 | 0.3 | 26894.3539 |  |  |  |  | 0 | 9783.1938 | 9783.1938 | 9783.1938 | 9783.1938 | 9783.1938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7661 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 13096.8332 | 0.2 | 0.3 | 20431.0598 |  |  |  |  | 0 | 5202.4444 | 5202.4444 | 5202.4444 | 5202.4444 | 5202.4444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7662 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 19701.1554 | 0.2 | 0.3 | 30733.8024 |  |  |  |  | 0 | 6681.7879 | 6681.7879 | 6681.7879 | 6681.7879 | 6681.7879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7663 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 31830.5437 | 0.2 | 0.3 | 49655.6481 |  |  |  |  | 0 | 10465.6469 | 10465.6469 | 10465.6469 | 10465.6469 | 10465.6469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7664 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 7221.0104 | 0.2 | 0.3 | 11264.7762 |  |  |  |  | 0 | 11090.2561 | 11090.2561 | 11090.2561 | 11090.2561 | 11090.2561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7665 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 24299.401 | 0.2 | 0.3 | 37907.0656 |  |  |  |  | 0 | 7494.5593 | 7494.5593 | 7494.5593 | 7494.5593 | 7494.5593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7666 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 24474.1455 | 0.2 | 0.3 | 38179.6669 |  |  |  |  | 0 | 5194.0247 | 5194.0247 | 5194.0247 | 5194.0247 | 5194.0247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7667 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 16910.2173 | 0.2 | 0.3 | 26379.9389 |  |  |  |  | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7668 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 25822.2063 | 0.2 | 0.3 | 40282.6418 |  |  |  |  | 0 | 5201.3244 | 5201.3244 | 5201.3244 | 5201.3244 | 5201.3244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7669 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 24296.3183 | 0.2 | 0.3 | 37902.2566 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7670 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 26087.7705 | 0.2 | 0.3 | 40696.922 |  |  |  |  | 0 | 9779.3434 | 9779.3434 | 9779.3434 | 9779.3434 | 9779.3434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7671 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 25116.638 | 0.2 | 0.3 | 39181.9553 |  |  |  |  | 0 | 5201.2736 | 5201.2736 | 5201.2736 | 5201.2736 | 5201.2736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7672 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 6918.9303 | 0.2 | 0.3 | 10793.5312 |  |  |  |  | 0 | 6742.8953 | 6742.8953 | 6742.8953 | 6742.8953 | 6742.8953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7673 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 16666.9632 | 0.2 | 0.3 | 26000.4626 |  |  |  |  | 0 | 9596.8212 | 9596.8212 | 9596.8212 | 9596.8212 | 9596.8212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7674 | MIRAMAR | 110361 | Private | 2036 | 5 | Swales | 66.6667 | 31508.5683 | 0.2 | 0.3 | 49153.3665 |  |  |  |  | 0 | 14298.9412 | 14298.9412 | 14298.9412 | 14298.9412 | 14298.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7675 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 28800.6022 | 0.2 | 0.3 | 44928.9394 |  |  |  |  | 0 | 11207.3562 | 11207.3562 | 11207.3562 | 11207.3562 | 11207.3562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7676 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 28644.3367 | 0.2 | 0.3 | 44685.1652 |  |  |  |  | 0 | 4349.592 | 4349.592 | 4349.592 | 4349.592 | 4349.592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7677 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 24408.5759 | 0.2 | 0.3 | 38077.3784 |  |  |  |  | 0 | 851.519 | 851.519 | 851.519 | 851.519 | 851.519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7678 | MIRAMAR | 110363 | Private | 2036 | 5 | Swales | 66.6667 | 3853.9483 | 0.2 | 0.3 | 6012.1594 |  |  |  |  | 0 | 9773.2637 | 9773.2637 | 9773.2637 | 9773.2637 | 9773.2637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7679 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 12343.6959 | 0.2 | 0.3 | 19256.1657 |  |  |  |  | 0 | 8696.2208 | 8696.2208 | 8696.2208 | 8696.2208 | 8696.2208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7680 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 21704.5657 | 0.2 | 0.3 | 33859.1224 |  |  |  |  | 0 | 4340.0292 | 4340.0292 | 4340.0292 | 4340.0292 | 4340.0292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7681 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16870.3415 | 0.2 | 0.3 | 26317.7328 |  |  |  |  | 0 | 5201.6185 | 5201.6185 | 5201.6185 | 5201.6185 | 5201.6185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7682 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 10096.8589 | 0.2 | 0.3 | 15751.0999 |  |  |  |  | 0 | 5201.3202 | 5201.3202 | 5201.3202 | 5201.3202 | 5201.3202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7683 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16628.7139 | 0.2 | 0.3 | 25940.7936 |  |  |  |  | 0 | 5200.0203 | 5200.0203 | 5200.0203 | 5200.0203 | 5200.0203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7684 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 7848.7881 | 0.2 | 0.3 | 12244.1094 |  |  |  |  | 0 | 9660.0738 | 9660.0738 | 9660.0738 | 9660.0738 | 9660.0738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7685 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 15094.02 | 0.2 | 0.3 | 23546.6712 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7686 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16668.2404 | 0.2 | 0.3 | 26002.455 |  |  |  |  | 0 | 5201.0991 | 5201.0991 | 5201.0991 | 5201.0991 | 5201.0991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7687 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 18331.217 | 0.2 | 0.3 | 28596.6985 |  |  |  |  | 0 | 9763.6662 | 9763.6662 | 9763.6662 | 9763.6662 | 9763.6662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7688 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 18045.2141 | 0.2 | 0.3 | 28150.534 |  |  |  |  | 0 | 11899.4679 | 11899.4679 | 11899.4679 | 11899.4679 | 11899.4679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7689 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 6099.7661 | 0.2 | 0.3 | 9515.6352 |  |  |  |  | 0 | 10505.9501 | 10505.9501 | 10505.9501 | 10505.9501 | 10505.9501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7690 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 11595.4611 | 0.2 | 0.3 | 18088.9193 |  |  |  |  | 0 | 8510.7216 | 8510.7216 | 8510.7216 | 8510.7216 | 8510.7216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7691 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16667.5157 | 0.2 | 0.3 | 26001.3244 |  |  |  |  | 0 | 14264.0289 | 14264.0289 | 14264.0289 | 14264.0289 | 14264.0289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7692 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 9059.9392 | 0.2 | 0.3 | 14133.5052 |  |  |  |  | 0 | 11482.5041 | 11482.5041 | 11482.5041 | 11482.5041 | 11482.5041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7693 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 5080.2938 | 0.2 | 0.3 | 7925.2583 |  |  |  |  | 0 | 2656.6199 | 2656.6199 | 2656.6199 | 2656.6199 | 2656.6199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7694 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 16763.873 | 0.2 | 0.3 | 26151.6419 |  |  |  |  | 0 | 2544.4056 | 2544.4056 | 2544.4056 | 2544.4056 | 2544.4056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7695 | MIRAMAR | 110364 | Private | 2036 | 5 | Swales | 66.6667 | 15059.4171 | 0.2 | 0.3 | 23492.6906 |  |  |  |  | 0 | 5200.9058 | 5200.9058 | 5200.9058 | 5200.9058 | 5200.9058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7696 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 19663.6835 | 0.2 | 0.3 | 30675.3463 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7697 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 21432.1056 | 0.2 | 0.3 | 33434.0847 |  |  |  |  | 0 | 8966.0998 | 8966.0998 | 8966.0998 | 8966.0998 | 8966.0998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7698 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 20773.7777 | 0.2 | 0.3 | 32407.0933 |  |  |  |  | 0 | 8878.4291 | 8878.4291 | 8878.4291 | 8878.4291 | 8878.4291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7699 | MIRAMAR | 110365 | Private | 2036 | 5 | Swales | 66.6667 | 22983.8759 | 0.2 | 0.3 | 35854.8464 |  |  |  |  | 0 | 8762.8104 | 8762.8104 | 8762.8104 | 8762.8104 | 8762.8104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7700 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 398.5336 | 0.2 | 0.3 | 621.7124 |  |  |  |  | 0 | 9768.4025 | 9768.4025 | 9768.4025 | 9768.4025 | 9768.4025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7701 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 24286.453 | 0.2 | 0.3 | 37886.8667 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7702 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 22920.9356 | 0.2 | 0.3 | 35756.6595 |  |  |  |  | 0 | 5200.8062 | 5200.8062 | 5200.8062 | 5200.8062 | 5200.8062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7703 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 16671.0018 | 0.2 | 0.3 | 26006.7628 |  |  |  |  | 0 | 7388.1913 | 7388.1913 | 7388.1913 | 7388.1913 | 7388.1913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7704 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 9071.1057 | 0.2 | 0.3 | 14150.9248 |  |  |  |  | 0 | 7497.8234 | 7497.8234 | 7497.8234 | 7497.8234 | 7497.8234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7705 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 7606.5088 | 0.2 | 0.3 | 11866.1537 |  |  |  |  | 0 | 8521.7694 | 8521.7694 | 8521.7694 | 8521.7694 | 8521.7694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7706 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 8336.034 | 0.2 | 0.3 | 13004.213 |  |  |  |  | 0 | 1450.4261 | 1450.4261 | 1450.4261 | 1450.4261 | 1450.4261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7707 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 8335.7606 | 0.2 | 0.3 | 13003.7865 |  |  |  |  | 0 | 5201.5405 | 5201.5405 | 5201.5405 | 5201.5405 | 5201.5405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7708 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 85.0167 | 0.2 | 0.3 | 132.626 |  |  |  |  | 0 | 2600.4675 | 2600.4675 | 2600.4675 | 2600.4675 | 2600.4675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7709 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 6811.4053 | 0.2 | 0.3 | 10625.7922 |  |  |  |  | 0 | 2600.4548 | 2600.4548 | 2600.4548 | 2600.4548 | 2600.4548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7710 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 18199.8571 | 0.2 | 0.3 | 28391.7771 |  |  |  |  | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7711 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 25354.6091 | 0.2 | 0.3 | 39553.1901 |  |  |  |  | 0 | 5201.9113 | 5201.9113 | 5201.9113 | 5201.9113 | 5201.9113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7712 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 16670.367 | 0.2 | 0.3 | 26005.7725 |  |  |  |  | 0 | 5619.0947 | 5619.0947 | 5619.0947 | 5619.0947 | 5619.0947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7713 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 8206.9347 | 0.2 | 0.3 | 12802.8181 |  |  |  |  | 0 | 5741.4668 | 5741.4668 | 5741.4668 | 5741.4668 | 5741.4668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7714 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 8467.0732 | 0.2 | 0.3 | 13208.6342 |  |  |  |  | 0 | 5833.9013 | 5833.9013 | 5833.9013 | 5833.9013 | 5833.9013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7715 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 7102.7933 | 0.2 | 0.3 | 11080.3575 |  |  |  |  | 0 | 9778.4082 | 9778.4082 | 9778.4082 | 9778.4082 | 9778.4082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7716 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 9568.9476 | 0.2 | 0.3 | 14927.5583 |  |  |  |  | 0 | 8977.1959 | 8977.1959 | 8977.1959 | 8977.1959 | 8977.1959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7717 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16672.5285 | 0.2 | 0.3 | 26009.1445 |  |  |  |  | 0 | 9140.6212 | 9140.6212 | 9140.6212 | 9140.6212 | 9140.6212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7718 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.5596 | 0.2 | 0.3 | 26007.633 |  |  |  |  | 0 | 5627.9486 | 5627.9486 | 5627.9486 | 5627.9486 | 5627.9486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7719 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 20887.7372 | 0.2 | 0.3 | 32584.87 |  |  |  |  | 0 | 7578.1163 | 7578.1163 | 7578.1163 | 7578.1163 | 7578.1163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7720 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 16672.1467 | 0.2 | 0.3 | 26008.5488 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7721 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 33619.1112 | 0.2 | 0.3 | 52445.8135 |  |  |  |  | 0 | 4034.5768 | 4034.5768 | 4034.5768 | 4034.5768 | 4034.5768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7722 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 23105.9227 | 0.2 | 0.3 | 36045.2394 |  |  |  |  | 0 | 6777.7156 | 6777.7156 | 6777.7156 | 6777.7156 | 6777.7156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7723 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 22023.1418 | 0.2 | 0.3 | 34356.1012 |  |  |  |  | 0 | 7023.7058 | 7023.7058 | 7023.7058 | 7023.7058 | 7023.7058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7724 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 25610.9975 | 0.2 | 0.3 | 39953.1562 |  |  |  |  | 0 | 9777.7783 | 9777.7783 | 9777.7783 | 9777.7783 | 9777.7783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7725 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 20089.6155 | 0.2 | 0.3 | 31339.8002 |  |  |  |  | 0 | 8398.9329 | 8398.9329 | 8398.9329 | 8398.9329 | 8398.9329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7726 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 30207.4592 | 0.2 | 0.3 | 47123.6364 |  |  |  |  | 0 | 4470.1149 | 4470.1149 | 4470.1149 | 4470.1149 | 4470.1149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7727 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 29844.9524 | 0.2 | 0.3 | 46558.1257 |  |  |  |  | 0 | 5201.9609 | 5201.9609 | 5201.9609 | 5201.9609 | 5201.9609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7728 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 22950.7319 | 0.2 | 0.3 | 35803.1417 |  |  |  |  | 0 | 5201.9667 | 5201.9667 | 5201.9667 | 5201.9667 | 5201.9667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7729 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 17574.6604 | 0.2 | 0.3 | 27416.4702 |  |  |  |  | 0 | 5201.6522 | 5201.6522 | 5201.6522 | 5201.6522 | 5201.6522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7730 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 21114.35 | 0.2 | 0.3 | 32938.386 |  |  |  |  | 0 | 5203.9266 | 5203.9266 | 5203.9266 | 5203.9266 | 5203.9266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7731 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 12549.7839 | 0.2 | 0.3 | 19577.6629 |  |  |  |  | 0 | 5201.0065 | 5201.0065 | 5201.0065 | 5201.0065 | 5201.0065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7732 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 554.1187 | 0.2 | 0.3 | 864.4252 |  |  |  |  | 0 | 8336.7595 | 8336.7595 | 8336.7595 | 8336.7595 | 8336.7595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7733 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 16117.4447 | 0.2 | 0.3 | 25143.2137 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7734 | COOPER CITY | 70403 | Private | 2026 | 5 | Swales | 66.6667 | 23624.2513 | 0.2 | 0.3 | 36853.832 |  |  |  |  | 0 | 7625.2635 | 7625.2635 | 7625.2635 | 7625.2635 | 7625.2635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7735 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16672.0681 | 0.2 | 0.3 | 26008.4262 |  |  |  |  | 0 | 5258.3154 | 5258.3154 | 5258.3154 | 5258.3154 | 5258.3154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7736 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.5213 | 0.2 | 0.3 | 26007.5732 |  |  |  |  | 0 | 1607.0893 | 1607.0893 | 1607.0893 | 1607.0893 | 1607.0893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7737 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 23932.8255 | 0.2 | 0.3 | 37335.2077 |  |  |  |  | 0 | 5747.605 | 5747.605 | 5747.605 | 5747.605 | 5747.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7738 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 5774.67 | 0.2 | 0.3 | 9008.4852 |  |  |  |  | 0 | 7163.1122 | 7163.1122 | 7163.1122 | 7163.1122 | 7163.1122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7739 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 19517.8801 | 0.2 | 0.3 | 30447.893 |  |  |  |  | 0 | 3046.4721 | 3046.4721 | 3046.4721 | 3046.4721 | 3046.4721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7740 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 38149.9275 | 0.2 | 0.3 | 59513.887 |  |  |  |  | 0 | 9360.6572 | 9360.6572 | 9360.6572 | 9360.6572 | 9360.6572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7741 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 24059.2121 | 0.2 | 0.3 | 37532.3709 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7742 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 20343.7761 | 0.2 | 0.3 | 31736.2907 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7743 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 16744.7931 | 0.2 | 0.3 | 26121.8772 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7744 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 16670.9179 | 0.2 | 0.3 | 26006.6319 |  |  |  |  | 0 | 9156.1399 | 9156.1399 | 9156.1399 | 9156.1399 | 9156.1399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7745 | DAVIE | 70102 | Private | 2030 | 5 | Swales | 66.6667 | 16684.4572 | 0.2 | 0.3 | 26027.7532 |  |  |  |  | 0 | 9779.8698 | 9779.8698 | 9779.8698 | 9779.8698 | 9779.8698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7746 | DAVIE | 70102 | Private | 2030 | 5 | Swales | 66.6667 | 17690.9442 | 0.2 | 0.3 | 27597.873 |  |  |  |  | 0 | 9778.8073 | 9778.8073 | 9778.8073 | 9778.8073 | 9778.8073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7747 | DAVIE | 70102 | Private | 2030 | 5 | Swales | 66.6667 | 16657.5108 | 0.2 | 0.3 | 25985.7168 |  |  |  |  | 0 | 9577.6933 | 9577.6933 | 9577.6933 | 9577.6933 | 9577.6933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7748 | DAVIE | 70102 | Private | 2030 | 5 | Swales | 66.6667 | 16688.7984 | 0.2 | 0.3 | 26034.5255 |  |  |  |  | 0 | 11733.014 | 11733.014 | 11733.014 | 11733.014 | 11733.014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7749 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 5017.7533 | 0.2 | 0.3 | 7827.6951 |  |  |  |  | 0 | 10254.4978 | 10254.4978 | 10254.4978 | 10254.4978 | 10254.4978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7750 | COOPER CITY | 70403 | Private | 2026 | 5 | Swales | 66.6667 | 16701.3221 | 0.2 | 0.3 | 26054.0624 |  |  |  |  | 0 | 7126.4899 | 7126.4899 | 7126.4899 | 7126.4899 | 7126.4899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7751 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 25766.273 | 0.2 | 0.3 | 40195.3859 |  |  |  |  | 0 | 3498.6943 | 3498.6943 | 3498.6943 | 3498.6943 | 3498.6943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7752 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 27579.9391 | 0.2 | 0.3 | 43024.7049 |  |  |  |  | 0 | 5201.8287 | 5201.8287 | 5201.8287 | 5201.8287 | 5201.8287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7753 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 28043.457 | 0.2 | 0.3 | 43747.7929 |  |  |  |  | 0 | 5201.825 | 5201.825 | 5201.825 | 5201.825 | 5201.825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7754 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 28726.5967 | 0.2 | 0.3 | 44813.4909 |  |  |  |  | 0 | 5201.5802 | 5201.5802 | 5201.5802 | 5201.5802 | 5201.5802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7755 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 13559.2863 | 0.2 | 0.3 | 21152.4866 |  |  |  |  | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7756 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16672.0681 | 0.2 | 0.3 | 26008.4262 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7757 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.2479 | 0.2 | 0.3 | 26007.1467 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7758 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 15872.2587 | 0.2 | 0.3 | 24760.7236 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7759 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 1542.0528 | 0.2 | 0.3 | 2405.6024 |  |  |  |  | 0 | 7024.1493 | 7024.1493 | 7024.1493 | 7024.1493 | 7024.1493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7760 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 6114.4343 | 0.2 | 0.3 | 9538.5175 |  |  |  |  | 0 | 5203.0015 | 5203.0015 | 5203.0015 | 5203.0015 | 5203.0015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7761 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 11786.6389 | 0.2 | 0.3 | 18387.1566 |  |  |  |  | 0 | 5201.1033 | 5201.1033 | 5201.1033 | 5201.1033 | 5201.1033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7762 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 20477.004 | 0.2 | 0.3 | 31944.1262 |  |  |  |  | 0 | 7649.4126 | 7649.4126 | 7649.4126 | 7649.4126 | 7649.4126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7763 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 21403.7614 | 0.2 | 0.3 | 33389.8678 |  |  |  |  | 0 | 5202.9592 | 5202.9592 | 5202.9592 | 5202.9592 | 5202.9592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7764 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 34383.581 | 0.2 | 0.3 | 53638.3864 |  |  |  |  | 0 | 5203.0369 | 5203.0369 | 5203.0369 | 5203.0369 | 5203.0369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7765 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 3926.5405 | 0.2 | 0.3 | 6125.4031 |  |  |  |  | 0 | 12214.3085 | 12214.3085 | 12214.3085 | 12214.3085 | 12214.3085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7766 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 8979.4549 | 0.2 | 0.3 | 14007.9497 |  |  |  |  | 0 | 8258.4005 | 8258.4005 | 8258.4005 | 8258.4005 | 8258.4005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7767 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 21423.2179 | 0.2 | 0.3 | 33420.2199 |  |  |  |  | 0 | 9795.5065 | 9795.5065 | 9795.5065 | 9795.5065 | 9795.5065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7768 | COOPER CITY | 70403 | Private | 2026 | 5 | Swales | 66.6667 | 16701.3221 | 0.2 | 0.3 | 26054.0624 |  |  |  |  | 0 | 9785.7359 | 9785.7359 | 9785.7359 | 9785.7359 | 9785.7359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7769 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16675.6567 | 0.2 | 0.3 | 26014.0244 |  |  |  |  | 0 | 7836.0734 | 7836.0734 | 7836.0734 | 7836.0734 | 7836.0734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7770 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16666.3232 | 0.2 | 0.3 | 25999.4642 |  |  |  |  | 0 | 7709.9076 | 7709.9076 | 7709.9076 | 7709.9076 | 7709.9076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7771 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16673.8161 | 0.2 | 0.3 | 26011.1531 |  |  |  |  | 0 | 9778.9537 | 9778.9537 | 9778.9537 | 9778.9537 | 9778.9537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7772 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16677.4868 | 0.2 | 0.3 | 26016.8794 |  |  |  |  | 0 | 7519.642 | 7519.642 | 7519.642 | 7519.642 | 7519.642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7773 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.7613 | 0.2 | 0.3 | 26007.9476 |  |  |  |  | 0 | 7288.373 | 7288.373 | 7288.373 | 7288.373 | 7288.373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7774 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.7413 | 0.2 | 0.3 | 26007.9164 |  |  |  |  | 0 | 5200.1268 | 5200.1268 | 5200.1268 | 5200.1268 | 5200.1268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7775 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.9701 | 0.2 | 0.3 | 26006.7133 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7776 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 25657.0839 | 0.2 | 0.3 | 40025.0508 |  |  |  |  | 0 | 9778.0859 | 9778.0859 | 9778.0859 | 9778.0859 | 9778.0859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7777 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 33360.6444 | 0.2 | 0.3 | 52042.6053 |  |  |  |  | 0 | 5201.9001 | 5201.9001 | 5201.9001 | 5201.9001 | 5201.9001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7778 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 33361.1995 | 0.2 | 0.3 | 52043.4713 |  |  |  |  | 0 | 5201.9767 | 5201.9767 | 5201.9767 | 5201.9767 | 5201.9767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7779 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 38222.1305 | 0.2 | 0.3 | 59626.5235 |  |  |  |  | 0 | 6420.8989 | 6420.8989 | 6420.8989 | 6420.8989 | 6420.8989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7780 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 28863.8786 | 0.2 | 0.3 | 45027.6506 |  |  |  |  | 0 | 7739.2352 | 7739.2352 | 7739.2352 | 7739.2352 | 7739.2352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7781 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 16683.0041 | 0.2 | 0.3 | 26025.4864 |  |  |  |  | 0 | 5200.9949 | 5200.9949 | 5200.9949 | 5200.9949 | 5200.9949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7782 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 17644.4371 | 0.2 | 0.3 | 27525.3219 |  |  |  |  | 0 | 7933.9215 | 7933.9215 | 7933.9215 | 7933.9215 | 7933.9215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7783 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 1817.9199 | 0.2 | 0.3 | 2835.955 |  |  |  |  | 0 | 5201.5208 | 5201.5208 | 5201.5208 | 5201.5208 | 5201.5208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7784 | DAVIE | 70602 | Public | 2033 | 5 | Swales | 66.6667 | 1757.026 | 0.2 | 0.3 | 2740.9606 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7785 | DAVIE | 70602 | Public | 2033 | 5 | Swales | 66.6667 | 8258.3343 | 0.2 | 0.3 | 12883.0016 |  |  |  |  | 0 | 9779.3152 | 9779.3152 | 9779.3152 | 9779.3152 | 9779.3152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7786 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 25371.3445 | 0.2 | 0.3 | 39579.2974 |  |  |  |  | 0 | 5201.8795 | 5201.8795 | 5201.8795 | 5201.8795 | 5201.8795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7787 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 46199.2481 | 0.2 | 0.3 | 72070.827 |  |  |  |  | 0 | 5202.0433 | 5202.0433 | 5202.0433 | 5202.0433 | 5202.0433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7788 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16652.6565 | 0.2 | 0.3 | 25978.1441 |  |  |  |  | 0 | 9183.8696 | 9183.8696 | 9183.8696 | 9183.8696 | 9183.8696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7789 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16674.6263 | 0.2 | 0.3 | 26012.4171 |  |  |  |  | 0 | 9777.4672 | 9777.4672 | 9777.4672 | 9777.4672 | 9777.4672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7790 | COOPER CITY | 70403 | Private | 2026 | 5 | Swales | 66.6667 | 22139.0505 | 0.2 | 0.3 | 34536.9187 |  |  |  |  | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7791 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 13228.6701 | 13228.6701 | 13228.6701 | 13228.6701 | 13228.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7792 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16702.4825 | 0.2 | 0.3 | 26055.8728 |  |  |  |  | 0 | 5261.4247 | 5261.4247 | 5261.4247 | 5261.4247 | 5261.4247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7793 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16679.5267 | 0.2 | 0.3 | 26020.0617 |  |  |  |  | 0 | 11876.0874 | 11876.0874 | 11876.0874 | 11876.0874 | 11876.0874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7794 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.9527 | 0.2 | 0.3 | 26006.6862 |  |  |  |  | 0 | 7801.8708 | 7801.8708 | 7801.8708 | 7801.8708 | 7801.8708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7795 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 29705.8193 | 0.2 | 0.3 | 46341.0782 |  |  |  |  | 0 | 7801.843 | 7801.843 | 7801.843 | 7801.843 | 7801.843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7796 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 31431.7784 | 0.2 | 0.3 | 49033.5743 |  |  |  |  | 0 | 6969.6504 | 6969.6504 | 6969.6504 | 6969.6504 | 6969.6504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7797 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 33360.4871 | 0.2 | 0.3 | 52042.3598 |  |  |  |  | 0 | 13175.7968 | 13175.7968 | 13175.7968 | 13175.7968 | 13175.7968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7798 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 7117.8762 | 0.2 | 0.3 | 11103.8869 |  |  |  |  | 0 | 6013.9271 | 6013.9271 | 6013.9271 | 6013.9271 | 6013.9271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7799 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 13242.4087 | 0.2 | 0.3 | 20658.1575 |  |  |  |  | 0 | 2797.0851 | 2797.0851 | 2797.0851 | 2797.0851 | 2797.0851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7800 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 9873.7928 | 0.2 | 0.3 | 15403.1168 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7801 | DAVIE | 70602 | Public | 2033 | 5 | Swales | 66.6667 | 20939.8735 | 0.2 | 0.3 | 32666.2027 |  |  |  |  | 0 | 5201.4274 | 5201.4274 | 5201.4274 | 5201.4274 | 5201.4274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7802 | DAVIE | 70602 | Public | 2033 | 5 | Swales | 66.6667 | 8414.8459 | 0.2 | 0.3 | 13127.1597 |  |  |  |  | 0 | 5233.5085 | 5233.5085 | 5233.5085 | 5233.5085 | 5233.5085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7803 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 6795.4697 | 0.2 | 0.3 | 10600.9328 |  |  |  |  | 0 | 2256.6943 | 2256.6943 | 2256.6943 | 2256.6943 | 2256.6943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7804 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 17263.3213 | 0.2 | 0.3 | 26930.7813 |  |  |  |  | 0 | 6089.3525 | 6089.3525 | 6089.3525 | 6089.3525 | 6089.3525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7805 | DAVIE | 70602 | Public | 2033 | 5 | Swales | 66.6667 | 21788.3723 | 0.2 | 0.3 | 33989.8608 |  |  |  |  | 0 | 7317.2036 | 7317.2036 | 7317.2036 | 7317.2036 | 7317.2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7806 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 14358.8991 | 0.2 | 0.3 | 22399.8826 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7807 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 34636.0791 | 0.2 | 0.3 | 54032.2833 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7808 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 34641.7531 | 0.2 | 0.3 | 54041.1348 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7809 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16703.2707 | 0.2 | 0.3 | 26057.1022 |  |  |  |  | 0 | 5994.9176 | 5994.9176 | 5994.9176 | 5994.9176 | 5994.9176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7810 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16725.3533 | 0.2 | 0.3 | 26091.5511 |  |  |  |  | 0 | 5317.4213 | 5317.4213 | 5317.4213 | 5317.4213 | 5317.4213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7811 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16702.4157 | 0.2 | 0.3 | 26055.7684 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7812 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16685.0791 | 0.2 | 0.3 | 26028.7233 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7813 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16751.9015 | 0.2 | 0.3 | 26132.9663 |  |  |  |  | 0 | 8015.0746 | 8015.0746 | 8015.0746 | 8015.0746 | 8015.0746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7814 | COOPER CITY | 70403 | Private | 2026 | 5 | Swales | 66.6667 | 16808.7691 | 0.2 | 0.3 | 26221.6798 |  |  |  |  | 0 | 5143.7299 | 5143.7299 | 5143.7299 | 5143.7299 | 5143.7299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7815 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16748.3473 | 0.2 | 0.3 | 26127.4217 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7816 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 33360.2668 | 0.2 | 0.3 | 52042.0162 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7817 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 52.0004 | 0.2 | 0.3 | 81.1206 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7818 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 28002.8935 | 0.2 | 0.3 | 43684.5138 |  |  |  |  | 0 | 617.2459 | 617.2459 | 617.2459 | 617.2459 | 617.2459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7819 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 7310.9241 | 0.2 | 0.3 | 11405.0416 |  |  |  |  | 0 | 5200.9417 | 5200.9417 | 5200.9417 | 5200.9417 | 5200.9417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7820 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 1279.7634 | 0.2 | 0.3 | 1996.4309 |  |  |  |  | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7821 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 24607.2318 | 0.2 | 0.3 | 38387.2816 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7822 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 23460.645 | 0.2 | 0.3 | 36598.6062 |  |  |  |  | 0 | 4000.3281 | 4000.3281 | 4000.3281 | 4000.3281 | 4000.3281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7823 | DAVIE | 70602 | Public | 2033 | 5 | Swales | 66.6667 | 3909.4687 | 0.2 | 0.3 | 6098.7711 |  |  |  |  | 0 | 1200.8767 | 1200.8767 | 1200.8767 | 1200.8767 | 1200.8767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7824 | DAVIE | 70602 | Public | 2033 | 5 | Swales | 66.6667 | 8975.8723 | 0.2 | 0.3 | 14002.3608 |  |  |  |  | 0 | 5203.1647 | 5203.1647 | 5203.1647 | 5203.1647 | 5203.1647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7825 | DAVIE | 70602 | Public | 2033 | 5 | Swales | 66.6667 | 16668.6608 | 0.2 | 0.3 | 26003.1108 |  |  |  |  | 0 | 5056.1016 | 5056.1016 | 5056.1016 | 5056.1016 | 5056.1016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7826 | DAVIE | 70602 | Public | 2033 | 5 | Swales | 66.6667 | 19101.5343 | 0.2 | 0.3 | 29798.3936 |  |  |  |  | 0 | 2720.1611 | 2720.1611 | 2720.1611 | 2720.1611 | 2720.1611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7827 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 29780.6915 | 0.2 | 0.3 | 46457.8788 |  |  |  |  | 0 | 2976.9947 | 2976.9947 | 2976.9947 | 2976.9947 | 2976.9947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7828 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 30661.0604 | 0.2 | 0.3 | 47831.2542 |  |  |  |  | 0 | 1219.6323 | 1219.6323 | 1219.6323 | 1219.6323 | 1219.6323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7829 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 26252.8803 | 0.2 | 0.3 | 40954.4932 |  |  |  |  | 0 | 4450.9695 | 4450.9695 | 4450.9695 | 4450.9695 | 4450.9695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7830 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16791.7069 | 0.2 | 0.3 | 26195.0627 |  |  |  |  | 0 | 5201.8547 | 5201.8547 | 5201.8547 | 5201.8547 | 5201.8547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7831 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16766.3686 | 0.2 | 0.3 | 26155.535 |  |  |  |  | 0 | 5369.6317 | 5369.6317 | 5369.6317 | 5369.6317 | 5369.6317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7832 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16810.0248 | 0.2 | 0.3 | 26223.6387 |  |  |  |  | 0 | 5201.4024 | 5201.4024 | 5201.4024 | 5201.4024 | 5201.4024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7833 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16988.8893 | 0.2 | 0.3 | 26502.6674 |  |  |  |  | 0 | 5662.7499 | 5662.7499 | 5662.7499 | 5662.7499 | 5662.7499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7834 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 27000.9071 | 0.2 | 0.3 | 42121.415 |  |  |  |  | 0 | 9708.8945 | 9708.8945 | 9708.8945 | 9708.8945 | 9708.8945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7835 | COOPER CITY | 70403 | Private | 2026 | 5 | Swales | 66.6667 | 28872.084 | 0.2 | 0.3 | 45040.451 |  |  |  |  | 0 | 7848.5569 | 7848.5569 | 7848.5569 | 7848.5569 | 7848.5569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7836 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 25675.7791 | 0.2 | 0.3 | 40054.2154 |  |  |  |  | 0 | 4672.3813 | 4672.3813 | 4672.3813 | 4672.3813 | 4672.3813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7837 | DAVIE | 70602 | Private | 2026 | 5 | Swales | 66.6667 | 20893.6103 | 0.2 | 0.3 | 32594.0321 |  |  |  |  | 0 | 2224.4615 | 2224.4615 | 2224.4615 | 2224.4615 | 2224.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7838 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 16690.1126 | 0.2 | 0.3 | 26036.5757 |  |  |  |  | 0 | 169.3812 | 169.3812 | 169.3812 | 169.3812 | 169.3812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7839 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 16691.753 | 0.2 | 0.3 | 26039.1347 |  |  |  |  | 0 | 5201.0665 | 5201.0665 | 5201.0665 | 5201.0665 | 5201.0665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7840 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 17451.0759 | 0.2 | 0.3 | 27223.6784 |  |  |  |  | 0 | 5844.8347 | 5844.8347 | 5844.8347 | 5844.8347 | 5844.8347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7841 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 16183.6481 | 0.2 | 0.3 | 25246.491 |  |  |  |  | 0 | 6852.1604 | 6852.1604 | 6852.1604 | 6852.1604 | 6852.1604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7842 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 2752.7549 | 0.2 | 0.3 | 4294.2977 |  |  |  |  | 0 | 4784.7555 | 4784.7555 | 4784.7555 | 4784.7555 | 4784.7555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7843 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 15689.4322 | 0.2 | 0.3 | 24475.5142 |  |  |  |  | 0 | 3982.6674 | 3982.6674 | 3982.6674 | 3982.6674 | 3982.6674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7844 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16676.4425 | 0.2 | 0.3 | 26015.2502 |  |  |  |  | 0 | 9186.1154 | 9186.1154 | 9186.1154 | 9186.1154 | 9186.1154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7845 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16673.4351 | 0.2 | 0.3 | 26010.5587 |  |  |  |  | 0 | 5202.6971 | 5202.6971 | 5202.6971 | 5202.6971 | 5202.6971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7846 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 15152.3692 | 0.2 | 0.3 | 23637.696 |  |  |  |  | 0 | 6619.8242 | 6619.8242 | 6619.8242 | 6619.8242 | 6619.8242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7847 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 1791.3148 | 0.2 | 0.3 | 2794.4511 |  |  |  |  | 0 | 7906.6887 | 7906.6887 | 7906.6887 | 7906.6887 | 7906.6887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7848 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 25222.1783 | 0.2 | 0.3 | 39346.5982 |  |  |  |  | 0 | 5327.4313 | 5327.4313 | 5327.4313 | 5327.4313 | 5327.4313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7849 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 32121.8908 | 0.2 | 0.3 | 50110.1496 |  |  |  |  | 0 | 5277.3904 | 5277.3904 | 5277.3904 | 5277.3904 | 5277.3904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7850 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 32288.0839 | 0.2 | 0.3 | 50369.4108 |  |  |  |  | 0 | 2176.5137 | 2176.5137 | 2176.5137 | 2176.5137 | 2176.5137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7851 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 12765.4638 | 0.2 | 0.3 | 19914.1235 |  |  |  |  | 0 | 7843.7333 | 7843.7333 | 7843.7333 | 7843.7333 | 7843.7333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7852 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 12846.7257 | 0.2 | 0.3 | 20040.892 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7853 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 31820.9402 | 0.2 | 0.3 | 49640.6667 |  |  |  |  | 0 | 5056.122 | 5056.122 | 5056.122 | 5056.122 | 5056.122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7854 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 30990.3016 | 0.2 | 0.3 | 48344.8705 |  |  |  |  | 0 | 547.8031 | 547.8031 | 547.8031 | 547.8031 | 547.8031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7855 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 18754.618 | 0.2 | 0.3 | 29257.2041 |  |  |  |  | 0 | 279.076 | 279.076 | 279.076 | 279.076 | 279.076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7856 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 17551.5274 | 0.2 | 0.3 | 27380.3827 |  |  |  |  | 0 | 5407.5589 | 5407.5589 | 5407.5589 | 5407.5589 | 5407.5589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7857 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 17317.4187 | 0.2 | 0.3 | 27015.1732 |  |  |  |  | 0 | 6609.7235 | 6609.7235 | 6609.7235 | 6609.7235 | 6609.7235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7858 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 17275.3729 | 0.2 | 0.3 | 26949.5818 |  |  |  |  | 0 | 6863.1928 | 6863.1928 | 6863.1928 | 6863.1928 | 6863.1928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7859 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 17459.3674 | 0.2 | 0.3 | 27236.6131 |  |  |  |  | 0 | 5203.0945 | 5203.0945 | 5203.0945 | 5203.0945 | 5203.0945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7860 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 34.543 | 0.2 | 0.3 | 53.8871 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7861 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 25655.1611 | 0.2 | 0.3 | 40022.0514 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7862 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 16675.0755 | 0.2 | 0.3 | 26013.1177 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7863 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 8708.0183 | 0.2 | 0.3 | 13584.5086 |  |  |  |  | 0 | 10405.2471 | 10405.2471 | 10405.2471 | 10405.2471 | 10405.2471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7864 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 7385.6697 | 0.2 | 0.3 | 11521.6448 |  |  |  |  | 0 | 2600.7073 | 2600.7073 | 2600.7073 | 2600.7073 | 2600.7073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7865 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 10951.7633 | 0.2 | 0.3 | 17084.7508 |  |  |  |  | 0 | 8928.3802 | 8928.3802 | 8928.3802 | 8928.3802 | 8928.3802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7866 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 25169.1083 | 0.2 | 0.3 | 39263.8089 |  |  |  |  | 0 | 2017.7351 | 2017.7351 | 2017.7351 | 2017.7351 | 2017.7351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7867 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 11111.5711 | 0.2 | 0.3 | 17334.0509 |  |  |  |  | 0 | 5201.1059 | 5201.1059 | 5201.1059 | 5201.1059 | 5201.1059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7868 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 14145.8267 | 0.2 | 0.3 | 22067.4896 |  |  |  |  | 0 | 5202.5885 | 5202.5885 | 5202.5885 | 5202.5885 | 5202.5885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7869 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 12278.2547 | 0.2 | 0.3 | 19154.0773 |  |  |  |  | 0 | 5203.0603 | 5203.0603 | 5203.0603 | 5203.0603 | 5203.0603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7870 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 15740.7815 | 0.2 | 0.3 | 24555.6192 |  |  |  |  | 0 | 1055.7349 | 1055.7349 | 1055.7349 | 1055.7349 | 1055.7349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7871 | COOPER CITY | 70404 | Public | 2033 | 5 | Swales | 66.6667 | 11419.3538 | 0.2 | 0.3 | 17814.1919 |  |  |  |  | 0 | 9754.963 | 9754.963 | 9754.963 | 9754.963 | 9754.963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7872 | COOPER CITY | 70404 | Public | 2033 | 5 | Swales | 66.6667 | 22114.7303 | 0.2 | 0.3 | 34498.9792 |  |  |  |  | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7873 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 16762.9513 | 0.2 | 0.3 | 26150.2041 |  |  |  |  | 0 | 3100.021 | 3100.021 | 3100.021 | 3100.021 | 3100.021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7874 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 16817.1177 | 0.2 | 0.3 | 26234.7037 |  |  |  |  | 0 | 4160.9496 | 4160.9496 | 4160.9496 | 4160.9496 | 4160.9496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7875 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 29356.4963 | 0.2 | 0.3 | 45796.1343 |  |  |  |  | 0 | 5126.5326 | 5126.5326 | 5126.5326 | 5126.5326 | 5126.5326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7876 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 15117.0326 | 0.2 | 0.3 | 23582.5709 |  |  |  |  | 0 | 9033.9607 | 9033.9607 | 9033.9607 | 9033.9607 | 9033.9607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7877 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 14843.0303 | 0.2 | 0.3 | 23155.1273 |  |  |  |  | 0 | 5196.4699 | 5196.4699 | 5196.4699 | 5196.4699 | 5196.4699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7878 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 31529.8208 | 0.2 | 0.3 | 49186.5204 |  |  |  |  | 0 | 2686.1103 | 2686.1103 | 2686.1103 | 2686.1103 | 2686.1103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7879 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 18179.6079 | 0.2 | 0.3 | 28360.1884 |  |  |  |  | 0 | 4408.149 | 4408.149 | 4408.149 | 4408.149 | 4408.149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7880 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 18327.0119 | 0.2 | 0.3 | 28590.1386 |  |  |  |  | 0 | 6061.1055 | 6061.1055 | 6061.1055 | 6061.1055 | 6061.1055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7881 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 25910.1848 | 0.2 | 0.3 | 40419.8883 |  |  |  |  | 0 | 5202.0013 | 5202.0013 | 5202.0013 | 5202.0013 | 5202.0013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7882 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 27200.9549 | 0.2 | 0.3 | 42433.4896 |  |  |  |  | 0 | 5201.9173 | 5201.9173 | 5201.9173 | 5201.9173 | 5201.9173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7883 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 1910.3187 | 0.2 | 0.3 | 2980.0971 |  |  |  |  | 0 | 5201.5317 | 5201.5317 | 5201.5317 | 5201.5317 | 5201.5317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7884 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 21070.5343 | 0.2 | 0.3 | 32870.0336 |  |  |  |  | 0 | 10405.0848 | 10405.0848 | 10405.0848 | 10405.0848 | 10405.0848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7885 | COOPER CITY | 70404 | Public | 2033 | 5 | Swales | 66.6667 | 16691.9917 | 0.2 | 0.3 | 26039.507 |  |  |  |  | 0 | 2600.8773 | 2600.8773 | 2600.8773 | 2600.8773 | 2600.8773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7886 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 16125.039 | 0.2 | 0.3 | 25155.0608 |  |  |  |  | 0 | 6054.3865 | 6054.3865 | 6054.3865 | 6054.3865 | 6054.3865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7887 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 16681.1722 | 0.2 | 0.3 | 26022.6286 |  |  |  |  | 0 | 5381.727 | 5381.727 | 5381.727 | 5381.727 | 5381.727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7888 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 5120.0777 | 0.2 | 0.3 | 7987.3213 |  |  |  |  | 0 | 7460.1707 | 7460.1707 | 7460.1707 | 7460.1707 | 7460.1707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7889 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 31642.1465 | 0.2 | 0.3 | 49361.7485 |  |  |  |  | 0 | 9873.5731 | 9873.5731 | 9873.5731 | 9873.5731 | 9873.5731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7890 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 17597.8161 | 0.2 | 0.3 | 27452.5932 |  |  |  |  | 0 | 5299.318 | 5299.318 | 5299.318 | 5299.318 | 5299.318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7891 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16995.9887 | 0.2 | 0.3 | 26513.7424 |  |  |  |  | 0 | 4213.4257 | 4213.4257 | 4213.4257 | 4213.4257 | 4213.4257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7892 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 19394.2526 | 0.2 | 0.3 | 30255.0341 |  |  |  |  | 0 | 6300.6921 | 6300.6921 | 6300.6921 | 6300.6921 | 6300.6921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7893 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 20770.0223 | 0.2 | 0.3 | 32401.2347 |  |  |  |  | 0 | 2599.4729 | 2599.4729 | 2599.4729 | 2599.4729 | 2599.4729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7894 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 17143.2431 | 0.2 | 0.3 | 26743.4592 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7895 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 13524.0179 | 0.2 | 0.3 | 21097.4679 |  |  |  |  | 0 | 5609.1895 | 5609.1895 | 5609.1895 | 5609.1895 | 5609.1895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7896 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 18699.0623 | 0.2 | 0.3 | 29170.5372 |  |  |  |  | 0 | 3978.8197 | 3978.8197 | 3978.8197 | 3978.8197 | 3978.8197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7897 | COOPER CITY | 70403 | Private | 2026 | 5 | Swales | 66.6667 | 16625.4031 | 0.2 | 0.3 | 25935.6288 |  |  |  |  | 0 | 5266.066 | 5266.066 | 5266.066 | 5266.066 | 5266.066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7898 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 22084.4495 | 0.2 | 0.3 | 34451.7413 |  |  |  |  | 0 | 9777.9997 | 9777.9997 | 9777.9997 | 9777.9997 | 9777.9997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7899 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16767.003 | 0.2 | 0.3 | 26156.5247 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7900 | COOPER CITY | 70404 | Public | 2033 | 5 | Swales | 66.6667 | 16674.1081 | 0.2 | 0.3 | 26011.6087 |  |  |  |  | 0 | 6486.6039 | 6486.6039 | 6486.6039 | 6486.6039 | 6486.6039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7901 | COOPER CITY | 70404 | Public | 2033 | 5 | Swales | 66.6667 | 19580.6714 | 0.2 | 0.3 | 30545.8474 |  |  |  |  | 0 | 6254.9855 | 6254.9855 | 6254.9855 | 6254.9855 | 6254.9855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7902 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 30871.0677 | 0.2 | 0.3 | 48158.8657 |  |  |  |  | 0 | 8994.143 | 8994.143 | 8994.143 | 8994.143 | 8994.143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7903 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 9932.9441 | 0.2 | 0.3 | 15495.3927 |  |  |  |  | 0 | 8280.0515 | 8280.0515 | 8280.0515 | 8280.0515 | 8280.0515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7904 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 7242.6901 | 0.2 | 0.3 | 11298.5966 |  |  |  |  | 0 | 6024.8163 | 6024.8163 | 6024.8163 | 6024.8163 | 6024.8163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7905 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 247.5783 | 0.2 | 0.3 | 386.2221 |  |  |  |  | 0 | 5038.4338 | 5038.4338 | 5038.4338 | 5038.4338 | 5038.4338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7906 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16278.5781 | 0.2 | 0.3 | 25394.5818 |  |  |  |  | 0 | 10761.1065 | 10761.1065 | 10761.1065 | 10761.1065 | 10761.1065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7907 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 560.1333 | 0.2 | 0.3 | 873.808 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7908 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16937.3819 | 0.2 | 0.3 | 26422.3158 |  |  |  |  | 0 | 6391.2959 | 6391.2959 | 6391.2959 | 6391.2959 | 6391.2959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7909 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 41593.2211 | 0.2 | 0.3 | 64885.425 |  |  |  |  | 0 | 4747.5652 | 4747.5652 | 4747.5652 | 4747.5652 | 4747.5652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7910 | COOPER CITY | 70403 | Private | 2026 | 5 | Swales | 66.6667 | 31420.5105 | 0.2 | 0.3 | 49015.9963 |  |  |  |  | 0 | 2165.9687 | 2165.9687 | 2165.9687 | 2165.9687 | 2165.9687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7911 | COOPER CITY | 70403 | Private | 2026 | 5 | Swales | 66.6667 | 24731.5079 | 0.2 | 0.3 | 38581.1523 |  |  |  |  | 0 | 9924.8699 | 9924.8699 | 9924.8699 | 9924.8699 | 9924.8699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7912 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 28849.4501 | 0.2 | 0.3 | 45005.1421 |  |  |  |  | 0 | 8641.9176 | 8641.9176 | 8641.9176 | 8641.9176 | 8641.9176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7913 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 31343.7888 | 0.2 | 0.3 | 48896.3105 |  |  |  |  | 0 | 2601.6241 | 2601.6241 | 2601.6241 | 2601.6241 | 2601.6241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7914 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 31353.8637 | 0.2 | 0.3 | 48912.0274 |  |  |  |  | 0 | 6707.711 | 6707.711 | 6707.711 | 6707.711 | 6707.711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7915 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 29785.4652 | 0.2 | 0.3 | 46465.3257 |  |  |  |  | 0 | 6900.9505 | 6900.9505 | 6900.9505 | 6900.9505 | 6900.9505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7916 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 18614.0531 | 0.2 | 0.3 | 29037.9229 |  |  |  |  | 0 | 7119.2023 | 7119.2023 | 7119.2023 | 7119.2023 | 7119.2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7917 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 31759.4433 | 0.2 | 0.3 | 49544.7316 |  |  |  |  | 0 | 7718.3888 | 7718.3888 | 7718.3888 | 7718.3888 | 7718.3888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7918 | COOPER CITY | 70403 | Private | 2026 | 5 | Swales | 66.6667 | 19614.4958 | 0.2 | 0.3 | 30598.6134 |  |  |  |  | 0 | 9782.6184 | 9782.6184 | 9782.6184 | 9782.6184 | 9782.6184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7919 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 32322.1247 | 0.2 | 0.3 | 50422.5146 |  |  |  |  | 0 | 9778.692 | 9778.692 | 9778.692 | 9778.692 | 9778.692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7920 | COOPER CITY | 70403 | Private | 2026 | 5 | Swales | 66.6667 | 27210.0303 | 0.2 | 0.3 | 42447.6472 |  |  |  |  | 0 | 6254.2086 | 6254.2086 | 6254.2086 | 6254.2086 | 6254.2086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7921 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 5410.792 | 0.2 | 0.3 | 8440.8355 |  |  |  |  | 0 | 5202.4599 | 5202.4599 | 5202.4599 | 5202.4599 | 5202.4599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7922 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 16540.0037 | 0.2 | 0.3 | 25802.4058 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7923 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 16679.1765 | 0.2 | 0.3 | 26019.5153 |  |  |  |  | 0 | 5267.1586 | 5267.1586 | 5267.1586 | 5267.1586 | 5267.1586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7924 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 16599.2574 | 0.2 | 0.3 | 25894.8415 |  |  |  |  | 0 | 8384.282 | 8384.282 | 8384.282 | 8384.282 | 8384.282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7925 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 16669.6074 | 0.2 | 0.3 | 26004.5875 |  |  |  |  | 0 | 5344.6058 | 5344.6058 | 5344.6058 | 5344.6058 | 5344.6058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7926 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 9419.5302 | 9419.5302 | 9419.5302 | 9419.5302 | 9419.5302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7927 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7928 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7929 | DAVIE | 70602 | Private | 2033 | 5 | Swales | 66.6667 | 7699.0109 | 0.2 | 0.3 | 12010.4571 |  |  |  |  | 0 | 5202.1448 | 5202.1448 | 5202.1448 | 5202.1448 | 5202.1448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7930 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 29422.3956 | 0.2 | 0.3 | 45898.9371 |  |  |  |  | 0 | 5200.9992 | 5200.9992 | 5200.9992 | 5200.9992 | 5200.9992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7931 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16677.7191 | 0.2 | 0.3 | 26017.2417 |  |  |  |  | 0 | 5201.4651 | 5201.4651 | 5201.4651 | 5201.4651 | 5201.4651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7932 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 5201.6808 | 5201.6808 | 5201.6808 | 5201.6808 | 5201.6808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7933 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16677.2627 | 0.2 | 0.3 | 26016.5298 |  |  |  |  | 0 | 9779.4821 | 9779.4821 | 9779.4821 | 9779.4821 | 9779.4821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7934 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 18539.3423 | 0.2 | 0.3 | 28921.3739 |  |  |  |  | 0 | 5200.7132 | 5200.7132 | 5200.7132 | 5200.7132 | 5200.7132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7935 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 14220.4788 | 0.2 | 0.3 | 22183.9469 |  |  |  |  | 0 | 6891.3736 | 6891.3736 | 6891.3736 | 6891.3736 | 6891.3736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7936 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16704.9221 | 0.2 | 0.3 | 26059.6785 |  |  |  |  | 0 | 8112.5103 | 8112.5103 | 8112.5103 | 8112.5103 | 8112.5103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7937 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16702.4713 | 0.2 | 0.3 | 26055.8553 |  |  |  |  | 0 | 2600.9143 | 2600.9143 | 2600.9143 | 2600.9143 | 2600.9143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7938 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 639.6319 | 0.2 | 0.3 | 997.8258 |  |  |  |  | 0 | 4168.8166 | 4168.8166 | 4168.8166 | 4168.8166 | 4168.8166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7939 | COOPER CITY | 70403 | Private | 2026 | 5 | Swales | 66.6667 | 27881.3992 | 0.2 | 0.3 | 43494.9828 |  |  |  |  | 0 | 5139.4537 | 5139.4537 | 5139.4537 | 5139.4537 | 5139.4537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7940 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 13837.7173 | 0.2 | 0.3 | 21586.839 |  |  |  |  | 0 | 6301.0357 | 6301.0357 | 6301.0357 | 6301.0357 | 6301.0357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7941 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16423.4837 | 0.2 | 0.3 | 25620.6345 |  |  |  |  | 0 | 5323.2803 | 5323.2803 | 5323.2803 | 5323.2803 | 5323.2803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7942 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 7980.181 | 0.2 | 0.3 | 12449.0824 |  |  |  |  | 0 | 6747.4254 | 6747.4254 | 6747.4254 | 6747.4254 | 6747.4254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7943 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 16675.9279 | 0.2 | 0.3 | 26014.4476 |  |  |  |  | 0 | 9714.7404 | 9714.7404 | 9714.7404 | 9714.7404 | 9714.7404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7944 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 16677.8095 | 0.2 | 0.3 | 26017.3828 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7945 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 18738.5341 | 0.2 | 0.3 | 29232.1132 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7946 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 12304.9492 | 0.2 | 0.3 | 19195.7208 |  |  |  |  | 0 | 5201.3509 | 5201.3509 | 5201.3509 | 5201.3509 | 5201.3509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7947 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 461.1084 | 0.2 | 0.3 | 719.3291 |  |  |  |  | 0 | 5200.887 | 5200.887 | 5200.887 | 5200.887 | 5200.887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7948 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 28849.7751 | 0.2 | 0.3 | 45005.6491 |  |  |  |  | 0 | 5201.0347 | 5201.0347 | 5201.0347 | 5201.0347 | 5201.0347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7949 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16678.1216 | 0.2 | 0.3 | 26017.8697 |  |  |  |  | 0 | 5201.4705 | 5201.4705 | 5201.4705 | 5201.4705 | 5201.4705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7950 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 2643.6811 | 2643.6811 | 2643.6811 | 2643.6811 | 2643.6811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7951 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 4962.267 | 4962.267 | 4962.267 | 4962.267 | 4962.267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7952 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16679.1127 | 0.2 | 0.3 | 26019.4158 |  |  |  |  | 0 | 2600.8216 | 2600.8216 | 2600.8216 | 2600.8216 | 2600.8216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7953 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 17327.9993 | 0.2 | 0.3 | 27031.679 |  |  |  |  | 0 | 1030.9458 | 1030.9458 | 1030.9458 | 1030.9458 | 1030.9458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7954 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16687.4659 | 0.2 | 0.3 | 26032.4469 |  |  |  |  | 0 | 5202.5673 | 5202.5673 | 5202.5673 | 5202.5673 | 5202.5673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7955 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 10545.923 | 10545.923 | 10545.923 | 10545.923 | 10545.923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7956 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 6792.5579 | 0.2 | 0.3 | 10596.3904 |  |  |  |  | 0 | 10479.9962 | 10479.9962 | 10479.9962 | 10479.9962 | 10479.9962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7957 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 18212.8133 | 0.2 | 0.3 | 28411.9887 |  |  |  |  | 0 | 5207.9583 | 5207.9583 | 5207.9583 | 5207.9583 | 5207.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7958 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16667.0304 | 0.2 | 0.3 | 26000.5674 |  |  |  |  | 0 | 618.271 | 618.271 | 618.271 | 618.271 | 618.271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7959 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 16675.3501 | 0.2 | 0.3 | 26013.5461 |  |  |  |  | 0 | 5101.6848 | 5101.6848 | 5101.6848 | 5101.6848 | 5101.6848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7960 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 8335.4872 | 0.2 | 0.3 | 13003.36 |  |  |  |  | 0 | 9779.3626 | 9779.3626 | 9779.3626 | 9779.3626 | 9779.3626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7961 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 16676.4425 | 0.2 | 0.3 | 26015.2502 |  |  |  |  | 0 | 8060.2762 | 8060.2762 | 8060.2762 | 8060.2762 | 8060.2762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7962 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 16676.4425 | 0.2 | 0.3 | 26015.2502 |  |  |  |  | 0 | 1219.0394 | 1219.0394 | 1219.0394 | 1219.0394 | 1219.0394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7963 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 26977.0792 | 0.2 | 0.3 | 42084.2436 |  |  |  |  | 0 | 5174.9625 | 5174.9625 | 5174.9625 | 5174.9625 | 5174.9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7964 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 139.2017 | 0.2 | 0.3 | 217.1546 |  |  |  |  | 0 | 6101.4867 | 6101.4867 | 6101.4867 | 6101.4867 | 6101.4867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7965 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 10067.8995 | 0.2 | 0.3 | 15705.9233 |  |  |  |  | 0 | 4729.324 | 4729.324 | 4729.324 | 4729.324 | 4729.324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7966 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 27845.947 | 0.2 | 0.3 | 43439.6773 |  |  |  |  | 0 | 4950.8051 | 4950.8051 | 4950.8051 | 4950.8051 | 4950.8051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7967 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 16676.8323 | 0.2 | 0.3 | 26015.8583 |  |  |  |  | 0 | 2307.6424 | 2307.6424 | 2307.6424 | 2307.6424 | 2307.6424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7968 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 21912.9053 | 0.2 | 0.3 | 34184.1323 |  |  |  |  | 0 | 7214.9027 | 7214.9027 | 7214.9027 | 7214.9027 | 7214.9027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7969 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 12282.0363 | 0.2 | 0.3 | 19159.9766 |  |  |  |  | 0 | 6620.2633 | 6620.2633 | 6620.2633 | 6620.2633 | 6620.2633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7970 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 17676.6439 | 0.2 | 0.3 | 27575.5644 |  |  |  |  | 0 | 9781.0758 | 9781.0758 | 9781.0758 | 9781.0758 | 9781.0758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7971 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 9092.142 | 0.2 | 0.3 | 14183.7415 |  |  |  |  | 0 | 5202.1073 | 5202.1073 | 5202.1073 | 5202.1073 | 5202.1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7972 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 7584.5243 | 0.2 | 0.3 | 11831.858 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7973 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 17561.7714 | 0.2 | 0.3 | 27396.3634 |  |  |  |  | 0 | 5201.7447 | 5201.7447 | 5201.7447 | 5201.7447 | 5201.7447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7974 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16680.0571 | 0.2 | 0.3 | 26020.889 |  |  |  |  | 0 | 5201.8207 | 5201.8207 | 5201.8207 | 5201.8207 | 5201.8207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7975 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 9780.0857 | 9780.0857 | 9780.0857 | 9780.0857 | 9780.0857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7976 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 3405.6789 | 3405.6789 | 3405.6789 | 3405.6789 | 3405.6789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7977 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 13971.6445 | 0.2 | 0.3 | 21795.7654 |  |  |  |  | 0 | 4584.0465 | 4584.0465 | 4584.0465 | 4584.0465 | 4584.0465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7978 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 3990.0935 | 0.2 | 0.3 | 6224.5459 |  |  |  |  | 0 | 100.198 | 100.198 | 100.198 | 100.198 | 100.198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7979 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 19561.9661 | 0.2 | 0.3 | 30516.6671 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7980 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 23622.8805 | 0.2 | 0.3 | 36851.6936 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7981 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 5370.6892 | 0.2 | 0.3 | 8378.2752 |  |  |  |  | 0 | 6990.5889 | 6990.5889 | 6990.5889 | 6990.5889 | 6990.5889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7982 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 28733.062 | 0.2 | 0.3 | 44823.5767 |  |  |  |  | 0 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7983 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 25824.8797 | 0.2 | 0.3 | 40286.8123 |  |  |  |  | 0 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7984 | COOPER CITY | 70403 | Public | 2026 | 5 | Swales | 66.6667 | 28986.6548 | 0.2 | 0.3 | 45219.1815 |  |  |  |  | 0 | 6224.1784 | 6224.1784 | 6224.1784 | 6224.1784 | 6224.1784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7985 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 4821.5101 | 0.2 | 0.3 | 7521.5557 |  |  |  |  | 0 | 5156.2284 | 5156.2284 | 5156.2284 | 5156.2284 | 5156.2284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7986 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 10883.3357 | 0.2 | 0.3 | 16978.0036 |  |  |  |  | 0 | 7475.5879 | 7475.5879 | 7475.5879 | 7475.5879 | 7475.5879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7987 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 27649.7365 | 0.2 | 0.3 | 43133.589 |  |  |  |  | 0 | 9791.9812 | 9791.9812 | 9791.9812 | 9791.9812 | 9791.9812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7988 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 25145.3761 | 0.2 | 0.3 | 39226.7868 |  |  |  |  | 0 | 5206.8033 | 5206.8033 | 5206.8033 | 5206.8033 | 5206.8033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7989 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 19024.5714 | 0.2 | 0.3 | 29678.3314 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7990 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 16692.6187 | 0.2 | 0.3 | 26040.4851 |  |  |  |  | 0 | 842.7172 | 842.7172 | 842.7172 | 842.7172 | 842.7172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7991 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 6303.1949 | 0.2 | 0.3 | 9832.984 |  |  |  |  | 0 | 9781.1041 | 9781.1041 | 9781.1041 | 9781.1041 | 9781.1041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7992 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 10373.3201 | 0.2 | 0.3 | 16182.3794 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7993 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 17654.5757 | 0.2 | 0.3 | 27541.1381 |  |  |  |  | 0 | 9780.5358 | 9780.5358 | 9780.5358 | 9780.5358 | 9780.5358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7994 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 17101.6808 | 0.2 | 0.3 | 26678.622 |  |  |  |  | 0 | 5201.8088 | 5201.8088 | 5201.8088 | 5201.8088 | 5201.8088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7995 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 18347.5355 | 0.2 | 0.3 | 28622.1553 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7996 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 16117.5657 | 0.2 | 0.3 | 25143.4025 |  |  |  |  | 0 | 3867.5497 | 3867.5497 | 3867.5497 | 3867.5497 | 3867.5497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7997 | DAVIE | 70602 | Private | 2036 | 5 | Swales | 66.6667 | 14214.6075 | 0.2 | 0.3 | 22174.7876 |  |  |  |  | 0 | 5200.7129 | 5200.7129 | 5200.7129 | 5200.7129 | 5200.7129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7998 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 14.5541 | 0.2 | 0.3 | 22.7044 |  |  |  |  | 0 | 3647.5665 | 3647.5665 | 3647.5665 | 3647.5665 | 3647.5665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7999 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 16661.9008 | 0.2 | 0.3 | 25992.5652 |  |  |  |  | 0 | 2932.404 | 2932.404 | 2932.404 | 2932.404 | 2932.404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8000 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 19307.9897 | 0.2 | 0.3 | 30120.4639 |  |  |  |  | 0 | 5201.8792 | 5201.8792 | 5201.8792 | 5201.8792 | 5201.8792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8001 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16674.8509 | 0.2 | 0.3 | 26012.7675 |  |  |  |  | 0 | 5201.9336 | 5201.9336 | 5201.9336 | 5201.9336 | 5201.9336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8002 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 9779.1002 | 9779.1002 | 9779.1002 | 9779.1002 | 9779.1002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8003 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8004 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 9462.9994 | 9462.9994 | 9462.9994 | 9462.9994 | 9462.9994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8005 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16675.4943 | 0.2 | 0.3 | 26013.7712 |  |  |  |  | 0 | 5519.733 | 5519.733 | 5519.733 | 5519.733 | 5519.733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8006 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 25870.0383 | 0.2 | 0.3 | 40357.2597 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8007 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 16672.8883 | 0.2 | 0.3 | 26009.7057 |  |  |  |  | 0 | 9990.549 | 9990.549 | 9990.549 | 9990.549 | 9990.549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8008 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6623 |  |  |  |  | 0 | 6031.6944 | 6031.6944 | 6031.6944 | 6031.6944 | 6031.6944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8009 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 16659.4752 | 0.2 | 0.3 | 25988.7813 |  |  |  |  | 0 | 9789.2293 | 9789.2293 | 9789.2293 | 9789.2293 | 9789.2293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8010 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 24655.7897 | 0.2 | 0.3 | 38463.032 |  |  |  |  | 0 | 5209.533 | 5209.533 | 5209.533 | 5209.533 | 5209.533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8011 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16676.3543 | 0.2 | 0.3 | 26015.1128 |  |  |  |  | 0 | 1553.8223 | 1553.8223 | 1553.8223 | 1553.8223 | 1553.8223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8012 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 2799.1243 | 2799.1243 | 2799.1243 | 2799.1243 | 2799.1243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8013 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 5202.7263 | 5202.7263 | 5202.7263 | 5202.7263 | 5202.7263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8014 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16676.4595 | 0.2 | 0.3 | 26015.2769 |  |  |  |  | 0 | 3622.6147 | 3622.6147 | 3622.6147 | 3622.6147 | 3622.6147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8015 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16675.8055 | 0.2 | 0.3 | 26014.2566 |  |  |  |  | 0 | 4277.3362 | 4277.3362 | 4277.3362 | 4277.3362 | 4277.3362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8016 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 31353.4228 | 0.2 | 0.3 | 48911.3396 |  |  |  |  | 0 | 5204.4604 | 5204.4604 | 5204.4604 | 5204.4604 | 5204.4604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8017 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16671.7947 | 0.2 | 0.3 | 26007.9997 |  |  |  |  | 0 | 9780.1972 | 9780.1972 | 9780.1972 | 9780.1972 | 9780.1972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8018 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 22910.05 | 0.2 | 0.3 | 35739.678 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8019 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 16751.0087 | 0.2 | 0.3 | 26131.5736 |  |  |  |  | 0 | 7585.6089 | 7585.6089 | 7585.6089 | 7585.6089 | 7585.6089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8020 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 17616.0207 | 0.2 | 0.3 | 27480.9922 |  |  |  |  | 0 | 7397.3155 | 7397.3155 | 7397.3155 | 7397.3155 | 7397.3155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8021 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 27248.3668 | 0.2 | 0.3 | 42507.4522 |  |  |  |  | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8022 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 31844.6565 | 0.2 | 0.3 | 49677.6642 |  |  |  |  | 0 | 8050.8044 | 8050.8044 | 8050.8044 | 8050.8044 | 8050.8044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8023 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 29726.9253 | 0.2 | 0.3 | 46374.0035 |  |  |  |  | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8024 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 33359.4466 | 0.2 | 0.3 | 52040.7367 |  |  |  |  | 0 | 9782.1883 | 9782.1883 | 9782.1883 | 9782.1883 | 9782.1883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8025 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 33347.2665 | 0.2 | 0.3 | 52021.7357 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8026 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 10412.8148 | 0.2 | 0.3 | 16243.9911 |  |  |  |  | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8027 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 24929.1015 | 0.2 | 0.3 | 38889.3983 |  |  |  |  | 0 | 3981.9075 | 3981.9075 | 3981.9075 | 3981.9075 | 3981.9075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8028 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 30393.057 | 0.2 | 0.3 | 47413.1689 |  |  |  |  | 0 | 1423.4431 | 1423.4431 | 1423.4431 | 1423.4431 | 1423.4431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8029 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 20314.6361 | 0.2 | 0.3 | 31690.8323 |  |  |  |  | 0 | 5615.1859 | 5615.1859 | 5615.1859 | 5615.1859 | 5615.1859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8030 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 16676.8163 | 0.2 | 0.3 | 26015.8335 |  |  |  |  | 0 | 927.0564 | 927.0564 | 927.0564 | 927.0564 | 927.0564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8031 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 23018.1531 | 0.2 | 0.3 | 35908.3189 |  |  |  |  | 0 | 5200.5131 | 5200.5131 | 5200.5131 | 5200.5131 | 5200.5131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8032 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 24033.9435 | 0.2 | 0.3 | 37492.9519 |  |  |  |  | 0 | 2302.7314 | 2302.7314 | 2302.7314 | 2302.7314 | 2302.7314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8033 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 2898.6168 | 2898.6168 | 2898.6168 | 2898.6168 | 2898.6168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8034 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 9505.5452 | 9505.5452 | 9505.5452 | 9505.5452 | 9505.5452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8035 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 5496.9417 | 5496.9417 | 5496.9417 | 5496.9417 | 5496.9417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8036 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 11919.2227 | 11919.2227 | 11919.2227 | 11919.2227 | 11919.2227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8037 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16675.7767 | 0.2 | 0.3 | 26014.2116 |  |  |  |  | 0 | 10893.2689 | 10893.2689 | 10893.2689 | 10893.2689 | 10893.2689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8038 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 31349.7453 | 0.2 | 0.3 | 48905.6026 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8039 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16672.6149 | 0.2 | 0.3 | 26009.2792 |  |  |  |  | 0 | 5201.4148 | 5201.4148 | 5201.4148 | 5201.4148 | 5201.4148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8040 | COOPER CITY | 70404 | Public | 2026 | 5 | Swales | 66.6667 | 29110.7589 | 0.2 | 0.3 | 45412.7839 |  |  |  |  | 0 | 5201.7504 | 5201.7504 | 5201.7504 | 5201.7504 | 5201.7504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8041 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 16719.8576 | 0.2 | 0.3 | 26082.9779 |  |  |  |  | 0 | 4935.8775 | 4935.8775 | 4935.8775 | 4935.8775 | 4935.8775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8042 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 16677.0964 | 0.2 | 0.3 | 26016.2704 |  |  |  |  | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8043 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 16674.8455 | 0.2 | 0.3 | 26012.759 |  |  |  |  | 0 | 3494.3334 | 3494.3334 | 3494.3334 | 3494.3334 | 3494.3334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8044 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 22249.1021 | 0.2 | 0.3 | 34708.5992 |  |  |  |  | 0 | 5199.9829 | 5199.9829 | 5199.9829 | 5199.9829 | 5199.9829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8045 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 26363.7685 | 0.2 | 0.3 | 41127.4788 |  |  |  |  | 0 | 5199.9829 | 5199.9829 | 5199.9829 | 5199.9829 | 5199.9829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8046 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 16680.2421 | 0.2 | 0.3 | 26021.1776 |  |  |  |  | 0 | 6090.9132 | 6090.9132 | 6090.9132 | 6090.9132 | 6090.9132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8047 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 19401.3152 | 0.2 | 0.3 | 30266.0517 |  |  |  |  | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8048 | COOPER CITY | 70403 | Private | 2033 | 5 | Swales | 66.6667 | 10857.1797 | 0.2 | 0.3 | 16937.2003 |  |  |  |  | 0 | 5340.5807 | 5340.5807 | 5340.5807 | 5340.5807 | 5340.5807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8049 | COOPER CITY | 70403 | Private | 2033 | 5 | Swales | 66.6667 | 16669.4821 | 0.2 | 0.3 | 26004.392 |  |  |  |  | 0 | 5594.7194 | 5594.7194 | 5594.7194 | 5594.7194 | 5594.7194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8050 | COOPER CITY | 70403 | Private | 2033 | 5 | Swales | 66.6667 | 6267.4023 | 0.2 | 0.3 | 9777.1475 |  |  |  |  | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8051 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 23354.016 | 0.2 | 0.3 | 36432.265 |  |  |  |  | 0 | 5201.7454 | 5201.7454 | 5201.7454 | 5201.7454 | 5201.7454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8052 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16675.688 | 0.2 | 0.3 | 26014.0733 |  |  |  |  | 0 | 5883.3328 | 5883.3328 | 5883.3328 | 5883.3328 | 5883.3328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8053 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 818.2311 | 818.2311 | 818.2311 | 818.2311 | 818.2311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8054 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 5200.967 | 5200.967 | 5200.967 | 5200.967 | 5200.967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8055 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16676.4425 | 0.2 | 0.3 | 26015.2502 |  |  |  |  | 0 | 8379.0354 | 8379.0354 | 8379.0354 | 8379.0354 | 8379.0354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8056 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16676.3035 | 0.2 | 0.3 | 26015.0335 |  |  |  |  | 0 | 10609.5155 | 10609.5155 | 10609.5155 | 10609.5155 | 10609.5155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8057 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 30028.9707 | 0.2 | 0.3 | 46845.1942 |  |  |  |  | 0 | 14209.9446 | 14209.9446 | 14209.9446 | 14209.9446 | 14209.9446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8058 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 25782.8451 | 0.2 | 0.3 | 40221.2383 |  |  |  |  | 0 | 9769.2603 | 9769.2603 | 9769.2603 | 9769.2603 | 9769.2603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8059 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 4384.5366 | 4384.5366 | 4384.5366 | 4384.5366 | 4384.5366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8060 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 5591.6446 | 5591.6446 | 5591.6446 | 5591.6446 | 5591.6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8061 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 16693.8297 | 0.2 | 0.3 | 26042.3744 |  |  |  |  | 0 | 5201.4852 | 5201.4852 | 5201.4852 | 5201.4852 | 5201.4852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8062 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 9160.3469 | 0.2 | 0.3 | 14290.1411 |  |  |  |  | 0 | 5202.3388 | 5202.3388 | 5202.3388 | 5202.3388 | 5202.3388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8063 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 16676.4935 | 0.2 | 0.3 | 26015.3298 |  |  |  |  | 0 | 10283.3378 | 10283.3378 | 10283.3378 | 10283.3378 | 10283.3378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8064 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 16687.0909 | 0.2 | 0.3 | 26031.8618 |  |  |  |  | 0 | 5200.7315 | 5200.7315 | 5200.7315 | 5200.7315 | 5200.7315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8065 | COOPER CITY | 70403 | Private | 2033 | 5 | Swales | 66.6667 | 31961.812 | 0.2 | 0.3 | 49860.4267 |  |  |  |  | 0 | 5201.7975 | 5201.7975 | 5201.7975 | 5201.7975 | 5201.7975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8066 | COOPER CITY | 70403 | Private | 2033 | 5 | Swales | 66.6667 | 30448.4517 | 0.2 | 0.3 | 47499.5846 |  |  |  |  | 0 | 2799.9963 | 2799.9963 | 2799.9963 | 2799.9963 | 2799.9963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8067 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 11278.4085 | 0.2 | 0.3 | 17594.3173 |  |  |  |  | 0 | 2405.1929 | 2405.1929 | 2405.1929 | 2405.1929 | 2405.1929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8068 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16674.3599 | 0.2 | 0.3 | 26012.0014 |  |  |  |  | 0 | 9780.6153 | 9780.6153 | 9780.6153 | 9780.6153 | 9780.6153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8069 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16674.2553 | 0.2 | 0.3 | 26011.8382 |  |  |  |  | 0 | 5203.3946 | 5203.3946 | 5203.3946 | 5203.3946 | 5203.3946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8070 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 5200.4989 | 5200.4989 | 5200.4989 | 5200.4989 | 5200.4989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8071 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16674.2553 | 0.2 | 0.3 | 26011.8382 |  |  |  |  | 0 | 0.299 | 0.299 | 0.299 | 0.299 | 0.299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8072 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 16674.4249 | 0.2 | 0.3 | 26012.1029 |  |  |  |  | 0 | 3982.8071 | 3982.8071 | 3982.8071 | 3982.8071 | 3982.8071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8073 | COOPER CITY | 70403 | Public | 2033 | 5 | Swales | 66.6667 | 15416.0093 | 0.2 | 0.3 | 24048.9745 |  |  |  |  | 0 | 5202.0493 | 5202.0493 | 5202.0493 | 5202.0493 | 5202.0493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8074 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 16970.0578 | 0.2 | 0.3 | 26473.2902 |  |  |  |  | 0 | 850.7295 | 850.7295 | 850.7295 | 850.7295 | 850.7295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8075 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 23398.6906 | 0.2 | 0.3 | 36501.9573 |  |  |  |  | 0 | 3636.1371 | 3636.1371 | 3636.1371 | 3636.1371 | 3636.1371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8076 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 12522.1881 | 0.2 | 0.3 | 19534.6134 |  |  |  |  | 0 | 9465.0843 | 9465.0843 | 9465.0843 | 9465.0843 | 9465.0843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8077 | DAVIE | 70102 | Public | 2030 | 5 | Swales | 66.6667 | 24815.9648 | 0.2 | 0.3 | 38712.9051 |  |  |  |  | 0 | 5701.9048 | 5701.9048 | 5701.9048 | 5701.9048 | 5701.9048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8078 | BMSD | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 1.1063 | 0.2 | 0.3 | 1.7258 |  |  |  |  | 0 | 5204.6379 | 5204.6379 | 5204.6379 | 5204.6379 | 5204.6379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8079 | DAVIE | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16673.4919 | 0.2 | 0.3 | 26010.6474 |  |  |  |  | 0 | 5204.8893 | 5204.8893 | 5204.8893 | 5204.8893 | 5204.8893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8080 | DAVIE | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 23860.6456 | 0.2 | 0.3 | 37222.6071 |  |  |  |  | 0 | 5942.2384 | 5942.2384 | 5942.2384 | 5942.2384 | 5942.2384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8081 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9475 | 0.2 | 0.3 | 26020.7182 |  |  |  |  | 0 | 1575.3832 | 1575.3832 | 1575.3832 | 1575.3832 | 1575.3832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8082 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 5214.7407 | 5214.7407 | 5214.7407 | 5214.7407 | 5214.7407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8083 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 1635.051 | 1635.051 | 1635.051 | 1635.051 | 1635.051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8084 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 7080.0824 | 0.2 | 0.3 | 11044.9285 |  |  |  |  | 0 | 6211.5559 | 6211.5559 | 6211.5559 | 6211.5559 | 6211.5559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8085 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 16675.9927 | 0.2 | 0.3 | 26014.5487 |  |  |  |  | 0 | 5201.5763 | 5201.5763 | 5201.5763 | 5201.5763 | 5201.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8086 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 16821.9267 | 0.2 | 0.3 | 26242.2056 |  |  |  |  | 0 | 5201.6884 | 5201.6884 | 5201.6884 | 5201.6884 | 5201.6884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8087 | DAVIE | 70503 | Private | 2026 | 5 | Swales | 66.6667 | 29903.8355 | 0.2 | 0.3 | 46649.9834 |  |  |  |  | 0 | 6534.7558 | 6534.7558 | 6534.7558 | 6534.7558 | 6534.7558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8088 | DAVIE | 70503 | Private | 2026 | 5 | Swales | 66.6667 | 33360.8136 | 0.2 | 0.3 | 52042.8692 |  |  |  |  | 0 | 5202.8243 | 5202.8243 | 5202.8243 | 5202.8243 | 5202.8243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8089 | DAVIE | 70503 | Private | 2026 | 5 | Swales | 66.6667 | 37706.7387 | 0.2 | 0.3 | 58822.5124 |  |  |  |  | 0 | 5202.8796 | 5202.8796 | 5202.8796 | 5202.8796 | 5202.8796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8090 | DAVIE | 70504 | Private | 2026 | 5 | Swales | 66.6667 | 37134.256 | 0.2 | 0.3 | 57929.4394 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8091 | DAVIE | 70504 | Private | 2030 | 5 | Swales | 66.6667 | 14380.8448 | 0.2 | 0.3 | 22434.1179 |  |  |  |  | 0 | 5802.6403 | 5802.6403 | 5802.6403 | 5802.6403 | 5802.6403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8092 | HOLLYWOOD | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 22080.1564 | 0.2 | 0.3 | 34445.044 |  |  |  |  | 0 | 2299.2289 | 2299.2289 | 2299.2289 | 2299.2289 | 2299.2289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8093 | HOLLYWOOD | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16692.4153 | 0.2 | 0.3 | 26040.1679 |  |  |  |  | 0 | 5200.3949 | 5200.3949 | 5200.3949 | 5200.3949 | 5200.3949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8094 | HOLLYWOOD | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 22209.777 | 0.2 | 0.3 | 34647.2521 |  |  |  |  | 0 | 5200.5229 | 5200.5229 | 5200.5229 | 5200.5229 | 5200.5229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8095 | HOLLYWOOD | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 25875.6731 | 0.2 | 0.3 | 40366.05 |  |  |  |  | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8096 | HOLLYWOOD | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16681.6371 | 0.2 | 0.3 | 26023.3539 |  |  |  |  | 0 | 5270.2134 | 5270.2134 | 5270.2134 | 5270.2134 | 5270.2134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8097 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 20923.4372 | 0.2 | 0.3 | 32640.562 |  |  |  |  | 0 | 2600.0097 | 2600.0097 | 2600.0097 | 2600.0097 | 2600.0097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8098 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 31344.3817 | 0.2 | 0.3 | 48897.2355 |  |  |  |  | 0 | 2599.9685 | 2599.9685 | 2599.9685 | 2599.9685 | 2599.9685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8099 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 696.9372 | 696.9372 | 696.9372 | 696.9372 | 696.9372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8100 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 23226.2765 | 0.2 | 0.3 | 36232.9913 |  |  |  |  | 0 | 278.7011 | 278.7011 | 278.7011 | 278.7011 | 278.7011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8101 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16675.4293 | 0.2 | 0.3 | 26013.6697 |  |  |  |  | 0 | 366.8278 | 366.8278 | 366.8278 | 366.8278 | 366.8278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8102 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8103 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16675.6223 | 0.2 | 0.3 | 26013.9707 |  |  |  |  | 0 | 2403.294 | 2403.294 | 2403.294 | 2403.294 | 2403.294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8104 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 8337.1067 | 0.2 | 0.3 | 13005.8865 |  |  |  |  | 0 | 5199.9881 | 5199.9881 | 5199.9881 | 5199.9881 | 5199.9881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8105 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 2540.9831 | 0.2 | 0.3 | 3963.9337 |  |  |  |  | 0 | 1447.8635 | 1447.8635 | 1447.8635 | 1447.8635 | 1447.8635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8106 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 15919.7303 | 0.2 | 0.3 | 24834.7793 |  |  |  |  | 0 | 5501.6684 | 5501.6684 | 5501.6684 | 5501.6684 | 5501.6684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8107 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 10745.2516 | 0.2 | 0.3 | 16762.5925 |  |  |  |  | 0 | 2506.8919 | 2506.8919 | 2506.8919 | 2506.8919 | 2506.8919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8108 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 731.302 | 0.2 | 0.3 | 1140.8311 |  |  |  |  | 0 | 2801.4291 | 2801.4291 | 2801.4291 | 2801.4291 | 2801.4291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8109 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 16682.5739 | 0.2 | 0.3 | 26024.8152 |  |  |  |  | 0 | 5207.4857 | 5207.4857 | 5207.4857 | 5207.4857 | 5207.4857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8110 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 16683.2545 | 0.2 | 0.3 | 26025.877 |  |  |  |  | 0 | 5207.3151 | 5207.3151 | 5207.3151 | 5207.3151 | 5207.3151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8111 | DAVIE | 70503 | Private | 2026 | 5 | Swales | 66.6667 | 24869.6149 | 0.2 | 0.3 | 38796.5992 |  |  |  |  | 0 | 5207.3151 | 5207.3151 | 5207.3151 | 5207.3151 | 5207.3151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8112 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16677.2627 | 0.2 | 0.3 | 26016.5298 |  |  |  |  | 0 | 5207.4004 | 5207.4004 | 5207.4004 | 5207.4004 | 5207.4004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8113 | DAVIE | 70503 | Private | 2026 | 5 | Swales | 66.6667 | 16862.5857 | 0.2 | 0.3 | 26305.6336 |  |  |  |  | 0 | 3558.7275 | 3558.7275 | 3558.7275 | 3558.7275 | 3558.7275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8114 | DAVIE | 70504 | Private | 2026 | 5 | Swales | 66.6667 | 22615.0749 | 0.2 | 0.3 | 35279.5168 |  |  |  |  | 0 | 5200.5861 | 5200.5861 | 5200.5861 | 5200.5861 | 5200.5861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8115 | DAVIE | 70504 | Private | 2030 | 5 | Swales | 66.6667 | 1616.5076 | 0.2 | 0.3 | 2521.7519 |  |  |  |  | 0 | 4469.7143 | 4469.7143 | 4469.7143 | 4469.7143 | 4469.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8116 | HOLLYWOOD | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 1333.8556 | 0.2 | 0.3 | 2080.8147 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8117 | HOLLYWOOD | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 17936.1056 | 0.2 | 0.3 | 27980.3247 |  |  |  |  | 0 | 7015.0241 | 7015.0241 | 7015.0241 | 7015.0241 | 7015.0241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8118 | HOLLYWOOD | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16675.7227 | 0.2 | 0.3 | 26014.1274 |  |  |  |  | 0 | 5203.4802 | 5203.4802 | 5203.4802 | 5203.4802 | 5203.4802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8119 | HOLLYWOOD | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 31409.7269 | 0.2 | 0.3 | 48999.174 |  |  |  |  | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8120 | HOLLYWOOD | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 22079.4101 | 0.2 | 0.3 | 34443.8797 |  |  |  |  | 0 | 3623.6901 | 3623.6901 | 3623.6901 | 3623.6901 | 3623.6901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8121 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 22312.6523 | 0.2 | 0.3 | 34807.7376 |  |  |  |  | 0 | 7551.0558 | 7551.0558 | 7551.0558 | 7551.0558 | 7551.0558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8122 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 25682.5011 | 0.2 | 0.3 | 40064.7017 |  |  |  |  | 0 | 6615.3234 | 6615.3234 | 6615.3234 | 6615.3234 | 6615.3234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8123 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16689.019 | 0.2 | 0.3 | 26034.8696 |  |  |  |  | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8124 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 22704.2543 | 0.2 | 0.3 | 35418.6368 |  |  |  |  | 0 | 5203.4889 | 5203.4889 | 5203.4889 | 5203.4889 | 5203.4889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8125 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3758 | 0.2 | 0.3 | 26018.2662 |  |  |  |  | 0 | 6736.6901 | 6736.6901 | 6736.6901 | 6736.6901 | 6736.6901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8126 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6623 |  |  |  |  | 0 | 5202.7068 | 5202.7068 | 5202.7068 | 5202.7068 | 5202.7068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8127 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6623 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8128 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16674.6855 | 0.2 | 0.3 | 26012.5093 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8129 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 21512.5546 | 0.2 | 0.3 | 33559.5852 |  |  |  |  | 0 | 5202.8726 | 5202.8726 | 5202.8726 | 5202.8726 | 5202.8726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8130 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 27348.1933 | 0.2 | 0.3 | 42663.1816 |  |  |  |  | 0 | 2404.2036 | 2404.2036 | 2404.2036 | 2404.2036 | 2404.2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8131 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 10268.682 | 0.2 | 0.3 | 16019.1439 |  |  |  |  | 0 | 2854.1835 | 2854.1835 | 2854.1835 | 2854.1835 | 2854.1835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8132 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 11382.4456 | 0.2 | 0.3 | 17756.6151 |  |  |  |  | 0 | 1836.6729 | 1836.6729 | 1836.6729 | 1836.6729 | 1836.6729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8133 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 14547.2039 | 0.2 | 0.3 | 22693.6381 |  |  |  |  | 0 | 2798.5499 | 2798.5499 | 2798.5499 | 2798.5499 | 2798.5499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8134 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 14950.7311 | 0.2 | 0.3 | 23323.1405 |  |  |  |  | 0 | 5202.1449 | 5202.1449 | 5202.1449 | 5202.1449 | 5202.1449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8135 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 9915.4188 | 0.2 | 0.3 | 15468.0533 |  |  |  |  | 0 | 5203.6971 | 5203.6971 | 5203.6971 | 5203.6971 | 5203.6971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8136 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 18466.6419 | 0.2 | 0.3 | 28807.9613 |  |  |  |  | 0 | 5203.7875 | 5203.7875 | 5203.7875 | 5203.7875 | 5203.7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8137 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 33343.9451 | 0.2 | 0.3 | 52016.5544 |  |  |  |  | 0 | 4326.6767 | 4326.6767 | 4326.6767 | 4326.6767 | 4326.6767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8138 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 34400.6015 | 0.2 | 0.3 | 53664.9384 |  |  |  |  | 0 | 2800.3581 | 2800.3581 | 2800.3581 | 2800.3581 | 2800.3581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8139 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 31364.679 | 0.2 | 0.3 | 48928.8992 |  |  |  |  | 0 | 2405.2647 | 2405.2647 | 2405.2647 | 2405.2647 | 2405.2647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8140 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16687.3785 | 0.2 | 0.3 | 26032.3105 |  |  |  |  | 0 | 1219.0388 | 1219.0388 | 1219.0388 | 1219.0388 | 1219.0388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8141 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16687.652 | 0.2 | 0.3 | 26032.7371 |  |  |  |  | 0 | 8052.2803 | 8052.2803 | 8052.2803 | 8052.2803 | 8052.2803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8142 | DAVIE | 70504 | Private | 2026 | 5 | Swales | 66.6667 | 20674.9968 | 0.2 | 0.3 | 32252.995 |  |  |  |  | 0 | 5202.8546 | 5202.8546 | 5202.8546 | 5202.8546 | 5202.8546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8143 | HOLLYWOOD | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 2220.7959 | 0.2 | 0.3 | 3464.4417 |  |  |  |  | 0 | 5202.5815 | 5202.5815 | 5202.5815 | 5202.5815 | 5202.5815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8144 | HOLLYWOOD | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 28996.7574 | 0.2 | 0.3 | 45234.9415 |  |  |  |  | 0 | 5202.6004 | 5202.6004 | 5202.6004 | 5202.6004 | 5202.6004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8145 | HOLLYWOOD | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 5731.7556 | 5731.7556 | 5731.7556 | 5731.7556 | 5731.7556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8146 | HOLLYWOOD | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 21784.0086 | 0.2 | 0.3 | 33983.0534 |  |  |  |  | 0 | 7466.4442 | 7466.4442 | 7466.4442 | 7466.4442 | 7466.4442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8147 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 20426.7669 | 0.2 | 0.3 | 31865.7564 |  |  |  |  | 0 | 10403.7691 | 10403.7691 | 10403.7691 | 10403.7691 | 10403.7691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8148 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 25284.6409 | 0.2 | 0.3 | 39444.0399 |  |  |  |  | 0 | 5201.9256 | 5201.9256 | 5201.9256 | 5201.9256 | 5201.9256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8149 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 10401.7377 | 10401.7377 | 10401.7377 | 10401.7377 | 10401.7377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8150 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 22419.5409 | 0.2 | 0.3 | 34974.4838 |  |  |  |  | 0 | 5458.7799 | 5458.7799 | 5458.7799 | 5458.7799 | 5458.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8151 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16679.5279 | 0.2 | 0.3 | 26020.0636 |  |  |  |  | 0 | 7143.071 | 7143.071 | 7143.071 | 7143.071 | 7143.071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8152 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 8285.662 | 8285.662 | 8285.662 | 8285.662 | 8285.662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8153 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 5202.4526 | 5202.4526 | 5202.4526 | 5202.4526 | 5202.4526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8154 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16674.7583 | 0.2 | 0.3 | 26012.623 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8155 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 21685.8296 | 0.2 | 0.3 | 33829.8942 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8156 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 23989.3183 | 0.2 | 0.3 | 37423.3366 |  |  |  |  | 0 | 6938.5736 | 6938.5736 | 6938.5736 | 6938.5736 | 6938.5736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8157 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 26637.7412 | 0.2 | 0.3 | 41554.8763 |  |  |  |  | 0 | 9378.0712 | 9378.0712 | 9378.0712 | 9378.0712 | 9378.0712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8158 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 2613.8555 | 0.2 | 0.3 | 4077.6145 |  |  |  |  | 0 | 5206.4736 | 5206.4736 | 5206.4736 | 5206.4736 | 5206.4736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8159 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 17252.2487 | 0.2 | 0.3 | 26913.5079 |  |  |  |  | 0 | 2945.5426 | 2945.5426 | 2945.5426 | 2945.5426 | 2945.5426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8160 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 11034.0267 | 0.2 | 0.3 | 17213.0817 |  |  |  |  | 0 | 9504.6829 | 9504.6829 | 9504.6829 | 9504.6829 | 9504.6829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8161 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 8725.4631 | 0.2 | 0.3 | 13611.7225 |  |  |  |  | 0 | 10403.048 | 10403.048 | 10403.048 | 10403.048 | 10403.048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8162 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 17457.3187 | 0.2 | 0.3 | 27233.4172 |  |  |  |  | 0 | 5201.7714 | 5201.7714 | 5201.7714 | 5201.7714 | 5201.7714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8163 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 9.7699 | 0.2 | 0.3 | 15.241 |  |  |  |  | 0 | 10402.0577 | 10402.0577 | 10402.0577 | 10402.0577 | 10402.0577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8164 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 16679.4468 | 0.2 | 0.3 | 26019.937 |  |  |  |  | 0 | 7179.6724 | 7179.6724 | 7179.6724 | 7179.6724 | 7179.6724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8165 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 24080.6119 | 0.2 | 0.3 | 37565.7545 |  |  |  |  | 0 | 7886.0045 | 7886.0045 | 7886.0045 | 7886.0045 | 7886.0045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8166 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16679.7626 | 0.2 | 0.3 | 26020.4297 |  |  |  |  | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8167 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4149 | 0.2 | 0.3 | 26019.8873 |  |  |  |  | 0 | 5115.0538 | 5115.0538 | 5115.0538 | 5115.0538 | 5115.0538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8168 | DAVIE | 70504 | Private | 2026 | 5 | Swales | 66.6667 | 45974.6192 | 0.2 | 0.3 | 71720.406 |  |  |  |  | 0 | 5202.2308 | 5202.2308 | 5202.2308 | 5202.2308 | 5202.2308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8169 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16674.6654 | 0.2 | 0.3 | 26012.478 |  |  |  |  | 0 | 5202.7369 | 5202.7369 | 5202.7369 | 5202.7369 | 5202.7369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8170 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 31317.2791 | 0.2 | 0.3 | 48854.9553 |  |  |  |  | 0 | 5724.1972 | 5724.1972 | 5724.1972 | 5724.1972 | 5724.1972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8171 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16683.0041 | 0.2 | 0.3 | 26025.4864 |  |  |  |  | 0 | 5200.0734 | 5200.0734 | 5200.0734 | 5200.0734 | 5200.0734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8172 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 31321.9697 | 0.2 | 0.3 | 48862.2727 |  |  |  |  | 0 | 3886.969 | 3886.969 | 3886.969 | 3886.969 | 3886.969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8173 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16658.3795 | 0.2 | 0.3 | 25987.0721 |  |  |  |  | 0 | 4623.8054 | 4623.8054 | 4623.8054 | 4623.8054 | 4623.8054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8174 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 10067.7943 | 10067.7943 | 10067.7943 | 10067.7943 | 10067.7943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8175 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 5675.3363 | 5675.3363 | 5675.3363 | 5675.3363 | 5675.3363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8176 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16675.0383 | 0.2 | 0.3 | 26013.0598 |  |  |  |  | 0 | 14328.5709 | 14328.5709 | 14328.5709 | 14328.5709 | 14328.5709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8177 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 8336.5945 | 0.2 | 0.3 | 13005.0874 |  |  |  |  | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8178 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 2398.3544 | 0.2 | 0.3 | 3741.4329 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8179 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 28522.5651 | 0.2 | 0.3 | 44495.2015 |  |  |  |  | 0 | 6461.0478 | 6461.0478 | 6461.0478 | 6461.0478 | 6461.0478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8180 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 31362.7339 | 0.2 | 0.3 | 48925.8649 |  |  |  |  | 0 | 8759.0148 | 8759.0148 | 8759.0148 | 8759.0148 | 8759.0148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8181 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 26022.5823 | 0.2 | 0.3 | 40595.2283 |  |  |  |  | 0 | 9538.1404 | 9538.1404 | 9538.1404 | 9538.1404 | 9538.1404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8182 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 1472.7697 | 0.2 | 0.3 | 2297.5208 |  |  |  |  | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8183 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 23445.2279 | 0.2 | 0.3 | 36574.5555 |  |  |  |  | 0 | 9405.8451 | 9405.8451 | 9405.8451 | 9405.8451 | 9405.8451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8184 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 32757.6463 | 0.2 | 0.3 | 51101.9282 |  |  |  |  | 0 | 5858.9872 | 5858.9872 | 5858.9872 | 5858.9872 | 5858.9872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8185 | DAVIE | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 13481.3202 | 0.2 | 0.3 | 21030.8595 |  |  |  |  | 0 | 9410.0876 | 9410.0876 | 9410.0876 | 9410.0876 | 9410.0876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8186 | DAVIE | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 16683.6081 | 0.2 | 0.3 | 26026.4286 |  |  |  |  | 0 | 6196.5662 | 6196.5662 | 6196.5662 | 6196.5662 | 6196.5662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8187 | DAVIE | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 20926.1245 | 0.2 | 0.3 | 32644.7542 |  |  |  |  | 0 | 3763.4703 | 3763.4703 | 3763.4703 | 3763.4703 | 3763.4703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8188 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 20192.8164 | 0.2 | 0.3 | 31500.7936 |  |  |  |  | 0 | 5174.5413 | 5174.5413 | 5174.5413 | 5174.5413 | 5174.5413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8189 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 15347.8297 | 0.2 | 0.3 | 23942.6144 |  |  |  |  | 0 | 10810.5152 | 10810.5152 | 10810.5152 | 10810.5152 | 10810.5152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8190 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16680.0426 | 0.2 | 0.3 | 26020.8665 |  |  |  |  | 0 | 7459.3596 | 7459.3596 | 7459.3596 | 7459.3596 | 7459.3596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8191 | DAVIE | 70504 | Private | 2026 | 5 | Swales | 66.6667 | 22533.2363 | 0.2 | 0.3 | 35151.8487 |  |  |  |  | 0 | 4248.5603 | 4248.5603 | 4248.5603 | 4248.5603 | 4248.5603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8192 | DAVIE | 70504 | Private | 2030 | 5 | Swales | 66.6667 | 21167.256 | 0.2 | 0.3 | 33020.9194 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8193 | DAVIE | 70504 | Private | 2030 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 9489.5284 | 9489.5284 | 9489.5284 | 9489.5284 | 9489.5284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8194 | DAVIE | 70504 | Private | 2030 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 9552.8013 | 9552.8013 | 9552.8013 | 9552.8013 | 9552.8013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8195 | DAVIE | 70504 | Private | 2030 | 5 | Swales | 66.6667 | 16683.0112 | 0.2 | 0.3 | 26025.4975 |  |  |  |  | 0 | 5200.369 | 5200.369 | 5200.369 | 5200.369 | 5200.369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8196 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16094.9365 | 0.2 | 0.3 | 25108.1009 |  |  |  |  | 0 | 5618.5364 | 5618.5364 | 5618.5364 | 5618.5364 | 5618.5364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8197 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 31353.2155 | 0.2 | 0.3 | 48911.0162 |  |  |  |  | 0 | 9256.1298 | 9256.1298 | 9256.1298 | 9256.1298 | 9256.1298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8198 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16684.3711 | 0.2 | 0.3 | 26027.619 |  |  |  |  | 0 | 5905.2506 | 5905.2506 | 5905.2506 | 5905.2506 | 5905.2506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8199 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 21637.9931 | 0.2 | 0.3 | 33755.2693 |  |  |  |  | 0 | 11670.1578 | 11670.1578 | 11670.1578 | 11670.1578 | 11670.1578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8200 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16678.5286 | 0.2 | 0.3 | 26018.5046 |  |  |  |  | 0 | 6877.443 | 6877.443 | 6877.443 | 6877.443 | 6877.443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8201 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16678.9031 | 0.2 | 0.3 | 26019.0889 |  |  |  |  | 0 | 8007.7126 | 8007.7126 | 8007.7126 | 8007.7126 | 8007.7126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8202 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6624 |  |  |  |  | 0 | 5208.9359 | 5208.9359 | 5208.9359 | 5208.9359 | 5208.9359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8203 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16678.5761 | 0.2 | 0.3 | 26018.5788 |  |  |  |  | 0 | 388.3301 | 388.3301 | 388.3301 | 388.3301 | 388.3301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8204 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8205 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 22684.8748 | 0.2 | 0.3 | 35388.4047 |  |  |  |  | 0 | 9774.994 | 9774.994 | 9774.994 | 9774.994 | 9774.994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8206 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 27109.5682 | 0.2 | 0.3 | 42290.9264 |  |  |  |  | 0 | 9167.961 | 9167.961 | 9167.961 | 9167.961 | 9167.961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8207 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 30744.8133 | 0.2 | 0.3 | 47961.9088 |  |  |  |  | 0 | 6090.7953 | 6090.7953 | 6090.7953 | 6090.7953 | 6090.7953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8208 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 28559.7011 | 0.2 | 0.3 | 44553.1337 |  |  |  |  | 0 | 4610.7059 | 4610.7059 | 4610.7059 | 4610.7059 | 4610.7059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8209 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 22803.0999 | 0.2 | 0.3 | 35572.8358 |  |  |  |  | 0 | 5489.0889 | 5489.0889 | 5489.0889 | 5489.0889 | 5489.0889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8210 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 20081.8491 | 0.2 | 0.3 | 31327.6846 |  |  |  |  | 0 | 4354.4628 | 4354.4628 | 4354.4628 | 4354.4628 | 4354.4628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8211 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 367.5345 | 0.2 | 0.3 | 573.3538 |  |  |  |  | 0 | 5585.5 | 5585.5 | 5585.5 | 5585.5 | 5585.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8212 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 3651.8423 | 0.2 | 0.3 | 5696.8739 |  |  |  |  | 0 | 5071.6905 | 5071.6905 | 5071.6905 | 5071.6905 | 5071.6905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8213 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 10028.6431 | 0.2 | 0.3 | 15644.6833 |  |  |  |  | 0 | 6549.701 | 6549.701 | 6549.701 | 6549.701 | 6549.701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8214 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 16082.2059 | 0.2 | 0.3 | 25088.2413 |  |  |  |  | 0 | 5201.9349 | 5201.9349 | 5201.9349 | 5201.9349 | 5201.9349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8215 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 22053.3876 | 0.2 | 0.3 | 34403.2847 |  |  |  |  | 0 | 7961.7906 | 7961.7906 | 7961.7906 | 7961.7906 | 7961.7906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8216 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 9651.8503 | 0.2 | 0.3 | 15056.8865 |  |  |  |  | 0 | 5204.214 | 5204.214 | 5204.214 | 5204.214 | 5204.214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8217 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 12211.1755 | 0.2 | 0.3 | 19049.4338 |  |  |  |  | 0 | 6110.7188 | 6110.7188 | 6110.7188 | 6110.7188 | 6110.7188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8218 | DAVIE | 70503 | Private | 2026 | 5 | Swales | 66.6667 | 18426.0393 | 0.2 | 0.3 | 28744.6214 |  |  |  |  | 0 | 6563.5924 | 6563.5924 | 6563.5924 | 6563.5924 | 6563.5924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8219 | DAVIE | 70504 | Private | 2030 | 5 | Swales | 66.6667 | 30912.6859 | 0.2 | 0.3 | 48223.7901 |  |  |  |  | 0 | 3448.9359 | 3448.9359 | 3448.9359 | 3448.9359 | 3448.9359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8220 | DAVIE | 70504 | Public | 2030 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 7063.7144 | 7063.7144 | 7063.7144 | 7063.7144 | 7063.7144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8221 | DAVIE | 70504 | Public | 2030 | 5 | Swales | 66.6667 | 16679.4341 | 0.2 | 0.3 | 26019.9172 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8222 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16675.6223 | 0.2 | 0.3 | 26013.9707 |  |  |  |  | 0 | 535.9539 | 535.9539 | 535.9539 | 535.9539 | 535.9539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8223 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 30388.3252 | 0.2 | 0.3 | 47405.7873 |  |  |  |  | 0 | 9782.9352 | 9782.9352 | 9782.9352 | 9782.9352 | 9782.9352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8224 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 9220.6193 | 0.2 | 0.3 | 14384.1661 |  |  |  |  | 0 | 7527.7732 | 7527.7732 | 7527.7732 | 7527.7732 | 7527.7732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8225 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 30415.1849 | 0.2 | 0.3 | 47447.6885 |  |  |  |  | 0 | 7185.0822 | 7185.0822 | 7185.0822 | 7185.0822 | 7185.0822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8226 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16681.3637 | 0.2 | 0.3 | 26022.9274 |  |  |  |  | 0 | 9440.9177 | 9440.9177 | 9440.9177 | 9440.9177 | 9440.9177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8227 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 21054.8341 | 0.2 | 0.3 | 32845.5412 |  |  |  |  | 0 | 6722.8931 | 6722.8931 | 6722.8931 | 6722.8931 | 6722.8931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8228 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16678.1221 | 0.2 | 0.3 | 26017.8705 |  |  |  |  | 0 | 5203.0622 | 5203.0622 | 5203.0622 | 5203.0622 | 5203.0622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8229 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2359 |  |  |  |  | 0 | 2305.3347 | 2305.3347 | 2305.3347 | 2305.3347 | 2305.3347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8230 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 7671.5876 | 7671.5876 | 7671.5876 | 7671.5876 | 7671.5876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8231 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16678.5633 | 0.2 | 0.3 | 26018.5588 |  |  |  |  | 0 | 5204.1986 | 5204.1986 | 5204.1986 | 5204.1986 | 5204.1986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8232 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16714.4454 | 0.2 | 0.3 | 26074.5348 |  |  |  |  | 0 | 8266.5295 | 8266.5295 | 8266.5295 | 8266.5295 | 8266.5295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8233 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 25731.0293 | 0.2 | 0.3 | 40140.4057 |  |  |  |  | 0 | 7808.6961 | 7808.6961 | 7808.6961 | 7808.6961 | 7808.6961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8234 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 18008.5446 | 0.2 | 0.3 | 28093.3296 |  |  |  |  | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8235 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 10865.1096 | 0.2 | 0.3 | 16949.571 |  |  |  |  | 0 | 5200.3931 | 5200.3931 | 5200.3931 | 5200.3931 | 5200.3931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8236 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 84.9483 | 0.2 | 0.3 | 132.5193 |  |  |  |  | 0 | 7150.3969 | 7150.3969 | 7150.3969 | 7150.3969 | 7150.3969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8237 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 14117.4362 | 0.2 | 0.3 | 22023.2005 |  |  |  |  | 0 | 7983.9832 | 7983.9832 | 7983.9832 | 7983.9832 | 7983.9832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8238 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 18075.5189 | 0.2 | 0.3 | 28197.8095 |  |  |  |  | 0 | 6667.7434 | 6667.7434 | 6667.7434 | 6667.7434 | 6667.7434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8239 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 2776.7093 | 0.2 | 0.3 | 4331.6666 |  |  |  |  | 0 | 3789.2113 | 3789.2113 | 3789.2113 | 3789.2113 | 3789.2113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8240 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 664.8673 | 0.2 | 0.3 | 1037.1929 |  |  |  |  | 0 | 5202.6363 | 5202.6363 | 5202.6363 | 5202.6363 | 5202.6363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8241 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 24084.0055 | 0.2 | 0.3 | 37571.0486 |  |  |  |  | 0 | 3567.461 | 3567.461 | 3567.461 | 3567.461 | 3567.461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8242 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 4189.2325 | 0.2 | 0.3 | 6535.2028 |  |  |  |  | 0 | 9421.7292 | 9421.7292 | 9421.7292 | 9421.7292 | 9421.7292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8243 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 13078.7773 | 0.2 | 0.3 | 20402.8925 |  |  |  |  | 0 | 8293.614 | 8293.614 | 8293.614 | 8293.614 | 8293.614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8244 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 16728.8667 | 0.2 | 0.3 | 26097.0321 |  |  |  |  | 0 | 10970.7463 | 10970.7463 | 10970.7463 | 10970.7463 | 10970.7463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8245 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 21193.2895 | 0.2 | 0.3 | 33061.5316 |  |  |  |  | 0 | 13641.086 | 13641.086 | 13641.086 | 13641.086 | 13641.086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8246 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 9458.4851 | 0.2 | 0.3 | 14755.2368 |  |  |  |  | 0 | 9513.0521 | 9513.0521 | 9513.0521 | 9513.0521 | 9513.0521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8247 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 12650.2122 | 0.2 | 0.3 | 19734.331 |  |  |  |  | 0 | 9382.536 | 9382.536 | 9382.536 | 9382.536 | 9382.536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8248 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 17636.1157 | 0.2 | 0.3 | 27512.3404 |  |  |  |  | 0 | 1219.4865 | 1219.4865 | 1219.4865 | 1219.4865 | 1219.4865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8249 | DAVIE | 70504 | Public | 2030 | 5 | Swales | 66.6667 | 16669.948 | 0.2 | 0.3 | 26005.1189 |  |  |  |  | 0 | 1220.2634 | 1220.2634 | 1220.2634 | 1220.2634 | 1220.2634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8250 | HOLLYWOOD | 90601 | Public | 2030 | 5 | Swales | 66.6667 | 18040.2933 | 0.2 | 0.3 | 28142.8575 |  |  |  |  | 0 | 1219.3876 | 1219.3876 | 1219.3876 | 1219.3876 | 1219.3876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8251 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 1229.1243 | 1229.1243 | 1229.1243 | 1229.1243 | 1229.1243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8252 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 20389.3049 | 0.2 | 0.3 | 31807.3157 |  |  |  |  | 0 | 1221.5159 | 1221.5159 | 1221.5159 | 1221.5159 | 1221.5159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8253 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 8110.7897 | 0.2 | 0.3 | 12652.832 |  |  |  |  | 0 | 5947.5597 | 5947.5597 | 5947.5597 | 5947.5597 | 5947.5597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8254 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 23846.3582 | 0.2 | 0.3 | 37200.3188 |  |  |  |  | 0 | 6103.5057 | 6103.5057 | 6103.5057 | 6103.5057 | 6103.5057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8255 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 10069.6811 | 0.2 | 0.3 | 15708.7026 |  |  |  |  | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8256 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16670.0518 | 0.2 | 0.3 | 26005.2808 |  |  |  |  | 0 | 4695.6555 | 4695.6555 | 4695.6555 | 4695.6555 | 4695.6555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8257 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16728.9357 | 0.2 | 0.3 | 26097.1397 |  |  |  |  | 0 | 8373.3614 | 8373.3614 | 8373.3614 | 8373.3614 | 8373.3614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8258 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 27724.7 | 0.2 | 0.3 | 43250.532 |  |  |  |  | 0 | 5628.2474 | 5628.2474 | 5628.2474 | 5628.2474 | 5628.2474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8259 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 18988.2943 | 0.2 | 0.3 | 29621.7391 |  |  |  |  | 0 | 5249.059 | 5249.059 | 5249.059 | 5249.059 | 5249.059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8260 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 8474.1173 | 0.2 | 0.3 | 13219.623 |  |  |  |  | 0 | 3704.9689 | 3704.9689 | 3704.9689 | 3704.9689 | 3704.9689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8261 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 15384.9437 | 0.2 | 0.3 | 24000.5121 |  |  |  |  | 0 | 5200.7059 | 5200.7059 | 5200.7059 | 5200.7059 | 5200.7059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8262 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 16678.519 | 0.2 | 0.3 | 26018.4896 |  |  |  |  | 0 | 8070.5223 | 8070.5223 | 8070.5223 | 8070.5223 | 8070.5223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8263 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 26157.0169 | 0.2 | 0.3 | 40804.9464 |  |  |  |  | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8264 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 16678.0487 | 0.2 | 0.3 | 26017.7559 |  |  |  |  | 0 | 8518.9265 | 8518.9265 | 8518.9265 | 8518.9265 | 8518.9265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8265 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 17198.5996 | 0.2 | 0.3 | 26829.8154 |  |  |  |  | 0 | 10404.8115 | 10404.8115 | 10404.8115 | 10404.8115 | 10404.8115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8266 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 24006.9291 | 0.2 | 0.3 | 37450.8093 |  |  |  |  | 0 | 4829.972 | 4829.972 | 4829.972 | 4829.972 | 4829.972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8267 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 6600.8621 | 0.2 | 0.3 | 10297.3448 |  |  |  |  | 0 | 8665.4732 | 8665.4732 | 8665.4732 | 8665.4732 | 8665.4732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8268 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 17352.2928 | 0.2 | 0.3 | 27069.5768 |  |  |  |  | 0 | 9782.3828 | 9782.3828 | 9782.3828 | 9782.3828 | 9782.3828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8269 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 31214.0608 | 0.2 | 0.3 | 48693.9348 |  |  |  |  | 0 | 5204.1701 | 5204.1701 | 5204.1701 | 5204.1701 | 5204.1701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8270 | DAVIE | 70503 | Private | 2026 | 5 | Swales | 66.6667 | 32508.0758 | 0.2 | 0.3 | 50712.5982 |  |  |  |  | 0 | 5307.8549 | 5307.8549 | 5307.8549 | 5307.8549 | 5307.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8271 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 31487.3535 | 0.2 | 0.3 | 49120.2715 |  |  |  |  | 0 | 13032.9797 | 13032.9797 | 13032.9797 | 13032.9797 | 13032.9797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8272 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 15577.4399 | 0.2 | 0.3 | 24300.8063 |  |  |  |  | 0 | 4288.7742 | 4288.7742 | 4288.7742 | 4288.7742 | 4288.7742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8273 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 8495.6772 | 0.2 | 0.3 | 13253.2564 |  |  |  |  | 0 | 5962.6932 | 5962.6932 | 5962.6932 | 5962.6932 | 5962.6932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8274 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 18041.8971 | 0.2 | 0.3 | 28145.3594 |  |  |  |  | 0 | 6551.154 | 6551.154 | 6551.154 | 6551.154 | 6551.154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8275 | DAVIE | 70504 | Public | 2030 | 5 | Swales | 66.6667 | 30492.752 | 0.2 | 0.3 | 47568.6931 |  |  |  |  | 0 | 6142.096 | 6142.096 | 6142.096 | 6142.096 | 6142.096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8276 | HOLLYWOOD | 90601 | Public | 2030 | 5 | Swales | 66.6667 | 30084.4492 | 0.2 | 0.3 | 46931.7408 |  |  |  |  | 0 | 6831.1481 | 6831.1481 | 6831.1481 | 6831.1481 | 6831.1481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8277 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16605.153 | 0.2 | 0.3 | 25904.0387 |  |  |  |  | 0 | 5203.5862 | 5203.5862 | 5203.5862 | 5203.5862 | 5203.5862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8278 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 25215.6507 | 0.2 | 0.3 | 39336.415 |  |  |  |  | 0 | 6198.8182 | 6198.8182 | 6198.8182 | 6198.8182 | 6198.8182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8279 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 13641.0911 | 0.2 | 0.3 | 21280.1022 |  |  |  |  | 0 | 1564.7232 | 1564.7232 | 1564.7232 | 1564.7232 | 1564.7232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8280 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16675.6499 | 0.2 | 0.3 | 26014.0139 |  |  |  |  | 0 | 5927.7218 | 5927.7218 | 5927.7218 | 5927.7218 | 5927.7218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8281 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16721.5539 | 0.2 | 0.3 | 26085.624 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8282 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 29583.4953 | 0.2 | 0.3 | 46150.2527 |  |  |  |  | 0 | 8204.4971 | 8204.4971 | 8204.4971 | 8204.4971 | 8204.4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8283 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 18647.3234 | 0.2 | 0.3 | 29089.8245 |  |  |  |  | 0 | 5201.7878 | 5201.7878 | 5201.7878 | 5201.7878 | 5201.7878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8284 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 8204.0887 | 0.2 | 0.3 | 12798.3783 |  |  |  |  | 0 | 9553.565 | 9553.565 | 9553.565 | 9553.565 | 9553.565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8285 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 1293.4953 | 0.2 | 0.3 | 2017.8527 |  |  |  |  | 0 | 11068.1575 | 11068.1575 | 11068.1575 | 11068.1575 | 11068.1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8286 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 16682.2417 | 0.2 | 0.3 | 26024.297 |  |  |  |  | 0 | 7070.5333 | 7070.5333 | 7070.5333 | 7070.5333 | 7070.5333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8287 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 16617.9796 | 0.2 | 0.3 | 25924.0482 |  |  |  |  | 0 | 5202.1899 | 5202.1899 | 5202.1899 | 5202.1899 | 5202.1899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8288 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 60.4133 | 0.2 | 0.3 | 94.2448 |  |  |  |  | 0 | 9751.8946 | 9751.8946 | 9751.8946 | 9751.8946 | 9751.8946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8289 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 7937.8193 | 0.2 | 0.3 | 12382.9981 |  |  |  |  | 0 | 9199.5947 | 9199.5947 | 9199.5947 | 9199.5947 | 9199.5947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8290 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 4448.8477 | 0.2 | 0.3 | 6940.2024 |  |  |  |  | 0 | 9581.2753 | 9581.2753 | 9581.2753 | 9581.2753 | 9581.2753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8291 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 16618.5372 | 0.2 | 0.3 | 25924.918 |  |  |  |  | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8292 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 18449.85 | 0.2 | 0.3 | 28781.766 |  |  |  |  | 0 | 7584.1447 | 7584.1447 | 7584.1447 | 7584.1447 | 7584.1447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8293 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 22324.0553 | 0.2 | 0.3 | 34825.5263 |  |  |  |  | 0 | 9113.3303 | 9113.3303 | 9113.3303 | 9113.3303 | 9113.3303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8294 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 6220.5483 | 0.2 | 0.3 | 9704.0554 |  |  |  |  | 0 | 5205.5636 | 5205.5636 | 5205.5636 | 5205.5636 | 5205.5636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8295 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 25926.0435 | 0.2 | 0.3 | 40444.6279 |  |  |  |  | 0 | 7643.2028 | 7643.2028 | 7643.2028 | 7643.2028 | 7643.2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8296 | DAVIE | 70503 | Private | 2026 | 5 | Swales | 66.6667 | 17450.9265 | 0.2 | 0.3 | 27223.4454 |  |  |  |  | 0 | 1690.6587 | 1690.6587 | 1690.6587 | 1690.6587 | 1690.6587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8297 | DAVIE | 70503 | Private | 2026 | 5 | Swales | 66.6667 | 22055.4363 | 0.2 | 0.3 | 34406.4807 |  |  |  |  | 0 | 5206.3543 | 5206.3543 | 5206.3543 | 5206.3543 | 5206.3543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8298 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16677.4239 | 0.2 | 0.3 | 26016.7812 |  |  |  |  | 0 | 7793.2576 | 7793.2576 | 7793.2576 | 7793.2576 | 7793.2576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8299 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16677.7618 | 0.2 | 0.3 | 26017.3084 |  |  |  |  | 0 | 1658.347 | 1658.347 | 1658.347 | 1658.347 | 1658.347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8300 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 19124.9408 | 0.2 | 0.3 | 29834.9076 |  |  |  |  | 0 | 5203.9907 | 5203.9907 | 5203.9907 | 5203.9907 | 5203.9907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8301 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16671.7947 | 0.2 | 0.3 | 26007.9997 |  |  |  |  | 0 | 2195.9017 | 2195.9017 | 2195.9017 | 2195.9017 | 2195.9017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8302 | HOLLYWOOD | 90601 | Public | 2030 | 5 | Swales | 66.6667 | 16672.0681 | 0.2 | 0.3 | 26008.4262 |  |  |  |  | 0 | 5205.2932 | 5205.2932 | 5205.2932 | 5205.2932 | 5205.2932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8303 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16686.5583 | 0.2 | 0.3 | 26031.031 |  |  |  |  | 0 | 2405.4281 | 2405.4281 | 2405.4281 | 2405.4281 | 2405.4281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8304 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 31256.2359 | 0.2 | 0.3 | 48759.7281 |  |  |  |  | 0 | 5202.5339 | 5202.5339 | 5202.5339 | 5202.5339 | 5202.5339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8305 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 9645.4469 | 0.2 | 0.3 | 15046.8972 |  |  |  |  | 0 | 996.7186 | 996.7186 | 996.7186 | 996.7186 | 996.7186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8306 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16585.0927 | 0.2 | 0.3 | 25872.7446 |  |  |  |  | 0 | 5202.2163 | 5202.2163 | 5202.2163 | 5202.2163 | 5202.2163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8307 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16675.6223 | 0.2 | 0.3 | 26013.9707 |  |  |  |  | 0 | 6359.6712 | 6359.6712 | 6359.6712 | 6359.6712 | 6359.6712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8308 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 17848.7099 | 0.2 | 0.3 | 27843.9875 |  |  |  |  | 0 | 5202.8116 | 5202.8116 | 5202.8116 | 5202.8116 | 5202.8116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8309 | TRIBAL LAND | 90602 | Private | 2026 | 5 | Swales | 66.6667 | 18380.939 | 0.2 | 0.3 | 28674.2648 |  |  |  |  | 0 | 2799.1107 | 2799.1107 | 2799.1107 | 2799.1107 | 2799.1107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8310 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16719.9135 | 0.2 | 0.3 | 26083.065 |  |  |  |  | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8311 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 29234.4016 | 0.2 | 0.3 | 45605.6665 |  |  |  |  | 0 | 8308.9429 | 8308.9429 | 8308.9429 | 8308.9429 | 8308.9429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8312 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 2631.2967 | 0.2 | 0.3 | 4104.8228 |  |  |  |  | 0 | 4055.4346 | 4055.4346 | 4055.4346 | 4055.4346 | 4055.4346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8313 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 16678.9031 | 0.2 | 0.3 | 26019.0889 |  |  |  |  | 0 | 5203.6823 | 5203.6823 | 5203.6823 | 5203.6823 | 5203.6823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8314 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 16681.8279 | 0.2 | 0.3 | 26023.6516 |  |  |  |  | 0 | 935.1292 | 935.1292 | 935.1292 | 935.1292 | 935.1292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8315 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 9901.8183 | 0.2 | 0.3 | 15446.8366 |  |  |  |  | 0 | 5204.0063 | 5204.0063 | 5204.0063 | 5204.0063 | 5204.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8316 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 6776.74 | 0.2 | 0.3 | 10571.7144 |  |  |  |  | 0 | 6744.2959 | 6744.2959 | 6744.2959 | 6744.2959 | 6744.2959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8317 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 14724.2161 | 0.2 | 0.3 | 22969.7772 |  |  |  |  | 0 | 2799.4576 | 2799.4576 | 2799.4576 | 2799.4576 | 2799.4576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8318 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 0.22993 | 0.2 | 0.3 | 0.3587 |  |  |  |  | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8319 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 16273.3831 | 0.2 | 0.3 | 25386.4777 |  |  |  |  | 0 | 9783.2838 | 9783.2838 | 9783.2838 | 9783.2838 | 9783.2838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8320 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 14628.6201 | 0.2 | 0.3 | 22820.6474 |  |  |  |  | 0 | 5203.4729 | 5203.4729 | 5203.4729 | 5203.4729 | 5203.4729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8321 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 18969.9854 | 0.2 | 0.3 | 29593.1772 |  |  |  |  | 0 | 5203.6781 | 5203.6781 | 5203.6781 | 5203.6781 | 5203.6781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8322 | DAVIE | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 2085.5989 | 0.2 | 0.3 | 3253.5342 |  |  |  |  | 0 | 5205.1469 | 5205.1469 | 5205.1469 | 5205.1469 | 5205.1469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8323 | DAVIE | 70503 | Private | 2026 | 5 | Swales | 66.6667 | 16997.7284 | 0.2 | 0.3 | 26516.4563 |  |  |  |  | 0 | 6898.9012 | 6898.9012 | 6898.9012 | 6898.9012 | 6898.9012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8324 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 21638.4077 | 0.2 | 0.3 | 33755.916 |  |  |  |  | 0 | 2799.2805 | 2799.2805 | 2799.2805 | 2799.2805 | 2799.2805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8325 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16681.0231 | 0.2 | 0.3 | 26022.396 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8326 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16681.8413 | 0.2 | 0.3 | 26023.6724 |  |  |  |  | 0 | 9781.9664 | 9781.9664 | 9781.9664 | 9781.9664 | 9781.9664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8327 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 19504.4962 | 0.2 | 0.3 | 30427.0141 |  |  |  |  | 0 | 5201.9923 | 5201.9923 | 5201.9923 | 5201.9923 | 5201.9923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8328 | HOLLYWOOD | 90601 | Private | 2026 | 5 | Swales | 66.6667 | 32011.0623 | 0.2 | 0.3 | 49937.2571 |  |  |  |  | 0 | 5202.009 | 5202.009 | 5202.009 | 5202.009 | 5202.009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8329 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31369.3827 | 0.2 | 0.3 | 48936.2371 |  |  |  |  | 0 | 1220.3733 | 1220.3733 | 1220.3733 | 1220.3733 | 1220.3733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8330 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31348.8202 | 0.2 | 0.3 | 48904.1595 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8331 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16679.1765 | 0.2 | 0.3 | 26019.5153 |  |  |  |  | 0 | 3511.6018 | 3511.6018 | 3511.6018 | 3511.6018 | 3511.6018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8332 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 31347.4746 | 0.2 | 0.3 | 48902.0604 |  |  |  |  | 0 | 6725.5616 | 6725.5616 | 6725.5616 | 6725.5616 | 6725.5616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8333 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16680.5995 | 0.2 | 0.3 | 26021.7353 |  |  |  |  | 0 | 4809.7682 | 4809.7682 | 4809.7682 | 4809.7682 | 4809.7682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8334 | TRIBAL LAND | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16799.5115 | 0.2 | 0.3 | 26207.2379 |  |  |  |  | 0 | 9769.7367 | 9769.7367 | 9769.7367 | 9769.7367 | 9769.7367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8335 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16680.113 | 0.2 | 0.3 | 26020.9763 |  |  |  |  | 0 | 2800.0091 | 2800.0091 | 2800.0091 | 2800.0091 | 2800.0091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8336 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 31397.5914 | 0.2 | 0.3 | 48980.2426 |  |  |  |  | 0 | 3625.4693 | 3625.4693 | 3625.4693 | 3625.4693 | 3625.4693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8337 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 25473.8917 | 0.2 | 0.3 | 39739.2711 |  |  |  |  | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8338 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16712.9044 | 0.2 | 0.3 | 26072.1309 |  |  |  |  | 0 | 6180.0394 | 6180.0394 | 6180.0394 | 6180.0394 | 6180.0394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8339 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 19382.2183 | 0.2 | 0.3 | 30236.2606 |  |  |  |  | 0 | 5202.9313 | 5202.9313 | 5202.9313 | 5202.9313 | 5202.9313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8340 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 14245.2112 | 0.2 | 0.3 | 22222.5295 |  |  |  |  | 0 | 1831.3606 | 1831.3606 | 1831.3606 | 1831.3606 | 1831.3606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8341 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 14575.6031 | 0.2 | 0.3 | 22737.9408 |  |  |  |  | 0 | 3980.2134 | 3980.2134 | 3980.2134 | 3980.2134 | 3980.2134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8342 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 16678.0744 | 0.2 | 0.3 | 26017.7961 |  |  |  |  | 0 | 3980.7798 | 3980.7798 | 3980.7798 | 3980.7798 | 3980.7798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8343 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 7391.5022 | 7391.5022 | 7391.5022 | 7391.5022 | 7391.5022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8344 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 16678.1647 | 0.2 | 0.3 | 26017.937 |  |  |  |  | 0 | 12385.2199 | 12385.2199 | 12385.2199 | 12385.2199 | 12385.2199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8345 | COOPER CITY | 70501 | Private | 2033 | 5 | Swales | 66.6667 | 20179.8791 | 0.2 | 0.3 | 31480.6114 |  |  |  |  | 0 | 5200.1515 | 5200.1515 | 5200.1515 | 5200.1515 | 5200.1515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8346 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 2896.1484 | 0.2 | 0.3 | 4517.9915 |  |  |  |  | 0 | 5200.0922 | 5200.0922 | 5200.0922 | 5200.0922 | 5200.0922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8347 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 20389.9445 | 0.2 | 0.3 | 31808.3134 |  |  |  |  | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8348 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 16678.1347 | 0.2 | 0.3 | 26017.8902 |  |  |  |  | 0 | 8930.8165 | 8930.8165 | 8930.8165 | 8930.8165 | 8930.8165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8349 | COOPER CITY | 70501 | Public | 2033 | 5 | Swales | 66.6667 | 13678.5131 | 0.2 | 0.3 | 21338.4804 |  |  |  |  | 0 | 18215.2932 | 18215.2932 | 18215.2932 | 18215.2932 | 18215.2932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8350 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 8294.7246 | 0.2 | 0.3 | 12939.7704 |  |  |  |  | 0 | 2154.5083 | 2154.5083 | 2154.5083 | 2154.5083 | 2154.5083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8351 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 1444.1201 | 0.2 | 0.3 | 2252.8274 |  |  |  |  | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8352 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 20351.0859 | 0.2 | 0.3 | 31747.6941 |  |  |  |  | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8353 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 15553.3063 | 0.2 | 0.3 | 24263.1578 |  |  |  |  | 0 | 9185.8569 | 9185.8569 | 9185.8569 | 9185.8569 | 9185.8569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8354 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 8517.8038 | 0.2 | 0.3 | 13287.7739 |  |  |  |  | 0 | 9563.1177 | 9563.1177 | 9563.1177 | 9563.1177 | 9563.1177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8355 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 10098.2381 | 0.2 | 0.3 | 15753.2515 |  |  |  |  | 0 | 3624.7268 | 3624.7268 | 3624.7268 | 3624.7268 | 3624.7268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8356 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 15447.4705 | 0.2 | 0.3 | 24098.054 |  |  |  |  | 0 | 2150.2748 | 2150.2748 | 2150.2748 | 2150.2748 | 2150.2748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8357 | DAVIE | 70503 | Private | 2026 | 5 | Swales | 66.6667 | 20847.1674 | 0.2 | 0.3 | 32521.5811 |  |  |  |  | 0 | 9777.5441 | 9777.5441 | 9777.5441 | 9777.5441 | 9777.5441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8358 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 31352.1809 | 0.2 | 0.3 | 48909.4023 |  |  |  |  | 0 | 9778.6495 | 9778.6495 | 9778.6495 | 9778.6495 | 9778.6495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8359 | DAVIE | 70504 | Public | 2026 | 5 | Swales | 66.6667 | 31390.3152 | 0.2 | 0.3 | 48968.8917 |  |  |  |  | 0 | 5201.5222 | 5201.5222 | 5201.5222 | 5201.5222 | 5201.5222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8360 | DAVIE | 70504 | Public | 2026 | 5 | Swales | 66.6667 | 23093.4128 | 0.2 | 0.3 | 36025.724 |  |  |  |  | 0 | 9777.9699 | 9777.9699 | 9777.9699 | 9777.9699 | 9777.9699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8361 | DAVIE | 70504 | Public | 2026 | 5 | Swales | 66.6667 | 16918.5241 | 0.2 | 0.3 | 26392.8976 |  |  |  |  | 0 | 5371.6756 | 5371.6756 | 5371.6756 | 5371.6756 | 5371.6756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8362 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16672.6716 | 0.2 | 0.3 | 26009.3677 |  |  |  |  | 0 | 5395.8853 | 5395.8853 | 5395.8853 | 5395.8853 | 5395.8853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8363 | HOLLYWOOD | 90601 | Private | 2026 | 5 | Swales | 66.6667 | 16676.19 | 0.2 | 0.3 | 26014.8564 |  |  |  |  | 0 | 2403.517 | 2403.517 | 2403.517 | 2403.517 | 2403.517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8364 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16672.0241 | 0.2 | 0.3 | 26008.3576 |  |  |  |  | 0 | 5200.2802 | 5200.2802 | 5200.2802 | 5200.2802 | 5200.2802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8365 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16669.0788 | 0.2 | 0.3 | 26003.7629 |  |  |  |  | 0 | 5200.6526 | 5200.6526 | 5200.6526 | 5200.6526 | 5200.6526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8366 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 26624.8432 | 0.2 | 0.3 | 41534.7554 |  |  |  |  | 0 | 5200.2118 | 5200.2118 | 5200.2118 | 5200.2118 | 5200.2118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8367 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16685.1913 | 0.2 | 0.3 | 26028.8985 |  |  |  |  | 0 | 4591.6038 | 4591.6038 | 4591.6038 | 4591.6038 | 4591.6038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8368 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 4154.8158 | 4154.8158 | 4154.8158 | 4154.8158 | 4154.8158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8369 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 31351.3479 | 0.2 | 0.3 | 48908.1027 |  |  |  |  | 0 | 4807.2922 | 4807.2922 | 4807.2922 | 4807.2922 | 4807.2922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8370 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16680.1072 | 0.2 | 0.3 | 26020.9672 |  |  |  |  | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8371 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16685.0186 | 0.2 | 0.3 | 26028.629 |  |  |  |  | 0 | 5200.6526 | 5200.6526 | 5200.6526 | 5200.6526 | 5200.6526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8372 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16833.5411 | 0.2 | 0.3 | 26260.3242 |  |  |  |  | 0 | 5200.1312 | 5200.1312 | 5200.1312 | 5200.1312 | 5200.1312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8373 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 5199.9991 | 5199.9991 | 5199.9991 | 5199.9991 | 5199.9991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8374 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16753.3393 | 0.2 | 0.3 | 26135.2093 |  |  |  |  | 0 | 4342.5611 | 4342.5611 | 4342.5611 | 4342.5611 | 4342.5611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8375 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 12955.9409 | 0.2 | 0.3 | 20211.2679 |  |  |  |  | 0 | 3983.4919 | 3983.4919 | 3983.4919 | 3983.4919 | 3983.4919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8376 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 7976.1631 | 0.2 | 0.3 | 12442.8145 |  |  |  |  | 0 | 1221.0091 | 1221.0091 | 1221.0091 | 1221.0091 | 1221.0091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8377 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 20057.195 | 0.2 | 0.3 | 31289.2242 |  |  |  |  | 0 | 3543.8512 | 3543.8512 | 3543.8512 | 3543.8512 | 3543.8512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8378 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 17310.7903 | 0.2 | 0.3 | 27004.8329 |  |  |  |  | 0 | 815.2032 | 815.2032 | 815.2032 | 815.2032 | 815.2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8379 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 7718.261 | 0.2 | 0.3 | 12040.4872 |  |  |  |  | 0 | 312.0439 | 312.0439 | 312.0439 | 312.0439 | 312.0439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8380 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 20844.1432 | 0.2 | 0.3 | 32516.8634 |  |  |  |  | 0 | 7498.925 | 7498.925 | 7498.925 | 7498.925 | 7498.925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8381 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16681.6431 | 0.2 | 0.3 | 26023.3633 |  |  |  |  | 0 | 2817.3169 | 2817.3169 | 2817.3169 | 2817.3169 | 2817.3169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8382 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16682.3925 | 0.2 | 0.3 | 26024.5322 |  |  |  |  | 0 | 9536.5664 | 9536.5664 | 9536.5664 | 9536.5664 | 9536.5664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8383 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 20786.7399 | 0.2 | 0.3 | 32427.3142 |  |  |  |  | 0 | 5205.9976 | 5205.9976 | 5205.9976 | 5205.9976 | 5205.9976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8384 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16669.04 | 0.2 | 0.3 | 26003.7024 |  |  |  |  | 0 | 5204.1996 | 5204.1996 | 5204.1996 | 5204.1996 | 5204.1996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8385 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16672.6807 | 0.2 | 0.3 | 26009.3819 |  |  |  |  | 0 | 2411.1603 | 2411.1603 | 2411.1603 | 2411.1603 | 2411.1603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8386 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16676.1361 | 0.2 | 0.3 | 26014.7724 |  |  |  |  | 0 | 3670.1238 | 3670.1238 | 3670.1238 | 3670.1238 | 3670.1238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8387 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16672.0129 | 0.2 | 0.3 | 26008.3402 |  |  |  |  | 0 | 7499.3095 | 7499.3095 | 7499.3095 | 7499.3095 | 7499.3095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8388 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16669.4166 | 0.2 | 0.3 | 26004.2899 |  |  |  |  | 0 | 2384.7418 | 2384.7418 | 2384.7418 | 2384.7418 | 2384.7418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8389 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 25982.5823 | 0.2 | 0.3 | 40532.8283 |  |  |  |  | 0 | 5452.9908 | 5452.9908 | 5452.9908 | 5452.9908 | 5452.9908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8390 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16683.0041 | 0.2 | 0.3 | 26025.4864 |  |  |  |  | 0 | 3981.2589 | 3981.2589 | 3981.2589 | 3981.2589 | 3981.2589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8391 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 3318.9462 | 3318.9462 | 3318.9462 | 3318.9462 | 3318.9462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8392 | HOLLYWOOD | 90602 | Public | 2026 | 5 | Swales | 66.6667 | 31351.6882 | 0.2 | 0.3 | 48908.6336 |  |  |  |  | 0 | 9789.5867 | 9789.5867 | 9789.5867 | 9789.5867 | 9789.5867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8393 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16680.4983 | 0.2 | 0.3 | 26021.5773 |  |  |  |  | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8394 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 6830.2904 | 0.2 | 0.3 | 10655.253 |  |  |  |  | 0 | 9788.1614 | 9788.1614 | 9788.1614 | 9788.1614 | 9788.1614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8395 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 19755.5393 | 0.2 | 0.3 | 30818.6413 |  |  |  |  | 0 | 5206.4539 | 5206.4539 | 5206.4539 | 5206.4539 | 5206.4539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8396 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 19738.244 | 0.2 | 0.3 | 30791.6606 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8397 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 28280.2905 | 0.2 | 0.3 | 44117.2531 |  |  |  |  | 0 | 7684.8168 | 7684.8168 | 7684.8168 | 7684.8168 | 7684.8168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8398 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16672.7753 | 0.2 | 0.3 | 26009.5295 |  |  |  |  | 0 | 2639.6504 | 2639.6504 | 2639.6504 | 2639.6504 | 2639.6504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8399 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16752.9951 | 0.2 | 0.3 | 26134.6724 |  |  |  |  | 0 | 9788.6249 | 9788.6249 | 9788.6249 | 9788.6249 | 9788.6249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8400 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 15699.8495 | 0.2 | 0.3 | 24491.7652 |  |  |  |  | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8401 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 16865.1117 | 0.2 | 0.3 | 26309.5742 |  |  |  |  | 0 | 9093.1162 | 9093.1162 | 9093.1162 | 9093.1162 | 9093.1162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8402 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 21008.9783 | 0.2 | 0.3 | 32774.0061 |  |  |  |  | 0 | 5903.7386 | 5903.7386 | 5903.7386 | 5903.7386 | 5903.7386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8403 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 115.8649 | 0.2 | 0.3 | 180.7493 |  |  |  |  | 0 | 5205.6091 | 5205.6091 | 5205.6091 | 5205.6091 | 5205.6091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8404 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 20377.6035 | 0.2 | 0.3 | 31789.0615 |  |  |  |  | 0 | 8033.5689 | 8033.5689 | 8033.5689 | 8033.5689 | 8033.5689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8405 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16681.0885 | 0.2 | 0.3 | 26022.498 |  |  |  |  | 0 | 5317.329 | 5317.329 | 5317.329 | 5317.329 | 5317.329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8406 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16681.8047 | 0.2 | 0.3 | 26023.6154 |  |  |  |  | 0 | 2379.4122 | 2379.4122 | 2379.4122 | 2379.4122 | 2379.4122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8407 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 21070.0578 | 0.2 | 0.3 | 32869.2902 |  |  |  |  | 0 | 6109.1935 | 6109.1935 | 6109.1935 | 6109.1935 | 6109.1935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8408 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16672.2225 | 0.2 | 0.3 | 26008.6672 |  |  |  |  | 0 | 7463.1579 | 7463.1579 | 7463.1579 | 7463.1579 | 7463.1579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8409 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 28.4668 | 0.2 | 0.3 | 44.4082 |  |  |  |  | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8410 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 6836.0329 | 0.2 | 0.3 | 10664.2114 |  |  |  |  | 0 | 8229.257 | 8229.257 | 8229.257 | 8229.257 | 8229.257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8411 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 30044.3432 | 0.2 | 0.3 | 46869.1754 |  |  |  |  | 0 | 1975.6186 | 1975.6186 | 1975.6186 | 1975.6186 | 1975.6186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8412 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31382.0945 | 0.2 | 0.3 | 48956.0674 |  |  |  |  | 0 | 9676.2012 | 9676.2012 | 9676.2012 | 9676.2012 | 9676.2012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8413 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31347.4831 | 0.2 | 0.3 | 48902.0737 |  |  |  |  | 0 | 2824.7403 | 2824.7403 | 2824.7403 | 2824.7403 | 2824.7403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8414 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31353.1718 | 0.2 | 0.3 | 48910.948 |  |  |  |  | 0 | 2882.9095 | 2882.9095 | 2882.9095 | 2882.9095 | 2882.9095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8415 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 20733.9735 | 0.2 | 0.3 | 32344.9987 |  |  |  |  | 0 | 3742.1424 | 3742.1424 | 3742.1424 | 3742.1424 | 3742.1424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8416 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 25562.3754 | 0.2 | 0.3 | 39877.3056 |  |  |  |  | 0 | 5205.5162 | 5205.5162 | 5205.5162 | 5205.5162 | 5205.5162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8417 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16682.4573 | 0.2 | 0.3 | 26024.6334 |  |  |  |  | 0 | 1301.9593 | 1301.9593 | 1301.9593 | 1301.9593 | 1301.9593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8418 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16684.6445 | 0.2 | 0.3 | 26028.0455 |  |  |  |  | 0 | 9782.3659 | 9782.3659 | 9782.3659 | 9782.3659 | 9782.3659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8419 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 31355.6738 | 0.2 | 0.3 | 48914.8511 |  |  |  |  | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8420 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16677.0646 | 0.2 | 0.3 | 26016.2208 |  |  |  |  | 0 | 5204.0486 | 5204.0486 | 5204.0486 | 5204.0486 | 5204.0486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8421 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 14998.2045 | 0.2 | 0.3 | 23397.199 |  |  |  |  | 0 | 9782.9098 | 9782.9098 | 9782.9098 | 9782.9098 | 9782.9098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8422 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 31410.9795 | 0.2 | 0.3 | 49001.128 |  |  |  |  | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8423 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 17094.2875 | 0.2 | 0.3 | 26667.0884 |  |  |  |  | 0 | 9785.6153 | 9785.6153 | 9785.6153 | 9785.6153 | 9785.6153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8424 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 16672.9677 | 0.2 | 0.3 | 26009.8297 |  |  |  |  | 0 | 5202.5278 | 5202.5278 | 5202.5278 | 5202.5278 | 5202.5278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8425 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 18730.6297 | 0.2 | 0.3 | 29219.7823 |  |  |  |  | 0 | 2404.2129 | 2404.2129 | 2404.2129 | 2404.2129 | 2404.2129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8426 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 23820.6186 | 0.2 | 0.3 | 37160.165 |  |  |  |  | 0 | 7652.7079 | 7652.7079 | 7652.7079 | 7652.7079 | 7652.7079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8427 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 21380.7197 | 0.2 | 0.3 | 33353.9227 |  |  |  |  | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8428 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 24762.7948 | 0.2 | 0.3 | 38629.9599 |  |  |  |  | 0 | 5206.4685 | 5206.4685 | 5206.4685 | 5206.4685 | 5206.4685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8429 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 18159.1074 | 0.2 | 0.3 | 28328.2075 |  |  |  |  | 0 | 9787.754 | 9787.754 | 9787.754 | 9787.754 | 9787.754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8430 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 1011.802 | 0.2 | 0.3 | 1578.4111 |  |  |  |  | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8431 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 17643.4547 | 0.2 | 0.3 | 27523.7894 |  |  |  |  | 0 | 6749.029 | 6749.029 | 6749.029 | 6749.029 | 6749.029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8432 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 25071.0009 | 0.2 | 0.3 | 39110.7615 |  |  |  |  | 0 | 3981.6128 | 3981.6128 | 3981.6128 | 3981.6128 | 3981.6128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8433 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 31327.6571 | 0.2 | 0.3 | 48871.145 |  |  |  |  | 0 | 9432.7557 | 9432.7557 | 9432.7557 | 9432.7557 | 9432.7557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8434 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16677.9177 | 0.2 | 0.3 | 26017.5516 |  |  |  |  | 0 | 5204.154 | 5204.154 | 5204.154 | 5204.154 | 5204.154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8435 | DAVIE | 70503 | Public | 2026 | 5 | Swales | 66.6667 | 16678.7165 | 0.2 | 0.3 | 26018.7978 |  |  |  |  | 0 | 5204.3746 | 5204.3746 | 5204.3746 | 5204.3746 | 5204.3746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8436 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 22261.4102 | 0.2 | 0.3 | 34727.7999 |  |  |  |  | 0 | 5889.9948 | 5889.9948 | 5889.9948 | 5889.9948 | 5889.9948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8437 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16653.4339 | 0.2 | 0.3 | 25979.3568 |  |  |  |  | 0 | 5203.3059 | 5203.3059 | 5203.3059 | 5203.3059 | 5203.3059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8438 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 9845.7992 | 0.2 | 0.3 | 15359.4468 |  |  |  |  | 0 | 9156.517 | 9156.517 | 9156.517 | 9156.517 | 9156.517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8439 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 18139.726 | 0.2 | 0.3 | 28297.9726 |  |  |  |  | 0 | 5203.0725 | 5203.0725 | 5203.0725 | 5203.0725 | 5203.0725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8440 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16670.701 | 0.2 | 0.3 | 26006.2936 |  |  |  |  | 0 | 5203.1316 | 5203.1316 | 5203.1316 | 5203.1316 | 5203.1316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8441 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16673.9336 | 0.2 | 0.3 | 26011.3364 |  |  |  |  | 0 | 9784.1875 | 9784.1875 | 9784.1875 | 9784.1875 | 9784.1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8442 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16672.6654 | 0.2 | 0.3 | 26009.358 |  |  |  |  | 0 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8443 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 25256.5339 | 0.2 | 0.3 | 39400.1929 |  |  |  |  | 0 | 9782.2365 | 9782.2365 | 9782.2365 | 9782.2365 | 9782.2365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8444 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16677.8095 | 0.2 | 0.3 | 26017.3829 |  |  |  |  | 0 | 5204.8689 | 5204.8689 | 5204.8689 | 5204.8689 | 5204.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8445 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16683.0041 | 0.2 | 0.3 | 26025.4864 |  |  |  |  | 0 | 5205.0918 | 5205.0918 | 5205.0918 | 5205.0918 | 5205.0918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8446 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 31355.9779 | 0.2 | 0.3 | 48915.3256 |  |  |  |  | 0 | 5203.6033 | 5203.6033 | 5203.6033 | 5203.6033 | 5203.6033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8447 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16684.9986 | 0.2 | 0.3 | 26028.5978 |  |  |  |  | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8448 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 16703.0287 | 0.2 | 0.3 | 26056.7247 |  |  |  |  | 0 | 4941.7627 | 4941.7627 | 4941.7627 | 4941.7627 | 4941.7627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8449 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 2.8721 | 0.2 | 0.3 | 4.4804 |  |  |  |  | 0 | 4124.2147 | 4124.2147 | 4124.2147 | 4124.2147 | 4124.2147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8450 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 26524.7306 | 0.2 | 0.3 | 41378.5797 |  |  |  |  | 0 | 2404.4389 | 2404.4389 | 2404.4389 | 2404.4389 | 2404.4389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8451 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 30733.4779 | 0.2 | 0.3 | 47944.2256 |  |  |  |  | 0 | 5202.1005 | 5202.1005 | 5202.1005 | 5202.1005 | 5202.1005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8452 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 7416.5876 | 0.2 | 0.3 | 11569.8767 |  |  |  |  | 0 | 1166.9641 | 1166.9641 | 1166.9641 | 1166.9641 | 1166.9641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8453 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 19833.8829 | 0.2 | 0.3 | 30940.8574 |  |  |  |  | 0 | 2676.1948 | 2676.1948 | 2676.1948 | 2676.1948 | 2676.1948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8454 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 17405.9774 | 0.2 | 0.3 | 27153.3247 |  |  |  |  | 0 | 9504.8046 | 9504.8046 | 9504.8046 | 9504.8046 | 9504.8046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8455 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 947.9253 | 0.2 | 0.3 | 1478.7634 |  |  |  |  | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8456 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 17819.8967 | 0.2 | 0.3 | 27799.0388 |  |  |  |  | 0 | 9192.987 | 9192.987 | 9192.987 | 9192.987 | 9192.987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8457 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 16971.369 | 0.2 | 0.3 | 26475.3356 |  |  |  |  | 0 | 8864.3397 | 8864.3397 | 8864.3397 | 8864.3397 | 8864.3397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8458 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 36085.7225 | 0.2 | 0.3 | 56293.7272 |  |  |  |  | 0 | 4036.6965 | 4036.6965 | 4036.6965 | 4036.6965 | 4036.6965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8459 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31394.5505 | 0.2 | 0.3 | 48975.4988 |  |  |  |  | 0 | 2527.8582 | 2527.8582 | 2527.8582 | 2527.8582 | 2527.8582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8460 | HOLLYWOOD | 90601 | Private | 2026 | 5 | Swales | 66.6667 | 16678.2656 | 0.2 | 0.3 | 26018.0943 |  |  |  |  | 0 | 5481.1573 | 5481.1573 | 5481.1573 | 5481.1573 | 5481.1573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8461 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16678.8497 | 0.2 | 0.3 | 26019.0055 |  |  |  |  | 0 | 8583.2591 | 8583.2591 | 8583.2591 | 8583.2591 | 8583.2591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8462 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 19794.7313 | 0.2 | 0.3 | 30879.7808 |  |  |  |  | 0 | 5202.7823 | 5202.7823 | 5202.7823 | 5202.7823 | 5202.7823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8463 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16670.9715 | 0.2 | 0.3 | 26006.7156 |  |  |  |  | 0 | 2404.5593 | 2404.5593 | 2404.5593 | 2404.5593 | 2404.5593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8464 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 26702.6409 | 0.2 | 0.3 | 41656.1199 |  |  |  |  | 0 | 4018.1315 | 4018.1315 | 4018.1315 | 4018.1315 | 4018.1315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8465 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 18432.4654 | 0.2 | 0.3 | 28754.646 |  |  |  |  | 0 | 3732.7211 | 3732.7211 | 3732.7211 | 3732.7211 | 3732.7211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8466 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 1202.6189 | 1202.6189 | 1202.6189 | 1202.6189 | 1202.6189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8467 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 24680.3 | 0.2 | 0.3 | 38501.268 |  |  |  |  | 0 | 2799.2788 | 2799.2788 | 2799.2788 | 2799.2788 | 2799.2788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8468 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8469 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16680.5435 | 0.2 | 0.3 | 26021.6479 |  |  |  |  | 0 | 8298.3661 | 8298.3661 | 8298.3661 | 8298.3661 | 8298.3661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8470 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 31355.7339 | 0.2 | 0.3 | 48914.9449 |  |  |  |  | 0 | 5201.9637 | 5201.9637 | 5201.9637 | 5201.9637 | 5201.9637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8471 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16684.8735 | 0.2 | 0.3 | 26028.4026 |  |  |  |  | 0 | 5202.4379 | 5202.4379 | 5202.4379 | 5202.4379 | 5202.4379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8472 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 22867.74 | 0.2 | 0.3 | 35673.6744 |  |  |  |  | 0 | 3568.9156 | 3568.9156 | 3568.9156 | 3568.9156 | 3568.9156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8473 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 17787.1006 | 0.2 | 0.3 | 27747.8769 |  |  |  |  | 0 | 5202.5651 | 5202.5651 | 5202.5651 | 5202.5651 | 5202.5651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8474 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 13769.0443 | 0.2 | 0.3 | 21479.7091 |  |  |  |  | 0 | 531.5712 | 531.5712 | 531.5712 | 531.5712 | 531.5712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8475 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 22602.1345 | 0.2 | 0.3 | 35259.3299 |  |  |  |  | 0 | 6113.1694 | 6113.1694 | 6113.1694 | 6113.1694 | 6113.1694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8476 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 17150.1384 | 0.2 | 0.3 | 26754.2159 |  |  |  |  | 0 | 8009.504 | 8009.504 | 8009.504 | 8009.504 | 8009.504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8477 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 18499.9697 | 0.2 | 0.3 | 28859.9527 |  |  |  |  | 0 | 5203.3252 | 5203.3252 | 5203.3252 | 5203.3252 | 5203.3252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8478 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 3836.9391 | 0.2 | 0.3 | 5985.6249 |  |  |  |  | 0 | 4672.8451 | 4672.8451 | 4672.8451 | 4672.8451 | 4672.8451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8479 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 4171.8163 | 0.2 | 0.3 | 6508.0335 |  |  |  |  | 0 | 1196.7255 | 1196.7255 | 1196.7255 | 1196.7255 | 1196.7255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8480 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 38233.7035 | 0.2 | 0.3 | 59644.5775 |  |  |  |  | 0 | 7730.5879 | 7730.5879 | 7730.5879 | 7730.5879 | 7730.5879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8481 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 15793.0951 | 0.2 | 0.3 | 24637.2283 |  |  |  |  | 0 | 5204.5262 | 5204.5262 | 5204.5262 | 5204.5262 | 5204.5262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8482 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 38491.467 | 0.2 | 0.3 | 60046.6885 |  |  |  |  | 0 | 5204.6842 | 5204.6842 | 5204.6842 | 5204.6842 | 5204.6842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8483 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 42439.8214 | 0.2 | 0.3 | 66206.1214 |  |  |  |  | 0 | 2445.119 | 2445.119 | 2445.119 | 2445.119 | 2445.119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8484 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16676.4361 | 0.2 | 0.3 | 26015.2404 |  |  |  |  | 0 | 2798.4106 | 2798.4106 | 2798.4106 | 2798.4106 | 2798.4106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8485 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31347.9291 | 0.2 | 0.3 | 48902.7694 |  |  |  |  | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8486 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 15597.1737 | 0.2 | 0.3 | 24331.5909 |  |  |  |  | 0 | 6699.38 | 6699.38 | 6699.38 | 6699.38 | 6699.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8487 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 17240.01 | 0.2 | 0.3 | 26894.4156 |  |  |  |  | 0 | 3980.0844 | 3980.0844 | 3980.0844 | 3980.0844 | 3980.0844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8488 | HOLLYWOOD | 90601 | Private | 2026 | 5 | Swales | 66.6667 | 30790.9559 | 0.2 | 0.3 | 48033.8912 |  |  |  |  | 0 | 2055.0265 | 2055.0265 | 2055.0265 | 2055.0265 | 2055.0265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8489 | HOLLYWOOD | 90601 | Private | 2026 | 5 | Swales | 66.6667 | 16681.0903 | 0.2 | 0.3 | 26022.5009 |  |  |  |  | 0 | 5082.2872 | 5082.2872 | 5082.2872 | 5082.2872 | 5082.2872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8490 | HOLLYWOOD | 90601 | Private | 2026 | 5 | Swales | 66.6667 | 31350.1514 | 0.2 | 0.3 | 48906.2362 |  |  |  |  | 0 | 122.3561 | 122.3561 | 122.3561 | 122.3561 | 122.3561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8491 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16679.3916 | 0.2 | 0.3 | 26019.8509 |  |  |  |  | 0 | 764.0037 | 764.0037 | 764.0037 | 764.0037 | 764.0037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8492 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16679.6396 | 0.2 | 0.3 | 26020.2378 |  |  |  |  | 0 | 900.5556 | 900.5556 | 900.5556 | 900.5556 | 900.5556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8493 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31345.4141 | 0.2 | 0.3 | 48898.846 |  |  |  |  | 0 | 4095.913 | 4095.913 | 4095.913 | 4095.913 | 4095.913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8494 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 28728.109 | 0.2 | 0.3 | 44815.85 |  |  |  |  | 0 | 2406.8333 | 2406.8333 | 2406.8333 | 2406.8333 | 2406.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8495 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 18846.6934 | 0.2 | 0.3 | 29400.8417 |  |  |  |  | 0 | 6605.6535 | 6605.6535 | 6605.6535 | 6605.6535 | 6605.6535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8496 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 24414.9459 | 0.2 | 0.3 | 38087.3157 |  |  |  |  | 0 | 5203.1939 | 5203.1939 | 5203.1939 | 5203.1939 | 5203.1939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8497 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16680.1639 | 0.2 | 0.3 | 26021.0557 |  |  |  |  | 0 | 4439.4865 | 4439.4865 | 4439.4865 | 4439.4865 | 4439.4865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8498 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 5822.8674 | 5822.8674 | 5822.8674 | 5822.8674 | 5822.8674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8499 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 31353.2791 | 0.2 | 0.3 | 48911.1153 |  |  |  |  | 0 | 610.5262 | 610.5262 | 610.5262 | 610.5262 | 610.5262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8500 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16686.0512 | 0.2 | 0.3 | 26030.2399 |  |  |  |  | 0 | 610.5683 | 610.5683 | 610.5683 | 610.5683 | 610.5683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8501 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 19774.2753 | 0.2 | 0.3 | 30847.8695 |  |  |  |  | 0 | 6622.6549 | 6622.6549 | 6622.6549 | 6622.6549 | 6622.6549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8502 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 4246.2239 | 0.2 | 0.3 | 6624.1092 |  |  |  |  | 0 | 5203.4164 | 5203.4164 | 5203.4164 | 5203.4164 | 5203.4164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8503 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 13950.3298 | 0.2 | 0.3 | 21762.5145 |  |  |  |  | 0 | 5203.5715 | 5203.5715 | 5203.5715 | 5203.5715 | 5203.5715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8504 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 20078 | 0.2 | 0.3 | 31321.68 |  |  |  |  | 0 | 6603.93 | 6603.93 | 6603.93 | 6603.93 | 6603.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8505 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 30528.0385 | 0.2 | 0.3 | 47623.74 |  |  |  |  | 0 | 6402.1113 | 6402.1113 | 6402.1113 | 6402.1113 | 6402.1113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8506 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 18667.528 | 0.2 | 0.3 | 29121.3437 |  |  |  |  | 0 | 5203.3968 | 5203.3968 | 5203.3968 | 5203.3968 | 5203.3968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8507 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16699.4083 | 0.2 | 0.3 | 26051.0769 |  |  |  |  | 0 | 5203.4002 | 5203.4002 | 5203.4002 | 5203.4002 | 5203.4002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8508 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16718.8198 | 0.2 | 0.3 | 26081.3589 |  |  |  |  | 0 | 2683.5941 | 2683.5941 | 2683.5941 | 2683.5941 | 2683.5941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8509 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31390.1983 | 0.2 | 0.3 | 48968.7093 |  |  |  |  | 0 | 1221.0431 | 1221.0431 | 1221.0431 | 1221.0431 | 1221.0431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8510 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9105 | 0.2 | 0.3 | 26023.7804 |  |  |  |  | 0 | 6636.9938 | 6636.9938 | 6636.9938 | 6636.9938 | 6636.9938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8511 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16682.4825 | 0.2 | 0.3 | 26024.6726 |  |  |  |  | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8512 | HOLLYWOOD | 90601 | Private | 2026 | 5 | Swales | 66.6667 | 31346.7333 | 0.2 | 0.3 | 48900.9039 |  |  |  |  | 0 | 2404.3448 | 2404.3448 | 2404.3448 | 2404.3448 | 2404.3448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8513 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16677.8095 | 0.2 | 0.3 | 26017.3828 |  |  |  |  | 0 | 4360.5676 | 4360.5676 | 4360.5676 | 4360.5676 | 4360.5676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8514 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31376.7147 | 0.2 | 0.3 | 48947.6749 |  |  |  |  | 0 | 5260.8031 | 5260.8031 | 5260.8031 | 5260.8031 | 5260.8031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8515 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16683.7817 | 0.2 | 0.3 | 26026.6994 |  |  |  |  | 0 | 5209.3672 | 5209.3672 | 5209.3672 | 5209.3672 | 5209.3672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8516 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16682.2501 | 0.2 | 0.3 | 26024.3101 |  |  |  |  | 0 | 3031.4246 | 3031.4246 | 3031.4246 | 3031.4246 | 3031.4246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8517 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 20629.9154 | 0.2 | 0.3 | 32182.668 |  |  |  |  | 0 | 2584.1654 | 2584.1654 | 2584.1654 | 2584.1654 | 2584.1654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8518 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 24070.3242 | 0.2 | 0.3 | 37549.7058 |  |  |  |  | 0 | 1220.8655 | 1220.8655 | 1220.8655 | 1220.8655 | 1220.8655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8519 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16679.5187 | 0.2 | 0.3 | 26020.0492 |  |  |  |  | 0 | 4087.6388 | 4087.6388 | 4087.6388 | 4087.6388 | 4087.6388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8520 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16681.0903 | 0.2 | 0.3 | 26022.5009 |  |  |  |  | 0 | 4864.5375 | 4864.5375 | 4864.5375 | 4864.5375 | 4864.5375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8521 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 31352.0816 | 0.2 | 0.3 | 48909.2473 |  |  |  |  | 0 | 5206.5267 | 5206.5267 | 5206.5267 | 5206.5267 | 5206.5267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8522 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16682.5465 | 0.2 | 0.3 | 26024.7726 |  |  |  |  | 0 | 1220.7824 | 1220.7824 | 1220.7824 | 1220.7824 | 1220.7824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8523 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 19869.8789 | 0.2 | 0.3 | 30997.0111 |  |  |  |  | 0 | 1481.2195 | 1481.2195 | 1481.2195 | 1481.2195 | 1481.2195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8524 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 16835.5747 | 0.2 | 0.3 | 26263.4965 |  |  |  |  | 0 | 1058.0733 | 1058.0733 | 1058.0733 | 1058.0733 | 1058.0733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8525 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 16719.3051 | 0.2 | 0.3 | 26082.1159 |  |  |  |  | 0 | 4873.1814 | 4873.1814 | 4873.1814 | 4873.1814 | 4873.1814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8526 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 18037.4302 | 0.2 | 0.3 | 28138.3911 |  |  |  |  | 0 | 5202.7954 | 5202.7954 | 5202.7954 | 5202.7954 | 5202.7954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8527 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 17145.6751 | 0.2 | 0.3 | 26747.2532 |  |  |  |  | 0 | 0.8839 | 0.8839 | 0.8839 | 0.8839 | 0.8839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8528 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 20525.7563 | 0.2 | 0.3 | 32020.1799 |  |  |  |  | 0 | 7175.5587 | 7175.5587 | 7175.5587 | 7175.5587 | 7175.5587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8529 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 16308.9061 | 0.2 | 0.3 | 25441.8936 |  |  |  |  | 0 | 5199.3372 | 5199.3372 | 5199.3372 | 5199.3372 | 5199.3372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8530 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 18216.873 | 0.2 | 0.3 | 28418.3219 |  |  |  |  | 0 | 5202.7033 | 5202.7033 | 5202.7033 | 5202.7033 | 5202.7033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8531 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16685.441 | 0.2 | 0.3 | 26029.288 |  |  |  |  | 0 | 9434.6167 | 9434.6167 | 9434.6167 | 9434.6167 | 9434.6167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8532 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16686.0401 | 0.2 | 0.3 | 26030.2225 |  |  |  |  | 0 | 2733.8593 | 2733.8593 | 2733.8593 | 2733.8593 | 2733.8593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8533 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31390.8427 | 0.2 | 0.3 | 48969.7146 |  |  |  |  | 0 | 2344.2064 | 2344.2064 | 2344.2064 | 2344.2064 | 2344.2064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8534 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16684.0977 | 0.2 | 0.3 | 26027.1925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7526.1238 | 7526.1238 | 7526.1238 | 7526.1238 | 7526.1238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8535 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16683.8246 | 0.2 | 0.3 | 26026.7664 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7647.7667 | 7647.7667 | 7647.7667 | 7647.7667 | 7647.7667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8536 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31346.6175 | 0.2 | 0.3 | 48900.7232 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 572.5178 | 572.5178 | 572.5178 | 572.5178 | 572.5178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8537 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8796.0599 | 8796.0599 | 8796.0599 | 8796.0599 | 8796.0599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8538 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31372.7078 | 0.2 | 0.3 | 48941.4242 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5294.5265 | 5294.5265 | 5294.5265 | 5294.5265 | 5294.5265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8539 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16681.7783 | 0.2 | 0.3 | 26023.5742 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8517.258 | 8517.258 | 8517.258 | 8517.258 | 8517.258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8540 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16680.1145 | 0.2 | 0.3 | 26020.9787 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5492.1429 | 5492.1429 | 5492.1429 | 5492.1429 | 5492.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8541 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 30969.2917 | 0.2 | 0.3 | 48312.0951 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4912.4267 | 4912.4267 | 4912.4267 | 4912.4267 | 4912.4267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8542 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16680.7515 | 0.2 | 0.3 | 26021.9724 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2243.7965 | 2243.7965 | 2243.7965 | 2243.7965 | 2243.7965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8543 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16682.8569 | 0.2 | 0.3 | 26025.2567 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4086.236 | 4086.236 | 4086.236 | 4086.236 | 4086.236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8544 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31349.223 | 0.2 | 0.3 | 48904.7879 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5220.9593 | 5220.9593 | 5220.9593 | 5220.9593 | 5220.9593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8545 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31347.9155 | 0.2 | 0.3 | 48902.7482 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10169.3551 | 10169.3551 | 10169.3551 | 10169.3551 | 10169.3551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8546 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 6161.8043 | 0.2 | 0.3 | 9612.4147 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2809.8779 | 2809.8779 | 2809.8779 | 2809.8779 | 2809.8779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8547 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 9718.3785 | 0.2 | 0.3 | 15160.6704 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4669.8358 | 4669.8358 | 4669.8358 | 4669.8358 | 4669.8358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8548 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16583.2974 | 0.2 | 0.3 | 25869.9439 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5574.2973 | 5574.2973 | 5574.2973 | 5574.2973 | 5574.2973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8549 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 31350.3906 | 0.2 | 0.3 | 48906.6093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3322.5469 | 3322.5469 | 3322.5469 | 3322.5469 | 3322.5469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8550 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16680.166 | 0.2 | 0.3 | 26021.059 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5216.3174 | 5216.3174 | 5216.3174 | 5216.3174 | 5216.3174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8551 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16678.7429 | 0.2 | 0.3 | 26018.8389 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10243.5807 | 10243.5807 | 10243.5807 | 10243.5807 | 10243.5807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8552 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16679.1765 | 0.2 | 0.3 | 26019.5153 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0164 | 5200.0164 | 5200.0164 | 5200.0164 | 5200.0164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8553 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 31355.8588 | 0.2 | 0.3 | 48915.1397 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8554 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16680.0759 | 0.2 | 0.3 | 26020.9185 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8555 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16680.5435 | 0.2 | 0.3 | 26021.6479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8556 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 31351.5007 | 0.2 | 0.3 | 48908.341 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5405.1346 | 5405.1346 | 5405.1346 | 5405.1346 | 5405.1346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8557 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16678.9623 | 0.2 | 0.3 | 26019.1811 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5394.6274 | 5394.6274 | 5394.6274 | 5394.6274 | 5394.6274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8558 | TRIBAL LAND | 90602 | Private | 2030 | 5 | Swales | 66.6667 | 10462.9794 | 0.2 | 0.3 | 16322.2479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6771.04 | 6771.04 | 6771.04 | 6771.04 | 6771.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8559 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 20847.6263 | 0.2 | 0.3 | 32522.2971 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6022 | 5201.6022 | 5201.6022 | 5201.6022 | 5201.6022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8560 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 16703.7827 | 0.2 | 0.3 | 26057.9011 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7268.0573 | 7268.0573 | 7268.0573 | 7268.0573 | 7268.0573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8561 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 25582.9963 | 0.2 | 0.3 | 39909.4743 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9251.07 | 9251.07 | 9251.07 | 9251.07 | 9251.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8562 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5782.6415 | 5782.6415 | 5782.6415 | 5782.6415 | 5782.6415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8563 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 16704.0134 | 0.2 | 0.3 | 26058.2609 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5525.1327 | 5525.1327 | 5525.1327 | 5525.1327 | 5525.1327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8564 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 17872.6851 | 0.2 | 0.3 | 27881.3888 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1043.8403 | 1043.8403 | 1043.8403 | 1043.8403 | 1043.8403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8565 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16681.1409 | 0.2 | 0.3 | 26022.5799 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9093.4226 | 9093.4226 | 9093.4226 | 9093.4226 | 9093.4226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8566 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16681.7408 | 0.2 | 0.3 | 26023.5156 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2996.3731 | 2996.3731 | 2996.3731 | 2996.3731 | 2996.3731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8567 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31385.4027 | 0.2 | 0.3 | 48961.2283 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4991.5162 | 4991.5162 | 4991.5162 | 4991.5162 | 4991.5162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8568 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16682.2584 | 0.2 | 0.3 | 26024.3231 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4277.9263 | 4277.9263 | 4277.9263 | 4277.9263 | 4277.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8569 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16683.1523 | 0.2 | 0.3 | 26025.7175 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5953.366 | 5953.366 | 5953.366 | 5953.366 | 5953.366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8570 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31352.2951 | 0.2 | 0.3 | 48909.5804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12103.1134 | 12103.1134 | 12103.1134 | 12103.1134 | 12103.1134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8571 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4499 | 0.2 | 0.3 | 26019.9419 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4954.3889 | 4954.3889 | 4954.3889 | 4954.3889 | 4954.3889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8572 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31379.0403 | 0.2 | 0.3 | 48951.3029 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5526.4616 | 5526.4616 | 5526.4616 | 5526.4616 | 5526.4616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8573 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16686.3016 | 0.2 | 0.3 | 26030.6305 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13510.0411 | 13510.0411 | 13510.0411 | 13510.0411 | 13510.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8574 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16683.2609 | 0.2 | 0.3 | 26025.887 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3140.6689 | 3140.6689 | 3140.6689 | 3140.6689 | 3140.6689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8575 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 21479.2752 | 0.2 | 0.3 | 33507.6693 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2816.657 | 2816.657 | 2816.657 | 2816.657 | 2816.657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8576 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 10516.8175 | 0.2 | 0.3 | 16406.2354 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3100.864 | 3100.864 | 3100.864 | 3100.864 | 3100.864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8577 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 12334.9911 | 0.2 | 0.3 | 19242.5862 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6272.7445 | 6272.7445 | 6272.7445 | 6272.7445 | 6272.7445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8578 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 10130.3925 | 0.2 | 0.3 | 15803.4122 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5225.9962 | 5225.9962 | 5225.9962 | 5225.9962 | 5225.9962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8579 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 31337.2487 | 0.2 | 0.3 | 48886.108 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5225.8316 | 5225.8316 | 5225.8316 | 5225.8316 | 5225.8316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8580 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16679.8896 | 0.2 | 0.3 | 26020.6278 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12310.1027 | 12310.1027 | 12310.1027 | 12310.1027 | 12310.1027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8581 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16679.8037 | 0.2 | 0.3 | 26020.4938 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8346.4733 | 8346.4733 | 8346.4733 | 8346.4733 | 8346.4733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8582 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16678.6471 | 0.2 | 0.3 | 26018.6895 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3316.033 | 3316.033 | 3316.033 | 3316.033 | 3316.033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8583 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 31375.0103 | 0.2 | 0.3 | 48945.0161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11171.2726 | 11171.2726 | 11171.2726 | 11171.2726 | 11171.2726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8584 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16681.6296 | 0.2 | 0.3 | 26023.3422 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10413.1585 | 10413.1585 | 10413.1585 | 10413.1585 | 10413.1585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8585 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16680.5435 | 0.2 | 0.3 | 26021.6479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5535.2252 | 5535.2252 | 5535.2252 | 5535.2252 | 5535.2252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8586 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 31353.6781 | 0.2 | 0.3 | 48911.7379 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 184.704 | 184.704 | 184.704 | 184.704 | 184.704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8587 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16684.8447 | 0.2 | 0.3 | 26028.3577 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6086.1088 | 6086.1088 | 6086.1088 | 6086.1088 | 6086.1088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8588 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 29324.2601 | 0.2 | 0.3 | 45745.8458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10517.0248 | 10517.0248 | 10517.0248 | 10517.0248 | 10517.0248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8589 | COOPER CITY | 70503 | Private | 2030 | 5 | Swales | 66.6667 | 16678.9031 | 0.2 | 0.3 | 26019.0888 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2237.1735 | 2237.1735 | 2237.1735 | 2237.1735 | 2237.1735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8590 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 16694.0739 | 0.2 | 0.3 | 26042.7553 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10176.309 | 10176.309 | 10176.309 | 10176.309 | 10176.309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8591 | COOPER CITY | 70503 | Public | 2030 | 5 | Swales | 66.6667 | 21298.9374 | 0.2 | 0.3 | 33226.3423 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 769.9719 | 769.9719 | 769.9719 | 769.9719 | 769.9719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8592 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 17424.3329 | 0.2 | 0.3 | 27181.9593 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8294.4306 | 8294.4306 | 8294.4306 | 8294.4306 | 8294.4306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8593 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16677.8779 | 0.2 | 0.3 | 26017.4896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10325.6087 | 10325.6087 | 10325.6087 | 10325.6087 | 10325.6087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8594 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16677.7974 | 0.2 | 0.3 | 26017.3639 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5400.9292 | 5400.9292 | 5400.9292 | 5400.9292 | 5400.9292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8595 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31382.2213 | 0.2 | 0.3 | 48956.2653 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7741.5457 | 7741.5457 | 7741.5457 | 7741.5457 | 7741.5457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8596 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16690.6217 | 0.2 | 0.3 | 26037.3699 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6278.0398 | 6278.0398 | 6278.0398 | 6278.0398 | 6278.0398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8597 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16691.7186 | 0.2 | 0.3 | 26039.081 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 151.3994 | 151.3994 | 151.3994 | 151.3994 | 151.3994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8598 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31355.6357 | 0.2 | 0.3 | 48914.7917 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5279.6032 | 5279.6032 | 5279.6032 | 5279.6032 | 5279.6032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8599 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7043.5796 | 7043.5796 | 7043.5796 | 7043.5796 | 7043.5796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8600 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 31372.1489 | 0.2 | 0.3 | 48940.5522 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10284.2099 | 10284.2099 | 10284.2099 | 10284.2099 | 10284.2099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8601 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16681.0816 | 0.2 | 0.3 | 26022.4873 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12094.6738 | 12094.6738 | 12094.6738 | 12094.6738 | 12094.6738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8602 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 16678.5763 | 0.2 | 0.3 | 26018.5791 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4733.0795 | 4733.0795 | 4733.0795 | 4733.0795 | 4733.0795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8603 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 22047.427 | 0.2 | 0.3 | 34393.9861 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2808.3995 | 2808.3995 | 2808.3995 | 2808.3995 | 2808.3995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8604 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 16680.3428 | 0.2 | 0.3 | 26021.3348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4001.8923 | 4001.8923 | 4001.8923 | 4001.8923 | 4001.8923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8605 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 11306.3496 | 0.2 | 0.3 | 17637.9054 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4466.7343 | 4466.7343 | 4466.7343 | 4466.7343 | 4466.7343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8606 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 6645.8975 | 0.2 | 0.3 | 10367.6 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5257.1421 | 5257.1421 | 5257.1421 | 5257.1421 | 5257.1421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8607 | HOLLYWOOD | 90602 | Public | 2030 | 5 | Swales | 66.6667 | 11606.2847 | 0.2 | 0.3 | 18105.8042 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5222.2286 | 5222.2286 | 5222.2286 | 5222.2286 | 5222.2286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8608 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 10594.0269 | 0.2 | 0.3 | 16526.682 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14184.9454 | 14184.9454 | 14184.9454 | 14184.9454 | 14184.9454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8609 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 8576.8088 | 0.2 | 0.3 | 13379.8217 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11579.8518 | 11579.8518 | 11579.8518 | 11579.8518 | 11579.8518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8610 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 5374.628 | 0.2 | 0.3 | 8384.4197 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6441.7646 | 6441.7646 | 6441.7646 | 6441.7646 | 6441.7646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8611 | HOLLYWOOD | 90601 | Public | 2026 | 5 | Swales | 66.6667 | 3641.5424 | 0.2 | 0.3 | 5680.8061 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3722.7191 | 3722.7191 | 3722.7191 | 3722.7191 | 3722.7191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8612 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 5693.9697 | 0.2 | 0.3 | 8882.5928 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2511.1901 | 2511.1901 | 2511.1901 | 2511.1901 | 2511.1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8613 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 10929.2651 | 0.2 | 0.3 | 17049.6536 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3047.9969 | 3047.9969 | 3047.9969 | 3047.9969 | 3047.9969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8614 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 7721.2545 | 0.2 | 0.3 | 12045.1571 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5546.4562 | 5546.4562 | 5546.4562 | 5546.4562 | 5546.4562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8615 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16695.3159 | 0.2 | 0.3 | 26044.6928 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10273.7914 | 10273.7914 | 10273.7914 | 10273.7914 | 10273.7914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8616 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 24106.8071 | 0.2 | 0.3 | 37606.6191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2353.8167 | 2353.8167 | 2353.8167 | 2353.8167 | 2353.8167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8617 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 15996.0918 | 0.2 | 0.3 | 24953.9032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11007.7605 | 11007.7605 | 11007.7605 | 11007.7605 | 11007.7605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8618 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16685.2794 | 0.2 | 0.3 | 26029.0359 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9683.731 | 9683.731 | 9683.731 | 9683.731 | 9683.731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8619 | HOLLYWOOD | 90700 | Public | 2033 | 5 | Swales | 66.6667 | 42219.9635 | 0.2 | 0.3 | 65863.143 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6951.1021 | 6951.1021 | 6951.1021 | 6951.1021 | 6951.1021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8620 | HOLLYWOOD | 90700 | Public | 2033 | 5 | Swales | 66.6667 | 30792.0774 | 0.2 | 0.3 | 48035.6407 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 568.9753 | 568.9753 | 568.9753 | 568.9753 | 568.9753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8621 | HOLLYWOOD | 90700 | Public | 2033 | 5 | Swales | 66.6667 | 22779.5164 | 0.2 | 0.3 | 35536.0456 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5666.623 | 5666.623 | 5666.623 | 5666.623 | 5666.623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8622 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 25748.6829 | 0.2 | 0.3 | 40167.9454 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1241.7697 | 1241.7697 | 1241.7697 | 1241.7697 | 1241.7697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8623 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 20066.1806 | 0.2 | 0.3 | 31303.2417 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2076.461 | 2076.461 | 2076.461 | 2076.461 | 2076.461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8624 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 23464.7125 | 0.2 | 0.3 | 36604.9514 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1755.0916 | 1755.0916 | 1755.0916 | 1755.0916 | 1755.0916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8625 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 18157.9925 | 0.2 | 0.3 | 28326.4682 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2689.7668 | 2689.7668 | 2689.7668 | 2689.7668 | 2689.7668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8626 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 30902.5437 | 0.2 | 0.3 | 48207.9681 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2513.4638 | 2513.4638 | 2513.4638 | 2513.4638 | 2513.4638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8627 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 16832.7781 | 0.2 | 0.3 | 26259.1338 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 457.1494 | 457.1494 | 457.1494 | 457.1494 | 457.1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8628 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 16683.2775 | 0.2 | 0.3 | 26025.913 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10764.9754 | 10764.9754 | 10764.9754 | 10764.9754 | 10764.9754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8629 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 17462.0219 | 0.2 | 0.3 | 27240.7541 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5508.0154 | 5508.0154 | 5508.0154 | 5508.0154 | 5508.0154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8630 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 13257.3561 | 0.2 | 0.3 | 20681.4755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1757.5923 | 1757.5923 | 1757.5923 | 1757.5923 | 1757.5923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8631 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 19229.8336 | 0.2 | 0.3 | 29998.5404 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4446.476 | 4446.476 | 4446.476 | 4446.476 | 4446.476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8632 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 16682.4573 | 0.2 | 0.3 | 26024.6334 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3725.1165 | 3725.1165 | 3725.1165 | 3725.1165 | 3725.1165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8633 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 10989.8453 | 0.2 | 0.3 | 17144.1587 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11612.512 | 11612.512 | 11612.512 | 11612.512 | 11612.512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8634 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 5788.4493 | 0.2 | 0.3 | 9029.9809 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1776.5334 | 1776.5334 | 1776.5334 | 1776.5334 | 1776.5334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8635 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 17728.9566 | 0.2 | 0.3 | 27657.1723 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3426.9184 | 3426.9184 | 3426.9184 | 3426.9184 | 3426.9184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8636 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 20815.1395 | 0.2 | 0.3 | 32471.6177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2508.3744 | 2508.3744 | 2508.3744 | 2508.3744 | 2508.3744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8637 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 17437.5087 | 0.2 | 0.3 | 27202.5136 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5801.6426 | 5801.6426 | 5801.6426 | 5801.6426 | 5801.6426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8638 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 17076.7143 | 0.2 | 0.3 | 26639.6744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1957.2322 | 1957.2322 | 1957.2322 | 1957.2322 | 1957.2322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8639 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 14165.8911 | 0.2 | 0.3 | 22098.7901 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5493.7138 | 5493.7138 | 5493.7138 | 5493.7138 | 5493.7138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8640 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 27222.6991 | 0.2 | 0.3 | 42467.4106 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4579.7746 | 4579.7746 | 4579.7746 | 4579.7746 | 4579.7746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8641 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 9129.4053 | 0.2 | 0.3 | 14241.8723 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6621.0451 | 6621.0451 | 6621.0451 | 6621.0451 | 6621.0451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8642 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 15252.8473 | 0.2 | 0.3 | 23794.4417 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.8296 | 5203.8296 | 5203.8296 | 5203.8296 | 5203.8296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8643 | HOLLYWOOD | 90700 | Public | 2033 | 5 | Swales | 66.6667 | 16682.1839 | 0.2 | 0.3 | 26024.2069 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8644 | HOLLYWOOD | 90700 | Public | 2033 | 5 | Swales | 66.6667 | 24470.5721 | 0.2 | 0.3 | 38174.0924 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3622.2375 | 3622.2375 | 3622.2375 | 3622.2375 | 3622.2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8645 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 23576.9481 | 0.2 | 0.3 | 36780.0391 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5249.9209 | 5249.9209 | 5249.9209 | 5249.9209 | 5249.9209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8646 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 24480.6039 | 0.2 | 0.3 | 38189.7421 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 566.0354 | 566.0354 | 566.0354 | 566.0354 | 566.0354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8647 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 25450.7933 | 0.2 | 0.3 | 39703.2376 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0729 | 5202.0729 | 5202.0729 | 5202.0729 | 5202.0729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8648 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 16863.9935 | 0.2 | 0.3 | 26307.8299 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1973.6085 | 1973.6085 | 1973.6085 | 1973.6085 | 1973.6085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8649 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 20462.0289 | 0.2 | 0.3 | 31920.7651 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6191.7509 | 6191.7509 | 6191.7509 | 6191.7509 | 6191.7509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8650 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 43831.5242 | 0.2 | 0.3 | 68377.1778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 193.9215 | 193.9215 | 193.9215 | 193.9215 | 193.9215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8651 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 2416.7867 | 0.2 | 0.3 | 3770.1873 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6433.857 | 6433.857 | 6433.857 | 6433.857 | 6433.857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8652 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 16729.0767 | 0.2 | 0.3 | 26097.3597 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9826.6943 | 9826.6943 | 9826.6943 | 9826.6943 | 9826.6943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8653 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 30935.0158 | 0.2 | 0.3 | 48258.6246 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10432.2407 | 10432.2407 | 10432.2407 | 10432.2407 | 10432.2407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8654 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 16729.4825 | 0.2 | 0.3 | 26097.9928 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11663.0162 | 11663.0162 | 11663.0162 | 11663.0162 | 11663.0162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8655 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 23682.9313 | 0.2 | 0.3 | 36945.3728 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10782.6047 | 10782.6047 | 10782.6047 | 10782.6047 | 10782.6047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8656 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 16681.6371 | 0.2 | 0.3 | 26023.3539 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12007.8159 | 12007.8159 | 12007.8159 | 12007.8159 | 12007.8159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8657 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4499 | 0.2 | 0.3 | 26019.9419 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10400.0151 | 10400.0151 | 10400.0151 | 10400.0151 | 10400.0151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8658 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4593 | 0.2 | 0.3 | 26019.9566 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10415.9164 | 10415.9164 | 10415.9164 | 10415.9164 | 10415.9164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8659 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 31365.9841 | 0.2 | 0.3 | 48930.9351 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2769.5766 | 2769.5766 | 2769.5766 | 2769.5766 | 2769.5766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8660 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16683.6013 | 0.2 | 0.3 | 26026.418 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8.4057 | 8.4057 | 8.4057 | 8.4057 | 8.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8661 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16684.7795 | 0.2 | 0.3 | 26028.256 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5310.444 | 5310.444 | 5310.444 | 5310.444 | 5310.444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8662 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16683.0572 | 0.2 | 0.3 | 26025.5692 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8663 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 28106.6436 | 0.2 | 0.3 | 43846.364 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 212.3097 | 212.3097 | 212.3097 | 212.3097 | 212.3097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8664 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 9703.2299 | 0.2 | 0.3 | 15137.0386 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5329.4025 | 5329.4025 | 5329.4025 | 5329.4025 | 5329.4025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8665 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 9706.6211 | 0.2 | 0.3 | 15142.329 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8823.0896 | 8823.0896 | 8823.0896 | 8823.0896 | 8823.0896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8666 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13945.6022 | 13945.6022 | 13945.6022 | 13945.6022 | 13945.6022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8667 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 20045.6227 | 0.2 | 0.3 | 31271.1715 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10402.2719 | 10402.2719 | 10402.2719 | 10402.2719 | 10402.2719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8668 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 27994.8773 | 0.2 | 0.3 | 43672.0086 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5226.3477 | 5226.3477 | 5226.3477 | 5226.3477 | 5226.3477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8669 | PEMBROKE PINES | 110308 | Public | 2036 | 5 | Swales | 66.6667 | 354.5827 | 0.2 | 0.3 | 553.1491 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7545.665 | 7545.665 | 7545.665 | 7545.665 | 7545.665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8670 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 21115.6985 | 0.2 | 0.3 | 32940.4897 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9770.5919 | 9770.5919 | 9770.5919 | 9770.5919 | 9770.5919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8671 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 16002.5049 | 0.2 | 0.3 | 24963.9076 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10646.2432 | 10646.2432 | 10646.2432 | 10646.2432 | 10646.2432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8672 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 10517.846 | 0.2 | 0.3 | 16407.8398 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.375 | 5203.375 | 5203.375 | 5203.375 | 5203.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8673 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 7804.3239 | 0.2 | 0.3 | 12174.7453 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1166 | 5200.1166 | 5200.1166 | 5200.1166 | 5200.1166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8674 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 18864.7603 | 0.2 | 0.3 | 29429.0261 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13746.9879 | 13746.9879 | 13746.9879 | 13746.9879 | 13746.9879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8675 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 27612.6934 | 0.2 | 0.3 | 43075.8017 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9722 | 5199.9722 | 5199.9722 | 5199.9722 | 5199.9722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8676 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 16280.0012 | 0.2 | 0.3 | 25396.8019 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8677 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 18395.5632 | 0.2 | 0.3 | 28697.0786 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8678 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 17797.7149 | 0.2 | 0.3 | 27764.4353 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7664 | 5200.7664 | 5200.7664 | 5200.7664 | 5200.7664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8679 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 24568.0254 | 0.2 | 0.3 | 38326.1196 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5359.7336 | 5359.7336 | 5359.7336 | 5359.7336 | 5359.7336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8680 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 15439.6778 | 0.2 | 0.3 | 24085.8974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.8426 | 2600.8426 | 2600.8426 | 2600.8426 | 2600.8426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8681 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 21197.4233 | 0.2 | 0.3 | 33067.9804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.7573 | 2600.7573 | 2600.7573 | 2600.7573 | 2600.7573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8682 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2216.0715 | 2216.0715 | 2216.0715 | 2216.0715 | 2216.0715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8683 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16680.9208 | 0.2 | 0.3 | 26022.2364 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2985.5117 | 2985.5117 | 2985.5117 | 2985.5117 | 2985.5117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8684 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 31361.7607 | 0.2 | 0.3 | 48924.3466 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 172.885 | 172.885 | 172.885 | 172.885 | 172.885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8685 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16681.1474 | 0.2 | 0.3 | 26022.5899 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5028.6427 | 5028.6427 | 5028.6427 | 5028.6427 | 5028.6427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8686 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9105 | 0.2 | 0.3 | 26023.7804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.5506 | 5205.5506 | 5205.5506 | 5205.5506 | 5205.5506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8687 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9628 | 0.2 | 0.3 | 26023.862 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5519.5746 | 5519.5746 | 5519.5746 | 5519.5746 | 5519.5746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8688 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 31396.9719 | 0.2 | 0.3 | 48979.2761 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5197.1434 | 5197.1434 | 5197.1434 | 5197.1434 | 5197.1434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8689 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 15221.3642 | 0.2 | 0.3 | 23745.3282 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.9051 | 5206.9051 | 5206.9051 | 5206.9051 | 5206.9051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8690 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 8398.4053 | 0.2 | 0.3 | 13101.5122 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1565.539 | 1565.539 | 1565.539 | 1565.539 | 1565.539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8691 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 10605.7849 | 0.2 | 0.3 | 16545.0244 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3839.1442 | 3839.1442 | 3839.1442 | 3839.1442 | 3839.1442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8692 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16681.7813 | 0.2 | 0.3 | 26023.5788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 143.8658 | 143.8658 | 143.8658 | 143.8658 | 143.8658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8693 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 31367.0933 | 0.2 | 0.3 | 48932.6655 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2836.7483 | 2836.7483 | 2836.7483 | 2836.7483 | 2836.7483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8694 | PEMBROKE PINES | 110308 | Public | 2033 | 5 | Swales | 66.6667 | 2311.3871 | 0.2 | 0.3 | 3605.7639 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2366.3716 | 2366.3716 | 2366.3716 | 2366.3716 | 2366.3716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8695 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 36618.5161 | 0.2 | 0.3 | 57124.8852 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1966.5968 | 1966.5968 | 1966.5968 | 1966.5968 | 1966.5968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8696 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 27335.5503 | 0.2 | 0.3 | 42643.4584 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3236.4759 | 3236.4759 | 3236.4759 | 3236.4759 | 3236.4759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8697 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 17685.3951 | 0.2 | 0.3 | 27589.2163 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4.5409 | 4.5409 | 4.5409 | 4.5409 | 4.5409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8698 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 18627.7731 | 0.2 | 0.3 | 29059.3261 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5198.513 | 5198.513 | 5198.513 | 5198.513 | 5198.513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8699 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 29072.9689 | 0.2 | 0.3 | 45353.8315 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5197.7563 | 5197.7563 | 5197.7563 | 5197.7563 | 5197.7563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8700 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 25903.6393 | 0.2 | 0.3 | 40409.6774 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8501.4904 | 8501.4904 | 8501.4904 | 8501.4904 | 8501.4904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8701 | PEMBROKE PINES | 90700 | Private | 2033 | 5 | Swales | 66.6667 | 31025.1595 | 0.2 | 0.3 | 48399.2489 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9935.5328 | 9935.5328 | 9935.5328 | 9935.5328 | 9935.5328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8702 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9274.8007 | 9274.8007 | 9274.8007 | 9274.8007 | 9274.8007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8703 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10408.1473 | 10408.1473 | 10408.1473 | 10408.1473 | 10408.1473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8704 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 31355.9513 | 0.2 | 0.3 | 48915.284 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10404.3471 | 10404.3471 | 10404.3471 | 10404.3471 | 10404.3471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8705 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9977 | 0.2 | 0.3 | 26020.7965 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3248.7982 | 3248.7982 | 3248.7982 | 3248.7982 | 3248.7982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8706 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16680.5435 | 0.2 | 0.3 | 26021.6479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7777.8797 | 7777.8797 | 7777.8797 | 7777.8797 | 7777.8797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8707 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16680.3183 | 0.2 | 0.3 | 26021.2965 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9482.6338 | 9482.6338 | 9482.6338 | 9482.6338 | 9482.6338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8708 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 31391.905 | 0.2 | 0.3 | 48971.3718 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6338.1665 | 6338.1665 | 6338.1665 | 6338.1665 | 6338.1665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8709 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16682.453 | 0.2 | 0.3 | 26024.6267 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1667 | 5203.1667 | 5203.1667 | 5203.1667 | 5203.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8710 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16678.0149 | 0.2 | 0.3 | 26017.7032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7181.6638 | 7181.6638 | 7181.6638 | 7181.6638 | 7181.6638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8711 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 11563.1401 | 0.2 | 0.3 | 18038.4985 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5216.5956 | 5216.5956 | 5216.5956 | 5216.5956 | 5216.5956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8712 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 10151.4311 | 0.2 | 0.3 | 15836.2325 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2541 | 5203.2541 | 5203.2541 | 5203.2541 | 5203.2541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8713 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 31354.577 | 0.2 | 0.3 | 48913.1401 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5518 | 5202.5518 | 5202.5518 | 5202.5518 | 5202.5518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8714 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 9954.695 | 0.2 | 0.3 | 15529.3242 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6941.7198 | 6941.7198 | 6941.7198 | 6941.7198 | 6941.7198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8715 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 16683.2775 | 0.2 | 0.3 | 26025.913 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8225.4958 | 8225.4958 | 8225.4958 | 8225.4958 | 8225.4958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8716 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 20965.2223 | 0.2 | 0.3 | 32705.7467 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.2355 | 5204.2355 | 5204.2355 | 5204.2355 | 5204.2355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8717 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 26784.9715 | 0.2 | 0.3 | 41784.5555 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6053.2103 | 6053.2103 | 6053.2103 | 6053.2103 | 6053.2103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8718 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 34953.6913 | 0.2 | 0.3 | 54527.7584 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8044.2477 | 8044.2477 | 8044.2477 | 8044.2477 | 8044.2477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8719 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 31196.1989 | 0.2 | 0.3 | 48666.0702 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8720 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 27725.661 | 0.2 | 0.3 | 43252.0312 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8721 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 7051.2479 | 0.2 | 0.3 | 10999.9468 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5208.4749 | 5208.4749 | 5208.4749 | 5208.4749 | 5208.4749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8722 | PEMBROKE PINES | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 34922.9823 | 0.2 | 0.3 | 54479.8524 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2858.0282 | 2858.0282 | 2858.0282 | 2858.0282 | 2858.0282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8723 | PEMBROKE PINES | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 1193.2377 | 0.2 | 0.3 | 1861.4508 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.066 | 5203.066 | 5203.066 | 5203.066 | 5203.066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8724 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16684.3711 | 0.2 | 0.3 | 26027.619 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.3724 | 5206.3724 | 5206.3724 | 5206.3724 | 5206.3724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8725 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16684.0977 | 0.2 | 0.3 | 26027.1925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5294.658 | 5294.658 | 5294.658 | 5294.658 | 5294.658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8726 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 31368.3425 | 0.2 | 0.3 | 48934.6142 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7300.3915 | 7300.3915 | 7300.3915 | 7300.3915 | 7300.3915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8727 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4736 | 0.2 | 0.3 | 26019.9788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3906.9227 | 3906.9227 | 3906.9227 | 3906.9227 | 3906.9227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8728 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7742.581 | 7742.581 | 7742.581 | 7742.581 | 7742.581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8729 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.34516 | 0.34516 | 0.34516 | 0.34516 | 0.34516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8730 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 31382.8267 | 0.2 | 0.3 | 48957.2097 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1295 | 5202.1295 | 5202.1295 | 5202.1295 | 5202.1295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8731 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16681.2839 | 0.2 | 0.3 | 26022.8029 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2208.9857 | 2208.9857 | 2208.9857 | 2208.9857 | 2208.9857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8732 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 30473.9419 | 0.2 | 0.3 | 47539.3493 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9097 | 5202.9097 | 5202.9097 | 5202.9097 | 5202.9097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8733 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 11192.7195 | 0.2 | 0.3 | 17460.6425 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5248.4411 | 5248.4411 | 5248.4411 | 5248.4411 | 5248.4411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8734 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 11377.7417 | 0.2 | 0.3 | 17749.277 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4486.8236 | 4486.8236 | 4486.8236 | 4486.8236 | 4486.8236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8735 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 24766.1059 | 0.2 | 0.3 | 38635.1253 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6889.0088 | 6889.0088 | 6889.0088 | 6889.0088 | 6889.0088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8736 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 21090.7919 | 0.2 | 0.3 | 32901.6354 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5208.0336 | 5208.0336 | 5208.0336 | 5208.0336 | 5208.0336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8737 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 16887.8979 | 0.2 | 0.3 | 26345.1208 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6929.4504 | 6929.4504 | 6929.4504 | 6929.4504 | 6929.4504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8738 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 24934.6213 | 0.2 | 0.3 | 38898.0092 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8073.21 | 8073.21 | 8073.21 | 8073.21 | 8073.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8739 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 1812.5447 | 0.2 | 0.3 | 2827.5697 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8740 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 32855.9671 | 0.2 | 0.3 | 51255.3087 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6528.1124 | 6528.1124 | 6528.1124 | 6528.1124 | 6528.1124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8741 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 33294.2819 | 0.2 | 0.3 | 51939.0797 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.4471 | 9779.4471 | 9779.4471 | 9779.4471 | 9779.4471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8742 | PEMBROKE PINES | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 36670.6163 | 0.2 | 0.3 | 57206.1615 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8743 | PEMBROKE PINES | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 6300.3167 | 0.2 | 0.3 | 9828.4941 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2601.1773 | 2601.1773 | 2601.1773 | 2601.1773 | 2601.1773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8744 | PEMBROKE PINES | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 16932.4309 | 0.2 | 0.3 | 26414.5922 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 792.7867 | 792.7867 | 792.7867 | 792.7867 | 792.7867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8745 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16681.6371 | 0.2 | 0.3 | 26023.3539 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4966.9559 | 4966.9559 | 4966.9559 | 4966.9559 | 4966.9559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8746 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9105 | 0.2 | 0.3 | 26023.7804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3352.5185 | 3352.5185 | 3352.5185 | 3352.5185 | 3352.5185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8747 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 31367.8005 | 0.2 | 0.3 | 48933.7687 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 228.1662 | 228.1662 | 228.1662 | 228.1662 | 228.1662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8748 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16681.8992 | 0.2 | 0.3 | 26023.7628 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.963 | 5204.963 | 5204.963 | 5204.963 | 5204.963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8749 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9105 | 0.2 | 0.3 | 26023.7804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.1754 | 5205.1754 | 5205.1754 | 5205.1754 | 5205.1754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8750 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9105 | 0.2 | 0.3 | 26023.7804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 504.3504 | 504.3504 | 504.3504 | 504.3504 | 504.3504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8751 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 28550.3495 | 0.2 | 0.3 | 44538.5452 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 416.1629 | 416.1629 | 416.1629 | 416.1629 | 416.1629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8752 | HOLLYWOOD | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 16677.7031 | 0.2 | 0.3 | 26017.2169 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5596.0649 | 5596.0649 | 5596.0649 | 5596.0649 | 5596.0649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8753 | HOLLYWOOD | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 18339.0345 | 0.2 | 0.3 | 28608.8939 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8255 | 5202.8255 | 5202.8255 | 5202.8255 | 5202.8255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8754 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16685.0455 | 0.2 | 0.3 | 26028.6709 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9799.8348 | 9799.8348 | 9799.8348 | 9799.8348 | 9799.8348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8755 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 11836.6229 | 0.2 | 0.3 | 18465.1317 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6888.7759 | 6888.7759 | 6888.7759 | 6888.7759 | 6888.7759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8756 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 11317.4729 | 0.2 | 0.3 | 17655.2578 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6961.5475 | 6961.5475 | 6961.5475 | 6961.5475 | 6961.5475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8757 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 16685.7381 | 0.2 | 0.3 | 26029.7515 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8012.9403 | 8012.9403 | 8012.9403 | 8012.9403 | 8012.9403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8758 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 11377.6154 | 0.2 | 0.3 | 17749.08 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.9739 | 5206.9739 | 5206.9739 | 5206.9739 | 5206.9739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8759 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 23357.9799 | 0.2 | 0.3 | 36438.4486 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5019 | 5202.5019 | 5202.5019 | 5202.5019 | 5202.5019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8760 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 18964.5647 | 0.2 | 0.3 | 29584.721 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6711.917 | 6711.917 | 6711.917 | 6711.917 | 6711.917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8761 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 30274.4443 | 0.2 | 0.3 | 47228.1332 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8532.6363 | 8532.6363 | 8532.6363 | 8532.6363 | 8532.6363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8762 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 18472.0669 | 0.2 | 0.3 | 28816.4244 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3203.8288 | 3203.8288 | 3203.8288 | 3203.8288 | 3203.8288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8763 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 31613.8948 | 0.2 | 0.3 | 49317.6759 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3551.323 | 3551.323 | 3551.323 | 3551.323 | 3551.323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8764 | PEMBROKE PINES | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 19426.7199 | 0.2 | 0.3 | 30305.683 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4538.7276 | 4538.7276 | 4538.7276 | 4538.7276 | 4538.7276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8765 | PEMBROKE PINES | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 982.0769 | 0.2 | 0.3 | 1532.0399 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4664.6281 | 4664.6281 | 4664.6281 | 4664.6281 | 4664.6281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8766 | PEMBROKE PINES | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 16710.5085 | 0.2 | 0.3 | 26068.3932 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3093.6107 | 3093.6107 | 3093.6107 | 3093.6107 | 3093.6107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8767 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2359 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5761.5923 | 5761.5923 | 5761.5923 | 5761.5923 | 5761.5923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8768 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6624 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10403.3109 | 10403.3109 | 10403.3109 | 10403.3109 | 10403.3109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8769 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 29566.4672 | 0.2 | 0.3 | 46123.6888 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10732.9877 | 10732.9877 | 10732.9877 | 10732.9877 | 10732.9877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8770 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 1920.2805 | 0.2 | 0.3 | 2995.6376 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 692.8883 | 692.8883 | 692.8883 | 692.8883 | 692.8883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8771 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 25885.1882 | 0.2 | 0.3 | 40380.8936 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9046.9883 | 9046.9883 | 9046.9883 | 9046.9883 | 9046.9883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8772 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 31410.5589 | 0.2 | 0.3 | 49000.4718 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8773 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 24.1133 | 0.2 | 0.3 | 37.6168 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6796.6107 | 6796.6107 | 6796.6107 | 6796.6107 | 6796.6107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8774 | PEMBROKE PINES | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 25432.0345 | 0.2 | 0.3 | 39673.9738 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6373.1513 | 6373.1513 | 6373.1513 | 6373.1513 | 6373.1513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8775 | PEMBROKE PINES | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 16688.7806 | 0.2 | 0.3 | 26034.4977 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7888.808 | 7888.808 | 7888.808 | 7888.808 | 7888.808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8776 | PEMBROKE PINES | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 16672.8085 | 0.2 | 0.3 | 26009.5813 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8777 | PEMBROKE PINES | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 19742.1493 | 0.2 | 0.3 | 30797.753 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5246 | 5202.5246 | 5202.5246 | 5202.5246 | 5202.5246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8778 | PEMBROKE PINES | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 19614.3993 | 0.2 | 0.3 | 30598.4629 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6765.9788 | 6765.9788 | 6765.9788 | 6765.9788 | 6765.9788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8779 | PEMBROKE PINES | 90700 | Private | 2026 | 5 | Swales | 66.6667 | 19796.4178 | 0.2 | 0.3 | 30882.4118 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8310.9753 | 8310.9753 | 8310.9753 | 8310.9753 | 8310.9753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8780 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16682.1839 | 0.2 | 0.3 | 26024.2069 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 815.5229 | 815.5229 | 815.5229 | 815.5229 | 815.5229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8781 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 16682.1839 | 0.2 | 0.3 | 26024.2069 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5382.7016 | 5382.7016 | 5382.7016 | 5382.7016 | 5382.7016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8782 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 20653.0694 | 0.2 | 0.3 | 32218.7883 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3442.6163 | 3442.6163 | 3442.6163 | 3442.6163 | 3442.6163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8783 | HOLLYWOOD | 90700 | Public | 2026 | 5 | Swales | 66.6667 | 12151.5529 | 0.2 | 0.3 | 18956.4226 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2722.3445 | 2722.3445 | 2722.3445 | 2722.3445 | 2722.3445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8784 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 18006.4542 | 0.2 | 0.3 | 28090.0686 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5446.6834 | 5446.6834 | 5446.6834 | 5446.6834 | 5446.6834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8785 | PEMBROKE PINES | 90700 | Private | 2036 | 5 | Swales | 66.6667 | 30876.3001 | 0.2 | 0.3 | 48167.0281 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 3.0482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8786 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16676.7531 | 0.2 | 0.3 | 26015.7348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9874 | 5203.9874 | 5203.9874 | 5203.9874 | 5203.9874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8787 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16678.7929 | 0.2 | 0.3 | 26018.917 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4956 | 5202.4956 | 5202.4956 | 5202.4956 | 5202.4956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8788 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16676.8932 | 0.2 | 0.3 | 26015.9534 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9770.9911 | 9770.9911 | 9770.9911 | 9770.9911 | 9770.9911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8789 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16682.4887 | 0.2 | 0.3 | 26024.6823 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8790 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9347 | 0.2 | 0.3 | 26020.6981 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2601.0175 | 2601.0175 | 2601.0175 | 2601.0175 | 2601.0175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8791 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 748.2866 | 748.2866 | 748.2866 | 748.2866 | 748.2866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8792 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.5435 | 0.2 | 0.3 | 26021.6479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 459.5042 | 459.5042 | 459.5042 | 459.5042 | 459.5042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8793 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16682.7307 | 0.2 | 0.3 | 26025.0599 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7314.9111 | 7314.9111 | 7314.9111 | 7314.9111 | 7314.9111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8794 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10220.3856 | 10220.3856 | 10220.3856 | 10220.3856 | 10220.3856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8795 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6624 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4206.1719 | 4206.1719 | 4206.1719 | 4206.1719 | 4206.1719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8796 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 29052.9126 | 0.2 | 0.3 | 45322.5437 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.2857 | 5205.2857 | 5205.2857 | 5205.2857 | 5205.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8797 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16682.2866 | 0.2 | 0.3 | 26024.3671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6528.9508 | 6528.9508 | 6528.9508 | 6528.9508 | 6528.9508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8798 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16682.4573 | 0.2 | 0.3 | 26024.6334 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6604.1839 | 6604.1839 | 6604.1839 | 6604.1839 | 6604.1839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8799 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16682.5614 | 0.2 | 0.3 | 26024.7958 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8800 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 21590.4254 | 0.2 | 0.3 | 33681.0636 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8801 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 24900.6991 | 0.2 | 0.3 | 38845.0905 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.0995 | 5205.0995 | 5205.0995 | 5205.0995 | 5205.0995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8802 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16683.6414 | 0.2 | 0.3 | 26026.4806 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5021.6202 | 5021.6202 | 5021.6202 | 5021.6202 | 5021.6202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8803 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 26342.9321 | 0.2 | 0.3 | 41094.974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8804 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 26930.7979 | 0.2 | 0.3 | 42012.0447 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7077.6809 | 7077.6809 | 7077.6809 | 7077.6809 | 7077.6809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8805 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 4159.106 | 0.2 | 0.3 | 6488.2054 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7114.5672 | 7114.5672 | 7114.5672 | 7114.5672 | 7114.5672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8806 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 17494.5224 | 0.2 | 0.3 | 27291.4549 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6265.5369 | 6265.5369 | 6265.5369 | 6265.5369 | 6265.5369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8807 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 28096.2601 | 0.2 | 0.3 | 43830.1658 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 114.6708 | 114.6708 | 114.6708 | 114.6708 | 114.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8808 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 11699.3706 | 0.2 | 0.3 | 18251.0181 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1139.3748 | 1139.3748 | 1139.3748 | 1139.3748 | 1139.3748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8809 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16684.7544 | 0.2 | 0.3 | 26028.2169 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3128.9367 | 3128.9367 | 3128.9367 | 3128.9367 | 3128.9367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8810 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 15692.2026 | 0.2 | 0.3 | 24479.8361 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5017.6483 | 5017.6483 | 5017.6483 | 5017.6483 | 5017.6483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8811 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2155 | 0.2 | 0.3 | 26021.1361 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9644.758 | 9644.758 | 9644.758 | 9644.758 | 9644.758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8812 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 18372.4109 | 0.2 | 0.3 | 28660.961 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8813 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16678.8208 | 0.2 | 0.3 | 26018.9604 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9834 | 5203.9834 | 5203.9834 | 5203.9834 | 5203.9834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8814 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16678.9031 | 0.2 | 0.3 | 26019.0888 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8815 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 31361.554 | 0.2 | 0.3 | 48924.0242 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9481.1575 | 9481.1575 | 9481.1575 | 9481.1575 | 9481.1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8816 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16679.8263 | 0.2 | 0.3 | 26020.529 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5214.907 | 5214.907 | 5214.907 | 5214.907 | 5214.907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8817 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8028.0811 | 8028.0811 | 8028.0811 | 8028.0811 | 8028.0811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8818 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16681.1856 | 0.2 | 0.3 | 26022.6495 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5639.5619 | 5639.5619 | 5639.5619 | 5639.5619 | 5639.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8819 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 21810.3203 | 0.2 | 0.3 | 34024.0997 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 866.3333 | 866.3333 | 866.3333 | 866.3333 | 866.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8820 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 23548.4879 | 0.2 | 0.3 | 36735.6412 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 207.4386 | 207.4386 | 207.4386 | 207.4386 | 207.4386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8821 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 28134.9761 | 0.2 | 0.3 | 43890.5628 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7514.2097 | 7514.2097 | 7514.2097 | 7514.2097 | 7514.2097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8822 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 31102.7283 | 0.2 | 0.3 | 48520.2562 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1307.0406 | 1307.0406 | 1307.0406 | 1307.0406 | 1307.0406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8823 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 30407.0449 | 0.2 | 0.3 | 47434.99 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4080.5785 | 4080.5785 | 4080.5785 | 4080.5785 | 4080.5785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8824 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 25614.6449 | 0.2 | 0.3 | 39958.846 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5219.4064 | 5219.4064 | 5219.4064 | 5219.4064 | 5219.4064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8825 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16676.6268 | 0.2 | 0.3 | 26015.5378 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0238 | 5201.0238 | 5201.0238 | 5201.0238 | 5201.0238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8826 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16678.6145 | 0.2 | 0.3 | 26018.6386 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5628.5715 | 5628.5715 | 5628.5715 | 5628.5715 | 5628.5715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8827 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16676.5271 | 0.2 | 0.3 | 26015.3823 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8828 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16682.4948 | 0.2 | 0.3 | 26024.6919 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6361.4631 | 6361.4631 | 6361.4631 | 6361.4631 | 6361.4631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8829 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16679.565 | 0.2 | 0.3 | 26020.1214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5219.4279 | 5219.4279 | 5219.4279 | 5219.4279 | 5219.4279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8830 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.1202 | 0.2 | 0.3 | 26020.9875 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8650.1064 | 8650.1064 | 8650.1064 | 8650.1064 | 8650.1064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8831 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.381 | 0.2 | 0.3 | 26021.3944 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7490.1619 | 7490.1619 | 7490.1619 | 7490.1619 | 7490.1619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8832 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16682.0032 | 0.2 | 0.3 | 26023.925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2059.469 | 2059.469 | 2059.469 | 2059.469 | 2059.469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8833 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16679.3523 | 0.2 | 0.3 | 26019.7896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5413.9154 | 5413.9154 | 5413.9154 | 5413.9154 | 5413.9154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8834 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 17286.7988 | 0.2 | 0.3 | 26967.4061 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9738.787 | 9738.787 | 9738.787 | 9738.787 | 9738.787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8835 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 29722.8435 | 0.2 | 0.3 | 46367.6358 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9513.7386 | 9513.7386 | 9513.7386 | 9513.7386 | 9513.7386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8836 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16681.2143 | 0.2 | 0.3 | 26022.6944 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9386.3482 | 9386.3482 | 9386.3482 | 9386.3482 | 9386.3482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8837 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16681.3637 | 0.2 | 0.3 | 26022.9274 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5217.1248 | 5217.1248 | 5217.1248 | 5217.1248 | 5217.1248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8838 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16681.0903 | 0.2 | 0.3 | 26022.5009 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9230.0505 | 9230.0505 | 9230.0505 | 9230.0505 | 9230.0505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8839 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16681.098 | 0.2 | 0.3 | 26022.5129 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1388.0405 | 1388.0405 | 1388.0405 | 1388.0405 | 1388.0405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8840 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 17811.2956 | 0.2 | 0.3 | 27785.6211 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5184.9836 | 5184.9836 | 5184.9836 | 5184.9836 | 5184.9836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8841 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 21872.4524 | 0.2 | 0.3 | 34121.0257 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5756.3532 | 5756.3532 | 5756.3532 | 5756.3532 | 5756.3532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8842 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 19195.748 | 0.2 | 0.3 | 29945.3669 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6965.1053 | 6965.1053 | 6965.1053 | 6965.1053 | 6965.1053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8843 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 27625.1871 | 0.2 | 0.3 | 43095.2918 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1940.8111 | 1940.8111 | 1940.8111 | 1940.8111 | 1940.8111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8844 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 14918.6077 | 0.2 | 0.3 | 23273.028 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8088.9256 | 8088.9256 | 8088.9256 | 8088.9256 | 8088.9256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8845 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16672.8883 | 0.2 | 0.3 | 26009.7057 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8846 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 20955.7003 | 0.2 | 0.3 | 32690.8924 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5216.613 | 5216.613 | 5216.613 | 5216.613 | 5216.613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8847 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 4503.9325 | 0.2 | 0.3 | 7026.1348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9121.1333 | 9121.1333 | 9121.1333 | 9121.1333 | 9121.1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8848 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16703.6787 | 0.2 | 0.3 | 26057.7388 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 820.9646 | 820.9646 | 820.9646 | 820.9646 | 820.9646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8849 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8668 | 0.2 | 0.3 | 26022.1522 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.071739 | 0.071739 | 0.071739 | 0.071739 | 0.071739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8850 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 19405.8996 | 0.2 | 0.3 | 30273.2034 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5077.2955 | 5077.2955 | 5077.2955 | 5077.2955 | 5077.2955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8851 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16683.2165 | 0.2 | 0.3 | 26025.8178 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4564.1295 | 4564.1295 | 4564.1295 | 4564.1295 | 4564.1295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8852 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16683.9746 | 0.2 | 0.3 | 26027.0004 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5918.6354 | 5918.6354 | 5918.6354 | 5918.6354 | 5918.6354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8853 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 22496.5209 | 0.2 | 0.3 | 35094.5727 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 650.7068 | 650.7068 | 650.7068 | 650.7068 | 650.7068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8854 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 31379.0362 | 0.2 | 0.3 | 48951.2965 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5241.4476 | 5241.4476 | 5241.4476 | 5241.4476 | 5241.4476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8855 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 21039.1144 | 0.2 | 0.3 | 32821.0185 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.1953 | 5204.1953 | 5204.1953 | 5204.1953 | 5204.1953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8856 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3796 | 0.2 | 0.3 | 26018.2722 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9796.0485 | 9796.0485 | 9796.0485 | 9796.0485 | 9796.0485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8857 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7947.8542 | 7947.8542 | 7947.8542 | 7947.8542 | 7947.8542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8858 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 31391.0397 | 0.2 | 0.3 | 48970.0219 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5214.4262 | 5214.4262 | 5214.4262 | 5214.4262 | 5214.4262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8859 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16686.3353 | 0.2 | 0.3 | 26030.683 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6047.2521 | 6047.2521 | 6047.2521 | 6047.2521 | 6047.2521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8860 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4444.5059 | 4444.5059 | 4444.5059 | 4444.5059 | 4444.5059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8861 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16687.4621 | 0.2 | 0.3 | 26032.4408 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2587.9541 | 2587.9541 | 2587.9541 | 2587.9541 | 2587.9541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8862 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 15372.6125 | 0.2 | 0.3 | 23981.2756 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 450.5655 | 450.5655 | 450.5655 | 450.5655 | 450.5655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8863 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 24492.8763 | 0.2 | 0.3 | 38208.887 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6349.5388 | 6349.5388 | 6349.5388 | 6349.5388 | 6349.5388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8864 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 19920.9476 | 0.2 | 0.3 | 31076.6783 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4852.6316 | 4852.6316 | 4852.6316 | 4852.6316 | 4852.6316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8865 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 3736.0473 | 0.2 | 0.3 | 5828.2337 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2657.5548 | 2657.5548 | 2657.5548 | 2657.5548 | 2657.5548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8866 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 8524.2675 | 0.2 | 0.3 | 13297.8572 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3150.6503 | 3150.6503 | 3150.6503 | 3150.6503 | 3150.6503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8867 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 15596.8579 | 0.2 | 0.3 | 24331.0983 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4819.6108 | 4819.6108 | 4819.6108 | 4819.6108 | 4819.6108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8868 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31354.4275 | 0.2 | 0.3 | 48912.9068 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.1934 | 5204.1934 | 5204.1934 | 5204.1934 | 5204.1934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8869 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31367.1131 | 0.2 | 0.3 | 48932.6965 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.7258 | 5205.7258 | 5205.7258 | 5205.7258 | 5205.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8870 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31358.5216 | 0.2 | 0.3 | 48919.2937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5252.0648 | 5252.0648 | 5252.0648 | 5252.0648 | 5252.0648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8871 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31366.1783 | 0.2 | 0.3 | 48931.2382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8872 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31386.8849 | 0.2 | 0.3 | 48963.5405 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5227.0419 | 5227.0419 | 5227.0419 | 5227.0419 | 5227.0419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8873 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31357.8826 | 0.2 | 0.3 | 48918.2969 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4042.2536 | 4042.2536 | 4042.2536 | 4042.2536 | 4042.2536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8874 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31356.7076 | 0.2 | 0.3 | 48916.4639 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2488.5629 | 2488.5629 | 2488.5629 | 2488.5629 | 2488.5629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8875 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31359.5343 | 0.2 | 0.3 | 48920.8736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6257.8448 | 6257.8448 | 6257.8448 | 6257.8448 | 6257.8448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8876 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31357.2606 | 0.2 | 0.3 | 48917.3265 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5400.9666 | 5400.9666 | 5400.9666 | 5400.9666 | 5400.9666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8877 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 30752.7613 | 0.2 | 0.3 | 47974.3077 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2408.0974 | 2408.0974 | 2408.0974 | 2408.0974 | 2408.0974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8878 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 29434.9751 | 0.2 | 0.3 | 45918.5611 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.3155 | 5204.3155 | 5204.3155 | 5204.3155 | 5204.3155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8879 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16681.6439 | 0.2 | 0.3 | 26023.3645 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2131.0506 | 2131.0506 | 2131.0506 | 2131.0506 | 2131.0506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8880 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9105 | 0.2 | 0.3 | 26023.7804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6163.7283 | 6163.7283 | 6163.7283 | 6163.7283 | 6163.7283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8881 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9105 | 0.2 | 0.3 | 26023.7804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6158.3321 | 6158.3321 | 6158.3321 | 6158.3321 | 6158.3321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8882 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16682.3168 | 0.2 | 0.3 | 26024.4142 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8823.4506 | 8823.4506 | 8823.4506 | 8823.4506 | 8823.4506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8883 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 18514.7031 | 0.2 | 0.3 | 28882.9368 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9059 | 5201.9059 | 5201.9059 | 5201.9059 | 5201.9059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8884 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16681.2854 | 0.2 | 0.3 | 26022.8052 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5226.9345 | 5226.9345 | 5226.9345 | 5226.9345 | 5226.9345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8885 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9105 | 0.2 | 0.3 | 26023.7804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4898.353 | 4898.353 | 4898.353 | 4898.353 | 4898.353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8886 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16676.7159 | 0.2 | 0.3 | 26015.6768 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5261.9148 | 5261.9148 | 5261.9148 | 5261.9148 | 5261.9148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8887 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6554.8012 | 6554.8012 | 6554.8012 | 6554.8012 | 6554.8012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8888 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16676.9893 | 0.2 | 0.3 | 26016.1033 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 36.1499 | 36.1499 | 36.1499 | 36.1499 | 36.1499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8889 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 18600.3692 | 0.2 | 0.3 | 29016.576 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7975.4611 | 7975.4611 | 7975.4611 | 7975.4611 | 7975.4611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8890 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 29436.2239 | 0.2 | 0.3 | 45920.5093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8891 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.6091 | 5205.6091 | 5205.6091 | 5205.6091 | 5205.6091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8892 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9782.9702 | 9782.9702 | 9782.9702 | 9782.9702 | 9782.9702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8893 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 18760.2811 | 0.2 | 0.3 | 29266.0385 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2442 | 5203.2442 | 5203.2442 | 5203.2442 | 5203.2442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8894 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16682.2835 | 0.2 | 0.3 | 26024.3622 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4679.4398 | 4679.4398 | 4679.4398 | 4679.4398 | 4679.4398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8895 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16682.7307 | 0.2 | 0.3 | 26025.0599 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9800.2256 | 9800.2256 | 9800.2256 | 9800.2256 | 9800.2256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8896 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16682.7758 | 0.2 | 0.3 | 26025.1302 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5333.4177 | 5333.4177 | 5333.4177 | 5333.4177 | 5333.4177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8897 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 31367.1299 | 0.2 | 0.3 | 48932.7227 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9659 | 5201.9659 | 5201.9659 | 5201.9659 | 5201.9659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8898 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16679.8717 | 0.2 | 0.3 | 26020.5998 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5843.9565 | 5843.9565 | 5843.9565 | 5843.9565 | 5843.9565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8899 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7432.033 | 7432.033 | 7432.033 | 7432.033 | 7432.033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8900 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9945 | 0.2 | 0.3 | 26020.7914 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6670.7845 | 6670.7845 | 6670.7845 | 6670.7845 | 6670.7845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8901 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 31358.6543 | 0.2 | 0.3 | 48919.5007 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7725.992 | 7725.992 | 7725.992 | 7725.992 | 7725.992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8902 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2114 | 0.2 | 0.3 | 26021.1298 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5665.6415 | 5665.6415 | 5665.6415 | 5665.6415 | 5665.6415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8903 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 315.6822 | 315.6822 | 315.6822 | 315.6822 | 315.6822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8904 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16681.5913 | 0.2 | 0.3 | 26023.2824 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5504.7579 | 5504.7579 | 5504.7579 | 5504.7579 | 5504.7579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8905 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 18323.1909 | 0.2 | 0.3 | 28584.1778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7822.1523 | 7822.1523 | 7822.1523 | 7822.1523 | 7822.1523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8906 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7880.0386 | 7880.0386 | 7880.0386 | 7880.0386 | 7880.0386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8907 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 24369.1736 | 0.2 | 0.3 | 38015.9108 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8908 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 12942.9556 | 0.2 | 0.3 | 20191.0107 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8909 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 11617.2883 | 0.2 | 0.3 | 18122.9698 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9783.0651 | 9783.0651 | 9783.0651 | 9783.0651 | 9783.0651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8910 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 9728.0285 | 0.2 | 0.3 | 15175.7245 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.7196 | 5205.7196 | 5205.7196 | 5205.7196 | 5205.7196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8911 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5211.3449 | 5211.3449 | 5211.3449 | 5211.3449 | 5211.3449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8912 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.89608 | 0.89608 | 0.89608 | 0.89608 | 0.89608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8913 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.5435 | 0.2 | 0.3 | 26021.6479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8275.7159 | 8275.7159 | 8275.7159 | 8275.7159 | 8275.7159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8914 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9588.8451 | 9588.8451 | 9588.8451 | 9588.8451 | 9588.8451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8915 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4499 | 0.2 | 0.3 | 26019.9419 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2313.9753 | 2313.9753 | 2313.9753 | 2313.9753 | 2313.9753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8916 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6188.1715 | 6188.1715 | 6188.1715 | 6188.1715 | 6188.1715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8917 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16677.8095 | 0.2 | 0.3 | 26017.3828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5430.6649 | 5430.6649 | 5430.6649 | 5430.6649 | 5430.6649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8918 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 295.7527 | 295.7527 | 295.7527 | 295.7527 | 295.7527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8919 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16675.0755 | 0.2 | 0.3 | 26013.1177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5559.8078 | 5559.8078 | 5559.8078 | 5559.8078 | 5559.8078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8920 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5295.0671 | 5295.0671 | 5295.0671 | 5295.0671 | 5295.0671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8921 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 26838.5113 | 0.2 | 0.3 | 41868.0776 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11258.7454 | 11258.7454 | 11258.7454 | 11258.7454 | 11258.7454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8922 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16681.0759 | 0.2 | 0.3 | 26022.4785 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7700.2536 | 7700.2536 | 7700.2536 | 7700.2536 | 7700.2536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8923 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16681.3637 | 0.2 | 0.3 | 26022.9274 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8924 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16681.3637 | 0.2 | 0.3 | 26022.9274 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8925 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16682.2695 | 0.2 | 0.3 | 26024.3404 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9782.989 | 9782.989 | 9782.989 | 9782.989 | 9782.989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8926 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 19166.0477 | 0.2 | 0.3 | 29899.0345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.6805 | 5205.6805 | 5205.6805 | 5205.6805 | 5205.6805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8927 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16681.3412 | 0.2 | 0.3 | 26022.8923 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7134.7349 | 7134.7349 | 7134.7349 | 7134.7349 | 7134.7349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8928 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16681.847 | 0.2 | 0.3 | 26023.6813 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5549.5754 | 5549.5754 | 5549.5754 | 5549.5754 | 5549.5754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8929 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16676.5397 | 0.2 | 0.3 | 26015.402 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4295.9418 | 4295.9418 | 4295.9418 | 4295.9418 | 4295.9418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8930 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16676.1531 | 0.2 | 0.3 | 26014.7989 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7051.866 | 7051.866 | 7051.866 | 7051.866 | 7051.866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8931 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 17627.4499 | 0.2 | 0.3 | 27498.8219 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5350.8432 | 5350.8432 | 5350.8432 | 5350.8432 | 5350.8432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8932 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 17936.8024 | 0.2 | 0.3 | 27981.4117 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5771.9905 | 5771.9905 | 5771.9905 | 5771.9905 | 5771.9905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8933 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 25146.2978 | 0.2 | 0.3 | 39228.2246 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1197.125 | 1197.125 | 1197.125 | 1197.125 | 1197.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8934 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 24615.4618 | 0.2 | 0.3 | 38400.1204 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1301.6067 | 1301.6067 | 1301.6067 | 1301.6067 | 1301.6067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8935 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16666.5449 | 0.2 | 0.3 | 25999.81 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11928.9155 | 11928.9155 | 11928.9155 | 11928.9155 | 11928.9155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8936 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16680.5435 | 0.2 | 0.3 | 26021.6479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4927.4457 | 4927.4457 | 4927.4457 | 4927.4457 | 4927.4457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8937 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16681.8089 | 0.2 | 0.3 | 26023.6219 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12009.3377 | 12009.3377 | 12009.3377 | 12009.3377 | 12009.3377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8938 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 31400.6285 | 0.2 | 0.3 | 48984.9805 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13241.2243 | 13241.2243 | 13241.2243 | 13241.2243 | 13241.2243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8939 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16686.5051 | 0.2 | 0.3 | 26030.9479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7617.4631 | 7617.4631 | 7617.4631 | 7617.4631 | 7617.4631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8940 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.2111 | 5204.2111 | 5204.2111 | 5204.2111 | 5204.2111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8941 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16681.1293 | 0.2 | 0.3 | 26022.5617 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8942 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 31398.7043 | 0.2 | 0.3 | 48981.9788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9782.2231 | 9782.2231 | 9782.2231 | 9782.2231 | 9782.2231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8943 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16687.7531 | 0.2 | 0.3 | 26032.8948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.048 | 5206.048 | 5206.048 | 5206.048 | 5206.048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8944 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6169.5739 | 6169.5739 | 6169.5739 | 6169.5739 | 6169.5739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8945 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16683.6817 | 0.2 | 0.3 | 26026.5434 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1324.8218 | 1324.8218 | 1324.8218 | 1324.8218 | 1324.8218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8946 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 3886.7562 | 0.2 | 0.3 | 6063.3397 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4352.5029 | 4352.5029 | 4352.5029 | 4352.5029 | 4352.5029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8947 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16679.5007 | 0.2 | 0.3 | 26020.021 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6264.336 | 6264.336 | 6264.336 | 6264.336 | 6264.336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8948 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 23805.25 | 0.2 | 0.3 | 37136.19 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9524.748 | 9524.748 | 9524.748 | 9524.748 | 9524.748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8949 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3136 | 0.2 | 0.3 | 26018.1692 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7509.9412 | 7509.9412 | 7509.9412 | 7509.9412 | 7509.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8950 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 13218.4461 | 0.2 | 0.3 | 20620.776 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0098 | 5204.0098 | 5204.0098 | 5204.0098 | 5204.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8951 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 8034.6141 | 0.2 | 0.3 | 12533.998 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 5204.5002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8952 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 29655.4242 | 0.2 | 0.3 | 46262.4618 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9781.8495 | 9781.8495 | 9781.8495 | 9781.8495 | 9781.8495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8953 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31366.6722 | 0.2 | 0.3 | 48932.0086 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.9545 | 5204.9545 | 5204.9545 | 5204.9545 | 5204.9545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8954 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31358.0846 | 0.2 | 0.3 | 48918.612 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6199.4022 | 6199.4022 | 6199.4022 | 6199.4022 | 6199.4022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8955 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31356.8691 | 0.2 | 0.3 | 48916.7157 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5252.6993 | 5252.6993 | 5252.6993 | 5252.6993 | 5252.6993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8956 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31370.2799 | 0.2 | 0.3 | 48937.6366 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5216.4232 | 5216.4232 | 5216.4232 | 5216.4232 | 5216.4232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8957 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31369.6459 | 0.2 | 0.3 | 48936.6476 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5627.6782 | 5627.6782 | 5627.6782 | 5627.6782 | 5627.6782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8958 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 27278.1513 | 0.2 | 0.3 | 42553.916 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5349.4506 | 5349.4506 | 5349.4506 | 5349.4506 | 5349.4506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8959 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 26712.9992 | 0.2 | 0.3 | 41672.2788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6404.036 | 6404.036 | 6404.036 | 6404.036 | 6404.036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8960 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 25914.4998 | 0.2 | 0.3 | 40426.6197 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5088.3787 | 5088.3787 | 5088.3787 | 5088.3787 | 5088.3787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8961 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 25260.6305 | 0.2 | 0.3 | 39406.5836 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1922.4829 | 1922.4829 | 1922.4829 | 1922.4829 | 1922.4829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8962 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31361.3445 | 0.2 | 0.3 | 48923.6974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3032.1341 | 3032.1341 | 3032.1341 | 3032.1341 | 3032.1341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8963 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.0166 | 0.2 | 0.3 | 26020.8259 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5173.9888 | 5173.9888 | 5173.9888 | 5173.9888 | 5173.9888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8964 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9781.3219 | 9781.3219 | 9781.3219 | 9781.3219 | 9781.3219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8965 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.2118 | 5204.2118 | 5204.2118 | 5204.2118 | 5204.2118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8966 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8477 | 0.2 | 0.3 | 26022.1224 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7678 | 5203.7678 | 5203.7678 | 5203.7678 | 5203.7678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8967 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31366.8311 | 0.2 | 0.3 | 48932.2566 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8968 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 20273.9396 | 0.2 | 0.3 | 31627.3458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9783.0279 | 9783.0279 | 9783.0279 | 9783.0279 | 9783.0279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8969 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 19516.8305 | 0.2 | 0.3 | 30446.2556 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.1837 | 5204.1837 | 5204.1837 | 5204.1837 | 5204.1837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8970 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31366.4153 | 0.2 | 0.3 | 48931.6078 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8971 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 18353.8753 | 0.2 | 0.3 | 28632.0454 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9781.6682 | 9781.6682 | 9781.6682 | 9781.6682 | 9781.6682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8972 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.8362 | 5203.8362 | 5203.8362 | 5203.8362 | 5203.8362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8973 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16674.143 | 0.2 | 0.3 | 26011.6631 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3264.4496 | 3264.4496 | 3264.4496 | 3264.4496 | 3264.4496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8974 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 30396.6188 | 0.2 | 0.3 | 47418.7253 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6504.4594 | 6504.4594 | 6504.4594 | 6504.4594 | 6504.4594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8975 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 19107.3084 | 0.2 | 0.3 | 29807.4011 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5211.5802 | 5211.5802 | 5211.5802 | 5211.5802 | 5211.5802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8976 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16680.5839 | 0.2 | 0.3 | 26021.7108 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7981.8949 | 7981.8949 | 7981.8949 | 7981.8949 | 7981.8949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8977 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8978 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16681.4572 | 0.2 | 0.3 | 26023.0732 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5211.6522 | 5211.6522 | 5211.6522 | 5211.6522 | 5211.6522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8979 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 21669.4515 | 0.2 | 0.3 | 33804.3443 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3281.2471 | 3281.2471 | 3281.2471 | 3281.2471 | 3281.2471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8980 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 31361.7869 | 0.2 | 0.3 | 48924.3876 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3848.5172 | 3848.5172 | 3848.5172 | 3848.5172 | 3848.5172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8981 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16682.4278 | 0.2 | 0.3 | 26024.5874 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3160.6824 | 3160.6824 | 3160.6824 | 3160.6824 | 3160.6824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8982 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16683.0857 | 0.2 | 0.3 | 26025.6137 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.2216 | 9777.2216 | 9777.2216 | 9777.2216 | 9777.2216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8983 | PEMBROKE PINES | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 24400.6343 | 0.2 | 0.3 | 38064.9895 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.1256 | 5204.1256 | 5204.1256 | 5204.1256 | 5204.1256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8984 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 31403.5854 | 0.2 | 0.3 | 48989.5932 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0988 | 5204.0988 | 5204.0988 | 5204.0988 | 5204.0988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8985 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16683.4842 | 0.2 | 0.3 | 26026.2354 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7379 | 5203.7379 | 5203.7379 | 5203.7379 | 5203.7379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8986 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16684.6445 | 0.2 | 0.3 | 26028.0455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9789.0032 | 9789.0032 | 9789.0032 | 9789.0032 | 9789.0032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8987 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 27285.8543 | 0.2 | 0.3 | 42565.9327 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.6684 | 5204.6684 | 5204.6684 | 5204.6684 | 5204.6684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8988 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 27852.5948 | 0.2 | 0.3 | 43450.0479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8989 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 31361.771 | 0.2 | 0.3 | 48924.3628 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9782.3476 | 9782.3476 | 9782.3476 | 9782.3476 | 9782.3476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8990 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 31356.6884 | 0.2 | 0.3 | 48916.4339 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.6715 | 5205.6715 | 5205.6715 | 5205.6715 | 5205.6715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8991 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 21052.5848 | 0.2 | 0.3 | 32842.0323 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9149.1692 | 9149.1692 | 9149.1692 | 9149.1692 | 9149.1692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8992 | HOLLYWOOD | 91300 | Private | 2026 | 5 | Swales | 66.6667 | 35695.0112 | 0.2 | 0.3 | 55684.2175 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8993 | HOLLYWOOD | 91300 | Private | 2026 | 5 | Swales | 66.6667 | 21131.3655 | 0.2 | 0.3 | 32964.9301 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5208.5511 | 5208.5511 | 5208.5511 | 5208.5511 | 5208.5511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8994 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 18383.927 | 0.2 | 0.3 | 28678.9261 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6645.2685 | 6645.2685 | 6645.2685 | 6645.2685 | 6645.2685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8995 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.1371 | 0.2 | 0.3 | 26021.0139 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.267 | 5204.267 | 5204.267 | 5204.267 | 5204.267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8996 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16678.9001 | 0.2 | 0.3 | 26019.0842 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3527.5811 | 3527.5811 | 3527.5811 | 3527.5811 | 3527.5811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8997 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2739 | 0.2 | 0.3 | 26021.2272 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2073.52 | 2073.52 | 2073.52 | 2073.52 | 2073.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8998 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16679.6914 | 0.2 | 0.3 | 26020.3186 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3621.1608 | 3621.1608 | 3621.1608 | 3621.1608 | 3621.1608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8999 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16675.3883 | 0.2 | 0.3 | 26013.6057 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5307 | 5202.5307 | 5202.5307 | 5202.5307 | 5202.5307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9000 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 18734.1089 | 0.2 | 0.3 | 29225.2099 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.707 | 5202.707 | 5202.707 | 5202.707 | 5202.707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9001 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9002 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4499 | 0.2 | 0.3 | 26019.9419 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8978 | 5202.8978 | 5202.8978 | 5202.8978 | 5202.8978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9003 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16679.1765 | 0.2 | 0.3 | 26019.5154 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.0917 | 5203.0917 | 5203.0917 | 5203.0917 | 5203.0917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9004 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 24908.6181 | 0.2 | 0.3 | 38857.4443 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1662 | 5202.1662 | 5202.1662 | 5202.1662 | 5202.1662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9005 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31364.2723 | 0.2 | 0.3 | 48928.2647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9006 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16683.0041 | 0.2 | 0.3 | 26025.4864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8125.4266 | 8125.4266 | 8125.4266 | 8125.4266 | 8125.4266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9007 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16682.9054 | 0.2 | 0.3 | 26025.3324 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7361 | 5203.7361 | 5203.7361 | 5203.7361 | 5203.7361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9008 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31360.3892 | 0.2 | 0.3 | 48922.2072 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9842 | 5203.9842 | 5203.9842 | 5203.9842 | 5203.9842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9009 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8953.0172 | 8953.0172 | 8953.0172 | 8953.0172 | 8953.0172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9010 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16676.5571 | 0.2 | 0.3 | 26015.429 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6736 | 5202.6736 | 5202.6736 | 5202.6736 | 5202.6736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9011 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16676.7434 | 0.2 | 0.3 | 26015.7197 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8953.5621 | 8953.5621 | 8953.5621 | 8953.5621 | 8953.5621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9012 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31362.0659 | 0.2 | 0.3 | 48924.8229 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9837 | 5200.9837 | 5200.9837 | 5200.9837 | 5200.9837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9013 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16540.7883 | 0.2 | 0.3 | 25803.6298 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6291.0178 | 6291.0178 | 6291.0178 | 6291.0178 | 6291.0178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9014 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16319.2819 | 0.2 | 0.3 | 25458.0797 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7423 | 5202.7423 | 5202.7423 | 5202.7423 | 5202.7423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9015 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16905.2444 | 0.2 | 0.3 | 26372.1813 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8741.7965 | 8741.7965 | 8741.7965 | 8741.7965 | 8741.7965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9016 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16683.5509 | 0.2 | 0.3 | 26026.3395 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2974 | 5203.2974 | 5203.2974 | 5203.2974 | 5203.2974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9017 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16683.3708 | 0.2 | 0.3 | 26026.0584 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9000.0712 | 9000.0712 | 9000.0712 | 9000.0712 | 9000.0712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9018 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 26620.9864 | 0.2 | 0.3 | 41528.7388 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9019 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 20845.9594 | 0.2 | 0.3 | 32519.6967 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8949.2371 | 8949.2371 | 8949.2371 | 8949.2371 | 8949.2371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9020 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16682.5797 | 0.2 | 0.3 | 26024.8243 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9021 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16682.9957 | 0.2 | 0.3 | 26025.4732 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8952.1148 | 8952.1148 | 8952.1148 | 8952.1148 | 8952.1148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9022 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 24753.0902 | 0.2 | 0.3 | 38614.8207 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5275.9279 | 5275.9279 | 5275.9279 | 5275.9279 | 5275.9279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9023 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 21403.2078 | 0.2 | 0.3 | 33389.0042 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.555 | 5199.555 | 5199.555 | 5199.555 | 5199.555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9024 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16686.8061 | 0.2 | 0.3 | 26031.4175 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8706.3598 | 8706.3598 | 8706.3598 | 8706.3598 | 8706.3598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9025 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6291.8227 | 6291.8227 | 6291.8227 | 6291.8227 | 6291.8227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9026 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 25637.8961 | 0.2 | 0.3 | 39995.118 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9027 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16681.7339 | 0.2 | 0.3 | 26023.5048 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8430.4445 | 8430.4445 | 8430.4445 | 8430.4445 | 8430.4445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9028 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.1636 | 0.2 | 0.3 | 26021.0552 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8933.1635 | 8933.1635 | 8933.1635 | 8933.1635 | 8933.1635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9029 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 22349.6904 | 0.2 | 0.3 | 34865.517 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7235.3081 | 7235.3081 | 7235.3081 | 7235.3081 | 7235.3081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9030 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.4075 | 0.2 | 0.3 | 26021.4356 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9031 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16681.7676 | 0.2 | 0.3 | 26023.5575 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.2914 | 5204.2914 | 5204.2914 | 5204.2914 | 5204.2914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9032 | HOLLYWOOD | 91300 | Private | 2026 | 5 | Swales | 66.6667 | 20012.379 | 0.2 | 0.3 | 31219.3112 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3679.7106 | 3679.7106 | 3679.7106 | 3679.7106 | 3679.7106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9033 | HOLLYWOOD | 91300 | Private | 2026 | 5 | Swales | 66.6667 | 16680.8814 | 0.2 | 0.3 | 26022.175 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5791.0455 | 5791.0455 | 5791.0455 | 5791.0455 | 5791.0455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9034 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16685.5895 | 0.2 | 0.3 | 26029.5197 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6047.8037 | 6047.8037 | 6047.8037 | 6047.8037 | 6047.8037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9035 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.0235 | 0.2 | 0.3 | 26020.8367 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6208.8366 | 6208.8366 | 6208.8366 | 6208.8366 | 6208.8366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9036 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16678.5749 | 0.2 | 0.3 | 26018.5768 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9787.0382 | 9787.0382 | 9787.0382 | 9787.0382 | 9787.0382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9037 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16679.6605 | 0.2 | 0.3 | 26020.2703 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.2994 | 5206.2994 | 5206.2994 | 5206.2994 | 5206.2994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9038 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16679.8029 | 0.2 | 0.3 | 26020.4925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7916 | 5203.7916 | 5203.7916 | 5203.7916 | 5203.7916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9039 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16672.2177 | 0.2 | 0.3 | 26008.6597 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2418 | 5203.2418 | 5203.2418 | 5203.2418 | 5203.2418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9040 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16686.0981 | 0.2 | 0.3 | 26030.313 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.121 | 5204.121 | 5204.121 | 5204.121 | 5204.121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9041 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 26798.8033 | 0.2 | 0.3 | 41806.1331 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5239 | 5203.5239 | 5203.5239 | 5203.5239 | 5203.5239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9042 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16682.7307 | 0.2 | 0.3 | 26025.0599 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.892 | 5203.892 | 5203.892 | 5203.892 | 5203.892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9043 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16682.7064 | 0.2 | 0.3 | 26025.022 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5481.5769 | 5481.5769 | 5481.5769 | 5481.5769 | 5481.5769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9044 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31354.4091 | 0.2 | 0.3 | 48912.8782 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.6275 | 5203.6275 | 5203.6275 | 5203.6275 | 5203.6275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9045 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16676.9893 | 0.2 | 0.3 | 26016.1033 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9046 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16676.1968 | 0.2 | 0.3 | 26014.867 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0462 | 5204.0462 | 5204.0462 | 5204.0462 | 5204.0462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9047 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16676.0359 | 0.2 | 0.3 | 26014.616 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7353 | 5203.7353 | 5203.7353 | 5203.7353 | 5203.7353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9048 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31360.0057 | 0.2 | 0.3 | 48921.6088 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9049 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 3260.3858 | 0.2 | 0.3 | 5086.2018 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4838.2821 | 4838.2821 | 4838.2821 | 4838.2821 | 4838.2821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9050 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 9457.5675 | 0.2 | 0.3 | 14753.8052 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5265.4419 | 5265.4419 | 5265.4419 | 5265.4419 | 5265.4419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9051 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16198.154 | 0.2 | 0.3 | 25269.1202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7930.3331 | 7930.3331 | 7930.3331 | 7930.3331 | 7930.3331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9052 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 23275.3326 | 0.2 | 0.3 | 36309.5189 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9784.2062 | 9784.2062 | 9784.2062 | 9784.2062 | 9784.2062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9053 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5514.5028 | 5514.5028 | 5514.5028 | 5514.5028 | 5514.5028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9054 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16681.2196 | 0.2 | 0.3 | 26022.7026 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9516 | 5203.9516 | 5203.9516 | 5203.9516 | 5203.9516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9055 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 27363.7823 | 0.2 | 0.3 | 42687.5004 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1772.1902 | 1772.1902 | 1772.1902 | 1772.1902 | 1772.1902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9056 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 20114.3758 | 0.2 | 0.3 | 31378.4262 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6677.3752 | 6677.3752 | 6677.3752 | 6677.3752 | 6677.3752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9057 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16682.801 | 0.2 | 0.3 | 26025.1696 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.6741 | 5204.6741 | 5204.6741 | 5204.6741 | 5204.6741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9058 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16683.0041 | 0.2 | 0.3 | 26025.4864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9059 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 25495.5955 | 0.2 | 0.3 | 39773.1289 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9785.2649 | 9785.2649 | 9785.2649 | 9785.2649 | 9785.2649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9060 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 22357.352 | 0.2 | 0.3 | 34877.4691 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.3059 | 5205.3059 | 5205.3059 | 5205.3059 | 5205.3059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9061 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.7276 | 0.2 | 0.3 | 26021.9351 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7599.5063 | 7599.5063 | 7599.5063 | 7599.5063 | 7599.5063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9062 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16681.0903 | 0.2 | 0.3 | 26022.5009 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.002 | 5203.002 | 5203.002 | 5203.002 | 5203.002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9063 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 26461.8069 | 0.2 | 0.3 | 41280.4188 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9644.7054 | 9644.7054 | 9644.7054 | 9644.7054 | 9644.7054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9064 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16681.6371 | 0.2 | 0.3 | 26023.3539 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4373 | 5202.4373 | 5202.4373 | 5202.4373 | 5202.4373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9065 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9066 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 21638.2113 | 0.2 | 0.3 | 33755.6096 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8551.2055 | 8551.2055 | 8551.2055 | 8551.2055 | 8551.2055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9067 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.021 | 0.2 | 0.3 | 26020.8328 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6440.2537 | 6440.2537 | 6440.2537 | 6440.2537 | 6440.2537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9068 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.0925 | 5203.0925 | 5203.0925 | 5203.0925 | 5203.0925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9069 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16681.0903 | 0.2 | 0.3 | 26022.5009 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10662.1958 | 10662.1958 | 10662.1958 | 10662.1958 | 10662.1958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9070 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.7719 | 0.2 | 0.3 | 26022.0042 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9.2954 | 9.2954 | 9.2954 | 9.2954 | 9.2954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9071 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31363.8217 | 0.2 | 0.3 | 48927.5619 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.5515 | 5204.5515 | 5204.5515 | 5204.5515 | 5204.5515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9072 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31358.4873 | 0.2 | 0.3 | 48919.2401 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9073 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31360.7273 | 0.2 | 0.3 | 48922.7346 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9785.3333 | 9785.3333 | 9785.3333 | 9785.3333 | 9785.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9074 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31361.3849 | 0.2 | 0.3 | 48923.7605 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.8821 | 5204.8821 | 5204.8821 | 5204.8821 | 5204.8821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9075 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31369.9563 | 0.2 | 0.3 | 48937.1319 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.1826 | 5205.1826 | 5205.1826 | 5205.1826 | 5205.1826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9076 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 22720.3682 | 0.2 | 0.3 | 35443.7744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.3148 | 5205.3148 | 5205.3148 | 5205.3148 | 5205.3148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9077 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16681.105 | 0.2 | 0.3 | 26022.5238 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9782.4532 | 9782.4532 | 9782.4532 | 9782.4532 | 9782.4532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9078 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 26136.7921 | 0.2 | 0.3 | 40773.3957 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.1624 | 5205.1624 | 5205.1624 | 5205.1624 | 5205.1624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9079 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.1633 | 0.2 | 0.3 | 26021.0548 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9080 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16680.0421 | 0.2 | 0.3 | 26020.8656 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7420.1968 | 7420.1968 | 7420.1968 | 7420.1968 | 7420.1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9081 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31359.8397 | 0.2 | 0.3 | 48921.35 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7568.9079 | 7568.9079 | 7568.9079 | 7568.9079 | 7568.9079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9082 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4499 | 0.2 | 0.3 | 26019.9419 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.4876 | 5204.4876 | 5204.4876 | 5204.4876 | 5204.4876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9083 | HOLLYWOOD | 91201 | Public | 2030 | 5 | Swales | 66.6667 | 16674.778 | 0.2 | 0.3 | 26012.6537 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5314.8057 | 5314.8057 | 5314.8057 | 5314.8057 | 5314.8057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9084 | HOLLYWOOD | 91201 | Public | 2030 | 5 | Swales | 66.6667 | 16675.343 | 0.2 | 0.3 | 26013.5351 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8363.7635 | 8363.7635 | 8363.7635 | 8363.7635 | 8363.7635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9085 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31367.3627 | 0.2 | 0.3 | 48933.0859 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5213.5183 | 5213.5183 | 5213.5183 | 5213.5183 | 5213.5183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9086 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 5140.1255 | 0.2 | 0.3 | 8018.5958 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1926.5148 | 1926.5148 | 1926.5148 | 1926.5148 | 1926.5148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9087 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 5096.9563 | 0.2 | 0.3 | 7951.2519 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.7559 | 5205.7559 | 5205.7559 | 5205.7559 | 5205.7559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9088 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 31498.2181 | 0.2 | 0.3 | 49137.2203 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.9503 | 5205.9503 | 5205.9503 | 5205.9503 | 5205.9503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9089 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 23975.5185 | 0.2 | 0.3 | 37401.8089 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9784.6988 | 9784.6988 | 9784.6988 | 9784.6988 | 9784.6988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9090 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16682.4573 | 0.2 | 0.3 | 26024.6334 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.5133 | 5204.5133 | 5204.5133 | 5204.5133 | 5204.5133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9091 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16683.0041 | 0.2 | 0.3 | 26025.4864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 5204.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9092 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 26205.3366 | 0.2 | 0.3 | 40880.3251 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.631 | 5204.631 | 5204.631 | 5204.631 | 5204.631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9093 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 31376.4303 | 0.2 | 0.3 | 48947.2312 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9784.8535 | 9784.8535 | 9784.8535 | 9784.8535 | 9784.8535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9094 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16686.8181 | 0.2 | 0.3 | 26031.4363 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.5447 | 5204.5447 | 5204.5447 | 5204.5447 | 5204.5447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9095 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16681.6371 | 0.2 | 0.3 | 26023.3539 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 5204.5855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9096 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 26002.1037 | 0.2 | 0.3 | 40563.2817 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5507.443 | 5507.443 | 5507.443 | 5507.443 | 5507.443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9097 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 21604.1613 | 0.2 | 0.3 | 33702.4917 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9473.8991 | 9473.8991 | 9473.8991 | 9473.8991 | 9473.8991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9098 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.7338 | 0.2 | 0.3 | 26021.9447 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5207.4173 | 5207.4173 | 5207.4173 | 5207.4173 | 5207.4173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9099 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3622.0533 | 3622.0533 | 3622.0533 | 3622.0533 | 3622.0533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9100 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 27107.3493 | 0.2 | 0.3 | 42287.4649 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2668.3313 | 2668.3313 | 2668.3313 | 2668.3313 | 2668.3313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9101 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9105 | 0.2 | 0.3 | 26023.7804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.6638 | 5205.6638 | 5205.6638 | 5205.6638 | 5205.6638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9102 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.865 | 5205.865 | 5205.865 | 5205.865 | 5205.865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9103 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 20725.7727 | 0.2 | 0.3 | 32332.2054 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9783.4756 | 9783.4756 | 9783.4756 | 9783.4756 | 9783.4756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9104 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16684.1904 | 0.2 | 0.3 | 26027.337 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.2115 | 5204.2115 | 5204.2115 | 5204.2115 | 5204.2115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9105 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 14563.7257 | 0.2 | 0.3 | 22719.4121 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9106 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4241 | 0.2 | 0.3 | 26019.9015 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.4736 | 5204.4736 | 5204.4736 | 5204.4736 | 5204.4736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9107 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9784.9782 | 9784.9782 | 9784.9782 | 9784.9782 | 9784.9782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9108 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4499 | 0.2 | 0.3 | 26019.9419 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.7344 | 5204.7344 | 5204.7344 | 5204.7344 | 5204.7344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9109 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9110 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.2802 | 5205.2802 | 5205.2802 | 5205.2802 | 5205.2802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9111 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16685.7381 | 0.2 | 0.3 | 26029.7515 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5286.9459 | 5286.9459 | 5286.9459 | 5286.9459 | 5286.9459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9112 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16682.2119 | 0.2 | 0.3 | 26024.2506 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3462.2868 | 3462.2868 | 3462.2868 | 3462.2868 | 3462.2868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9113 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 25422.0146 | 0.2 | 0.3 | 39658.3428 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9114 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16683.0167 | 0.2 | 0.3 | 26025.5061 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9782.5163 | 9782.5163 | 9782.5163 | 9782.5163 | 9782.5163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9115 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 16683.3145 | 0.2 | 0.3 | 26025.9706 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.8687 | 5204.8687 | 5204.8687 | 5204.8687 | 5204.8687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9116 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31360.9323 | 0.2 | 0.3 | 48923.0543 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.1826 | 5205.1826 | 5205.1826 | 5205.1826 | 5205.1826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9117 | HOLLYWOOD | 91201 | Public | 2030 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.1987 | 5205.1987 | 5205.1987 | 5205.1987 | 5205.1987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9118 | HOLLYWOOD | 91201 | Public | 2030 | 5 | Swales | 66.6667 | 16675.9545 | 0.2 | 0.3 | 26014.4891 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9783.368 | 9783.368 | 9783.368 | 9783.368 | 9783.368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9119 | HOLLYWOOD | 91201 | Public | 2030 | 5 | Swales | 66.6667 | 16676.5759 | 0.2 | 0.3 | 26015.4585 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.2784 | 5205.2784 | 5205.2784 | 5205.2784 | 5205.2784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9120 | HOLLYWOOD | 91201 | Public | 2026 | 5 | Swales | 66.6667 | 31348.6225 | 0.2 | 0.3 | 48903.851 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9121 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 30951.0274 | 0.2 | 0.3 | 48283.6027 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.7329 | 5205.7329 | 5205.7329 | 5205.7329 | 5205.7329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9122 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16683.1983 | 0.2 | 0.3 | 26025.7893 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5569.2798 | 5569.2798 | 5569.2798 | 5569.2798 | 5569.2798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9123 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16683.5509 | 0.2 | 0.3 | 26026.3395 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1839.4888 | 1839.4888 | 1839.4888 | 1839.4888 | 1839.4888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9124 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16683.5509 | 0.2 | 0.3 | 26026.3395 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2382.1137 | 2382.1137 | 2382.1137 | 2382.1137 | 2382.1137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9125 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16686.4511 | 0.2 | 0.3 | 26030.8637 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8585.9532 | 8585.9532 | 8585.9532 | 8585.9532 | 8585.9532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9126 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 31402.75 | 0.2 | 0.3 | 48988.29 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.0646 | 5205.0646 | 5205.0646 | 5205.0646 | 5205.0646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9127 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16681.2469 | 0.2 | 0.3 | 26022.7452 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.3532 | 5205.3532 | 5205.3532 | 5205.3532 | 5205.3532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9128 | PEMBROKE PINES | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.5577 | 0.2 | 0.3 | 26021.67 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.441 | 5205.441 | 5205.441 | 5205.441 | 5205.441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9129 | PEMBROKE PINES | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 26905.1299 | 0.2 | 0.3 | 41972.0026 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9783.7458 | 9783.7458 | 9783.7458 | 9783.7458 | 9783.7458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9130 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 19125.6767 | 0.2 | 0.3 | 29836.0557 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.4758 | 5204.4758 | 5204.4758 | 5204.4758 | 5204.4758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9131 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16881.2823 | 0.2 | 0.3 | 26334.8004 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9132 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.5854 | 5204.5854 | 5204.5854 | 5204.5854 | 5204.5854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9133 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 27828.3441 | 0.2 | 0.3 | 43412.2167 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9782.7965 | 9782.7965 | 9782.7965 | 9782.7965 | 9782.7965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9134 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16681.7468 | 0.2 | 0.3 | 26023.525 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1383.3092 | 1383.3092 | 1383.3092 | 1383.3092 | 1383.3092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9135 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16679.6667 | 0.2 | 0.3 | 26020.28 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5107.0014 | 5107.0014 | 5107.0014 | 5107.0014 | 5107.0014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9136 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 20047.0137 | 0.2 | 0.3 | 31273.3414 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2822.6012 | 2822.6012 | 2822.6012 | 2822.6012 | 2822.6012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9137 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16685.3319 | 0.2 | 0.3 | 26029.1177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7372.1534 | 7372.1534 | 7372.1534 | 7372.1534 | 7372.1534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9138 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 20870.8158 | 0.2 | 0.3 | 32558.4726 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2818.125 | 2818.125 | 2818.125 | 2818.125 | 2818.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9139 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 6823.1047 | 0.2 | 0.3 | 10644.0434 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5104.0115 | 5104.0115 | 5104.0115 | 5104.0115 | 5104.0115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9140 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 18985.3256 | 0.2 | 0.3 | 29617.1079 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.6554 | 5204.6554 | 5204.6554 | 5204.6554 | 5204.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9141 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31348.9215 | 0.2 | 0.3 | 48904.3175 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9783.109 | 9783.109 | 9783.109 | 9783.109 | 9783.109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9142 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 20181.5344 | 0.2 | 0.3 | 31483.1937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.584 | 5204.584 | 5204.584 | 5204.584 | 5204.584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9143 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 14580.7113 | 0.2 | 0.3 | 22745.9097 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9144 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 21177.7933 | 0.2 | 0.3 | 33037.3575 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.0705 | 5205.0705 | 5205.0705 | 5205.0705 | 5205.0705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9145 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 16673.6097 | 0.2 | 0.3 | 26010.8312 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5968.3238 | 5968.3238 | 5968.3238 | 5968.3238 | 5968.3238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9146 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.3319 | 5205.3319 | 5205.3319 | 5205.3319 | 5205.3319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9147 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 26043.034 | 0.2 | 0.3 | 40627.133 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9148 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 16678.6413 | 0.2 | 0.3 | 26018.6804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8814.7765 | 8814.7765 | 8814.7765 | 8814.7765 | 8814.7765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9149 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 16679.4364 | 0.2 | 0.3 | 26019.9208 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2964.457 | 2964.457 | 2964.457 | 2964.457 | 2964.457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9150 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 28695.5681 | 0.2 | 0.3 | 44765.0862 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2722.2589 | 2722.2589 | 2722.2589 | 2722.2589 | 2722.2589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9151 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16678.8403 | 0.2 | 0.3 | 26018.9909 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4806.9272 | 4806.9272 | 4806.9272 | 4806.9272 | 4806.9272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9152 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16678.9031 | 0.2 | 0.3 | 26019.0889 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9783.7908 | 9783.7908 | 9783.7908 | 9783.7908 | 9783.7908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9153 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 17376.9549 | 0.2 | 0.3 | 27108.0497 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.4429 | 5205.4429 | 5205.4429 | 5205.4429 | 5205.4429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9154 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 1558.0989 | 0.2 | 0.3 | 2430.6342 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 5205.4385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9155 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.736 | 5205.736 | 5205.736 | 5205.736 | 5205.736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9156 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 31370.8946 | 0.2 | 0.3 | 48938.5956 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4985.9756 | 4985.9756 | 4985.9756 | 4985.9756 | 4985.9756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9157 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16677.641 | 0.2 | 0.3 | 26017.12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.8626 | 5204.8626 | 5204.8626 | 5204.8626 | 5204.8626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9158 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16678.2977 | 0.2 | 0.3 | 26018.1444 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9159 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 20984.6883 | 0.2 | 0.3 | 32736.1138 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8258.2977 | 8258.2977 | 8258.2977 | 8258.2977 | 8258.2977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9160 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9105 | 0.2 | 0.3 | 26023.7804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6152.454 | 6152.454 | 6152.454 | 6152.454 | 6152.454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9161 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3145.4677 | 3145.4677 | 3145.4677 | 3145.4677 | 3145.4677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9162 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16691.4796 | 0.2 | 0.3 | 26038.7082 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3060.1699 | 3060.1699 | 3060.1699 | 3060.1699 | 3060.1699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9163 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16685.1913 | 0.2 | 0.3 | 26028.8985 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7933.3038 | 7933.3038 | 7933.3038 | 7933.3038 | 7933.3038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9164 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16687.1051 | 0.2 | 0.3 | 26031.884 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.1012 | 5205.1012 | 5205.1012 | 5205.1012 | 5205.1012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9165 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16685.1913 | 0.2 | 0.3 | 26028.8985 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8524.1089 | 8524.1089 | 8524.1089 | 8524.1089 | 8524.1089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9166 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16687.1051 | 0.2 | 0.3 | 26031.884 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8158.9813 | 8158.9813 | 8158.9813 | 8158.9813 | 8158.9813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9167 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16688.7456 | 0.2 | 0.3 | 26034.4431 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7625.669 | 7625.669 | 7625.669 | 7625.669 | 7625.669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9168 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4643.4663 | 4643.4663 | 4643.4663 | 4643.4663 | 4643.4663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9169 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16693.3934 | 0.2 | 0.3 | 26041.6937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2683.366 | 2683.366 | 2683.366 | 2683.366 | 2683.366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9170 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16693.3934 | 0.2 | 0.3 | 26041.6937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6877.7063 | 6877.7063 | 6877.7063 | 6877.7063 | 6877.7063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9171 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16689.8392 | 0.2 | 0.3 | 26036.1492 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2602.8355 | 2602.8355 | 2602.8355 | 2602.8355 | 2602.8355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9172 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16688.4722 | 0.2 | 0.3 | 26034.0166 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2902.7259 | 2902.7259 | 2902.7259 | 2902.7259 | 2902.7259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9173 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16701.7598 | 0.2 | 0.3 | 26054.7453 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9622.349 | 9622.349 | 9622.349 | 9622.349 | 9622.349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9174 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16685.8902 | 0.2 | 0.3 | 26029.9887 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 5205.2679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9175 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16674.6315 | 0.2 | 0.3 | 26012.4251 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5065.5155 | 5065.5155 | 5065.5155 | 5065.5155 | 5065.5155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9176 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16674.8223 | 0.2 | 0.3 | 26012.7228 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5297.1915 | 5297.1915 | 5297.1915 | 5297.1915 | 5297.1915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9177 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16672.0977 | 0.2 | 0.3 | 26008.4724 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5491.1713 | 5491.1713 | 5491.1713 | 5491.1713 | 5491.1713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9178 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16681.5245 | 0.2 | 0.3 | 26023.1782 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6246.5565 | 6246.5565 | 6246.5565 | 6246.5565 | 6246.5565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9179 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 20540.1833 | 0.2 | 0.3 | 32042.6859 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5636.4415 | 5636.4415 | 5636.4415 | 5636.4415 | 5636.4415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9180 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16671.6742 | 0.2 | 0.3 | 26007.8118 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5214.0962 | 5214.0962 | 5214.0962 | 5214.0962 | 5214.0962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9181 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16672.3415 | 0.2 | 0.3 | 26008.8527 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4815.131 | 4815.131 | 4815.131 | 4815.131 | 4815.131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9182 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 26934.1024 | 0.2 | 0.3 | 42017.1997 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3192.1139 | 3192.1139 | 3192.1139 | 3192.1139 | 3192.1139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9183 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 16675.236 | 0.2 | 0.3 | 26013.3682 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5882.3543 | 5882.3543 | 5882.3543 | 5882.3543 | 5882.3543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9184 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 28697.3145 | 0.2 | 0.3 | 44767.8107 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2660.1038 | 2660.1038 | 2660.1038 | 2660.1038 | 2660.1038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9185 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16681.0903 | 0.2 | 0.3 | 26022.5009 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 267.0478 | 267.0478 | 267.0478 | 267.0478 | 267.0478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9186 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16595.2894 | 0.2 | 0.3 | 25888.6515 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2426.9925 | 2426.9925 | 2426.9925 | 2426.9925 | 2426.9925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9187 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16681.8166 | 0.2 | 0.3 | 26023.6339 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 185.0902 | 185.0902 | 185.0902 | 185.0902 | 185.0902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9188 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16682.4573 | 0.2 | 0.3 | 26024.6334 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0443 | 5200.0443 | 5200.0443 | 5200.0443 | 5200.0443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9189 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16975.5816 | 0.2 | 0.3 | 26481.9073 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9190 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 12983.853 | 0.2 | 0.3 | 20254.8107 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4806.1877 | 4806.1877 | 4806.1877 | 4806.1877 | 4806.1877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9191 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 29992.2542 | 0.2 | 0.3 | 46787.9166 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6407.0664 | 6407.0664 | 6407.0664 | 6407.0664 | 6407.0664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9192 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16683.5509 | 0.2 | 0.3 | 26026.3395 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9871 | 5199.9871 | 5199.9871 | 5199.9871 | 5199.9871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9193 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 31363.1473 | 0.2 | 0.3 | 48926.5097 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9194 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16678.2517 | 0.2 | 0.3 | 26018.0727 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9195 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16678.5825 | 0.2 | 0.3 | 26018.5886 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0542 | 5200.0542 | 5200.0542 | 5200.0542 | 5200.0542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9196 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 21787.9248 | 0.2 | 0.3 | 33989.1627 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8188.6215 | 8188.6215 | 8188.6215 | 8188.6215 | 8188.6215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9197 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16681.3347 | 0.2 | 0.3 | 26022.8822 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9198 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16674.6775 | 0.2 | 0.3 | 26012.4968 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9912 | 5199.9912 | 5199.9912 | 5199.9912 | 5199.9912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9199 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 26612.1651 | 0.2 | 0.3 | 41514.9776 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9200 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 27005.1227 | 0.2 | 0.3 | 42127.9915 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9201 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16824.6775 | 0.2 | 0.3 | 26246.497 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7804.8484 | 7804.8484 | 7804.8484 | 7804.8484 | 7804.8484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9202 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31368.688 | 0.2 | 0.3 | 48935.1533 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7565.5959 | 7565.5959 | 7565.5959 | 7565.5959 | 7565.5959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9203 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31365.1284 | 0.2 | 0.3 | 48929.6003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3062 | 5200.3062 | 5200.3062 | 5200.3062 | 5200.3062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9204 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31370.9579 | 0.2 | 0.3 | 48938.6944 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5608.4438 | 5608.4438 | 5608.4438 | 5608.4438 | 5608.4438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9205 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31367.6287 | 0.2 | 0.3 | 48933.5007 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9206 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31364.8495 | 0.2 | 0.3 | 48929.1652 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9207 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31376.5627 | 0.2 | 0.3 | 48947.4378 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2599.9896 | 2599.9896 | 2599.9896 | 2599.9896 | 2599.9896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9208 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31375.8833 | 0.2 | 0.3 | 48946.378 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9209 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31367.0745 | 0.2 | 0.3 | 48932.6363 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1780.3958 | 1780.3958 | 1780.3958 | 1780.3958 | 1780.3958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9210 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31367.848 | 0.2 | 0.3 | 48933.8429 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9192.7396 | 9192.7396 | 9192.7396 | 9192.7396 | 9192.7396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9211 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31372.6364 | 0.2 | 0.3 | 48941.3128 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4359 | 5200.4359 | 5200.4359 | 5200.4359 | 5200.4359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9212 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 27719.9008 | 0.2 | 0.3 | 43243.0452 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9142.2703 | 9142.2703 | 9142.2703 | 9142.2703 | 9142.2703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9213 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16674.2553 | 0.2 | 0.3 | 26011.8382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6958.6266 | 6958.6266 | 6958.6266 | 6958.6266 | 6958.6266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9214 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16675.1475 | 0.2 | 0.3 | 26013.2302 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9215 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16672.1368 | 0.2 | 0.3 | 26008.5334 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.981 | 5199.981 | 5199.981 | 5199.981 | 5199.981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9216 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16671.5634 | 0.2 | 0.3 | 26007.6389 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9841 | 5199.9841 | 5199.9841 | 5199.9841 | 5199.9841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9217 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 17396.4257 | 0.2 | 0.3 | 27138.424 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9218 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 11469.8281 | 0.2 | 0.3 | 17892.9318 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8786.4921 | 8786.4921 | 8786.4921 | 8786.4921 | 8786.4921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9219 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9220 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 28591.7189 | 0.2 | 0.3 | 44603.0814 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0853 | 5200.0853 | 5200.0853 | 5200.0853 | 5200.0853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9221 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 16669.8197 | 0.2 | 0.3 | 26004.9187 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9038.458 | 9038.458 | 9038.458 | 9038.458 | 9038.458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9222 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 20163.5187 | 0.2 | 0.3 | 31455.0892 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9090.0262 | 9090.0262 | 9090.0262 | 9090.0262 | 9090.0262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9223 | PEMBROKE PINES | 110313 | Private | 2026 | 5 | Swales | 66.6667 | 8701.0287 | 0.2 | 0.3 | 13573.6047 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9224 | PEMBROKE PINES | 110313 | Private | 2026 | 5 | Swales | 66.6667 | 19417.4176 | 0.2 | 0.3 | 30291.1715 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9225 | PEMBROKE PINES | 110313 | Private | 2026 | 5 | Swales | 66.6667 | 20621.9596 | 0.2 | 0.3 | 32170.257 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5676.099 | 5676.099 | 5676.099 | 5676.099 | 5676.099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9226 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16165.6827 | 0.2 | 0.3 | 25218.4651 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5306.4266 | 5306.4266 | 5306.4266 | 5306.4266 | 5306.4266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9227 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 12541.8482 | 0.2 | 0.3 | 19565.2832 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5295.7588 | 5295.7588 | 5295.7588 | 5295.7588 | 5295.7588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9228 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 20444.9673 | 0.2 | 0.3 | 31894.149 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4188.1516 | 4188.1516 | 4188.1516 | 4188.1516 | 4188.1516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9229 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16684.6445 | 0.2 | 0.3 | 26028.0455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5265.2889 | 5265.2889 | 5265.2889 | 5265.2889 | 5265.2889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9230 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16684.1531 | 0.2 | 0.3 | 26027.2788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1354 | 5200.1354 | 5200.1354 | 5200.1354 | 5200.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9231 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16756.8131 | 0.2 | 0.3 | 26140.6285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5223.2607 | 5223.2607 | 5223.2607 | 5223.2607 | 5223.2607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9232 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 31376.6503 | 0.2 | 0.3 | 48947.5745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5229.0466 | 5229.0466 | 5229.0466 | 5229.0466 | 5229.0466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9233 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16679.1765 | 0.2 | 0.3 | 26019.5154 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2723.2963 | 2723.2963 | 2723.2963 | 2723.2963 | 2723.2963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9234 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 31360.2113 | 0.2 | 0.3 | 48921.9297 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9647 | 5199.9647 | 5199.9647 | 5199.9647 | 5199.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9235 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16679.1347 | 0.2 | 0.3 | 26019.4501 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9236 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16679.6675 | 0.2 | 0.3 | 26020.2812 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5255.603 | 5255.603 | 5255.603 | 5255.603 | 5255.603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9237 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 31695.1491 | 0.2 | 0.3 | 49444.4325 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9450.7748 | 9450.7748 | 9450.7748 | 9450.7748 | 9450.7748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9238 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 17668.8417 | 0.2 | 0.3 | 27563.3931 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5410.0239 | 5410.0239 | 5410.0239 | 5410.0239 | 5410.0239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9239 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 30038.7117 | 0.2 | 0.3 | 46860.3903 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8527.8074 | 8527.8074 | 8527.8074 | 8527.8074 | 8527.8074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9240 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 11527.2223 | 0.2 | 0.3 | 17982.4667 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5386.5474 | 5386.5474 | 5386.5474 | 5386.5474 | 5386.5474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9241 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 22368.4181 | 0.2 | 0.3 | 34894.7323 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5386.7495 | 5386.7495 | 5386.7495 | 5386.7495 | 5386.7495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9242 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16689.0308 | 0.2 | 0.3 | 26034.888 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7658.714 | 7658.714 | 7658.714 | 7658.714 | 7658.714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9243 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16692.7123 | 0.2 | 0.3 | 26040.6312 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5308.038 | 5308.038 | 5308.038 | 5308.038 | 5308.038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9244 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16697.4542 | 0.2 | 0.3 | 26048.0286 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5299.0843 | 5299.0843 | 5299.0843 | 5299.0843 | 5299.0843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9245 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16689.3315 | 0.2 | 0.3 | 26035.3571 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5997.393 | 5997.393 | 5997.393 | 5997.393 | 5997.393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9246 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16686.6226 | 0.2 | 0.3 | 26031.1313 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7427.0235 | 7427.0235 | 7427.0235 | 7427.0235 | 7427.0235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9247 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16690.9809 | 0.2 | 0.3 | 26037.9302 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1163.0523 | 1163.0523 | 1163.0523 | 1163.0523 | 1163.0523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9248 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16693.0955 | 0.2 | 0.3 | 26041.229 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5495.0587 | 5495.0587 | 5495.0587 | 5495.0587 | 5495.0587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9249 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16688.583 | 0.2 | 0.3 | 26034.1895 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6262.3419 | 6262.3419 | 6262.3419 | 6262.3419 | 6262.3419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9250 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16690.5691 | 0.2 | 0.3 | 26037.2877 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5347.6361 | 5347.6361 | 5347.6361 | 5347.6361 | 5347.6361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9251 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16691.9749 | 0.2 | 0.3 | 26039.4808 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5365.022 | 5365.022 | 5365.022 | 5365.022 | 5365.022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9252 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16673.2898 | 0.2 | 0.3 | 26010.3321 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4858.1691 | 4858.1691 | 4858.1691 | 4858.1691 | 4858.1691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9253 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16675.0755 | 0.2 | 0.3 | 26013.1177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 121.9626 | 121.9626 | 121.9626 | 121.9626 | 121.9626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9254 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16674.1105 | 0.2 | 0.3 | 26011.6123 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 515.9835 | 515.9835 | 515.9835 | 515.9835 | 515.9835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9255 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 19712.4439 | 0.2 | 0.3 | 30751.4124 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5252.3063 | 5252.3063 | 5252.3063 | 5252.3063 | 5252.3063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9256 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 22272.7762 | 0.2 | 0.3 | 34745.5309 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6578.8416 | 6578.8416 | 6578.8416 | 6578.8416 | 6578.8416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9257 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 21912.4259 | 0.2 | 0.3 | 34183.3844 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6247.7949 | 6247.7949 | 6247.7949 | 6247.7949 | 6247.7949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9258 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 18715.3803 | 0.2 | 0.3 | 29195.9932 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2193.3005 | 2193.3005 | 2193.3005 | 2193.3005 | 2193.3005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9259 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 21143.6587 | 0.2 | 0.3 | 32984.1076 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5330.1084 | 5330.1084 | 5330.1084 | 5330.1084 | 5330.1084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9260 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 16675.4561 | 0.2 | 0.3 | 26013.7116 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5378.3446 | 5378.3446 | 5378.3446 | 5378.3446 | 5378.3446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9261 | HOLLYWOOD | 91202 | Private | 2030 | 5 | Swales | 66.6667 | 28018.5785 | 0.2 | 0.3 | 43708.9824 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5350.289 | 5350.289 | 5350.289 | 5350.289 | 5350.289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9262 | PEMBROKE PINES | 110313 | Private | 2026 | 5 | Swales | 66.6667 | 16732.4899 | 0.2 | 0.3 | 26102.6843 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1223.4755 | 1223.4755 | 1223.4755 | 1223.4755 | 1223.4755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9263 | PEMBROKE PINES | 110313 | Private | 2026 | 5 | Swales | 66.6667 | 8627.6783 | 0.2 | 0.3 | 13459.1782 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1927 | 5200.1927 | 5200.1927 | 5200.1927 | 5200.1927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9264 | PEMBROKE PINES | 110313 | Private | 2026 | 5 | Swales | 66.6667 | 20648.1369 | 0.2 | 0.3 | 32211.0935 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9265 | PEMBROKE PINES | 110313 | Private | 2026 | 5 | Swales | 66.6667 | 12023.7552 | 0.2 | 0.3 | 18757.0581 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6864.6826 | 6864.6826 | 6864.6826 | 6864.6826 | 6864.6826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9266 | PEMBROKE PINES | 110313 | Private | 2026 | 5 | Swales | 66.6667 | 29416.9182 | 0.2 | 0.3 | 45890.3924 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 308.8715 | 308.8715 | 308.8715 | 308.8715 | 308.8715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9267 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 24987.2248 | 0.2 | 0.3 | 38980.0707 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2376.1897 | 2376.1897 | 2376.1897 | 2376.1897 | 2376.1897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9268 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16684.6445 | 0.2 | 0.3 | 26028.0455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2946.3954 | 2946.3954 | 2946.3954 | 2946.3954 | 2946.3954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9269 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16702.1706 | 0.2 | 0.3 | 26055.3861 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5240.7497 | 5240.7497 | 5240.7497 | 5240.7497 | 5240.7497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9270 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 4498.7467 | 0.2 | 0.3 | 7018.0449 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5368.125 | 5368.125 | 5368.125 | 5368.125 | 5368.125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9271 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 28499.1258 | 0.2 | 0.3 | 44458.6362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9272 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.5435 | 0.2 | 0.3 | 26021.6479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5365.5299 | 5365.5299 | 5365.5299 | 5365.5299 | 5365.5299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9273 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 31375.891 | 0.2 | 0.3 | 48946.39 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.6154 | 5203.6154 | 5203.6154 | 5203.6154 | 5203.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9274 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16678.7429 | 0.2 | 0.3 | 26018.8389 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4332.4695 | 4332.4695 | 4332.4695 | 4332.4695 | 4332.4695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9275 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16679.5172 | 0.2 | 0.3 | 26020.0468 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6596.2758 | 6596.2758 | 6596.2758 | 6596.2758 | 6596.2758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9276 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 23332.5189 | 0.2 | 0.3 | 36398.7295 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2072.2879 | 2072.2879 | 2072.2879 | 2072.2879 | 2072.2879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9277 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 10150.344 | 0.2 | 0.3 | 15834.5366 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6420.1574 | 6420.1574 | 6420.1574 | 6420.1574 | 6420.1574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9278 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 28256.4467 | 0.2 | 0.3 | 44080.0568 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9279 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 22594.0221 | 0.2 | 0.3 | 35246.6745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7694.0578 | 7694.0578 | 7694.0578 | 7694.0578 | 7694.0578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9280 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 15188.2321 | 0.2 | 0.3 | 23693.6421 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7943.5615 | 7943.5615 | 7943.5615 | 7943.5615 | 7943.5615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9281 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16688.4722 | 0.2 | 0.3 | 26034.0166 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8042.1951 | 8042.1951 | 8042.1951 | 8042.1951 | 8042.1951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9282 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16691.753 | 0.2 | 0.3 | 26039.1347 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8239.3724 | 8239.3724 | 8239.3724 | 8239.3724 | 8239.3724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9283 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16691.6359 | 0.2 | 0.3 | 26038.952 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8470.9598 | 8470.9598 | 8470.9598 | 8470.9598 | 8470.9598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9284 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16689.3799 | 0.2 | 0.3 | 26035.4327 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8615.0733 | 8615.0733 | 8615.0733 | 8615.0733 | 8615.0733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9285 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16686.6869 | 0.2 | 0.3 | 26031.2315 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8805.8533 | 8805.8533 | 8805.8533 | 8805.8533 | 8805.8533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9286 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16690.8493 | 0.2 | 0.3 | 26037.7249 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.0666 | 5203.0666 | 5203.0666 | 5203.0666 | 5203.0666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9287 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16692.6961 | 0.2 | 0.3 | 26040.6059 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9288 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16688.3445 | 0.2 | 0.3 | 26033.8174 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9289 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16689.9491 | 0.2 | 0.3 | 26036.3206 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8995.8581 | 8995.8581 | 8995.8581 | 8995.8581 | 8995.8581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9290 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16690.9319 | 0.2 | 0.3 | 26037.8537 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9288.6733 | 9288.6733 | 9288.6733 | 9288.6733 | 9288.6733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9291 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16673.3295 | 0.2 | 0.3 | 26010.394 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9270.4747 | 9270.4747 | 9270.4747 | 9270.4747 | 9270.4747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9292 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 8983.5885 | 0.2 | 0.3 | 14014.3981 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8017 | 5201.8017 | 5201.8017 | 5201.8017 | 5201.8017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9293 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 23465.1578 | 0.2 | 0.3 | 36605.6462 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.913 | 5202.913 | 5202.913 | 5202.913 | 5202.913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9294 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31350.0575 | 0.2 | 0.3 | 48906.0896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.859 | 5202.859 | 5202.859 | 5202.859 | 5202.859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9295 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16673.4314 | 0.2 | 0.3 | 26010.553 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3481 | 5202.3481 | 5202.3481 | 5202.3481 | 5202.3481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9296 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16673.7085 | 0.2 | 0.3 | 26010.9852 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8747 | 5202.8747 | 5202.8747 | 5202.8747 | 5202.8747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9297 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16673.7347 | 0.2 | 0.3 | 26011.0261 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6728.9128 | 6728.9128 | 6728.9128 | 6728.9128 | 6728.9128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9298 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 20634.9965 | 0.2 | 0.3 | 32190.5946 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.117 | 5202.117 | 5202.117 | 5202.117 | 5202.117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9299 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 16677.2353 | 0.2 | 0.3 | 26016.487 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6253.1467 | 6253.1467 | 6253.1467 | 6253.1467 | 6253.1467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9300 | HOLLYWOOD | 91202 | Private | 2030 | 5 | Swales | 66.6667 | 28846.382 | 0.2 | 0.3 | 45000.3559 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7803.6368 | 7803.6368 | 7803.6368 | 7803.6368 | 7803.6368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9301 | PEMBROKE PINES | 110313 | Private | 2026 | 5 | Swales | 66.6667 | 6642.0754 | 0.2 | 0.3 | 10361.6376 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12743.9959 | 12743.9959 | 12743.9959 | 12743.9959 | 12743.9959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9302 | PEMBROKE PINES | 110313 | Private | 2026 | 5 | Swales | 66.6667 | 17618.1954 | 0.2 | 0.3 | 27484.3848 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7011.4856 | 7011.4856 | 7011.4856 | 7011.4856 | 7011.4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9303 | PEMBROKE PINES | 110313 | Private | 2026 | 5 | Swales | 66.6667 | 17852.2725 | 0.2 | 0.3 | 27849.545 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7818 | 5202.7818 | 5202.7818 | 5202.7818 | 5202.7818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9304 | PEMBROKE PINES | 110313 | Private | 2026 | 5 | Swales | 66.6667 | 588.8747 | 0.2 | 0.3 | 918.6445 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9305 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 495.7029 | 0.2 | 0.3 | 773.2966 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9483.9864 | 9483.9864 | 9483.9864 | 9483.9864 | 9483.9864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9306 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 28159.1153 | 0.2 | 0.3 | 43928.2199 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9307 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9308 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16681.2524 | 0.2 | 0.3 | 26022.7537 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9309 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 19262.3919 | 0.2 | 0.3 | 30049.3314 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9310 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 22348.5148 | 0.2 | 0.3 | 34863.6831 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9311 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 15480.4136 | 0.2 | 0.3 | 24149.4452 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7276.9029 | 7276.9029 | 7276.9029 | 7276.9029 | 7276.9029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9312 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 31356.6744 | 0.2 | 0.3 | 48916.4121 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7896.7237 | 7896.7237 | 7896.7237 | 7896.7237 | 7896.7237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9313 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16676.6913 | 0.2 | 0.3 | 26015.6385 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8967.732 | 8967.732 | 8967.732 | 8967.732 | 8967.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9314 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16677.6365 | 0.2 | 0.3 | 26017.113 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7803.4662 | 7803.4662 | 7803.4662 | 7803.4662 | 7803.4662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9315 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 32350.1885 | 0.2 | 0.3 | 50466.2941 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10639.5239 | 10639.5239 | 10639.5239 | 10639.5239 | 10639.5239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9316 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 14372.2135 | 0.2 | 0.3 | 22420.6531 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 846.2744 | 846.2744 | 846.2744 | 846.2744 | 846.2744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9317 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 27720.4403 | 0.2 | 0.3 | 43243.8868 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7982.6128 | 7982.6128 | 7982.6128 | 7982.6128 | 7982.6128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9318 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 26281.3677 | 0.2 | 0.3 | 40998.9337 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.512 | 5202.512 | 5202.512 | 5202.512 | 5202.512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9319 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 28563.1532 | 0.2 | 0.3 | 44558.519 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9320 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 25146.2121 | 0.2 | 0.3 | 39228.0909 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9570.2255 | 9570.2255 | 9570.2255 | 9570.2255 | 9570.2255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9321 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 30847.8771 | 0.2 | 0.3 | 48122.6882 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7342 | 5201.7342 | 5201.7342 | 5201.7342 | 5201.7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9322 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 23827.0679 | 0.2 | 0.3 | 37170.226 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7001 | 5202.7001 | 5202.7001 | 5202.7001 | 5202.7001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9323 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31370.6993 | 0.2 | 0.3 | 48938.291 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5318 | 5202.5318 | 5202.5318 | 5202.5318 | 5202.5318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9324 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31426.4901 | 0.2 | 0.3 | 49025.3246 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5212.9605 | 5212.9605 | 5212.9605 | 5212.9605 | 5212.9605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9325 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 22057.8327 | 0.2 | 0.3 | 34410.219 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7095.3237 | 7095.3237 | 7095.3237 | 7095.3237 | 7095.3237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9326 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31431.4677 | 0.2 | 0.3 | 49033.0897 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8042.9499 | 8042.9499 | 8042.9499 | 8042.9499 | 8042.9499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9327 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 20881.7275 | 0.2 | 0.3 | 32575.4948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7124.1745 | 7124.1745 | 7124.1745 | 7124.1745 | 7124.1745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9328 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31492.3549 | 0.2 | 0.3 | 49128.0736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5589.0851 | 5589.0851 | 5589.0851 | 5589.0851 | 5589.0851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9329 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31504.1618 | 0.2 | 0.3 | 49146.4924 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9330 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 25523.1531 | 0.2 | 0.3 | 39816.1189 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7559.4123 | 7559.4123 | 7559.4123 | 7559.4123 | 7559.4123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9331 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16706.8871 | 0.2 | 0.3 | 26062.7438 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.5573 | 2600.5573 | 2600.5573 | 2600.5573 | 2600.5573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9332 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 23043.0701 | 0.2 | 0.3 | 35947.1893 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9780.035 | 9780.035 | 9780.035 | 9780.035 | 9780.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9333 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16674.1232 | 0.2 | 0.3 | 26011.6322 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9782.2918 | 9782.2918 | 9782.2918 | 9782.2918 | 9782.2918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9334 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 25748.5756 | 0.2 | 0.3 | 40167.7779 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9782.0325 | 9782.0325 | 9782.0325 | 9782.0325 | 9782.0325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9335 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 17184.4205 | 0.2 | 0.3 | 26807.6959 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9781.3104 | 9781.3104 | 9781.3104 | 9781.3104 | 9781.3104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9336 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 9094.9011 | 0.2 | 0.3 | 14188.0458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.9519 | 9779.9519 | 9779.9519 | 9779.9519 | 9779.9519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9337 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9773.2979 | 9773.2979 | 9773.2979 | 9773.2979 | 9773.2979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9338 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 28683.4521 | 0.2 | 0.3 | 44746.1853 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7889.5154 | 7889.5154 | 7889.5154 | 7889.5154 | 7889.5154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9339 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 17078.5079 | 0.2 | 0.3 | 26642.4724 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3513.644 | 3513.644 | 3513.644 | 3513.644 | 3513.644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9340 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 13229.8383 | 0.2 | 0.3 | 20638.5477 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5298.8301 | 5298.8301 | 5298.8301 | 5298.8301 | 5298.8301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9341 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 5367.5467 | 0.2 | 0.3 | 8373.3728 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6410.4247 | 6410.4247 | 6410.4247 | 6410.4247 | 6410.4247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9342 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16686.5026 | 0.2 | 0.3 | 26030.9441 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3583.0289 | 3583.0289 | 3583.0289 | 3583.0289 | 3583.0289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9343 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 22654.107 | 0.2 | 0.3 | 35340.4069 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3787.772 | 3787.772 | 3787.772 | 3787.772 | 3787.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9344 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 8992.9627 | 0.2 | 0.3 | 14029.0219 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.0082 | 5203.0082 | 5203.0082 | 5203.0082 | 5203.0082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9345 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 26386.3811 | 0.2 | 0.3 | 41162.7545 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9346 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16680.9189 | 0.2 | 0.3 | 26022.2334 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8703.8187 | 8703.8187 | 8703.8187 | 8703.8187 | 8703.8187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9347 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16681.3637 | 0.2 | 0.3 | 26022.9274 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6372.5382 | 6372.5382 | 6372.5382 | 6372.5382 | 6372.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9348 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 28762.1385 | 0.2 | 0.3 | 44868.936 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9991 | 5201.9991 | 5201.9991 | 5201.9991 | 5201.9991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9349 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 20687.8423 | 0.2 | 0.3 | 32273.0339 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5241 | 5202.5241 | 5202.5241 | 5202.5241 | 5202.5241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9350 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 19807.8117 | 0.2 | 0.3 | 30900.1863 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9139 | 5203.9139 | 5203.9139 | 5203.9139 | 5203.9139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9351 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16668.8933 | 0.2 | 0.3 | 26003.4736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2048 | 5201.2048 | 5201.2048 | 5201.2048 | 5201.2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9352 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 19852.3891 | 0.2 | 0.3 | 30969.7269 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6117.1613 | 6117.1613 | 6117.1613 | 6117.1613 | 6117.1613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9353 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 6788.6022 | 0.2 | 0.3 | 10590.2194 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.705 | 5202.705 | 5202.705 | 5202.705 | 5202.705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9354 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 23168.1753 | 0.2 | 0.3 | 36142.3534 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9355 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31844.1251 | 0.2 | 0.3 | 49676.8351 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9356 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 21986.1433 | 0.2 | 0.3 | 34298.3836 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7286 | 5202.7286 | 5202.7286 | 5202.7286 | 5202.7286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9357 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16706.4213 | 0.2 | 0.3 | 26062.0173 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7425.0279 | 7425.0279 | 7425.0279 | 7425.0279 | 7425.0279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9358 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16683.2485 | 0.2 | 0.3 | 26025.8676 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4621.1079 | 4621.1079 | 4621.1079 | 4621.1079 | 4621.1079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9359 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 25349.3661 | 0.2 | 0.3 | 39545.0112 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6592.1965 | 6592.1965 | 6592.1965 | 6592.1965 | 6592.1965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9360 | HOLLYWOOD | 91202 | Private | 2026 | 5 | Swales | 66.6667 | 31763.7166 | 0.2 | 0.3 | 49551.3979 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6503.5202 | 6503.5202 | 6503.5202 | 6503.5202 | 6503.5202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9361 | HOLLYWOOD | 91202 | Private | 2026 | 5 | Swales | 66.6667 | 27647.7175 | 0.2 | 0.3 | 43130.4392 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6264.1657 | 6264.1657 | 6264.1657 | 6264.1657 | 6264.1657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9362 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 30744.976 | 0.2 | 0.3 | 47962.1626 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9029.0011 | 9029.0011 | 9029.0011 | 9029.0011 | 9029.0011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9363 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 12657.2831 | 0.2 | 0.3 | 19745.3616 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8831.1416 | 8831.1416 | 8831.1416 | 8831.1416 | 8831.1416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9364 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16108.9155 | 0.2 | 0.3 | 25129.9081 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5479.1189 | 5479.1189 | 5479.1189 | 5479.1189 | 5479.1189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9365 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 25485.7183 | 0.2 | 0.3 | 39757.7206 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7370.5104 | 7370.5104 | 7370.5104 | 7370.5104 | 7370.5104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9366 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 24930.5831 | 0.2 | 0.3 | 38891.7096 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.223 | 5205.223 | 5205.223 | 5205.223 | 5205.223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9367 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 25543.1608 | 0.2 | 0.3 | 39847.3308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7804.9024 | 7804.9024 | 7804.9024 | 7804.9024 | 7804.9024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9368 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 28945.2023 | 0.2 | 0.3 | 45154.5156 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8300.4967 | 8300.4967 | 8300.4967 | 8300.4967 | 8300.4967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9369 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 8110.5373 | 0.2 | 0.3 | 12652.4382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7197.8417 | 7197.8417 | 7197.8417 | 7197.8417 | 7197.8417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9370 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7546.4669 | 7546.4669 | 7546.4669 | 7546.4669 | 7546.4669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9371 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 28692.6757 | 0.2 | 0.3 | 44760.5741 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2647.2137 | 2647.2137 | 2647.2137 | 2647.2137 | 2647.2137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9372 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16675.5584 | 0.2 | 0.3 | 26013.8711 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9373 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0382 | 5202.0382 | 5202.0382 | 5202.0382 | 5202.0382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9374 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4044.2751 | 4044.2751 | 4044.2751 | 4044.2751 | 4044.2751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9375 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16676.8632 | 0.2 | 0.3 | 26015.9066 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5616.4174 | 5616.4174 | 5616.4174 | 5616.4174 | 5616.4174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9376 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 18501.3108 | 0.2 | 0.3 | 28862.0448 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7168.1287 | 7168.1287 | 7168.1287 | 7168.1287 | 7168.1287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9377 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 17136.6709 | 0.2 | 0.3 | 26733.2067 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9693.4175 | 9693.4175 | 9693.4175 | 9693.4175 | 9693.4175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9378 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 13705.4726 | 0.2 | 0.3 | 21380.5373 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7288.3027 | 7288.3027 | 7288.3027 | 7288.3027 | 7288.3027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9379 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 20895.2369 | 0.2 | 0.3 | 32596.5696 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9697.5521 | 9697.5521 | 9697.5521 | 9697.5521 | 9697.5521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9380 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 25475.2155 | 0.2 | 0.3 | 39741.3361 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9381 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 31169.4248 | 0.2 | 0.3 | 48624.3027 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6198.3206 | 6198.3206 | 6198.3206 | 6198.3206 | 6198.3206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9382 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 8884.684 | 0.2 | 0.3 | 13860.107 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9409.8928 | 9409.8928 | 9409.8928 | 9409.8928 | 9409.8928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9383 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 22368.4381 | 0.2 | 0.3 | 34894.7634 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9384 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 11294.4216 | 0.2 | 0.3 | 17619.2977 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3390.599 | 3390.599 | 3390.599 | 3390.599 | 3390.599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9385 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 15633.0355 | 0.2 | 0.3 | 24387.5353 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7260.7408 | 7260.7408 | 7260.7408 | 7260.7408 | 7260.7408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9386 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 27848.5119 | 0.2 | 0.3 | 43443.6786 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4764.8374 | 4764.8374 | 4764.8374 | 4764.8374 | 4764.8374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9387 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 11092.4341 | 0.2 | 0.3 | 17304.1972 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5300.5548 | 5300.5548 | 5300.5548 | 5300.5548 | 5300.5548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9388 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 25955.4683 | 0.2 | 0.3 | 40490.5305 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8245 | 5201.8245 | 5201.8245 | 5201.8245 | 5201.8245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9389 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 21601.1611 | 0.2 | 0.3 | 33697.8113 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1026.508 | 1026.508 | 1026.508 | 1026.508 | 1026.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9390 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 28910.3519 | 0.2 | 0.3 | 45100.1489 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4181.5095 | 4181.5095 | 4181.5095 | 4181.5095 | 4181.5095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9391 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16696.5845 | 0.2 | 0.3 | 26046.6719 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9392 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16540.9625 | 0.2 | 0.3 | 25803.9016 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8242 | 5201.8242 | 5201.8242 | 5201.8242 | 5201.8242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9393 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16592.2054 | 0.2 | 0.3 | 25883.8404 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7393 | 5201.7393 | 5201.7393 | 5201.7393 | 5201.7393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9394 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 15950.3749 | 0.2 | 0.3 | 24882.5848 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9823.4784 | 9823.4784 | 9823.4784 | 9823.4784 | 9823.4784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9395 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16078.9627 | 0.2 | 0.3 | 25083.1818 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0609 | 5202.0609 | 5202.0609 | 5202.0609 | 5202.0609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9396 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 10861.3961 | 0.2 | 0.3 | 16943.778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9397 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 15840.5473 | 0.2 | 0.3 | 24711.2538 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0233 | 5202.0233 | 5202.0233 | 5202.0233 | 5202.0233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9398 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16998.6551 | 0.2 | 0.3 | 26517.9019 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3665.6272 | 3665.6272 | 3665.6272 | 3665.6272 | 3665.6272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9399 | HOLLYWOOD | 91202 | Private | 2026 | 5 | Swales | 66.6667 | 16881.5219 | 0.2 | 0.3 | 26335.1741 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1237 | 5201.1237 | 5201.1237 | 5201.1237 | 5201.1237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9400 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16066.1103 | 0.2 | 0.3 | 25063.1321 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4747 | 5201.4747 | 5201.4747 | 5201.4747 | 5201.4747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9401 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 13391.7599 | 0.2 | 0.3 | 20891.1454 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5046.7338 | 5046.7338 | 5046.7338 | 5046.7338 | 5046.7338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9402 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 15384.0999 | 0.2 | 0.3 | 23999.1958 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 155.1679 | 155.1679 | 155.1679 | 155.1679 | 155.1679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9403 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 15221.7825 | 0.2 | 0.3 | 23745.9808 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1042.4015 | 1042.4015 | 1042.4015 | 1042.4015 | 1042.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9404 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 17204.5403 | 0.2 | 0.3 | 26839.0828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5296.5939 | 5296.5939 | 5296.5939 | 5296.5939 | 5296.5939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9405 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 14690.9894 | 0.2 | 0.3 | 22917.9435 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4777 | 5202.4777 | 5202.4777 | 5202.4777 | 5202.4777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9406 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16942.4614 | 0.2 | 0.3 | 26430.2398 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3081.6841 | 3081.6841 | 3081.6841 | 3081.6841 | 3081.6841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9407 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 15710.1508 | 0.2 | 0.3 | 24507.8352 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4038.4314 | 4038.4314 | 4038.4314 | 4038.4314 | 4038.4314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9408 | HOLLYWOOD | 91202 | Public | 2030 | 5 | Swales | 66.6667 | 16910.0253 | 0.2 | 0.3 | 26379.6394 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6272.5624 | 6272.5624 | 6272.5624 | 6272.5624 | 6272.5624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9409 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9990.1166 | 9990.1166 | 9990.1166 | 9990.1166 | 9990.1166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9410 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 25337.3159 | 0.2 | 0.3 | 39526.2129 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8200.5923 | 8200.5923 | 8200.5923 | 8200.5923 | 8200.5923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9411 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 21985.2053 | 0.2 | 0.3 | 34296.9203 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7761.9888 | 7761.9888 | 7761.9888 | 7761.9888 | 7761.9888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9412 | PEMBROKE PINES | 110313 | Private | 2026 | 5 | Swales | 66.6667 | 22297.9932 | 0.2 | 0.3 | 34784.8694 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7480.6081 | 7480.6081 | 7480.6081 | 7480.6081 | 7480.6081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9413 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 31840.5737 | 0.2 | 0.3 | 49671.295 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8777.756 | 8777.756 | 8777.756 | 8777.756 | 8777.756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9414 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16676.9893 | 0.2 | 0.3 | 26016.1033 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7955.5024 | 7955.5024 | 7955.5024 | 7955.5024 | 7955.5024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9415 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 19546.5463 | 0.2 | 0.3 | 30492.6122 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 588.6837 | 588.6837 | 588.6837 | 588.6837 | 588.6837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9416 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 16491.4673 | 0.2 | 0.3 | 25726.689 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5369.1844 | 5369.1844 | 5369.1844 | 5369.1844 | 5369.1844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9417 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 1046.6863 | 0.2 | 0.3 | 1632.8307 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1020.2328 | 1020.2328 | 1020.2328 | 1020.2328 | 1020.2328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9418 | HOLLYWOOD | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 20913.0411 | 0.2 | 0.3 | 32624.3442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9807 | 5200.9807 | 5200.9807 | 5200.9807 | 5200.9807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9419 | HOLLYWOOD | 91300 | Public | 2026 | 5 | Swales | 66.6667 | 23548.257 | 0.2 | 0.3 | 36735.2809 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3293 | 5201.3293 | 5201.3293 | 5201.3293 | 5201.3293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9420 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 25353.286 | 0.2 | 0.3 | 39551.1262 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2920.8664 | 2920.8664 | 2920.8664 | 2920.8664 | 2920.8664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9421 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 25770.3413 | 0.2 | 0.3 | 40201.7324 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2281.0888 | 2281.0888 | 2281.0888 | 2281.0888 | 2281.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9422 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 31361.6845 | 0.2 | 0.3 | 48924.2278 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9915.3356 | 9915.3356 | 9915.3356 | 9915.3356 | 9915.3356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9423 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16018.4803 | 0.2 | 0.3 | 24988.8292 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9424 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16473.2269 | 0.2 | 0.3 | 25698.2339 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2328.9739 | 2328.9739 | 2328.9739 | 2328.9739 | 2328.9739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9425 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 15966.4033 | 0.2 | 0.3 | 24907.5892 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6529.1986 | 6529.1986 | 6529.1986 | 6529.1986 | 6529.1986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9426 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 14227.6451 | 0.2 | 0.3 | 22195.1264 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3150.4832 | 3150.4832 | 3150.4832 | 3150.4832 | 3150.4832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9427 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 28539.9341 | 0.2 | 0.3 | 44522.2972 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9937.0694 | 9937.0694 | 9937.0694 | 9937.0694 | 9937.0694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9428 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 15185.579 | 0.2 | 0.3 | 23689.5032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7696.5632 | 7696.5632 | 7696.5632 | 7696.5632 | 7696.5632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9429 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 17162.2415 | 0.2 | 0.3 | 26773.0968 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9430 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16542.6105 | 0.2 | 0.3 | 25806.4723 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1731 | 5202.1731 | 5202.1731 | 5202.1731 | 5202.1731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9431 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16108.2335 | 0.2 | 0.3 | 25128.8442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9665.6431 | 9665.6431 | 9665.6431 | 9665.6431 | 9665.6431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9432 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 15974.9985 | 0.2 | 0.3 | 24920.9977 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10219.5089 | 10219.5089 | 10219.5089 | 10219.5089 | 10219.5089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9433 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16688.2765 | 0.2 | 0.3 | 26033.7114 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10404.7109 | 10404.7109 | 10404.7109 | 10404.7109 | 10404.7109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9434 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16693.3934 | 0.2 | 0.3 | 26041.6937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6579.9395 | 6579.9395 | 6579.9395 | 6579.9395 | 6579.9395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9435 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16690.386 | 0.2 | 0.3 | 26037.0022 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6302.87 | 6302.87 | 6302.87 | 6302.87 | 6302.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9436 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16693.3934 | 0.2 | 0.3 | 26041.6937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8483.109 | 8483.109 | 8483.109 | 8483.109 | 8483.109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9437 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16687.9254 | 0.2 | 0.3 | 26033.1636 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9708.2042 | 9708.2042 | 9708.2042 | 9708.2042 | 9708.2042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9438 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16689.5151 | 0.2 | 0.3 | 26035.6435 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9692.0667 | 9692.0667 | 9692.0667 | 9692.0667 | 9692.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9439 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16693.0601 | 0.2 | 0.3 | 26041.1737 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 865.9287 | 865.9287 | 865.9287 | 865.9287 | 865.9287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9440 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 23783.403 | 0.2 | 0.3 | 37102.1087 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2235.1632 | 2235.1632 | 2235.1632 | 2235.1632 | 2235.1632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9441 | PEMBROKE PINES | 110313 | Private | 2026 | 5 | Swales | 66.6667 | 30241.3631 | 0.2 | 0.3 | 47176.5264 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5421.3458 | 5421.3458 | 5421.3458 | 5421.3458 | 5421.3458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9442 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 18472.2029 | 0.2 | 0.3 | 28816.6366 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6146.3163 | 6146.3163 | 6146.3163 | 6146.3163 | 6146.3163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9443 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 25081.8405 | 0.2 | 0.3 | 39127.6711 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5035.3099 | 5035.3099 | 5035.3099 | 5035.3099 | 5035.3099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9444 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16677.5361 | 0.2 | 0.3 | 26016.9563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1211.8917 | 1211.8917 | 1211.8917 | 1211.8917 | 1211.8917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9445 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 17090.0989 | 0.2 | 0.3 | 26660.5542 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7106.789 | 7106.789 | 7106.789 | 7106.789 | 7106.789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9446 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 31376.8148 | 0.2 | 0.3 | 48947.8311 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4353.7334 | 4353.7334 | 4353.7334 | 4353.7334 | 4353.7334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9447 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 17524.6151 | 0.2 | 0.3 | 27338.3996 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2508.5695 | 2508.5695 | 2508.5695 | 2508.5695 | 2508.5695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9448 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 31466.6882 | 0.2 | 0.3 | 49088.0336 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5522.4701 | 5522.4701 | 5522.4701 | 5522.4701 | 5522.4701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9449 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16676.2698 | 0.2 | 0.3 | 26014.9809 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5247.9194 | 5247.9194 | 5247.9194 | 5247.9194 | 5247.9194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9450 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 29955.3787 | 0.2 | 0.3 | 46730.3907 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9079.5979 | 9079.5979 | 9079.5979 | 9079.5979 | 9079.5979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9451 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16678.6238 | 0.2 | 0.3 | 26018.6531 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1388 | 5201.1388 | 5201.1388 | 5201.1388 | 5201.1388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9452 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16685.1177 | 0.2 | 0.3 | 26028.7836 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5465.05 | 5465.05 | 5465.05 | 5465.05 | 5465.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9453 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 18848.2671 | 0.2 | 0.3 | 29403.2967 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6235.1654 | 6235.1654 | 6235.1654 | 6235.1654 | 6235.1654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9454 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 18129.3123 | 0.2 | 0.3 | 28281.7271 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.563 | 5203.563 | 5203.563 | 5203.563 | 5203.563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9455 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 17488.0161 | 0.2 | 0.3 | 27281.3051 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5128.068 | 5128.068 | 5128.068 | 5128.068 | 5128.068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9456 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 17075.7414 | 0.2 | 0.3 | 26638.1566 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9457 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16589.2901 | 0.2 | 0.3 | 25879.2925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6066 | 5201.6066 | 5201.6066 | 5201.6066 | 5201.6066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9458 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 23230.7817 | 0.2 | 0.3 | 36240.0194 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1392.5257 | 1392.5257 | 1392.5257 | 1392.5257 | 1392.5257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9459 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 23914.4347 | 0.2 | 0.3 | 37306.5182 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5377.4105 | 5377.4105 | 5377.4105 | 5377.4105 | 5377.4105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9460 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 27755.2455 | 0.2 | 0.3 | 43298.1829 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3712.2815 | 3712.2815 | 3712.2815 | 3712.2815 | 3712.2815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9461 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31337.8992 | 0.2 | 0.3 | 48887.1228 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1491.7197 | 1491.7197 | 1491.7197 | 1491.7197 | 1491.7197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9462 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 30792.8003 | 0.2 | 0.3 | 48036.7684 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5215.8176 | 5215.8176 | 5215.8176 | 5215.8176 | 5215.8176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9463 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 31364.1619 | 0.2 | 0.3 | 48928.0926 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5223.1097 | 5223.1097 | 5223.1097 | 5223.1097 | 5223.1097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9464 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 29722.2939 | 0.2 | 0.3 | 46366.7785 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9465 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 29158.7339 | 0.2 | 0.3 | 45487.6248 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8561 | 5201.8561 | 5201.8561 | 5201.8561 | 5201.8561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9466 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 28691.1886 | 0.2 | 0.3 | 44758.2542 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12807.2221 | 12807.2221 | 12807.2221 | 12807.2221 | 12807.2221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9467 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 28360.7708 | 0.2 | 0.3 | 44242.8024 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10406.1531 | 10406.1531 | 10406.1531 | 10406.1531 | 10406.1531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9468 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 13139.581 | 0.2 | 0.3 | 20497.7464 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5944.7751 | 5944.7751 | 5944.7751 | 5944.7751 | 5944.7751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9469 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16699.5074 | 0.2 | 0.3 | 26051.2315 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6136.1999 | 6136.1999 | 6136.1999 | 6136.1999 | 6136.1999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9470 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16692.8051 | 0.2 | 0.3 | 26040.7759 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6428 | 5202.6428 | 5202.6428 | 5202.6428 | 5202.6428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9471 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 24037.8785 | 0.2 | 0.3 | 37499.0905 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5250.3999 | 5250.3999 | 5250.3999 | 5250.3999 | 5250.3999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9472 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16674.0137 | 0.2 | 0.3 | 26011.4614 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6589.1112 | 6589.1112 | 6589.1112 | 6589.1112 | 6589.1112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9473 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5831.2806 | 5831.2806 | 5831.2806 | 5831.2806 | 5831.2806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9474 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 16208.9667 | 0.2 | 0.3 | 25285.988 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5235.5907 | 5235.5907 | 5235.5907 | 5235.5907 | 5235.5907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9475 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 5544.6577 | 0.2 | 0.3 | 8649.6661 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 500.121 | 500.121 | 500.121 | 500.121 | 500.121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9476 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 20589.4671 | 0.2 | 0.3 | 32119.5687 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9477 | PEMBROKE PINES | 110313 | Public | 2026 | 5 | Swales | 66.6667 | 20105.1864 | 0.2 | 0.3 | 31364.0908 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2299.4844 | 2299.4844 | 2299.4844 | 2299.4844 | 2299.4844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9478 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16675.8676 | 0.2 | 0.3 | 26014.3535 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2904.672 | 2904.672 | 2904.672 | 2904.672 | 2904.672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9479 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4751.1365 | 4751.1365 | 4751.1365 | 4751.1365 | 4751.1365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9480 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7780.8354 | 7780.8354 | 7780.8354 | 7780.8354 | 7780.8354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9481 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 16676.6157 | 0.2 | 0.3 | 26015.5205 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.5265 | 9779.5265 | 9779.5265 | 9779.5265 | 9779.5265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9482 | HOLLYWOOD | 91202 | Private | 2026 | 5 | Swales | 66.6667 | 25357.4419 | 0.2 | 0.3 | 39557.6093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7851.0807 | 7851.0807 | 7851.0807 | 7851.0807 | 7851.0807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9483 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 17206.3919 | 0.2 | 0.3 | 26841.9714 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7602.781 | 7602.781 | 7602.781 | 7602.781 | 7602.781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9484 | HOLLYWOOD | 91202 | Public | 2026 | 5 | Swales | 66.6667 | 54.9446 | 0.2 | 0.3 | 85.7136 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5194.7756 | 5194.7756 | 5194.7756 | 5194.7756 | 5194.7756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9485 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 15409.757 | 0.2 | 0.3 | 24039.2209 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5879.0254 | 5879.0254 | 5879.0254 | 5879.0254 | 5879.0254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9486 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16678.5832 | 0.2 | 0.3 | 26018.5898 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9574.095 | 9574.095 | 9574.095 | 9574.095 | 9574.095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9487 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6624 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8394.0805 | 8394.0805 | 8394.0805 | 8394.0805 | 8394.0805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9488 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 20188.0623 | 0.2 | 0.3 | 31493.3771 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5848.2611 | 5848.2611 | 5848.2611 | 5848.2611 | 5848.2611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9489 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9263 | 0.2 | 0.3 | 26023.8051 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1.899 | 1.899 | 1.899 | 1.899 | 1.899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9490 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 21354.0105 | 0.2 | 0.3 | 33312.2563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1669.032 | 1669.032 | 1669.032 | 1669.032 | 1669.032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9491 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 21453.2841 | 0.2 | 0.3 | 33467.1232 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9492 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 17117.4718 | 0.2 | 0.3 | 26703.256 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 64.2753 | 64.2753 | 64.2753 | 64.2753 | 64.2753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9493 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 943.9368 | 0.2 | 0.3 | 1472.5414 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5139.982 | 5139.982 | 5139.982 | 5139.982 | 5139.982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9494 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 23978.7803 | 0.2 | 0.3 | 37406.8972 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0154 | 5202.0154 | 5202.0154 | 5202.0154 | 5202.0154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9495 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 15632.1177 | 0.2 | 0.3 | 24386.1037 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0567 | 5200.0567 | 5200.0567 | 5200.0567 | 5200.0567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9496 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 29521.3501 | 0.2 | 0.3 | 46053.3061 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7495.8976 | 7495.8976 | 7495.8976 | 7495.8976 | 7495.8976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9497 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 20196.8867 | 0.2 | 0.3 | 31507.1433 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2593.7045 | 2593.7045 | 2593.7045 | 2593.7045 | 2593.7045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9498 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16676.2327 | 0.2 | 0.3 | 26014.9231 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5590.6903 | 5590.6903 | 5590.6903 | 5590.6903 | 5590.6903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9499 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16680.5435 | 0.2 | 0.3 | 26021.6479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2638.0774 | 2638.0774 | 2638.0774 | 2638.0774 | 2638.0774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9500 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 25844.9241 | 0.2 | 0.3 | 40318.0816 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5458.6616 | 5458.6616 | 5458.6616 | 5458.6616 | 5458.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9501 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16681.3637 | 0.2 | 0.3 | 26022.9274 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9502 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16879.5589 | 0.2 | 0.3 | 26332.1119 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9503 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 7429.133 | 0.2 | 0.3 | 11589.4475 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5009.3436 | 5009.3436 | 5009.3436 | 5009.3436 | 5009.3436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9504 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5893.3111 | 5893.3111 | 5893.3111 | 5893.3111 | 5893.3111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9505 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16690.8838 | 0.2 | 0.3 | 26037.7787 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4170.0848 | 4170.0848 | 4170.0848 | 4170.0848 | 4170.0848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9506 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16682.5542 | 0.2 | 0.3 | 26024.7846 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9598 | 5201.9598 | 5201.9598 | 5201.9598 | 5201.9598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9507 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 19232.6095 | 0.2 | 0.3 | 30002.8709 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2616.255 | 2616.255 | 2616.255 | 2616.255 | 2616.255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9508 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16678.9111 | 0.2 | 0.3 | 26019.1013 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2400.9469 | 2400.9469 | 2400.9469 | 2400.9469 | 2400.9469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9509 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 22136.2287 | 0.2 | 0.3 | 34532.5168 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5925.6581 | 5925.6581 | 5925.6581 | 5925.6581 | 5925.6581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9510 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16685.7381 | 0.2 | 0.3 | 26029.7515 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6301.004 | 6301.004 | 6301.004 | 6301.004 | 6301.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9511 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 25837.3835 | 0.2 | 0.3 | 40306.3182 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10662.1678 | 10662.1678 | 10662.1678 | 10662.1678 | 10662.1678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9512 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 30577.0751 | 0.2 | 0.3 | 47700.2372 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13697.9322 | 13697.9322 | 13697.9322 | 13697.9322 | 13697.9322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9513 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 24095.7743 | 0.2 | 0.3 | 37589.408 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9090.5828 | 9090.5828 | 9090.5828 | 9090.5828 | 9090.5828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9514 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 18441.6539 | 0.2 | 0.3 | 28768.9801 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11762.0965 | 11762.0965 | 11762.0965 | 11762.0965 | 11762.0965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9515 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 17488.8155 | 0.2 | 0.3 | 27282.5521 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9269.7756 | 9269.7756 | 9269.7756 | 9269.7756 | 9269.7756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9516 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 11107.3841 | 0.2 | 0.3 | 17327.5191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5412.3633 | 5412.3633 | 5412.3633 | 5412.3633 | 5412.3633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9517 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16665.2403 | 0.2 | 0.3 | 25997.7748 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2598.4639 | 2598.4639 | 2598.4639 | 2598.4639 | 2598.4639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9518 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 27904.9994 | 0.2 | 0.3 | 43531.7991 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2599.9896 | 2599.9896 | 2599.9896 | 2599.9896 | 2599.9896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9519 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 31364.708 | 0.2 | 0.3 | 48928.9445 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7280.5875 | 7280.5875 | 7280.5875 | 7280.5875 | 7280.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9520 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 18131.6385 | 0.2 | 0.3 | 28285.3561 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8395.5268 | 8395.5268 | 8395.5268 | 8395.5268 | 8395.5268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9521 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 25434.8185 | 0.2 | 0.3 | 39678.3169 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9824.3224 | 9824.3224 | 9824.3224 | 9824.3224 | 9824.3224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9522 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 31358.6348 | 0.2 | 0.3 | 48919.4703 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5964.9948 | 5964.9948 | 5964.9948 | 5964.9948 | 5964.9948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9523 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9105 | 0.2 | 0.3 | 26023.7804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8225.525 | 8225.525 | 8225.525 | 8225.525 | 8225.525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9524 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16682.23 | 0.2 | 0.3 | 26024.2788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9320.2207 | 9320.2207 | 9320.2207 | 9320.2207 | 9320.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9525 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 31361.7991 | 0.2 | 0.3 | 48924.4066 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 15.9398 | 15.9398 | 15.9398 | 15.9398 | 15.9398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9526 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 17880.2937 | 0.2 | 0.3 | 27893.2582 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1400.0489 | 1400.0489 | 1400.0489 | 1400.0489 | 1400.0489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9527 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 27034.6301 | 0.2 | 0.3 | 42174.0229 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2910.2082 | 2910.2082 | 2910.2082 | 2910.2082 | 2910.2082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9528 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 26186.2932 | 0.2 | 0.3 | 40850.6174 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3733.8783 | 3733.8783 | 3733.8783 | 3733.8783 | 3733.8783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9529 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16680.9953 | 0.2 | 0.3 | 26022.3526 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3584.0674 | 3584.0674 | 3584.0674 | 3584.0674 | 3584.0674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9530 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16684.1741 | 0.2 | 0.3 | 26027.3115 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3806.6229 | 3806.6229 | 3806.6229 | 3806.6229 | 3806.6229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9531 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 24684.5413 | 0.2 | 0.3 | 38507.8844 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5607.4607 | 5607.4607 | 5607.4607 | 5607.4607 | 5607.4607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9532 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 13968.6067 | 0.2 | 0.3 | 21791.0265 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8366.4676 | 8366.4676 | 8366.4676 | 8366.4676 | 8366.4676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9533 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 17531.6397 | 0.2 | 0.3 | 27349.3579 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9434.0508 | 9434.0508 | 9434.0508 | 9434.0508 | 9434.0508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9534 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 28289.4501 | 0.2 | 0.3 | 44131.5421 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2599.9697 | 2599.9697 | 2599.9697 | 2599.9697 | 2599.9697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9535 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 17100.5801 | 0.2 | 0.3 | 26676.9049 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9176.71 | 9176.71 | 9176.71 | 9176.71 | 9176.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9536 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 20166.0985 | 0.2 | 0.3 | 31459.1136 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6518.1069 | 6518.1069 | 6518.1069 | 6518.1069 | 6518.1069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9537 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16676.7159 | 0.2 | 0.3 | 26015.6768 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9923.5307 | 9923.5307 | 9923.5307 | 9923.5307 | 9923.5307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9538 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9918.2705 | 9918.2705 | 9918.2705 | 9918.2705 | 9918.2705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9539 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10004.1167 | 10004.1167 | 10004.1167 | 10004.1167 | 10004.1167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9540 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16679.4126 | 0.2 | 0.3 | 26019.8837 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9909.0579 | 9909.0579 | 9909.0579 | 9909.0579 | 9909.0579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9541 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 17863.1644 | 0.2 | 0.3 | 27866.5365 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9278.3845 | 9278.3845 | 9278.3845 | 9278.3845 | 9278.3845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9542 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16683.2057 | 0.2 | 0.3 | 26025.8009 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14325.0883 | 14325.0883 | 14325.0883 | 14325.0883 | 14325.0883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9543 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16718.7398 | 0.2 | 0.3 | 26081.2341 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14114.1597 | 14114.1597 | 14114.1597 | 14114.1597 | 14114.1597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9544 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 9676.3957 | 0.2 | 0.3 | 15095.1773 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5565.7819 | 5565.7819 | 5565.7819 | 5565.7819 | 5565.7819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9545 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16676.7159 | 0.2 | 0.3 | 26015.6768 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7310.3678 | 7310.3678 | 7310.3678 | 7310.3678 | 7310.3678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9546 | PEMBROKE PINES | 110100 | Private | 2026 | 5 | Swales | 66.6667 | 16676.4425 | 0.2 | 0.3 | 26015.2502 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9619.9369 | 9619.9369 | 9619.9369 | 9619.9369 | 9619.9369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9547 | PEMBROKE PINES | 110100 | Private | 2026 | 5 | Swales | 66.6667 | 16680.2701 | 0.2 | 0.3 | 26021.2214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2232.2088 | 2232.2088 | 2232.2088 | 2232.2088 | 2232.2088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9548 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 18089.6679 | 0.2 | 0.3 | 28219.882 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3776.6673 | 3776.6673 | 3776.6673 | 3776.6673 | 3776.6673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9549 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16689.9871 | 0.2 | 0.3 | 26036.3798 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5652.646 | 5652.646 | 5652.646 | 5652.646 | 5652.646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9550 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 21501.3401 | 0.2 | 0.3 | 33542.0906 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3464.9958 | 3464.9958 | 3464.9958 | 3464.9958 | 3464.9958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9551 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 25410.5145 | 0.2 | 0.3 | 39640.4026 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11921.6085 | 11921.6085 | 11921.6085 | 11921.6085 | 11921.6085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9552 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 24673.9821 | 0.2 | 0.3 | 38491.412 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4701.124 | 4701.124 | 4701.124 | 4701.124 | 4701.124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9553 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 13758.1453 | 0.2 | 0.3 | 21462.7067 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11056.4366 | 11056.4366 | 11056.4366 | 11056.4366 | 11056.4366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9554 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 18465.1151 | 0.2 | 0.3 | 28805.5795 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7171.9568 | 7171.9568 | 7171.9568 | 7171.9568 | 7171.9568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9555 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 27020.6554 | 0.2 | 0.3 | 42152.2224 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6915.231 | 6915.231 | 6915.231 | 6915.231 | 6915.231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9556 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 28631.9342 | 0.2 | 0.3 | 44665.8174 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5018.135 | 5018.135 | 5018.135 | 5018.135 | 5018.135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9557 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 27916.0531 | 0.2 | 0.3 | 43549.0429 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6231.4778 | 6231.4778 | 6231.4778 | 6231.4778 | 6231.4778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9558 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 27172.5983 | 0.2 | 0.3 | 42389.2533 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1240.4598 | 1240.4598 | 1240.4598 | 1240.4598 | 1240.4598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9559 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 31370.1379 | 0.2 | 0.3 | 48937.4152 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4781.3141 | 4781.3141 | 4781.3141 | 4781.3141 | 4781.3141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9560 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 21981.3496 | 0.2 | 0.3 | 34290.9054 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3302.9899 | 3302.9899 | 3302.9899 | 3302.9899 | 3302.9899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9561 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16679.7125 | 0.2 | 0.3 | 26020.3514 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6343.9513 | 6343.9513 | 6343.9513 | 6343.9513 | 6343.9513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9562 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16675.82 | 0.2 | 0.3 | 26014.2792 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9899 | 5199.9899 | 5199.9899 | 5199.9899 | 5199.9899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9563 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 23711.1271 | 0.2 | 0.3 | 36989.3582 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1664 | 5200.1664 | 5200.1664 | 5200.1664 | 5200.1664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9564 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 31350.9875 | 0.2 | 0.3 | 48907.5406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9312 | 5202.9312 | 5202.9312 | 5202.9312 | 5202.9312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9565 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 23506.0939 | 0.2 | 0.3 | 36669.5065 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.6443 | 5205.6443 | 5205.6443 | 5205.6443 | 5205.6443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9566 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 22729.5611 | 0.2 | 0.3 | 35458.1153 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3723.4405 | 3723.4405 | 3723.4405 | 3723.4405 | 3723.4405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9567 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 30864.4215 | 0.2 | 0.3 | 48148.4976 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4293 | 5200.4293 | 5200.4293 | 5200.4293 | 5200.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9568 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16661.3005 | 0.2 | 0.3 | 25991.6287 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9073.8792 | 9073.8792 | 9073.8792 | 9073.8792 | 9073.8792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9569 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16810.668 | 0.2 | 0.3 | 26224.6421 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6527.1852 | 6527.1852 | 6527.1852 | 6527.1852 | 6527.1852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9570 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 17965.9488 | 0.2 | 0.3 | 28026.8801 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9571 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 14992.0805 | 0.2 | 0.3 | 23387.6455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2458 | 5200.2458 | 5200.2458 | 5200.2458 | 5200.2458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9572 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 25348.6327 | 0.2 | 0.3 | 39543.867 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1880.8299 | 1880.8299 | 1880.8299 | 1880.8299 | 1880.8299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9573 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 17931.8865 | 0.2 | 0.3 | 27973.743 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6736.7206 | 6736.7206 | 6736.7206 | 6736.7206 | 6736.7206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9574 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 23190.0901 | 0.2 | 0.3 | 36176.5406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9956.7785 | 9956.7785 | 9956.7785 | 9956.7785 | 9956.7785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9575 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11060.3666 | 11060.3666 | 11060.3666 | 11060.3666 | 11060.3666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9576 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16680.4212 | 0.2 | 0.3 | 26021.4571 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 666.2973 | 666.2973 | 666.2973 | 666.2973 | 666.2973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9577 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 11793.9443 | 0.2 | 0.3 | 18398.5532 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4485.8992 | 4485.8992 | 4485.8992 | 4485.8992 | 4485.8992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9578 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16676.6305 | 0.2 | 0.3 | 26015.5436 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5353.5492 | 5353.5492 | 5353.5492 | 5353.5492 | 5353.5492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9579 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16447.7306 | 0.2 | 0.3 | 25658.4597 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6127.4929 | 6127.4929 | 6127.4929 | 6127.4929 | 6127.4929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9580 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16675.7141 | 0.2 | 0.3 | 26014.1139 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5505.0918 | 5505.0918 | 5505.0918 | 5505.0918 | 5505.0918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9581 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16770.3137 | 0.2 | 0.3 | 26161.6893 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5651.5617 | 5651.5617 | 5651.5617 | 5651.5617 | 5651.5617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9582 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 10270.2332 | 0.2 | 0.3 | 16021.5638 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1807.9086 | 1807.9086 | 1807.9086 | 1807.9086 | 1807.9086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9583 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 28974.7315 | 0.2 | 0.3 | 45200.5812 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3541.9332 | 3541.9332 | 3541.9332 | 3541.9332 | 3541.9332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9584 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 17091.6934 | 0.2 | 0.3 | 26663.0417 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8188.3927 | 8188.3927 | 8188.3927 | 8188.3927 | 8188.3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9585 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 25353.5579 | 0.2 | 0.3 | 39551.5504 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7826.7624 | 7826.7624 | 7826.7624 | 7826.7624 | 7826.7624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9586 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 31359.2962 | 0.2 | 0.3 | 48920.5021 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7004.4633 | 7004.4633 | 7004.4633 | 7004.4633 | 7004.4633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9587 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 26513.9001 | 0.2 | 0.3 | 41361.6841 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5144.4904 | 5144.4904 | 5144.4904 | 5144.4904 | 5144.4904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9588 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16991.7909 | 0.2 | 0.3 | 26507.1939 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3886.75 | 3886.75 | 3886.75 | 3886.75 | 3886.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9589 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 18090.4686 | 0.2 | 0.3 | 28221.131 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1937.5642 | 1937.5642 | 1937.5642 | 1937.5642 | 1937.5642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9590 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 29514.7115 | 0.2 | 0.3 | 46042.95 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4860.7286 | 4860.7286 | 4860.7286 | 4860.7286 | 4860.7286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9591 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 12209.3237 | 0.2 | 0.3 | 19046.545 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6769.4131 | 6769.4131 | 6769.4131 | 6769.4131 | 6769.4131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9592 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 28615.416 | 0.2 | 0.3 | 44640.049 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7904.5222 | 7904.5222 | 7904.5222 | 7904.5222 | 7904.5222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9593 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 18561.0433 | 0.2 | 0.3 | 28955.2275 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13159.2817 | 13159.2817 | 13159.2817 | 13159.2817 | 13159.2817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9594 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 19383.9862 | 0.2 | 0.3 | 30239.0185 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11368.4955 | 11368.4955 | 11368.4955 | 11368.4955 | 11368.4955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9595 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 19900.1172 | 0.2 | 0.3 | 31044.1828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9619.6505 | 9619.6505 | 9619.6505 | 9619.6505 | 9619.6505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9596 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 31368.7121 | 0.2 | 0.3 | 48935.1909 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6.3698 | 6.3698 | 6.3698 | 6.3698 | 6.3698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9597 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 31361.5405 | 0.2 | 0.3 | 48924.0032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10421.5075 | 10421.5075 | 10421.5075 | 10421.5075 | 10421.5075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9598 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 21994.2283 | 0.2 | 0.3 | 34310.9962 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0109 | 5201.0109 | 5201.0109 | 5201.0109 | 5201.0109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9599 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 22506.0711 | 0.2 | 0.3 | 35109.4709 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5219.1512 | 5219.1512 | 5219.1512 | 5219.1512 | 5219.1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9600 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 23179.0166 | 0.2 | 0.3 | 36159.2659 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5136.1751 | 5136.1751 | 5136.1751 | 5136.1751 | 5136.1751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9601 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 27527.5169 | 0.2 | 0.3 | 42942.9263 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6764.8726 | 6764.8726 | 6764.8726 | 6764.8726 | 6764.8726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9602 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 27361.4069 | 0.2 | 0.3 | 42683.7948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3632.8293 | 3632.8293 | 3632.8293 | 3632.8293 | 3632.8293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9603 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 17134.631 | 0.2 | 0.3 | 26730.0244 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6403.4698 | 6403.4698 | 6403.4698 | 6403.4698 | 6403.4698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9604 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2025 | 0.2 | 0.3 | 26021.116 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8860.3327 | 8860.3327 | 8860.3327 | 8860.3327 | 8860.3327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9605 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16687.1052 | 0.2 | 0.3 | 26031.8841 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1904.7689 | 1904.7689 | 1904.7689 | 1904.7689 | 1904.7689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9606 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16900.1188 | 0.2 | 0.3 | 26364.1853 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6415.1608 | 6415.1608 | 6415.1608 | 6415.1608 | 6415.1608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9607 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16174.7669 | 0.2 | 0.3 | 25232.6363 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10400.7164 | 10400.7164 | 10400.7164 | 10400.7164 | 10400.7164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9608 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 24197.5622 | 0.2 | 0.3 | 37748.197 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9609 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 15023.4853 | 0.2 | 0.3 | 23436.637 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6701 | 5201.6701 | 5201.6701 | 5201.6701 | 5201.6701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9610 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 31034.282 | 0.2 | 0.3 | 48413.4799 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5207.4004 | 5207.4004 | 5207.4004 | 5207.4004 | 5207.4004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9611 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16686.857 | 0.2 | 0.3 | 26031.4969 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7553.757 | 7553.757 | 7553.757 | 7553.757 | 7553.757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9612 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16678.8191 | 0.2 | 0.3 | 26018.9578 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6012.7776 | 6012.7776 | 6012.7776 | 6012.7776 | 6012.7776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9613 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16677.057 | 0.2 | 0.3 | 26016.2089 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6089.2536 | 6089.2536 | 6089.2536 | 6089.2536 | 6089.2536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9614 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16679.8751 | 0.2 | 0.3 | 26020.6052 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9016.0839 | 9016.0839 | 9016.0839 | 9016.0839 | 9016.0839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9615 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16677.9612 | 0.2 | 0.3 | 26017.6195 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 29.8069 | 29.8069 | 29.8069 | 29.8069 | 29.8069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9616 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16679.1409 | 0.2 | 0.3 | 26019.4598 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7601 | 5200.7601 | 5200.7601 | 5200.7601 | 5200.7601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9617 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16677.0478 | 0.2 | 0.3 | 26016.1946 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9412.5516 | 9412.5516 | 9412.5516 | 9412.5516 | 9412.5516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9618 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16678.8469 | 0.2 | 0.3 | 26019.0011 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9738.9915 | 9738.9915 | 9738.9915 | 9738.9915 | 9738.9915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9619 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16680.8781 | 0.2 | 0.3 | 26022.1698 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4146.023 | 4146.023 | 4146.023 | 4146.023 | 4146.023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9620 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6623 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.7764 | 5204.7764 | 5204.7764 | 5204.7764 | 5204.7764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9621 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16669.3023 | 0.2 | 0.3 | 26004.1115 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1998.0082 | 1998.0082 | 1998.0082 | 1998.0082 | 1998.0082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9622 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3953 | 0.2 | 0.3 | 26018.2967 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 899.9349 | 899.9349 | 899.9349 | 899.9349 | 899.9349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9623 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1544 | 5203.1544 | 5203.1544 | 5203.1544 | 5203.1544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9624 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16685.4353 | 0.2 | 0.3 | 26029.279 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5982.8979 | 5982.8979 | 5982.8979 | 5982.8979 | 5982.8979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9625 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 21181.8203 | 0.2 | 0.3 | 33043.6397 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5284.5427 | 5284.5427 | 5284.5427 | 5284.5427 | 5284.5427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9626 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 13422.5025 | 0.2 | 0.3 | 20939.104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5361.8248 | 5361.8248 | 5361.8248 | 5361.8248 | 5361.8248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9627 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 26502.7197 | 0.2 | 0.3 | 41344.2427 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6477.2321 | 6477.2321 | 6477.2321 | 6477.2321 | 6477.2321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9628 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 20832.7485 | 0.2 | 0.3 | 32499.0876 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8571.0042 | 8571.0042 | 8571.0042 | 8571.0042 | 8571.0042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9629 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 19124.9759 | 0.2 | 0.3 | 29834.9625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9630 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 17569.1567 | 0.2 | 0.3 | 27407.8845 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8340.2937 | 8340.2937 | 8340.2937 | 8340.2937 | 8340.2937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9631 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16678.2932 | 0.2 | 0.3 | 26018.1374 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9444.7541 | 9444.7541 | 9444.7541 | 9444.7541 | 9444.7541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9632 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16677.2627 | 0.2 | 0.3 | 26016.5298 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8707.5863 | 8707.5863 | 8707.5863 | 8707.5863 | 8707.5863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9633 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16679.6354 | 0.2 | 0.3 | 26020.2312 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7967.0547 | 7967.0547 | 7967.0547 | 7967.0547 | 7967.0547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9634 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16678.6389 | 0.2 | 0.3 | 26018.6766 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8134.7829 | 8134.7829 | 8134.7829 | 8134.7829 | 8134.7829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9635 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16678.9031 | 0.2 | 0.3 | 26019.0889 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8966.4175 | 8966.4175 | 8966.4175 | 8966.4175 | 8966.4175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9636 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16677.2189 | 0.2 | 0.3 | 26016.4615 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5481.2355 | 5481.2355 | 5481.2355 | 5481.2355 | 5481.2355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9637 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16678.4922 | 0.2 | 0.3 | 26018.4478 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5235.8353 | 5235.8353 | 5235.8353 | 5235.8353 | 5235.8353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9638 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16680.2433 | 0.2 | 0.3 | 26021.1795 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7985.0252 | 7985.0252 | 7985.0252 | 7985.0252 | 7985.0252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9639 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16681.4306 | 0.2 | 0.3 | 26023.0317 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3077.5882 | 3077.5882 | 3077.5882 | 3077.5882 | 3077.5882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9640 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16750.7188 | 0.2 | 0.3 | 26131.1213 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7791.3581 | 7791.3581 | 7791.3581 | 7791.3581 | 7791.3581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9641 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16678.4137 | 0.2 | 0.3 | 26018.3254 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5497.5711 | 5497.5711 | 5497.5711 | 5497.5711 | 5497.5711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9642 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16680.5132 | 0.2 | 0.3 | 26021.6006 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1524.5268 | 1524.5268 | 1524.5268 | 1524.5268 | 1524.5268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9643 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 21663.7035 | 0.2 | 0.3 | 33795.3774 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5047.8089 | 5047.8089 | 5047.8089 | 5047.8089 | 5047.8089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9644 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 12799.7067 | 0.2 | 0.3 | 19967.5425 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.044 | 5200.044 | 5200.044 | 5200.044 | 5200.044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9645 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 27854.755 | 0.2 | 0.3 | 43453.4178 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9923 | 5199.9923 | 5199.9923 | 5199.9923 | 5199.9923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9646 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 8703.3601 | 0.2 | 0.3 | 13577.2417 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5431.1656 | 5431.1656 | 5431.1656 | 5431.1656 | 5431.1656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9647 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16974.4159 | 0.2 | 0.3 | 26480.0888 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7453.0807 | 7453.0807 | 7453.0807 | 7453.0807 | 7453.0807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9648 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 28397.2034 | 0.2 | 0.3 | 44299.6373 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8043.8274 | 8043.8274 | 8043.8274 | 8043.8274 | 8043.8274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9649 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 15507.3143 | 0.2 | 0.3 | 24191.4103 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6523.1852 | 6523.1852 | 6523.1852 | 6523.1852 | 6523.1852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9650 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16876.4163 | 0.2 | 0.3 | 26327.2095 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5036.0288 | 5036.0288 | 5036.0288 | 5036.0288 | 5036.0288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9651 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 25417.7343 | 0.2 | 0.3 | 39651.6656 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2883.6258 | 2883.6258 | 2883.6258 | 2883.6258 | 2883.6258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9652 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 31359.6352 | 0.2 | 0.3 | 48921.0309 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9961.1381 | 9961.1381 | 9961.1381 | 9961.1381 | 9961.1381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9653 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 17674.6884 | 0.2 | 0.3 | 27572.5139 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1062 | 5200.1062 | 5200.1062 | 5200.1062 | 5200.1062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9654 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16679.3322 | 0.2 | 0.3 | 26019.7582 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6295.6398 | 6295.6398 | 6295.6398 | 6295.6398 | 6295.6398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9655 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 10655.6371 | 0.2 | 0.3 | 16622.7939 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5918.4829 | 5918.4829 | 5918.4829 | 5918.4829 | 5918.4829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9656 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 31358.8254 | 0.2 | 0.3 | 48919.7676 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5514.2356 | 5514.2356 | 5514.2356 | 5514.2356 | 5514.2356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9657 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 20470.0481 | 0.2 | 0.3 | 31933.275 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5712.0156 | 5712.0156 | 5712.0156 | 5712.0156 | 5712.0156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9658 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 19381.0363 | 0.2 | 0.3 | 30234.4166 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4880.9155 | 4880.9155 | 4880.9155 | 4880.9155 | 4880.9155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9659 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 31629.1692 | 0.2 | 0.3 | 49341.504 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6428.9232 | 6428.9232 | 6428.9232 | 6428.9232 | 6428.9232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9660 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 19043.0495 | 0.2 | 0.3 | 29707.1572 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9449 | 5199.9449 | 5199.9449 | 5199.9449 | 5199.9449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9661 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 18466.6909 | 0.2 | 0.3 | 28808.0379 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13832.7401 | 13832.7401 | 13832.7401 | 13832.7401 | 13832.7401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9662 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 30885.1167 | 0.2 | 0.3 | 48180.782 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9663 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 12971.8447 | 0.2 | 0.3 | 20236.0778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9664 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 5657.9196 | 0.2 | 0.3 | 8826.3546 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5426.324 | 5426.324 | 5426.324 | 5426.324 | 5426.324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9665 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 28782.8503 | 0.2 | 0.3 | 44901.2465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6344.7066 | 6344.7066 | 6344.7066 | 6344.7066 | 6344.7066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9666 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 5680.0968 | 0.2 | 0.3 | 8860.951 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1118 | 2600.1118 | 2600.1118 | 2600.1118 | 2600.1118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9667 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 21401.8437 | 0.2 | 0.3 | 33386.8761 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1722 | 2600.1722 | 2600.1722 | 2600.1722 | 2600.1722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9668 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.6477 | 0.2 | 0.3 | 26023.3705 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5000.6581 | 5000.6581 | 5000.6581 | 5000.6581 | 5000.6581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9669 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16682.1839 | 0.2 | 0.3 | 26024.2069 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5705.0786 | 5705.0786 | 5705.0786 | 5705.0786 | 5705.0786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9670 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 31363.0287 | 0.2 | 0.3 | 48926.3247 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9519.7249 | 9519.7249 | 9519.7249 | 9519.7249 | 9519.7249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9671 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16683.6727 | 0.2 | 0.3 | 26026.5294 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9162 | 5199.9162 | 5199.9162 | 5199.9162 | 5199.9162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9672 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 24357.3921 | 0.2 | 0.3 | 37997.5316 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1698 | 5200.1698 | 5200.1698 | 5200.1698 | 5200.1698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9673 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16676.2886 | 0.2 | 0.3 | 26015.0102 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6785.0734 | 6785.0734 | 6785.0734 | 6785.0734 | 6785.0734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9674 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 30912.5173 | 0.2 | 0.3 | 48223.5269 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6321.0042 | 6321.0042 | 6321.0042 | 6321.0042 | 6321.0042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9675 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16674.4784 | 0.2 | 0.3 | 26012.1863 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 594.2128 | 594.2128 | 594.2128 | 594.2128 | 594.2128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9676 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6624 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7233.9154 | 7233.9154 | 7233.9154 | 7233.9154 | 7233.9154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9677 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 27407.7099 | 0.2 | 0.3 | 42756.0275 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5266.3161 | 5266.3161 | 5266.3161 | 5266.3161 | 5266.3161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9678 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 20641.8389 | 0.2 | 0.3 | 32201.2687 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4389.7932 | 4389.7932 | 4389.7932 | 4389.7932 | 4389.7932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9679 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16676.5785 | 0.2 | 0.3 | 26015.4625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6620.5244 | 6620.5244 | 6620.5244 | 6620.5244 | 6620.5244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9680 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 19627.6246 | 0.2 | 0.3 | 30619.0944 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6469.6214 | 6469.6214 | 6469.6214 | 6469.6214 | 6469.6214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9681 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 16687.4342 | 0.2 | 0.3 | 26032.3974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6075.758 | 6075.758 | 6075.758 | 6075.758 | 6075.758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9682 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 30146.1425 | 0.2 | 0.3 | 47027.9824 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5478.8846 | 5478.8846 | 5478.8846 | 5478.8846 | 5478.8846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9683 | PEMBROKE PINES | 110100 | Public | 2026 | 5 | Swales | 66.6667 | 17373.1515 | 0.2 | 0.3 | 27102.1164 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9634.8442 | 9634.8442 | 9634.8442 | 9634.8442 | 9634.8442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9684 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 34173.7046 | 0.2 | 0.3 | 53310.9792 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6626.857 | 6626.857 | 6626.857 | 6626.857 | 6626.857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9685 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 29.7929 | 0.2 | 0.3 | 46.477 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4917.6511 | 4917.6511 | 4917.6511 | 4917.6511 | 4917.6511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9686 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.2549 | 0.2 | 0.3 | 26022.7577 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8992.8395 | 8992.8395 | 8992.8395 | 8992.8395 | 8992.8395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9687 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.3637 | 0.2 | 0.3 | 26022.9274 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8422.6088 | 8422.6088 | 8422.6088 | 8422.6088 | 8422.6088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9688 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 31363.2476 | 0.2 | 0.3 | 48926.6663 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5349.3922 | 5349.3922 | 5349.3922 | 5349.3922 | 5349.3922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9689 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16682.3145 | 0.2 | 0.3 | 26024.4107 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6559.6263 | 6559.6263 | 6559.6263 | 6559.6263 | 6559.6263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9690 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16683.2775 | 0.2 | 0.3 | 26025.913 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 151.8958 | 151.8958 | 151.8958 | 151.8958 | 151.8958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9691 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16683.7011 | 0.2 | 0.3 | 26026.5738 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7967.9666 | 7967.9666 | 7967.9666 | 7967.9666 | 7967.9666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9692 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 31354.0165 | 0.2 | 0.3 | 48912.2658 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5733.3347 | 5733.3347 | 5733.3347 | 5733.3347 | 5733.3347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9693 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16683.2127 | 0.2 | 0.3 | 26025.8118 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5318.2644 | 5318.2644 | 5318.2644 | 5318.2644 | 5318.2644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9694 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16683.5509 | 0.2 | 0.3 | 26026.3395 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6437.9976 | 6437.9976 | 6437.9976 | 6437.9976 | 6437.9976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9695 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 23782.682 | 0.2 | 0.3 | 37100.9839 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4420.064 | 4420.064 | 4420.064 | 4420.064 | 4420.064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9696 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 24259.3202 | 0.2 | 0.3 | 37844.5395 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5120.4184 | 5120.4184 | 5120.4184 | 5120.4184 | 5120.4184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9697 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.05 | 0.2 | 0.3 | 26022.438 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 411.0022 | 411.0022 | 411.0022 | 411.0022 | 411.0022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9698 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 17034.6337 | 0.2 | 0.3 | 26574.0285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 328.7977 | 328.7977 | 328.7977 | 328.7977 | 328.7977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9699 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 26806.9344 | 0.2 | 0.3 | 41818.8177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8174.4295 | 8174.4295 | 8174.4295 | 8174.4295 | 8174.4295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9700 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16709.9945 | 0.2 | 0.3 | 26067.5914 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12918.3939 | 12918.3939 | 12918.3939 | 12918.3939 | 12918.3939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9701 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 6174.727 | 0.2 | 0.3 | 9632.5741 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5252.0535 | 5252.0535 | 5252.0535 | 5252.0535 | 5252.0535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9702 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16685.1149 | 0.2 | 0.3 | 26028.7793 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5446.5818 | 5446.5818 | 5446.5818 | 5446.5818 | 5446.5818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9703 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16685.7381 | 0.2 | 0.3 | 26029.7515 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5622.0868 | 5622.0868 | 5622.0868 | 5622.0868 | 5622.0868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9704 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 31361.214 | 0.2 | 0.3 | 48923.4938 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 25.173 | 25.173 | 25.173 | 25.173 | 25.173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9705 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.1323 | 0.2 | 0.3 | 26022.5664 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 711.5247 | 711.5247 | 711.5247 | 711.5247 | 711.5247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9706 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.9105 | 0.2 | 0.3 | 26023.7804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 389.1262 | 389.1262 | 389.1262 | 389.1262 | 389.1262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9707 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.5097 | 0.2 | 0.3 | 26023.1552 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2798.4685 | 2798.4685 | 2798.4685 | 2798.4685 | 2798.4685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9708 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 31361.71 | 0.2 | 0.3 | 48924.2676 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9709 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.2331 | 0.2 | 0.3 | 26022.7237 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2401.9512 | 2401.9512 | 2401.9512 | 2401.9512 | 2401.9512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9710 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.3637 | 0.2 | 0.3 | 26022.9274 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2798.3816 | 2798.3816 | 2798.3816 | 2798.3816 | 2798.3816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9711 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 17652.0608 | 0.2 | 0.3 | 27537.2148 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4468.0707 | 4468.0707 | 4468.0707 | 4468.0707 | 4468.0707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9712 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 30365.0613 | 0.2 | 0.3 | 47369.4956 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7859.6468 | 7859.6468 | 7859.6468 | 7859.6468 | 7859.6468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9713 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16690.4402 | 0.2 | 0.3 | 26037.0867 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7998.2069 | 7998.2069 | 7998.2069 | 7998.2069 | 7998.2069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9714 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 11609.1452 | 0.2 | 0.3 | 18110.2665 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9715 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 8552.3439 | 0.2 | 0.3 | 13341.6565 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7992.5566 | 7992.5566 | 7992.5566 | 7992.5566 | 7992.5566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9716 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16684.8197 | 0.2 | 0.3 | 26028.3188 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7421.9811 | 7421.9811 | 7421.9811 | 7421.9811 | 7421.9811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9717 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16685.4647 | 0.2 | 0.3 | 26029.325 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1187 | 5200.1187 | 5200.1187 | 5200.1187 | 5200.1187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9718 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 31357.2936 | 0.2 | 0.3 | 48917.378 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7924.36 | 7924.36 | 7924.36 | 7924.36 | 7924.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9719 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16680.1649 | 0.2 | 0.3 | 26021.0573 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4851 | 5200.4851 | 5200.4851 | 5200.4851 | 5200.4851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9720 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6734.1018 | 6734.1018 | 6734.1018 | 6734.1018 | 6734.1018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9721 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.0052 | 0.2 | 0.3 | 26022.3681 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8486 | 5199.8486 | 5199.8486 | 5199.8486 | 5199.8486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9722 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 31362.1097 | 0.2 | 0.3 | 48924.8911 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5727.196 | 5727.196 | 5727.196 | 5727.196 | 5727.196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9723 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.8411 | 0.2 | 0.3 | 26023.6722 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6277.3183 | 6277.3183 | 6277.3183 | 6277.3183 | 6277.3183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9724 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.6371 | 0.2 | 0.3 | 26023.3539 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5110.7147 | 5110.7147 | 5110.7147 | 5110.7147 | 5110.7147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9725 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16683.5905 | 0.2 | 0.3 | 26026.4012 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 435.7928 | 435.7928 | 435.7928 | 435.7928 | 435.7928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9726 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16945.3393 | 0.2 | 0.3 | 26434.7294 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5279.1496 | 5279.1496 | 5279.1496 | 5279.1496 | 5279.1496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9727 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 11097.073 | 0.2 | 0.3 | 17311.4339 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5799.1787 | 5799.1787 | 5799.1787 | 5799.1787 | 5799.1787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9728 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16680.5435 | 0.2 | 0.3 | 26021.6479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6345.7518 | 6345.7518 | 6345.7518 | 6345.7518 | 6345.7518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9729 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 31354.2188 | 0.2 | 0.3 | 48912.5813 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7413.3809 | 7413.3809 | 7413.3809 | 7413.3809 | 7413.3809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9730 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16682.2713 | 0.2 | 0.3 | 26024.3433 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5957.7055 | 5957.7055 | 5957.7055 | 5957.7055 | 5957.7055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9731 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16683.2775 | 0.2 | 0.3 | 26025.913 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5373.0559 | 5373.0559 | 5373.0559 | 5373.0559 | 5373.0559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9732 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16683.3291 | 0.2 | 0.3 | 26025.9934 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.81139 | 0.81139 | 0.81139 | 0.81139 | 0.81139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9733 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 31356.9488 | 0.2 | 0.3 | 48916.8401 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6777.162 | 6777.162 | 6777.162 | 6777.162 | 6777.162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9734 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16683.5845 | 0.2 | 0.3 | 26026.3918 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1058.515 | 1058.515 | 1058.515 | 1058.515 | 1058.515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9735 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16684.0977 | 0.2 | 0.3 | 26027.1925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7933.4146 | 7933.4146 | 7933.4146 | 7933.4146 | 7933.4146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9736 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16685.0412 | 0.2 | 0.3 | 26028.6643 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5951.6303 | 5951.6303 | 5951.6303 | 5951.6303 | 5951.6303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9737 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 17850.2557 | 0.2 | 0.3 | 27846.3989 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8791.7558 | 8791.7558 | 8791.7558 | 8791.7558 | 8791.7558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9738 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 5895.7974 | 0.2 | 0.3 | 9197.4439 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6891.6117 | 6891.6117 | 6891.6117 | 6891.6117 | 6891.6117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9739 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 7634.9797 | 0.2 | 0.3 | 11910.5684 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5019.7574 | 5019.7574 | 5019.7574 | 5019.7574 | 5019.7574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9740 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 27519.0807 | 0.2 | 0.3 | 42929.7658 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5057.8332 | 5057.8332 | 5057.8332 | 5057.8332 | 5057.8332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9741 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16682.8993 | 0.2 | 0.3 | 26025.3229 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5032.7797 | 5032.7797 | 5032.7797 | 5032.7797 | 5032.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9742 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16683.8243 | 0.2 | 0.3 | 26026.766 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 940.1448 | 940.1448 | 940.1448 | 940.1448 | 940.1448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9743 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16684.1057 | 0.2 | 0.3 | 26027.2049 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9410.8222 | 9410.8222 | 9410.8222 | 9410.8222 | 9410.8222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9744 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 31358.1595 | 0.2 | 0.3 | 48918.7288 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5271.0075 | 5271.0075 | 5271.0075 | 5271.0075 | 5271.0075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9745 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.0121 | 0.2 | 0.3 | 26022.3788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3027.9708 | 3027.9708 | 3027.9708 | 3027.9708 | 3027.9708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9746 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.6371 | 0.2 | 0.3 | 26023.3539 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5274.6511 | 5274.6511 | 5274.6511 | 5274.6511 | 5274.6511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9747 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.3633 | 0.2 | 0.3 | 26022.9268 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3807.0665 | 3807.0665 | 3807.0665 | 3807.0665 | 3807.0665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9748 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 31355.1169 | 0.2 | 0.3 | 48913.9823 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4504.5229 | 4504.5229 | 4504.5229 | 4504.5229 | 4504.5229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9749 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 4433.6833 | 0.2 | 0.3 | 6916.546 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8689.6832 | 8689.6832 | 8689.6832 | 8689.6832 | 8689.6832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9750 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16368.5943 | 0.2 | 0.3 | 25535.0072 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9391.4798 | 9391.4798 | 9391.4798 | 9391.4798 | 9391.4798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9751 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 9046.7988 | 0.2 | 0.3 | 14113.0061 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3767.2662 | 3767.2662 | 3767.2662 | 3767.2662 | 3767.2662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9752 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 23628.6968 | 0.2 | 0.3 | 36860.767 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7424.8013 | 7424.8013 | 7424.8013 | 7424.8013 | 7424.8013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9753 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 9032.452 | 0.2 | 0.3 | 14090.6251 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9754 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16359.0113 | 0.2 | 0.3 | 25520.0577 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4412.0856 | 4412.0856 | 4412.0856 | 4412.0856 | 4412.0856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9755 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.5877 | 0.2 | 0.3 | 26023.2768 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5406.0614 | 5406.0614 | 5406.0614 | 5406.0614 | 5406.0614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9756 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 31356.1186 | 0.2 | 0.3 | 48915.545 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5526.9165 | 5526.9165 | 5526.9165 | 5526.9165 | 5526.9165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9757 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.3589 | 0.2 | 0.3 | 26022.9199 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3260.1538 | 3260.1538 | 3260.1538 | 3260.1538 | 3260.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9758 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16681.6371 | 0.2 | 0.3 | 26023.3539 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4375.9204 | 4375.9204 | 4375.9204 | 4375.9204 | 4375.9204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9759 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16682.9183 | 0.2 | 0.3 | 26025.3525 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4342.8447 | 4342.8447 | 4342.8447 | 4342.8447 | 4342.8447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9760 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 19129.243 | 0.2 | 0.3 | 29841.6191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6943.6323 | 6943.6323 | 6943.6323 | 6943.6323 | 6943.6323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9761 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16683.7559 | 0.2 | 0.3 | 26026.6593 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6877.9048 | 6877.9048 | 6877.9048 | 6877.9048 | 6877.9048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9762 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16684.0977 | 0.2 | 0.3 | 26027.1925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5215.921 | 5215.921 | 5215.921 | 5215.921 | 5215.921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9763 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 28252.4887 | 0.2 | 0.3 | 44073.8824 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0395 | 5200.0395 | 5200.0395 | 5200.0395 | 5200.0395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9764 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 9501.4647 | 0.2 | 0.3 | 14822.2849 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8905.4246 | 8905.4246 | 8905.4246 | 8905.4246 | 8905.4246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9765 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 8725.1889 | 0.2 | 0.3 | 13611.2947 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7543.834 | 7543.834 | 7543.834 | 7543.834 | 7543.834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9766 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 15406.8179 | 0.2 | 0.3 | 24034.636 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7827.8539 | 7827.8539 | 7827.8539 | 7827.8539 | 7827.8539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9767 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 31358.3039 | 0.2 | 0.3 | 48918.954 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9768 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16684.1117 | 0.2 | 0.3 | 26027.2143 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7097.6142 | 7097.6142 | 7097.6142 | 7097.6142 | 7097.6142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9769 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16684.0977 | 0.2 | 0.3 | 26027.1925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5261.5567 | 5261.5567 | 5261.5567 | 5261.5567 | 5261.5567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9770 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16685.0513 | 0.2 | 0.3 | 26028.68 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5642.8122 | 5642.8122 | 5642.8122 | 5642.8122 | 5642.8122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9771 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 15980.6909 | 0.2 | 0.3 | 24929.8778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2074.6335 | 2074.6335 | 2074.6335 | 2074.6335 | 2074.6335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9772 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16682.2519 | 0.2 | 0.3 | 26024.3129 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8699 | 5200.8699 | 5200.8699 | 5200.8699 | 5200.8699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9773 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16683.0041 | 0.2 | 0.3 | 26025.4864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7809.6366 | 7809.6366 | 7809.6366 | 7809.6366 | 7809.6366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9774 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 26468.9028 | 0.2 | 0.3 | 41291.4884 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.6074 | 5199.6074 | 5199.6074 | 5199.6074 | 5199.6074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9775 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 19719.404 | 0.2 | 0.3 | 30762.2702 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.6143 | 5199.6143 | 5199.6143 | 5199.6143 | 5199.6143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9776 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 10081.6272 | 0.2 | 0.3 | 15727.3384 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7758.8357 | 7758.8357 | 7758.8357 | 7758.8357 | 7758.8357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9777 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 9808.2369 | 0.2 | 0.3 | 15300.8495 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7206.6372 | 7206.6372 | 7206.6372 | 7206.6372 | 7206.6372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9778 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 25427.2558 | 0.2 | 0.3 | 39666.519 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4453.1545 | 4453.1545 | 4453.1545 | 4453.1545 | 4453.1545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9779 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16683.0167 | 0.2 | 0.3 | 26025.5061 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7084.3927 | 7084.3927 | 7084.3927 | 7084.3927 | 7084.3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9780 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 27320.862 | 0.2 | 0.3 | 42620.5447 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7067.1246 | 7067.1246 | 7067.1246 | 7067.1246 | 7067.1246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9781 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 26150.5809 | 0.2 | 0.3 | 40794.9063 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6653.6414 | 6653.6414 | 6653.6414 | 6653.6414 | 6653.6414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9782 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 24441.2469 | 0.2 | 0.3 | 38128.3451 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.4269 | 5199.4269 | 5199.4269 | 5199.4269 | 5199.4269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9783 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 14882.9049 | 0.2 | 0.3 | 23217.3317 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.7735 | 5199.7735 | 5199.7735 | 5199.7735 | 5199.7735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9784 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 8600.5322 | 0.2 | 0.3 | 13416.8302 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6765.5132 | 6765.5132 | 6765.5132 | 6765.5132 | 6765.5132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9785 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 22043.9305 | 0.2 | 0.3 | 34388.5315 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7277.6095 | 7277.6095 | 7277.6095 | 7277.6095 | 7277.6095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9786 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 8342.4214 | 0.2 | 0.3 | 13014.1774 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3128.5404 | 3128.5404 | 3128.5404 | 3128.5404 | 3128.5404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9787 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 9303.6088 | 0.2 | 0.3 | 14513.6297 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5390.5555 | 5390.5555 | 5390.5555 | 5390.5555 | 5390.5555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9788 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 30840.8623 | 0.2 | 0.3 | 48111.7452 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3444.3156 | 3444.3156 | 3444.3156 | 3444.3156 | 3444.3156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9789 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16683.5509 | 0.2 | 0.3 | 26026.3395 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6989.1042 | 6989.1042 | 6989.1042 | 6989.1042 | 6989.1042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9790 | PEMBROKE PINES | 110100 | Public | 2030 | 5 | Swales | 66.6667 | 16235.6265 | 0.2 | 0.3 | 25327.5774 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6584.7147 | 6584.7147 | 6584.7147 | 6584.7147 | 6584.7147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9791 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1542 | 0.2 | 0.3 | 26005.4406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9086 | 5200.9086 | 5200.9086 | 5200.9086 | 5200.9086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9792 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8809 | 0.2 | 0.3 | 26005.0142 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6926.7721 | 6926.7721 | 6926.7721 | 6926.7721 | 6926.7721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9793 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8809 | 0.2 | 0.3 | 26005.0142 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5232.2372 | 5232.2372 | 5232.2372 | 5232.2372 | 5232.2372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9794 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.6129 | 0.2 | 0.3 | 26004.5961 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8161.7048 | 8161.7048 | 8161.7048 | 8161.7048 | 8161.7048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9795 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.7973 | 0.2 | 0.3 | 26006.4437 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6900.8857 | 6900.8857 | 6900.8857 | 6900.8857 | 6900.8857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9796 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.9744 | 0.2 | 0.3 | 26006.7201 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4433.5288 | 4433.5288 | 4433.5288 | 4433.5288 | 4433.5288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9797 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.701 | 0.2 | 0.3 | 26006.2936 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5420.3376 | 5420.3376 | 5420.3376 | 5420.3376 | 5420.3376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9798 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.536 | 0.2 | 0.3 | 26006.0362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5252.3836 | 5252.3836 | 5252.3836 | 5252.3836 | 5252.3836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9799 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1279 | 0.2 | 0.3 | 26005.3995 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 941.7079 | 941.7079 | 941.7079 | 941.7079 | 941.7079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9800 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1542 | 0.2 | 0.3 | 26005.4406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5025.7559 | 5025.7559 | 5025.7559 | 5025.7559 | 5025.7559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9801 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5394.7604 | 5394.7604 | 5394.7604 | 5394.7604 | 5394.7604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9802 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1094 | 0.2 | 0.3 | 26005.3707 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7511.2856 | 7511.2856 | 7511.2856 | 7511.2856 | 7511.2856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9803 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31340.4031 | 0.2 | 0.3 | 48891.0289 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5260.3199 | 5260.3199 | 5260.3199 | 5260.3199 | 5260.3199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9804 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.5129 | 0.2 | 0.3 | 26006.0001 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2925.7688 | 2925.7688 | 2925.7688 | 2925.7688 | 2925.7688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9805 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.9745 | 0.2 | 0.3 | 26006.7202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10217.3907 | 10217.3907 | 10217.3907 | 10217.3907 | 10217.3907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9806 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.701 | 0.2 | 0.3 | 26006.2936 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7470.7455 | 7470.7455 | 7470.7455 | 7470.7455 | 7470.7455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9807 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2460.4 | 2460.4 | 2460.4 | 2460.4 | 2460.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9808 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.9698 | 0.2 | 0.3 | 26006.7129 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2335.2341 | 2335.2341 | 2335.2341 | 2335.2341 | 2335.2341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9809 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 21657.5726 | 0.2 | 0.3 | 33785.8133 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4982.8362 | 4982.8362 | 4982.8362 | 4982.8362 | 4982.8362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9810 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.1397 | 0.2 | 0.3 | 26003.858 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10247.4573 | 10247.4573 | 10247.4573 | 10247.4573 | 10247.4573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9811 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16678.7588 | 0.2 | 0.3 | 26018.8637 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6197.3048 | 6197.3048 | 6197.3048 | 6197.3048 | 6197.3048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9812 | PEMBROKE PINES | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 34885.9487 | 0.2 | 0.3 | 54422.0799 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6411.719 | 6411.719 | 6411.719 | 6411.719 | 6411.719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9813 | PEMBROKE PINES | 110404 | Public | 2030 | 5 | Swales | 66.6667 | 16978.1779 | 0.2 | 0.3 | 26485.9575 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 905.8922 | 905.8922 | 905.8922 | 905.8922 | 905.8922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9814 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.701 | 0.2 | 0.3 | 26006.2936 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5788.3781 | 5788.3781 | 5788.3781 | 5788.3781 | 5788.3781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9815 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6686.4964 | 6686.4964 | 6686.4964 | 6686.4964 | 6686.4964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9816 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1543 | 0.2 | 0.3 | 26005.4407 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7109.1228 | 7109.1228 | 7109.1228 | 7109.1228 | 7109.1228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9817 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.3558 | 0.2 | 0.3 | 26005.755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5152.353 | 5152.353 | 5152.353 | 5152.353 | 5152.353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9818 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31337.581 | 0.2 | 0.3 | 48886.6264 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6482.7901 | 6482.7901 | 6482.7901 | 6482.7901 | 6482.7901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9819 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8645 | 0.2 | 0.3 | 26004.9886 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4276.9406 | 4276.9406 | 4276.9406 | 4276.9406 | 4276.9406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9820 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1542 | 0.2 | 0.3 | 26005.4406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4260.0629 | 4260.0629 | 4260.0629 | 4260.0629 | 4260.0629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9821 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1542 | 0.2 | 0.3 | 26005.4406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7689.5167 | 7689.5167 | 7689.5167 | 7689.5167 | 7689.5167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9822 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.364 | 0.2 | 0.3 | 26005.7678 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5276.7788 | 5276.7788 | 5276.7788 | 5276.7788 | 5276.7788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9823 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 19050.0088 | 0.2 | 0.3 | 29718.0137 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8307.1392 | 8307.1392 | 8307.1392 | 8307.1392 | 8307.1392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9824 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1062 | 0.2 | 0.3 | 26005.3657 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4356.5381 | 4356.5381 | 4356.5381 | 4356.5381 | 4356.5381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9825 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2748.0488 | 2748.0488 | 2748.0488 | 2748.0488 | 2748.0488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9826 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5506.3993 | 5506.3993 | 5506.3993 | 5506.3993 | 5506.3993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9827 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.5985 | 0.2 | 0.3 | 26006.1336 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7728.4665 | 7728.4665 | 7728.4665 | 7728.4665 | 7728.4665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9828 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31342.2547 | 0.2 | 0.3 | 48893.9173 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6266.1651 | 6266.1651 | 6266.1651 | 6266.1651 | 6266.1651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9829 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16668.9002 | 0.2 | 0.3 | 26003.4843 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5252.9979 | 5252.9979 | 5252.9979 | 5252.9979 | 5252.9979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9830 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5606.3236 | 5606.3236 | 5606.3236 | 5606.3236 | 5606.3236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9831 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3955.2712 | 3955.2712 | 3955.2712 | 3955.2712 | 3955.2712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9832 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16674.1441 | 0.2 | 0.3 | 26011.6648 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7885.3221 | 7885.3221 | 7885.3221 | 7885.3221 | 7885.3221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9833 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 23763.4688 | 0.2 | 0.3 | 37071.0113 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.8902 | 5205.8902 | 5205.8902 | 5205.8902 | 5205.8902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9834 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31583.7728 | 0.2 | 0.3 | 49270.6856 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4861.1741 | 4861.1741 | 4861.1741 | 4861.1741 | 4861.1741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9835 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31429.7339 | 0.2 | 0.3 | 49030.3848 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7431.2131 | 7431.2131 | 7431.2131 | 7431.2131 | 7431.2131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9836 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 29250.0781 | 0.2 | 0.3 | 45630.1219 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5359.5854 | 5359.5854 | 5359.5854 | 5359.5854 | 5359.5854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9837 | PEMBROKE PINES | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 34595.1735 | 0.2 | 0.3 | 53968.4706 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5223.4969 | 5223.4969 | 5223.4969 | 5223.4969 | 5223.4969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9838 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.0158 | 0.2 | 0.3 | 26005.2246 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5615.8021 | 5615.8021 | 5615.8021 | 5615.8021 | 5615.8021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9839 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1542 | 0.2 | 0.3 | 26005.4406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0071 | 5200.0071 | 5200.0071 | 5200.0071 | 5200.0071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9840 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1542 | 0.2 | 0.3 | 26005.4406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.041 | 5200.041 | 5200.041 | 5200.041 | 5200.041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9841 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.9152 | 0.2 | 0.3 | 26005.0677 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5685.3085 | 5685.3085 | 5685.3085 | 5685.3085 | 5685.3085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9842 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31341.8911 | 0.2 | 0.3 | 48893.3501 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8464.603 | 8464.603 | 8464.603 | 8464.603 | 8464.603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9843 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8554 | 0.2 | 0.3 | 26004.9744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7153.7676 | 7153.7676 | 7153.7676 | 7153.7676 | 7153.7676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9844 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7687.5145 | 7687.5145 | 7687.5145 | 7687.5145 | 7687.5145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9845 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3009.0787 | 3009.0787 | 3009.0787 | 3009.0787 | 3009.0787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9846 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.0378 | 0.2 | 0.3 | 26005.259 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5313.6452 | 5313.6452 | 5313.6452 | 5313.6452 | 5313.6452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9847 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 19406.6922 | 0.2 | 0.3 | 30274.4398 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2905.8197 | 2905.8197 | 2905.8197 | 2905.8197 | 2905.8197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9848 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.7651 | 0.2 | 0.3 | 26004.8336 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4278.3693 | 4278.3693 | 4278.3693 | 4278.3693 | 4278.3693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9849 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8809 | 0.2 | 0.3 | 26005.0142 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11565.3169 | 11565.3169 | 11565.3169 | 11565.3169 | 11565.3169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9850 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2.0653 | 2.0653 | 2.0653 | 2.0653 | 2.0653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9851 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.148 | 0.2 | 0.3 | 26005.4309 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7513.783 | 7513.783 | 7513.783 | 7513.783 | 7513.783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9852 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31337.5597 | 0.2 | 0.3 | 48886.5932 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4112.3546 | 4112.3546 | 4112.3546 | 4112.3546 | 4112.3546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9853 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.9906 | 0.2 | 0.3 | 26005.1853 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7293.0949 | 7293.0949 | 7293.0949 | 7293.0949 | 7293.0949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9854 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1542 | 0.2 | 0.3 | 26005.4406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9843 | 5199.9843 | 5199.9843 | 5199.9843 | 5199.9843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9855 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9981 | 5199.9981 | 5199.9981 | 5199.9981 | 5199.9981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9856 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8223 | 0.2 | 0.3 | 26004.9228 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2925 | 5200.2925 | 5200.2925 | 5200.2925 | 5200.2925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9857 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 29073.1138 | 0.2 | 0.3 | 45354.0575 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9858 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16674.6457 | 0.2 | 0.3 | 26012.4473 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2944 | 5200.2944 | 5200.2944 | 5200.2944 | 5200.2944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9859 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16677.1515 | 0.2 | 0.3 | 26016.3564 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5632.9568 | 5632.9568 | 5632.9568 | 5632.9568 | 5632.9568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9860 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16676.9249 | 0.2 | 0.3 | 26016.0028 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5356.5309 | 5356.5309 | 5356.5309 | 5356.5309 | 5356.5309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9861 | PEMBROKE PINES | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 425.3969 | 0.2 | 0.3 | 663.6191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7740.2901 | 7740.2901 | 7740.2901 | 7740.2901 | 7740.2901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9862 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.9089 | 0.2 | 0.3 | 26006.6178 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1057.6998 | 1057.6998 | 1057.6998 | 1057.6998 | 1057.6998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9863 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.2479 | 0.2 | 0.3 | 26007.1467 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2414.6963 | 2414.6963 | 2414.6963 | 2414.6963 | 2414.6963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9864 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.9744 | 0.2 | 0.3 | 26006.7201 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2907.7747 | 2907.7747 | 2907.7747 | 2907.7747 | 2907.7747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9865 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.5838 | 0.2 | 0.3 | 26006.1107 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 86.9757 | 86.9757 | 86.9757 | 86.9757 | 86.9757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9866 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31343.2058 | 0.2 | 0.3 | 48895.401 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1339.202 | 1339.202 | 1339.202 | 1339.202 | 1339.202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9867 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.6338 | 0.2 | 0.3 | 26004.6287 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 773.7518 | 773.7518 | 773.7518 | 773.7518 | 773.7518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9868 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7617.9993 | 7617.9993 | 7617.9993 | 7617.9993 | 7617.9993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9869 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1543 | 0.2 | 0.3 | 26005.4407 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9870 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.7567 | 0.2 | 0.3 | 26004.8204 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6553.4491 | 6553.4491 | 6553.4491 | 6553.4491 | 6553.4491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9871 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 19765.5175 | 0.2 | 0.3 | 30834.2074 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 17047.1739 | 17047.1739 | 17047.1739 | 17047.1739 | 17047.1739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9872 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.3433 | 0.2 | 0.3 | 26005.7355 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13560.4855 | 13560.4855 | 13560.4855 | 13560.4855 | 13560.4855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9873 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.9744 | 0.2 | 0.3 | 26006.7201 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9824.4866 | 9824.4866 | 9824.4866 | 9824.4866 | 9824.4866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9874 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.701 | 0.2 | 0.3 | 26006.2936 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 868.4108 | 868.4108 | 868.4108 | 868.4108 | 868.4108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9875 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.5259 | 0.2 | 0.3 | 26006.0204 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6043.1849 | 6043.1849 | 6043.1849 | 6043.1849 | 6043.1849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9876 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31342.8693 | 0.2 | 0.3 | 48894.8762 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10350.18 | 10350.18 | 10350.18 | 10350.18 | 10350.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9877 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8721 | 0.2 | 0.3 | 26005.0004 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5183.516 | 5183.516 | 5183.516 | 5183.516 | 5183.516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9878 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8809 | 0.2 | 0.3 | 26005.0142 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14124.1986 | 14124.1986 | 14124.1986 | 14124.1986 | 14124.1986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9879 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1542 | 0.2 | 0.3 | 26005.4406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6852.578 | 6852.578 | 6852.578 | 6852.578 | 6852.578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9880 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.9465 | 0.2 | 0.3 | 26005.1165 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14715.5343 | 14715.5343 | 14715.5343 | 14715.5343 | 14715.5343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9881 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 29900.5233 | 0.2 | 0.3 | 46644.8164 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9063.5408 | 9063.5408 | 9063.5408 | 9063.5408 | 9063.5408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9882 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 17143.1446 | 0.2 | 0.3 | 26743.3056 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10338.9489 | 10338.9489 | 10338.9489 | 10338.9489 | 10338.9489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9883 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16838.6761 | 0.2 | 0.3 | 26268.3347 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6855.967 | 6855.967 | 6855.967 | 6855.967 | 6855.967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9884 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16688.8693 | 0.2 | 0.3 | 26034.6362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2935 | 5201.2935 | 5201.2935 | 5201.2935 | 5201.2935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9885 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.2299 | 0.2 | 0.3 | 26005.5587 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5188.7852 | 5188.7852 | 5188.7852 | 5188.7852 | 5188.7852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9886 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1543 | 0.2 | 0.3 | 26005.4407 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1874.2017 | 1874.2017 | 1874.2017 | 1874.2017 | 1874.2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9887 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1543 | 0.2 | 0.3 | 26005.4407 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6374.581 | 6374.581 | 6374.581 | 6374.581 | 6374.581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9888 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.2135 | 0.2 | 0.3 | 26005.533 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8515.1816 | 8515.1816 | 8515.1816 | 8515.1816 | 8515.1816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9889 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31339.2047 | 0.2 | 0.3 | 48889.1593 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2102.7672 | 2102.7672 | 2102.7672 | 2102.7672 | 2102.7672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9890 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.7083 | 0.2 | 0.3 | 26004.745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9891 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9892 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1542 | 0.2 | 0.3 | 26005.4406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9553.6565 | 9553.6565 | 9553.6565 | 9553.6565 | 9553.6565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9893 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1191 | 0.2 | 0.3 | 26005.3857 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10808.9241 | 10808.9241 | 10808.9241 | 10808.9241 | 10808.9241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9894 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31339.5829 | 0.2 | 0.3 | 48889.7494 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6128.707 | 6128.707 | 6128.707 | 6128.707 | 6128.707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9895 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 21385.2938 | 0.2 | 0.3 | 33361.0583 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9174.6132 | 9174.6132 | 9174.6132 | 9174.6132 | 9174.6132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9896 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 21571.0531 | 0.2 | 0.3 | 33650.8429 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 138.5391 | 138.5391 | 138.5391 | 138.5391 | 138.5391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9897 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 22184.8276 | 0.2 | 0.3 | 34608.3311 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9898 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 22414.939 | 0.2 | 0.3 | 34967.3048 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9899 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31345.9292 | 0.2 | 0.3 | 48899.6496 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10039.5871 | 10039.5871 | 10039.5871 | 10039.5871 | 10039.5871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9900 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1669 | 0.2 | 0.3 | 26005.4603 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9448.373 | 9448.373 | 9448.373 | 9448.373 | 9448.373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9901 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12019.1314 | 12019.1314 | 12019.1314 | 12019.1314 | 12019.1314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9902 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9282.3136 | 9282.3136 | 9282.3136 | 9282.3136 | 9282.3136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9903 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.4029 | 0.2 | 0.3 | 26005.8286 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7265.0782 | 7265.0782 | 7265.0782 | 7265.0782 | 7265.0782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9904 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 34187.9175 | 0.2 | 0.3 | 53333.1512 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2543.6835 | 2543.6835 | 2543.6835 | 2543.6835 | 2543.6835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9905 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 23360.9067 | 0.2 | 0.3 | 36443.0144 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6017 | 5200.6017 | 5200.6017 | 5200.6017 | 5200.6017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9906 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 18343.2851 | 0.2 | 0.3 | 28615.5247 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4113.4883 | 4113.4883 | 4113.4883 | 4113.4883 | 4113.4883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9907 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 18063.192 | 0.2 | 0.3 | 28178.5795 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5237.8049 | 5237.8049 | 5237.8049 | 5237.8049 | 5237.8049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9908 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.679 | 0.2 | 0.3 | 26007.8192 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8086 | 5199.8086 | 5199.8086 | 5199.8086 | 5199.8086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9909 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.7947 | 0.2 | 0.3 | 26007.9997 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9910 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.7947 | 0.2 | 0.3 | 26007.9997 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9911 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.307 | 0.2 | 0.3 | 26007.2389 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5930.0874 | 5930.0874 | 5930.0874 | 5930.0874 | 5930.0874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9912 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31341.3363 | 0.2 | 0.3 | 48892.4846 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3225.3271 | 3225.3271 | 3225.3271 | 3225.3271 | 3225.3271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9913 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.6131 | 0.2 | 0.3 | 26004.5964 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5645.1689 | 5645.1689 | 5645.1689 | 5645.1689 | 5645.1689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9914 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2925.5987 | 2925.5987 | 2925.5987 | 2925.5987 | 2925.5987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9915 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.6074 | 0.2 | 0.3 | 26004.5875 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3273.0751 | 3273.0751 | 3273.0751 | 3273.0751 | 3273.0751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9916 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8564 | 0.2 | 0.3 | 26004.976 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 814.7221 | 814.7221 | 814.7221 | 814.7221 | 814.7221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9917 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 20289.8238 | 0.2 | 0.3 | 31652.1251 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0429 | 5200.0429 | 5200.0429 | 5200.0429 | 5200.0429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9918 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8185 | 0.2 | 0.3 | 26004.9168 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4281.4969 | 4281.4969 | 4281.4969 | 4281.4969 | 4281.4969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9919 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.0053 | 0.2 | 0.3 | 26005.2083 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5397.5966 | 5397.5966 | 5397.5966 | 5397.5966 | 5397.5966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9920 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.3739 | 0.2 | 0.3 | 26004.2233 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9921 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.0471 | 0.2 | 0.3 | 26005.2735 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2698 | 5201.2698 | 5201.2698 | 5201.2698 | 5201.2698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9922 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 24250.5846 | 0.2 | 0.3 | 37830.912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5195.6759 | 5195.6759 | 5195.6759 | 5195.6759 | 5195.6759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9923 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.3533 | 0.2 | 0.3 | 26004.1911 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.9474 | 9776.9474 | 9776.9474 | 9776.9474 | 9776.9474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9924 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9760.9601 | 9760.9601 | 9760.9601 | 9760.9601 | 9760.9601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9925 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5454.6026 | 5454.6026 | 5454.6026 | 5454.6026 | 5454.6026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9926 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 26119.2317 | 0.2 | 0.3 | 40746.0014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9373 | 5200.9373 | 5200.9373 | 5200.9373 | 5200.9373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9927 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 14621.8549 | 0.2 | 0.3 | 22810.0936 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8418 | 5200.8418 | 5200.8418 | 5200.8418 | 5200.8418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9928 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 25393.1674 | 0.2 | 0.3 | 39613.3411 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2979.3031 | 2979.3031 | 2979.3031 | 2979.3031 | 2979.3031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9929 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 30230.048 | 0.2 | 0.3 | 47158.8749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4827.1559 | 4827.1559 | 4827.1559 | 4827.1559 | 4827.1559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9930 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 19703.1645 | 0.2 | 0.3 | 30736.9367 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3879.512 | 3879.512 | 3879.512 | 3879.512 | 3879.512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9931 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.3229 | 0.2 | 0.3 | 26005.7038 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7250.1494 | 7250.1494 | 7250.1494 | 7250.1494 | 7250.1494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9932 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9933 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9934 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.9675 | 0.2 | 0.3 | 26005.1494 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1320.4672 | 1320.4672 | 1320.4672 | 1320.4672 | 1320.4672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9935 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31336.9631 | 0.2 | 0.3 | 48885.6625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8424.6434 | 8424.6434 | 8424.6434 | 8424.6434 | 8424.6434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9936 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.221 | 0.2 | 0.3 | 26003.9848 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8491 | 5200.8491 | 5200.8491 | 5200.8491 | 5200.8491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9937 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9721 | 5200.9721 | 5200.9721 | 5200.9721 | 5200.9721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9938 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.6074 | 0.2 | 0.3 | 26004.5875 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5336.8266 | 5336.8266 | 5336.8266 | 5336.8266 | 5336.8266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9939 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.591 | 0.2 | 0.3 | 26004.562 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4492.4362 | 4492.4362 | 4492.4362 | 4492.4362 | 4492.4362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9940 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 20649.8101 | 0.2 | 0.3 | 32213.7037 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5926.5454 | 5926.5454 | 5926.5454 | 5926.5454 | 5926.5454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9941 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.6092 | 9776.6092 | 9776.6092 | 9776.6092 | 9776.6092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9942 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.6408 | 9776.6408 | 9776.6408 | 9776.6408 | 9776.6408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9943 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.993 | 5199.993 | 5199.993 | 5199.993 | 5199.993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9944 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5916.8471 | 5916.8471 | 5916.8471 | 5916.8471 | 5916.8471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9945 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 23955.0151 | 0.2 | 0.3 | 37369.8235 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5266.0295 | 5266.0295 | 5266.0295 | 5266.0295 | 5266.0295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9946 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.2464 | 0.2 | 0.3 | 26005.5844 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3818 | 5202.3818 | 5202.3818 | 5202.3818 | 5202.3818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9947 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8089.6218 | 8089.6218 | 8089.6218 | 8089.6218 | 8089.6218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9948 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1478 | 0.2 | 0.3 | 26005.4306 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7486.8619 | 7486.8619 | 7486.8619 | 7486.8619 | 7486.8619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9949 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 25731.4747 | 0.2 | 0.3 | 40141.1006 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8974 | 5200.8974 | 5200.8974 | 5200.8974 | 5200.8974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9950 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 17904.0993 | 0.2 | 0.3 | 27930.395 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4323.5808 | 4323.5808 | 4323.5808 | 4323.5808 | 4323.5808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9951 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 18020.7799 | 0.2 | 0.3 | 28112.4166 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1399 | 5200.1399 | 5200.1399 | 5200.1399 | 5200.1399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9952 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16452.3443 | 0.2 | 0.3 | 25665.6571 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6723.2376 | 6723.2376 | 6723.2376 | 6723.2376 | 6723.2376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9953 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 1684.3584 | 0.2 | 0.3 | 2627.5991 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3968 | 5200.3968 | 5200.3968 | 5200.3968 | 5200.3968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9954 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 17514.6427 | 0.2 | 0.3 | 27322.8426 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0381 | 5201.0381 | 5201.0381 | 5201.0381 | 5201.0381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9955 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 17893.5755 | 0.2 | 0.3 | 27913.9778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9956 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 18230.9418 | 0.2 | 0.3 | 28440.2692 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5579.8007 | 5579.8007 | 5579.8007 | 5579.8007 | 5579.8007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9957 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 18319.3789 | 0.2 | 0.3 | 28578.231 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8091.3531 | 8091.3531 | 8091.3531 | 8091.3531 | 8091.3531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9958 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31344.5857 | 0.2 | 0.3 | 48897.5537 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5413.0081 | 5413.0081 | 5413.0081 | 5413.0081 | 5413.0081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9959 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 19296.4307 | 0.2 | 0.3 | 30102.4318 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1868.5353 | 1868.5353 | 1868.5353 | 1868.5353 | 1868.5353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9960 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 19571.3038 | 0.2 | 0.3 | 30531.2339 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 619.1022 | 619.1022 | 619.1022 | 619.1022 | 619.1022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9961 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 19950.6802 | 0.2 | 0.3 | 31123.0611 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4.6466 | 4.6466 | 4.6466 | 4.6466 | 4.6466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9962 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 20314.0816 | 0.2 | 0.3 | 31689.9673 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3369.5147 | 3369.5147 | 3369.5147 | 3369.5147 | 3369.5147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9963 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 20986.5419 | 0.2 | 0.3 | 32739.0053 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10273.2462 | 10273.2462 | 10273.2462 | 10273.2462 | 10273.2462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9964 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.111 | 5200.111 | 5200.111 | 5200.111 | 5200.111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9965 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8501.0773 | 8501.0773 | 8501.0773 | 8501.0773 | 8501.0773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9966 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.6074 | 0.2 | 0.3 | 26004.5875 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9967 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1542 | 0.2 | 0.3 | 26005.4406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4977.9763 | 4977.9763 | 4977.9763 | 4977.9763 | 4977.9763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9968 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 23492.4342 | 0.2 | 0.3 | 36648.1974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7716.2927 | 7716.2927 | 7716.2927 | 7716.2927 | 7716.2927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9969 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 23051.9689 | 0.2 | 0.3 | 35961.0714 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9970 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 23401.003 | 0.2 | 0.3 | 36505.5647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6394.6594 | 6394.6594 | 6394.6594 | 6394.6594 | 6394.6594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9971 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16880.4514 | 0.2 | 0.3 | 26333.5042 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5198.9107 | 5198.9107 | 5198.9107 | 5198.9107 | 5198.9107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9972 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 19437.2857 | 0.2 | 0.3 | 30322.1656 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9745 | 5199.9745 | 5199.9745 | 5199.9745 | 5199.9745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9973 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 17727.8417 | 0.2 | 0.3 | 27655.433 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5222.0899 | 5222.0899 | 5222.0899 | 5222.0899 | 5222.0899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9974 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 17829.1063 | 0.2 | 0.3 | 27813.4058 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7822.2447 | 7822.2447 | 7822.2447 | 7822.2447 | 7822.2447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9975 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 15343.1787 | 0.2 | 0.3 | 23935.3588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9848.8405 | 9848.8405 | 9848.8405 | 9848.8405 | 9848.8405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9976 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16667.9699 | 0.2 | 0.3 | 26002.033 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9823.5141 | 9823.5141 | 9823.5141 | 9823.5141 | 9823.5141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9977 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.9977 | 0.2 | 0.3 | 26005.1965 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9787.2048 | 9787.2048 | 9787.2048 | 9787.2048 | 9787.2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9978 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16668.477 | 0.2 | 0.3 | 26002.8241 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5899.6165 | 5899.6165 | 5899.6165 | 5899.6165 | 5899.6165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9979 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.2029 | 0.2 | 0.3 | 26005.5166 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8140.0757 | 8140.0757 | 8140.0757 | 8140.0757 | 8140.0757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9980 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.3071 | 0.2 | 0.3 | 26007.239 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9605.8513 | 9605.8513 | 9605.8513 | 9605.8513 | 9605.8513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9981 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16668.3653 | 0.2 | 0.3 | 26002.6498 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9603.78 | 9603.78 | 9603.78 | 9603.78 | 9603.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9982 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.2885 | 0.2 | 0.3 | 26004.0901 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5654.8192 | 5654.8192 | 5654.8192 | 5654.8192 | 5654.8192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9983 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16668.7846 | 0.2 | 0.3 | 26003.304 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7976.6795 | 7976.6795 | 7976.6795 | 7976.6795 | 7976.6795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9984 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.7304 | 0.2 | 0.3 | 26007.8994 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5975.1823 | 5975.1823 | 5975.1823 | 5975.1823 | 5975.1823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9985 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1069 | 0.2 | 0.3 | 26005.3667 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7996.9296 | 7996.9296 | 7996.9296 | 7996.9296 | 7996.9296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9986 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3479 | 5200.3479 | 5200.3479 | 5200.3479 | 5200.3479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9987 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8485 | 0.2 | 0.3 | 26004.9637 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8655.2774 | 8655.2774 | 8655.2774 | 8655.2774 | 8655.2774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9988 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.5315 | 0.2 | 0.3 | 26004.4692 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5806.1893 | 5806.1893 | 5806.1893 | 5806.1893 | 5806.1893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9989 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.3085 | 0.2 | 0.3 | 26005.6813 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5238.1234 | 5238.1234 | 5238.1234 | 5238.1234 | 5238.1234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9990 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16668.0565 | 0.2 | 0.3 | 26002.1681 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4973.7694 | 4973.7694 | 4973.7694 | 4973.7694 | 4973.7694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9991 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.9253 | 0.2 | 0.3 | 26006.6434 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6540.5911 | 6540.5911 | 6540.5911 | 6540.5911 | 6540.5911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9992 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 23070.9656 | 0.2 | 0.3 | 35990.7063 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6528.606 | 6528.606 | 6528.606 | 6528.606 | 6528.606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9993 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 29092.8501 | 0.2 | 0.3 | 45384.8461 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3192.3647 | 3192.3647 | 3192.3647 | 3192.3647 | 3192.3647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9994 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 15704.0099 | 0.2 | 0.3 | 24498.2555 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9995 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 14807.5394 | 0.2 | 0.3 | 23099.7615 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9996 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 11970.7207 | 0.2 | 0.3 | 18674.3243 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9997 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 11595.519 | 0.2 | 0.3 | 18089.0096 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9998 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16667.6785 | 0.2 | 0.3 | 26001.5784 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9999 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.4262 | 0.2 | 0.3 | 26004.3049 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10000 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16668.2607 | 0.2 | 0.3 | 26002.4866 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10001 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.2424 | 0.2 | 0.3 | 26005.5781 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10002 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.4729 | 0.2 | 0.3 | 26007.4977 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10003 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16668.6734 | 0.2 | 0.3 | 26003.1305 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8741.1148 | 8741.1148 | 8741.1148 | 8741.1148 | 8741.1148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10004 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16668.5116 | 0.2 | 0.3 | 26002.8781 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8211.0947 | 8211.0947 | 8211.0947 | 8211.0947 | 8211.0947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10005 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.0396 | 0.2 | 0.3 | 26003.7018 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8628.6507 | 8628.6507 | 8628.6507 | 8628.6507 | 8628.6507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10006 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.2671 | 0.2 | 0.3 | 26007.1766 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5933.5901 | 5933.5901 | 5933.5901 | 5933.5901 | 5933.5901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10007 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.0519 | 0.2 | 0.3 | 26005.281 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5405.1678 | 5405.1678 | 5405.1678 | 5405.1678 | 5405.1678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10008 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.1057 | 0.2 | 0.3 | 26003.8048 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2182 | 5200.2182 | 5200.2182 | 5200.2182 | 5200.2182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10009 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1806 | 5200.1806 | 5200.1806 | 5200.1806 | 5200.1806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10010 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.253 | 5200.253 | 5200.253 | 5200.253 | 5200.253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10011 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 18479.0622 | 0.2 | 0.3 | 28827.337 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2702 | 5200.2702 | 5200.2702 | 5200.2702 | 5200.2702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10012 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 23874.4035 | 0.2 | 0.3 | 37244.0695 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2362 | 5200.2362 | 5200.2362 | 5200.2362 | 5200.2362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10013 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 23965.7407 | 0.2 | 0.3 | 37386.5554 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5257.8834 | 5257.8834 | 5257.8834 | 5257.8834 | 5257.8834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10014 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 25455.961 | 0.2 | 0.3 | 39711.2992 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9459.3431 | 9459.3431 | 9459.3431 | 9459.3431 | 9459.3431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10015 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31576.3164 | 0.2 | 0.3 | 49259.0536 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9358.1227 | 9358.1227 | 9358.1227 | 9358.1227 | 9358.1227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10016 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31892.9777 | 0.2 | 0.3 | 49753.0453 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9780.0108 | 9780.0108 | 9780.0108 | 9780.0108 | 9780.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10017 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31962.6414 | 0.2 | 0.3 | 49861.7206 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9849 | 5199.9849 | 5199.9849 | 5199.9849 | 5199.9849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10018 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 26668.2592 | 0.2 | 0.3 | 41602.4844 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4415.8409 | 4415.8409 | 4415.8409 | 4415.8409 | 4415.8409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10019 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31347.0667 | 0.2 | 0.3 | 48901.4241 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3547.6714 | 3547.6714 | 3547.6714 | 3547.6714 | 3547.6714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10020 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 20651.0964 | 0.2 | 0.3 | 32215.7104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2957.5683 | 2957.5683 | 2957.5683 | 2957.5683 | 2957.5683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10021 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 20379.7497 | 0.2 | 0.3 | 31792.4096 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3864.2067 | 3864.2067 | 3864.2067 | 3864.2067 | 3864.2067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10022 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 20040.1968 | 0.2 | 0.3 | 31262.707 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9846.844 | 9846.844 | 9846.844 | 9846.844 | 9846.844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10023 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31340.7714 | 0.2 | 0.3 | 48891.6034 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4158.6081 | 4158.6081 | 4158.6081 | 4158.6081 | 4158.6081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10024 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 19554.3455 | 0.2 | 0.3 | 30504.779 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3128.603 | 3128.603 | 3128.603 | 3128.603 | 3128.603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10025 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 19005.8642 | 0.2 | 0.3 | 29649.1482 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.076 | 2600.076 | 2600.076 | 2600.076 | 2600.076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10026 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 18780.3261 | 0.2 | 0.3 | 29297.3088 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7777.194 | 7777.194 | 7777.194 | 7777.194 | 7777.194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10027 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 18513.3583 | 0.2 | 0.3 | 28880.8389 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9001.1967 | 9001.1967 | 9001.1967 | 9001.1967 | 9001.1967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10028 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31341.3633 | 0.2 | 0.3 | 48892.5267 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9805.9075 | 9805.9075 | 9805.9075 | 9805.9075 | 9805.9075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10029 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31340.9022 | 0.2 | 0.3 | 48891.8074 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9794.163 | 9794.163 | 9794.163 | 9794.163 | 9794.163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10030 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31339.6651 | 0.2 | 0.3 | 48889.8775 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5185.7474 | 5185.7474 | 5185.7474 | 5185.7474 | 5185.7474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10031 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31339.6759 | 0.2 | 0.3 | 48889.8944 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3227.5734 | 3227.5734 | 3227.5734 | 3227.5734 | 3227.5734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10032 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 29529.2287 | 0.2 | 0.3 | 46065.5967 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10327.1185 | 10327.1185 | 10327.1185 | 10327.1185 | 10327.1185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10033 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 8693.8047 | 0.2 | 0.3 | 13562.3354 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6724.1575 | 6724.1575 | 6724.1575 | 6724.1575 | 6724.1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10034 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 11821.0216 | 0.2 | 0.3 | 18440.7937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2484.5633 | 2484.5633 | 2484.5633 | 2484.5633 | 2484.5633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10035 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 14777.0255 | 0.2 | 0.3 | 23052.1598 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10036 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 18732.439 | 0.2 | 0.3 | 29222.6048 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2599.9789 | 2599.9789 | 2599.9789 | 2599.9789 | 2599.9789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10037 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 17228.1467 | 0.2 | 0.3 | 26875.9088 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2687.4883 | 2687.4883 | 2687.4883 | 2687.4883 | 2687.4883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10038 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 17241.2601 | 0.2 | 0.3 | 26896.3658 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3641.7304 | 3641.7304 | 3641.7304 | 3641.7304 | 3641.7304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10039 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 17277.2417 | 0.2 | 0.3 | 26952.4971 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4671.5364 | 4671.5364 | 4671.5364 | 4671.5364 | 4671.5364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10040 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 25685.9757 | 0.2 | 0.3 | 40070.122 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.873 | 5199.873 | 5199.873 | 5199.873 | 5199.873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10041 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.1379 | 0.2 | 0.3 | 26003.8551 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 875.1561 | 875.1561 | 875.1561 | 875.1561 | 875.1561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10042 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5904.2677 | 5904.2677 | 5904.2677 | 5904.2677 | 5904.2677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10043 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.2385 | 0.2 | 0.3 | 26004.012 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0934 | 5200.0934 | 5200.0934 | 5200.0934 | 5200.0934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10044 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31338.2258 | 0.2 | 0.3 | 48887.6322 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10045 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.5899 | 0.2 | 0.3 | 26006.1202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0214 | 5200.0214 | 5200.0214 | 5200.0214 | 5200.0214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10046 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.9744 | 0.2 | 0.3 | 26006.7201 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1225.6133 | 1225.6133 | 1225.6133 | 1225.6133 | 1225.6133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10047 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.9745 | 0.2 | 0.3 | 26006.7202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4069.958 | 4069.958 | 4069.958 | 4069.958 | 4069.958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10048 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.9212 | 0.2 | 0.3 | 26006.6371 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3501 | 5200.3501 | 5200.3501 | 5200.3501 | 5200.3501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10049 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 22198.1629 | 0.2 | 0.3 | 34629.1342 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.0304 | 5206.0304 | 5206.0304 | 5206.0304 | 5206.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10050 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.7011 | 0.2 | 0.3 | 26006.2937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2832.8559 | 2832.8559 | 2832.8559 | 2832.8559 | 2832.8559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10051 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6783.557 | 6783.557 | 6783.557 | 6783.557 | 6783.557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10052 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.7011 | 0.2 | 0.3 | 26006.2937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9334 | 5200.9334 | 5200.9334 | 5200.9334 | 5200.9334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10053 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 22506.0293 | 0.2 | 0.3 | 35109.4058 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2425.5099 | 2425.5099 | 2425.5099 | 2425.5099 | 2425.5099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10054 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.5103 | 0.2 | 0.3 | 26005.996 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8399.5066 | 8399.5066 | 8399.5066 | 8399.5066 | 8399.5066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10055 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 13184.002 | 0.2 | 0.3 | 20567.0431 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10056 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 10746.2501 | 0.2 | 0.3 | 16764.1501 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6568.2699 | 6568.2699 | 6568.2699 | 6568.2699 | 6568.2699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10057 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 17380.0189 | 0.2 | 0.3 | 27112.8294 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7732.5575 | 7732.5575 | 7732.5575 | 7732.5575 | 7732.5575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10058 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16541.6535 | 0.2 | 0.3 | 25804.9794 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10059 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 15759.4047 | 0.2 | 0.3 | 24584.6714 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10060 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 17114.8025 | 0.2 | 0.3 | 26699.092 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2725 | 5200.2725 | 5200.2725 | 5200.2725 | 5200.2725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10061 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 25451.1226 | 0.2 | 0.3 | 39703.7513 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5131.5671 | 5131.5671 | 5131.5671 | 5131.5671 | 5131.5671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10062 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 26461.4917 | 0.2 | 0.3 | 41279.9271 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2125.6457 | 2125.6457 | 2125.6457 | 2125.6457 | 2125.6457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10063 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 26728.5243 | 0.2 | 0.3 | 41696.4979 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5754.7404 | 5754.7404 | 5754.7404 | 5754.7404 | 5754.7404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10064 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 27112.9299 | 0.2 | 0.3 | 42296.1706 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10065 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31338.6253 | 0.2 | 0.3 | 48888.2555 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.238 | 9776.238 | 9776.238 | 9776.238 | 9776.238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10066 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 27818.5994 | 0.2 | 0.3 | 43397.0151 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6657.7704 | 6657.7704 | 6657.7704 | 6657.7704 | 6657.7704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10067 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 28199.243 | 0.2 | 0.3 | 43990.8191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5673.7924 | 5673.7924 | 5673.7924 | 5673.7924 | 5673.7924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10068 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.2687 | 0.2 | 0.3 | 26004.0592 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6257.8857 | 6257.8857 | 6257.8857 | 6257.8857 | 6257.8857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10069 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.5535 | 0.2 | 0.3 | 26004.5034 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6288.422 | 6288.422 | 6288.422 | 6288.422 | 6288.422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10070 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 22430.5648 | 0.2 | 0.3 | 34991.6811 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7271.8225 | 7271.8225 | 7271.8225 | 7271.8225 | 7271.8225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10071 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.7011 | 0.2 | 0.3 | 26006.2937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9919 | 5199.9919 | 5199.9919 | 5199.9919 | 5199.9919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10072 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.6074 | 0.2 | 0.3 | 26004.5875 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3602.6114 | 3602.6114 | 3602.6114 | 3602.6114 | 3602.6114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10073 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6413.1569 | 6413.1569 | 6413.1569 | 6413.1569 | 6413.1569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10074 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 22013.2915 | 0.2 | 0.3 | 34340.7347 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8479 | 5200.8479 | 5200.8479 | 5200.8479 | 5200.8479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10075 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31277.314 | 0.2 | 0.3 | 48792.6098 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5785.1459 | 5785.1459 | 5785.1459 | 5785.1459 | 5785.1459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10076 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 26242.7515 | 0.2 | 0.3 | 40938.6923 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10077 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16824.1131 | 0.2 | 0.3 | 26245.6165 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5784.807 | 5784.807 | 5784.807 | 5784.807 | 5784.807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10078 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16429.6905 | 0.2 | 0.3 | 25630.3171 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7774.6332 | 7774.6332 | 7774.6332 | 7774.6332 | 7774.6332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10079 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16524.1651 | 0.2 | 0.3 | 25777.6976 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6422.0391 | 6422.0391 | 6422.0391 | 6422.0391 | 6422.0391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10080 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 12298.5855 | 0.2 | 0.3 | 19185.7934 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10081 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 5812.8751 | 0.2 | 0.3 | 9068.0852 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1008 | 5200.1008 | 5200.1008 | 5200.1008 | 5200.1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10082 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4366 | 5200.4366 | 5200.4366 | 5200.4366 | 5200.4366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10083 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.5213 | 0.2 | 0.3 | 26007.5732 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7370.7804 | 7370.7804 | 7370.7804 | 7370.7804 | 7370.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10084 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.4277 | 0.2 | 0.3 | 26005.8672 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4939.6151 | 4939.6151 | 4939.6151 | 4939.6151 | 4939.6151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10085 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5356.551 | 5356.551 | 5356.551 | 5356.551 | 5356.551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10086 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16670.9745 | 0.2 | 0.3 | 26006.7202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10087 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9040.8227 | 9040.8227 | 9040.8227 | 9040.8227 | 9040.8227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10088 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9867 | 5199.9867 | 5199.9867 | 5199.9867 | 5199.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10089 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5209.6183 | 5209.6183 | 5209.6183 | 5209.6183 | 5209.6183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10090 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.3401 | 0.2 | 0.3 | 26005.7306 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.668 | 5200.668 | 5200.668 | 5200.668 | 5200.668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10091 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16669.5155 | 0.2 | 0.3 | 26004.4442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5049.4912 | 5049.4912 | 5049.4912 | 5049.4912 | 5049.4912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10092 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.1699 | 0.2 | 0.3 | 26005.4651 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9683 | 5200.9683 | 5200.9683 | 5200.9683 | 5200.9683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10093 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16670.7139 | 0.2 | 0.3 | 26006.3136 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5859.6815 | 5859.6815 | 5859.6815 | 5859.6815 | 5859.6815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10094 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16667.1751 | 0.2 | 0.3 | 26000.7931 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5834.6661 | 5834.6661 | 5834.6661 | 5834.6661 | 5834.6661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10095 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16668.6369 | 0.2 | 0.3 | 26003.0735 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4481.7017 | 4481.7017 | 4481.7017 | 4481.7017 | 4481.7017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10096 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16869.5509 | 0.2 | 0.3 | 26316.4994 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8444.4528 | 8444.4528 | 8444.4528 | 8444.4528 | 8444.4528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10097 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16867.8687 | 0.2 | 0.3 | 26313.8752 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5668.5669 | 5668.5669 | 5668.5669 | 5668.5669 | 5668.5669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10098 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16850.4194 | 0.2 | 0.3 | 26286.6543 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6406.0099 | 6406.0099 | 6406.0099 | 6406.0099 | 6406.0099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10099 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16905.2669 | 0.2 | 0.3 | 26372.2163 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10100 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31345.6519 | 0.2 | 0.3 | 48899.2169 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10101 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 28031.6061 | 0.2 | 0.3 | 43729.3056 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5244.6134 | 5244.6134 | 5244.6134 | 5244.6134 | 5244.6134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10102 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 27405.1293 | 0.2 | 0.3 | 42752.0017 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6242.7187 | 6242.7187 | 6242.7187 | 6242.7187 | 6242.7187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10103 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 27033.8691 | 0.2 | 0.3 | 42172.8358 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.9396 | 5205.9396 | 5205.9396 | 5205.9396 | 5205.9396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10104 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 26531.2354 | 0.2 | 0.3 | 41388.7272 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7448.0948 | 7448.0948 | 7448.0948 | 7448.0948 | 7448.0948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10105 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 28912.8238 | 0.2 | 0.3 | 45104.0051 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9179.0646 | 9179.0646 | 9179.0646 | 9179.0646 | 9179.0646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10106 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 28360.0099 | 0.2 | 0.3 | 44241.6154 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6720.7885 | 6720.7885 | 6720.7885 | 6720.7885 | 6720.7885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10107 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16676.5962 | 0.2 | 0.3 | 26015.4901 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3967 | 5201.3967 | 5201.3967 | 5201.3967 | 5201.3967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10108 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16671.7647 | 0.2 | 0.3 | 26007.953 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.7905 | 5204.7905 | 5204.7905 | 5204.7905 | 5204.7905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10109 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 24222.1854 | 0.2 | 0.3 | 37786.6092 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5699.6704 | 5699.6704 | 5699.6704 | 5699.6704 | 5699.6704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10110 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 22943.9708 | 0.2 | 0.3 | 35792.5944 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7507.2121 | 7507.2121 | 7507.2121 | 7507.2121 | 7507.2121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10111 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 22485.0134 | 0.2 | 0.3 | 35076.6209 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10112 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 21998.7297 | 0.2 | 0.3 | 34318.0184 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9026 | 5199.9026 | 5199.9026 | 5199.9026 | 5199.9026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10113 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31344.8018 | 0.2 | 0.3 | 48897.8908 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5232.2197 | 5232.2197 | 5232.2197 | 5232.2197 | 5232.2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10114 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 21046.6479 | 0.2 | 0.3 | 32832.7708 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6794.4119 | 6794.4119 | 6794.4119 | 6794.4119 | 6794.4119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10115 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 20425.2566 | 0.2 | 0.3 | 31863.4003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4338.8332 | 4338.8332 | 4338.8332 | 4338.8332 | 4338.8332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10116 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31519.0909 | 0.2 | 0.3 | 49169.7818 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2113.0268 | 2113.0268 | 2113.0268 | 2113.0268 | 2113.0268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10117 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31617.3437 | 0.2 | 0.3 | 49323.0561 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2908 | 5202.2908 | 5202.2908 | 5202.2908 | 5202.2908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10118 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31629.9241 | 0.2 | 0.3 | 49342.6815 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6688.8105 | 6688.8105 | 6688.8105 | 6688.8105 | 6688.8105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10119 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 26053.0457 | 0.2 | 0.3 | 40642.7513 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6670.0995 | 6670.0995 | 6670.0995 | 6670.0995 | 6670.0995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10120 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 24037.7739 | 0.2 | 0.3 | 37498.9272 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6917.7139 | 6917.7139 | 6917.7139 | 6917.7139 | 6917.7139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10121 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16673.0969 | 0.2 | 0.3 | 26010.0311 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5245.1153 | 5245.1153 | 5245.1153 | 5245.1153 | 5245.1153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10122 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16673.4351 | 0.2 | 0.3 | 26010.5587 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7437.625 | 7437.625 | 7437.625 | 7437.625 | 7437.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10123 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16673.7085 | 0.2 | 0.3 | 26010.9852 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3707.2617 | 3707.2617 | 3707.2617 | 3707.2617 | 3707.2617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10124 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16673.6655 | 0.2 | 0.3 | 26010.9181 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4451 | 5200.4451 | 5200.4451 | 5200.4451 | 5200.4451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10125 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 21148.5591 | 0.2 | 0.3 | 32991.7522 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5388.868 | 5388.868 | 5388.868 | 5388.868 | 5388.868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10126 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 26872.2016 | 0.2 | 0.3 | 41920.6345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6416.3097 | 6416.3097 | 6416.3097 | 6416.3097 | 6416.3097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10127 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1733 | 5200.1733 | 5200.1733 | 5200.1733 | 5200.1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10128 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6234.7468 | 6234.7468 | 6234.7468 | 6234.7468 | 6234.7468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10129 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16673.823 | 0.2 | 0.3 | 26011.1639 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2584.3022 | 2584.3022 | 2584.3022 | 2584.3022 | 2584.3022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10130 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16668.4628 | 0.2 | 0.3 | 26002.802 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5991.6361 | 5991.6361 | 5991.6361 | 5991.6361 | 5991.6361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10131 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4609.419 | 4609.419 | 4609.419 | 4609.419 | 4609.419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10132 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16673.6847 | 0.2 | 0.3 | 26010.9482 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3573.5984 | 3573.5984 | 3573.5984 | 3573.5984 | 3573.5984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10133 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31344.7734 | 0.2 | 0.3 | 48897.8465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4586.7469 | 4586.7469 | 4586.7469 | 4586.7469 | 4586.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10134 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16673.2616 | 0.2 | 0.3 | 26010.2881 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7800.7061 | 7800.7061 | 7800.7061 | 7800.7061 | 7800.7061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10135 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16673.4607 | 0.2 | 0.3 | 26010.5986 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4224.4956 | 4224.4956 | 4224.4956 | 4224.4956 | 4224.4956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10136 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 23585.0704 | 0.2 | 0.3 | 36792.7098 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.927 | 5202.927 | 5202.927 | 5202.927 | 5202.927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10137 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16776.7512 | 0.2 | 0.3 | 26171.7319 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5686.0271 | 5686.0271 | 5686.0271 | 5686.0271 | 5686.0271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10138 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16758.1681 | 0.2 | 0.3 | 26142.7423 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4408.9008 | 4408.9008 | 4408.9008 | 4408.9008 | 4408.9008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10139 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16764.8529 | 0.2 | 0.3 | 26153.1706 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7817.5124 | 7817.5124 | 7817.5124 | 7817.5124 | 7817.5124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10140 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 23478.4661 | 0.2 | 0.3 | 36626.4072 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2436.8005 | 2436.8005 | 2436.8005 | 2436.8005 | 2436.8005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10141 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16673.6219 | 0.2 | 0.3 | 26010.8502 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5524 | 5200.5524 | 5200.5524 | 5200.5524 | 5200.5524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10142 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16674.1597 | 0.2 | 0.3 | 26011.6892 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4238 | 5200.4238 | 5200.4238 | 5200.4238 | 5200.4238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10143 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16674.6099 | 0.2 | 0.3 | 26012.3915 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2472.3755 | 2472.3755 | 2472.3755 | 2472.3755 | 2472.3755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10144 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16673.8786 | 0.2 | 0.3 | 26011.2506 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 477.3834 | 477.3834 | 477.3834 | 477.3834 | 477.3834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10145 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16674.2843 | 0.2 | 0.3 | 26011.8836 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2377.4878 | 2377.4878 | 2377.4878 | 2377.4878 | 2377.4878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10146 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31350.1265 | 0.2 | 0.3 | 48906.1974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 545.2406 | 545.2406 | 545.2406 | 545.2406 | 545.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10147 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16673.7085 | 0.2 | 0.3 | 26010.9852 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4756.583 | 4756.583 | 4756.583 | 4756.583 | 4756.583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10148 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8795.3327 | 8795.3327 | 8795.3327 | 8795.3327 | 8795.3327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10149 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16673.1285 | 0.2 | 0.3 | 26010.0805 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9857.0608 | 9857.0608 | 9857.0608 | 9857.0608 | 9857.0608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10150 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16666.2138 | 0.2 | 0.3 | 25999.2935 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12511.9314 | 12511.9314 | 12511.9314 | 12511.9314 | 12511.9314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10151 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.0744 | 9777.0744 | 9777.0744 | 9777.0744 | 9777.0744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10152 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16674.7935 | 0.2 | 0.3 | 26012.6778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8409.6008 | 8409.6008 | 8409.6008 | 8409.6008 | 8409.6008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10153 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31350.7686 | 0.2 | 0.3 | 48907.199 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9010.1694 | 9010.1694 | 9010.1694 | 9010.1694 | 9010.1694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10154 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16673.5867 | 0.2 | 0.3 | 26010.7953 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2718.4023 | 2718.4023 | 2718.4023 | 2718.4023 | 2718.4023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10155 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16674.3272 | 0.2 | 0.3 | 26011.9504 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7649.9387 | 7649.9387 | 7649.9387 | 7649.9387 | 7649.9387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10156 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 22035.1519 | 0.2 | 0.3 | 34374.8369 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4917.6679 | 4917.6679 | 4917.6679 | 4917.6679 | 4917.6679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10157 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16703.4335 | 0.2 | 0.3 | 26057.3562 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11112.5677 | 11112.5677 | 11112.5677 | 11112.5677 | 11112.5677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10158 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16712.3754 | 0.2 | 0.3 | 26071.3056 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11800.2902 | 11800.2902 | 11800.2902 | 11800.2902 | 11800.2902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10159 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16715.6633 | 0.2 | 0.3 | 26076.4348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2237.6917 | 2237.6917 | 2237.6917 | 2237.6917 | 2237.6917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10160 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 22741.0476 | 0.2 | 0.3 | 35476.0343 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4371.6946 | 4371.6946 | 4371.6946 | 4371.6946 | 4371.6946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10161 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16674.4381 | 0.2 | 0.3 | 26012.1234 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5257.5273 | 5257.5273 | 5257.5273 | 5257.5273 | 5257.5273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10162 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16674.1819 | 0.2 | 0.3 | 26011.7238 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4073.0586 | 4073.0586 | 4073.0586 | 4073.0586 | 4073.0586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10163 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16674.6859 | 0.2 | 0.3 | 26012.5101 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4863.1357 | 4863.1357 | 4863.1357 | 4863.1357 | 4863.1357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10164 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16674.7024 | 0.2 | 0.3 | 26012.5357 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7589.4558 | 7589.4558 | 7589.4558 | 7589.4558 | 7589.4558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10165 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16674.8224 | 0.2 | 0.3 | 26012.7229 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6035.5132 | 6035.5132 | 6035.5132 | 6035.5132 | 6035.5132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10166 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 31350.1199 | 0.2 | 0.3 | 48906.187 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6687.9762 | 6687.9762 | 6687.9762 | 6687.9762 | 6687.9762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10167 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16675.074 | 0.2 | 0.3 | 26013.1154 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8477.7788 | 8477.7788 | 8477.7788 | 8477.7788 | 8477.7788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10168 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16675.0755 | 0.2 | 0.3 | 26013.1177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9298.3871 | 9298.3871 | 9298.3871 | 9298.3871 | 9298.3871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10169 | MIRAMAR | 110403 | Public | 2026 | 5 | Swales | 66.6667 | 16674.0903 | 0.2 | 0.3 | 26011.5809 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8417.1813 | 8417.1813 | 8417.1813 | 8417.1813 | 8417.1813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10170 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16673.4493 | 0.2 | 0.3 | 26010.5809 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9355.2055 | 9355.2055 | 9355.2055 | 9355.2055 | 9355.2055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10171 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10031.5308 | 10031.5308 | 10031.5308 | 10031.5308 | 10031.5308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10172 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16674.6022 | 0.2 | 0.3 | 26012.3794 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7800.3953 | 7800.3953 | 7800.3953 | 7800.3953 | 7800.3953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10173 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 31350.8549 | 0.2 | 0.3 | 48907.3336 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11867.0024 | 11867.0024 | 11867.0024 | 11867.0024 | 11867.0024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10174 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16672.2309 | 0.2 | 0.3 | 26008.6803 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5178.711 | 5178.711 | 5178.711 | 5178.711 | 5178.711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10175 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16672.5986 | 0.2 | 0.3 | 26009.2538 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4454.5138 | 4454.5138 | 4454.5138 | 4454.5138 | 4454.5138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10176 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 21211.5539 | 0.2 | 0.3 | 33090.024 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6990.1151 | 6990.1151 | 6990.1151 | 6990.1151 | 6990.1151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10177 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16678.3855 | 0.2 | 0.3 | 26018.2814 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.010317 | 0.010317 | 0.010317 | 0.010317 | 0.010317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10178 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9905 | 0.2 | 0.3 | 26023.9052 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8373.5982 | 8373.5982 | 8373.5982 | 8373.5982 | 8373.5982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10179 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 16813.5139 | 0.2 | 0.3 | 26229.0816 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10180 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 1706.5359 | 0.2 | 0.3 | 2662.1961 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9771.3297 | 9771.3297 | 9771.3297 | 9771.3297 | 9771.3297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10181 | MIRAMAR | 110404 | Public | 2026 | 5 | Swales | 66.6667 | 2.1606 | 0.2 | 0.3 | 3.3705 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1660.918 | 1660.918 | 1660.918 | 1660.918 | 1660.918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10182 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.3346 | 5206.3346 | 5206.3346 | 5206.3346 | 5206.3346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10183 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.8741 | 0.2 | 0.3 | 26011.2436 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9606.8085 | 9606.8085 | 9606.8085 | 9606.8085 | 9606.8085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10184 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.7165 | 0.2 | 0.3 | 26010.9977 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 450.1116 | 450.1116 | 450.1116 | 450.1116 | 450.1116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10185 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.0851 | 0.2 | 0.3 | 26011.5727 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9996 | 5203.9996 | 5203.9996 | 5203.9996 | 5203.9996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10186 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.5532 | 0.2 | 0.3 | 26012.303 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3918.7332 | 3918.7332 | 3918.7332 | 3918.7332 | 3918.7332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10187 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4757.691 | 4757.691 | 4757.691 | 4757.691 | 4757.691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10188 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.8645 | 0.2 | 0.3 | 26012.7887 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5186.4681 | 5186.4681 | 5186.4681 | 5186.4681 | 5186.4681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10189 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16663.5297 | 0.2 | 0.3 | 25995.1064 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1865.7618 | 1865.7618 | 1865.7618 | 1865.7618 | 1865.7618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10190 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10191 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10192 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 24775.3405 | 0.2 | 0.3 | 38649.5312 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7748.2555 | 7748.2555 | 7748.2555 | 7748.2555 | 7748.2555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10193 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.744 | 0.2 | 0.3 | 26011.0406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2087.2974 | 2087.2974 | 2087.2974 | 2087.2974 | 2087.2974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10194 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.2553 | 0.2 | 0.3 | 26011.8382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4425.55 | 4425.55 | 4425.55 | 4425.55 | 4425.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10195 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.1851 | 0.2 | 0.3 | 26011.7287 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5219.974 | 5219.974 | 5219.974 | 5219.974 | 5219.974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10196 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 23001.0669 | 0.2 | 0.3 | 35881.6643 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4599.5908 | 4599.5908 | 4599.5908 | 4599.5908 | 4599.5908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10197 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16680.7389 | 0.2 | 0.3 | 26021.9527 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7845.1702 | 7845.1702 | 7845.1702 | 7845.1702 | 7845.1702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10198 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 750.6944 | 0.2 | 0.3 | 1171.0833 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10199 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 7707.9435 | 0.2 | 0.3 | 12024.3919 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6760.1734 | 6760.1734 | 6760.1734 | 6760.1734 | 6760.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10200 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 9157.5255 | 0.2 | 0.3 | 14285.7398 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10201 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 15921.2259 | 0.2 | 0.3 | 24837.1125 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1458.2608 | 1458.2608 | 1458.2608 | 1458.2608 | 1458.2608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10202 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.0071 | 0.2 | 0.3 | 26011.451 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3656.4524 | 3656.4524 | 3656.4524 | 3656.4524 | 3656.4524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10203 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4061.3582 | 4061.3582 | 4061.3582 | 4061.3582 | 4061.3582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10204 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.9197 | 0.2 | 0.3 | 26012.8748 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3.0743 | 3.0743 | 3.0743 | 3.0743 | 3.0743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10205 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16797.5544 | 0.2 | 0.3 | 26204.1849 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7014.935 | 7014.935 | 7014.935 | 7014.935 | 7014.935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10206 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 3197.9686 | 0.2 | 0.3 | 4988.831 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6046.0646 | 6046.0646 | 6046.0646 | 6046.0646 | 6046.0646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10207 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.9263 | 0.2 | 0.3 | 26012.8851 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2562.2163 | 2562.2163 | 2562.2163 | 2562.2163 | 2562.2163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10208 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 21777.2653 | 0.2 | 0.3 | 33972.5338 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2638.3678 | 2638.3678 | 2638.3678 | 2638.3678 | 2638.3678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10209 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16672.1297 | 0.2 | 0.3 | 26008.5224 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4628.8472 | 4628.8472 | 4628.8472 | 4628.8472 | 4628.8472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10210 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16672.3415 | 0.2 | 0.3 | 26008.8527 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6521.6363 | 6521.6363 | 6521.6363 | 6521.6363 | 6521.6363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10211 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16672.7349 | 0.2 | 0.3 | 26009.4664 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9492.735 | 9492.735 | 9492.735 | 9492.735 | 9492.735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10212 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.1679 | 0.2 | 0.3 | 26010.142 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7166.3531 | 7166.3531 | 7166.3531 | 7166.3531 | 7166.3531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10213 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.7085 | 0.2 | 0.3 | 26010.9852 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0704 | 5200.0704 | 5200.0704 | 5200.0704 | 5200.0704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10214 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.7085 | 0.2 | 0.3 | 26010.9852 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9290.6045 | 9290.6045 | 9290.6045 | 9290.6045 | 9290.6045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10215 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.8248 | 0.2 | 0.3 | 26011.1667 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5185.1636 | 5185.1636 | 5185.1636 | 5185.1636 | 5185.1636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10216 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 18396.2353 | 0.2 | 0.3 | 28698.1271 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10217 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 17293.5529 | 0.2 | 0.3 | 26977.9425 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4973.7437 | 4973.7437 | 4973.7437 | 4973.7437 | 4973.7437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10218 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 18230.8803 | 0.2 | 0.3 | 28440.1732 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6204.2218 | 6204.2218 | 6204.2218 | 6204.2218 | 6204.2218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10219 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 31919.9925 | 0.2 | 0.3 | 49795.1882 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5790.3998 | 5790.3998 | 5790.3998 | 5790.3998 | 5790.3998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10220 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.1463 | 0.2 | 0.3 | 26010.1082 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7023.5945 | 7023.5945 | 7023.5945 | 7023.5945 | 7023.5945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10221 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.7085 | 0.2 | 0.3 | 26010.9852 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5677.3521 | 5677.3521 | 5677.3521 | 5677.3521 | 5677.3521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10222 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.7085 | 0.2 | 0.3 | 26010.9852 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8389.0566 | 8389.0566 | 8389.0566 | 8389.0566 | 8389.0566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10223 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.7784 | 0.2 | 0.3 | 26012.6543 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1057.8446 | 1057.8446 | 1057.8446 | 1057.8446 | 1057.8446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10224 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 18008.367 | 0.2 | 0.3 | 28093.0525 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1228.15 | 1228.15 | 1228.15 | 1228.15 | 1228.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10225 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.2157 | 0.2 | 0.3 | 26011.7765 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8727.2683 | 8727.2683 | 8727.2683 | 8727.2683 | 8727.2683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10226 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.7085 | 0.2 | 0.3 | 26010.9852 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5213.0303 | 5213.0303 | 5213.0303 | 5213.0303 | 5213.0303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10227 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12570.3259 | 12570.3259 | 12570.3259 | 12570.3259 | 12570.3259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10228 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7386.1467 | 7386.1467 | 7386.1467 | 7386.1467 | 7386.1467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10229 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.5505 | 0.2 | 0.3 | 26012.2987 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9958.7265 | 9958.7265 | 9958.7265 | 9958.7265 | 9958.7265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10230 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.9027 | 0.2 | 0.3 | 26012.8483 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8191.733 | 8191.733 | 8191.733 | 8191.733 | 8191.733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10231 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16675.0755 | 0.2 | 0.3 | 26013.1177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8066.5738 | 8066.5738 | 8066.5738 | 8066.5738 | 8066.5738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10232 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7071.9224 | 7071.9224 | 7071.9224 | 7071.9224 | 7071.9224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10233 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16675.0475 | 0.2 | 0.3 | 26013.074 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9869 | 5199.9869 | 5199.9869 | 5199.9869 | 5199.9869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10234 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 15678.7001 | 0.2 | 0.3 | 24458.7721 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9448.5749 | 9448.5749 | 9448.5749 | 9448.5749 | 9448.5749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10235 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16461.0935 | 0.2 | 0.3 | 25679.3059 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4917.5125 | 4917.5125 | 4917.5125 | 4917.5125 | 4917.5125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10236 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 15502.8455 | 0.2 | 0.3 | 24184.4389 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 284.0947 | 284.0947 | 284.0947 | 284.0947 | 284.0947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10237 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 31032.6659 | 0.2 | 0.3 | 48410.9588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5534.1082 | 5534.1082 | 5534.1082 | 5534.1082 | 5534.1082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10238 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.3189 | 0.2 | 0.3 | 26011.9375 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4499.5008 | 4499.5008 | 4499.5008 | 4499.5008 | 4499.5008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10239 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.2553 | 0.2 | 0.3 | 26011.8382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8638.9999 | 8638.9999 | 8638.9999 | 8638.9999 | 8638.9999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10240 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8686.6836 | 8686.6836 | 8686.6836 | 8686.6836 | 8686.6836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10241 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16675.6119 | 0.2 | 0.3 | 26013.9546 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4096.8953 | 4096.8953 | 4096.8953 | 4096.8953 | 4096.8953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10242 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 18710.9288 | 0.2 | 0.3 | 29189.0489 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1178.8343 | 1178.8343 | 1178.8343 | 1178.8343 | 1178.8343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10243 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5783.3497 | 5783.3497 | 5783.3497 | 5783.3497 | 5783.3497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10244 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5246.5353 | 5246.5353 | 5246.5353 | 5246.5353 | 5246.5353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10245 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.2553 | 0.2 | 0.3 | 26011.8382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9795.8314 | 9795.8314 | 9795.8314 | 9795.8314 | 9795.8314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10246 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.6277 | 0.2 | 0.3 | 26012.4193 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5211.239 | 5211.239 | 5211.239 | 5211.239 | 5211.239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10247 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.4134 | 0.2 | 0.3 | 26012.0849 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8431.8797 | 8431.8797 | 8431.8797 | 8431.8797 | 8431.8797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10248 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8374.6131 | 8374.6131 | 8374.6131 | 8374.6131 | 8374.6131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10249 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7161.7513 | 7161.7513 | 7161.7513 | 7161.7513 | 7161.7513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10250 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.7865 | 0.2 | 0.3 | 26012.667 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7809.2348 | 7809.2348 | 7809.2348 | 7809.2348 | 7809.2348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10251 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 17248.4287 | 0.2 | 0.3 | 26907.5488 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7474.5883 | 7474.5883 | 7474.5883 | 7474.5883 | 7474.5883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10252 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16861.4469 | 0.2 | 0.3 | 26303.8571 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6971.4802 | 6971.4802 | 6971.4802 | 6971.4802 | 6971.4802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10253 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 18395.9175 | 0.2 | 0.3 | 28697.6312 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.062 | 5200.062 | 5200.062 | 5200.062 | 5200.062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10254 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 31682.8196 | 0.2 | 0.3 | 49425.1986 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9496.6567 | 9496.6567 | 9496.6567 | 9496.6567 | 9496.6567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10255 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16672.8189 | 0.2 | 0.3 | 26009.5974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2819.1036 | 2819.1036 | 2819.1036 | 2819.1036 | 2819.1036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10256 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.7085 | 0.2 | 0.3 | 26010.9852 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2382.4926 | 2382.4926 | 2382.4926 | 2382.4926 | 2382.4926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10257 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.4351 | 0.2 | 0.3 | 26010.5587 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.1612 | 5205.1612 | 5205.1612 | 5205.1612 | 5205.1612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10258 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.1639 | 0.2 | 0.3 | 26011.6957 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3475.4883 | 3475.4883 | 3475.4883 | 3475.4883 | 3475.4883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10259 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 19442.8408 | 0.2 | 0.3 | 30330.8316 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1828 | 5202.1828 | 5202.1828 | 5202.1828 | 5202.1828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10260 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4309.4944 | 4309.4944 | 4309.4944 | 4309.4944 | 4309.4944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10261 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.2553 | 0.2 | 0.3 | 26011.8382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8054.1935 | 8054.1935 | 8054.1935 | 8054.1935 | 8054.1935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10262 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.7085 | 0.2 | 0.3 | 26010.9852 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7426.2204 | 7426.2204 | 7426.2204 | 7426.2204 | 7426.2204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10263 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.2605 | 0.2 | 0.3 | 26011.8463 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5289.0942 | 5289.0942 | 5289.0942 | 5289.0942 | 5289.0942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10264 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.4007 | 0.2 | 0.3 | 26012.065 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1351 | 5201.1351 | 5201.1351 | 5201.1351 | 5201.1351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10265 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5211.9122 | 5211.9122 | 5211.9122 | 5211.9122 | 5211.9122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10266 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.2553 | 0.2 | 0.3 | 26011.8382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7265.2352 | 7265.2352 | 7265.2352 | 7265.2352 | 7265.2352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10267 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.0137 | 0.2 | 0.3 | 26011.4614 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8656.313 | 8656.313 | 8656.313 | 8656.313 | 8656.313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10268 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 8336.6032 | 0.2 | 0.3 | 13005.101 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11471.7639 | 11471.7639 | 11471.7639 | 11471.7639 | 11471.7639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10269 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 12460.8005 | 0.2 | 0.3 | 19438.8488 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4942.7964 | 4942.7964 | 4942.7964 | 4942.7964 | 4942.7964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10270 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.1617 | 0.2 | 0.3 | 26010.1322 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4030.9165 | 4030.9165 | 4030.9165 | 4030.9165 | 4030.9165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10271 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.6943 | 0.2 | 0.3 | 26010.9632 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8530.6625 | 8530.6625 | 8530.6625 | 8530.6625 | 8530.6625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10272 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.3906 | 0.2 | 0.3 | 26010.4893 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5238.1669 | 5238.1669 | 5238.1669 | 5238.1669 | 5238.1669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10273 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.1617 | 0.2 | 0.3 | 26010.1322 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6914.8211 | 6914.8211 | 6914.8211 | 6914.8211 | 6914.8211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10274 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.4351 | 0.2 | 0.3 | 26010.5587 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200 | 5200 | 5200 | 5200 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10275 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.1492 | 0.2 | 0.3 | 26010.1128 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9505.4598 | 9505.4598 | 9505.4598 | 9505.4598 | 9505.4598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10276 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16679.9135 | 0.2 | 0.3 | 26020.665 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2251.5341 | 2251.5341 | 2251.5341 | 2251.5341 | 2251.5341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10277 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 27795.0508 | 0.2 | 0.3 | 43360.2792 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7410.6101 | 7410.6101 | 7410.6101 | 7410.6101 | 7410.6101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10278 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.1941 | 0.2 | 0.3 | 26010.1828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4354.3864 | 4354.3864 | 4354.3864 | 4354.3864 | 4354.3864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10279 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.1617 | 0.2 | 0.3 | 26010.1322 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6888.5693 | 6888.5693 | 6888.5693 | 6888.5693 | 6888.5693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10280 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5457.6532 | 5457.6532 | 5457.6532 | 5457.6532 | 5457.6532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10281 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.2553 | 0.2 | 0.3 | 26011.8382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5341.4117 | 5341.4117 | 5341.4117 | 5341.4117 | 5341.4117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10282 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.6423 | 0.2 | 0.3 | 26012.4419 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9249 | 5200.9249 | 5200.9249 | 5200.9249 | 5200.9249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10283 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 30389.623 | 0.2 | 0.3 | 47407.8119 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5216.3618 | 5216.3618 | 5216.3618 | 5216.3618 | 5216.3618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10284 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16672.9945 | 0.2 | 0.3 | 26009.8715 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9484.0879 | 9484.0879 | 9484.0879 | 9484.0879 | 9484.0879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10285 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 15480.2897 | 0.2 | 0.3 | 24149.2519 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6633.5561 | 6633.5561 | 6633.5561 | 6633.5561 | 6633.5561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10286 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16672.913 | 0.2 | 0.3 | 26009.7443 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7745.3029 | 7745.3029 | 7745.3029 | 7745.3029 | 7745.3029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10287 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.0209 | 0.2 | 0.3 | 26011.4727 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9018.4745 | 9018.4745 | 9018.4745 | 9018.4745 | 9018.4745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10288 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 21807.6605 | 0.2 | 0.3 | 34019.9504 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1911 | 5200.1911 | 5200.1911 | 5200.1911 | 5200.1911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10289 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 25507.0197 | 0.2 | 0.3 | 39790.9507 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10455.0282 | 10455.0282 | 10455.0282 | 10455.0282 | 10455.0282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10290 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.1996 | 0.2 | 0.3 | 26011.7514 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5718.8948 | 5718.8948 | 5718.8948 | 5718.8948 | 5718.8948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10291 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.2553 | 0.2 | 0.3 | 26011.8382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7523.718 | 7523.718 | 7523.718 | 7523.718 | 7523.718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10292 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.2553 | 0.2 | 0.3 | 26011.8382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10352.0802 | 10352.0802 | 10352.0802 | 10352.0802 | 10352.0802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10293 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7432.5916 | 7432.5916 | 7432.5916 | 7432.5916 | 7432.5916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10294 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16674.506 | 0.2 | 0.3 | 26012.2294 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.9063 | 9776.9063 | 9776.9063 | 9776.9063 | 9776.9063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10295 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 32469.6756 | 0.2 | 0.3 | 50652.6939 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0669 | 5200.0669 | 5200.0669 | 5200.0669 | 5200.0669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10296 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16672.8285 | 0.2 | 0.3 | 26009.6124 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8152.9226 | 8152.9226 | 8152.9226 | 8152.9226 | 8152.9226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10297 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 17686.7547 | 0.2 | 0.3 | 27591.3374 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9926 | 5199.9926 | 5199.9926 | 5199.9926 | 5199.9926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10298 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.2739 | 0.2 | 0.3 | 26010.3072 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5807.2358 | 5807.2358 | 5807.2358 | 5807.2358 | 5807.2358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10299 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16673.2639 | 0.2 | 0.3 | 26010.2917 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0402 | 5201.0402 | 5201.0402 | 5201.0402 | 5201.0402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10300 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 20149.7985 | 0.2 | 0.3 | 31433.6856 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11191.8476 | 11191.8476 | 11191.8476 | 11191.8476 | 11191.8476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10301 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 13730.576 | 0.2 | 0.3 | 21419.6986 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5536.8018 | 5536.8018 | 5536.8018 | 5536.8018 | 5536.8018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10302 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16672.7791 | 0.2 | 0.3 | 26009.5353 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3178.0085 | 3178.0085 | 3178.0085 | 3178.0085 | 3178.0085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10303 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16672.6149 | 0.2 | 0.3 | 26009.2792 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4489.7044 | 4489.7044 | 4489.7044 | 4489.7044 | 4489.7044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10304 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16676.4425 | 0.2 | 0.3 | 26015.2502 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3767.4259 | 3767.4259 | 3767.4259 | 3767.4259 | 3767.4259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10305 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3266.7336 | 3266.7336 | 3266.7336 | 3266.7336 | 3266.7336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10306 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 16676.3958 | 0.2 | 0.3 | 26015.1774 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8844.2566 | 8844.2566 | 8844.2566 | 8844.2566 | 8844.2566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10307 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 11575.2138 | 0.2 | 0.3 | 18057.3335 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5220.2913 | 5220.2913 | 5220.2913 | 5220.2913 | 5220.2913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10308 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 8336.0871 | 0.2 | 0.3 | 13004.2959 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4987.8875 | 4987.8875 | 4987.8875 | 4987.8875 | 4987.8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10309 | MIRAMAR | 110402 | Public | 2026 | 5 | Swales | 66.6667 | 4391.5657 | 0.2 | 0.3 | 6850.8424 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2294.514 | 2294.514 | 2294.514 | 2294.514 | 2294.514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10310 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 2290.6275 | 0.2 | 0.3 | 3573.379 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 866.28 | 866.28 | 866.28 | 866.28 | 866.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10311 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 301.9621 | 0.2 | 0.3 | 471.0608 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.4468 | 2600.4468 | 2600.4468 | 2600.4468 | 2600.4468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10312 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 4785.5157 | 0.2 | 0.3 | 7465.4044 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0122 | 5201.0122 | 5201.0122 | 5201.0122 | 5201.0122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10313 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 16216.6931 | 0.2 | 0.3 | 25298.0413 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7510.3029 | 7510.3029 | 7510.3029 | 7510.3029 | 7510.3029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10314 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 19175.628 | 0.2 | 0.3 | 29913.9797 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6412.9695 | 6412.9695 | 6412.9695 | 6412.9695 | 6412.9695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10315 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 20866.1953 | 0.2 | 0.3 | 32551.2647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9219.1262 | 9219.1262 | 9219.1262 | 9219.1262 | 9219.1262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10316 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 20688.0231 | 0.2 | 0.3 | 32273.316 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6610.3106 | 6610.3106 | 6610.3106 | 6610.3106 | 6610.3106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10317 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 25210.692 | 0.2 | 0.3 | 39328.6795 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8472.9343 | 8472.9343 | 8472.9343 | 8472.9343 | 8472.9343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10318 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 2541.6246 | 0.2 | 0.3 | 3964.9344 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5492.1563 | 5492.1563 | 5492.1563 | 5492.1563 | 5492.1563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10319 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 21545.9213 | 0.2 | 0.3 | 33611.6372 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5027.5463 | 5027.5463 | 5027.5463 | 5027.5463 | 5027.5463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10320 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 17493.3264 | 0.2 | 0.3 | 27289.5892 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6656.3291 | 6656.3291 | 6656.3291 | 6656.3291 | 6656.3291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10321 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 16666.2897 | 0.2 | 0.3 | 25999.412 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9441 | 5199.9441 | 5199.9441 | 5199.9441 | 5199.9441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10322 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 23416.9294 | 0.2 | 0.3 | 36530.4099 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8889.8241 | 8889.8241 | 8889.8241 | 8889.8241 | 8889.8241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10323 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 24330.4146 | 0.2 | 0.3 | 37955.4468 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7947.0138 | 7947.0138 | 7947.0138 | 7947.0138 | 7947.0138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10324 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 29885.2277 | 0.2 | 0.3 | 46620.9552 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11349.3983 | 11349.3983 | 11349.3983 | 11349.3983 | 11349.3983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10325 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 33995.3291 | 0.2 | 0.3 | 53032.7134 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5781.3902 | 5781.3902 | 5781.3902 | 5781.3902 | 5781.3902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10326 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 30605.5768 | 0.2 | 0.3 | 47744.6998 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10327 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 28981.4742 | 0.2 | 0.3 | 45211.0998 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11656.4804 | 11656.4804 | 11656.4804 | 11656.4804 | 11656.4804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10328 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 45362.176 | 0.2 | 0.3 | 70764.9946 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12478.048 | 12478.048 | 12478.048 | 12478.048 | 12478.048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10329 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8481.819 | 8481.819 | 8481.819 | 8481.819 | 8481.819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10330 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9667.7948 | 9667.7948 | 9667.7948 | 9667.7948 | 9667.7948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10331 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10235.2177 | 10235.2177 | 10235.2177 | 10235.2177 | 10235.2177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10332 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 12462.4097 | 0.2 | 0.3 | 19441.3591 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6592.3969 | 6592.3969 | 6592.3969 | 6592.3969 | 6592.3969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10333 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 19054.6054 | 0.2 | 0.3 | 29725.1844 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0554 | 5200.0554 | 5200.0554 | 5200.0554 | 5200.0554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10334 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9494.2859 | 9494.2859 | 9494.2859 | 9494.2859 | 9494.2859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10335 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 23036.6553 | 0.2 | 0.3 | 35937.1823 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 361.863 | 361.863 | 361.863 | 361.863 | 361.863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10336 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 16667.5547 | 0.2 | 0.3 | 26001.3854 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9268 | 5199.9268 | 5199.9268 | 5199.9268 | 5199.9268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10337 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 20705.4097 | 0.2 | 0.3 | 32300.4392 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5700.2901 | 5700.2901 | 5700.2901 | 5700.2901 | 5700.2901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10338 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 28540.0122 | 0.2 | 0.3 | 44522.419 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6543.4725 | 6543.4725 | 6543.4725 | 6543.4725 | 6543.4725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10339 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 17229.5352 | 0.2 | 0.3 | 26878.0749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9858 | 5199.9858 | 5199.9858 | 5199.9858 | 5199.9858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10340 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 18019.1875 | 0.2 | 0.3 | 28109.9324 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7682.8152 | 7682.8152 | 7682.8152 | 7682.8152 | 7682.8152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10341 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 4383.8539 | 0.2 | 0.3 | 6838.8121 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2286.8732 | 2286.8732 | 2286.8732 | 2286.8732 | 2286.8732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10342 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 6329.6722 | 0.2 | 0.3 | 9874.2886 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8126.47 | 8126.47 | 8126.47 | 8126.47 | 8126.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10343 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 20308.5463 | 0.2 | 0.3 | 31681.3322 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4530.5743 | 4530.5743 | 4530.5743 | 4530.5743 | 4530.5743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10344 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 14928.2025 | 0.2 | 0.3 | 23287.9958 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4993 | 5200.4993 | 5200.4993 | 5200.4993 | 5200.4993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10345 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 22598.8413 | 0.2 | 0.3 | 35254.1924 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2663 | 5200.2663 | 5200.2663 | 5200.2663 | 5200.2663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10346 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 20923.2264 | 0.2 | 0.3 | 32640.2332 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5855.7869 | 5855.7869 | 5855.7869 | 5855.7869 | 5855.7869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10347 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 13311.1563 | 0.2 | 0.3 | 20765.4039 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 502.0185 | 502.0185 | 502.0185 | 502.0185 | 502.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10348 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 16667.2577 | 0.2 | 0.3 | 26000.922 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3559.2822 | 3559.2822 | 3559.2822 | 3559.2822 | 3559.2822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10349 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10350 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 24632.6634 | 0.2 | 0.3 | 38426.9549 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10351 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 16666.6626 | 0.2 | 0.3 | 25999.9937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6871.1309 | 6871.1309 | 6871.1309 | 6871.1309 | 6871.1309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10352 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 22579.2733 | 0.2 | 0.3 | 35223.6663 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10353 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 28370.6729 | 0.2 | 0.3 | 44258.2498 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8350.6743 | 8350.6743 | 8350.6743 | 8350.6743 | 8350.6743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10354 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 16867.0039 | 0.2 | 0.3 | 26312.526 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9115.6599 | 9115.6599 | 9115.6599 | 9115.6599 | 9115.6599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10355 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 19605.4721 | 0.2 | 0.3 | 30584.5364 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7386.4176 | 7386.4176 | 7386.4176 | 7386.4176 | 7386.4176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10356 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6792.0788 | 6792.0788 | 6792.0788 | 6792.0788 | 6792.0788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10357 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 20671.9791 | 0.2 | 0.3 | 32248.2873 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9922 | 5199.9922 | 5199.9922 | 5199.9922 | 5199.9922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10358 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 29715.9093 | 0.2 | 0.3 | 46356.8185 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10359 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 26478.3878 | 0.2 | 0.3 | 41306.285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10360 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 6278.8946 | 0.2 | 0.3 | 9795.0756 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8930.1806 | 8930.1806 | 8930.1806 | 8930.1806 | 8930.1806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10361 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 5029.8039 | 0.2 | 0.3 | 7846.4941 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6479.8498 | 6479.8498 | 6479.8498 | 6479.8498 | 6479.8498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10362 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 2102.4788 | 0.2 | 0.3 | 3279.8669 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4044.4509 | 4044.4509 | 4044.4509 | 4044.4509 | 4044.4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10363 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 3364.9283 | 0.2 | 0.3 | 5249.2881 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3561.5078 | 3561.5078 | 3561.5078 | 3561.5078 | 3561.5078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10364 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 27966.1327 | 0.2 | 0.3 | 43627.1671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9314.9598 | 9314.9598 | 9314.9598 | 9314.9598 | 9314.9598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10365 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 28473.7072 | 0.2 | 0.3 | 44418.9832 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4072.8738 | 4072.8738 | 4072.8738 | 4072.8738 | 4072.8738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10366 | DAVIE | 70304 | Private | 2026 | 5 | Swales | 66.6667 | 33850.6934 | 0.2 | 0.3 | 52807.0817 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9144.8823 | 9144.8823 | 9144.8823 | 9144.8823 | 9144.8823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10367 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 32206.1297 | 0.2 | 0.3 | 50241.5623 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8763.4371 | 8763.4371 | 8763.4371 | 8763.4371 | 8763.4371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10368 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 32007.7715 | 0.2 | 0.3 | 49932.1235 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2001.719 | 2001.719 | 2001.719 | 2001.719 | 2001.719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10369 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 28020.7571 | 0.2 | 0.3 | 43712.3811 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6702.1055 | 6702.1055 | 6702.1055 | 6702.1055 | 6702.1055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10370 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.9699 | 0.2 | 0.3 | 26000.4731 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2483.8929 | 2483.8929 | 2483.8929 | 2483.8929 | 2483.8929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10371 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5220.816 | 5220.816 | 5220.816 | 5220.816 | 5220.816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10372 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.9375 | 0.2 | 0.3 | 26000.4224 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3531.9755 | 3531.9755 | 3531.9755 | 3531.9755 | 3531.9755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10373 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 18544.4335 | 0.2 | 0.3 | 28929.3163 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1412.1281 | 1412.1281 | 1412.1281 | 1412.1281 | 1412.1281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10374 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 39183.9441 | 0.2 | 0.3 | 61126.9528 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10375 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 22369.6308 | 0.2 | 0.3 | 34896.624 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10376 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 18720.9225 | 0.2 | 0.3 | 29204.639 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8892.2095 | 8892.2095 | 8892.2095 | 8892.2095 | 8892.2095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10377 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 19980.6409 | 0.2 | 0.3 | 31169.7999 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7276.7619 | 7276.7619 | 7276.7619 | 7276.7619 | 7276.7619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10378 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 11690.1305 | 0.2 | 0.3 | 18236.6035 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5629 | 5200.5629 | 5200.5629 | 5200.5629 | 5200.5629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10379 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 7382.2249 | 0.2 | 0.3 | 11516.2709 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9111 | 5202.9111 | 5202.9111 | 5202.9111 | 5202.9111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10380 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 19343.9911 | 0.2 | 0.3 | 30176.6262 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10419.2067 | 10419.2067 | 10419.2067 | 10419.2067 | 10419.2067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10381 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 30679.5245 | 0.2 | 0.3 | 47860.0583 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5133.1596 | 5133.1596 | 5133.1596 | 5133.1596 | 5133.1596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10382 | DAVIE | 70304 | Private | 2033 | 5 | Swales | 66.6667 | 28949.0327 | 0.2 | 0.3 | 45160.491 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4639.3309 | 4639.3309 | 4639.3309 | 4639.3309 | 4639.3309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10383 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 20383.9633 | 0.2 | 0.3 | 31798.9828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5239.0334 | 5239.0334 | 5239.0334 | 5239.0334 | 5239.0334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10384 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 16714.1733 | 0.2 | 0.3 | 26074.1103 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5269.4786 | 5269.4786 | 5269.4786 | 5269.4786 | 5269.4786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10385 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 17282.5743 | 0.2 | 0.3 | 26960.8159 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3203.6529 | 3203.6529 | 3203.6529 | 3203.6529 | 3203.6529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10386 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 18787.5947 | 0.2 | 0.3 | 29308.6478 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6944.1352 | 6944.1352 | 6944.1352 | 6944.1352 | 6944.1352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10387 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 19846.5567 | 0.2 | 0.3 | 30960.6285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4043 | 5201.4043 | 5201.4043 | 5201.4043 | 5201.4043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10388 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 14417.0447 | 0.2 | 0.3 | 22490.5898 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1490.7391 | 1490.7391 | 1490.7391 | 1490.7391 | 1490.7391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10389 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 22072.4035 | 0.2 | 0.3 | 34432.9495 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4558.1672 | 4558.1672 | 4558.1672 | 4558.1672 | 4558.1672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10390 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 31181.0202 | 0.2 | 0.3 | 48642.3915 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1580.9643 | 1580.9643 | 1580.9643 | 1580.9643 | 1580.9643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10391 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 4864.9 | 0.2 | 0.3 | 7589.244 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5146.4079 | 5146.4079 | 5146.4079 | 5146.4079 | 5146.4079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10392 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 10152.9568 | 0.2 | 0.3 | 15838.6126 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8293.9989 | 8293.9989 | 8293.9989 | 8293.9989 | 8293.9989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10393 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 18123.0059 | 0.2 | 0.3 | 28271.8893 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10394 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 33333.4734 | 0.2 | 0.3 | 52000.2185 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8327.3493 | 8327.3493 | 8327.3493 | 8327.3493 | 8327.3493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10395 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7635.2646 | 7635.2646 | 7635.2646 | 7635.2646 | 7635.2646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10396 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6421.9493 | 6421.9493 | 6421.9493 | 6421.9493 | 6421.9493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10397 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7661.1843 | 7661.1843 | 7661.1843 | 7661.1843 | 7661.1843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10398 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 16678.1251 | 0.2 | 0.3 | 26017.8751 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4741.3128 | 4741.3128 | 4741.3128 | 4741.3128 | 4741.3128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10399 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 24064.6271 | 0.2 | 0.3 | 37540.8182 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0501 | 5200.0501 | 5200.0501 | 5200.0501 | 5200.0501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10400 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 23976.9423 | 0.2 | 0.3 | 37404.03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5217.1105 | 5217.1105 | 5217.1105 | 5217.1105 | 5217.1105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10401 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 17017.2703 | 0.2 | 0.3 | 26546.9416 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1456.3771 | 1456.3771 | 1456.3771 | 1456.3771 | 1456.3771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10402 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2800.096 | 2800.096 | 2800.096 | 2800.096 | 2800.096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10403 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5354.3762 | 5354.3762 | 5354.3762 | 5354.3762 | 5354.3762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10404 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 15130.246 | 0.2 | 0.3 | 23603.1838 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4758 | 5200.4758 | 5200.4758 | 5200.4758 | 5200.4758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10405 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6072 | 0.2 | 0.3 | 25999.9072 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 644.3914 | 644.3914 | 644.3914 | 644.3914 | 644.3914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10406 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 23491.6165 | 0.2 | 0.3 | 36646.9217 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7269.9152 | 7269.9152 | 7269.9152 | 7269.9152 | 7269.9152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10407 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16732.069 | 0.2 | 0.3 | 26102.0276 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1488.9487 | 1488.9487 | 1488.9487 | 1488.9487 | 1488.9487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10408 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 28779.3105 | 0.2 | 0.3 | 44895.7243 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4284.7453 | 4284.7453 | 4284.7453 | 4284.7453 | 4284.7453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10409 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 29660.9623 | 0.2 | 0.3 | 46271.1012 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0931 | 5204.0931 | 5204.0931 | 5204.0931 | 5204.0931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10410 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 46000.8053 | 0.2 | 0.3 | 71761.2562 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7731 | 5200.7731 | 5200.7731 | 5200.7731 | 5200.7731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10411 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 31333.7845 | 0.2 | 0.3 | 48880.7039 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7762.7226 | 7762.7226 | 7762.7226 | 7762.7226 | 7762.7226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10412 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 31334.0976 | 0.2 | 0.3 | 48881.1923 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7803 | 5201.7803 | 5201.7803 | 5201.7803 | 5201.7803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10413 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 31333.6041 | 0.2 | 0.3 | 48880.4224 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.856 | 5201.856 | 5201.856 | 5201.856 | 5201.856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10414 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 19354.3675 | 0.2 | 0.3 | 30192.8134 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4842.8406 | 4842.8406 | 4842.8406 | 4842.8406 | 4842.8406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10415 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 16109.3221 | 0.2 | 0.3 | 25130.5425 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6350.7771 | 6350.7771 | 6350.7771 | 6350.7771 | 6350.7771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10416 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 8333.4682 | 0.2 | 0.3 | 13000.2104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1555 | 5200.1555 | 5200.1555 | 5200.1555 | 5200.1555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10417 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16594.9759 | 0.2 | 0.3 | 25888.1624 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3316.5752 | 3316.5752 | 3316.5752 | 3316.5752 | 3316.5752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10418 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 23664.9923 | 0.2 | 0.3 | 36917.3879 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4813.7889 | 4813.7889 | 4813.7889 | 4813.7889 | 4813.7889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10419 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 28296.1599 | 0.2 | 0.3 | 44142.0095 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5272.6394 | 5272.6394 | 5272.6394 | 5272.6394 | 5272.6394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10420 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 16668.4152 | 0.2 | 0.3 | 26002.7277 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5303.7378 | 5303.7378 | 5303.7378 | 5303.7378 | 5303.7378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10421 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 16670.8529 | 0.2 | 0.3 | 26006.5306 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5245.7313 | 5245.7313 | 5245.7313 | 5245.7313 | 5245.7313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10422 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 24124.0271 | 0.2 | 0.3 | 37633.4822 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4015.6952 | 4015.6952 | 4015.6952 | 4015.6952 | 4015.6952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10423 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 14789.517 | 0.2 | 0.3 | 23071.6465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4658.2363 | 4658.2363 | 4658.2363 | 4658.2363 | 4658.2363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10424 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 23122.4523 | 0.2 | 0.3 | 36071.0256 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3658 | 5201.3658 | 5201.3658 | 5201.3658 | 5201.3658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10425 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6002 | 0.2 | 0.3 | 25999.8963 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6495.526 | 6495.526 | 6495.526 | 6495.526 | 6495.526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10426 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 766.0018 | 766.0018 | 766.0018 | 766.0018 | 766.0018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10427 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6052 | 0.2 | 0.3 | 25999.9041 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5388.6309 | 5388.6309 | 5388.6309 | 5388.6309 | 5388.6309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10428 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 27109.0775 | 0.2 | 0.3 | 42290.1608 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3377.9383 | 3377.9383 | 3377.9383 | 3377.9383 | 3377.9383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10429 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 33333.1643 | 0.2 | 0.3 | 51999.7363 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6208.3793 | 6208.3793 | 6208.3793 | 6208.3793 | 6208.3793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10430 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16667.2431 | 0.2 | 0.3 | 26000.8993 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2567.6778 | 2567.6778 | 2567.6778 | 2567.6778 | 2567.6778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10431 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16667.1347 | 0.2 | 0.3 | 26000.7301 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1985 | 5202.1985 | 5202.1985 | 5202.1985 | 5202.1985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10432 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6604 | 0.2 | 0.3 | 25999.9902 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1654.5302 | 1654.5302 | 1654.5302 | 1654.5302 | 1654.5302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10433 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 24749.4171 | 0.2 | 0.3 | 38609.0907 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8230.5289 | 8230.5289 | 8230.5289 | 8230.5289 | 8230.5289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10434 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 31828.3157 | 0.2 | 0.3 | 49652.1724 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9903 | 5199.9903 | 5199.9903 | 5199.9903 | 5199.9903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10435 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 8333.1384 | 0.2 | 0.3 | 12999.6959 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7206.6635 | 7206.6635 | 7206.6635 | 7206.6635 | 7206.6635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10436 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 23459.0116 | 0.2 | 0.3 | 36596.0581 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2053.6721 | 2053.6721 | 2053.6721 | 2053.6721 | 2053.6721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10437 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4719.72 | 4719.72 | 4719.72 | 4719.72 | 4719.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10438 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 20401.097 | 0.2 | 0.3 | 31825.7113 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2220.3132 | 2220.3132 | 2220.3132 | 2220.3132 | 2220.3132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10439 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7839.2826 | 7839.2826 | 7839.2826 | 7839.2826 | 7839.2826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10440 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 18316.3945 | 0.2 | 0.3 | 28573.5755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6690.4956 | 6690.4956 | 6690.4956 | 6690.4956 | 6690.4956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10441 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 21190.2627 | 0.2 | 0.3 | 33056.8098 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10293.4729 | 10293.4729 | 10293.4729 | 10293.4729 | 10293.4729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10442 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 6310.9907 | 0.2 | 0.3 | 9845.1455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10443 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 29132.5165 | 0.2 | 0.3 | 45446.7258 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10444 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 11874.3084 | 0.2 | 0.3 | 18523.9211 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8615.5893 | 8615.5893 | 8615.5893 | 8615.5893 | 8615.5893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10445 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 9060.5964 | 0.2 | 0.3 | 14134.5304 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5208.3336 | 5208.3336 | 5208.3336 | 5208.3336 | 5208.3336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10446 | DAVIE | 70304 | Private | 2036 | 5 | Swales | 66.6667 | 10303.139 | 0.2 | 0.3 | 16072.8968 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5208.3134 | 5208.3134 | 5208.3134 | 5208.3134 | 5208.3134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10447 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.8151 | 0.2 | 0.3 | 26000.2315 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3022 | 5201.3022 | 5201.3022 | 5201.3022 | 5201.3022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10448 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5097.4523 | 5097.4523 | 5097.4523 | 5097.4523 | 5097.4523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10449 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.7411 | 0.2 | 0.3 | 26000.1162 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8409.6286 | 8409.6286 | 8409.6286 | 8409.6286 | 8409.6286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10450 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 12558.9106 | 0.2 | 0.3 | 19591.9005 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.8466 | 5203.8466 | 5203.8466 | 5203.8466 | 5203.8466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10451 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 33332.998 | 0.2 | 0.3 | 51999.4769 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4247.8906 | 4247.8906 | 4247.8906 | 4247.8906 | 4247.8906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10452 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16667.5013 | 0.2 | 0.3 | 26001.302 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6162.6256 | 6162.6256 | 6162.6256 | 6162.6256 | 6162.6256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10453 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16667.3783 | 0.2 | 0.3 | 26001.1101 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8757.0758 | 8757.0758 | 8757.0758 | 8757.0758 | 8757.0758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10454 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.8465 | 0.2 | 0.3 | 26000.2806 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10455 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 21915.4855 | 0.2 | 0.3 | 34188.1573 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2225.04 | 2225.04 | 2225.04 | 2225.04 | 2225.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10456 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 24104.9344 | 0.2 | 0.3 | 37603.6977 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4560.9939 | 4560.9939 | 4560.9939 | 4560.9939 | 4560.9939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10457 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 8333.9901 | 0.2 | 0.3 | 13001.0245 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4031.0304 | 4031.0304 | 4031.0304 | 4031.0304 | 4031.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10458 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 39178.323 | 0.2 | 0.3 | 61118.1839 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6455.8926 | 6455.8926 | 6455.8926 | 6455.8926 | 6455.8926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10459 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 32413.6702 | 0.2 | 0.3 | 50565.3255 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3515.7109 | 3515.7109 | 3515.7109 | 3515.7109 | 3515.7109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10460 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 33333.4734 | 0.2 | 0.3 | 52000.2185 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6699.7129 | 6699.7129 | 6699.7129 | 6699.7129 | 6699.7129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10461 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 33333.565 | 0.2 | 0.3 | 52000.3614 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8833.2653 | 8833.2653 | 8833.2653 | 8833.2653 | 8833.2653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10462 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 37820.0504 | 0.2 | 0.3 | 58999.2786 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10463 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 1476.4055 | 0.2 | 0.3 | 2303.1925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10464 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 28965.2092 | 0.2 | 0.3 | 45185.7264 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8699.9726 | 8699.9726 | 8699.9726 | 8699.9726 | 8699.9726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10465 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 33336.5313 | 0.2 | 0.3 | 52004.9889 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10466 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 30719.1637 | 0.2 | 0.3 | 47921.8953 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8257.8116 | 8257.8116 | 8257.8116 | 8257.8116 | 8257.8116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10467 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 25000.0544 | 0.2 | 0.3 | 39000.0849 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7800.9064 | 7800.9064 | 7800.9064 | 7800.9064 | 7800.9064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10468 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 25346.6663 | 0.2 | 0.3 | 39540.7994 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6831.9356 | 6831.9356 | 6831.9356 | 6831.9356 | 6831.9356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10469 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 21548.546 | 0.2 | 0.3 | 33615.7318 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 86.1203 | 86.1203 | 86.1203 | 86.1203 | 86.1203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10470 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 24768.9887 | 0.2 | 0.3 | 38639.6223 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9751.4989 | 9751.4989 | 9751.4989 | 9751.4989 | 9751.4989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10471 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 17835.3291 | 0.2 | 0.3 | 27823.1133 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7371.6306 | 7371.6306 | 7371.6306 | 7371.6306 | 7371.6306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10472 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 10543.7007 | 0.2 | 0.3 | 16448.1731 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7368.7573 | 7368.7573 | 7368.7573 | 7368.7573 | 7368.7573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10473 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 13088.1665 | 0.2 | 0.3 | 20417.5398 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6276.1907 | 6276.1907 | 6276.1907 | 6276.1907 | 6276.1907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10474 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 21972.5869 | 0.2 | 0.3 | 34277.2355 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7558.4671 | 7558.4671 | 7558.4671 | 7558.4671 | 7558.4671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10475 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 24196.5602 | 0.2 | 0.3 | 37746.6339 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6623.7747 | 6623.7747 | 6623.7747 | 6623.7747 | 6623.7747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10476 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 8333.8155 | 0.2 | 0.3 | 13000.7522 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4842.0567 | 4842.0567 | 4842.0567 | 4842.0567 | 4842.0567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10477 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 28046.1823 | 0.2 | 0.3 | 43752.0443 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10478 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 17585.9575 | 0.2 | 0.3 | 27434.0936 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7513 | 5201.7513 | 5201.7513 | 5201.7513 | 5201.7513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10479 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9722.5008 | 9722.5008 | 9722.5008 | 9722.5008 | 9722.5008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10480 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.5503 | 0.2 | 0.3 | 25999.8185 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9775 | 5199.9775 | 5199.9775 | 5199.9775 | 5199.9775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10481 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 23297.2695 | 0.2 | 0.3 | 36343.7405 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10482 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 23029.5561 | 0.2 | 0.3 | 35926.1076 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10483 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 21686.1377 | 0.2 | 0.3 | 33830.3749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5756.9306 | 5756.9306 | 5756.9306 | 5756.9306 | 5756.9306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10484 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 25432.3799 | 0.2 | 0.3 | 39674.5126 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6697.8992 | 6697.8992 | 6697.8992 | 6697.8992 | 6697.8992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10485 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 29865.2805 | 0.2 | 0.3 | 46589.8375 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10486 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 2755.3828 | 0.2 | 0.3 | 4298.3972 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6616.5934 | 6616.5934 | 6616.5934 | 6616.5934 | 6616.5934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10487 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 8333.4923 | 0.2 | 0.3 | 13000.2479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10513.1564 | 10513.1564 | 10513.1564 | 10513.1564 | 10513.1564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10488 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 7986.6858 | 0.2 | 0.3 | 12459.2298 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2096.7149 | 2096.7149 | 2096.7149 | 2096.7149 | 2096.7149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10489 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 29697.4223 | 0.2 | 0.3 | 46327.9787 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6692.9692 | 6692.9692 | 6692.9692 | 6692.9692 | 6692.9692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10490 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.7891 | 0.2 | 0.3 | 26000.191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1253.7564 | 1253.7564 | 1253.7564 | 1253.7564 | 1253.7564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10491 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8751.3985 | 8751.3985 | 8751.3985 | 8751.3985 | 8751.3985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10492 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10493 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.7409 | 0.2 | 0.3 | 26000.1158 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10494 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 24511.9172 | 0.2 | 0.3 | 38238.5908 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8865.8831 | 8865.8831 | 8865.8831 | 8865.8831 | 8865.8831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10495 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 32234.3204 | 0.2 | 0.3 | 50285.5398 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10496 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 8333.1634 | 0.2 | 0.3 | 12999.7349 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9301.0048 | 9301.0048 | 9301.0048 | 9301.0048 | 9301.0048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10497 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 21791.777 | 0.2 | 0.3 | 33995.1721 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10498 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6058 | 0.2 | 0.3 | 25999.905 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10499 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.9185 | 0.2 | 0.3 | 26000.3929 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5834.0564 | 5834.0564 | 5834.0564 | 5834.0564 | 5834.0564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10500 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.9817 | 0.2 | 0.3 | 26000.4914 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9675.96 | 9675.96 | 9675.96 | 9675.96 | 9675.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10501 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16984.2629 | 0.2 | 0.3 | 26495.4502 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10502 | DAVIE | 70205 | Private | 2026 | 5 | Swales | 66.6667 | 22387.6495 | 0.2 | 0.3 | 34924.7332 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5288.423 | 5288.423 | 5288.423 | 5288.423 | 5288.423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10503 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 21358.5715 | 0.2 | 0.3 | 33319.3715 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7901.8674 | 7901.8674 | 7901.8674 | 7901.8674 | 7901.8674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10504 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3952.1252 | 3952.1252 | 3952.1252 | 3952.1252 | 3952.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10505 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1897.7933 | 1897.7933 | 1897.7933 | 1897.7933 | 1897.7933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10506 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 18093.7043 | 0.2 | 0.3 | 28226.1788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5972.8959 | 5972.8959 | 5972.8959 | 5972.8959 | 5972.8959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10507 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 16667.964 | 0.2 | 0.3 | 26002.0238 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9565.744 | 9565.744 | 9565.744 | 9565.744 | 9565.744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10508 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7446.1739 | 7446.1739 | 7446.1739 | 7446.1739 | 7446.1739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10509 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 10381.2645 | 0.2 | 0.3 | 16194.7726 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11331.8668 | 11331.8668 | 11331.8668 | 11331.8668 | 11331.8668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10510 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6733 | 0.2 | 0.3 | 26000.0104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9343.5759 | 9343.5759 | 9343.5759 | 9343.5759 | 9343.5759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10511 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6071 | 0.2 | 0.3 | 25999.9071 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7165.672 | 7165.672 | 7165.672 | 7165.672 | 7165.672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10512 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9396.117 | 9396.117 | 9396.117 | 9396.117 | 9396.117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10513 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6207 | 0.2 | 0.3 | 25999.9283 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 293.0077 | 293.0077 | 293.0077 | 293.0077 | 293.0077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10514 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 42672.0747 | 0.2 | 0.3 | 66568.4365 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5110.9286 | 5110.9286 | 5110.9286 | 5110.9286 | 5110.9286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10515 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 33333.8283 | 0.2 | 0.3 | 52000.7721 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.4621 | 5206.4621 | 5206.4621 | 5206.4621 | 5206.4621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10516 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 33333.7468 | 0.2 | 0.3 | 52000.645 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.7849 | 5206.7849 | 5206.7849 | 5206.7849 | 5206.7849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10517 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 33333.4734 | 0.2 | 0.3 | 52000.2185 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2418.7254 | 2418.7254 | 2418.7254 | 2418.7254 | 2418.7254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10518 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 33325.6671 | 0.2 | 0.3 | 51988.0406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8585.1319 | 8585.1319 | 8585.1319 | 8585.1319 | 8585.1319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10519 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 22081.0655 | 0.2 | 0.3 | 34446.4621 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10520 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 30783.7239 | 0.2 | 0.3 | 48022.6092 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10521 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 7553.1313 | 0.2 | 0.3 | 11782.8849 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5235.2211 | 5235.2211 | 5235.2211 | 5235.2211 | 5235.2211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10522 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 25136.9035 | 0.2 | 0.3 | 39213.5694 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.0366 | 5205.0366 | 5205.0366 | 5205.0366 | 5205.0366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10523 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 22663.6675 | 0.2 | 0.3 | 35355.3212 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4215 | 5201.4215 | 5201.4215 | 5201.4215 | 5201.4215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10524 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9597.4694 | 9597.4694 | 9597.4694 | 9597.4694 | 9597.4694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10525 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 16679.0608 | 0.2 | 0.3 | 26019.3348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8616.7407 | 8616.7407 | 8616.7407 | 8616.7407 | 8616.7407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10526 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 16666.9679 | 0.2 | 0.3 | 26000.4699 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 690.5603 | 690.5603 | 690.5603 | 690.5603 | 690.5603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10527 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 17647.2857 | 0.2 | 0.3 | 27529.7656 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5770.959 | 5770.959 | 5770.959 | 5770.959 | 5770.959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10528 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6009 | 0.2 | 0.3 | 25999.8975 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2196.0892 | 2196.0892 | 2196.0892 | 2196.0892 | 2196.0892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10529 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5323.7393 | 5323.7393 | 5323.7393 | 5323.7393 | 5323.7393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10530 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4271.3503 | 4271.3503 | 4271.3503 | 4271.3503 | 4271.3503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10531 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6137 | 0.2 | 0.3 | 25999.9174 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1645.3164 | 1645.3164 | 1645.3164 | 1645.3164 | 1645.3164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10532 | DAVIE | 70323 | Private | 2026 | 5 | Swales | 66.6667 | 31334.3033 | 0.2 | 0.3 | 48881.5132 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6298.6114 | 6298.6114 | 6298.6114 | 6298.6114 | 6298.6114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10533 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6093 | 0.2 | 0.3 | 25999.9105 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6367.123 | 6367.123 | 6367.123 | 6367.123 | 6367.123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10534 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6353.7829 | 6353.7829 | 6353.7829 | 6353.7829 | 6353.7829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10535 | DAVIE | 70324 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6512 | 0.2 | 0.3 | 25999.9759 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8081.1579 | 8081.1579 | 8081.1579 | 8081.1579 | 8081.1579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10536 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 25258.0153 | 0.2 | 0.3 | 39402.5038 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8766.8178 | 8766.8178 | 8766.8178 | 8766.8178 | 8766.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10537 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 31334.9249 | 0.2 | 0.3 | 48882.4828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7479.4211 | 7479.4211 | 7479.4211 | 7479.4211 | 7479.4211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10538 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8573 | 0.2 | 0.3 | 26000.2974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6971.1361 | 6971.1361 | 6971.1361 | 6971.1361 | 6971.1361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10539 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16988.6591 | 0.2 | 0.3 | 26502.3082 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1747.9998 | 1747.9998 | 1747.9998 | 1747.9998 | 1747.9998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10540 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 20102.1775 | 0.2 | 0.3 | 31359.397 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4319.5889 | 4319.5889 | 4319.5889 | 4319.5889 | 4319.5889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10541 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 22666.961 | 0.2 | 0.3 | 35360.4592 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6339.9472 | 6339.9472 | 6339.9472 | 6339.9472 | 6339.9472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10542 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 11027.8176 | 0.2 | 0.3 | 17203.3955 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.2062 | 5206.2062 | 5206.2062 | 5206.2062 | 5206.2062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10543 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 20588.5949 | 0.2 | 0.3 | 32118.2081 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.2449 | 5206.2449 | 5206.2449 | 5206.2449 | 5206.2449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10544 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 22670.9313 | 0.2 | 0.3 | 35366.6528 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6374.167 | 6374.167 | 6374.167 | 6374.167 | 6374.167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10545 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 12134.8663 | 0.2 | 0.3 | 18930.3914 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9396.2824 | 9396.2824 | 9396.2824 | 9396.2824 | 9396.2824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10546 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 17018.4307 | 0.2 | 0.3 | 26548.7519 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7573.9823 | 7573.9823 | 7573.9823 | 7573.9823 | 7573.9823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10547 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 27813.6861 | 0.2 | 0.3 | 43389.3504 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7222.1365 | 7222.1365 | 7222.1365 | 7222.1365 | 7222.1365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10548 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6082 | 0.2 | 0.3 | 25999.9088 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6493.9383 | 6493.9383 | 6493.9383 | 6493.9383 | 6493.9383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10549 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 7693.6044 | 0.2 | 0.3 | 12002.0229 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4465.9406 | 4465.9406 | 4465.9406 | 4465.9406 | 4465.9406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10550 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 8973.0013 | 0.2 | 0.3 | 13997.8821 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5579.801 | 5579.801 | 5579.801 | 5579.801 | 5579.801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10551 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 10529.7081 | 0.2 | 0.3 | 16426.3447 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9614.5896 | 9614.5896 | 9614.5896 | 9614.5896 | 9614.5896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10552 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 26075.2855 | 0.2 | 0.3 | 40677.4454 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9805.8956 | 9805.8956 | 9805.8956 | 9805.8956 | 9805.8956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10553 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 16670.0255 | 0.2 | 0.3 | 26005.2398 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1085.3895 | 1085.3895 | 1085.3895 | 1085.3895 | 1085.3895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10554 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 16727.5193 | 0.2 | 0.3 | 26094.9301 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6716.2373 | 6716.2373 | 6716.2373 | 6716.2373 | 6716.2373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10555 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 16669.2503 | 0.2 | 0.3 | 26004.0304 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.2286 | 9779.2286 | 9779.2286 | 9779.2286 | 9779.2286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10556 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 19175.2073 | 0.2 | 0.3 | 29913.3234 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4372.2154 | 4372.2154 | 4372.2154 | 4372.2154 | 4372.2154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10557 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 29779.4118 | 0.2 | 0.3 | 46455.8824 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5230.9888 | 5230.9888 | 5230.9888 | 5230.9888 | 5230.9888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10558 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3165 | 5202.3165 | 5202.3165 | 5202.3165 | 5202.3165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10559 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9935 | 5202.9935 | 5202.9935 | 5202.9935 | 5202.9935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10560 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 30989.8584 | 0.2 | 0.3 | 48344.1791 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7451 | 5202.7451 | 5202.7451 | 5202.7451 | 5202.7451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10561 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16770.6698 | 0.2 | 0.3 | 26162.2449 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3326.5176 | 3326.5176 | 3326.5176 | 3326.5176 | 3326.5176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10562 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 36788.912 | 0.2 | 0.3 | 57390.7027 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4467.4064 | 4467.4064 | 4467.4064 | 4467.4064 | 4467.4064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10563 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 17107.1323 | 0.2 | 0.3 | 26687.1263 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2124.6463 | 2124.6463 | 2124.6463 | 2124.6463 | 2124.6463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10564 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 18842.6756 | 0.2 | 0.3 | 29394.5739 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2599.8953 | 2599.8953 | 2599.8953 | 2599.8953 | 2599.8953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10565 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 550.2001 | 0.2 | 0.3 | 858.3121 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2046.8363 | 2046.8363 | 2046.8363 | 2046.8363 | 2046.8363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10566 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 26652.1508 | 0.2 | 0.3 | 41577.3552 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5197.7261 | 5197.7261 | 5197.7261 | 5197.7261 | 5197.7261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10567 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 41823.9926 | 0.2 | 0.3 | 65245.4285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4814.0213 | 4814.0213 | 4814.0213 | 4814.0213 | 4814.0213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10568 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 29090.1864 | 0.2 | 0.3 | 45380.6908 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.9404 | 5206.9404 | 5206.9404 | 5206.9404 | 5206.9404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10569 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 22774.3383 | 0.2 | 0.3 | 35527.9678 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6456.5114 | 6456.5114 | 6456.5114 | 6456.5114 | 6456.5114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10570 | DAVIE | 70304 | Public | 2033 | 5 | Swales | 66.6667 | 3473.2369 | 0.2 | 0.3 | 5418.2495 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9535.5418 | 9535.5418 | 9535.5418 | 9535.5418 | 9535.5418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10571 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 38183.6523 | 0.2 | 0.3 | 59566.4976 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8026.0257 | 8026.0257 | 8026.0257 | 8026.0257 | 8026.0257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10572 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6772 | 0.2 | 0.3 | 26000.0164 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8377.8011 | 8377.8011 | 8377.8011 | 8377.8011 | 8377.8011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10573 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 17199.9586 | 0.2 | 0.3 | 26831.9354 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11953.0217 | 11953.0217 | 11953.0217 | 11953.0217 | 11953.0217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10574 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 24208.5949 | 0.2 | 0.3 | 37765.408 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7802.3833 | 7802.3833 | 7802.3833 | 7802.3833 | 7802.3833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10575 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 31337.0995 | 0.2 | 0.3 | 48885.8752 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2601.0238 | 2601.0238 | 2601.0238 | 2601.0238 | 2601.0238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10576 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 28732.2683 | 0.2 | 0.3 | 44822.3385 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8315.9846 | 8315.9846 | 8315.9846 | 8315.9846 | 8315.9846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10577 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 21959.5295 | 0.2 | 0.3 | 34256.866 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1314.3354 | 1314.3354 | 1314.3354 | 1314.3354 | 1314.3354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10578 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 10599.8969 | 0.2 | 0.3 | 16535.8392 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9559.7044 | 9559.7044 | 9559.7044 | 9559.7044 | 9559.7044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10579 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 9157.211 | 0.2 | 0.3 | 14285.2492 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9939 | 5202.9939 | 5202.9939 | 5202.9939 | 5202.9939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10580 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 26366.7651 | 0.2 | 0.3 | 41132.1536 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3468.1967 | 3468.1967 | 3468.1967 | 3468.1967 | 3468.1967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10581 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 17276.9435 | 0.2 | 0.3 | 26952.0318 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4335.2967 | 4335.2967 | 4335.2967 | 4335.2967 | 4335.2967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10582 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 16667.3967 | 0.2 | 0.3 | 26001.1389 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3459.5019 | 3459.5019 | 3459.5019 | 3459.5019 | 3459.5019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10583 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 16666.0532 | 0.2 | 0.3 | 25999.043 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9537.3058 | 9537.3058 | 9537.3058 | 9537.3058 | 9537.3058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10584 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 16666.4961 | 0.2 | 0.3 | 25999.734 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10585 | DAVIE | 70324 | Private | 2026 | 5 | Swales | 66.6667 | 11953.4659 | 0.2 | 0.3 | 18647.4069 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4622 | 5200.4622 | 5200.4622 | 5200.4622 | 5200.4622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10586 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 23672.5648 | 0.2 | 0.3 | 36929.2011 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6384.8847 | 6384.8847 | 6384.8847 | 6384.8847 | 6384.8847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10587 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 27220.7213 | 0.2 | 0.3 | 42464.3252 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9882.0185 | 9882.0185 | 9882.0185 | 9882.0185 | 9882.0185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10588 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9583.7796 | 9583.7796 | 9583.7796 | 9583.7796 | 9583.7796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10589 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16666.5999 | 0.2 | 0.3 | 25999.8958 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.5462 | 5206.5462 | 5206.5462 | 5206.5462 | 5206.5462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10590 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 23910.7335 | 0.2 | 0.3 | 37300.7443 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5799.7987 | 5799.7987 | 5799.7987 | 5799.7987 | 5799.7987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10591 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 26066.199 | 0.2 | 0.3 | 40663.2704 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8023.2637 | 8023.2637 | 8023.2637 | 8023.2637 | 8023.2637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10592 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16676.2658 | 0.2 | 0.3 | 26014.9746 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.993 | 5199.993 | 5199.993 | 5199.993 | 5199.993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10593 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 9649.6995 | 0.2 | 0.3 | 15053.5312 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10594 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 3657.4335 | 0.2 | 0.3 | 5705.5962 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9548.9755 | 9548.9755 | 9548.9755 | 9548.9755 | 9548.9755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10595 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 21434.182 | 0.2 | 0.3 | 33437.3239 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7675.4477 | 7675.4477 | 7675.4477 | 7675.4477 | 7675.4477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10596 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 17068.8223 | 0.2 | 0.3 | 26627.3627 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5838.6011 | 5838.6011 | 5838.6011 | 5838.6011 | 5838.6011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10597 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 19816.9873 | 0.2 | 0.3 | 30914.5002 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6366.3381 | 6366.3381 | 6366.3381 | 6366.3381 | 6366.3381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10598 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 17603.5611 | 0.2 | 0.3 | 27461.5553 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3980.4646 | 3980.4646 | 3980.4646 | 3980.4646 | 3980.4646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10599 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 17225.423 | 0.2 | 0.3 | 26871.6599 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5265.9265 | 5265.9265 | 5265.9265 | 5265.9265 | 5265.9265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10600 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 27042.5661 | 0.2 | 0.3 | 42186.4031 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10601 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 35886.0315 | 0.2 | 0.3 | 55982.2091 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10602 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 12266.9596 | 0.2 | 0.3 | 19136.457 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5910.4449 | 5910.4449 | 5910.4449 | 5910.4449 | 5910.4449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10603 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 25866.0495 | 0.2 | 0.3 | 40351.0372 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7744.5107 | 7744.5107 | 7744.5107 | 7744.5107 | 7744.5107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10604 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 11549.8652 | 0.2 | 0.3 | 18017.7897 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6140.6632 | 6140.6632 | 6140.6632 | 6140.6632 | 6140.6632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10605 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 20018.1877 | 0.2 | 0.3 | 31228.3728 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9809 | 5199.9809 | 5199.9809 | 5199.9809 | 5199.9809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10606 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 15626.761 | 0.2 | 0.3 | 24377.7472 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7857.0472 | 7857.0472 | 7857.0472 | 7857.0472 | 7857.0472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10607 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16666.8019 | 0.2 | 0.3 | 26000.211 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7070.2703 | 7070.2703 | 7070.2703 | 7070.2703 | 7070.2703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10608 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 21743.3165 | 0.2 | 0.3 | 33919.5738 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3333.0407 | 3333.0407 | 3333.0407 | 3333.0407 | 3333.0407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10609 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 20380.8579 | 0.2 | 0.3 | 31794.1384 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6510.7543 | 6510.7543 | 6510.7543 | 6510.7543 | 6510.7543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10610 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0326 | 5200.0326 | 5200.0326 | 5200.0326 | 5200.0326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10611 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 26267.8469 | 0.2 | 0.3 | 40977.8411 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9887 | 5199.9887 | 5199.9887 | 5199.9887 | 5199.9887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10612 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 31351.155 | 0.2 | 0.3 | 48907.8018 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6660.7004 | 6660.7004 | 6660.7004 | 6660.7004 | 6660.7004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10613 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 31632.9317 | 0.2 | 0.3 | 49347.3735 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5190.6875 | 5190.6875 | 5190.6875 | 5190.6875 | 5190.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10614 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 19060.5592 | 0.2 | 0.3 | 29734.4724 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.3946 | 9777.3946 | 9777.3946 | 9777.3946 | 9777.3946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10615 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 17082.5013 | 0.2 | 0.3 | 26648.702 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5658.0174 | 5658.0174 | 5658.0174 | 5658.0174 | 5658.0174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10616 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 17325.1431 | 0.2 | 0.3 | 27027.2232 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5398.1745 | 5398.1745 | 5398.1745 | 5398.1745 | 5398.1745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10617 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 24356.5549 | 0.2 | 0.3 | 37996.2257 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5676.9166 | 5676.9166 | 5676.9166 | 5676.9166 | 5676.9166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10618 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 21489.303 | 0.2 | 0.3 | 33523.3127 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5358.3444 | 5358.3444 | 5358.3444 | 5358.3444 | 5358.3444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10619 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 26188.4595 | 0.2 | 0.3 | 40853.9968 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7051.7176 | 7051.7176 | 7051.7176 | 7051.7176 | 7051.7176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10620 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16671.7443 | 0.2 | 0.3 | 26007.9212 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0597 | 5200.0597 | 5200.0597 | 5200.0597 | 5200.0597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10621 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 12273.5397 | 0.2 | 0.3 | 19146.7219 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10622 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 17681.5629 | 0.2 | 0.3 | 27583.2381 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9814 | 5199.9814 | 5199.9814 | 5199.9814 | 5199.9814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10623 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 14723.8029 | 0.2 | 0.3 | 22969.1325 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6546.9583 | 6546.9583 | 6546.9583 | 6546.9583 | 6546.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10624 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 32788.0385 | 0.2 | 0.3 | 51149.3401 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9302 | 5200.9302 | 5200.9302 | 5200.9302 | 5200.9302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10625 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 18114.4658 | 0.2 | 0.3 | 28258.5666 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7914.3128 | 7914.3128 | 7914.3128 | 7914.3128 | 7914.3128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10626 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 12652.9713 | 0.2 | 0.3 | 19738.6353 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9892 | 5199.9892 | 5199.9892 | 5199.9892 | 5199.9892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10627 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 96.195 | 0.2 | 0.3 | 150.0642 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10628 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16676.2804 | 0.2 | 0.3 | 26014.9974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9624.7952 | 9624.7952 | 9624.7952 | 9624.7952 | 9624.7952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10629 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 6460.1071 | 0.2 | 0.3 | 10077.767 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8530.7478 | 8530.7478 | 8530.7478 | 8530.7478 | 8530.7478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10630 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 2065.3604 | 0.2 | 0.3 | 3221.9622 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10631 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 16623.3721 | 0.2 | 0.3 | 25932.4605 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7673.6029 | 7673.6029 | 7673.6029 | 7673.6029 | 7673.6029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10632 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 5157.0745 | 0.2 | 0.3 | 8045.0362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5240.1058 | 5240.1058 | 5240.1058 | 5240.1058 | 5240.1058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10633 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 14470.3935 | 0.2 | 0.3 | 22573.8139 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9029.2104 | 9029.2104 | 9029.2104 | 9029.2104 | 9029.2104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10634 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 29124.7566 | 0.2 | 0.3 | 45434.6203 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8151 | 5199.8151 | 5199.8151 | 5199.8151 | 5199.8151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10635 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 1501.2843 | 0.2 | 0.3 | 2342.0036 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9811 | 5199.9811 | 5199.9811 | 5199.9811 | 5199.9811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10636 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 17002.488 | 0.2 | 0.3 | 26523.8813 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9811 | 5199.9811 | 5199.9811 | 5199.9811 | 5199.9811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10637 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16672.8605 | 0.2 | 0.3 | 26009.6623 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9058.0652 | 9058.0652 | 9058.0652 | 9058.0652 | 9058.0652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10638 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5990.01 | 5990.01 | 5990.01 | 5990.01 | 5990.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10639 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 30791.9987 | 0.2 | 0.3 | 48035.518 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5796.3445 | 5796.3445 | 5796.3445 | 5796.3445 | 5796.3445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10640 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 24173.3848 | 0.2 | 0.3 | 37710.4803 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6388.5145 | 6388.5145 | 6388.5145 | 6388.5145 | 6388.5145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10641 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16666.7539 | 0.2 | 0.3 | 26000.136 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6253.0409 | 6253.0409 | 6253.0409 | 6253.0409 | 6253.0409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10642 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16667.6344 | 0.2 | 0.3 | 26001.5097 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0873 | 5200.0873 | 5200.0873 | 5200.0873 | 5200.0873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10643 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16678.2443 | 0.2 | 0.3 | 26018.0612 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6197.9297 | 6197.9297 | 6197.9297 | 6197.9297 | 6197.9297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10644 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16666.9406 | 0.2 | 0.3 | 26000.4273 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6111.365 | 6111.365 | 6111.365 | 6111.365 | 6111.365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10645 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16666.8915 | 0.2 | 0.3 | 26000.3507 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11090.763 | 11090.763 | 11090.763 | 11090.763 | 11090.763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10646 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16666.3457 | 0.2 | 0.3 | 25999.4992 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7800.1718 | 7800.1718 | 7800.1718 | 7800.1718 | 7800.1718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10647 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 29308.9329 | 0.2 | 0.3 | 45721.9353 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7809.2809 | 7809.2809 | 7809.2809 | 7809.2809 | 7809.2809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10648 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 33344.0558 | 0.2 | 0.3 | 52016.727 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10714.0715 | 10714.0715 | 10714.0715 | 10714.0715 | 10714.0715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10649 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 33336.6272 | 0.2 | 0.3 | 52005.1384 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.5448 | 9779.5448 | 9779.5448 | 9779.5448 | 9779.5448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10650 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 31162.5677 | 0.2 | 0.3 | 48613.6057 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2856 | 5200.2856 | 5200.2856 | 5200.2856 | 5200.2856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10651 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 26114.0315 | 0.2 | 0.3 | 40737.8891 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10652 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16666.6171 | 0.2 | 0.3 | 25999.9227 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3356 | 5200.3356 | 5200.3356 | 5200.3356 | 5200.3356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10653 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 19626.5541 | 0.2 | 0.3 | 30617.4243 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6435.7217 | 6435.7217 | 6435.7217 | 6435.7217 | 6435.7217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10654 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16088.8238 | 0.2 | 0.3 | 25098.5651 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10655 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 21402.4981 | 0.2 | 0.3 | 33387.897 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7792.3262 | 7792.3262 | 7792.3262 | 7792.3262 | 7792.3262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10656 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 18025.7348 | 0.2 | 0.3 | 28120.1463 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9975 | 5199.9975 | 5199.9975 | 5199.9975 | 5199.9975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10657 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 33441.4155 | 0.2 | 0.3 | 52168.6082 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10658 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 39001.6664 | 0.2 | 0.3 | 60842.5996 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9759.2611 | 9759.2611 | 9759.2611 | 9759.2611 | 9759.2611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10659 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 10830.009 | 0.2 | 0.3 | 16894.814 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8483.9821 | 8483.9821 | 8483.9821 | 8483.9821 | 8483.9821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10660 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 21165.0287 | 0.2 | 0.3 | 33017.4448 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10661 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 9704.7113 | 0.2 | 0.3 | 15139.3496 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7735.9355 | 7735.9355 | 7735.9355 | 7735.9355 | 7735.9355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10662 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 11530.4737 | 0.2 | 0.3 | 17987.5389 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7355 | 5200.7355 | 5200.7355 | 5200.7355 | 5200.7355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10663 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 12960.614 | 0.2 | 0.3 | 20218.5578 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 932.6428 | 932.6428 | 932.6428 | 932.6428 | 932.6428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10664 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 20886.4139 | 0.2 | 0.3 | 32582.8057 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5253.0123 | 5253.0123 | 5253.0123 | 5253.0123 | 5253.0123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10665 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 4480.2365 | 0.2 | 0.3 | 6989.169 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9074.2506 | 9074.2506 | 9074.2506 | 9074.2506 | 9074.2506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10666 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6387 | 0.2 | 0.3 | 25999.9564 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9913 | 5199.9913 | 5199.9913 | 5199.9913 | 5199.9913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10667 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5880.8429 | 5880.8429 | 5880.8429 | 5880.8429 | 5880.8429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10668 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9160.7973 | 9160.7973 | 9160.7973 | 9160.7973 | 9160.7973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10669 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5760.9446 | 5760.9446 | 5760.9446 | 5760.9446 | 5760.9446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10670 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.018 | 5200.018 | 5200.018 | 5200.018 | 5200.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10671 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 31428.3831 | 0.2 | 0.3 | 49028.2777 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10672 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 20614.4758 | 0.2 | 0.3 | 32158.5822 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5862.7163 | 5862.7163 | 5862.7163 | 5862.7163 | 5862.7163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10673 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 9635.9731 | 0.2 | 0.3 | 15032.1181 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7858.1385 | 7858.1385 | 7858.1385 | 7858.1385 | 7858.1385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10674 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 11301.6163 | 0.2 | 0.3 | 17630.5214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4853.1004 | 4853.1004 | 4853.1004 | 4853.1004 | 4853.1004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10675 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 12218.4145 | 0.2 | 0.3 | 19060.7267 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0739 | 5200.0739 | 5200.0739 | 5200.0739 | 5200.0739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10676 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 28338.6759 | 0.2 | 0.3 | 44208.3345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10677 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1646 | 5200.1646 | 5200.1646 | 5200.1646 | 5200.1646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10678 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 25938.0566 | 0.2 | 0.3 | 40463.3683 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1983.2096 | 1983.2096 | 1983.2096 | 1983.2096 | 1983.2096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10679 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16791.4498 | 0.2 | 0.3 | 26194.6617 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8410.3189 | 8410.3189 | 8410.3189 | 8410.3189 | 8410.3189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10680 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 16683.4289 | 0.2 | 0.3 | 26026.149 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4802.6448 | 4802.6448 | 4802.6448 | 4802.6448 | 4802.6448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10681 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 17421.6189 | 0.2 | 0.3 | 27177.7254 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4006.9499 | 4006.9499 | 4006.9499 | 4006.9499 | 4006.9499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10682 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 17562.5199 | 0.2 | 0.3 | 27397.531 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2979.5073 | 2979.5073 | 2979.5073 | 2979.5073 | 2979.5073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10683 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 16919.2247 | 0.2 | 0.3 | 26393.9906 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.226 | 2600.226 | 2600.226 | 2600.226 | 2600.226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10684 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 645.9709 | 0.2 | 0.3 | 1007.7146 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10685 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 26133.7049 | 0.2 | 0.3 | 40768.5797 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1267.084 | 1267.084 | 1267.084 | 1267.084 | 1267.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10686 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16667.1653 | 0.2 | 0.3 | 26000.7778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2729.2222 | 2729.2222 | 2729.2222 | 2729.2222 | 2729.2222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10687 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 21428.9619 | 0.2 | 0.3 | 33429.1806 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3948 | 5200.3948 | 5200.3948 | 5200.3948 | 5200.3948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10688 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 21724.1099 | 0.2 | 0.3 | 33889.6114 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10689 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 7689.016 | 0.2 | 0.3 | 11994.865 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.56 | 5200.56 | 5200.56 | 5200.56 | 5200.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10690 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 15876.6092 | 0.2 | 0.3 | 24767.5104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6260.0406 | 6260.0406 | 6260.0406 | 6260.0406 | 6260.0406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10691 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 25022.3243 | 0.2 | 0.3 | 39034.8259 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6221.9231 | 6221.9231 | 6221.9231 | 6221.9231 | 6221.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10692 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 31562.6489 | 0.2 | 0.3 | 49237.7323 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3821.1436 | 3821.1436 | 3821.1436 | 3821.1436 | 3821.1436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10693 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 13921.5786 | 0.2 | 0.3 | 21717.6626 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5215.2822 | 5215.2822 | 5215.2822 | 5215.2822 | 5215.2822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10694 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 13481.1675 | 0.2 | 0.3 | 21030.6214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2564.3429 | 2564.3429 | 2564.3429 | 2564.3429 | 2564.3429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10695 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 16902.6603 | 0.2 | 0.3 | 26368.1501 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3778.6232 | 3778.6232 | 3778.6232 | 3778.6232 | 3778.6232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10696 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 16875.4071 | 0.2 | 0.3 | 26325.6351 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9834 | 5199.9834 | 5199.9834 | 5199.9834 | 5199.9834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10697 | DAVIE | 70304 | Public | 2036 | 5 | Swales | 66.6667 | 11125.8586 | 0.2 | 0.3 | 17356.3394 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10698 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 28845.3348 | 0.2 | 0.3 | 44998.7223 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6174.5225 | 6174.5225 | 6174.5225 | 6174.5225 | 6174.5225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10699 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 26540.2459 | 0.2 | 0.3 | 41402.7837 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10700 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 17785.3129 | 0.2 | 0.3 | 27745.0881 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3395.9261 | 3395.9261 | 3395.9261 | 3395.9261 | 3395.9261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10701 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 16016.7203 | 0.2 | 0.3 | 24986.0836 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 844.7601 | 844.7601 | 844.7601 | 844.7601 | 844.7601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10702 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 650.1149 | 0.2 | 0.3 | 1014.1793 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5306.0516 | 5306.0516 | 5306.0516 | 5306.0516 | 5306.0516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10703 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 25908.7453 | 0.2 | 0.3 | 40417.6427 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10704 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16666.6219 | 0.2 | 0.3 | 25999.9301 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.049 | 9776.049 | 9776.049 | 9776.049 | 9776.049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10705 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 7835.3396 | 0.2 | 0.3 | 12223.1298 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5633.8997 | 5633.8997 | 5633.8997 | 5633.8997 | 5633.8997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10706 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 20400.0605 | 0.2 | 0.3 | 31824.0943 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8865.1516 | 8865.1516 | 8865.1516 | 8865.1516 | 8865.1516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10707 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 23328.0141 | 0.2 | 0.3 | 36391.702 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10708 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 25289.2802 | 0.2 | 0.3 | 39451.2771 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0373 | 5200.0373 | 5200.0373 | 5200.0373 | 5200.0373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10709 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16843.1947 | 0.2 | 0.3 | 26275.3838 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5713.7504 | 5713.7504 | 5713.7504 | 5713.7504 | 5713.7504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10710 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 8555.8683 | 0.2 | 0.3 | 13347.1546 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5666.2379 | 5666.2379 | 5666.2379 | 5666.2379 | 5666.2379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10711 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 32214.229 | 0.2 | 0.3 | 50254.1972 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4595.0401 | 4595.0401 | 4595.0401 | 4595.0401 | 4595.0401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10712 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 17599.9079 | 0.2 | 0.3 | 27455.8563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3979 | 5200.3979 | 5200.3979 | 5200.3979 | 5200.3979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10713 | DAVIE | 70323 | Public | 2026 | 5 | Swales | 66.6667 | 22289.1164 | 0.2 | 0.3 | 34771.0216 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10714 | DAVIE | 70323 | Private | 2026 | 5 | Swales | 66.6667 | 20397.8496 | 0.2 | 0.3 | 31820.6454 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5274 | 5200.5274 | 5200.5274 | 5200.5274 | 5200.5274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10715 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 16666.4773 | 0.2 | 0.3 | 25999.7046 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6166.7551 | 6166.7551 | 6166.7551 | 6166.7551 | 6166.7551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10716 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 15287.1162 | 0.2 | 0.3 | 23847.9013 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8636.9309 | 8636.9309 | 8636.9309 | 8636.9309 | 8636.9309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10717 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 1379.7211 | 0.2 | 0.3 | 2152.365 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5222.0654 | 5222.0654 | 5222.0654 | 5222.0654 | 5222.0654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10718 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 30547.8537 | 0.2 | 0.3 | 47654.6518 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5211.6655 | 5211.6655 | 5211.6655 | 5211.6655 | 5211.6655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10719 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 25026.2305 | 0.2 | 0.3 | 39040.9196 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6646.6254 | 6646.6254 | 6646.6254 | 6646.6254 | 6646.6254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10720 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 18588.2965 | 0.2 | 0.3 | 28997.7426 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4445.4972 | 4445.4972 | 4445.4972 | 4445.4972 | 4445.4972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10721 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 20591.7926 | 0.2 | 0.3 | 32123.1965 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.987 | 5199.987 | 5199.987 | 5199.987 | 5199.987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10722 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 13201.1767 | 0.2 | 0.3 | 20593.8357 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10723 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 27429.037 | 0.2 | 0.3 | 42789.2977 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6632.7354 | 6632.7354 | 6632.7354 | 6632.7354 | 6632.7354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10724 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 9977.5619 | 0.2 | 0.3 | 15564.9966 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6520.2003 | 6520.2003 | 6520.2003 | 6520.2003 | 6520.2003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10725 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16805.8335 | 0.2 | 0.3 | 26217.1002 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8037.6407 | 8037.6407 | 8037.6407 | 8037.6407 | 8037.6407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10726 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10727 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 25059.3033 | 0.2 | 0.3 | 39092.5132 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9832.1285 | 9832.1285 | 9832.1285 | 9832.1285 | 9832.1285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10728 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 9041.2064 | 0.2 | 0.3 | 14104.282 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9208 | 5199.9208 | 5199.9208 | 5199.9208 | 5199.9208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10729 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16728.2978 | 0.2 | 0.3 | 26096.1446 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10730 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16712.153 | 0.2 | 0.3 | 26070.9587 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10731 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 17238.2438 | 0.2 | 0.3 | 26891.6603 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9775.9872 | 9775.9872 | 9775.9872 | 9775.9872 | 9775.9872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10732 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 20021.0143 | 0.2 | 0.3 | 31232.7824 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0543 | 5200.0543 | 5200.0543 | 5200.0543 | 5200.0543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10733 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 18065.5176 | 0.2 | 0.3 | 28182.2075 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7013.5772 | 7013.5772 | 7013.5772 | 7013.5772 | 7013.5772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10734 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 16711.8469 | 0.2 | 0.3 | 26070.4812 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8696.9256 | 8696.9256 | 8696.9256 | 8696.9256 | 8696.9256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10735 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 16666.4762 | 0.2 | 0.3 | 25999.7029 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10736 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 13068.3846 | 0.2 | 0.3 | 20386.68 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3189 | 5200.3189 | 5200.3189 | 5200.3189 | 5200.3189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10737 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 3598.5513 | 0.2 | 0.3 | 5613.7401 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5289.2538 | 5289.2538 | 5289.2538 | 5289.2538 | 5289.2538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10738 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 21339.9798 | 0.2 | 0.3 | 33290.3685 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2482 | 5200.2482 | 5200.2482 | 5200.2482 | 5200.2482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10739 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 8333.5021 | 0.2 | 0.3 | 13000.2632 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6122.3867 | 6122.3867 | 6122.3867 | 6122.3867 | 6122.3867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10740 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 18179.9969 | 0.2 | 0.3 | 28360.7952 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2214 | 5200.2214 | 5200.2214 | 5200.2214 | 5200.2214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10741 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16666.8385 | 0.2 | 0.3 | 26000.268 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10742 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 25000.2051 | 0.2 | 0.3 | 39000.32 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1976 | 5200.1976 | 5200.1976 | 5200.1976 | 5200.1976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10743 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 25000.6023 | 0.2 | 0.3 | 39000.9395 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6438.267 | 6438.267 | 6438.267 | 6438.267 | 6438.267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10744 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 18398.3627 | 0.2 | 0.3 | 28701.4458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9997 | 5199.9997 | 5199.9997 | 5199.9997 | 5199.9997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10745 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10746 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0159 | 5200.0159 | 5200.0159 | 5200.0159 | 5200.0159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10747 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 24967.7023 | 0.2 | 0.3 | 38949.6156 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6228.492 | 6228.492 | 6228.492 | 6228.492 | 6228.492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10748 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 21304.1859 | 0.2 | 0.3 | 33234.53 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6604.7313 | 6604.7313 | 6604.7313 | 6604.7313 | 6604.7313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10749 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16809.0131 | 0.2 | 0.3 | 26222.0604 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2855.5766 | 2855.5766 | 2855.5766 | 2855.5766 | 2855.5766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10750 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16712.1597 | 0.2 | 0.3 | 26070.9691 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 809.6092 | 809.6092 | 809.6092 | 809.6092 | 809.6092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10751 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 27100.0484 | 0.2 | 0.3 | 42276.0755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5377.798 | 5377.798 | 5377.798 | 5377.798 | 5377.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10752 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 36741.0536 | 0.2 | 0.3 | 57316.0436 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7097.7944 | 7097.7944 | 7097.7944 | 7097.7944 | 7097.7944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10753 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 15433.1123 | 0.2 | 0.3 | 24075.6551 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0675 | 5200.0675 | 5200.0675 | 5200.0675 | 5200.0675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10754 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 10231.1342 | 0.2 | 0.3 | 15960.5694 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10755 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 18853.6995 | 0.2 | 0.3 | 29411.7713 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7443.5497 | 7443.5497 | 7443.5497 | 7443.5497 | 7443.5497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10756 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 8525.9737 | 0.2 | 0.3 | 13300.519 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5781.0242 | 5781.0242 | 5781.0242 | 5781.0242 | 5781.0242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10757 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 20021.9958 | 0.2 | 0.3 | 31234.3134 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9051.6765 | 9051.6765 | 9051.6765 | 9051.6765 | 9051.6765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10758 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 19668.4709 | 0.2 | 0.3 | 30682.8147 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10759 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 596.0447 | 0.2 | 0.3 | 929.8297 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9863.5899 | 9863.5899 | 9863.5899 | 9863.5899 | 9863.5899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10760 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16667.3707 | 0.2 | 0.3 | 26001.0982 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9939 | 5199.9939 | 5199.9939 | 5199.9939 | 5199.9939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10761 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16666.7496 | 0.2 | 0.3 | 26000.1294 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10762 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 25000.3893 | 0.2 | 0.3 | 39000.6073 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10763 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 25000.4707 | 0.2 | 0.3 | 39000.7343 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.0011 | 9776.0011 | 9776.0011 | 9776.0011 | 9776.0011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10764 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16666.7137 | 0.2 | 0.3 | 26000.0734 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0538 | 5200.0538 | 5200.0538 | 5200.0538 | 5200.0538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10765 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 33586.3275 | 0.2 | 0.3 | 52394.6708 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8089.8604 | 8089.8604 | 8089.8604 | 8089.8604 | 8089.8604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10766 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 26468.2001 | 0.2 | 0.3 | 41290.3922 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8025 | 5200.8025 | 5200.8025 | 5200.8025 | 5200.8025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10767 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 31058.3247 | 0.2 | 0.3 | 48450.9865 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0086 | 5201.0086 | 5201.0086 | 5201.0086 | 5201.0086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10768 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 17292.4589 | 0.2 | 0.3 | 26976.2358 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10769 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 3087.4643 | 0.2 | 0.3 | 4816.4444 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7150.1816 | 7150.1816 | 7150.1816 | 7150.1816 | 7150.1816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10770 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 855.9223 | 0.2 | 0.3 | 1335.2388 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2923 | 5200.2923 | 5200.2923 | 5200.2923 | 5200.2923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10771 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 7778.8221 | 0.2 | 0.3 | 12134.9625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10772 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 593.2377 | 0.2 | 0.3 | 925.4509 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5199 | 5200.5199 | 5200.5199 | 5200.5199 | 5200.5199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10773 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 5945.3507 | 0.2 | 0.3 | 9274.747 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7062.1692 | 7062.1692 | 7062.1692 | 7062.1692 | 7062.1692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10774 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 16669.8831 | 0.2 | 0.3 | 26005.0177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7424.9545 | 7424.9545 | 7424.9545 | 7424.9545 | 7424.9545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10775 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 16668.3035 | 0.2 | 0.3 | 26002.5534 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6671.0274 | 6671.0274 | 6671.0274 | 6671.0274 | 6671.0274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10776 | DAVIE | 70205 | Private | 2036 | 5 | Swales | 66.6667 | 7239.7611 | 0.2 | 0.3 | 11294.0273 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11700.0433 | 11700.0433 | 11700.0433 | 11700.0433 | 11700.0433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10777 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 48092.1515 | 0.2 | 0.3 | 75023.7563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7810.1774 | 7810.1774 | 7810.1774 | 7810.1774 | 7810.1774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10778 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 44757.6442 | 0.2 | 0.3 | 69821.925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11633.4184 | 11633.4184 | 11633.4184 | 11633.4184 | 11633.4184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10779 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 33103.1671 | 0.2 | 0.3 | 51640.9406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8862.1641 | 8862.1641 | 8862.1641 | 8862.1641 | 8862.1641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10780 | DAVIE | 70213 | Public | 2036 | 5 | Swales | 66.6667 | 15111.3827 | 0.2 | 0.3 | 23573.757 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5424.7798 | 5424.7798 | 5424.7798 | 5424.7798 | 5424.7798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10781 | DAVIE | 70213 | Public | 2036 | 5 | Swales | 66.6667 | 12788.5998 | 0.2 | 0.3 | 19950.2157 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0011 | 5200.0011 | 5200.0011 | 5200.0011 | 5200.0011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10782 | DAVIE | 70213 | Public | 2036 | 5 | Swales | 66.6667 | 20507.0392 | 0.2 | 0.3 | 31990.9812 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8518 | 5200.8518 | 5200.8518 | 5200.8518 | 5200.8518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10783 | DAVIE | 70213 | Public | 2036 | 5 | Swales | 66.6667 | 24072.1445 | 0.2 | 0.3 | 37552.5455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6177.8884 | 6177.8884 | 6177.8884 | 6177.8884 | 6177.8884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10784 | DAVIE | 70213 | Public | 2036 | 5 | Swales | 66.6667 | 5801.3825 | 0.2 | 0.3 | 9050.1566 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9791.2452 | 9791.2452 | 9791.2452 | 9791.2452 | 9791.2452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10785 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.8086 | 0.2 | 0.3 | 26000.2214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3756.6884 | 3756.6884 | 3756.6884 | 3756.6884 | 3756.6884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10786 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9409.3253 | 9409.3253 | 9409.3253 | 9409.3253 | 9409.3253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10787 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 15404.4476 | 0.2 | 0.3 | 24030.9383 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7132.1632 | 7132.1632 | 7132.1632 | 7132.1632 | 7132.1632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10788 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 26321.4263 | 0.2 | 0.3 | 41061.425 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4328.0537 | 4328.0537 | 4328.0537 | 4328.0537 | 4328.0537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10789 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 21229.0842 | 0.2 | 0.3 | 33117.3714 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9948 | 5199.9948 | 5199.9948 | 5199.9948 | 5199.9948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10790 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 25005.3681 | 0.2 | 0.3 | 39008.3742 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9894 | 5199.9894 | 5199.9894 | 5199.9894 | 5199.9894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10791 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 25003.6219 | 0.2 | 0.3 | 39005.6501 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8558.9942 | 8558.9942 | 8558.9942 | 8558.9942 | 8558.9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10792 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 31757.4653 | 0.2 | 0.3 | 49541.6458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5673.1017 | 5673.1017 | 5673.1017 | 5673.1017 | 5673.1017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10793 | DAVIE | 70213 | Public | 2036 | 5 | Swales | 66.6667 | 16674.8225 | 0.2 | 0.3 | 26012.7232 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4788.2601 | 4788.2601 | 4788.2601 | 4788.2601 | 4788.2601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10794 | DAVIE | 70213 | Public | 2036 | 5 | Swales | 66.6667 | 16678.4979 | 0.2 | 0.3 | 26018.4568 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10795 | DAVIE | 70213 | Public | 2036 | 5 | Swales | 66.6667 | 16680.2447 | 0.2 | 0.3 | 26021.1817 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9788.9537 | 9788.9537 | 9788.9537 | 9788.9537 | 9788.9537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10796 | DAVIE | 70213 | Public | 2036 | 5 | Swales | 66.6667 | 16680.8169 | 0.2 | 0.3 | 26022.0744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9955 | 5199.9955 | 5199.9955 | 5199.9955 | 5199.9955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10797 | DAVIE | 70213 | Public | 2036 | 5 | Swales | 66.6667 | 16881.296 | 0.2 | 0.3 | 26334.8218 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10798 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 29763.0992 | 0.2 | 0.3 | 46430.4348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10799 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 17276.287 | 0.2 | 0.3 | 26951.0077 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5855.6228 | 5855.6228 | 5855.6228 | 5855.6228 | 5855.6228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10800 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 4302.4799 | 0.2 | 0.3 | 6711.8686 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9799 | 5199.9799 | 5199.9799 | 5199.9799 | 5199.9799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10801 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 18731.5659 | 0.2 | 0.3 | 29221.2428 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3809.7081 | 3809.7081 | 3809.7081 | 3809.7081 | 3809.7081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10802 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.9109 | 0.2 | 0.3 | 26000.381 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 646.1904 | 646.1904 | 646.1904 | 646.1904 | 646.1904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10803 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1473 | 0.2 | 0.3 | 26000.7497 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10804 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16667.2473 | 0.2 | 0.3 | 26000.9057 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7150.8704 | 7150.8704 | 7150.8704 | 7150.8704 | 7150.8704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10805 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 15860.7723 | 0.2 | 0.3 | 24742.8047 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1793 | 5200.1793 | 5200.1793 | 5200.1793 | 5200.1793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10806 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 14684.2293 | 0.2 | 0.3 | 22907.3978 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10807 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 7692.2662 | 0.2 | 0.3 | 11999.9353 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2637 | 5200.2637 | 5200.2637 | 5200.2637 | 5200.2637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10808 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 14189.4809 | 0.2 | 0.3 | 22135.5902 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7146.5594 | 7146.5594 | 7146.5594 | 7146.5594 | 7146.5594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10809 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16667.3925 | 0.2 | 0.3 | 26001.1322 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10810 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 21688.5009 | 0.2 | 0.3 | 33834.0615 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7235.642 | 7235.642 | 7235.642 | 7235.642 | 7235.642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10811 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 20535.4691 | 0.2 | 0.3 | 32035.3318 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8914.2168 | 8914.2168 | 8914.2168 | 8914.2168 | 8914.2168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10812 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6255 | 0.2 | 0.3 | 25999.9357 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7790.2409 | 7790.2409 | 7790.2409 | 7790.2409 | 7790.2409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10813 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11159.8099 | 11159.8099 | 11159.8099 | 11159.8099 | 11159.8099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10814 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5263.2186 | 5263.2186 | 5263.2186 | 5263.2186 | 5263.2186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10815 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 16666.8403 | 0.2 | 0.3 | 26000.2708 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8663.6156 | 8663.6156 | 8663.6156 | 8663.6156 | 8663.6156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10816 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 26245.5816 | 0.2 | 0.3 | 40943.1073 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5375.9745 | 5375.9745 | 5375.9745 | 5375.9745 | 5375.9745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10817 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6557.4027 | 6557.4027 | 6557.4027 | 6557.4027 | 6557.4027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10818 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6386 | 0.2 | 0.3 | 25999.9562 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5214.5983 | 5214.5983 | 5214.5983 | 5214.5983 | 5214.5983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10819 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 8333.5734 | 0.2 | 0.3 | 13000.3745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4022.2643 | 4022.2643 | 4022.2643 | 4022.2643 | 4022.2643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10820 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 8333.5734 | 0.2 | 0.3 | 13000.3745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0629 | 5200.0629 | 5200.0629 | 5200.0629 | 5200.0629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10821 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 25015.5396 | 0.2 | 0.3 | 39024.2418 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0097 | 5200.0097 | 5200.0097 | 5200.0097 | 5200.0097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10822 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 24248.7047 | 0.2 | 0.3 | 37827.9794 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7584.4703 | 7584.4703 | 7584.4703 | 7584.4703 | 7584.4703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10823 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 16667.6479 | 0.2 | 0.3 | 26001.5308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5559.583 | 5559.583 | 5559.583 | 5559.583 | 5559.583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10824 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 17975.7813 | 0.2 | 0.3 | 28042.2189 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7227.2795 | 7227.2795 | 7227.2795 | 7227.2795 | 7227.2795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10825 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 28785.8051 | 0.2 | 0.3 | 44905.8559 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0213 | 5200.0213 | 5200.0213 | 5200.0213 | 5200.0213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10826 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 12606.2627 | 0.2 | 0.3 | 19665.7699 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10827 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 8332.3705 | 0.2 | 0.3 | 12998.4979 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10828 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 981.4523 | 0.2 | 0.3 | 1531.0656 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10829 | DAVIE | 70213 | Public | 2036 | 5 | Swales | 66.6667 | 16678.0754 | 0.2 | 0.3 | 26017.7976 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0223 | 5200.0223 | 5200.0223 | 5200.0223 | 5200.0223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10830 | DAVIE | 70213 | Public | 2036 | 5 | Swales | 66.6667 | 16679.5477 | 0.2 | 0.3 | 26020.0944 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6003.9319 | 6003.9319 | 6003.9319 | 6003.9319 | 6003.9319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10831 | DAVIE | 70213 | Public | 2036 | 5 | Swales | 66.6667 | 31769.6288 | 0.2 | 0.3 | 49560.6209 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 186.3751 | 186.3751 | 186.3751 | 186.3751 | 186.3751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10832 | DAVIE | 70213 | Public | 2036 | 5 | Swales | 66.6667 | 19507.6602 | 0.2 | 0.3 | 30431.9499 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1171 | 5200.1171 | 5200.1171 | 5200.1171 | 5200.1171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10833 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 38853.9019 | 0.2 | 0.3 | 60612.0869 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6988.1509 | 6988.1509 | 6988.1509 | 6988.1509 | 6988.1509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10834 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 33367.3753 | 0.2 | 0.3 | 52053.1054 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1255 | 5200.1255 | 5200.1255 | 5200.1255 | 5200.1255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10835 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 39289.4765 | 0.2 | 0.3 | 61291.5833 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10836 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 29608.3554 | 0.2 | 0.3 | 46189.0344 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1593 | 5200.1593 | 5200.1593 | 5200.1593 | 5200.1593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10837 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 37027.6776 | 0.2 | 0.3 | 57763.1771 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7863.1022 | 7863.1022 | 7863.1022 | 7863.1022 | 7863.1022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10838 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 21739.2308 | 0.2 | 0.3 | 33913.2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5635.7255 | 5635.7255 | 5635.7255 | 5635.7255 | 5635.7255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10839 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16116.3333 | 0.2 | 0.3 | 25141.4799 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6234.1119 | 6234.1119 | 6234.1119 | 6234.1119 | 6234.1119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10840 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 456.9641 | 0.2 | 0.3 | 712.864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4464.8686 | 4464.8686 | 4464.8686 | 4464.8686 | 4464.8686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10841 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16452.4416 | 0.2 | 0.3 | 25665.8089 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7210.1782 | 7210.1782 | 7210.1782 | 7210.1782 | 7210.1782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10842 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 2087.4323 | 0.2 | 0.3 | 3256.3944 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0069 | 5200.0069 | 5200.0069 | 5200.0069 | 5200.0069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10843 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7377 | 0.2 | 0.3 | 26000.1109 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9844 | 5199.9844 | 5199.9844 | 5199.9844 | 5199.9844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10844 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16668.5138 | 0.2 | 0.3 | 26002.8815 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5347.6789 | 5347.6789 | 5347.6789 | 5347.6789 | 5347.6789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10845 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16668.0736 | 0.2 | 0.3 | 26002.1948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5221.6595 | 5221.6595 | 5221.6595 | 5221.6595 | 5221.6595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10846 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3662.6256 | 3662.6256 | 3662.6256 | 3662.6256 | 3662.6256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10847 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9249.1836 | 9249.1836 | 9249.1836 | 9249.1836 | 9249.1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10848 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 8333.3 | 0.2 | 0.3 | 12999.948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6941.5496 | 6941.5496 | 6941.5496 | 6941.5496 | 6941.5496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10849 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 8333.5734 | 0.2 | 0.3 | 13000.3745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6624.3132 | 6624.3132 | 6624.3132 | 6624.3132 | 6624.3132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10850 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 5706.3968 | 0.2 | 0.3 | 8901.979 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7419.1587 | 7419.1587 | 7419.1587 | 7419.1587 | 7419.1587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10851 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 29463.909 | 0.2 | 0.3 | 45963.698 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9941 | 5199.9941 | 5199.9941 | 5199.9941 | 5199.9941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10852 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 16668.0638 | 0.2 | 0.3 | 26002.1795 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7432.3872 | 7432.3872 | 7432.3872 | 7432.3872 | 7432.3872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10853 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 29302.1483 | 0.2 | 0.3 | 45711.3513 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0484 | 5202.0484 | 5202.0484 | 5202.0484 | 5202.0484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10854 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 12960.9243 | 0.2 | 0.3 | 20219.042 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3971.0162 | 3971.0162 | 3971.0162 | 3971.0162 | 3971.0162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10855 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6034 | 0.2 | 0.3 | 25999.9013 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8622.0193 | 8622.0193 | 8622.0193 | 8622.0193 | 8622.0193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10856 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9190.5135 | 9190.5135 | 9190.5135 | 9190.5135 | 9190.5135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10857 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 14238.2034 | 0.2 | 0.3 | 22211.5973 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8405.5673 | 8405.5673 | 8405.5673 | 8405.5673 | 8405.5673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10858 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 3126.1911 | 0.2 | 0.3 | 4876.8581 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5431 | 5203.5431 | 5203.5431 | 5203.5431 | 5203.5431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10859 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 35135.2565 | 0.2 | 0.3 | 54811.0001 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0617 | 5200.0617 | 5200.0617 | 5200.0617 | 5200.0617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10860 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16526.6088 | 0.2 | 0.3 | 25781.5097 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5830.3461 | 5830.3461 | 5830.3461 | 5830.3461 | 5830.3461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10861 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16678.5943 | 0.2 | 0.3 | 26018.6071 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1668.255 | 1668.255 | 1668.255 | 1668.255 | 1668.255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10862 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16680.1095 | 0.2 | 0.3 | 26020.9708 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4118.0876 | 4118.0876 | 4118.0876 | 4118.0876 | 4118.0876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10863 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 14984.1691 | 0.2 | 0.3 | 23375.3037 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2851.877 | 2851.877 | 2851.877 | 2851.877 | 2851.877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10864 | DAVIE | 70213 | Public | 2036 | 5 | Swales | 66.6667 | 22487.4403 | 0.2 | 0.3 | 35080.4068 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0528 | 5202.0528 | 5202.0528 | 5202.0528 | 5202.0528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10865 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 26899.9456 | 0.2 | 0.3 | 41963.9151 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0644 | 5202.0644 | 5202.0644 | 5202.0644 | 5202.0644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10866 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16685.4647 | 0.2 | 0.3 | 26029.325 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5063 | 5201.5063 | 5201.5063 | 5201.5063 | 5201.5063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10867 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 33962.2181 | 0.2 | 0.3 | 52981.0603 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 344.7861 | 344.7861 | 344.7861 | 344.7861 | 344.7861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10868 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 28204.6237 | 0.2 | 0.3 | 43999.213 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1718.8297 | 1718.8297 | 1718.8297 | 1718.8297 | 1718.8297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10869 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 39016.7146 | 0.2 | 0.3 | 60866.0748 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1892 | 2600.1892 | 2600.1892 | 2600.1892 | 2600.1892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10870 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16683.2661 | 0.2 | 0.3 | 26025.8952 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.2455 | 2600.2455 | 2600.2455 | 2600.2455 | 2600.2455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10871 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 18334.3774 | 0.2 | 0.3 | 28601.6287 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3002.6941 | 3002.6941 | 3002.6941 | 3002.6941 | 3002.6941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10872 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 20000.4419 | 0.2 | 0.3 | 31200.6893 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4580.4027 | 4580.4027 | 4580.4027 | 4580.4027 | 4580.4027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10873 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 26791.974 | 0.2 | 0.3 | 41795.4794 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1045.2664 | 1045.2664 | 1045.2664 | 1045.2664 | 1045.2664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10874 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16982.3315 | 0.2 | 0.3 | 26492.4372 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6602.0498 | 6602.0498 | 6602.0498 | 6602.0498 | 6602.0498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10875 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8873 | 0.2 | 0.3 | 26000.3441 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3405.6558 | 3405.6558 | 3405.6558 | 3405.6558 | 3405.6558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10876 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8597 | 0.2 | 0.3 | 26000.3012 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4153 | 5200.4153 | 5200.4153 | 5200.4153 | 5200.4153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10877 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8027 | 0.2 | 0.3 | 26000.2122 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10878 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 31361.7756 | 0.2 | 0.3 | 48924.3699 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.353 | 5200.353 | 5200.353 | 5200.353 | 5200.353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10879 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16692.1427 | 0.2 | 0.3 | 26039.7427 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6735.656 | 6735.656 | 6735.656 | 6735.656 | 6735.656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10880 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16694.071 | 0.2 | 0.3 | 26042.7508 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3238.7159 | 3238.7159 | 3238.7159 | 3238.7159 | 3238.7159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10881 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 8333.642 | 0.2 | 0.3 | 13000.4815 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3368 | 5200.3368 | 5200.3368 | 5200.3368 | 5200.3368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10882 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 8333.5734 | 0.2 | 0.3 | 13000.3745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8623 | 5201.8623 | 5201.8623 | 5201.8623 | 5201.8623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10883 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 8333.5734 | 0.2 | 0.3 | 13000.3745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7802.5074 | 7802.5074 | 7802.5074 | 7802.5074 | 7802.5074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10884 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 8333.6259 | 0.2 | 0.3 | 13000.4565 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9522.4284 | 9522.4284 | 9522.4284 | 9522.4284 | 9522.4284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10885 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 22303.2903 | 0.2 | 0.3 | 34793.1328 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6731.4583 | 6731.4583 | 6731.4583 | 6731.4583 | 6731.4583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10886 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5223.4403 | 5223.4403 | 5223.4403 | 5223.4403 | 5223.4403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10887 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6058 | 0.2 | 0.3 | 25999.905 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1737 | 5202.1737 | 5202.1737 | 5202.1737 | 5202.1737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10888 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6157 | 0.2 | 0.3 | 25999.9204 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2261.0965 | 2261.0965 | 2261.0965 | 2261.0965 | 2261.0965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10889 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.5999 | 0.2 | 0.3 | 25999.8958 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7454.2226 | 7454.2226 | 7454.2226 | 7454.2226 | 7454.2226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10890 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 28161.8338 | 0.2 | 0.3 | 43932.4607 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7837.8966 | 7837.8966 | 7837.8966 | 7837.8966 | 7837.8966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10891 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5336.4838 | 5336.4838 | 5336.4838 | 5336.4838 | 5336.4838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10892 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.9401 | 0.2 | 0.3 | 26000.4266 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2634 | 5200.2634 | 5200.2634 | 5200.2634 | 5200.2634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10893 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 28969.4167 | 0.2 | 0.3 | 45192.29 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10894 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 29134.6993 | 0.2 | 0.3 | 45450.131 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4855.43 | 4855.43 | 4855.43 | 4855.43 | 4855.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10895 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16670.7623 | 0.2 | 0.3 | 26006.3891 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3481.4574 | 3481.4574 | 3481.4574 | 3481.4574 | 3481.4574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10896 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8358 | 0.2 | 0.3 | 26000.2638 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7424.5104 | 7424.5104 | 7424.5104 | 7424.5104 | 7424.5104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10897 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 32472.0427 | 0.2 | 0.3 | 50656.3866 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.2744 | 2600.2744 | 2600.2744 | 2600.2744 | 2600.2744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10898 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 25275.1406 | 0.2 | 0.3 | 39429.2193 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.2455 | 2600.2455 | 2600.2455 | 2600.2455 | 2600.2455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10899 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 22784.916 | 0.2 | 0.3 | 35544.469 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2602.2287 | 2602.2287 | 2602.2287 | 2602.2287 | 2602.2287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10900 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16678.2551 | 0.2 | 0.3 | 26018.078 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2361.5228 | 2361.5228 | 2361.5228 | 2361.5228 | 2361.5228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10901 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16678.2499 | 0.2 | 0.3 | 26018.0699 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5980.1518 | 5980.1518 | 5980.1518 | 5980.1518 | 5980.1518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10902 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 20852.9792 | 0.2 | 0.3 | 32530.6476 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6380.5808 | 6380.5808 | 6380.5808 | 6380.5808 | 6380.5808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10903 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 26057.0481 | 0.2 | 0.3 | 40648.9951 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4364 | 5202.4364 | 5202.4364 | 5202.4364 | 5202.4364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10904 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16683.8243 | 0.2 | 0.3 | 26026.766 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4480.3699 | 4480.3699 | 4480.3699 | 4480.3699 | 4480.3699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10905 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 33717.2682 | 0.2 | 0.3 | 52598.9384 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5288.853 | 5288.853 | 5288.853 | 5288.853 | 5288.853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10906 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 21850.2437 | 0.2 | 0.3 | 34086.3802 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7889.303 | 7889.303 | 7889.303 | 7889.303 | 7889.303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10907 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 28461.7603 | 0.2 | 0.3 | 44400.346 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2881 | 5200.2881 | 5200.2881 | 5200.2881 | 5200.2881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10908 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16682.4573 | 0.2 | 0.3 | 26024.6334 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10909 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.096 | 5200.096 | 5200.096 | 5200.096 | 5200.096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10910 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16680.5435 | 0.2 | 0.3 | 26021.6479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5094.9544 | 5094.9544 | 5094.9544 | 5094.9544 | 5094.9544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10911 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 13659.5149 | 0.2 | 0.3 | 21308.8433 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0592 | 5200.0592 | 5200.0592 | 5200.0592 | 5200.0592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10912 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 4424.0073 | 0.2 | 0.3 | 6901.4513 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10913 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8963 | 5199.8963 | 5199.8963 | 5199.8963 | 5199.8963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10914 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 7893.0106 | 0.2 | 0.3 | 12313.0965 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.4922 | 9776.4922 | 9776.4922 | 9776.4922 | 9776.4922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10915 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 12179.7193 | 0.2 | 0.3 | 19000.3622 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10916 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 12820.5465 | 0.2 | 0.3 | 20000.0526 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5226.6609 | 5226.6609 | 5226.6609 | 5226.6609 | 5226.6609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10917 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16666.5335 | 0.2 | 0.3 | 25999.7922 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2145.7187 | 2145.7187 | 2145.7187 | 2145.7187 | 2145.7187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10918 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 15123.4167 | 0.2 | 0.3 | 23592.5301 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5226.6474 | 5226.6474 | 5226.6474 | 5226.6474 | 5226.6474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10919 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 8333.4327 | 0.2 | 0.3 | 13000.1551 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1520.8067 | 1520.8067 | 1520.8067 | 1520.8067 | 1520.8067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10920 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 8333.5734 | 0.2 | 0.3 | 13000.3745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3681.5861 | 3681.5861 | 3681.5861 | 3681.5861 | 3681.5861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10921 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 8333.5734 | 0.2 | 0.3 | 13000.3745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5553.1869 | 5553.1869 | 5553.1869 | 5553.1869 | 5553.1869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10922 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 8333.626 | 0.2 | 0.3 | 13000.4566 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2244.8234 | 2244.8234 | 2244.8234 | 2244.8234 | 2244.8234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10923 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.3266 | 0.2 | 0.3 | 25999.4695 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9185 | 5199.9185 | 5199.9185 | 5199.9185 | 5199.9185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10924 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7471.9058 | 7471.9058 | 7471.9058 | 7471.9058 | 7471.9058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10925 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 3906.2836 | 0.2 | 0.3 | 6093.8024 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3052.3938 | 3052.3938 | 3052.3938 | 3052.3938 | 3052.3938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10926 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8171 | 0.2 | 0.3 | 26000.2347 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4857.9917 | 4857.9917 | 4857.9917 | 4857.9917 | 4857.9917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10927 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 23257.3314 | 0.2 | 0.3 | 36281.437 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5560.2176 | 5560.2176 | 5560.2176 | 5560.2176 | 5560.2176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10928 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 27327.7257 | 0.2 | 0.3 | 42631.252 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10929 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 22030.3123 | 0.2 | 0.3 | 34367.2872 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10930 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 21395.9174 | 0.2 | 0.3 | 33377.6311 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1012 | 5200.1012 | 5200.1012 | 5200.1012 | 5200.1012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10931 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16671.4515 | 0.2 | 0.3 | 26007.4643 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.1612 | 9776.1612 | 9776.1612 | 9776.1612 | 9776.1612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10932 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 25503.9569 | 0.2 | 0.3 | 39786.1728 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2609 | 5200.2609 | 5200.2609 | 5200.2609 | 5200.2609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10933 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 45485.899 | 0.2 | 0.3 | 70958.0024 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10934 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 33374.8827 | 0.2 | 0.3 | 52064.8171 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4796.1192 | 4796.1192 | 4796.1192 | 4796.1192 | 4796.1192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10935 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 41694.5614 | 0.2 | 0.3 | 65043.5158 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3458.8298 | 3458.8298 | 3458.8298 | 3458.8298 | 3458.8298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10936 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16681.9455 | 0.2 | 0.3 | 26023.835 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5911.6271 | 5911.6271 | 5911.6271 | 5911.6271 | 5911.6271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10937 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16678.0108 | 0.2 | 0.3 | 26017.6968 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3421.7421 | 3421.7421 | 3421.7421 | 3421.7421 | 3421.7421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10938 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16678.4374 | 0.2 | 0.3 | 26018.3623 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9963 | 5199.9963 | 5199.9963 | 5199.9963 | 5199.9963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10939 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 3218.1876 | 0.2 | 0.3 | 5020.3727 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.968 | 5199.968 | 5199.968 | 5199.968 | 5199.968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10940 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 2967.4078 | 0.2 | 0.3 | 4629.1562 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4357.4038 | 4357.4038 | 4357.4038 | 4357.4038 | 4357.4038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10941 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 20665.1148 | 0.2 | 0.3 | 32237.5791 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4393.1508 | 4393.1508 | 4393.1508 | 4393.1508 | 4393.1508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10942 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 1533.2017 | 0.2 | 0.3 | 2391.7946 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2544 | 5200.2544 | 5200.2544 | 5200.2544 | 5200.2544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10943 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 9965.5395 | 0.2 | 0.3 | 15546.2417 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10944 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16673.9663 | 0.2 | 0.3 | 26011.3874 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0038 | 5200.0038 | 5200.0038 | 5200.0038 | 5200.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10945 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.8768 | 9776.8768 | 9776.8768 | 9776.8768 | 9776.8768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10946 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8088.7203 | 8088.7203 | 8088.7203 | 8088.7203 | 8088.7203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10947 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2868.2544 | 2868.2544 | 2868.2544 | 2868.2544 | 2868.2544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10948 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6163 | 0.2 | 0.3 | 25999.9215 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5240.4726 | 5240.4726 | 5240.4726 | 5240.4726 | 5240.4726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10949 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16095.383 | 0.2 | 0.3 | 25108.7975 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2765.8566 | 2765.8566 | 2765.8566 | 2765.8566 | 2765.8566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10950 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 18192.6251 | 0.2 | 0.3 | 28380.4951 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4037.5382 | 4037.5382 | 4037.5382 | 4037.5382 | 4037.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10951 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 17007.7776 | 0.2 | 0.3 | 26532.1331 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8994.0742 | 8994.0742 | 8994.0742 | 8994.0742 | 8994.0742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10952 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 16973.5859 | 0.2 | 0.3 | 26478.7941 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3807.4727 | 3807.4727 | 3807.4727 | 3807.4727 | 3807.4727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10953 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 13423.5629 | 0.2 | 0.3 | 20940.7581 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10954 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16875.9261 | 0.2 | 0.3 | 26326.4447 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5879.8336 | 5879.8336 | 5879.8336 | 5879.8336 | 5879.8336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10955 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16667.1008 | 0.2 | 0.3 | 26000.6772 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6412.3693 | 6412.3693 | 6412.3693 | 6412.3693 | 6412.3693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10956 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 12760.2727 | 0.2 | 0.3 | 19906.0254 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4184.2243 | 4184.2243 | 4184.2243 | 4184.2243 | 4184.2243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10957 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 19868.6701 | 0.2 | 0.3 | 30995.1254 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0095 | 5200.0095 | 5200.0095 | 5200.0095 | 5200.0095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10958 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 21332.1345 | 0.2 | 0.3 | 33278.1298 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10959 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 29866.4225 | 0.2 | 0.3 | 46591.619 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5451.4075 | 5451.4075 | 5451.4075 | 5451.4075 | 5451.4075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10960 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 10738.0071 | 0.2 | 0.3 | 16751.2911 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5678.0946 | 5678.0946 | 5678.0946 | 5678.0946 | 5678.0946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10961 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16683.715 | 0.2 | 0.3 | 26026.5954 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1148.9609 | 1148.9609 | 1148.9609 | 1148.9609 | 1148.9609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10962 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16676.7067 | 0.2 | 0.3 | 26015.6624 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5754.1876 | 5754.1876 | 5754.1876 | 5754.1876 | 5754.1876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10963 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 9405.4821 | 0.2 | 0.3 | 14672.552 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2787 | 5201.2787 | 5201.2787 | 5201.2787 | 5201.2787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10964 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 25211.2664 | 0.2 | 0.3 | 39329.5756 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6521.4928 | 6521.4928 | 6521.4928 | 6521.4928 | 6521.4928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10965 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 24547.9761 | 0.2 | 0.3 | 38294.8428 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4407.3593 | 4407.3593 | 4407.3593 | 4407.3593 | 4407.3593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10966 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 31914.3605 | 0.2 | 0.3 | 49786.4024 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6170.0572 | 6170.0572 | 6170.0572 | 6170.0572 | 6170.0572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10967 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 31351.5901 | 0.2 | 0.3 | 48908.4805 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5435.7066 | 5435.7066 | 5435.7066 | 5435.7066 | 5435.7066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10968 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 31361.4113 | 0.2 | 0.3 | 48923.8016 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8773.7136 | 8773.7136 | 8773.7136 | 8773.7136 | 8773.7136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10969 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 31378.1705 | 0.2 | 0.3 | 48949.946 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5912.0885 | 5912.0885 | 5912.0885 | 5912.0885 | 5912.0885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10970 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 24232.5039 | 0.2 | 0.3 | 37802.7061 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3917 | 5200.3917 | 5200.3917 | 5200.3917 | 5200.3917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10971 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 24058.8977 | 0.2 | 0.3 | 37531.8805 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7657.7782 | 7657.7782 | 7657.7782 | 7657.7782 | 7657.7782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10972 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 36895.9603 | 0.2 | 0.3 | 57557.698 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2703.4973 | 2703.4973 | 2703.4973 | 2703.4973 | 2703.4973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10973 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 27013.1693 | 0.2 | 0.3 | 42140.5442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.6913 | 5206.6913 | 5206.6913 | 5206.6913 | 5206.6913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10974 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 28164.2977 | 0.2 | 0.3 | 43936.3045 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5213.8202 | 5213.8202 | 5213.8202 | 5213.8202 | 5213.8202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10975 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 17544.9865 | 0.2 | 0.3 | 27370.179 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5211.3799 | 5211.3799 | 5211.3799 | 5211.3799 | 5211.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10976 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 16741.2203 | 0.2 | 0.3 | 26116.3036 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11326.6643 | 11326.6643 | 11326.6643 | 11326.6643 | 11326.6643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10977 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 16759.7649 | 0.2 | 0.3 | 26145.2332 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8225.8236 | 8225.8236 | 8225.8236 | 8225.8236 | 8225.8236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10978 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 8728.5139 | 0.2 | 0.3 | 13616.4817 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6466.6079 | 6466.6079 | 6466.6079 | 6466.6079 | 6466.6079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10979 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.5535 | 0.2 | 0.3 | 25999.8235 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11312.6106 | 11312.6106 | 11312.6106 | 11312.6106 | 11312.6106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10980 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11384.3103 | 11384.3103 | 11384.3103 | 11384.3103 | 11384.3103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10981 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 16844.8813 | 0.2 | 0.3 | 26278.0148 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10855.9803 | 10855.9803 | 10855.9803 | 10855.9803 | 10855.9803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10982 | DAVIE | 70323 | Public | 2030 | 5 | Swales | 66.6667 | 30290.9448 | 0.2 | 0.3 | 47253.8739 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11324.3717 | 11324.3717 | 11324.3717 | 11324.3717 | 11324.3717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10983 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 25128.5696 | 0.2 | 0.3 | 39200.5686 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14050.4417 | 14050.4417 | 14050.4417 | 14050.4417 | 14050.4417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10984 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6051 | 0.2 | 0.3 | 25999.9039 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 213.0955 | 213.0955 | 213.0955 | 213.0955 | 213.0955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10985 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6553.9837 | 6553.9837 | 6553.9837 | 6553.9837 | 6553.9837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10986 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 26560.0287 | 0.2 | 0.3 | 41433.6448 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7877.6466 | 7877.6466 | 7877.6466 | 7877.6466 | 7877.6466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10987 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 8250.5493 | 0.2 | 0.3 | 12870.8569 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 125.3441 | 125.3441 | 125.3441 | 125.3441 | 125.3441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10988 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 8417.1303 | 0.2 | 0.3 | 13130.7232 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5636.0645 | 5636.0645 | 5636.0645 | 5636.0645 | 5636.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10989 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 8333.1676 | 0.2 | 0.3 | 12999.7415 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.763 | 5201.763 | 5201.763 | 5201.763 | 5201.763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10990 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 8333.3623 | 0.2 | 0.3 | 13000.0451 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6881.481 | 6881.481 | 6881.481 | 6881.481 | 6881.481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10991 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 39412.9247 | 0.2 | 0.3 | 61484.1625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 564.1485 | 564.1485 | 564.1485 | 564.1485 | 564.1485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10992 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 23012.1378 | 0.2 | 0.3 | 35898.935 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4863.7998 | 4863.7998 | 4863.7998 | 4863.7998 | 4863.7998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10993 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16684.4026 | 0.2 | 0.3 | 26027.6681 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5514.3859 | 5514.3859 | 5514.3859 | 5514.3859 | 5514.3859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10994 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 31369.2835 | 0.2 | 0.3 | 48936.0822 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6444.9956 | 6444.9956 | 6444.9956 | 6444.9956 | 6444.9956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10995 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16681.793 | 0.2 | 0.3 | 26023.5971 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9845.4045 | 9845.4045 | 9845.4045 | 9845.4045 | 9845.4045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10996 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 29718.6534 | 0.2 | 0.3 | 46361.0993 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.981 | 5199.981 | 5199.981 | 5199.981 | 5199.981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10997 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16683.3877 | 0.2 | 0.3 | 26026.0848 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5491.087 | 5491.087 | 5491.087 | 5491.087 | 5491.087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10998 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16683.2574 | 0.2 | 0.3 | 26025.8815 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4486.2064 | 4486.2064 | 4486.2064 | 4486.2064 | 4486.2064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10999 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16685.2525 | 0.2 | 0.3 | 26028.9938 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5419.7406 | 5419.7406 | 5419.7406 | 5419.7406 | 5419.7406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11000 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 6056.2797 | 0.2 | 0.3 | 9447.7964 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1894.0174 | 1894.0174 | 1894.0174 | 1894.0174 | 1894.0174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11001 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 7812.5444 | 0.2 | 0.3 | 12187.5693 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4323.4285 | 4323.4285 | 4323.4285 | 4323.4285 | 4323.4285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11002 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 29001.8511 | 0.2 | 0.3 | 45242.8878 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5288.495 | 5288.495 | 5288.495 | 5288.495 | 5288.495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11003 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 13106.9497 | 0.2 | 0.3 | 20446.8416 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8673.9551 | 8673.9551 | 8673.9551 | 8673.9551 | 8673.9551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11004 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 14651.3521 | 0.2 | 0.3 | 22856.1093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9540.4806 | 9540.4806 | 9540.4806 | 9540.4806 | 9540.4806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11005 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16167.4521 | 0.2 | 0.3 | 25221.2252 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9768.6936 | 9768.6936 | 9768.6936 | 9768.6936 | 9768.6936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11006 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16666.9782 | 0.2 | 0.3 | 26000.486 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 622.4489 | 622.4489 | 622.4489 | 622.4489 | 622.4489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11007 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 17339.8203 | 0.2 | 0.3 | 27050.1196 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10278.3419 | 10278.3419 | 10278.3419 | 10278.3419 | 10278.3419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11008 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 27332.7159 | 0.2 | 0.3 | 42639.0369 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6316.0752 | 6316.0752 | 6316.0752 | 6316.0752 | 6316.0752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11009 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 7954.6107 | 0.2 | 0.3 | 12409.1927 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 109.2642 | 109.2642 | 109.2642 | 109.2642 | 109.2642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11010 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 8712.4871 | 0.2 | 0.3 | 13591.4798 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.0509 | 5203.0509 | 5203.0509 | 5203.0509 | 5203.0509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11011 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 8333.4751 | 0.2 | 0.3 | 13000.2212 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 340.3418 | 340.3418 | 340.3418 | 340.3418 | 340.3418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11012 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 8334.1201 | 0.2 | 0.3 | 13001.2273 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1817.4769 | 1817.4769 | 1817.4769 | 1817.4769 | 1817.4769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11013 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 22415.7471 | 0.2 | 0.3 | 34968.5655 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8105.0941 | 8105.0941 | 8105.0941 | 8105.0941 | 8105.0941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11014 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 23833.3535 | 0.2 | 0.3 | 37180.0314 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11015 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 41805.6243 | 0.2 | 0.3 | 65216.7739 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9191.5051 | 9191.5051 | 9191.5051 | 9191.5051 | 9191.5051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11016 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 33613.7453 | 0.2 | 0.3 | 52437.4426 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5626.0351 | 5626.0351 | 5626.0351 | 5626.0351 | 5626.0351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11017 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 45263.8703 | 0.2 | 0.3 | 70611.6376 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11018 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16683.5509 | 0.2 | 0.3 | 26026.3395 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9825.8423 | 9825.8423 | 9825.8423 | 9825.8423 | 9825.8423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11019 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16683.0041 | 0.2 | 0.3 | 26025.4864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1049 | 5200.1049 | 5200.1049 | 5200.1049 | 5200.1049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11020 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16684.9179 | 0.2 | 0.3 | 26028.472 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7381.9723 | 7381.9723 | 7381.9723 | 7381.9723 | 7381.9723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11021 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 26652.2724 | 0.2 | 0.3 | 41577.5449 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9065.8435 | 9065.8435 | 9065.8435 | 9065.8435 | 9065.8435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11022 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 3560.0369 | 0.2 | 0.3 | 5553.6576 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3080.4352 | 3080.4352 | 3080.4352 | 3080.4352 | 3080.4352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11023 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 2015.7947 | 0.2 | 0.3 | 3144.6397 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6169.9706 | 6169.9706 | 6169.9706 | 6169.9706 | 6169.9706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11024 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 499.5205 | 0.2 | 0.3 | 779.252 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3095.7712 | 3095.7712 | 3095.7712 | 3095.7712 | 3095.7712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11025 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 17264.5749 | 0.2 | 0.3 | 26932.7368 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6879.8155 | 6879.8155 | 6879.8155 | 6879.8155 | 6879.8155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11026 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 17265.2229 | 0.2 | 0.3 | 26933.7477 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10550.2054 | 10550.2054 | 10550.2054 | 10550.2054 | 10550.2054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11027 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 8333.5129 | 0.2 | 0.3 | 13000.2801 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8609.3962 | 8609.3962 | 8609.3962 | 8609.3962 | 8609.3962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11028 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 8333.3601 | 0.2 | 0.3 | 13000.0418 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4737.7412 | 4737.7412 | 4737.7412 | 4737.7412 | 4737.7412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11029 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 8332.7532 | 0.2 | 0.3 | 12999.095 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6056.8675 | 6056.8675 | 6056.8675 | 6056.8675 | 6056.8675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11030 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 8333.3 | 0.2 | 0.3 | 12999.948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3983.8096 | 3983.8096 | 3983.8096 | 3983.8096 | 3983.8096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11031 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 17823.2165 | 0.2 | 0.3 | 27804.2177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3801.0006 | 3801.0006 | 3801.0006 | 3801.0006 | 3801.0006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11032 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 33235.0627 | 0.2 | 0.3 | 51846.6979 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3647.7443 | 3647.7443 | 3647.7443 | 3647.7443 | 3647.7443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11033 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 34940.8066 | 0.2 | 0.3 | 54507.6583 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5231.9524 | 5231.9524 | 5231.9524 | 5231.9524 | 5231.9524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11034 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16683.9277 | 0.2 | 0.3 | 26026.9273 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7543.9638 | 7543.9638 | 7543.9638 | 7543.9638 | 7543.9638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11035 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 33129.0571 | 0.2 | 0.3 | 51681.329 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2610.3175 | 2610.3175 | 2610.3175 | 2610.3175 | 2610.3175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11036 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 10697.0083 | 0.2 | 0.3 | 16687.333 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9763.8199 | 9763.8199 | 9763.8199 | 9763.8199 | 9763.8199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11037 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 36702.6049 | 0.2 | 0.3 | 57256.0636 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11038 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 26855.0568 | 0.2 | 0.3 | 41893.8886 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9279.2653 | 9279.2653 | 9279.2653 | 9279.2653 | 9279.2653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11039 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 463.9817 | 0.2 | 0.3 | 723.8114 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3223.4662 | 3223.4662 | 3223.4662 | 3223.4662 | 3223.4662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11040 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 11937.2415 | 0.2 | 0.3 | 18622.0968 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9902 | 5199.9902 | 5199.9902 | 5199.9902 | 5199.9902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11041 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 27493.5364 | 0.2 | 0.3 | 42889.9168 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9785.0664 | 9785.0664 | 9785.0664 | 9785.0664 | 9785.0664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11042 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 24189.9393 | 0.2 | 0.3 | 37736.3054 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5515 | 5200.5515 | 5200.5515 | 5200.5515 | 5200.5515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11043 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 24547.1603 | 0.2 | 0.3 | 38293.57 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5226.0617 | 5226.0617 | 5226.0617 | 5226.0617 | 5226.0617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11044 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 17012.9422 | 0.2 | 0.3 | 26540.1898 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2719.8977 | 2719.8977 | 2719.8977 | 2719.8977 | 2719.8977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11045 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 16984.2444 | 0.2 | 0.3 | 26495.4213 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4833.4913 | 4833.4913 | 4833.4913 | 4833.4913 | 4833.4913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11046 | DAVIE | 70323 | Private | 2030 | 5 | Swales | 66.6667 | 19222.4136 | 0.2 | 0.3 | 29986.9652 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4078.1292 | 4078.1292 | 4078.1292 | 4078.1292 | 4078.1292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11047 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 8333.3173 | 0.2 | 0.3 | 12999.975 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3561.5125 | 3561.5125 | 3561.5125 | 3561.5125 | 3561.5125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11048 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 8333.3179 | 0.2 | 0.3 | 12999.9759 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4839.3933 | 4839.3933 | 4839.3933 | 4839.3933 | 4839.3933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11049 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 8333.3282 | 0.2 | 0.3 | 12999.992 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9505.1285 | 9505.1285 | 9505.1285 | 9505.1285 | 9505.1285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11050 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 8333.3215 | 0.2 | 0.3 | 12999.9816 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10479.3002 | 10479.3002 | 10479.3002 | 10479.3002 | 10479.3002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11051 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 16826.176 | 0.2 | 0.3 | 26248.8346 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11696.1868 | 11696.1868 | 11696.1868 | 11696.1868 | 11696.1868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11052 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 15124.5091 | 0.2 | 0.3 | 23594.2341 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11659.8005 | 11659.8005 | 11659.8005 | 11659.8005 | 11659.8005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11053 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 19115.7255 | 0.2 | 0.3 | 29820.5317 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12935.4477 | 12935.4477 | 12935.4477 | 12935.4477 | 12935.4477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11054 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 31598.3136 | 0.2 | 0.3 | 49293.3692 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2635.9416 | 2635.9416 | 2635.9416 | 2635.9416 | 2635.9416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11055 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 26858.9532 | 0.2 | 0.3 | 41899.967 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9984.4409 | 9984.4409 | 9984.4409 | 9984.4409 | 9984.4409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11056 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 32641.2976 | 0.2 | 0.3 | 50920.4243 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9412.4302 | 9412.4302 | 9412.4302 | 9412.4302 | 9412.4302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11057 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 28814.6994 | 0.2 | 0.3 | 44950.9311 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1254.7403 | 1254.7403 | 1254.7403 | 1254.7403 | 1254.7403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11058 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 36503.2064 | 0.2 | 0.3 | 56945.002 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7301.2302 | 7301.2302 | 7301.2302 | 7301.2302 | 7301.2302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11059 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 12004.1571 | 0.2 | 0.3 | 18726.485 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5233.7344 | 5233.7344 | 5233.7344 | 5233.7344 | 5233.7344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11060 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 29010.3413 | 0.2 | 0.3 | 45256.1324 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5266.2394 | 5266.2394 | 5266.2394 | 5266.2394 | 5266.2394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11061 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16685.1079 | 0.2 | 0.3 | 26028.7683 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5271.7461 | 5271.7461 | 5271.7461 | 5271.7461 | 5271.7461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11062 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 33625.2574 | 0.2 | 0.3 | 52455.4015 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11063 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 13651.8739 | 0.2 | 0.3 | 21296.9233 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.8093 | 9778.8093 | 9778.8093 | 9778.8093 | 9778.8093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11064 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 29102.0851 | 0.2 | 0.3 | 45399.2527 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.009 | 5200.009 | 5200.009 | 5200.009 | 5200.009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11065 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 22112.8569 | 0.2 | 0.3 | 34496.0568 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5290.2942 | 5290.2942 | 5290.2942 | 5290.2942 | 5290.2942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11066 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 27013.7012 | 0.2 | 0.3 | 42141.3739 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3549.6341 | 3549.6341 | 3549.6341 | 3549.6341 | 3549.6341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11067 | DAVIE | 70306 | Public | 2033 | 5 | Swales | 66.6667 | 16666.874 | 0.2 | 0.3 | 26000.3234 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6805.6889 | 6805.6889 | 6805.6889 | 6805.6889 | 6805.6889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11068 | DAVIE | 70306 | Public | 2033 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6768.5034 | 6768.5034 | 6768.5034 | 6768.5034 | 6768.5034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11069 | DAVIE | 70306 | Public | 2033 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4174.9248 | 4174.9248 | 4174.9248 | 4174.9248 | 4174.9248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11070 | DAVIE | 70306 | Public | 2033 | 5 | Swales | 66.6667 | 16666.6956 | 0.2 | 0.3 | 26000.0451 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3255.1277 | 3255.1277 | 3255.1277 | 3255.1277 | 3255.1277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11071 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 20150.6599 | 0.2 | 0.3 | 31435.0295 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6340.6697 | 6340.6697 | 6340.6697 | 6340.6697 | 6340.6697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11072 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 19816.9362 | 0.2 | 0.3 | 30914.4205 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11057.0969 | 11057.0969 | 11057.0969 | 11057.0969 | 11057.0969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11073 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 18451.2111 | 0.2 | 0.3 | 28783.8893 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5279.1128 | 5279.1128 | 5279.1128 | 5279.1128 | 5279.1128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11074 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 17018.3269 | 0.2 | 0.3 | 26548.59 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2564.4687 | 2564.4687 | 2564.4687 | 2564.4687 | 2564.4687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11075 | DAVIE | 70210 | Private | 2026 | 5 | Swales | 66.6667 | 28640.0337 | 0.2 | 0.3 | 44678.4525 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1484.0188 | 1484.0188 | 1484.0188 | 1484.0188 | 1484.0188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11076 | DAVIE | 70210 | Private | 2026 | 5 | Swales | 66.6667 | 22311.5179 | 0.2 | 0.3 | 34805.9679 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8423.1977 | 8423.1977 | 8423.1977 | 8423.1977 | 8423.1977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11077 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 19835.3499 | 0.2 | 0.3 | 30943.1458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4776.0573 | 4776.0573 | 4776.0573 | 4776.0573 | 4776.0573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11078 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 13088.3069 | 0.2 | 0.3 | 20417.7587 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8142 | 5200.8142 | 5200.8142 | 5200.8142 | 5200.8142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11079 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 33370.3827 | 0.2 | 0.3 | 52057.7971 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5399.6676 | 5399.6676 | 5399.6676 | 5399.6676 | 5399.6676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11080 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16685.1913 | 0.2 | 0.3 | 26028.8985 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5379.2792 | 5379.2792 | 5379.2792 | 5379.2792 | 5379.2792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11081 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 33849.2519 | 0.2 | 0.3 | 52804.833 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9440.4115 | 9440.4115 | 9440.4115 | 9440.4115 | 9440.4115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11082 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 31914.7124 | 0.2 | 0.3 | 49786.9513 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5909.7684 | 5909.7684 | 5909.7684 | 5909.7684 | 5909.7684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11083 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 22542.5293 | 0.2 | 0.3 | 35166.3458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6777.4764 | 6777.4764 | 6777.4764 | 6777.4764 | 6777.4764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11084 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 44997.0549 | 0.2 | 0.3 | 70195.4057 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7537.1265 | 7537.1265 | 7537.1265 | 7537.1265 | 7537.1265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11085 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 8930.6866 | 0.2 | 0.3 | 13931.8711 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9899.3135 | 9899.3135 | 9899.3135 | 9899.3135 | 9899.3135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11086 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 8702.6878 | 0.2 | 0.3 | 13576.193 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10487.1509 | 10487.1509 | 10487.1509 | 10487.1509 | 10487.1509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11087 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 22634.9349 | 0.2 | 0.3 | 35310.4985 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8083.0671 | 8083.0671 | 8083.0671 | 8083.0671 | 8083.0671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11088 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 19966.4587 | 0.2 | 0.3 | 31147.6755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1773.7204 | 1773.7204 | 1773.7204 | 1773.7204 | 1773.7204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11089 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 28421.3243 | 0.2 | 0.3 | 44337.266 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11090 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 20992.9677 | 0.2 | 0.3 | 32749.0296 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.5994 | 5199.5994 | 5199.5994 | 5199.5994 | 5199.5994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11091 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 26804.187 | 0.2 | 0.3 | 41814.5317 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9318.7933 | 9318.7933 | 9318.7933 | 9318.7933 | 9318.7933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11092 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 44697.6685 | 0.2 | 0.3 | 69728.3629 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11093 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 27949.7089 | 0.2 | 0.3 | 43601.5458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9771.2338 | 9771.2338 | 9771.2338 | 9771.2338 | 9771.2338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11094 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 29322.5904 | 0.2 | 0.3 | 45743.241 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8471.6672 | 8471.6672 | 8471.6672 | 8471.6672 | 8471.6672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11095 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 10358.6257 | 0.2 | 0.3 | 16159.456 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2621.4406 | 2621.4406 | 2621.4406 | 2621.4406 | 2621.4406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11096 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 33235.7596 | 0.2 | 0.3 | 51847.785 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9040.4594 | 9040.4594 | 9040.4594 | 9040.4594 | 9040.4594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11097 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 18028.9887 | 0.2 | 0.3 | 28125.2223 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9199.1697 | 9199.1697 | 9199.1697 | 9199.1697 | 9199.1697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11098 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 20916.4114 | 0.2 | 0.3 | 32629.6018 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13303.8516 | 13303.8516 | 13303.8516 | 13303.8516 | 13303.8516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11099 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 16668.4104 | 0.2 | 0.3 | 26002.7202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9334.7439 | 9334.7439 | 9334.7439 | 9334.7439 | 9334.7439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11100 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 6434.1807 | 0.2 | 0.3 | 10037.3218 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7838.5661 | 7838.5661 | 7838.5661 | 7838.5661 | 7838.5661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11101 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 28817.9691 | 0.2 | 0.3 | 44956.0317 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11102 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 1735.2276 | 0.2 | 0.3 | 2706.9551 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8393.4467 | 8393.4467 | 8393.4467 | 8393.4467 | 8393.4467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11103 | DAVIE | 70204 | Public | 2033 | 5 | Swales | 66.6667 | 17212.8577 | 0.2 | 0.3 | 26852.058 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8317.5397 | 8317.5397 | 8317.5397 | 8317.5397 | 8317.5397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11104 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 1389.1423 | 0.2 | 0.3 | 2167.062 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8504.1579 | 8504.1579 | 8504.1579 | 8504.1579 | 8504.1579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11105 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 18553.9603 | 0.2 | 0.3 | 28944.1781 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14624.7396 | 14624.7396 | 14624.7396 | 14624.7396 | 14624.7396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11106 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6226.6467 | 6226.6467 | 6226.6467 | 6226.6467 | 6226.6467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11107 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 18748.1909 | 0.2 | 0.3 | 29247.1779 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6855.118 | 6855.118 | 6855.118 | 6855.118 | 6855.118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11108 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 2400.178 | 0.2 | 0.3 | 3744.2777 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5217.2818 | 5217.2818 | 5217.2818 | 5217.2818 | 5217.2818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11109 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16666.9099 | 0.2 | 0.3 | 26000.3794 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1462 | 5200.1462 | 5200.1462 | 5200.1462 | 5200.1462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11110 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 11591.2634 | 0.2 | 0.3 | 18082.3709 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5673.3702 | 5673.3702 | 5673.3702 | 5673.3702 | 5673.3702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11111 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 15260.4485 | 0.2 | 0.3 | 23806.2996 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 330.4201 | 330.4201 | 330.4201 | 330.4201 | 330.4201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11112 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 29372.9951 | 0.2 | 0.3 | 45821.8723 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5451.1346 | 5451.1346 | 5451.1346 | 5451.1346 | 5451.1346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11113 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 20736.896 | 0.2 | 0.3 | 32349.5578 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8041.5163 | 8041.5163 | 8041.5163 | 8041.5163 | 8041.5163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11114 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 19912.9963 | 0.2 | 0.3 | 31064.2742 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5890.952 | 5890.952 | 5890.952 | 5890.952 | 5890.952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11115 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 4254.0255 | 0.2 | 0.3 | 6636.2797 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3283.6594 | 3283.6594 | 3283.6594 | 3283.6594 | 3283.6594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11116 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 32697.6031 | 0.2 | 0.3 | 51008.2608 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7134.7304 | 7134.7304 | 7134.7304 | 7134.7304 | 7134.7304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11117 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 33372.3895 | 0.2 | 0.3 | 52060.9277 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 440.1123 | 440.1123 | 440.1123 | 440.1123 | 440.1123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11118 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 46038.7229 | 0.2 | 0.3 | 71820.4077 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6846.7843 | 6846.7843 | 6846.7843 | 6846.7843 | 6846.7843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11119 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 29054.3475 | 0.2 | 0.3 | 45324.7822 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9500.103 | 9500.103 | 9500.103 | 9500.103 | 9500.103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11120 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 22819.4233 | 0.2 | 0.3 | 35598.3003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1573.0683 | 1573.0683 | 1573.0683 | 1573.0683 | 1573.0683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11121 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 15633.2803 | 0.2 | 0.3 | 24387.9173 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6581.3789 | 6581.3789 | 6581.3789 | 6581.3789 | 6581.3789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11122 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 29759.7439 | 0.2 | 0.3 | 46425.2004 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4956.6499 | 4956.6499 | 4956.6499 | 4956.6499 | 4956.6499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11123 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 10139.228 | 0.2 | 0.3 | 15817.1957 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7808.2784 | 7808.2784 | 7808.2784 | 7808.2784 | 7808.2784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11124 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 27942.7912 | 0.2 | 0.3 | 43590.7543 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4781.2852 | 4781.2852 | 4781.2852 | 4781.2852 | 4781.2852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11125 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 12262.9221 | 0.2 | 0.3 | 19130.1585 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5219.0867 | 5219.0867 | 5219.0867 | 5219.0867 | 5219.0867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11126 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 16674.8002 | 0.2 | 0.3 | 26012.6883 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7094.6089 | 7094.6089 | 7094.6089 | 7094.6089 | 7094.6089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11127 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 16314.4401 | 0.2 | 0.3 | 25450.5266 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5214.3505 | 5214.3505 | 5214.3505 | 5214.3505 | 5214.3505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11128 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 18900.9702 | 0.2 | 0.3 | 29485.5135 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9790.1581 | 9790.1581 | 9790.1581 | 9790.1581 | 9790.1581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11129 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 1077.4589 | 0.2 | 0.3 | 1680.8359 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5209.3205 | 5209.3205 | 5209.3205 | 5209.3205 | 5209.3205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11130 | DAVIE | 70204 | Public | 2033 | 5 | Swales | 66.6667 | 17212.8577 | 0.2 | 0.3 | 26852.058 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5207.6237 | 5207.6237 | 5207.6237 | 5207.6237 | 5207.6237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11131 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 8334.849 | 0.2 | 0.3 | 13002.3644 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7133.6363 | 7133.6363 | 7133.6363 | 7133.6363 | 7133.6363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11132 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 8334.5531 | 0.2 | 0.3 | 13001.9029 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5221.0819 | 5221.0819 | 5221.0819 | 5221.0819 | 5221.0819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11133 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 8333.3205 | 0.2 | 0.3 | 12999.9799 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4567 | 5201.4567 | 5201.4567 | 5201.4567 | 5201.4567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11134 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 8333.3205 | 0.2 | 0.3 | 12999.9799 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5278.0988 | 5278.0988 | 5278.0988 | 5278.0988 | 5278.0988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11135 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2677.8902 | 2677.8902 | 2677.8902 | 2677.8902 | 2677.8902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11136 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 39.7554 | 0.2 | 0.3 | 62.0184 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6533.0161 | 6533.0161 | 6533.0161 | 6533.0161 | 6533.0161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11137 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 7546.0913 | 0.2 | 0.3 | 11771.9024 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7345.828 | 7345.828 | 7345.828 | 7345.828 | 7345.828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11138 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 8563.6857 | 0.2 | 0.3 | 13359.3497 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6623.9032 | 6623.9032 | 6623.9032 | 6623.9032 | 6623.9032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11139 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 12803.6325 | 0.2 | 0.3 | 19973.6668 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8619.6456 | 8619.6456 | 8619.6456 | 8619.6456 | 8619.6456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11140 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 1650.9915 | 0.2 | 0.3 | 2575.5468 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11141 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 997.0383 | 0.2 | 0.3 | 1555.3797 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.268 | 9776.268 | 9776.268 | 9776.268 | 9776.268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11142 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 21544.8263 | 0.2 | 0.3 | 33609.9291 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2158 | 5200.2158 | 5200.2158 | 5200.2158 | 5200.2158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11143 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 17950.08 | 0.2 | 0.3 | 28002.1248 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.3738 | 9776.3738 | 9776.3738 | 9776.3738 | 9776.3738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11144 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 24852.8255 | 0.2 | 0.3 | 38770.4077 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1023 | 5200.1023 | 5200.1023 | 5200.1023 | 5200.1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11145 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 21044.3411 | 0.2 | 0.3 | 32829.1722 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5207.2552 | 5207.2552 | 5207.2552 | 5207.2552 | 5207.2552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11146 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 1863.542 | 0.2 | 0.3 | 2907.1255 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8220.5632 | 8220.5632 | 8220.5632 | 8220.5632 | 8220.5632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11147 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 17356.6338 | 0.2 | 0.3 | 27076.3487 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11083.6303 | 11083.6303 | 11083.6303 | 11083.6303 | 11083.6303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11148 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16674.9389 | 0.2 | 0.3 | 26012.9046 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10407.1058 | 10407.1058 | 10407.1058 | 10407.1058 | 10407.1058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11149 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 31365.5256 | 0.2 | 0.3 | 48930.2199 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10425.7677 | 10425.7677 | 10425.7677 | 10425.7677 | 10425.7677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11150 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16687.5478 | 0.2 | 0.3 | 26032.5746 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4738.7856 | 4738.7856 | 4738.7856 | 4738.7856 | 4738.7856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11151 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 18502.331 | 0.2 | 0.3 | 28863.6364 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5498 | 5201.5498 | 5201.5498 | 5201.5498 | 5201.5498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11152 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 19346.3703 | 0.2 | 0.3 | 30180.3376 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5101.1738 | 5101.1738 | 5101.1738 | 5101.1738 | 5101.1738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11153 | DAVIE | 70210 | Private | 2026 | 5 | Swales | 66.6667 | 30810.4665 | 0.2 | 0.3 | 48064.3278 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 100.4925 | 100.4925 | 100.4925 | 100.4925 | 100.4925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11154 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 40031.2341 | 0.2 | 0.3 | 62448.7251 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5174.5719 | 5174.5719 | 5174.5719 | 5174.5719 | 5174.5719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11155 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 19718.7875 | 0.2 | 0.3 | 30761.3084 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11156 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8109 | 0.2 | 0.3 | 26000.2251 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4243.4244 | 4243.4244 | 4243.4244 | 4243.4244 | 4243.4244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11157 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 63.0284 | 0.2 | 0.3 | 98.3243 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11158 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 23015.8852 | 0.2 | 0.3 | 35904.7809 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5685.561 | 5685.561 | 5685.561 | 5685.561 | 5685.561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11159 | DAVIE | 70204 | Public | 2033 | 5 | Swales | 66.6667 | 17212.8577 | 0.2 | 0.3 | 26852.058 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9771 | 5199.9771 | 5199.9771 | 5199.9771 | 5199.9771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11160 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 8333.4331 | 0.2 | 0.3 | 13000.1557 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5617.3705 | 5617.3705 | 5617.3705 | 5617.3705 | 5617.3705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11161 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 8333.3942 | 0.2 | 0.3 | 13000.095 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1898 | 5200.1898 | 5200.1898 | 5200.1898 | 5200.1898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11162 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 8333.5734 | 0.2 | 0.3 | 13000.3745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.601 | 5206.601 | 5206.601 | 5206.601 | 5206.601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11163 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 8333.3 | 0.2 | 0.3 | 12999.948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4636.138 | 4636.138 | 4636.138 | 4636.138 | 4636.138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11164 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 16666.4149 | 0.2 | 0.3 | 25999.6072 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1256.5542 | 1256.5542 | 1256.5542 | 1256.5542 | 1256.5542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11165 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 20207.2124 | 0.2 | 0.3 | 31523.2513 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5828.1546 | 5828.1546 | 5828.1546 | 5828.1546 | 5828.1546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11166 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 9133.401 | 0.2 | 0.3 | 14248.1056 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8835.8999 | 8835.8999 | 8835.8999 | 8835.8999 | 8835.8999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11167 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 8109.282 | 0.2 | 0.3 | 12650.4799 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2909 | 5200.2909 | 5200.2909 | 5200.2909 | 5200.2909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11168 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 3887.2365 | 0.2 | 0.3 | 6064.089 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7021.2788 | 7021.2788 | 7021.2788 | 7021.2788 | 7021.2788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11169 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 26720.5974 | 0.2 | 0.3 | 41684.1319 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 594.6961 | 594.6961 | 594.6961 | 594.6961 | 594.6961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11170 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 18326.1899 | 0.2 | 0.3 | 28588.8563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6470.4164 | 6470.4164 | 6470.4164 | 6470.4164 | 6470.4164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11171 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 19548.0542 | 0.2 | 0.3 | 30494.9646 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2599.9896 | 2599.9896 | 2599.9896 | 2599.9896 | 2599.9896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11172 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 18836.917 | 0.2 | 0.3 | 29385.5905 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8653.951 | 8653.951 | 8653.951 | 8653.951 | 8653.951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11173 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 6275.1572 | 0.2 | 0.3 | 9789.2452 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9332.1552 | 9332.1552 | 9332.1552 | 9332.1552 | 9332.1552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11174 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 22750.7725 | 0.2 | 0.3 | 35491.205 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5839.8482 | 5839.8482 | 5839.8482 | 5839.8482 | 5839.8482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11175 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 29579.0698 | 0.2 | 0.3 | 46143.3489 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8117.9895 | 8117.9895 | 8117.9895 | 8117.9895 | 8117.9895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11176 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 2236.4155 | 0.2 | 0.3 | 3488.8081 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6329.7381 | 6329.7381 | 6329.7381 | 6329.7381 | 6329.7381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11177 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 24847.2569 | 0.2 | 0.3 | 38761.7208 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.0247 | 5199.0247 | 5199.0247 | 5199.0247 | 5199.0247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11178 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 25375.9367 | 0.2 | 0.3 | 39586.4612 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10038.2242 | 10038.2242 | 10038.2242 | 10038.2242 | 10038.2242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11179 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 41117.4578 | 0.2 | 0.3 | 64143.2342 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8966.097 | 8966.097 | 8966.097 | 8966.097 | 8966.097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11180 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 27099.8152 | 0.2 | 0.3 | 42275.7117 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6437 | 5201.6437 | 5201.6437 | 5201.6437 | 5201.6437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11181 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 19078.1314 | 0.2 | 0.3 | 29761.885 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3559.3284 | 3559.3284 | 3559.3284 | 3559.3284 | 3559.3284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11182 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16689.2924 | 0.2 | 0.3 | 26035.2961 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1390.6855 | 1390.6855 | 1390.6855 | 1390.6855 | 1390.6855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11183 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 33338.9882 | 0.2 | 0.3 | 52008.8216 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2599.9043 | 2599.9043 | 2599.9043 | 2599.9043 | 2599.9043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11184 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 35.5247 | 0.2 | 0.3 | 55.4186 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1015.564 | 1015.564 | 1015.564 | 1015.564 | 1015.564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11185 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 24039.9409 | 0.2 | 0.3 | 37502.3079 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10615.2965 | 10615.2965 | 10615.2965 | 10615.2965 | 10615.2965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11186 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 28983.4195 | 0.2 | 0.3 | 45214.1345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7097.0395 | 7097.0395 | 7097.0395 | 7097.0395 | 7097.0395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11187 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 23083.8215 | 0.2 | 0.3 | 36010.7615 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11113.4582 | 11113.4582 | 11113.4582 | 11113.4582 | 11113.4582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11188 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 12704.7611 | 0.2 | 0.3 | 19819.4273 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1495 | 5200.1495 | 5200.1495 | 5200.1495 | 5200.1495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11189 | DAVIE | 70204 | Public | 2033 | 5 | Swales | 66.6667 | 12948.7583 | 0.2 | 0.3 | 20200.063 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5765.944 | 5765.944 | 5765.944 | 5765.944 | 5765.944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11190 | DAVIE | 70204 | Public | 2033 | 5 | Swales | 66.6667 | 10754.1177 | 0.2 | 0.3 | 16776.4236 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1982.7125 | 1982.7125 | 1982.7125 | 1982.7125 | 1982.7125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11191 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 7869.5275 | 0.2 | 0.3 | 12276.4628 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5906.2534 | 5906.2534 | 5906.2534 | 5906.2534 | 5906.2534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11192 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 8856.045 | 0.2 | 0.3 | 13815.4302 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7922.4509 | 7922.4509 | 7922.4509 | 7922.4509 | 7922.4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11193 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 78.3352 | 0.2 | 0.3 | 122.2029 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9034.3048 | 9034.3048 | 9034.3048 | 9034.3048 | 9034.3048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11194 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 20788.3008 | 0.2 | 0.3 | 32429.7492 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9569.8394 | 9569.8394 | 9569.8394 | 9569.8394 | 9569.8394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11195 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 22982.7759 | 0.2 | 0.3 | 35853.1305 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5623.1922 | 5623.1922 | 5623.1922 | 5623.1922 | 5623.1922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11196 | DAVIE | 70205 | Public | 2033 | 5 | Swales | 66.6667 | 27563.183 | 0.2 | 0.3 | 42998.5655 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5714.7423 | 5714.7423 | 5714.7423 | 5714.7423 | 5714.7423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11197 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16685.6427 | 0.2 | 0.3 | 26029.6027 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10400.6004 | 10400.6004 | 10400.6004 | 10400.6004 | 10400.6004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11198 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 17102.9853 | 0.2 | 0.3 | 26680.657 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2145 | 5200.2145 | 5200.2145 | 5200.2145 | 5200.2145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11199 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 17564.1086 | 0.2 | 0.3 | 27400.0094 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9066.0501 | 9066.0501 | 9066.0501 | 9066.0501 | 9066.0501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11200 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 5622.0745 | 0.2 | 0.3 | 8770.4363 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7300.9962 | 7300.9962 | 7300.9962 | 7300.9962 | 7300.9962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11201 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 26623.2385 | 0.2 | 0.3 | 41532.2521 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 192.1848 | 192.1848 | 192.1848 | 192.1848 | 192.1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11202 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 14477.853 | 0.2 | 0.3 | 22585.4507 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5271.5828 | 5271.5828 | 5271.5828 | 5271.5828 | 5271.5828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11203 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 36286.4491 | 0.2 | 0.3 | 56606.8605 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8778.9782 | 8778.9782 | 8778.9782 | 8778.9782 | 8778.9782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11204 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 47765.4545 | 0.2 | 0.3 | 74514.109 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11205 | DAVIE | 70212 | Private | 2036 | 5 | Swales | 66.6667 | 103.4183 | 0.2 | 0.3 | 161.3326 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11206 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 27212.6721 | 0.2 | 0.3 | 42451.7684 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4761.0417 | 4761.0417 | 4761.0417 | 4761.0417 | 4761.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11207 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 28566.1813 | 0.2 | 0.3 | 44563.2429 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7541.1923 | 7541.1923 | 7541.1923 | 7541.1923 | 7541.1923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11208 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 45928.3611 | 0.2 | 0.3 | 71648.2434 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8377.53 | 8377.53 | 8377.53 | 8377.53 | 8377.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11209 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 30742.2729 | 0.2 | 0.3 | 47957.9458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.2473 | 9776.2473 | 9776.2473 | 9776.2473 | 9776.2473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11210 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 17748.1244 | 0.2 | 0.3 | 27687.0741 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9129.2546 | 9129.2546 | 9129.2546 | 9129.2546 | 9129.2546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11211 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 16689.019 | 0.2 | 0.3 | 26034.8696 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5292.8955 | 5292.8955 | 5292.8955 | 5292.8955 | 5292.8955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11212 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 36627.8111 | 0.2 | 0.3 | 57139.3853 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8825.188 | 8825.188 | 8825.188 | 8825.188 | 8825.188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11213 | DAVIE | 70210 | Public | 2026 | 5 | Swales | 66.6667 | 3795.2195 | 0.2 | 0.3 | 5920.5424 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.707 | 5201.707 | 5201.707 | 5201.707 | 5201.707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11214 | DAVIE | 70210 | Private | 2036 | 5 | Swales | 66.6667 | 40606.3318 | 0.2 | 0.3 | 63345.8776 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4007 | 5201.4007 | 5201.4007 | 5201.4007 | 5201.4007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11215 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 4187.2001 | 0.2 | 0.3 | 6532.0321 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7807.9208 | 7807.9208 | 7807.9208 | 7807.9208 | 7807.9208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11216 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 21741.8783 | 0.2 | 0.3 | 33917.3302 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3493 | 5202.3493 | 5202.3493 | 5202.3493 | 5202.3493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11217 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 10850.3987 | 0.2 | 0.3 | 16926.6219 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10403.9329 | 10403.9329 | 10403.9329 | 10403.9329 | 10403.9329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11218 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 23804.5626 | 0.2 | 0.3 | 37135.1177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 663.3738 | 663.3738 | 663.3738 | 663.3738 | 663.3738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11219 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16948.1497 | 0.2 | 0.3 | 26439.1136 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4540.3829 | 4540.3829 | 4540.3829 | 4540.3829 | 4540.3829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11220 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 16748.789 | 0.2 | 0.3 | 26128.1108 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4757.8819 | 4757.8819 | 4757.8819 | 4757.8819 | 4757.8819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11221 | DAVIE | 70205 | Public | 2036 | 5 | Swales | 66.6667 | 2803.6108 | 0.2 | 0.3 | 4373.6328 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 378.4623 | 378.4623 | 378.4623 | 378.4623 | 378.4623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11222 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 24225.6051 | 0.2 | 0.3 | 37791.944 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5235.8746 | 5235.8746 | 5235.8746 | 5235.8746 | 5235.8746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11223 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16674.2521 | 0.2 | 0.3 | 26011.8333 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6219.1554 | 6219.1554 | 6219.1554 | 6219.1554 | 6219.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11224 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16676.0702 | 0.2 | 0.3 | 26014.6695 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8159.3 | 8159.3 | 8159.3 | 8159.3 | 8159.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11225 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16783.714 | 0.2 | 0.3 | 26182.5938 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10630.3006 | 10630.3006 | 10630.3006 | 10630.3006 | 10630.3006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11226 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 22126.3584 | 0.2 | 0.3 | 34517.1191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10128.5687 | 10128.5687 | 10128.5687 | 10128.5687 | 10128.5687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11227 | DAVIE | 70213 | Private | 2033 | 5 | Swales | 66.6667 | 21021.8128 | 0.2 | 0.3 | 32794.028 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12.5445 | 12.5445 | 12.5445 | 12.5445 | 12.5445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11228 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 3556.6917 | 0.2 | 0.3 | 5548.439 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6079.268 | 6079.268 | 6079.268 | 6079.268 | 6079.268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11229 | DAVIE | 70213 | Private | 2036 | 5 | Swales | 66.6667 | 16637.1945 | 0.2 | 0.3 | 25954.0235 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3533.514 | 3533.514 | 3533.514 | 3533.514 | 3533.514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11230 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 22054.0861 | 0.2 | 0.3 | 34404.3743 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5207.1468 | 5207.1468 | 5207.1468 | 5207.1468 | 5207.1468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11231 | DAVIE | 70204 | Private | 2033 | 5 | Swales | 66.6667 | 18508.7468 | 0.2 | 0.3 | 28873.645 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9909 | 5199.9909 | 5199.9909 | 5199.9909 | 5199.9909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11232 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 3727.7317 | 0.2 | 0.3 | 5815.2615 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6758 | 5202.6758 | 5202.6758 | 5202.6758 | 5202.6758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11233 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 17612.3675 | 0.2 | 0.3 | 27475.2934 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6253.4626 | 6253.4626 | 6253.4626 | 6253.4626 | 6253.4626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11234 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 20071.6087 | 0.2 | 0.3 | 31311.7095 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5357.7337 | 5357.7337 | 5357.7337 | 5357.7337 | 5357.7337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11235 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 17139.8593 | 0.2 | 0.3 | 26738.1805 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7149.5891 | 7149.5891 | 7149.5891 | 7149.5891 | 7149.5891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11236 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 17195.5833 | 0.2 | 0.3 | 26825.1099 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9373 | 5201.9373 | 5201.9373 | 5201.9373 | 5201.9373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11237 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 15571.0549 | 0.2 | 0.3 | 24290.8456 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5043 | 5200.5043 | 5200.5043 | 5200.5043 | 5200.5043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11238 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 390.9057 | 0.2 | 0.3 | 609.8129 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7576 | 5201.7576 | 5201.7576 | 5201.7576 | 5201.7576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11239 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16667.5237 | 0.2 | 0.3 | 26001.3369 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4606.1718 | 4606.1718 | 4606.1718 | 4606.1718 | 4606.1718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11240 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16668.7473 | 0.2 | 0.3 | 26003.2458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5797.3295 | 5797.3295 | 5797.3295 | 5797.3295 | 5797.3295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11241 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16667.3234 | 0.2 | 0.3 | 26001.0245 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7502 | 5201.7502 | 5201.7502 | 5201.7502 | 5201.7502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11242 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1509.3733 | 1509.3733 | 1509.3733 | 1509.3733 | 1509.3733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11243 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.5907 | 0.2 | 0.3 | 25999.8814 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1700.3479 | 1700.3479 | 1700.3479 | 1700.3479 | 1700.3479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11244 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 16672.2787 | 0.2 | 0.3 | 26008.7547 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7919.9861 | 7919.9861 | 7919.9861 | 7919.9861 | 7919.9861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11245 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 16693.8517 | 0.2 | 0.3 | 26042.4087 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6977.1569 | 6977.1569 | 6977.1569 | 6977.1569 | 6977.1569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11246 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 10055.2849 | 0.2 | 0.3 | 15686.2444 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6293.686 | 6293.686 | 6293.686 | 6293.686 | 6293.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11247 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 36330.1311 | 0.2 | 0.3 | 56675.0045 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3765.6974 | 3765.6974 | 3765.6974 | 3765.6974 | 3765.6974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11248 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 17375.7815 | 0.2 | 0.3 | 27106.2191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5223.8255 | 5223.8255 | 5223.8255 | 5223.8255 | 5223.8255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11249 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 22509.3257 | 0.2 | 0.3 | 35114.5481 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11250 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 1653.7933 | 0.2 | 0.3 | 2579.9175 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11251 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 16834.3151 | 0.2 | 0.3 | 26261.5315 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5800.482 | 5800.482 | 5800.482 | 5800.482 | 5800.482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11252 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 21086.0308 | 0.2 | 0.3 | 32894.208 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2053.4444 | 2053.4444 | 2053.4444 | 2053.4444 | 2053.4444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11253 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6153 | 0.2 | 0.3 | 25999.9198 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5266.7724 | 5266.7724 | 5266.7724 | 5266.7724 | 5266.7724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11254 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7197 | 0.2 | 0.3 | 26000.0828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6520.1726 | 6520.1726 | 6520.1726 | 6520.1726 | 6520.1726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11255 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.3266 | 0.2 | 0.3 | 25999.4695 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9426.4714 | 9426.4714 | 9426.4714 | 9426.4714 | 9426.4714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11256 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5282.5838 | 5282.5838 | 5282.5838 | 5282.5838 | 5282.5838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11257 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8123 | 0.2 | 0.3 | 26000.2272 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7838.2682 | 7838.2682 | 7838.2682 | 7838.2682 | 7838.2682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11258 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8709 | 0.2 | 0.3 | 26000.3187 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6475.4279 | 6475.4279 | 6475.4279 | 6475.4279 | 6475.4279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11259 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5589.5085 | 5589.5085 | 5589.5085 | 5589.5085 | 5589.5085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11260 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7694.134 | 7694.134 | 7694.134 | 7694.134 | 7694.134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11261 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16666.7075 | 0.2 | 0.3 | 26000.0636 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2172 | 5201.2172 | 5201.2172 | 5201.2172 | 5201.2172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11262 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 4210.6086 | 0.2 | 0.3 | 6568.5494 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4960.8739 | 4960.8739 | 4960.8739 | 4960.8739 | 4960.8739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11263 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 16025.2432 | 0.2 | 0.3 | 24999.3794 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0399 | 5200.0399 | 5200.0399 | 5200.0399 | 5200.0399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11264 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 3288.1791 | 0.2 | 0.3 | 5129.5593 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11265 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 27861.5756 | 0.2 | 0.3 | 43464.0579 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0302 | 5200.0302 | 5200.0302 | 5200.0302 | 5200.0302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11266 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 31112.4818 | 0.2 | 0.3 | 48535.4716 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6526.3036 | 6526.3036 | 6526.3036 | 6526.3036 | 6526.3036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11267 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 16467.8959 | 0.2 | 0.3 | 25689.9176 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5226.3353 | 5226.3353 | 5226.3353 | 5226.3353 | 5226.3353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11268 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 11637.971 | 0.2 | 0.3 | 18155.2348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11269 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 25546.5687 | 0.2 | 0.3 | 39852.6471 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8431.2964 | 8431.2964 | 8431.2964 | 8431.2964 | 8431.2964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11270 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 23911.98 | 0.2 | 0.3 | 37302.6888 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7913.4161 | 7913.4161 | 7913.4161 | 7913.4161 | 7913.4161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11271 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 26635.1747 | 0.2 | 0.3 | 41550.8726 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1654.053 | 1654.053 | 1654.053 | 1654.053 | 1654.053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11272 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 2144.7826 | 0.2 | 0.3 | 3345.8609 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6821.4717 | 6821.4717 | 6821.4717 | 6821.4717 | 6821.4717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11273 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 34367.0619 | 0.2 | 0.3 | 53612.6166 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8651.6178 | 8651.6178 | 8651.6178 | 8651.6178 | 8651.6178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11274 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 2.1218 | 0.2 | 0.3 | 3.31 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1769.0869 | 1769.0869 | 1769.0869 | 1769.0869 | 1769.0869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11275 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 5768.948 | 0.2 | 0.3 | 8999.5589 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3960.3814 | 3960.3814 | 3960.3814 | 3960.3814 | 3960.3814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11276 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 8334.9404 | 0.2 | 0.3 | 13002.507 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2121.5597 | 2121.5597 | 2121.5597 | 2121.5597 | 2121.5597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11277 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 22748.0513 | 0.2 | 0.3 | 35486.96 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10581.0632 | 10581.0632 | 10581.0632 | 10581.0632 | 10581.0632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11278 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 21273.8886 | 0.2 | 0.3 | 33187.2662 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11016.7977 | 11016.7977 | 11016.7977 | 11016.7977 | 11016.7977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11279 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 27341.1108 | 0.2 | 0.3 | 42652.1328 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6070.8986 | 6070.8986 | 6070.8986 | 6070.8986 | 6070.8986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11280 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 16954.6022 | 0.2 | 0.3 | 26449.1794 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6972.8837 | 6972.8837 | 6972.8837 | 6972.8837 | 6972.8837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11281 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 19917.8339 | 0.2 | 0.3 | 31071.8208 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1839.7514 | 1839.7514 | 1839.7514 | 1839.7514 | 1839.7514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11282 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 16702.3818 | 0.2 | 0.3 | 26055.7156 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7495.4302 | 7495.4302 | 7495.4302 | 7495.4302 | 7495.4302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11283 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 23042.6877 | 0.2 | 0.3 | 35946.5929 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7398.6604 | 7398.6604 | 7398.6604 | 7398.6604 | 7398.6604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11284 | DAVIE | 70211 | Public | 2026 | 5 | Swales | 66.6667 | 17837.1103 | 0.2 | 0.3 | 27825.8921 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6656.4173 | 6656.4173 | 6656.4173 | 6656.4173 | 6656.4173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11285 | DAVIE | 70211 | Public | 2026 | 5 | Swales | 66.6667 | 20023.9303 | 0.2 | 0.3 | 31237.3313 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9520.3133 | 9520.3133 | 9520.3133 | 9520.3133 | 9520.3133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11286 | DAVIE | 70211 | Public | 2026 | 5 | Swales | 66.6667 | 21495.6493 | 0.2 | 0.3 | 33533.213 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10658.548 | 10658.548 | 10658.548 | 10658.548 | 10658.548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11287 | DAVIE | 70211 | Public | 2026 | 5 | Swales | 66.6667 | 16782.2897 | 0.2 | 0.3 | 26180.3719 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2696.0487 | 2696.0487 | 2696.0487 | 2696.0487 | 2696.0487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11288 | DAVIE | 70211 | Public | 2026 | 5 | Swales | 66.6667 | 31450.3803 | 0.2 | 0.3 | 49062.5932 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11289 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 15135.8611 | 0.2 | 0.3 | 23611.9434 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7431.2461 | 7431.2461 | 7431.2461 | 7431.2461 | 7431.2461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11290 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 22675.5171 | 0.2 | 0.3 | 35373.8067 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7958.8869 | 7958.8869 | 7958.8869 | 7958.8869 | 7958.8869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11291 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 29907.1531 | 0.2 | 0.3 | 46655.1588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 802.2574 | 802.2574 | 802.2574 | 802.2574 | 802.2574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11292 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 11437.623 | 0.2 | 0.3 | 17842.6919 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6097.6193 | 6097.6193 | 6097.6193 | 6097.6193 | 6097.6193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11293 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 18181.2335 | 0.2 | 0.3 | 28362.7243 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7025.1464 | 7025.1464 | 7025.1464 | 7025.1464 | 7025.1464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11294 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 10903.5415 | 0.2 | 0.3 | 17009.5248 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11295 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 8335.4872 | 0.2 | 0.3 | 13003.36 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7512.2136 | 7512.2136 | 7512.2136 | 7512.2136 | 7512.2136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11296 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 22672.2167 | 0.2 | 0.3 | 35368.658 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5499.4116 | 5499.4116 | 5499.4116 | 5499.4116 | 5499.4116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11297 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 21031.5919 | 0.2 | 0.3 | 32809.2834 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9053.0669 | 9053.0669 | 9053.0669 | 9053.0669 | 9053.0669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11298 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 8791.9308 | 0.2 | 0.3 | 13715.412 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9121.1206 | 9121.1206 | 9121.1206 | 9121.1206 | 9121.1206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11299 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 16810.2587 | 0.2 | 0.3 | 26224.0036 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9983.6066 | 9983.6066 | 9983.6066 | 9983.6066 | 9983.6066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11300 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 30589.4677 | 0.2 | 0.3 | 47719.5696 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10381.4989 | 10381.4989 | 10381.4989 | 10381.4989 | 10381.4989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11301 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 16778.7533 | 0.2 | 0.3 | 26174.8552 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3927.3881 | 3927.3881 | 3927.3881 | 3927.3881 | 3927.3881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11302 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 28609.7857 | 0.2 | 0.3 | 44631.2657 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6431.3962 | 6431.3962 | 6431.3962 | 6431.3962 | 6431.3962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11303 | DAVIE | 70209 | Private | 2036 | 5 | Swales | 66.6667 | 16033.4615 | 0.2 | 0.3 | 25012.1999 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2091 | 5200.2091 | 5200.2091 | 5200.2091 | 5200.2091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11304 | DAVIE | 70209 | Private | 2036 | 5 | Swales | 66.6667 | 32177.9597 | 0.2 | 0.3 | 50197.6171 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11305 | DAVIE | 70211 | Public | 2026 | 5 | Swales | 66.6667 | 24523.4175 | 0.2 | 0.3 | 38256.5314 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10562.0142 | 10562.0142 | 10562.0142 | 10562.0142 | 10562.0142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11306 | DAVIE | 70211 | Public | 2026 | 5 | Swales | 66.6667 | 21905.5559 | 0.2 | 0.3 | 34172.6672 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10909.678 | 10909.678 | 10909.678 | 10909.678 | 10909.678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11307 | DAVIE | 70211 | Public | 2026 | 5 | Swales | 66.6667 | 19221.7675 | 0.2 | 0.3 | 29985.9572 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2563.45 | 2563.45 | 2563.45 | 2563.45 | 2563.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11308 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 21826.4872 | 0.2 | 0.3 | 34049.32 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11309 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16827.6163 | 0.2 | 0.3 | 26251.0815 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2543.0839 | 2543.0839 | 2543.0839 | 2543.0839 | 2543.0839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11310 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16999.2968 | 0.2 | 0.3 | 26518.903 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1534.4035 | 1534.4035 | 1534.4035 | 1534.4035 | 1534.4035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11311 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16667.9271 | 0.2 | 0.3 | 26001.9663 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9346.0149 | 9346.0149 | 9346.0149 | 9346.0149 | 9346.0149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11312 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16748.9298 | 0.2 | 0.3 | 26128.3305 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9388.8742 | 9388.8742 | 9388.8742 | 9388.8742 | 9388.8742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11313 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16837.1257 | 0.2 | 0.3 | 26265.9161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10173.9992 | 10173.9992 | 10173.9992 | 10173.9992 | 10173.9992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11314 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16799.1113 | 0.2 | 0.3 | 26206.6136 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7334.8616 | 7334.8616 | 7334.8616 | 7334.8616 | 7334.8616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11315 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 23903.4243 | 0.2 | 0.3 | 37289.3419 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7327.0861 | 7327.0861 | 7327.0861 | 7327.0861 | 7327.0861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11316 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 26793.704 | 0.2 | 0.3 | 41798.1782 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2593.3347 | 2593.3347 | 2593.3347 | 2593.3347 | 2593.3347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11317 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16666.646 | 0.2 | 0.3 | 25999.9678 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5014.4509 | 5014.4509 | 5014.4509 | 5014.4509 | 5014.4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11318 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 17281.9134 | 0.2 | 0.3 | 26959.7849 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5466 | 5200.5466 | 5200.5466 | 5200.5466 | 5200.5466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11319 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 24065.4028 | 0.2 | 0.3 | 37542.0284 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11320 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 16676.4147 | 0.2 | 0.3 | 26015.2069 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5596 | 5200.5596 | 5200.5596 | 5200.5596 | 5200.5596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11321 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 1558.1641 | 0.2 | 0.3 | 2430.736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7155.9896 | 7155.9896 | 7155.9896 | 7155.9896 | 7155.9896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11322 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 16555.3665 | 0.2 | 0.3 | 25826.3717 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5062.7861 | 5062.7861 | 5062.7861 | 5062.7861 | 5062.7861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11323 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 21051.3759 | 0.2 | 0.3 | 32840.1464 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7885.8519 | 7885.8519 | 7885.8519 | 7885.8519 | 7885.8519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11324 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 29085.1769 | 0.2 | 0.3 | 45372.8759 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7728.8018 | 7728.8018 | 7728.8018 | 7728.8018 | 7728.8018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11325 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 16698.2769 | 0.2 | 0.3 | 26049.3119 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9235.6869 | 9235.6869 | 9235.6869 | 9235.6869 | 9235.6869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11326 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 27701.8883 | 0.2 | 0.3 | 43214.9457 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9897.6086 | 9897.6086 | 9897.6086 | 9897.6086 | 9897.6086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11327 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 713.7003 | 0.2 | 0.3 | 1113.3725 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9567.6066 | 9567.6066 | 9567.6066 | 9567.6066 | 9567.6066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11328 | DAVIE | 70209 | Private | 2036 | 5 | Swales | 66.6667 | 18765.3503 | 0.2 | 0.3 | 29273.9464 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7440.5688 | 7440.5688 | 7440.5688 | 7440.5688 | 7440.5688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11329 | DAVIE | 70209 | Private | 2036 | 5 | Swales | 66.6667 | 17862.9071 | 0.2 | 0.3 | 27866.135 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8586.1046 | 8586.1046 | 8586.1046 | 8586.1046 | 8586.1046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11330 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16682.4573 | 0.2 | 0.3 | 26024.6334 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11331 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 14942.8579 | 0.2 | 0.3 | 23310.8584 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.3345 | 5204.3345 | 5204.3345 | 5204.3345 | 5204.3345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11332 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 22300.4396 | 0.2 | 0.3 | 34788.6858 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3130.0037 | 3130.0037 | 3130.0037 | 3130.0037 | 3130.0037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11333 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16895.1432 | 0.2 | 0.3 | 26356.4234 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6416.6346 | 6416.6346 | 6416.6346 | 6416.6346 | 6416.6346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11334 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 17529.0931 | 0.2 | 0.3 | 27345.3853 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3570.2997 | 3570.2997 | 3570.2997 | 3570.2997 | 3570.2997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11335 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 4957.6439 | 0.2 | 0.3 | 7733.9245 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5703.5026 | 5703.5026 | 5703.5026 | 5703.5026 | 5703.5026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11336 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 291.8269 | 0.2 | 0.3 | 455.2499 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6320.1459 | 6320.1459 | 6320.1459 | 6320.1459 | 6320.1459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11337 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 2606.9109 | 0.2 | 0.3 | 4066.7811 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5824.4901 | 5824.4901 | 5824.4901 | 5824.4901 | 5824.4901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11338 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 26532.6211 | 0.2 | 0.3 | 41390.889 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4371.5913 | 4371.5913 | 4371.5913 | 4371.5913 | 4371.5913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11339 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 16830.7092 | 0.2 | 0.3 | 26255.9064 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5523.753 | 5523.753 | 5523.753 | 5523.753 | 5523.753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11340 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 18589.8875 | 0.2 | 0.3 | 29000.2246 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1062.0872 | 1062.0872 | 1062.0872 | 1062.0872 | 1062.0872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11341 | DAVIE | 70209 | Private | 2033 | 5 | Swales | 66.6667 | 10593.7476 | 0.2 | 0.3 | 16526.2463 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5359.7608 | 5359.7608 | 5359.7608 | 5359.7608 | 5359.7608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11342 | DAVIE | 70209 | Private | 2036 | 5 | Swales | 66.6667 | 16799.6375 | 0.2 | 0.3 | 26207.4346 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 943.5045 | 943.5045 | 943.5045 | 943.5045 | 943.5045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11343 | DAVIE | 70209 | Private | 2036 | 5 | Swales | 66.6667 | 19101.4826 | 0.2 | 0.3 | 29798.3129 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8489.1538 | 8489.1538 | 8489.1538 | 8489.1538 | 8489.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11344 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 18351.7611 | 0.2 | 0.3 | 28628.7474 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5608.3463 | 5608.3463 | 5608.3463 | 5608.3463 | 5608.3463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11345 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 17122.3065 | 0.2 | 0.3 | 26710.7982 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6847.2904 | 6847.2904 | 6847.2904 | 6847.2904 | 6847.2904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11346 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16689.324 | 0.2 | 0.3 | 26035.3454 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7087.4995 | 7087.4995 | 7087.4995 | 7087.4995 | 7087.4995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11347 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 17192.6644 | 0.2 | 0.3 | 26820.5565 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10400.3154 | 10400.3154 | 10400.3154 | 10400.3154 | 10400.3154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11348 | DAVIE | 70209 | Private | 2036 | 5 | Swales | 66.6667 | 9030.1651 | 0.2 | 0.3 | 14087.0576 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2056 | 5200.2056 | 5200.2056 | 5200.2056 | 5200.2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11349 | DAVIE | 70209 | Private | 2036 | 5 | Swales | 66.6667 | 29712.6714 | 0.2 | 0.3 | 46351.7674 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7391.1039 | 7391.1039 | 7391.1039 | 7391.1039 | 7391.1039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11350 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 19214.9798 | 0.2 | 0.3 | 29975.3685 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8335.5152 | 8335.5152 | 8335.5152 | 8335.5152 | 8335.5152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11351 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 17677.7505 | 0.2 | 0.3 | 27577.2907 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8764.5827 | 8764.5827 | 8764.5827 | 8764.5827 | 8764.5827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11352 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16815.8661 | 0.2 | 0.3 | 26232.7512 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6342.9063 | 6342.9063 | 6342.9063 | 6342.9063 | 6342.9063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11353 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16808.0252 | 0.2 | 0.3 | 26220.5193 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5335.1263 | 5335.1263 | 5335.1263 | 5335.1263 | 5335.1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11354 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16671.5213 | 0.2 | 0.3 | 26007.5732 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3295.8904 | 3295.8904 | 3295.8904 | 3295.8904 | 3295.8904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11355 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16686.1601 | 0.2 | 0.3 | 26030.4098 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3501 | 5200.3501 | 5200.3501 | 5200.3501 | 5200.3501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11356 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16876.809 | 0.2 | 0.3 | 26327.822 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0975 | 5204.0975 | 5204.0975 | 5204.0975 | 5204.0975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11357 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16902.8649 | 0.2 | 0.3 | 26368.4692 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6322.5317 | 6322.5317 | 6322.5317 | 6322.5317 | 6322.5317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11358 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 12597.1037 | 0.2 | 0.3 | 19651.4817 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5470.4002 | 5470.4002 | 5470.4002 | 5470.4002 | 5470.4002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11359 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 12817.6308 | 0.2 | 0.3 | 19995.504 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7457.245 | 7457.245 | 7457.245 | 7457.245 | 7457.245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11360 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16680.0104 | 0.2 | 0.3 | 26020.8162 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6744.7465 | 6744.7465 | 6744.7465 | 6744.7465 | 6744.7465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11361 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16772.8215 | 0.2 | 0.3 | 26165.6016 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10953.1619 | 10953.1619 | 10953.1619 | 10953.1619 | 10953.1619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11362 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 21736.3229 | 0.2 | 0.3 | 33908.6637 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13981.1924 | 13981.1924 | 13981.1924 | 13981.1924 | 13981.1924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11363 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 8363.5912 | 0.2 | 0.3 | 13047.2023 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9818.9011 | 9818.9011 | 9818.9011 | 9818.9011 | 9818.9011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11364 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 16668.8583 | 0.2 | 0.3 | 26003.419 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5936.1115 | 5936.1115 | 5936.1115 | 5936.1115 | 5936.1115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11365 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 19252.3275 | 0.2 | 0.3 | 30033.6308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10110.6346 | 10110.6346 | 10110.6346 | 10110.6346 | 10110.6346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11366 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 23.856 | 0.2 | 0.3 | 37.2154 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6818.9352 | 6818.9352 | 6818.9352 | 6818.9352 | 6818.9352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11367 | DAVIE | 70209 | Public | 2033 | 5 | Swales | 66.6667 | 11948.7229 | 0.2 | 0.3 | 18640.0077 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5726.5371 | 5726.5371 | 5726.5371 | 5726.5371 | 5726.5371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11368 | DAVIE | 70209 | Public | 2033 | 5 | Swales | 66.6667 | 17567.779 | 0.2 | 0.3 | 27405.7352 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5682.2533 | 5682.2533 | 5682.2533 | 5682.2533 | 5682.2533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11369 | DAVIE | 70209 | Public | 2033 | 5 | Swales | 66.6667 | 18953.4131 | 0.2 | 0.3 | 29567.3244 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8077.7803 | 8077.7803 | 8077.7803 | 8077.7803 | 8077.7803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11370 | DAVIE | 70209 | Public | 2033 | 5 | Swales | 66.6667 | 5896.0629 | 0.2 | 0.3 | 9197.8581 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4118.4873 | 4118.4873 | 4118.4873 | 4118.4873 | 4118.4873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11371 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 11713.9963 | 0.2 | 0.3 | 18273.8342 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4483.3805 | 4483.3805 | 4483.3805 | 4483.3805 | 4483.3805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11372 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16667.2333 | 0.2 | 0.3 | 26000.8839 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4296.3042 | 4296.3042 | 4296.3042 | 4296.3042 | 4296.3042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11373 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0199 | 0.2 | 0.3 | 26000.5511 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4461.6765 | 4461.6765 | 4461.6765 | 4461.6765 | 4461.6765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11374 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 23156.8103 | 0.2 | 0.3 | 36124.6241 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5180.6699 | 5180.6699 | 5180.6699 | 5180.6699 | 5180.6699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11375 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 16669.4717 | 0.2 | 0.3 | 26004.3759 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4253.9946 | 4253.9946 | 4253.9946 | 4253.9946 | 4253.9946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11376 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 16585.9739 | 0.2 | 0.3 | 25874.1192 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6495.4006 | 6495.4006 | 6495.4006 | 6495.4006 | 6495.4006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11377 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 82.8368 | 0.2 | 0.3 | 129.2254 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10549.2263 | 10549.2263 | 10549.2263 | 10549.2263 | 10549.2263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11378 | DAVIE | 70209 | Public | 2033 | 5 | Swales | 66.6667 | 6845.7003 | 0.2 | 0.3 | 10679.2925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9012.6499 | 9012.6499 | 9012.6499 | 9012.6499 | 9012.6499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11379 | DAVIE | 70209 | Public | 2033 | 5 | Swales | 66.6667 | 11265.9788 | 0.2 | 0.3 | 17574.9269 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5970.1452 | 5970.1452 | 5970.1452 | 5970.1452 | 5970.1452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11380 | DAVIE | 70209 | Public | 2033 | 5 | Swales | 66.6667 | 20234.3064 | 0.2 | 0.3 | 31565.518 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6499.7843 | 6499.7843 | 6499.7843 | 6499.7843 | 6499.7843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11381 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 2225.0663 | 0.2 | 0.3 | 3471.1034 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9890.8298 | 9890.8298 | 9890.8298 | 9890.8298 | 9890.8298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11382 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 9700.7549 | 0.2 | 0.3 | 15133.1776 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6820.2768 | 6820.2768 | 6820.2768 | 6820.2768 | 6820.2768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11383 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 25191.6329 | 0.2 | 0.3 | 39298.9473 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6568.2359 | 6568.2359 | 6568.2359 | 6568.2359 | 6568.2359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11384 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 19485.4173 | 0.2 | 0.3 | 30397.251 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5221.4706 | 5221.4706 | 5221.4706 | 5221.4706 | 5221.4706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11385 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 17261.2499 | 0.2 | 0.3 | 26927.5498 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1455.1925 | 1455.1925 | 1455.1925 | 1455.1925 | 1455.1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11386 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 19755.4473 | 0.2 | 0.3 | 30818.4977 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3198.0334 | 3198.0334 | 3198.0334 | 3198.0334 | 3198.0334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11387 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6603 | 0.2 | 0.3 | 25999.9901 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4719.0849 | 4719.0849 | 4719.0849 | 4719.0849 | 4719.0849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11388 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1221.9552 | 1221.9552 | 1221.9552 | 1221.9552 | 1221.9552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11389 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8139 | 0.2 | 0.3 | 26000.2297 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8552.8642 | 8552.8642 | 8552.8642 | 8552.8642 | 8552.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11390 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 26349.0305 | 0.2 | 0.3 | 41104.4875 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5229.4831 | 5229.4831 | 5229.4831 | 5229.4831 | 5229.4831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11391 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 16670.2879 | 0.2 | 0.3 | 26005.6492 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8032.9989 | 8032.9989 | 8032.9989 | 8032.9989 | 8032.9989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11392 | DAVIE | 70209 | Public | 2033 | 5 | Swales | 66.6667 | 18948.5728 | 0.2 | 0.3 | 29559.7736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4273.557 | 4273.557 | 4273.557 | 4273.557 | 4273.557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11393 | DAVIE | 70209 | Public | 2033 | 5 | Swales | 66.6667 | 22678.6758 | 0.2 | 0.3 | 35378.7342 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1815.7371 | 1815.7371 | 1815.7371 | 1815.7371 | 1815.7371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11394 | DAVIE | 70209 | Public | 2033 | 5 | Swales | 66.6667 | 27527.5835 | 0.2 | 0.3 | 42943.0303 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4072.8817 | 4072.8817 | 4072.8817 | 4072.8817 | 4072.8817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11395 | DAVIE | 70209 | Public | 2033 | 5 | Swales | 66.6667 | 20555.1784 | 0.2 | 0.3 | 32066.0783 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4431.9933 | 4431.9933 | 4431.9933 | 4431.9933 | 4431.9933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11396 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 16356.5232 | 0.2 | 0.3 | 25516.1762 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1043 | 5201.1043 | 5201.1043 | 5201.1043 | 5201.1043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11397 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 15018.4632 | 0.2 | 0.3 | 23428.8026 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5581.6696 | 5581.6696 | 5581.6696 | 5581.6696 | 5581.6696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11398 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 6609.8667 | 0.2 | 0.3 | 10311.3921 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8203.293 | 8203.293 | 8203.293 | 8203.293 | 8203.293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11399 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 28479.0743 | 0.2 | 0.3 | 44427.356 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11400 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 27754.9292 | 0.2 | 0.3 | 43297.6896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7846.9253 | 7846.9253 | 7846.9253 | 7846.9253 | 7846.9253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11401 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 39041.3469 | 0.2 | 0.3 | 60904.5011 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6306.9291 | 6306.9291 | 6306.9291 | 6306.9291 | 6306.9291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11402 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 38252.2621 | 0.2 | 0.3 | 59673.5289 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7173 | 5201.7173 | 5201.7173 | 5201.7173 | 5201.7173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11403 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3222 | 5200.3222 | 5200.3222 | 5200.3222 | 5200.3222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11404 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 16983.2017 | 0.2 | 0.3 | 26493.7947 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9752.384 | 9752.384 | 9752.384 | 9752.384 | 9752.384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11405 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 16676.5082 | 0.2 | 0.3 | 26015.3528 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9688.9447 | 9688.9447 | 9688.9447 | 9688.9447 | 9688.9447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11406 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 25531.8819 | 0.2 | 0.3 | 39829.7357 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10400.5891 | 10400.5891 | 10400.5891 | 10400.5891 | 10400.5891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11407 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 833.8339 | 0.2 | 0.3 | 1300.7809 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7436.1882 | 7436.1882 | 7436.1882 | 7436.1882 | 7436.1882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11408 | DAVIE | 70209 | Public | 2033 | 5 | Swales | 66.6667 | 31389.6031 | 0.2 | 0.3 | 48967.7809 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3900.491 | 3900.491 | 3900.491 | 3900.491 | 3900.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11409 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 17218.2503 | 0.2 | 0.3 | 26860.4705 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4607.1404 | 4607.1404 | 4607.1404 | 4607.1404 | 4607.1404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11410 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 19301.806 | 0.2 | 0.3 | 30110.8174 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8471.4322 | 8471.4322 | 8471.4322 | 8471.4322 | 8471.4322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11411 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 17237.962 | 0.2 | 0.3 | 26891.2207 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2518.1836 | 2518.1836 | 2518.1836 | 2518.1836 | 2518.1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11412 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 17611.7741 | 0.2 | 0.3 | 27474.3676 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2034.0348 | 2034.0348 | 2034.0348 | 2034.0348 | 2034.0348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11413 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 36186.6911 | 0.2 | 0.3 | 56451.2381 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4580.0657 | 4580.0657 | 4580.0657 | 4580.0657 | 4580.0657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11414 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 22142.6259 | 0.2 | 0.3 | 34542.4965 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2693.6247 | 2693.6247 | 2693.6247 | 2693.6247 | 2693.6247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11415 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 10913.574 | 0.2 | 0.3 | 17025.1754 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2757.1305 | 2757.1305 | 2757.1305 | 2757.1305 | 2757.1305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11416 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 27104.1299 | 0.2 | 0.3 | 42282.4426 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10279.2572 | 10279.2572 | 10279.2572 | 10279.2572 | 10279.2572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11417 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16667.0401 | 0.2 | 0.3 | 26000.5825 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6527.1259 | 6527.1259 | 6527.1259 | 6527.1259 | 6527.1259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11418 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7103.9192 | 7103.9192 | 7103.9192 | 7103.9192 | 7103.9192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11419 | DAVIE | 70306 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1289 | 0.2 | 0.3 | 26000.7211 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2057.2389 | 2057.2389 | 2057.2389 | 2057.2389 | 2057.2389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11420 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 21449.6123 | 0.2 | 0.3 | 33461.3952 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1317.5397 | 1317.5397 | 1317.5397 | 1317.5397 | 1317.5397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11421 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 20658.0765 | 0.2 | 0.3 | 32226.5993 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4525.9656 | 4525.9656 | 4525.9656 | 4525.9656 | 4525.9656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11422 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 18471.423 | 0.2 | 0.3 | 28815.4199 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5409.0348 | 5409.0348 | 5409.0348 | 5409.0348 | 5409.0348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11423 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 6285.25 | 0.2 | 0.3 | 9804.99 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5975.1498 | 5975.1498 | 5975.1498 | 5975.1498 | 5975.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11424 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 6266.3659 | 0.2 | 0.3 | 9775.5309 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6036.344 | 6036.344 | 6036.344 | 6036.344 | 6036.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11425 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 21791.8833 | 0.2 | 0.3 | 33995.3379 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 691.3334 | 691.3334 | 691.3334 | 691.3334 | 691.3334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11426 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 27147.5016 | 0.2 | 0.3 | 42350.1025 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4379.9158 | 4379.9158 | 4379.9158 | 4379.9158 | 4379.9158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11427 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 20764.7499 | 0.2 | 0.3 | 32393.0099 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3028.3289 | 3028.3289 | 3028.3289 | 3028.3289 | 3028.3289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11428 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 15185.4081 | 0.2 | 0.3 | 23689.2366 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2856.5839 | 2856.5839 | 2856.5839 | 2856.5839 | 2856.5839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11429 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 17868.8205 | 0.2 | 0.3 | 27875.3599 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5136.1894 | 5136.1894 | 5136.1894 | 5136.1894 | 5136.1894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11430 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 20024.9838 | 0.2 | 0.3 | 31238.9747 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9866.1296 | 9866.1296 | 9866.1296 | 9866.1296 | 9866.1296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11431 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 5694.7013 | 0.2 | 0.3 | 8883.7341 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10024.7562 | 10024.7562 | 10024.7562 | 10024.7562 | 10024.7562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11432 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 21117.7491 | 0.2 | 0.3 | 32943.6885 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7374.3884 | 7374.3884 | 7374.3884 | 7374.3884 | 7374.3884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11433 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 7456.2699 | 0.2 | 0.3 | 11631.7811 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2314.6347 | 2314.6347 | 2314.6347 | 2314.6347 | 2314.6347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11434 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 17416.6039 | 0.2 | 0.3 | 27169.9021 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5420.4813 | 5420.4813 | 5420.4813 | 5420.4813 | 5420.4813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11435 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16673.1353 | 0.2 | 0.3 | 26010.091 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6623.0766 | 6623.0766 | 6623.0766 | 6623.0766 | 6623.0766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11436 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16669.1969 | 0.2 | 0.3 | 26003.9472 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4982.6821 | 4982.6821 | 4982.6821 | 4982.6821 | 4982.6821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11437 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16668.5138 | 0.2 | 0.3 | 26002.8815 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 947.3501 | 947.3501 | 947.3501 | 947.3501 | 947.3501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11438 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 25384.6539 | 0.2 | 0.3 | 39600.0601 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8243.4283 | 8243.4283 | 8243.4283 | 8243.4283 | 8243.4283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11439 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16683.5509 | 0.2 | 0.3 | 26026.3395 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6878.2293 | 6878.2293 | 6878.2293 | 6878.2293 | 6878.2293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11440 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16679.1813 | 0.2 | 0.3 | 26019.5228 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5224.8839 | 5224.8839 | 5224.8839 | 5224.8839 | 5224.8839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11441 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16670.1543 | 0.2 | 0.3 | 26005.4407 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5445.9304 | 5445.9304 | 5445.9304 | 5445.9304 | 5445.9304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11442 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 17186.2641 | 0.2 | 0.3 | 26810.5719 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 979.709 | 979.709 | 979.709 | 979.709 | 979.709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11443 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 10188.0931 | 0.2 | 0.3 | 15893.4252 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5699.0959 | 5699.0959 | 5699.0959 | 5699.0959 | 5699.0959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11444 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 12640.7557 | 0.2 | 0.3 | 19719.5788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11445 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 31869.2635 | 0.2 | 0.3 | 49716.0511 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0678 | 5200.0678 | 5200.0678 | 5200.0678 | 5200.0678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11446 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 27705.0291 | 0.2 | 0.3 | 43219.8454 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6389.0522 | 6389.0522 | 6389.0522 | 6389.0522 | 6389.0522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11447 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 7029.8092 | 0.2 | 0.3 | 10966.5024 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5898.3063 | 5898.3063 | 5898.3063 | 5898.3063 | 5898.3063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11448 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 17083.6807 | 0.2 | 0.3 | 26650.5418 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.495 | 5201.495 | 5201.495 | 5201.495 | 5201.495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11449 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 17238.2841 | 0.2 | 0.3 | 26891.7231 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1744.1114 | 1744.1114 | 1744.1114 | 1744.1114 | 1744.1114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11450 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 17148.3623 | 0.2 | 0.3 | 26751.4452 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6414.2528 | 6414.2528 | 6414.2528 | 6414.2528 | 6414.2528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11451 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 3921.3957 | 0.2 | 0.3 | 6117.3773 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10431.8395 | 10431.8395 | 10431.8395 | 10431.8395 | 10431.8395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11452 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 17259.6095 | 0.2 | 0.3 | 26924.9908 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3174.29 | 3174.29 | 3174.29 | 3174.29 | 3174.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11453 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 16667.2843 | 0.2 | 0.3 | 26000.9635 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5209.3235 | 5209.3235 | 5209.3235 | 5209.3235 | 5209.3235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11454 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5300.1733 | 5300.1733 | 5300.1733 | 5300.1733 | 5300.1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11455 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 22002.1877 | 0.2 | 0.3 | 34323.4128 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3395.3303 | 3395.3303 | 3395.3303 | 3395.3303 | 3395.3303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11456 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 989.9729 | 0.2 | 0.3 | 1544.3577 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9424.3791 | 9424.3791 | 9424.3791 | 9424.3791 | 9424.3791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11457 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 15689.4604 | 0.2 | 0.3 | 24475.5582 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5964.625 | 5964.625 | 5964.625 | 5964.625 | 5964.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11458 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 977.413 | 0.2 | 0.3 | 1524.7643 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7482.8524 | 7482.8524 | 7482.8524 | 7482.8524 | 7482.8524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11459 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16688.7456 | 0.2 | 0.3 | 26034.4431 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9211.5703 | 9211.5703 | 9211.5703 | 9211.5703 | 9211.5703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11460 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 19131.8287 | 0.2 | 0.3 | 29845.6527 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5419.6949 | 5419.6949 | 5419.6949 | 5419.6949 | 5419.6949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11461 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 17047.1034 | 0.2 | 0.3 | 26593.4813 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6837.3302 | 6837.3302 | 6837.3302 | 6837.3302 | 6837.3302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11462 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 13679.0143 | 0.2 | 0.3 | 21339.2623 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5426.294 | 5426.294 | 5426.294 | 5426.294 | 5426.294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11463 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 5213.6879 | 0.2 | 0.3 | 8133.3531 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 178.5226 | 178.5226 | 178.5226 | 178.5226 | 178.5226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11464 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 13440.9521 | 0.2 | 0.3 | 20967.8853 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5124.6102 | 5124.6102 | 5124.6102 | 5124.6102 | 5124.6102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11465 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 7615.9927 | 0.2 | 0.3 | 11880.9486 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2194 | 5200.2194 | 5200.2194 | 5200.2194 | 5200.2194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11466 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 9443.5749 | 0.2 | 0.3 | 14731.9768 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5193.9972 | 5193.9972 | 5193.9972 | 5193.9972 | 5193.9972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11467 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 17706.5164 | 0.2 | 0.3 | 27622.1656 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11468 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 27648.4421 | 0.2 | 0.3 | 43131.5697 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4273.1567 | 4273.1567 | 4273.1567 | 4273.1567 | 4273.1567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11469 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 16797.2747 | 0.2 | 0.3 | 26203.7485 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10791.8347 | 10791.8347 | 10791.8347 | 10791.8347 | 10791.8347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11470 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 15732.9314 | 0.2 | 0.3 | 24543.373 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8113.2022 | 8113.2022 | 8113.2022 | 8113.2022 | 8113.2022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11471 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 933.942 | 0.2 | 0.3 | 1456.9495 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13944.1986 | 13944.1986 | 13944.1986 | 13944.1986 | 13944.1986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11472 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 21585.4341 | 0.2 | 0.3 | 33673.2772 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3168.2762 | 3168.2762 | 3168.2762 | 3168.2762 | 3168.2762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11473 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 18073.1099 | 0.2 | 0.3 | 28194.0514 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.8653 | 5204.8653 | 5204.8653 | 5204.8653 | 5204.8653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11474 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 17285.6641 | 0.2 | 0.3 | 26965.636 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8005.6372 | 8005.6372 | 8005.6372 | 8005.6372 | 8005.6372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11475 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 3369.3272 | 0.2 | 0.3 | 5256.1504 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9782.5368 | 9782.5368 | 9782.5368 | 9782.5368 | 9782.5368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11476 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 20890.3255 | 0.2 | 0.3 | 32588.9078 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4303 | 5201.4303 | 5201.4303 | 5201.4303 | 5201.4303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11477 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 31696.4871 | 0.2 | 0.3 | 49446.5198 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8459.7232 | 8459.7232 | 8459.7232 | 8459.7232 | 8459.7232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11478 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 17205.5289 | 0.2 | 0.3 | 26840.625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7033.0467 | 7033.0467 | 7033.0467 | 7033.0467 | 7033.0467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11479 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5331.9277 | 5331.9277 | 5331.9277 | 5331.9277 | 5331.9277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11480 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 31210.7038 | 0.2 | 0.3 | 48688.6979 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5976.0457 | 5976.0457 | 5976.0457 | 5976.0457 | 5976.0457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11481 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 476.5423 | 0.2 | 0.3 | 743.4059 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5420.0909 | 5420.0909 | 5420.0909 | 5420.0909 | 5420.0909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11482 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16656.4841 | 0.2 | 0.3 | 25984.1152 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6825.6451 | 6825.6451 | 6825.6451 | 6825.6451 | 6825.6451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11483 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 23209.8155 | 0.2 | 0.3 | 36207.3121 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6670.1117 | 6670.1117 | 6670.1117 | 6670.1117 | 6670.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11484 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 18867.6805 | 0.2 | 0.3 | 29433.5816 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5333.8347 | 5333.8347 | 5333.8347 | 5333.8347 | 5333.8347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11485 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6324.2198 | 6324.2198 | 6324.2198 | 6324.2198 | 6324.2198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11486 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 17197.2113 | 0.2 | 0.3 | 26827.6496 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5830.8606 | 5830.8606 | 5830.8606 | 5830.8606 | 5830.8606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11487 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 33202.1556 | 0.2 | 0.3 | 51795.3627 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5748.2294 | 5748.2294 | 5748.2294 | 5748.2294 | 5748.2294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11488 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 19388.8077 | 0.2 | 0.3 | 30246.5401 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2839.0246 | 2839.0246 | 2839.0246 | 2839.0246 | 2839.0246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11489 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 17245.3925 | 0.2 | 0.3 | 26902.8124 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9280.8663 | 9280.8663 | 9280.8663 | 9280.8663 | 9280.8663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11490 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 6265.3039 | 0.2 | 0.3 | 9773.8741 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9423.3493 | 9423.3493 | 9423.3493 | 9423.3493 | 9423.3493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11491 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 16678.2545 | 0.2 | 0.3 | 26018.0771 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1324.9251 | 1324.9251 | 1324.9251 | 1324.9251 | 1324.9251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11492 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 6786.0171 | 0.2 | 0.3 | 10586.1866 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8317.6278 | 8317.6278 | 8317.6278 | 8317.6278 | 8317.6278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11493 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 10585.7547 | 0.2 | 0.3 | 16513.7774 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8215.0965 | 8215.0965 | 8215.0965 | 8215.0965 | 8215.0965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11494 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16671.7947 | 0.2 | 0.3 | 26007.9997 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10725.2812 | 10725.2812 | 10725.2812 | 10725.2812 | 10725.2812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11495 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 12704.9491 | 0.2 | 0.3 | 19819.7205 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7909.4449 | 7909.4449 | 7909.4449 | 7909.4449 | 7909.4449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11496 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 8980.4927 | 0.2 | 0.3 | 14009.5686 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9241.6379 | 9241.6379 | 9241.6379 | 9241.6379 | 9241.6379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11497 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 13384.1476 | 0.2 | 0.3 | 20879.2703 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4082.6836 | 4082.6836 | 4082.6836 | 4082.6836 | 4082.6836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11498 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 16679.4452 | 0.2 | 0.3 | 26019.9345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5224.8803 | 5224.8803 | 5224.8803 | 5224.8803 | 5224.8803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11499 | DAVIE | 70103 | Private | 2030 | 5 | Swales | 66.6667 | 13886.1201 | 0.2 | 0.3 | 21662.3473 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6384.5124 | 6384.5124 | 6384.5124 | 6384.5124 | 6384.5124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11500 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 3136.0185 | 0.2 | 0.3 | 4892.1889 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0627 | 5201.0627 | 5201.0627 | 5201.0627 | 5201.0627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11501 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 25046.7718 | 0.2 | 0.3 | 39072.964 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7573.5633 | 7573.5633 | 7573.5633 | 7573.5633 | 7573.5633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11502 | DAVIE | 70103 | Private | 2026 | 5 | Swales | 66.6667 | 22519.3099 | 0.2 | 0.3 | 35130.1234 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9906.1827 | 9906.1827 | 9906.1827 | 9906.1827 | 9906.1827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11503 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 21141.9095 | 0.2 | 0.3 | 32981.3788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7537 | 5200.7537 | 5200.7537 | 5200.7537 | 5200.7537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11504 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 15748.2717 | 0.2 | 0.3 | 24567.3039 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6159.5598 | 6159.5598 | 6159.5598 | 6159.5598 | 6159.5598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11505 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 17086.8852 | 0.2 | 0.3 | 26655.5409 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6039.6489 | 6039.6489 | 6039.6489 | 6039.6489 | 6039.6489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11506 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16683.8905 | 0.2 | 0.3 | 26026.8692 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11507 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16697.6365 | 0.2 | 0.3 | 26048.3129 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7662.87 | 7662.87 | 7662.87 | 7662.87 | 7662.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11508 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 29614.7894 | 0.2 | 0.3 | 46199.0715 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.5579 | 9778.5579 | 9778.5579 | 9778.5579 | 9778.5579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11509 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16694.7605 | 0.2 | 0.3 | 26043.8263 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0916 | 5200.0916 | 5200.0916 | 5200.0916 | 5200.0916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11510 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16687.1051 | 0.2 | 0.3 | 26031.884 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7193.1229 | 7193.1229 | 7193.1229 | 7193.1229 | 7193.1229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11511 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16679.7233 | 0.2 | 0.3 | 26020.3684 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6443.9003 | 6443.9003 | 6443.9003 | 6443.9003 | 6443.9003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11512 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16692.7113 | 0.2 | 0.3 | 26040.6297 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3780.9409 | 3780.9409 | 3780.9409 | 3780.9409 | 3780.9409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11513 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 13515.8185 | 0.2 | 0.3 | 21084.6768 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11514 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 24538.3873 | 0.2 | 0.3 | 38279.8841 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11515 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1132.0808 | 1132.0808 | 1132.0808 | 1132.0808 | 1132.0808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11516 | DAVIE | 70209 | Public | 2036 | 5 | Swales | 66.6667 | 20270.3761 | 0.2 | 0.3 | 31621.7867 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3336.7171 | 3336.7171 | 3336.7171 | 3336.7171 | 3336.7171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11517 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 6641.9483 | 0.2 | 0.3 | 10361.4394 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3227.8655 | 3227.8655 | 3227.8655 | 3227.8655 | 3227.8655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11518 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 20577.4277 | 0.2 | 0.3 | 32100.7872 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6749.866 | 6749.866 | 6749.866 | 6749.866 | 6749.866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11519 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 16672.8883 | 0.2 | 0.3 | 26009.7057 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7694.1312 | 7694.1312 | 7694.1312 | 7694.1312 | 7694.1312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11520 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 24660.4415 | 0.2 | 0.3 | 38470.2888 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8774.1968 | 8774.1968 | 8774.1968 | 8774.1968 | 8774.1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11521 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 25460.1331 | 0.2 | 0.3 | 39717.8076 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5441.772 | 5441.772 | 5441.772 | 5441.772 | 5441.772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11522 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 25776.2663 | 0.2 | 0.3 | 40210.9755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8717.2598 | 8717.2598 | 8717.2598 | 8717.2598 | 8717.2598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11523 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 26408.2449 | 0.2 | 0.3 | 41196.8621 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8909.4433 | 8909.4433 | 8909.4433 | 8909.4433 | 8909.4433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11524 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 27150.5122 | 0.2 | 0.3 | 42354.799 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10487.6 | 10487.6 | 10487.6 | 10487.6 | 10487.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11525 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 27612.4144 | 0.2 | 0.3 | 43075.3665 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9002.915 | 9002.915 | 9002.915 | 9002.915 | 9002.915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11526 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 28223.8888 | 0.2 | 0.3 | 44029.2665 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4634.4246 | 4634.4246 | 4634.4246 | 4634.4246 | 4634.4246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11527 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16676.4955 | 0.2 | 0.3 | 26015.333 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6229.7945 | 6229.7945 | 6229.7945 | 6229.7945 | 6229.7945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11528 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16677.2627 | 0.2 | 0.3 | 26016.5298 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11529 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16677.2627 | 0.2 | 0.3 | 26016.5298 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9724.9517 | 9724.9517 | 9724.9517 | 9724.9517 | 9724.9517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11530 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 28832.8786 | 0.2 | 0.3 | 44979.2906 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2249.4722 | 2249.4722 | 2249.4722 | 2249.4722 | 2249.4722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11531 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5288.8467 | 5288.8467 | 5288.8467 | 5288.8467 | 5288.8467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11532 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 29771.3887 | 0.2 | 0.3 | 46443.3664 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4255.7487 | 4255.7487 | 4255.7487 | 4255.7487 | 4255.7487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11533 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 29713.0599 | 0.2 | 0.3 | 46352.3734 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11534 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16672.4415 | 0.2 | 0.3 | 26009.0087 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4024.151 | 4024.151 | 4024.151 | 4024.151 | 4024.151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11535 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16676.0031 | 0.2 | 0.3 | 26014.5649 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5613.9377 | 5613.9377 | 5613.9377 | 5613.9377 | 5613.9377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11536 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16675.8301 | 0.2 | 0.3 | 26014.295 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6280.4043 | 6280.4043 | 6280.4043 | 6280.4043 | 6280.4043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11537 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16674.1927 | 0.2 | 0.3 | 26011.7407 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10819.7978 | 10819.7978 | 10819.7978 | 10819.7978 | 10819.7978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11538 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16675.8805 | 0.2 | 0.3 | 26014.3736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6024.2512 | 6024.2512 | 6024.2512 | 6024.2512 | 6024.2512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11539 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 21567.0281 | 0.2 | 0.3 | 33644.5638 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3941.1722 | 3941.1722 | 3941.1722 | 3941.1722 | 3941.1722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11540 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16673.4518 | 0.2 | 0.3 | 26010.5848 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3220.4003 | 3220.4003 | 3220.4003 | 3220.4003 | 3220.4003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11541 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 20042.1367 | 0.2 | 0.3 | 31265.7333 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7902.4136 | 7902.4136 | 7902.4136 | 7902.4136 | 7902.4136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11542 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 25011.6563 | 0.2 | 0.3 | 39018.1838 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2124.7105 | 2124.7105 | 2124.7105 | 2124.7105 | 2124.7105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11543 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 40846.1408 | 0.2 | 0.3 | 63719.9796 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6330.0029 | 6330.0029 | 6330.0029 | 6330.0029 | 6330.0029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11544 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 15235.3015 | 0.2 | 0.3 | 23767.0704 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3491.7878 | 3491.7878 | 3491.7878 | 3491.7878 | 3491.7878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11545 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 1450.3304 | 0.2 | 0.3 | 2262.5154 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3362.0823 | 3362.0823 | 3362.0823 | 3362.0823 | 3362.0823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11546 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 22472.7102 | 0.2 | 0.3 | 35057.4279 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6835.6532 | 6835.6532 | 6835.6532 | 6835.6532 | 6835.6532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11547 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16675.5826 | 0.2 | 0.3 | 26013.9089 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2068 | 5200.2068 | 5200.2068 | 5200.2068 | 5200.2068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11548 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16675.6223 | 0.2 | 0.3 | 26013.9707 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7414.852 | 7414.852 | 7414.852 | 7414.852 | 7414.852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11549 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 30397.3923 | 0.2 | 0.3 | 47419.9319 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4032.1115 | 4032.1115 | 4032.1115 | 4032.1115 | 4032.1115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11550 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16672.6149 | 0.2 | 0.3 | 26009.2792 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 419.5465 | 419.5465 | 419.5465 | 419.5465 | 419.5465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11551 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7557.7216 | 7557.7216 | 7557.7216 | 7557.7216 | 7557.7216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11552 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1253 | 5202.1253 | 5202.1253 | 5202.1253 | 5202.1253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11553 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16673.7085 | 0.2 | 0.3 | 26010.9852 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5277.3192 | 5277.3192 | 5277.3192 | 5277.3192 | 5277.3192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11554 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16675.6223 | 0.2 | 0.3 | 26013.9707 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2160.9312 | 2160.9312 | 2160.9312 | 2160.9312 | 2160.9312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11555 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 23323.4067 | 0.2 | 0.3 | 36384.5144 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9839 | 5199.9839 | 5199.9839 | 5199.9839 | 5199.9839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11556 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 25310.0119 | 0.2 | 0.3 | 39483.6186 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5166.6201 | 5166.6201 | 5166.6201 | 5166.6201 | 5166.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11557 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 28742.7308 | 0.2 | 0.3 | 44838.66 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 212.6383 | 212.6383 | 212.6383 | 212.6383 | 212.6383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11558 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 25011.1095 | 0.2 | 0.3 | 39017.3308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3291.2697 | 3291.2697 | 3291.2697 | 3291.2697 | 3291.2697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11559 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 34101.0382 | 0.2 | 0.3 | 53197.6196 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5526.743 | 5526.743 | 5526.743 | 5526.743 | 5526.743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11560 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 2712.4178 | 0.2 | 0.3 | 4231.3718 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7200.898 | 7200.898 | 7200.898 | 7200.898 | 7200.898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11561 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 8450.9617 | 0.2 | 0.3 | 13183.5003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7341.6121 | 7341.6121 | 7341.6121 | 7341.6121 | 7341.6121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11562 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 29639.9404 | 0.2 | 0.3 | 46238.307 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9343.4975 | 9343.4975 | 9343.4975 | 9343.4975 | 9343.4975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11563 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 37136.1082 | 0.2 | 0.3 | 57932.3288 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5362.1963 | 5362.1963 | 5362.1963 | 5362.1963 | 5362.1963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11564 | DAVIE | 70204 | Private | 2036 | 5 | Swales | 66.6667 | 4883.116 | 0.2 | 0.3 | 7617.661 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.5121 | 2600.5121 | 2600.5121 | 2600.5121 | 2600.5121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11565 | DAVIE | 70204 | Public | 2036 | 5 | Swales | 66.6667 | 21836.7963 | 0.2 | 0.3 | 34065.4022 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.5121 | 2600.5121 | 2600.5121 | 2600.5121 | 2600.5121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11566 | DAVIE | 70204 | Public | 2036 | 5 | Swales | 66.6667 | 16672.5971 | 0.2 | 0.3 | 26009.2514 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5855.5764 | 5855.5764 | 5855.5764 | 5855.5764 | 5855.5764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11567 | DAVIE | 70204 | Public | 2036 | 5 | Swales | 66.6667 | 16672.6149 | 0.2 | 0.3 | 26009.2792 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4478.7792 | 4478.7792 | 4478.7792 | 4478.7792 | 4478.7792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11568 | DAVIE | 70204 | Public | 2036 | 5 | Swales | 66.6667 | 16672.8883 | 0.2 | 0.3 | 26009.7057 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2691.8931 | 2691.8931 | 2691.8931 | 2691.8931 | 2691.8931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11569 | DAVIE | 70204 | Public | 2036 | 5 | Swales | 66.6667 | 16672.9462 | 0.2 | 0.3 | 26009.7961 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4828.3054 | 4828.3054 | 4828.3054 | 4828.3054 | 4828.3054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11570 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 25585.2975 | 0.2 | 0.3 | 39913.0642 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5778.8303 | 5778.8303 | 5778.8303 | 5778.8303 | 5778.8303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11571 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16674.7179 | 0.2 | 0.3 | 26012.56 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5493.0609 | 5493.0609 | 5493.0609 | 5493.0609 | 5493.0609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11572 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4456.0987 | 4456.0987 | 4456.0987 | 4456.0987 | 4456.0987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11573 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 30673.7995 | 0.2 | 0.3 | 47851.1273 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7924.4127 | 7924.4127 | 7924.4127 | 7924.4127 | 7924.4127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11574 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16672.2251 | 0.2 | 0.3 | 26008.6711 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7901.8696 | 7901.8696 | 7901.8696 | 7901.8696 | 7901.8696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11575 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16675.3209 | 0.2 | 0.3 | 26013.5007 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7656.0155 | 7656.0155 | 7656.0155 | 7656.0155 | 7656.0155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11576 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16674.7813 | 0.2 | 0.3 | 26012.6589 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5168.5637 | 5168.5637 | 5168.5637 | 5168.5637 | 5168.5637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11577 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16708.2067 | 0.2 | 0.3 | 26064.8025 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5342.8068 | 5342.8068 | 5342.8068 | 5342.8068 | 5342.8068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11578 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 22741.4221 | 0.2 | 0.3 | 35476.6184 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4788.043 | 4788.043 | 4788.043 | 4788.043 | 4788.043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11579 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 25778.6857 | 0.2 | 0.3 | 40214.7496 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7814.6854 | 7814.6854 | 7814.6854 | 7814.6854 | 7814.6854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11580 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 22833.8925 | 0.2 | 0.3 | 35620.8724 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9990.1833 | 9990.1833 | 9990.1833 | 9990.1833 | 9990.1833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11581 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 17913.7342 | 0.2 | 0.3 | 27945.4254 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5261.5665 | 5261.5665 | 5261.5665 | 5261.5665 | 5261.5665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11582 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16676.9893 | 0.2 | 0.3 | 26016.1033 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9347.6736 | 9347.6736 | 9347.6736 | 9347.6736 | 9347.6736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11583 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 24228.8857 | 0.2 | 0.3 | 37797.0616 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5223.4681 | 5223.4681 | 5223.4681 | 5223.4681 | 5223.4681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11584 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 8335.1195 | 0.2 | 0.3 | 13002.7864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.6045 | 5205.6045 | 5205.6045 | 5205.6045 | 5205.6045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11585 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 23119.0049 | 0.2 | 0.3 | 36065.6476 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8743.7576 | 8743.7576 | 8743.7576 | 8743.7576 | 8743.7576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11586 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 35113.7029 | 0.2 | 0.3 | 54777.3765 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4559.8366 | 4559.8366 | 4559.8366 | 4559.8366 | 4559.8366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11587 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 31346.266 | 0.2 | 0.3 | 48900.175 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1474.2696 | 1474.2696 | 1474.2696 | 1474.2696 | 1474.2696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11588 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 31353.4993 | 0.2 | 0.3 | 48911.459 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8155.8103 | 8155.8103 | 8155.8103 | 8155.8103 | 8155.8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11589 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 31352.6683 | 0.2 | 0.3 | 48910.1625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6576.7563 | 6576.7563 | 6576.7563 | 6576.7563 | 6576.7563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11590 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 31350.3539 | 0.2 | 0.3 | 48906.552 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5326.0362 | 5326.0362 | 5326.0362 | 5326.0362 | 5326.0362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11591 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 31345.9997 | 0.2 | 0.3 | 48899.7595 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3330.4316 | 3330.4316 | 3330.4316 | 3330.4316 | 3330.4316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11592 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 31324.6726 | 0.2 | 0.3 | 48866.4893 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7416.052 | 7416.052 | 7416.052 | 7416.052 | 7416.052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11593 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 25286.9085 | 0.2 | 0.3 | 39447.5772 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3302.0412 | 3302.0412 | 3302.0412 | 3302.0412 | 3302.0412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11594 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 11261.6794 | 0.2 | 0.3 | 17568.2199 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6525.4205 | 6525.4205 | 6525.4205 | 6525.4205 | 6525.4205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11595 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16983.4299 | 0.2 | 0.3 | 26494.1507 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7438.9527 | 7438.9527 | 7438.9527 | 7438.9527 | 7438.9527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11596 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 20546.2331 | 0.2 | 0.3 | 32052.1237 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8035.7406 | 8035.7406 | 8035.7406 | 8035.7406 | 8035.7406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11597 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 11484.0669 | 0.2 | 0.3 | 17915.1443 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6823.4758 | 6823.4758 | 6823.4758 | 6823.4758 | 6823.4758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11598 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 5683.6508 | 0.2 | 0.3 | 8866.4952 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5306.0549 | 5306.0549 | 5306.0549 | 5306.0549 | 5306.0549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11599 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 20382.1027 | 0.2 | 0.3 | 31796.0802 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5222.4786 | 5222.4786 | 5222.4786 | 5222.4786 | 5222.4786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11600 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 12140.2948 | 0.2 | 0.3 | 18938.8599 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.4803 | 5204.4803 | 5204.4803 | 5204.4803 | 5204.4803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11601 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16676.3084 | 0.2 | 0.3 | 26015.0411 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5715 | 5200.5715 | 5200.5715 | 5200.5715 | 5200.5715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11602 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16676.7159 | 0.2 | 0.3 | 26015.6768 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2071.6432 | 2071.6432 | 2071.6432 | 2071.6432 | 2071.6432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11603 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 27896.8547 | 0.2 | 0.3 | 43519.0934 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7223.1508 | 7223.1508 | 7223.1508 | 7223.1508 | 7223.1508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11604 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 20424.8018 | 0.2 | 0.3 | 31862.6908 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11783.2162 | 11783.2162 | 11783.2162 | 11783.2162 | 11783.2162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11605 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16673.0741 | 0.2 | 0.3 | 26009.9955 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4954.9726 | 4954.9726 | 4954.9726 | 4954.9726 | 4954.9726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11606 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16674.7566 | 0.2 | 0.3 | 26012.6203 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5381.1025 | 5381.1025 | 5381.1025 | 5381.1025 | 5381.1025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11607 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16679.2111 | 0.2 | 0.3 | 26019.5694 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5611.9958 | 5611.9958 | 5611.9958 | 5611.9958 | 5611.9958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11608 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16670.5281 | 0.2 | 0.3 | 26006.0238 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7330.4153 | 7330.4153 | 7330.4153 | 7330.4153 | 7330.4153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11609 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 19606.2862 | 0.2 | 0.3 | 30585.8065 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1941.9552 | 1941.9552 | 1941.9552 | 1941.9552 | 1941.9552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11610 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16675.3366 | 0.2 | 0.3 | 26013.5251 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5345.7006 | 5345.7006 | 5345.7006 | 5345.7006 | 5345.7006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11611 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16675.8957 | 0.2 | 0.3 | 26014.3972 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 621.7071 | 621.7071 | 621.7071 | 621.7071 | 621.7071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11612 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16675.6223 | 0.2 | 0.3 | 26013.9707 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9012.7228 | 9012.7228 | 9012.7228 | 9012.7228 | 9012.7228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11613 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16675.4121 | 0.2 | 0.3 | 26013.6429 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5220.9288 | 5220.9288 | 5220.9288 | 5220.9288 | 5220.9288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11614 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 23798.1663 | 0.2 | 0.3 | 37125.1394 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9040.4887 | 9040.4887 | 9040.4887 | 9040.4887 | 9040.4887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11615 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 14811.2434 | 0.2 | 0.3 | 23105.5397 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2610.0192 | 2610.0192 | 2610.0192 | 2610.0192 | 2610.0192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11616 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 21128.835 | 0.2 | 0.3 | 32960.9826 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2239.9108 | 2239.9108 | 2239.9108 | 2239.9108 | 2239.9108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11617 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 20844.6159 | 0.2 | 0.3 | 32517.6008 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.737 | 5200.737 | 5200.737 | 5200.737 | 5200.737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11618 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 20077.4541 | 0.2 | 0.3 | 31320.8283 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2262.5649 | 2262.5649 | 2262.5649 | 2262.5649 | 2262.5649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11619 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 28939.1059 | 0.2 | 0.3 | 45145.0053 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1152.7863 | 1152.7863 | 1152.7863 | 1152.7863 | 1152.7863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11620 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 28304.9409 | 0.2 | 0.3 | 44155.7079 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10943.1077 | 10943.1077 | 10943.1077 | 10943.1077 | 10943.1077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11621 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 17561.2785 | 0.2 | 0.3 | 27395.5944 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10007.4317 | 10007.4317 | 10007.4317 | 10007.4317 | 10007.4317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11622 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 23623.4307 | 0.2 | 0.3 | 36852.5518 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13451.0948 | 13451.0948 | 13451.0948 | 13451.0948 | 13451.0948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11623 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 13090.2544 | 0.2 | 0.3 | 20420.7969 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9143.2611 | 9143.2611 | 9143.2611 | 9143.2611 | 9143.2611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11624 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16897.411 | 0.2 | 0.3 | 26359.9612 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5841.8229 | 5841.8229 | 5841.8229 | 5841.8229 | 5841.8229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11625 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 9139.6603 | 0.2 | 0.3 | 14257.8701 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7414.9154 | 7414.9154 | 7414.9154 | 7414.9154 | 7414.9154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11626 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 8333.3178 | 0.2 | 0.3 | 12999.9758 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6944.8266 | 6944.8266 | 6944.8266 | 6944.8266 | 6944.8266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11627 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 3655.5443 | 0.2 | 0.3 | 5702.6492 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4720.3078 | 4720.3078 | 4720.3078 | 4720.3078 | 4720.3078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11628 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 8609.5859 | 0.2 | 0.3 | 13430.954 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1217.605 | 1217.605 | 1217.605 | 1217.605 | 1217.605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11629 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16691.7186 | 0.2 | 0.3 | 26039.081 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8422.0257 | 8422.0257 | 8422.0257 | 8422.0257 | 8422.0257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11630 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16701.0322 | 0.2 | 0.3 | 26053.6102 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9690.41 | 9690.41 | 9690.41 | 9690.41 | 9690.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11631 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16709.9861 | 0.2 | 0.3 | 26067.5783 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5002.5988 | 5002.5988 | 5002.5988 | 5002.5988 | 5002.5988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11632 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 13902.168 | 0.2 | 0.3 | 21687.3821 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11633 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 20040.6673 | 0.2 | 0.3 | 31263.4409 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11634 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 31392.7335 | 0.2 | 0.3 | 48972.6642 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5715.3591 | 5715.3591 | 5715.3591 | 5715.3591 | 5715.3591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11635 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 27422.8054 | 0.2 | 0.3 | 42779.5764 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7601.9925 | 7601.9925 | 7601.9925 | 7601.9925 | 7601.9925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11636 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 16683.4069 | 0.2 | 0.3 | 26026.1148 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3981.9025 | 3981.9025 | 3981.9025 | 3981.9025 | 3981.9025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11637 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 25015.7127 | 0.2 | 0.3 | 39024.5118 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6925.3621 | 6925.3621 | 6925.3621 | 6925.3621 | 6925.3621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11638 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 26604.1562 | 0.2 | 0.3 | 41502.4837 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4358.0089 | 4358.0089 | 4358.0089 | 4358.0089 | 4358.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11639 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 23070.0053 | 0.2 | 0.3 | 35989.2083 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1051.7946 | 1051.7946 | 1051.7946 | 1051.7946 | 1051.7946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11640 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 24187.3938 | 0.2 | 0.3 | 37732.3343 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3932.3069 | 3932.3069 | 3932.3069 | 3932.3069 | 3932.3069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11641 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 8484.6592 | 0.2 | 0.3 | 13236.0684 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9970.7809 | 9970.7809 | 9970.7809 | 9970.7809 | 9970.7809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11642 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16672.8883 | 0.2 | 0.3 | 26009.7057 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7259.5618 | 7259.5618 | 7259.5618 | 7259.5618 | 7259.5618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11643 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16673.1993 | 0.2 | 0.3 | 26010.191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5669.9074 | 5669.9074 | 5669.9074 | 5669.9074 | 5669.9074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11644 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 12962.4201 | 0.2 | 0.3 | 20221.3754 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7621.8146 | 7621.8146 | 7621.8146 | 7621.8146 | 7621.8146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11645 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 18001.3379 | 0.2 | 0.3 | 28082.0872 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9091.4839 | 9091.4839 | 9091.4839 | 9091.4839 | 9091.4839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11646 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 22974.7713 | 0.2 | 0.3 | 35840.6433 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9049.6109 | 9049.6109 | 9049.6109 | 9049.6109 | 9049.6109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11647 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 31068.6459 | 0.2 | 0.3 | 48467.0877 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8986.8875 | 8986.8875 | 8986.8875 | 8986.8875 | 8986.8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11648 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 23359.9445 | 0.2 | 0.3 | 36441.5134 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8657.2033 | 8657.2033 | 8657.2033 | 8657.2033 | 8657.2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11649 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 31081.8977 | 0.2 | 0.3 | 48487.7604 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8580.6556 | 8580.6556 | 8580.6556 | 8580.6556 | 8580.6556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11650 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 12007.9936 | 0.2 | 0.3 | 18732.47 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8547.2596 | 8547.2596 | 8547.2596 | 8547.2596 | 8547.2596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11651 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 7234.5525 | 0.2 | 0.3 | 11285.902 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8457.4446 | 8457.4446 | 8457.4446 | 8457.4446 | 8457.4446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11652 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 7565.0744 | 0.2 | 0.3 | 11801.5161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8379.9072 | 8379.9072 | 8379.9072 | 8379.9072 | 8379.9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11653 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 8333.3178 | 0.2 | 0.3 | 12999.9758 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6134.3332 | 6134.3332 | 6134.3332 | 6134.3332 | 6134.3332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11654 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 21079.1961 | 0.2 | 0.3 | 32883.5459 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7392.0501 | 7392.0501 | 7392.0501 | 7392.0501 | 7392.0501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11655 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 17898.6712 | 0.2 | 0.3 | 27921.9271 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10893.9667 | 10893.9667 | 10893.9667 | 10893.9667 | 10893.9667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11656 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16682.168 | 0.2 | 0.3 | 26024.1821 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4735.1161 | 4735.1161 | 4735.1161 | 4735.1161 | 4735.1161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11657 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 16742.9244 | 0.2 | 0.3 | 26118.9621 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4718.4484 | 4718.4484 | 4718.4484 | 4718.4484 | 4718.4484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11658 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 16729.4066 | 0.2 | 0.3 | 26097.8743 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5057.8243 | 5057.8243 | 5057.8243 | 5057.8243 | 5057.8243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11659 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 16677.2627 | 0.2 | 0.3 | 26016.5298 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11660 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 19866.4121 | 0.2 | 0.3 | 30991.6029 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11661 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 30159.9129 | 0.2 | 0.3 | 47049.4642 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3660.5811 | 3660.5811 | 3660.5811 | 3660.5811 | 3660.5811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11662 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7469.5541 | 7469.5541 | 7469.5541 | 7469.5541 | 7469.5541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11663 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 10867.3044 | 0.2 | 0.3 | 16952.9949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7127.434 | 7127.434 | 7127.434 | 7127.434 | 7127.434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11664 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 23271.605 | 0.2 | 0.3 | 36303.7038 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6139.5085 | 6139.5085 | 6139.5085 | 6139.5085 | 6139.5085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11665 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 15271.9149 | 0.2 | 0.3 | 23824.1872 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5349.5842 | 5349.5842 | 5349.5842 | 5349.5842 | 5349.5842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11666 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 16988.9576 | 0.2 | 0.3 | 26502.7739 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 933.2008 | 933.2008 | 933.2008 | 933.2008 | 933.2008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11667 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 16672.5145 | 0.2 | 0.3 | 26009.1226 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3983.4297 | 3983.4297 | 3983.4297 | 3983.4297 | 3983.4297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11668 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 3290.0896 | 0.2 | 0.3 | 5132.5398 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7666 | 5201.7666 | 5201.7666 | 5201.7666 | 5201.7666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11669 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 13402.2741 | 0.2 | 0.3 | 20907.5476 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.399 | 5200.399 | 5200.399 | 5200.399 | 5200.399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11670 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16672.3415 | 0.2 | 0.3 | 26008.8527 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5287.82 | 5287.82 | 5287.82 | 5287.82 | 5287.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11671 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16672.5133 | 0.2 | 0.3 | 26009.1208 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5836.2293 | 5836.2293 | 5836.2293 | 5836.2293 | 5836.2293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11672 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16672.2412 | 0.2 | 0.3 | 26008.6963 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11673 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 31485.5077 | 0.2 | 0.3 | 49117.3921 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4026 | 5201.4026 | 5201.4026 | 5201.4026 | 5201.4026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11674 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 16673.2723 | 0.2 | 0.3 | 26010.3047 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11675 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16673.1617 | 0.2 | 0.3 | 26010.1322 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 247.6672 | 247.6672 | 247.6672 | 247.6672 | 247.6672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11676 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16673.1517 | 0.2 | 0.3 | 26010.1166 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 742.2084 | 742.2084 | 742.2084 | 742.2084 | 742.2084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11677 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 11748.805 | 0.2 | 0.3 | 18328.1358 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2096.7799 | 2096.7799 | 2096.7799 | 2096.7799 | 2096.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11678 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16670.2684 | 0.2 | 0.3 | 26005.6187 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 57.3437 | 57.3437 | 57.3437 | 57.3437 | 57.3437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11679 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16671.3934 | 0.2 | 0.3 | 26007.3737 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9487.5326 | 9487.5326 | 9487.5326 | 9487.5326 | 9487.5326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11680 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16175.4289 | 0.2 | 0.3 | 25233.669 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.9361 | 9778.9361 | 9778.9361 | 9778.9361 | 9778.9361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11681 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 497.3331 | 0.2 | 0.3 | 775.8396 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8789.4829 | 8789.4829 | 8789.4829 | 8789.4829 | 8789.4829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11682 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16674.8613 | 0.2 | 0.3 | 26012.7837 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8979.2527 | 8979.2527 | 8979.2527 | 8979.2527 | 8979.2527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11683 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16670.5544 | 0.2 | 0.3 | 26006.0649 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7838.8 | 7838.8 | 7838.8 | 7838.8 | 7838.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11684 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16672.0044 | 0.2 | 0.3 | 26008.3269 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5120.9103 | 5120.9103 | 5120.9103 | 5120.9103 | 5120.9103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11685 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16670.1873 | 0.2 | 0.3 | 26005.4922 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3993.6577 | 3993.6577 | 3993.6577 | 3993.6577 | 3993.6577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11686 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 5611.4045 | 0.2 | 0.3 | 8753.791 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5493.1566 | 5493.1566 | 5493.1566 | 5493.1566 | 5493.1566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11687 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 18046.5435 | 0.2 | 0.3 | 28152.6078 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3509 | 5202.3509 | 5202.3509 | 5202.3509 | 5202.3509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11688 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16781.9757 | 0.2 | 0.3 | 26179.8821 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9829.9397 | 9829.9397 | 9829.9397 | 9829.9397 | 9829.9397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11689 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16831.47 | 0.2 | 0.3 | 26257.0932 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2287.1734 | 2287.1734 | 2287.1734 | 2287.1734 | 2287.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11690 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 17665.9963 | 0.2 | 0.3 | 27558.9542 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 467.8043 | 467.8043 | 467.8043 | 467.8043 | 467.8043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11691 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 1960.3673 | 0.2 | 0.3 | 3058.173 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10351.3252 | 10351.3252 | 10351.3252 | 10351.3252 | 10351.3252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11692 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 5794.579 | 0.2 | 0.3 | 9039.5432 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6529.7171 | 6529.7171 | 6529.7171 | 6529.7171 | 6529.7171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11693 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 22183.4988 | 0.2 | 0.3 | 34606.2581 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5492.2428 | 5492.2428 | 5492.2428 | 5492.2428 | 5492.2428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11694 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16671.3763 | 0.2 | 0.3 | 26007.3471 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 685.7716 | 685.7716 | 685.7716 | 685.7716 | 685.7716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11695 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 25061.6256 | 0.2 | 0.3 | 39096.1359 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11696 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 9164.6113 | 0.2 | 0.3 | 14296.7937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7574.1073 | 7574.1073 | 7574.1073 | 7574.1073 | 7574.1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11697 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16670.4751 | 0.2 | 0.3 | 26005.9412 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11828.4337 | 11828.4337 | 11828.4337 | 11828.4337 | 11828.4337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11698 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 19699.7923 | 0.2 | 0.3 | 30731.6759 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5125.1905 | 5125.1905 | 5125.1905 | 5125.1905 | 5125.1905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11699 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 16930.2353 | 0.2 | 0.3 | 26411.167 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5316.7091 | 5316.7091 | 5316.7091 | 5316.7091 | 5316.7091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11700 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 3913.2507 | 0.2 | 0.3 | 6104.6711 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5744.0607 | 5744.0607 | 5744.0607 | 5744.0607 | 5744.0607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11701 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 7137.325 | 0.2 | 0.3 | 11134.227 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9271.9947 | 9271.9947 | 9271.9947 | 9271.9947 | 9271.9947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11702 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 20585.8889 | 0.2 | 0.3 | 32113.9867 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7248.8233 | 7248.8233 | 7248.8233 | 7248.8233 | 7248.8233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11703 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 17880.6713 | 0.2 | 0.3 | 27893.8472 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6593.0421 | 6593.0421 | 6593.0421 | 6593.0421 | 6593.0421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11704 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 19605.796 | 0.2 | 0.3 | 30585.0418 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8849.2856 | 8849.2856 | 8849.2856 | 8849.2856 | 8849.2856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11705 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 29144.8723 | 0.2 | 0.3 | 45466.0007 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7156.5076 | 7156.5076 | 7156.5076 | 7156.5076 | 7156.5076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11706 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 16671.6163 | 0.2 | 0.3 | 26007.7215 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11707 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 15910.713 | 0.2 | 0.3 | 24820.7123 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9106.6767 | 9106.6767 | 9106.6767 | 9106.6767 | 9106.6767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11708 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 3341.0304 | 0.2 | 0.3 | 5212.0074 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6556.7774 | 6556.7774 | 6556.7774 | 6556.7774 | 6556.7774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11709 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 16976.2624 | 0.2 | 0.3 | 26482.9693 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11710 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 16674.6079 | 0.2 | 0.3 | 26012.3884 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1454 | 5200.1454 | 5200.1454 | 5200.1454 | 5200.1454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11711 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 9877.1927 | 0.2 | 0.3 | 15408.4207 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0174 | 5200.0174 | 5200.0174 | 5200.0174 | 5200.0174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11712 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 12943.6903 | 0.2 | 0.3 | 20192.1568 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3553.1459 | 3553.1459 | 3553.1459 | 3553.1459 | 3553.1459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11713 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 20104.3667 | 0.2 | 0.3 | 31362.812 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11922.4222 | 11922.4222 | 11922.4222 | 11922.4222 | 11922.4222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11714 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 32019.6044 | 0.2 | 0.3 | 49950.5829 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6185.9395 | 6185.9395 | 6185.9395 | 6185.9395 | 6185.9395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11715 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 26283.9497 | 0.2 | 0.3 | 41002.9615 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6166.5043 | 6166.5043 | 6166.5043 | 6166.5043 | 6166.5043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11716 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 24878.1693 | 0.2 | 0.3 | 38809.9441 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 626.2613 | 626.2613 | 626.2613 | 626.2613 | 626.2613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11717 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 23976.3081 | 0.2 | 0.3 | 37403.0407 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7587.1531 | 7587.1531 | 7587.1531 | 7587.1531 | 7587.1531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11718 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 28133.8333 | 0.2 | 0.3 | 43888.7799 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.117 | 5200.117 | 5200.117 | 5200.117 | 5200.117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11719 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 25498.4051 | 0.2 | 0.3 | 39777.512 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5957.7133 | 5957.7133 | 5957.7133 | 5957.7133 | 5957.7133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11720 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 1886.8067 | 0.2 | 0.3 | 2943.4185 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5209.814 | 5209.814 | 5209.814 | 5209.814 | 5209.814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11721 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 17208.9243 | 0.2 | 0.3 | 26845.922 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4393.0112 | 4393.0112 | 4393.0112 | 4393.0112 | 4393.0112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11722 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 3269.977 | 0.2 | 0.3 | 5101.1641 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3089.2109 | 3089.2109 | 3089.2109 | 3089.2109 | 3089.2109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11723 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16669.8101 | 0.2 | 0.3 | 26004.9037 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1591.9679 | 1591.9679 | 1591.9679 | 1591.9679 | 1591.9679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11724 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16670.9274 | 0.2 | 0.3 | 26006.6467 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 24.5033 | 24.5033 | 24.5033 | 24.5033 | 24.5033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11725 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 9361.7512 | 0.2 | 0.3 | 14604.3319 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2630.4411 | 2630.4411 | 2630.4411 | 2630.4411 | 2630.4411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11726 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 7311.1821 | 0.2 | 0.3 | 11405.444 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3730.8248 | 3730.8248 | 3730.8248 | 3730.8248 | 3730.8248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11727 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 18731.9252 | 0.2 | 0.3 | 29221.8033 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5349.8629 | 5349.8629 | 5349.8629 | 5349.8629 | 5349.8629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11728 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16717.0395 | 0.2 | 0.3 | 26078.5816 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5691.0354 | 5691.0354 | 5691.0354 | 5691.0354 | 5691.0354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11729 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 17398.9892 | 0.2 | 0.3 | 27142.4232 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4614.6868 | 4614.6868 | 4614.6868 | 4614.6868 | 4614.6868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11730 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16734.5586 | 0.2 | 0.3 | 26105.9114 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3577.4499 | 3577.4499 | 3577.4499 | 3577.4499 | 3577.4499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11731 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 17484.4571 | 0.2 | 0.3 | 27275.7531 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4632.7589 | 4632.7589 | 4632.7589 | 4632.7589 | 4632.7589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11732 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 15695.5575 | 0.2 | 0.3 | 24485.0698 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4732 | 5200.4732 | 5200.4732 | 5200.4732 | 5200.4732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11733 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16491.0239 | 0.2 | 0.3 | 25725.9973 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5223.1975 | 5223.1975 | 5223.1975 | 5223.1975 | 5223.1975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11734 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16937.7843 | 0.2 | 0.3 | 26422.9436 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9131.3845 | 9131.3845 | 9131.3845 | 9131.3845 | 9131.3845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11735 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 17196.7186 | 0.2 | 0.3 | 26826.881 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10672.0022 | 10672.0022 | 10672.0022 | 10672.0022 | 10672.0022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11736 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 17786.4666 | 0.2 | 0.3 | 27746.8879 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7135.1638 | 7135.1638 | 7135.1638 | 7135.1638 | 7135.1638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11737 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 28396.1079 | 0.2 | 0.3 | 44297.9283 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4688.1833 | 4688.1833 | 4688.1833 | 4688.1833 | 4688.1833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11738 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 17745.6923 | 0.2 | 0.3 | 27683.28 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9307.9146 | 9307.9146 | 9307.9146 | 9307.9146 | 9307.9146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11739 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 9111.5423 | 0.2 | 0.3 | 14214.006 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2466 | 5200.2466 | 5200.2466 | 5200.2466 | 5200.2466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11740 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 5004.9967 | 0.2 | 0.3 | 7807.7949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11741 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 11673.7181 | 0.2 | 0.3 | 18211.0002 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3202 | 5200.3202 | 5200.3202 | 5200.3202 | 5200.3202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11742 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16673.0286 | 0.2 | 0.3 | 26009.9246 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3288.2252 | 3288.2252 | 3288.2252 | 3288.2252 | 3288.2252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11743 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 16677.8095 | 0.2 | 0.3 | 26017.3828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1560.6207 | 1560.6207 | 1560.6207 | 1560.6207 | 1560.6207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11744 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 16677.3866 | 0.2 | 0.3 | 26016.7231 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1401.0556 | 1401.0556 | 1401.0556 | 1401.0556 | 1401.0556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11745 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 5879.8363 | 0.2 | 0.3 | 9172.5447 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 452.736 | 452.736 | 452.736 | 452.736 | 452.736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11746 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 27512.1285 | 0.2 | 0.3 | 42918.9204 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1600.0676 | 1600.0676 | 1600.0676 | 1600.0676 | 1600.0676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11747 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 31373.2579 | 0.2 | 0.3 | 48942.2824 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9559 | 5202.9559 | 5202.9559 | 5202.9559 | 5202.9559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11748 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 19661.2331 | 0.2 | 0.3 | 30671.5236 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6988 | 5201.6988 | 5201.6988 | 5201.6988 | 5201.6988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11749 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 15180.5508 | 0.2 | 0.3 | 23681.6592 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5568.2066 | 5568.2066 | 5568.2066 | 5568.2066 | 5568.2066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11750 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 17845.705 | 0.2 | 0.3 | 27839.2998 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11116.5472 | 11116.5472 | 11116.5472 | 11116.5472 | 11116.5472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11751 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 16675.0893 | 0.2 | 0.3 | 26013.1393 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10924.1274 | 10924.1274 | 10924.1274 | 10924.1274 | 10924.1274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11752 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 16674.6904 | 0.2 | 0.3 | 26012.517 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10263.342 | 10263.342 | 10263.342 | 10263.342 | 10263.342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11753 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 16674.8021 | 0.2 | 0.3 | 26012.6912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5531.2597 | 5531.2597 | 5531.2597 | 5531.2597 | 5531.2597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11754 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 26558.2423 | 0.2 | 0.3 | 41430.858 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7774.6363 | 7774.6363 | 7774.6363 | 7774.6363 | 7774.6363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11755 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 31779.9219 | 0.2 | 0.3 | 49576.6782 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11427.6371 | 11427.6371 | 11427.6371 | 11427.6371 | 11427.6371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11756 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5428.1082 | 5428.1082 | 5428.1082 | 5428.1082 | 5428.1082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11757 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 7464.6599 | 0.2 | 0.3 | 11644.8695 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 959.6484 | 959.6484 | 959.6484 | 959.6484 | 959.6484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11758 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 20926.9187 | 0.2 | 0.3 | 32645.9932 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5549.2126 | 5549.2126 | 5549.2126 | 5549.2126 | 5549.2126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11759 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 10097.7025 | 0.2 | 0.3 | 15752.4158 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8245.1187 | 8245.1187 | 8245.1187 | 8245.1187 | 8245.1187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11760 | DAVIE | 70601 | Public | 2030 | 5 | Swales | 66.6667 | 31849.5814 | 0.2 | 0.3 | 49685.347 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.8082 | 9778.8082 | 9778.8082 | 9778.8082 | 9778.8082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11761 | DAVIE | 70601 | Public | 2030 | 5 | Swales | 66.6667 | 24668.4717 | 0.2 | 0.3 | 38482.8158 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8909.9435 | 8909.9435 | 8909.9435 | 8909.9435 | 8909.9435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11762 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16673.1617 | 0.2 | 0.3 | 26010.1322 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1433.6669 | 1433.6669 | 1433.6669 | 1433.6669 | 1433.6669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11763 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16673.6316 | 0.2 | 0.3 | 26010.8653 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2933.1188 | 2933.1188 | 2933.1188 | 2933.1188 | 2933.1188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11764 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 30979.6255 | 0.2 | 0.3 | 48328.2157 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 792.653 | 792.653 | 792.653 | 792.653 | 792.653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11765 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 32754.8362 | 0.2 | 0.3 | 51097.5445 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11181.7081 | 11181.7081 | 11181.7081 | 11181.7081 | 11181.7081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11766 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 33348.4324 | 0.2 | 0.3 | 52023.5545 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 234.2325 | 234.2325 | 234.2325 | 234.2325 | 234.2325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11767 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 21089.5496 | 0.2 | 0.3 | 32899.6974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4291.1254 | 4291.1254 | 4291.1254 | 4291.1254 | 4291.1254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11768 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 20201.5064 | 0.2 | 0.3 | 31514.35 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1555.6214 | 1555.6214 | 1555.6214 | 1555.6214 | 1555.6214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11769 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 27189.4519 | 0.2 | 0.3 | 42415.545 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11770 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 31116.039 | 0.2 | 0.3 | 48541.0208 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11771 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 31064.3163 | 0.2 | 0.3 | 48460.3335 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2127.5495 | 2127.5495 | 2127.5495 | 2127.5495 | 2127.5495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11772 | COUNTY REGIONAL FACILITY | 110600 | Public | 2030 | 5 | Swales | 66.6667 | 2775.4124 | 0.2 | 0.3 | 4329.6433 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6359.7852 | 6359.7852 | 6359.7852 | 6359.7852 | 6359.7852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11773 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16696.6743 | 0.2 | 0.3 | 26046.8119 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6295.1328 | 6295.1328 | 6295.1328 | 6295.1328 | 6295.1328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11774 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 6652.2537 | 0.2 | 0.3 | 10377.5157 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4141.0537 | 4141.0537 | 4141.0537 | 4141.0537 | 4141.0537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11775 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 12777.3835 | 0.2 | 0.3 | 19932.7183 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1343.4911 | 1343.4911 | 1343.4911 | 1343.4911 | 1343.4911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11776 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16696.4119 | 0.2 | 0.3 | 26046.4026 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2111 | 5200.2111 | 5200.2111 | 5200.2111 | 5200.2111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11777 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16673.8887 | 0.2 | 0.3 | 26011.2664 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7854.0091 | 7854.0091 | 7854.0091 | 7854.0091 | 7854.0091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11778 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 16678.0829 | 0.2 | 0.3 | 26017.8093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9971.1442 | 9971.1442 | 9971.1442 | 9971.1442 | 9971.1442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11779 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 16676.9893 | 0.2 | 0.3 | 26016.1033 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5817.2539 | 5817.2539 | 5817.2539 | 5817.2539 | 5817.2539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11780 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 10890.1191 | 0.2 | 0.3 | 16988.5858 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1150.7273 | 1150.7273 | 1150.7273 | 1150.7273 | 1150.7273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11781 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.152 | 5200.152 | 5200.152 | 5200.152 | 5200.152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11782 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 16570.2139 | 0.2 | 0.3 | 25849.5337 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11783 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 754.9103 | 0.2 | 0.3 | 1177.66 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11784 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 7163.9847 | 0.2 | 0.3 | 11175.8162 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5433.4503 | 5433.4503 | 5433.4503 | 5433.4503 | 5433.4503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11785 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 17376.1083 | 0.2 | 0.3 | 27106.729 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2406 | 5200.2406 | 5200.2406 | 5200.2406 | 5200.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11786 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 19699.7317 | 0.2 | 0.3 | 30731.5815 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11787 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 16138.8139 | 0.2 | 0.3 | 25176.5496 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3363 | 5200.3363 | 5200.3363 | 5200.3363 | 5200.3363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11788 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 3884.2682 | 0.2 | 0.3 | 6059.4584 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3054.7488 | 3054.7488 | 3054.7488 | 3054.7488 | 3054.7488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11789 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 22778.1699 | 0.2 | 0.3 | 35533.945 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12443.4974 | 12443.4974 | 12443.4974 | 12443.4974 | 12443.4974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11790 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 13954.2739 | 0.2 | 0.3 | 21768.6672 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5459.2954 | 5459.2954 | 5459.2954 | 5459.2954 | 5459.2954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11791 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 8040.2869 | 0.2 | 0.3 | 12542.8476 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5514.2005 | 5514.2005 | 5514.2005 | 5514.2005 | 5514.2005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11792 | DAVIE | 70601 | Public | 2030 | 5 | Swales | 66.6667 | 17700.2248 | 0.2 | 0.3 | 27612.3507 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5561.669 | 5561.669 | 5561.669 | 5561.669 | 5561.669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11793 | DAVIE | 70601 | Public | 2030 | 5 | Swales | 66.6667 | 16820.2545 | 0.2 | 0.3 | 26239.597 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5594.3349 | 5594.3349 | 5594.3349 | 5594.3349 | 5594.3349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11794 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 29101.2753 | 0.2 | 0.3 | 45397.9894 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5647.8938 | 5647.8938 | 5647.8938 | 5647.8938 | 5647.8938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11795 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 16670.3168 | 0.2 | 0.3 | 26005.6942 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4669.6199 | 4669.6199 | 4669.6199 | 4669.6199 | 4669.6199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11796 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 17516.1859 | 0.2 | 0.3 | 27325.25 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9574.2879 | 9574.2879 | 9574.2879 | 9574.2879 | 9574.2879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11797 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 19984.5044 | 0.2 | 0.3 | 31175.8269 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6264.4461 | 6264.4461 | 6264.4461 | 6264.4461 | 6264.4461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11798 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16678.0864 | 0.2 | 0.3 | 26017.8148 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1607 | 5200.1607 | 5200.1607 | 5200.1607 | 5200.1607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11799 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16436.1153 | 0.2 | 0.3 | 25640.3399 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11800 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11801 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16671.8161 | 0.2 | 0.3 | 26008.0332 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.5906 | 9776.5906 | 9776.5906 | 9776.5906 | 9776.5906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11802 | COUNTY REGIONAL FACILITY | 110600 | Public | 2030 | 5 | Swales | 66.6667 | 4463.2234 | 0.2 | 0.3 | 6962.6285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0058 | 5200.0058 | 5200.0058 | 5200.0058 | 5200.0058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11803 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 10338.7463 | 0.2 | 0.3 | 16128.4443 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11804 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 18071.5806 | 0.2 | 0.3 | 28191.6657 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.133 | 5200.133 | 5200.133 | 5200.133 | 5200.133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11805 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 18562.2486 | 0.2 | 0.3 | 28957.1078 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7733.3262 | 7733.3262 | 7733.3262 | 7733.3262 | 7733.3262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11806 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 8876.0835 | 0.2 | 0.3 | 13846.6903 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14272.5875 | 14272.5875 | 14272.5875 | 14272.5875 | 14272.5875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11807 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16696.4009 | 0.2 | 0.3 | 26046.3854 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9496.8592 | 9496.8592 | 9496.8592 | 9496.8592 | 9496.8592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11808 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 17560.1935 | 0.2 | 0.3 | 27393.9018 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5038.4868 | 5038.4868 | 5038.4868 | 5038.4868 | 5038.4868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11809 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 12887.6873 | 0.2 | 0.3 | 20104.7921 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10487.8679 | 10487.8679 | 10487.8679 | 10487.8679 | 10487.8679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11810 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 14652.6319 | 0.2 | 0.3 | 22858.1058 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3598 | 5200.3598 | 5200.3598 | 5200.3598 | 5200.3598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11811 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 15570.4699 | 0.2 | 0.3 | 24289.933 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4109.1176 | 4109.1176 | 4109.1176 | 4109.1176 | 4109.1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11812 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 2283.8963 | 0.2 | 0.3 | 3562.8782 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1637 | 5200.1637 | 5200.1637 | 5200.1637 | 5200.1637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11813 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6624 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3961 | 5200.3961 | 5200.3961 | 5200.3961 | 5200.3961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11814 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 3910.0567 | 0.2 | 0.3 | 6099.6885 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.298 | 5200.298 | 5200.298 | 5200.298 | 5200.298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11815 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 15620.107 | 0.2 | 0.3 | 24367.3669 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8346 | 5200.8346 | 5200.8346 | 5200.8346 | 5200.8346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11816 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 16714.3172 | 0.2 | 0.3 | 26074.3348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5208.6478 | 5208.6478 | 5208.6478 | 5208.6478 | 5208.6478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11817 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 19727.272 | 0.2 | 0.3 | 30774.5443 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6667.3479 | 6667.3479 | 6667.3479 | 6667.3479 | 6667.3479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11818 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 17235.2902 | 0.2 | 0.3 | 26887.0527 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8467.3264 | 8467.3264 | 8467.3264 | 8467.3264 | 8467.3264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11819 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 11898.338 | 0.2 | 0.3 | 18561.4073 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9649.3738 | 9649.3738 | 9649.3738 | 9649.3738 | 9649.3738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11820 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 4781.1528 | 0.2 | 0.3 | 7458.5984 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13128.0094 | 13128.0094 | 13128.0094 | 13128.0094 | 13128.0094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11821 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 16717.3642 | 0.2 | 0.3 | 26079.0882 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 278.4376 | 278.4376 | 278.4376 | 278.4376 | 278.4376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11822 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 16740.7363 | 0.2 | 0.3 | 26115.5487 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4192.2836 | 4192.2836 | 4192.2836 | 4192.2836 | 4192.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11823 | DAVIE | 70601 | Public | 2030 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7288.0994 | 7288.0994 | 7288.0994 | 7288.0994 | 7288.0994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11824 | DAVIE | 70601 | Public | 2030 | 5 | Swales | 66.6667 | 16672.6158 | 0.2 | 0.3 | 26009.2806 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6141.1822 | 6141.1822 | 6141.1822 | 6141.1822 | 6141.1822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11825 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 41048.7889 | 0.2 | 0.3 | 64036.1106 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3366 | 5200.3366 | 5200.3366 | 5200.3366 | 5200.3366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11826 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 33353.0547 | 0.2 | 0.3 | 52030.7654 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11827 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 19053.7662 | 0.2 | 0.3 | 29723.8753 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11828 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 19667.3073 | 0.2 | 0.3 | 30680.9993 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.4499 | 9776.4499 | 9776.4499 | 9776.4499 | 9776.4499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11829 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16675.1373 | 0.2 | 0.3 | 26013.2141 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9782 | 5199.9782 | 5199.9782 | 5199.9782 | 5199.9782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11830 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16828.2049 | 0.2 | 0.3 | 26251.9997 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11831 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 21118.9463 | 0.2 | 0.3 | 32945.5562 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1694 | 5200.1694 | 5200.1694 | 5200.1694 | 5200.1694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11832 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 18690.0019 | 0.2 | 0.3 | 29156.403 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7782.2989 | 7782.2989 | 7782.2989 | 7782.2989 | 7782.2989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11833 | COUNTY REGIONAL FACILITY | 110600 | Public | 2030 | 5 | Swales | 66.6667 | 16780.7395 | 0.2 | 0.3 | 26177.9536 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11628.0474 | 11628.0474 | 11628.0474 | 11628.0474 | 11628.0474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11834 | COUNTY REGIONAL FACILITY | 110600 | Public | 2030 | 5 | Swales | 66.6667 | 1602.9519 | 0.2 | 0.3 | 2500.6049 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8025.378 | 8025.378 | 8025.378 | 8025.378 | 8025.378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11835 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16676.6438 | 0.2 | 0.3 | 26015.5643 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2218.9924 | 2218.9924 | 2218.9924 | 2218.9924 | 2218.9924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11836 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16779.6065 | 0.2 | 0.3 | 26176.1862 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6129.2224 | 6129.2224 | 6129.2224 | 6129.2224 | 6129.2224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11837 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16697.0694 | 0.2 | 0.3 | 26047.4283 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10.9865 | 10.9865 | 10.9865 | 10.9865 | 10.9865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11838 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 1666.0061 | 0.2 | 0.3 | 2598.9695 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5212.7669 | 5212.7669 | 5212.7669 | 5212.7669 | 5212.7669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11839 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 14552.8093 | 0.2 | 0.3 | 22702.3825 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7048 | 5201.7048 | 5201.7048 | 5201.7048 | 5201.7048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11840 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 21731.9067 | 0.2 | 0.3 | 33901.7744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7040.6991 | 7040.6991 | 7040.6991 | 7040.6991 | 7040.6991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11841 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 14659.3909 | 0.2 | 0.3 | 22868.6499 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6863 | 5202.6863 | 5202.6863 | 5202.6863 | 5202.6863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11842 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 4201.2145 | 0.2 | 0.3 | 6553.8946 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11843 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 12759.7956 | 0.2 | 0.3 | 19905.2811 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11844 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 20642.6575 | 0.2 | 0.3 | 32202.5456 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11845 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 16936.7465 | 0.2 | 0.3 | 26421.3245 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11846 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 11799.793 | 0.2 | 0.3 | 18407.6771 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11847 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 16679.9967 | 0.2 | 0.3 | 26020.7949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11848 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11849 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 7370.1423 | 0.2 | 0.3 | 11497.4219 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9699.3419 | 9699.3419 | 9699.3419 | 9699.3419 | 9699.3419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11850 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 9309.8463 | 0.2 | 0.3 | 14523.3602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1349.0827 | 1349.0827 | 1349.0827 | 1349.0827 | 1349.0827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11851 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 15228.0016 | 0.2 | 0.3 | 23755.6825 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10375.7661 | 10375.7661 | 10375.7661 | 10375.7661 | 10375.7661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11852 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 24938.5749 | 0.2 | 0.3 | 38904.1769 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12107.0583 | 12107.0583 | 12107.0583 | 12107.0583 | 12107.0583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11853 | DAVIE | 70601 | Public | 2030 | 5 | Swales | 66.6667 | 31344.6361 | 0.2 | 0.3 | 48897.6324 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4691.6073 | 4691.6073 | 4691.6073 | 4691.6073 | 4691.6073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11854 | DAVIE | 70601 | Public | 2030 | 5 | Swales | 66.6667 | 25163.7201 | 0.2 | 0.3 | 39255.4033 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4718.0421 | 4718.0421 | 4718.0421 | 4718.0421 | 4718.0421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11855 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 24367.8879 | 0.2 | 0.3 | 38013.9052 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11207.5501 | 11207.5501 | 11207.5501 | 11207.5501 | 11207.5501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11856 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16649.9219 | 0.2 | 0.3 | 25973.8781 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2881.7502 | 2881.7502 | 2881.7502 | 2881.7502 | 2881.7502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11857 | DAVIE | 70104 | Private | 2030 | 5 | Swales | 66.6667 | 18843.0301 | 0.2 | 0.3 | 29395.1269 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1482.2722 | 1482.2722 | 1482.2722 | 1482.2722 | 1482.2722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11858 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 30686.2021 | 0.2 | 0.3 | 47870.4752 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13231.6531 | 13231.6531 | 13231.6531 | 13231.6531 | 13231.6531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11859 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 26904.1041 | 0.2 | 0.3 | 41970.4023 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2196 | 5200.2196 | 5200.2196 | 5200.2196 | 5200.2196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11860 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 18744.4265 | 0.2 | 0.3 | 29241.3054 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9251.9847 | 9251.9847 | 9251.9847 | 9251.9847 | 9251.9847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11861 | COUNTY REGIONAL FACILITY | 110600 | Public | 2030 | 5 | Swales | 66.6667 | 6.0866 | 0.2 | 0.3 | 9.4951 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5270.5184 | 5270.5184 | 5270.5184 | 5270.5184 | 5270.5184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11862 | COUNTY REGIONAL FACILITY | 110600 | Public | 2030 | 5 | Swales | 66.6667 | 5349.4616 | 0.2 | 0.3 | 8345.1601 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1578.2804 | 1578.2804 | 1578.2804 | 1578.2804 | 1578.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11863 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 24531.9502 | 0.2 | 0.3 | 38269.8423 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6131.5329 | 6131.5329 | 6131.5329 | 6131.5329 | 6131.5329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11864 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16741.7585 | 0.2 | 0.3 | 26117.1433 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1224 | 5200.1224 | 5200.1224 | 5200.1224 | 5200.1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11865 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 18101.1609 | 0.2 | 0.3 | 28237.811 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11866 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16677.6967 | 0.2 | 0.3 | 26017.2069 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11867 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16679.1765 | 0.2 | 0.3 | 26019.5154 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9455.2638 | 9455.2638 | 9455.2638 | 9455.2638 | 9455.2638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11868 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 11169.098 | 0.2 | 0.3 | 17423.7929 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0484 | 5200.0484 | 5200.0484 | 5200.0484 | 5200.0484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11869 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16675.0755 | 0.2 | 0.3 | 26013.1177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11870 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 11370.7707 | 0.2 | 0.3 | 17738.4023 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11773.3714 | 11773.3714 | 11773.3714 | 11773.3714 | 11773.3714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11871 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 2387.5436 | 0.2 | 0.3 | 3724.568 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6557.748 | 6557.748 | 6557.748 | 6557.748 | 6557.748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11872 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 27440.5451 | 0.2 | 0.3 | 42807.2503 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 90.1373 | 90.1373 | 90.1373 | 90.1373 | 90.1373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11873 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6313 | 0.2 | 0.3 | 25999.9448 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9543.6859 | 9543.6859 | 9543.6859 | 9543.6859 | 9543.6859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11874 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 19461.3197 | 0.2 | 0.3 | 30359.6588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 35.3729 | 35.3729 | 35.3729 | 35.3729 | 35.3729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11875 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 16679.5557 | 0.2 | 0.3 | 26020.1068 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9260.0853 | 9260.0853 | 9260.0853 | 9260.0853 | 9260.0853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11876 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1712.9649 | 1712.9649 | 1712.9649 | 1712.9649 | 1712.9649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11877 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 206.0106 | 0.2 | 0.3 | 321.3765 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9768.6359 | 9768.6359 | 9768.6359 | 9768.6359 | 9768.6359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11878 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 16474.3012 | 0.2 | 0.3 | 25699.9099 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 609.8274 | 609.8274 | 609.8274 | 609.8274 | 609.8274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11879 | DAVIE | 70601 | Public | 2030 | 5 | Swales | 66.6667 | 16673.1263 | 0.2 | 0.3 | 26010.077 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2091.7935 | 2091.7935 | 2091.7935 | 2091.7935 | 2091.7935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11880 | DAVIE | 70601 | Public | 2030 | 5 | Swales | 66.6667 | 16666.8484 | 0.2 | 0.3 | 26000.2835 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2603.1751 | 2603.1751 | 2603.1751 | 2603.1751 | 2603.1751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11881 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 24025.3129 | 0.2 | 0.3 | 37479.4882 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2006.4446 | 2006.4446 | 2006.4446 | 2006.4446 | 2006.4446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11882 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 8313.1555 | 0.2 | 0.3 | 12968.5226 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1469.65 | 1469.65 | 1469.65 | 1469.65 | 1469.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11883 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 17918.8792 | 0.2 | 0.3 | 27953.4516 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1275.1824 | 1275.1824 | 1275.1824 | 1275.1824 | 1275.1824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11884 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 8455.3761 | 0.2 | 0.3 | 13190.3868 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 333.5161 | 333.5161 | 333.5161 | 333.5161 | 333.5161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11885 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 17495.7104 | 0.2 | 0.3 | 27293.3082 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3473.2418 | 3473.2418 | 3473.2418 | 3473.2418 | 3473.2418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11886 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3420.1011 | 3420.1011 | 3420.1011 | 3420.1011 | 3420.1011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11887 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 16676.1691 | 0.2 | 0.3 | 26014.8237 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 459.8316 | 459.8316 | 459.8316 | 459.8316 | 459.8316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11888 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 14075.2007 | 0.2 | 0.3 | 21957.313 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3228.3504 | 3228.3504 | 3228.3504 | 3228.3504 | 3228.3504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11889 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 17089.9807 | 0.2 | 0.3 | 26660.3698 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5683.6412 | 5683.6412 | 5683.6412 | 5683.6412 | 5683.6412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11890 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16761.9679 | 0.2 | 0.3 | 26148.6699 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8239.9455 | 8239.9455 | 8239.9455 | 8239.9455 | 8239.9455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11891 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16822.5006 | 0.2 | 0.3 | 26243.1009 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12.8341 | 12.8341 | 12.8341 | 12.8341 | 12.8341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11892 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16676.1537 | 0.2 | 0.3 | 26014.7998 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12473.7756 | 12473.7756 | 12473.7756 | 12473.7756 | 12473.7756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11893 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16673.1103 | 0.2 | 0.3 | 26010.0521 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1672.1568 | 1672.1568 | 1672.1568 | 1672.1568 | 1672.1568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11894 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 26591.4588 | 0.2 | 0.3 | 41482.6757 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7178.4399 | 7178.4399 | 7178.4399 | 7178.4399 | 7178.4399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11895 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 24148.5413 | 0.2 | 0.3 | 37671.7245 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11896 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 21568.6408 | 0.2 | 0.3 | 33647.0796 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11897 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 1994.8186 | 0.2 | 0.3 | 3111.917 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.8847 | 9777.8847 | 9777.8847 | 9777.8847 | 9777.8847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11898 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16691.8891 | 0.2 | 0.3 | 26039.3469 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0916 | 5200.0916 | 5200.0916 | 5200.0916 | 5200.0916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11899 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 3909.9097 | 0.2 | 0.3 | 6099.4592 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11900 | DAVIE | 70208 | Private | 2036 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11901 | DAVIE | 70209 | Private | 2036 | 5 | Swales | 66.6667 | 16047.6573 | 0.2 | 0.3 | 25034.3454 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5289.3758 | 5289.3758 | 5289.3758 | 5289.3758 | 5289.3758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11902 | DAVIE | 70209 | Private | 2036 | 5 | Swales | 66.6667 | 27427.333 | 0.2 | 0.3 | 42786.6395 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7456 | 5201.7456 | 5201.7456 | 5201.7456 | 5201.7456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11903 | DAVIE | 70209 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9269 | 5203.9269 | 5203.9269 | 5203.9269 | 5203.9269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11904 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 18772.8209 | 0.2 | 0.3 | 29285.6006 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6051 | 5201.6051 | 5201.6051 | 5201.6051 | 5201.6051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11905 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 24376.7024 | 0.2 | 0.3 | 38027.6557 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7327.0118 | 7327.0118 | 7327.0118 | 7327.0118 | 7327.0118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11906 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 16674.4755 | 0.2 | 0.3 | 26012.1817 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9352.9839 | 9352.9839 | 9352.9839 | 9352.9839 | 9352.9839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11907 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 24248.3248 | 0.2 | 0.3 | 37827.3867 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 505.4588 | 505.4588 | 505.4588 | 505.4588 | 505.4588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11908 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 16055.5886 | 0.2 | 0.3 | 25046.7182 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5450.0689 | 5450.0689 | 5450.0689 | 5450.0689 | 5450.0689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11909 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 18888.8177 | 0.2 | 0.3 | 29466.5557 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6813.6228 | 6813.6228 | 6813.6228 | 6813.6228 | 6813.6228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11910 | DAVIE | 70601 | Private | 2030 | 5 | Swales | 66.6667 | 13365.6564 | 0.2 | 0.3 | 20850.424 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1935.1316 | 1935.1316 | 1935.1316 | 1935.1316 | 1935.1316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11911 | DAVIE | 70601 | Public | 2030 | 5 | Swales | 66.6667 | 16672.9482 | 0.2 | 0.3 | 26009.7992 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5646.3197 | 5646.3197 | 5646.3197 | 5646.3197 | 5646.3197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11912 | DAVIE | 70104 | Public | 2030 | 5 | Swales | 66.6667 | 8385.4327 | 0.2 | 0.3 | 13081.275 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8086 | 5199.8086 | 5199.8086 | 5199.8086 | 5199.8086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11913 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16674.6658 | 0.2 | 0.3 | 26012.4786 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11914 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 4033.1629 | 0.2 | 0.3 | 6291.7342 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0175 | 5200.0175 | 5200.0175 | 5200.0175 | 5200.0175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11915 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 1679.8295 | 0.2 | 0.3 | 2620.5341 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5881.3133 | 5881.3133 | 5881.3133 | 5881.3133 | 5881.3133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11916 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 1498.1031 | 0.2 | 0.3 | 2337.0408 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4262.7963 | 4262.7963 | 4262.7963 | 4262.7963 | 4262.7963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11917 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 8369.4288 | 0.2 | 0.3 | 13056.3089 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1544 | 5200.1544 | 5200.1544 | 5200.1544 | 5200.1544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11918 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 23272.3768 | 0.2 | 0.3 | 36304.9078 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11919 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16562.0895 | 0.2 | 0.3 | 25836.8597 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1697 | 5200.1697 | 5200.1697 | 5200.1697 | 5200.1697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11920 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 111.7143 | 0.2 | 0.3 | 174.2744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7867.7706 | 7867.7706 | 7867.7706 | 7867.7706 | 7867.7706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11921 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 8390.0095 | 0.2 | 0.3 | 13088.4149 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0965 | 5200.0965 | 5200.0965 | 5200.0965 | 5200.0965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11922 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 8285.3275 | 0.2 | 0.3 | 12925.1108 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11923 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16748.1531 | 0.2 | 0.3 | 26127.1189 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11924 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 12765.4173 | 0.2 | 0.3 | 19914.0509 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.1021 | 5206.1021 | 5206.1021 | 5206.1021 | 5206.1021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11925 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 16676.4425 | 0.2 | 0.3 | 26015.2502 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3990.1225 | 3990.1225 | 3990.1225 | 3990.1225 | 3990.1225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11926 | DAVIE | 70209 | Private | 2036 | 5 | Swales | 66.6667 | 15658.8457 | 0.2 | 0.3 | 24427.7992 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2656 | 5200.2656 | 5200.2656 | 5200.2656 | 5200.2656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11927 | DAVIE | 70209 | Private | 2036 | 5 | Swales | 66.6667 | 28224.8849 | 0.2 | 0.3 | 44030.8205 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11928 | DAVIE | 70209 | Private | 2036 | 5 | Swales | 66.6667 | 22757.3192 | 0.2 | 0.3 | 35501.418 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11929 | DAVIE | 70209 | Private | 2036 | 5 | Swales | 66.6667 | 20040.6813 | 0.2 | 0.3 | 31263.4628 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7745.8611 | 7745.8611 | 7745.8611 | 7745.8611 | 7745.8611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11930 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 16675.0631 | 0.2 | 0.3 | 26013.0984 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5353.3725 | 5353.3725 | 5353.3725 | 5353.3725 | 5353.3725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11931 | DAVIE | 70211 | Private | 2036 | 5 | Swales | 66.6667 | 13584.2137 | 0.2 | 0.3 | 21191.3734 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9926 | 5199.9926 | 5199.9926 | 5199.9926 | 5199.9926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11932 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 18145.3937 | 0.2 | 0.3 | 28306.8141 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11933 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 12639.3837 | 0.2 | 0.3 | 19717.4385 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11934 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 15137.3311 | 0.2 | 0.3 | 23614.2365 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2026 | 5200.2026 | 5200.2026 | 5200.2026 | 5200.2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11935 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16733.3045 | 0.2 | 0.3 | 26103.9551 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7015.0214 | 7015.0214 | 7015.0214 | 7015.0214 | 7015.0214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11936 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 15363.1089 | 0.2 | 0.3 | 23966.4499 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13886.7736 | 13886.7736 | 13886.7736 | 13886.7736 | 13886.7736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11937 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 8308.6015 | 0.2 | 0.3 | 12961.4183 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4654.359 | 4654.359 | 4654.359 | 4654.359 | 4654.359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11938 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 19611.7936 | 0.2 | 0.3 | 30594.398 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8046.7841 | 8046.7841 | 8046.7841 | 8046.7841 | 8046.7841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11939 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 10099.5479 | 0.2 | 0.3 | 15755.2947 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5242.8835 | 5242.8835 | 5242.8835 | 5242.8835 | 5242.8835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11940 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 6575.1587 | 0.2 | 0.3 | 10257.2476 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11941 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 5962.5063 | 0.2 | 0.3 | 9301.5098 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11942 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 10711.4611 | 0.2 | 0.3 | 16709.8794 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.6905 | 9777.6905 | 9777.6905 | 9777.6905 | 9777.6905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11943 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16866.1716 | 0.2 | 0.3 | 26311.2277 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0339 | 5200.0339 | 5200.0339 | 5200.0339 | 5200.0339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11944 | DAVIE | 70208 | Public | 2036 | 5 | Swales | 66.6667 | 3909.9754 | 0.2 | 0.3 | 6099.5616 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11945 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16673.6759 | 0.2 | 0.3 | 26010.9344 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9832.0213 | 9832.0213 | 9832.0213 | 9832.0213 | 9832.0213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11946 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16674.1811 | 0.2 | 0.3 | 26011.7226 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5557.4588 | 5557.4588 | 5557.4588 | 5557.4588 | 5557.4588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11947 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 6512.6303 | 0.2 | 0.3 | 10159.7033 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6555.1333 | 6555.1333 | 6555.1333 | 6555.1333 | 6555.1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11948 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 10425.6089 | 0.2 | 0.3 | 16263.9498 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11949 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 25.8221 | 0.2 | 0.3 | 40.2825 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9752.1227 | 9752.1227 | 9752.1227 | 9752.1227 | 9752.1227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11950 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 16647.6999 | 0.2 | 0.3 | 25970.4118 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7621.5615 | 7621.5615 | 7621.5615 | 7621.5615 | 7621.5615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11951 | DAVIE | 70306 | Private | 2036 | 5 | Swales | 66.6667 | 17235.4607 | 0.2 | 0.3 | 26887.3187 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2331.8908 | 2331.8908 | 2331.8908 | 2331.8908 | 2331.8908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11952 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 10108.4595 | 0.2 | 0.3 | 15769.1968 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5909.1265 | 5909.1265 | 5909.1265 | 5909.1265 | 5909.1265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11953 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 20928.8909 | 0.2 | 0.3 | 32649.0698 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9745.7625 | 9745.7625 | 9745.7625 | 9745.7625 | 9745.7625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11954 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 30936.5273 | 0.2 | 0.3 | 48260.9825 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5772.3091 | 5772.3091 | 5772.3091 | 5772.3091 | 5772.3091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11955 | SOUTHWEST RANCHES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 30163.2873 | 0.2 | 0.3 | 47054.7281 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5517.8714 | 5517.8714 | 5517.8714 | 5517.8714 | 5517.8714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11956 | SOUTHWEST RANCHES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 21550.6704 | 0.2 | 0.3 | 33619.0458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11957 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 15425.5167 | 0.2 | 0.3 | 24063.806 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11958 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 3464.1634 | 0.2 | 0.3 | 5404.0949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.097 | 5200.097 | 5200.097 | 5200.097 | 5200.097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11959 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 27735.8227 | 0.2 | 0.3 | 43267.8834 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8122.3281 | 8122.3281 | 8122.3281 | 8122.3281 | 8122.3281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11960 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 25844.5725 | 0.2 | 0.3 | 40317.533 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6773.0841 | 6773.0841 | 6773.0841 | 6773.0841 | 6773.0841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11961 | SOUTHWEST RANCHES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 16666.9412 | 0.2 | 0.3 | 26000.4283 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2288 | 5200.2288 | 5200.2288 | 5200.2288 | 5200.2288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11962 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 18597.0539 | 0.2 | 0.3 | 29011.404 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11963 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 21474.439 | 0.2 | 0.3 | 33500.1248 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3454 | 5200.3454 | 5200.3454 | 5200.3454 | 5200.3454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11964 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16499.9643 | 0.2 | 0.3 | 25739.9443 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.4373 | 9776.4373 | 9776.4373 | 9776.4373 | 9776.4373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11965 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 30422.7006 | 0.2 | 0.3 | 47459.4129 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3208 | 5200.3208 | 5200.3208 | 5200.3208 | 5200.3208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11966 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 24640.3061 | 0.2 | 0.3 | 38438.8775 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11967 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 31464.4708 | 0.2 | 0.3 | 49084.5744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11968 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 31064.048 | 0.2 | 0.3 | 48459.9149 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3257 | 5200.3257 | 5200.3257 | 5200.3257 | 5200.3257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11969 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 40412.0736 | 0.2 | 0.3 | 63042.8348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5965.6793 | 5965.6793 | 5965.6793 | 5965.6793 | 5965.6793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11970 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 9908.0003 | 0.2 | 0.3 | 15456.4804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2843 | 5200.2843 | 5200.2843 | 5200.2843 | 5200.2843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11971 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 21216.3297 | 0.2 | 0.3 | 33097.4743 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11972 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 21486.6358 | 0.2 | 0.3 | 33519.1518 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11973 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16666.5191 | 0.2 | 0.3 | 25999.7697 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9577.2784 | 9577.2784 | 9577.2784 | 9577.2784 | 9577.2784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11974 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5328.5255 | 5328.5255 | 5328.5255 | 5328.5255 | 5328.5255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11975 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16666.5519 | 0.2 | 0.3 | 25999.821 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3576 | 5200.3576 | 5200.3576 | 5200.3576 | 5200.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11976 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 13261.2112 | 0.2 | 0.3 | 20687.4895 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11977 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 17032.1085 | 0.2 | 0.3 | 26570.0892 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11978 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3365 | 5200.3365 | 5200.3365 | 5200.3365 | 5200.3365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11979 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8713.0203 | 8713.0203 | 8713.0203 | 8713.0203 | 8713.0203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11980 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 22283.7161 | 0.2 | 0.3 | 34762.5971 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7617.1742 | 7617.1742 | 7617.1742 | 7617.1742 | 7617.1742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11981 | SOUTHWEST RANCHES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7235.867 | 7235.867 | 7235.867 | 7235.867 | 7235.867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11982 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 25288.6107 | 0.2 | 0.3 | 39450.2326 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1272.3358 | 1272.3358 | 1272.3358 | 1272.3358 | 1272.3358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11983 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 18310.9792 | 0.2 | 0.3 | 28565.1276 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8809.2592 | 8809.2592 | 8809.2592 | 8809.2592 | 8809.2592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11984 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 4655.5887 | 0.2 | 0.3 | 7262.7184 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.8976 | 9777.8976 | 9777.8976 | 9777.8976 | 9777.8976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11985 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 15428.6766 | 0.2 | 0.3 | 24068.7355 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1546 | 5200.1546 | 5200.1546 | 5200.1546 | 5200.1546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11986 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 1402.2209 | 0.2 | 0.3 | 2187.4647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11987 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 10495.1401 | 0.2 | 0.3 | 16372.4185 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.3896 | 9777.3896 | 9777.3896 | 9777.3896 | 9777.3896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11988 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 8420.1781 | 0.2 | 0.3 | 13135.4778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4875.6801 | 4875.6801 | 4875.6801 | 4875.6801 | 4875.6801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11989 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 1226.7493 | 0.2 | 0.3 | 1913.729 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11990 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 7198.8274 | 0.2 | 0.3 | 11230.1707 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9119.1199 | 9119.1199 | 9119.1199 | 9119.1199 | 9119.1199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11991 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16714.1672 | 0.2 | 0.3 | 26074.1008 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7326 | 5201.7326 | 5201.7326 | 5201.7326 | 5201.7326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11992 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16702.3305 | 0.2 | 0.3 | 26055.6355 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6615 | 5201.6615 | 5201.6615 | 5201.6615 | 5201.6615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11993 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16699.3621 | 0.2 | 0.3 | 26051.0049 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7612.8446 | 7612.8446 | 7612.8446 | 7612.8446 | 7612.8446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11994 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16676.7725 | 0.2 | 0.3 | 26015.7652 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1917 | 2600.1917 | 2600.1917 | 2600.1917 | 2600.1917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11995 | SOUTHWEST RANCHES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 16676.5187 | 0.2 | 0.3 | 26015.3692 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4761.6405 | 4761.6405 | 4761.6405 | 4761.6405 | 4761.6405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11996 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 3733.5678 | 0.2 | 0.3 | 5824.3658 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5519.7834 | 5519.7834 | 5519.7834 | 5519.7834 | 5519.7834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11997 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16417.6623 | 0.2 | 0.3 | 25611.5532 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11998 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16674.2553 | 0.2 | 0.3 | 26011.8382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3954 | 5200.3954 | 5200.3954 | 5200.3954 | 5200.3954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11999 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16672.3415 | 0.2 | 0.3 | 26008.8527 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7372.1651 | 7372.1651 | 7372.1651 | 7372.1651 | 7372.1651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12000 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16676.7159 | 0.2 | 0.3 | 26015.6768 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12001 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16837.9973 | 0.2 | 0.3 | 26267.2758 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7459.0443 | 7459.0443 | 7459.0443 | 7459.0443 | 7459.0443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12002 | SOUTHWEST RANCHES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 25523.8079 | 0.2 | 0.3 | 39817.1404 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9748.6503 | 9748.6503 | 9748.6503 | 9748.6503 | 9748.6503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12003 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 29239.2043 | 0.2 | 0.3 | 45613.1587 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7557.0046 | 7557.0046 | 7557.0046 | 7557.0046 | 7557.0046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12004 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 16910.3747 | 0.2 | 0.3 | 26380.1845 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12005 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 17699.2111 | 0.2 | 0.3 | 27610.7693 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4015 | 5200.4015 | 5200.4015 | 5200.4015 | 5200.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12006 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 17414.0005 | 0.2 | 0.3 | 27165.8408 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7211.2829 | 7211.2829 | 7211.2829 | 7211.2829 | 7211.2829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12007 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 2851.2341 | 0.2 | 0.3 | 4447.9251 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7777.8883 | 7777.8883 | 7777.8883 | 7777.8883 | 7777.8883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12008 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 8332.0976 | 0.2 | 0.3 | 12998.0723 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12009 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16674.2003 | 0.2 | 0.3 | 26011.7525 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12010 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 19906.6541 | 0.2 | 0.3 | 31054.3803 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1339 | 5200.1339 | 5200.1339 | 5200.1339 | 5200.1339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12011 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 29629.6011 | 0.2 | 0.3 | 46222.1777 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5909.7427 | 5909.7427 | 5909.7427 | 5909.7427 | 5909.7427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12012 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.6224 | 9776.6224 | 9776.6224 | 9776.6224 | 9776.6224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12013 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.1951 | 9776.1951 | 9776.1951 | 9776.1951 | 9776.1951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12014 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 27544.2258 | 0.2 | 0.3 | 42968.9922 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.6098 | 9777.6098 | 9777.6098 | 9777.6098 | 9777.6098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12015 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 0.024267 | 0.2 | 0.3 | 0.037856 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5838.7416 | 5838.7416 | 5838.7416 | 5838.7416 | 5838.7416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12016 | SOUTHWEST RANCHES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 16667.3203 | 0.2 | 0.3 | 26001.0197 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5338.6375 | 5338.6375 | 5338.6375 | 5338.6375 | 5338.6375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12017 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 18503.6671 | 0.2 | 0.3 | 28865.7206 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3830.6095 | 3830.6095 | 3830.6095 | 3830.6095 | 3830.6095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12018 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 2549.1591 | 0.2 | 0.3 | 3976.6881 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12019 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 13829.2057 | 0.2 | 0.3 | 21573.5609 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12020 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 23920.8017 | 0.2 | 0.3 | 37316.4506 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1488 | 5200.1488 | 5200.1488 | 5200.1488 | 5200.1488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12021 | COOPER CITY | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 21783.1675 | 0.2 | 0.3 | 33981.7414 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9665.0637 | 9665.0637 | 9665.0637 | 9665.0637 | 9665.0637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12022 | SOUTHWEST RANCHES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 16667.0615 | 0.2 | 0.3 | 26000.616 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2392.6994 | 2392.6994 | 2392.6994 | 2392.6994 | 2392.6994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12023 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 94.3793 | 0.2 | 0.3 | 147.2318 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7445.9401 | 7445.9401 | 7445.9401 | 7445.9401 | 7445.9401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12024 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 27523.5581 | 0.2 | 0.3 | 42936.7506 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5154.5844 | 5154.5844 | 5154.5844 | 5154.5844 | 5154.5844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12025 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 16759.3347 | 0.2 | 0.3 | 26144.5621 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5298.9084 | 5298.9084 | 5298.9084 | 5298.9084 | 5298.9084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12026 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 16677.2627 | 0.2 | 0.3 | 26016.5298 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6977.1666 | 6977.1666 | 6977.1666 | 6977.1666 | 6977.1666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12027 | SOUTHWEST RANCHES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 16667.3677 | 0.2 | 0.3 | 26001.0936 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7533.0593 | 7533.0593 | 7533.0593 | 7533.0593 | 7533.0593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12028 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 8376.1399 | 0.2 | 0.3 | 13066.7782 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8056.582 | 8056.582 | 8056.582 | 8056.582 | 8056.582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12029 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 15314.3033 | 0.2 | 0.3 | 23890.3131 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3040.0959 | 3040.0959 | 3040.0959 | 3040.0959 | 3040.0959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12030 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 16864.2464 | 0.2 | 0.3 | 26308.2244 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1222 | 5201.1222 | 5201.1222 | 5201.1222 | 5201.1222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12031 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 16673.8553 | 0.2 | 0.3 | 26011.2142 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5925.3932 | 5925.3932 | 5925.3932 | 5925.3932 | 5925.3932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12032 | PEMBROKE PINES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 31333.7943 | 0.2 | 0.3 | 48880.7191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1769 | 5200.1769 | 5200.1769 | 5200.1769 | 5200.1769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12033 | PEMBROKE PINES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 24557.4915 | 0.2 | 0.3 | 38309.6867 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12034 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 3105.8259 | 0.2 | 0.3 | 4845.0884 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12035 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 30664.1015 | 0.2 | 0.3 | 47835.9983 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9708.862 | 9708.862 | 9708.862 | 9708.862 | 9708.862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12036 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 15700.7741 | 0.2 | 0.3 | 24493.2076 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5221.2744 | 5221.2744 | 5221.2744 | 5221.2744 | 5221.2744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12037 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 25288.6609 | 0.2 | 0.3 | 39450.311 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.117 | 5200.117 | 5200.117 | 5200.117 | 5200.117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12038 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 17538.3191 | 0.2 | 0.3 | 27359.7778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12039 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 2135.6992 | 0.2 | 0.3 | 3331.6908 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12040 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 13148.7488 | 0.2 | 0.3 | 20512.0481 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.352 | 5200.352 | 5200.352 | 5200.352 | 5200.352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12041 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 29067.3575 | 0.2 | 0.3 | 45345.0776 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8993.4261 | 8993.4261 | 8993.4261 | 8993.4261 | 8993.4261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12042 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16677.1083 | 0.2 | 0.3 | 26016.289 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5546.2608 | 5546.2608 | 5546.2608 | 5546.2608 | 5546.2608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12043 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 26695.9667 | 0.2 | 0.3 | 41645.708 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7733.156 | 7733.156 | 7733.156 | 7733.156 | 7733.156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12044 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 29895.9335 | 0.2 | 0.3 | 46637.6563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6361.8489 | 6361.8489 | 6361.8489 | 6361.8489 | 6361.8489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12045 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 7055.2351 | 0.2 | 0.3 | 11006.1668 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.135 | 5200.135 | 5200.135 | 5200.135 | 5200.135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12046 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 3786.4173 | 0.2 | 0.3 | 5906.811 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12047 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 21074.5213 | 0.2 | 0.3 | 32876.2533 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12048 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 4714.8869 | 0.2 | 0.3 | 7355.2236 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1913 | 5200.1913 | 5200.1913 | 5200.1913 | 5200.1913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12049 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16676.4057 | 0.2 | 0.3 | 26015.1928 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8944.0625 | 8944.0625 | 8944.0625 | 8944.0625 | 8944.0625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12050 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16685.7613 | 0.2 | 0.3 | 26029.7876 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7447.1529 | 7447.1529 | 7447.1529 | 7447.1529 | 7447.1529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12051 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 10472.1629 | 0.2 | 0.3 | 16336.5741 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7109.0381 | 7109.0381 | 7109.0381 | 7109.0381 | 7109.0381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12052 | SOUTHWEST RANCHES | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 13406.8102 | 0.2 | 0.3 | 20914.6239 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5321.8181 | 5321.8181 | 5321.8181 | 5321.8181 | 5321.8181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12053 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 22165.5743 | 0.2 | 0.3 | 34578.2959 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5830.5684 | 5830.5684 | 5830.5684 | 5830.5684 | 5830.5684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12054 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 11313.3371 | 0.2 | 0.3 | 17648.8059 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7905 | 5201.7905 | 5201.7905 | 5201.7905 | 5201.7905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12055 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 21258.2677 | 0.2 | 0.3 | 33162.8977 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 107.3334 | 107.3334 | 107.3334 | 107.3334 | 107.3334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12056 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 20630.8902 | 0.2 | 0.3 | 32184.1887 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5141.58 | 5141.58 | 5141.58 | 5141.58 | 5141.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12057 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 31013.7519 | 0.2 | 0.3 | 48381.4529 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2631.0436 | 2631.0436 | 2631.0436 | 2631.0436 | 2631.0436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12058 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 234.5583 | 0.2 | 0.3 | 365.9109 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2696.7832 | 2696.7832 | 2696.7832 | 2696.7832 | 2696.7832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12059 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16677.4883 | 0.2 | 0.3 | 26016.8817 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6532 | 5202.6532 | 5202.6532 | 5202.6532 | 5202.6532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12060 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 24934.3703 | 0.2 | 0.3 | 38897.6176 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12061 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16673.0546 | 0.2 | 0.3 | 26009.9652 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12062 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 8075.0025 | 0.2 | 0.3 | 12597.0038 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9764.4254 | 9764.4254 | 9764.4254 | 9764.4254 | 9764.4254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12063 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 8628.2146 | 0.2 | 0.3 | 13460.0148 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1699.385 | 1699.385 | 1699.385 | 1699.385 | 1699.385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12064 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 3.4007 | 0.2 | 0.3 | 5.305 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5287.1379 | 5287.1379 | 5287.1379 | 5287.1379 | 5287.1379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12065 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 4068.6958 | 0.2 | 0.3 | 6347.1654 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12066 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 8437.4745 | 0.2 | 0.3 | 13162.4602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12067 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 24865.5719 | 0.2 | 0.3 | 38790.2921 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1571 | 5200.1571 | 5200.1571 | 5200.1571 | 5200.1571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12068 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 30119.4791 | 0.2 | 0.3 | 46986.3874 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5548.5805 | 5548.5805 | 5548.5805 | 5548.5805 | 5548.5805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12069 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 2526.3055 | 0.2 | 0.3 | 3941.0366 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6444.4509 | 6444.4509 | 6444.4509 | 6444.4509 | 6444.4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12070 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 14981.0237 | 0.2 | 0.3 | 23370.397 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9570.2589 | 9570.2589 | 9570.2589 | 9570.2589 | 9570.2589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12071 | PEMBROKE PINES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 9687.0356 | 0.2 | 0.3 | 15111.7755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6773 | 5202.6773 | 5202.6773 | 5202.6773 | 5202.6773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12072 | PEMBROKE PINES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 44963.392 | 0.2 | 0.3 | 70142.8915 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5440.4057 | 5440.4057 | 5440.4057 | 5440.4057 | 5440.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12073 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16789.2487 | 0.2 | 0.3 | 26191.2279 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12074 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 12608.7232 | 0.2 | 0.3 | 19669.6082 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6848.7158 | 6848.7158 | 6848.7158 | 6848.7158 | 6848.7158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12075 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 8240.1792 | 0.2 | 0.3 | 12854.6796 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3775.2259 | 3775.2259 | 3775.2259 | 3775.2259 | 3775.2259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12076 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 1400.0826 | 0.2 | 0.3 | 2184.1289 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11216.4133 | 11216.4133 | 11216.4133 | 11216.4133 | 11216.4133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12077 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 6169.8659 | 0.2 | 0.3 | 9624.9909 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6019.9067 | 6019.9067 | 6019.9067 | 6019.9067 | 6019.9067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12078 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16678.2575 | 0.2 | 0.3 | 26018.0816 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5534.2671 | 5534.2671 | 5534.2671 | 5534.2671 | 5534.2671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12079 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 15826.4287 | 0.2 | 0.3 | 24689.2287 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8041.5001 | 8041.5001 | 8041.5001 | 8041.5001 | 8041.5001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12080 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 32.2643 | 0.2 | 0.3 | 50.3323 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3860.3221 | 3860.3221 | 3860.3221 | 3860.3221 | 3860.3221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12081 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 19340.1616 | 0.2 | 0.3 | 30170.6521 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1406.2713 | 1406.2713 | 1406.2713 | 1406.2713 | 1406.2713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12082 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 35750.0245 | 0.2 | 0.3 | 55770.0382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3697.826 | 3697.826 | 3697.826 | 3697.826 | 3697.826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12083 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 17582.2557 | 0.2 | 0.3 | 27428.3189 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 15.3188 | 15.3188 | 15.3188 | 15.3188 | 15.3188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12084 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 17498.4469 | 0.2 | 0.3 | 27297.5771 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1092.2003 | 1092.2003 | 1092.2003 | 1092.2003 | 1092.2003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12085 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 23802.4803 | 0.2 | 0.3 | 37131.8692 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1174.2731 | 1174.2731 | 1174.2731 | 1174.2731 | 1174.2731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12086 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 30293.5591 | 0.2 | 0.3 | 47257.9522 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2737.5529 | 2737.5529 | 2737.5529 | 2737.5529 | 2737.5529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12087 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 30760.7567 | 0.2 | 0.3 | 47986.7804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1430.8689 | 1430.8689 | 1430.8689 | 1430.8689 | 1430.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12088 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 31243.9794 | 0.2 | 0.3 | 48740.6079 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7712 | 5201.7712 | 5201.7712 | 5201.7712 | 5201.7712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12089 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 17395.015 | 0.2 | 0.3 | 27136.2234 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12090 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 8071.5409 | 0.2 | 0.3 | 12591.6038 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12091 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 32435.5676 | 0.2 | 0.3 | 50599.4855 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9704.6169 | 9704.6169 | 9704.6169 | 9704.6169 | 9704.6169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12092 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 13705.6 | 0.2 | 0.3 | 21380.736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1058.7203 | 1058.7203 | 1058.7203 | 1058.7203 | 1058.7203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12093 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 14169.3067 | 0.2 | 0.3 | 22104.1184 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5278.7234 | 5278.7234 | 5278.7234 | 5278.7234 | 5278.7234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12094 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 21531.1207 | 0.2 | 0.3 | 33588.5483 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0306 | 5200.0306 | 5200.0306 | 5200.0306 | 5200.0306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12095 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 26085.517 | 0.2 | 0.3 | 40693.4065 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2039.1726 | 2039.1726 | 2039.1726 | 2039.1726 | 2039.1726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12096 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 25850.7428 | 0.2 | 0.3 | 40327.1588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8815.524 | 8815.524 | 8815.524 | 8815.524 | 8815.524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12097 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 12089.2765 | 0.2 | 0.3 | 18859.2713 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12098 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 22118.5145 | 0.2 | 0.3 | 34504.8826 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5566 | 5202.5566 | 5202.5566 | 5202.5566 | 5202.5566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12099 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 32911.3313 | 0.2 | 0.3 | 51341.6769 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5231.2238 | 5231.2238 | 5231.2238 | 5231.2238 | 5231.2238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12100 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 19117.9597 | 0.2 | 0.3 | 29824.0172 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5237.5585 | 5237.5585 | 5237.5585 | 5237.5585 | 5237.5585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12101 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6598 | 0.2 | 0.3 | 25999.9893 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6072.8694 | 6072.8694 | 6072.8694 | 6072.8694 | 6072.8694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12102 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4848 | 5201.4848 | 5201.4848 | 5201.4848 | 5201.4848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12103 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 10948.711 | 0.2 | 0.3 | 17079.9892 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7555.5833 | 7555.5833 | 7555.5833 | 7555.5833 | 7555.5833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12104 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16806.3189 | 0.2 | 0.3 | 26217.8574 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2822.7984 | 2822.7984 | 2822.7984 | 2822.7984 | 2822.7984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12105 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 20130.233 | 0.2 | 0.3 | 31403.1635 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2377.5047 | 2377.5047 | 2377.5047 | 2377.5047 | 2377.5047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12106 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16702.8397 | 0.2 | 0.3 | 26056.43 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9801.658 | 9801.658 | 9801.658 | 9801.658 | 9801.658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12107 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 17558.6925 | 0.2 | 0.3 | 27391.5602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12108 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 25821.3669 | 0.2 | 0.3 | 40281.3323 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1313 | 5200.1313 | 5200.1313 | 5200.1313 | 5200.1313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12109 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16667.6621 | 0.2 | 0.3 | 26001.5528 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9792.6529 | 9792.6529 | 9792.6529 | 9792.6529 | 9792.6529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12110 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 17739.9565 | 0.2 | 0.3 | 27674.3322 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.908 | 5200.908 | 5200.908 | 5200.908 | 5200.908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12111 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 17172.3495 | 0.2 | 0.3 | 26788.8652 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4965.656 | 4965.656 | 4965.656 | 4965.656 | 4965.656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12112 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16726.4889 | 0.2 | 0.3 | 26093.3227 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8651.9991 | 8651.9991 | 8651.9991 | 8651.9991 | 8651.9991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12113 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 26741.8811 | 0.2 | 0.3 | 41717.3346 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8837 | 5200.8837 | 5200.8837 | 5200.8837 | 5200.8837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12114 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 16856.9592 | 0.2 | 0.3 | 26296.8564 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5718.6927 | 5718.6927 | 5718.6927 | 5718.6927 | 5718.6927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12115 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 30524.7345 | 0.2 | 0.3 | 47618.5858 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0474 | 5200.0474 | 5200.0474 | 5200.0474 | 5200.0474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12116 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 26170.8392 | 0.2 | 0.3 | 40826.5092 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12117 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 24868.7325 | 0.2 | 0.3 | 38795.2228 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12118 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 17804.6401 | 0.2 | 0.3 | 27775.2385 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9754.3003 | 9754.3003 | 9754.3003 | 9754.3003 | 9754.3003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12119 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 1.7704 | 0.2 | 0.3 | 2.7618 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5236.0567 | 5236.0567 | 5236.0567 | 5236.0567 | 5236.0567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12120 | SOUTHWEST RANCHES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 14656.8437 | 0.2 | 0.3 | 22864.6762 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9938 | 5199.9938 | 5199.9938 | 5199.9938 | 5199.9938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12121 | SOUTHWEST RANCHES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6092 | 0.2 | 0.3 | 25999.9104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.897 | 5199.897 | 5199.897 | 5199.897 | 5199.897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12122 | SOUTHWEST RANCHES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 22222.0705 | 0.2 | 0.3 | 34666.43 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5799.1718 | 5799.1718 | 5799.1718 | 5799.1718 | 5799.1718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12123 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 14109.8263 | 0.2 | 0.3 | 22011.3291 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2786.5225 | 2786.5225 | 2786.5225 | 2786.5225 | 2786.5225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12124 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6643 | 0.2 | 0.3 | 25999.9964 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6403.2451 | 6403.2451 | 6403.2451 | 6403.2451 | 6403.2451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12125 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 7143.7791 | 0.2 | 0.3 | 11144.2953 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7808.3818 | 7808.3818 | 7808.3818 | 7808.3818 | 7808.3818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12126 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 27942.0888 | 0.2 | 0.3 | 43589.6585 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5860.3433 | 5860.3433 | 5860.3433 | 5860.3433 | 5860.3433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12127 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 12439.3413 | 0.2 | 0.3 | 19405.3725 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12128 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 4433.9903 | 0.2 | 0.3 | 6917.0248 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2773 | 5200.2773 | 5200.2773 | 5200.2773 | 5200.2773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12129 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 31053.0465 | 0.2 | 0.3 | 48442.7526 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3071.4487 | 3071.4487 | 3071.4487 | 3071.4487 | 3071.4487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12130 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 25939.167 | 0.2 | 0.3 | 40465.1005 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9543 | 5201.9543 | 5201.9543 | 5201.9543 | 5201.9543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12131 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 27207.6117 | 0.2 | 0.3 | 42443.8742 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2798.5811 | 2798.5811 | 2798.5811 | 2798.5811 | 2798.5811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12132 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 21840.6377 | 0.2 | 0.3 | 34071.3949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6296.0914 | 6296.0914 | 6296.0914 | 6296.0914 | 6296.0914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12133 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 19678.7198 | 0.2 | 0.3 | 30698.8029 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5148.7911 | 5148.7911 | 5148.7911 | 5148.7911 | 5148.7911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12134 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 9885.9822 | 0.2 | 0.3 | 15422.1322 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 495.4328 | 495.4328 | 495.4328 | 495.4328 | 495.4328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12135 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 1445.4359 | 0.2 | 0.3 | 2254.8801 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5613.6291 | 5613.6291 | 5613.6291 | 5613.6291 | 5613.6291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12136 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 15937.287 | 0.2 | 0.3 | 24862.1677 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2947 | 5200.2947 | 5200.2947 | 5200.2947 | 5200.2947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12137 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 20496.3812 | 0.2 | 0.3 | 31974.3547 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12138 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 4715.1468 | 0.2 | 0.3 | 7355.629 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0032 | 5200.0032 | 5200.0032 | 5200.0032 | 5200.0032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12139 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 24215.3989 | 0.2 | 0.3 | 37776.0223 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6688.4255 | 6688.4255 | 6688.4255 | 6688.4255 | 6688.4255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12140 | SOUTHWEST RANCHES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 16677.8611 | 0.2 | 0.3 | 26017.4633 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.101 | 5200.101 | 5200.101 | 5200.101 | 5200.101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12141 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 30392.6201 | 0.2 | 0.3 | 47412.4873 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12142 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8019.4909 | 8019.4909 | 8019.4909 | 8019.4909 | 8019.4909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12143 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 23992.832 | 0.2 | 0.3 | 37428.8179 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9491.3376 | 9491.3376 | 9491.3376 | 9491.3376 | 9491.3376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12144 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16905.7171 | 0.2 | 0.3 | 26372.9186 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8447.3325 | 8447.3325 | 8447.3325 | 8447.3325 | 8447.3325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12145 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 32355.9114 | 0.2 | 0.3 | 50475.2218 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12146 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 23869.5699 | 0.2 | 0.3 | 37236.529 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0682 | 5200.0682 | 5200.0682 | 5200.0682 | 5200.0682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12147 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 18705.9058 | 0.2 | 0.3 | 29181.213 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.2208 | 9777.2208 | 9777.2208 | 9777.2208 | 9777.2208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12148 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 13405.3541 | 0.2 | 0.3 | 20912.3523 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6162.766 | 6162.766 | 6162.766 | 6162.766 | 6162.766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12149 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 3518.3657 | 0.2 | 0.3 | 5488.6505 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3803.9538 | 3803.9538 | 3803.9538 | 3803.9538 | 3803.9538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12150 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 5193.8977 | 0.2 | 0.3 | 8102.4804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12151 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 11479.6583 | 0.2 | 0.3 | 17908.267 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5253.3554 | 5253.3554 | 5253.3554 | 5253.3554 | 5253.3554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12152 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 16675.3489 | 0.2 | 0.3 | 26013.5442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4591 | 5200.4591 | 5200.4591 | 5200.4591 | 5200.4591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12153 | SOUTHWEST RANCHES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 16678.3523 | 0.2 | 0.3 | 26018.2295 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2582.2803 | 2582.2803 | 2582.2803 | 2582.2803 | 2582.2803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12154 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16666.5078 | 0.2 | 0.3 | 25999.7522 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12155 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16684.7197 | 0.2 | 0.3 | 26028.1628 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12156 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16673.4351 | 0.2 | 0.3 | 26010.5587 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4296.4894 | 4296.4894 | 4296.4894 | 4296.4894 | 4296.4894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12157 | DAVIE | 70316 | Private | 2036 | 5 | Swales | 66.6667 | 4104.6761 | 0.2 | 0.3 | 6403.2948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5101.3335 | 5101.3335 | 5101.3335 | 5101.3335 | 5101.3335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12158 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 29328.6537 | 0.2 | 0.3 | 45752.6998 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.353 | 5200.353 | 5200.353 | 5200.353 | 5200.353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12159 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 16673.1617 | 0.2 | 0.3 | 26010.1322 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2505 | 5200.2505 | 5200.2505 | 5200.2505 | 5200.2505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12160 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 16688.3853 | 0.2 | 0.3 | 26033.8811 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12161 | SOUTHWEST RANCHES | 70314 | Public | 2036 | 5 | Swales | 66.6667 | 20317.2271 | 0.2 | 0.3 | 31694.8743 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2368 | 5200.2368 | 5200.2368 | 5200.2368 | 5200.2368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12162 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16685.9289 | 0.2 | 0.3 | 26030.049 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9992.6322 | 9992.6322 | 9992.6322 | 9992.6322 | 9992.6322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12163 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16681.1993 | 0.2 | 0.3 | 26022.6709 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4995.1199 | 4995.1199 | 4995.1199 | 4995.1199 | 4995.1199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12164 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 21298.9385 | 0.2 | 0.3 | 33226.344 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5013.8039 | 5013.8039 | 5013.8039 | 5013.8039 | 5013.8039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12165 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 19997.9117 | 0.2 | 0.3 | 31196.7422 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5208.4104 | 5208.4104 | 5208.4104 | 5208.4104 | 5208.4104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12166 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16673.4506 | 0.2 | 0.3 | 26010.5829 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.7386 | 9777.7386 | 9777.7386 | 9777.7386 | 9777.7386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12167 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 12772.9258 | 0.2 | 0.3 | 19925.7642 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5143.9335 | 5143.9335 | 5143.9335 | 5143.9335 | 5143.9335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12168 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 382.7213 | 0.2 | 0.3 | 597.0452 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7158 | 5200.7158 | 5200.7158 | 5200.7158 | 5200.7158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12169 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 26708.0328 | 0.2 | 0.3 | 41664.5312 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12170 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 16672.8883 | 0.2 | 0.3 | 26009.7057 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8058.966 | 8058.966 | 8058.966 | 8058.966 | 8058.966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12171 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 16677.4869 | 0.2 | 0.3 | 26016.8795 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7875.0387 | 7875.0387 | 7875.0387 | 7875.0387 | 7875.0387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12172 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 28979.2369 | 0.2 | 0.3 | 45207.6095 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12173 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12174 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 24609.5668 | 0.2 | 0.3 | 38390.9242 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1945 | 5200.1945 | 5200.1945 | 5200.1945 | 5200.1945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12175 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 24434.9067 | 0.2 | 0.3 | 38118.4544 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4879.0365 | 4879.0365 | 4879.0365 | 4879.0365 | 4879.0365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12176 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16668.1297 | 0.2 | 0.3 | 26002.2824 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2709 | 5202.2709 | 5202.2709 | 5202.2709 | 5202.2709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12177 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 12575.1223 | 0.2 | 0.3 | 19617.1908 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5843.1073 | 5843.1073 | 5843.1073 | 5843.1073 | 5843.1073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12178 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 19326.2015 | 0.2 | 0.3 | 30148.8744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5378.5916 | 5378.5916 | 5378.5916 | 5378.5916 | 5378.5916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12179 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 487.1897 | 0.2 | 0.3 | 760.0159 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1232.9014 | 1232.9014 | 1232.9014 | 1232.9014 | 1232.9014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12180 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 2.2587 | 0.2 | 0.3 | 3.5236 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5221.7144 | 5221.7144 | 5221.7144 | 5221.7144 | 5221.7144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12181 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 22782.4157 | 0.2 | 0.3 | 35540.5684 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2620.5191 | 2620.5191 | 2620.5191 | 2620.5191 | 2620.5191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12182 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 818.1533 | 0.2 | 0.3 | 1276.3192 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4054.5409 | 4054.5409 | 4054.5409 | 4054.5409 | 4054.5409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12183 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 16673.3683 | 0.2 | 0.3 | 26010.4546 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1732.8236 | 1732.8236 | 1732.8236 | 1732.8236 | 1732.8236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12184 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 16679.3508 | 0.2 | 0.3 | 26019.7872 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1118.5775 | 1118.5775 | 1118.5775 | 1118.5775 | 1118.5775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12185 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 32009.7837 | 0.2 | 0.3 | 49935.2625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 133.8555 | 133.8555 | 133.8555 | 133.8555 | 133.8555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12186 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 18262.3416 | 0.2 | 0.3 | 28489.2529 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2642.3254 | 2642.3254 | 2642.3254 | 2642.3254 | 2642.3254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12187 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 520.4505 | 0.2 | 0.3 | 811.9027 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12188 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 21838.8819 | 0.2 | 0.3 | 34068.6558 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12189 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 19999.5352 | 0.2 | 0.3 | 31199.2749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2066.2953 | 2066.2953 | 2066.2953 | 2066.2953 | 2066.2953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12190 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 1326.5753 | 0.2 | 0.3 | 2069.4575 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4198.5183 | 4198.5183 | 4198.5183 | 4198.5183 | 4198.5183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12191 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 25341.6999 | 0.2 | 0.3 | 39533.0519 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2146.5056 | 2146.5056 | 2146.5056 | 2146.5056 | 2146.5056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12192 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 6433.3921 | 0.2 | 0.3 | 10036.0917 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 98.9367 | 98.9367 | 98.9367 | 98.9367 | 98.9367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12193 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 14613.9687 | 0.2 | 0.3 | 22797.7912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8098 | 5201.8098 | 5201.8098 | 5201.8098 | 5201.8098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12194 | PEMBROKE PINES | 70314 | Private | 2036 | 5 | Swales | 66.6667 | 21544.4227 | 0.2 | 0.3 | 33609.2995 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2343.1758 | 2343.1758 | 2343.1758 | 2343.1758 | 2343.1758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12195 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 16746.7069 | 0.2 | 0.3 | 26124.8627 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5297.9795 | 5297.9795 | 5297.9795 | 5297.9795 | 5297.9795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12196 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 17725.1479 | 0.2 | 0.3 | 27651.2308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4886.5698 | 4886.5698 | 4886.5698 | 4886.5698 | 4886.5698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12197 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 17170.3062 | 0.2 | 0.3 | 26785.6777 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 357.1323 | 357.1323 | 357.1323 | 357.1323 | 357.1323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12198 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 5187.5491 | 0.2 | 0.3 | 8092.5766 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7545.1102 | 7545.1102 | 7545.1102 | 7545.1102 | 7545.1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12199 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 23370.5955 | 0.2 | 0.3 | 36458.129 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5560.7325 | 5560.7325 | 5560.7325 | 5560.7325 | 5560.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12200 | DAVIE | 70315 | Private | 2036 | 5 | Swales | 66.6667 | 5922.0313 | 0.2 | 0.3 | 9238.3689 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4728.7559 | 4728.7559 | 4728.7559 | 4728.7559 | 4728.7559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12201 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 16673.7605 | 0.2 | 0.3 | 26011.0663 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4831 | 5200.4831 | 5200.4831 | 5200.4831 | 5200.4831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12202 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 17026.6398 | 0.2 | 0.3 | 26561.5581 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8694 | 5200.8694 | 5200.8694 | 5200.8694 | 5200.8694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12203 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 16838.8057 | 0.2 | 0.3 | 26268.5368 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8086 | 5199.8086 | 5199.8086 | 5199.8086 | 5199.8086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12204 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 16686.8107 | 0.2 | 0.3 | 26031.4246 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4012.6378 | 4012.6378 | 4012.6378 | 4012.6378 | 4012.6378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12205 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 16720.8169 | 0.2 | 0.3 | 26084.4744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5917.1514 | 5917.1514 | 5917.1514 | 5917.1514 | 5917.1514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12206 | DAVIE | 70316 | Public | 2036 | 5 | Swales | 66.6667 | 28871.3443 | 0.2 | 0.3 | 45039.2971 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5230.3965 | 5230.3965 | 5230.3965 | 5230.3965 | 5230.3965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12207 | DAVIE | 110327 | Public | 2036 | 5 | Swales | 66.6667 | 23788.2109 | 0.2 | 0.3 | 37109.6091 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5212.6174 | 5212.6174 | 5212.6174 | 5212.6174 | 5212.6174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12208 | DAVIE | 110327 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3393.936 | 3393.936 | 3393.936 | 3393.936 | 3393.936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12209 | DAVIE | 110327 | Public | 2036 | 5 | Swales | 66.6667 | 19190.653 | 0.2 | 0.3 | 29937.4187 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2593.1963 | 2593.1963 | 2593.1963 | 2593.1963 | 2593.1963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12210 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16832.7256 | 0.2 | 0.3 | 26259.0519 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3970.3355 | 3970.3355 | 3970.3355 | 3970.3355 | 3970.3355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12211 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 17409.3007 | 0.2 | 0.3 | 27158.509 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5732.4514 | 5732.4514 | 5732.4514 | 5732.4514 | 5732.4514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12212 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 15492.4597 | 0.2 | 0.3 | 24168.2371 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1781 | 5200.1781 | 5200.1781 | 5200.1781 | 5200.1781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12213 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 2794.3611 | 0.2 | 0.3 | 4359.2033 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4394.6503 | 4394.6503 | 4394.6503 | 4394.6503 | 4394.6503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12214 | DAVIE | 110327 | Public | 2036 | 5 | Swales | 66.6667 | 17411.5477 | 0.2 | 0.3 | 27162.0144 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5466.1957 | 5466.1957 | 5466.1957 | 5466.1957 | 5466.1957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12215 | DAVIE | 110327 | Public | 2036 | 5 | Swales | 66.6667 | 18471.3912 | 0.2 | 0.3 | 28815.3703 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7617.2643 | 7617.2643 | 7617.2643 | 7617.2643 | 7617.2643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12216 | DAVIE | 110327 | Public | 2036 | 5 | Swales | 66.6667 | 12244.2709 | 0.2 | 0.3 | 19101.0626 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3617 | 5200.3617 | 5200.3617 | 5200.3617 | 5200.3617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12217 | DAVIE | 110327 | Public | 2036 | 5 | Swales | 66.6667 | 25503.7733 | 0.2 | 0.3 | 39785.8864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3504 | 5200.3504 | 5200.3504 | 5200.3504 | 5200.3504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12218 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 1720.7023 | 0.2 | 0.3 | 2684.2956 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4362.3051 | 4362.3051 | 4362.3051 | 4362.3051 | 4362.3051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12219 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 1640.4191 | 0.2 | 0.3 | 2559.0537 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4169.1463 | 4169.1463 | 4169.1463 | 4169.1463 | 4169.1463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12220 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16754.4057 | 0.2 | 0.3 | 26136.8728 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6099.2973 | 6099.2973 | 6099.2973 | 6099.2973 | 6099.2973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12221 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 12462.1801 | 0.2 | 0.3 | 19441.0009 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12222 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 14056.8633 | 0.2 | 0.3 | 21928.7068 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3709 | 5200.3709 | 5200.3709 | 5200.3709 | 5200.3709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12223 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 18719.748 | 0.2 | 0.3 | 29202.8069 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6330.1546 | 6330.1546 | 6330.1546 | 6330.1546 | 6330.1546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12224 | DAVIE | 110327 | Public | 2036 | 5 | Swales | 66.6667 | 23920.4049 | 0.2 | 0.3 | 37315.8316 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9149.9145 | 9149.9145 | 9149.9145 | 9149.9145 | 9149.9145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12225 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 24403.7167 | 0.2 | 0.3 | 38069.798 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5898.128 | 5898.128 | 5898.128 | 5898.128 | 5898.128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12226 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 15219.2313 | 0.2 | 0.3 | 23742.0008 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12227 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 375.5023 | 0.2 | 0.3 | 585.7836 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2428 | 5200.2428 | 5200.2428 | 5200.2428 | 5200.2428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12228 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 16700.7586 | 0.2 | 0.3 | 26053.1834 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8716.45 | 8716.45 | 8716.45 | 8716.45 | 8716.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12229 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 21584.6311 | 0.2 | 0.3 | 33672.0246 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4016 | 5200.4016 | 5200.4016 | 5200.4016 | 5200.4016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12230 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 8293.0252 | 0.2 | 0.3 | 12937.1193 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12231 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 8273.5237 | 0.2 | 0.3 | 12906.6969 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5207.8642 | 5207.8642 | 5207.8642 | 5207.8642 | 5207.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12232 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 10100.5908 | 0.2 | 0.3 | 15756.9216 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8194.8734 | 8194.8734 | 8194.8734 | 8194.8734 | 8194.8734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12233 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 24936.8333 | 0.2 | 0.3 | 38901.46 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.9422 | 9778.9422 | 9778.9422 | 9778.9422 | 9778.9422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12234 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 21601.417 | 0.2 | 0.3 | 33698.2105 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3293 | 5200.3293 | 5200.3293 | 5200.3293 | 5200.3293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12235 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 8376.5609 | 0.2 | 0.3 | 13067.435 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12236 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 8394.4403 | 0.2 | 0.3 | 13095.3268 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12237 | PEMBROKE PINES | 110347 | Private | 2036 | 5 | Swales | 66.6667 | 22182.8997 | 0.2 | 0.3 | 34605.3235 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3153 | 5200.3153 | 5200.3153 | 5200.3153 | 5200.3153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12238 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13857.2483 | 0.2 | 0.3 | 21617.3073 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8257.0238 | 8257.0238 | 8257.0238 | 8257.0238 | 8257.0238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12239 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17400.2565 | 0.2 | 0.3 | 27144.4001 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7009.2411 | 7009.2411 | 7009.2411 | 7009.2411 | 7009.2411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12240 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17128.6306 | 0.2 | 0.3 | 26720.6637 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6728.1086 | 6728.1086 | 6728.1086 | 6728.1086 | 6728.1086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12241 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16670.1542 | 0.2 | 0.3 | 26005.4406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5973.8073 | 5973.8073 | 5973.8073 | 5973.8073 | 5973.8073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12242 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18122.8363 | 0.2 | 0.3 | 28271.6247 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5277.1708 | 5277.1708 | 5277.1708 | 5277.1708 | 5277.1708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12243 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16973.2534 | 0.2 | 0.3 | 26478.2753 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5233.0156 | 5233.0156 | 5233.0156 | 5233.0156 | 5233.0156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12244 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13223.9988 | 0.2 | 0.3 | 20629.4381 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5213.3297 | 5213.3297 | 5213.3297 | 5213.3297 | 5213.3297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12245 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16759.6285 | 0.2 | 0.3 | 26145.0205 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7396 | 5200.7396 | 5200.7396 | 5200.7396 | 5200.7396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12246 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16687.9316 | 0.2 | 0.3 | 26033.1733 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1114.7061 | 1114.7061 | 1114.7061 | 1114.7061 | 1114.7061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12247 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15899.3232 | 0.2 | 0.3 | 24802.9442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10259.5892 | 10259.5892 | 10259.5892 | 10259.5892 | 10259.5892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12248 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 8731.4145 | 0.2 | 0.3 | 13621.0066 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5536.4048 | 5536.4048 | 5536.4048 | 5536.4048 | 5536.4048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12249 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16681.7837 | 0.2 | 0.3 | 26023.5825 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7174.2518 | 7174.2518 | 7174.2518 | 7174.2518 | 7174.2518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12250 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21073.5933 | 0.2 | 0.3 | 32874.8056 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.352 | 5200.352 | 5200.352 | 5200.352 | 5200.352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12251 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16340.5595 | 0.2 | 0.3 | 25491.2728 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2775 | 5200.2775 | 5200.2775 | 5200.2775 | 5200.2775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12252 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16187.4367 | 0.2 | 0.3 | 25252.4013 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6992.2052 | 6992.2052 | 6992.2052 | 6992.2052 | 6992.2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12253 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 30408.7994 | 0.2 | 0.3 | 47437.7271 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.146 | 5200.146 | 5200.146 | 5200.146 | 5200.146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12254 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18422.463 | 0.2 | 0.3 | 28739.0423 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12255 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 3233.8839 | 0.2 | 0.3 | 5044.8589 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6306.9752 | 6306.9752 | 6306.9752 | 6306.9752 | 6306.9752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12256 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10093.5671 | 0.2 | 0.3 | 15745.9646 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5725.4267 | 5725.4267 | 5725.4267 | 5725.4267 | 5725.4267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12257 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18878.7942 | 0.2 | 0.3 | 29450.919 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12258 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17661.2373 | 0.2 | 0.3 | 27551.5302 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2923.5756 | 2923.5756 | 2923.5756 | 2923.5756 | 2923.5756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12259 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17173.3191 | 0.2 | 0.3 | 26790.3778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6224.3492 | 6224.3492 | 6224.3492 | 6224.3492 | 6224.3492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12260 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 25558.9554 | 0.2 | 0.3 | 39871.9704 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5236.3044 | 5236.3044 | 5236.3044 | 5236.3044 | 5236.3044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12261 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 633.9225 | 0.2 | 0.3 | 988.9192 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5215.0151 | 5215.0151 | 5215.0151 | 5215.0151 | 5215.0151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12262 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19019.6484 | 0.2 | 0.3 | 29670.6515 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2156 | 5201.2156 | 5201.2156 | 5201.2156 | 5201.2156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12263 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16668.2404 | 0.2 | 0.3 | 26002.455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3459.6739 | 3459.6739 | 3459.6739 | 3459.6739 | 3459.6739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12264 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 487.5816 | 0.2 | 0.3 | 760.6273 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7333.8596 | 7333.8596 | 7333.8596 | 7333.8596 | 7333.8596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12265 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 29469.0647 | 0.2 | 0.3 | 45971.741 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12266 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1386.0707 | 0.2 | 0.3 | 2162.2703 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9798 | 5200.9798 | 5200.9798 | 5200.9798 | 5200.9798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12267 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12321.6583 | 0.2 | 0.3 | 19221.787 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1238.1131 | 1238.1131 | 1238.1131 | 1238.1131 | 1238.1131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12268 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 5779.4748 | 0.2 | 0.3 | 9015.9807 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5239.7715 | 5239.7715 | 5239.7715 | 5239.7715 | 5239.7715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12269 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20771.8985 | 0.2 | 0.3 | 32404.1616 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12270 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22684.9145 | 0.2 | 0.3 | 35388.4667 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8989.2669 | 8989.2669 | 8989.2669 | 8989.2669 | 8989.2669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12271 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1079.0685 | 0.2 | 0.3 | 1683.3469 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5844.9311 | 5844.9311 | 5844.9311 | 5844.9311 | 5844.9311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12272 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16672.6149 | 0.2 | 0.3 | 26009.2792 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12273 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16657.02 | 0.2 | 0.3 | 25984.9512 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6394.9326 | 6394.9326 | 6394.9326 | 6394.9326 | 6394.9326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12274 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16684.6346 | 0.2 | 0.3 | 26028.03 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0191 | 5200.0191 | 5200.0191 | 5200.0191 | 5200.0191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12275 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16125.0223 | 0.2 | 0.3 | 25155.0348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5335 | 5200.5335 | 5200.5335 | 5200.5335 | 5200.5335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12276 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18048.4065 | 0.2 | 0.3 | 28155.5141 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1477 | 5200.1477 | 5200.1477 | 5200.1477 | 5200.1477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12277 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11773.9517 | 0.2 | 0.3 | 18367.3647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2066 | 5200.2066 | 5200.2066 | 5200.2066 | 5200.2066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12278 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17642.0991 | 0.2 | 0.3 | 27521.6746 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8102.0081 | 8102.0081 | 8102.0081 | 8102.0081 | 8102.0081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12279 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17762.1659 | 0.2 | 0.3 | 27708.9788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5284.8625 | 5284.8625 | 5284.8625 | 5284.8625 | 5284.8625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12280 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 269.3765 | 0.2 | 0.3 | 420.2273 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9868 | 5199.9868 | 5199.9868 | 5199.9868 | 5199.9868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12281 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16091.689 | 0.2 | 0.3 | 25103.0348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12282 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 9657.3146 | 0.2 | 0.3 | 15065.4108 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9019.5466 | 9019.5466 | 9019.5466 | 9019.5466 | 9019.5466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12283 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16072.8909 | 0.2 | 0.3 | 25073.7099 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2024.0817 | 2024.0817 | 2024.0817 | 2024.0817 | 2024.0817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12284 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 26689.7822 | 0.2 | 0.3 | 41636.0602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2238 | 5200.2238 | 5200.2238 | 5200.2238 | 5200.2238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12285 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 8423.5817 | 0.2 | 0.3 | 13140.7875 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7194 | 5202.7194 | 5202.7194 | 5202.7194 | 5202.7194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12286 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12781.5848 | 0.2 | 0.3 | 19939.2723 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5219.5944 | 5219.5944 | 5219.5944 | 5219.5944 | 5219.5944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12287 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16678.3563 | 0.2 | 0.3 | 26018.2358 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9463.3392 | 9463.3392 | 9463.3392 | 9463.3392 | 9463.3392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12288 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 952.7273 | 0.2 | 0.3 | 1486.2545 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5249.0553 | 5249.0553 | 5249.0553 | 5249.0553 | 5249.0553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12289 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16105.6225 | 0.2 | 0.3 | 25124.771 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5214.8227 | 5214.8227 | 5214.8227 | 5214.8227 | 5214.8227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12290 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 9647.7753 | 0.2 | 0.3 | 15050.5294 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5579 | 5203.5579 | 5203.5579 | 5203.5579 | 5203.5579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12291 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16849.3517 | 0.2 | 0.3 | 26284.9887 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7353.6025 | 7353.6025 | 7353.6025 | 7353.6025 | 7353.6025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12292 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13991.2704 | 0.2 | 0.3 | 21826.3818 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12293 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10151.2803 | 0.2 | 0.3 | 15835.9973 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6167.3924 | 6167.3924 | 6167.3924 | 6167.3924 | 6167.3924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12294 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 29642.4465 | 0.2 | 0.3 | 46242.2166 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5602 | 5200.5602 | 5200.5602 | 5200.5602 | 5200.5602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12295 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16678.6297 | 0.2 | 0.3 | 26018.6624 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12296 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16690.5495 | 0.2 | 0.3 | 26037.2573 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12297 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 9372.4203 | 0.2 | 0.3 | 14620.9756 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6603 | 5200.6603 | 5200.6603 | 5200.6603 | 5200.6603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12298 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17332.1223 | 0.2 | 0.3 | 27038.1108 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8249.8597 | 8249.8597 | 8249.8597 | 8249.8597 | 8249.8597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12299 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1687.0256 | 0.2 | 0.3 | 2631.7599 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6345.5411 | 6345.5411 | 6345.5411 | 6345.5411 | 6345.5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12300 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 7463.7037 | 0.2 | 0.3 | 11643.3777 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0238 | 5200.0238 | 5200.0238 | 5200.0238 | 5200.0238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12301 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17123.2189 | 0.2 | 0.3 | 26712.2215 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12302 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16696.4009 | 0.2 | 0.3 | 26046.3854 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9240.5074 | 9240.5074 | 9240.5074 | 9240.5074 | 9240.5074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12303 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14195.5187 | 0.2 | 0.3 | 22145.0091 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5279.6345 | 5279.6345 | 5279.6345 | 5279.6345 | 5279.6345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12304 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15539.2145 | 0.2 | 0.3 | 24241.1747 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4804 | 5200.4804 | 5200.4804 | 5200.4804 | 5200.4804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12305 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17053.7049 | 0.2 | 0.3 | 26603.7797 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.421 | 5201.421 | 5201.421 | 5201.421 | 5201.421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12306 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16690.386 | 0.2 | 0.3 | 26037.0022 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5216.9263 | 5216.9263 | 5216.9263 | 5216.9263 | 5216.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12307 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9454.4486 | 9454.4486 | 9454.4486 | 9454.4486 | 9454.4486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12308 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20014.3753 | 0.2 | 0.3 | 31222.4255 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5254.2229 | 5254.2229 | 5254.2229 | 5254.2229 | 5254.2229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12309 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 29538.2666 | 0.2 | 0.3 | 46079.6959 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5216.2285 | 5216.2285 | 5216.2285 | 5216.2285 | 5216.2285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12310 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2985.23 | 0.2 | 0.3 | 4656.9588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.6668 | 5203.6668 | 5203.6668 | 5203.6668 | 5203.6668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12311 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16720.0165 | 0.2 | 0.3 | 26083.2258 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5308.8236 | 5308.8236 | 5308.8236 | 5308.8236 | 5308.8236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12312 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16680.0143 | 0.2 | 0.3 | 26020.8223 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12313 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8219.6317 | 8219.6317 | 8219.6317 | 8219.6317 | 8219.6317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12314 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4341.4556 | 4341.4556 | 4341.4556 | 4341.4556 | 4341.4556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12315 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16673.459 | 0.2 | 0.3 | 26010.596 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9795 | 5199.9795 | 5199.9795 | 5199.9795 | 5199.9795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12316 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 7538.5882 | 0.2 | 0.3 | 11760.1976 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3364.3238 | 3364.3238 | 3364.3238 | 3364.3238 | 3364.3238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12317 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16724.2496 | 0.2 | 0.3 | 26089.8294 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5150.5984 | 5150.5984 | 5150.5984 | 5150.5984 | 5150.5984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12318 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1.6969 | 0.2 | 0.3 | 2.6471 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1321 | 5200.1321 | 5200.1321 | 5200.1321 | 5200.1321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12319 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 30909.6231 | 0.2 | 0.3 | 48219.012 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7169 | 5201.7169 | 5201.7169 | 5201.7169 | 5201.7169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12320 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16699.1213 | 0.2 | 0.3 | 26050.6292 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5216.3003 | 5216.3003 | 5216.3003 | 5216.3003 | 5216.3003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12321 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 27637.5434 | 0.2 | 0.3 | 43114.5677 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9457.1725 | 9457.1725 | 9457.1725 | 9457.1725 | 9457.1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12322 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 31341.8837 | 0.2 | 0.3 | 48893.3385 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5253.3523 | 5253.3523 | 5253.3523 | 5253.3523 | 5253.3523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12323 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12672.1363 | 0.2 | 0.3 | 19768.5327 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5222.9024 | 5222.9024 | 5222.9024 | 5222.9024 | 5222.9024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12324 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13670.0465 | 0.2 | 0.3 | 21325.2725 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2038 | 5202.2038 | 5202.2038 | 5202.2038 | 5202.2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12325 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 5043.2865 | 0.2 | 0.3 | 7867.5269 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7306.8454 | 7306.8454 | 7306.8454 | 7306.8454 | 7306.8454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12326 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 28870.1981 | 0.2 | 0.3 | 45037.5091 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12327 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17389.7089 | 0.2 | 0.3 | 27127.9458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4072.5474 | 4072.5474 | 4072.5474 | 4072.5474 | 4072.5474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12328 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 28513.5297 | 0.2 | 0.3 | 44481.1064 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6157.3562 | 6157.3562 | 6157.3562 | 6157.3562 | 6157.3562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12329 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16675.0755 | 0.2 | 0.3 | 26013.1177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1903 | 5201.1903 | 5201.1903 | 5201.1903 | 5201.1903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12330 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17149.274 | 0.2 | 0.3 | 26752.8674 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5213.3016 | 5213.3016 | 5213.3016 | 5213.3016 | 5213.3016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12331 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 9064.5853 | 0.2 | 0.3 | 14140.7531 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9453.27 | 9453.27 | 9453.27 | 9453.27 | 9453.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12332 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16673.3407 | 0.2 | 0.3 | 26010.4115 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5257.0404 | 5257.0404 | 5257.0404 | 5257.0404 | 5257.0404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12333 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 25355.3987 | 0.2 | 0.3 | 39554.422 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5222.522 | 5222.522 | 5222.522 | 5222.522 | 5222.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12334 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16691.1292 | 0.2 | 0.3 | 26038.1616 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.4174 | 5204.4174 | 5204.4174 | 5204.4174 | 5204.4174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12335 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13427.8832 | 0.2 | 0.3 | 20947.4978 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5454.4333 | 5454.4333 | 5454.4333 | 5454.4333 | 5454.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12336 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 29085.6295 | 0.2 | 0.3 | 45373.5821 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12337 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16676.4335 | 0.2 | 0.3 | 26015.2362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3680.9777 | 3680.9777 | 3680.9777 | 3680.9777 | 3680.9777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12338 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1015 | 5200.1015 | 5200.1015 | 5200.1015 | 5200.1015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12339 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4293 | 0.2 | 0.3 | 26001.1897 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.0763 | 5203.0763 | 5203.0763 | 5203.0763 | 5203.0763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12340 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17536.3229 | 0.2 | 0.3 | 27356.6638 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4292 | 5200.4292 | 5200.4292 | 5200.4292 | 5200.4292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12341 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16670.0185 | 0.2 | 0.3 | 26005.2289 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3296 | 5200.3296 | 5200.3296 | 5200.3296 | 5200.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12342 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 4971.4015 | 0.2 | 0.3 | 7755.3864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8635.56 | 8635.56 | 8635.56 | 8635.56 | 8635.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12343 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16681.3637 | 0.2 | 0.3 | 26022.9274 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7162.1319 | 7162.1319 | 7162.1319 | 7162.1319 | 7162.1319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12344 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16695.4637 | 0.2 | 0.3 | 26044.9233 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12345 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11034.2435 | 0.2 | 0.3 | 17213.4198 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7862.2534 | 7862.2534 | 7862.2534 | 7862.2534 | 7862.2534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12346 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17022.5581 | 0.2 | 0.3 | 26555.1907 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 957.7688 | 957.7688 | 957.7688 | 957.7688 | 957.7688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12347 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16668.891 | 0.2 | 0.3 | 26003.47 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2599.7994 | 2599.7994 | 2599.7994 | 2599.7994 | 2599.7994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12348 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17604.2268 | 0.2 | 0.3 | 27462.5938 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7497.3858 | 7497.3858 | 7497.3858 | 7497.3858 | 7497.3858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12349 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 7331.2996 | 0.2 | 0.3 | 11436.8274 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5374 | 5201.5374 | 5201.5374 | 5201.5374 | 5201.5374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12350 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18163.9714 | 0.2 | 0.3 | 28335.7954 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5212.0676 | 5212.0676 | 5212.0676 | 5212.0676 | 5212.0676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12351 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9448.9592 | 9448.9592 | 9448.9592 | 9448.9592 | 9448.9592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12352 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22043.6661 | 0.2 | 0.3 | 34388.1192 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5261.0712 | 5261.0712 | 5261.0712 | 5261.0712 | 5261.0712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12353 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 4258.8417 | 0.2 | 0.3 | 6643.7931 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5225.0472 | 5225.0472 | 5225.0472 | 5225.0472 | 5225.0472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12354 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16146.5422 | 0.2 | 0.3 | 25188.6058 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9758 | 5203.9758 | 5203.9758 | 5203.9758 | 5203.9758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12355 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17344.4216 | 0.2 | 0.3 | 27057.2977 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9161.5708 | 9161.5708 | 9161.5708 | 9161.5708 | 9161.5708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12356 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14959.2453 | 0.2 | 0.3 | 23336.4226 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12357 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22556.8826 | 0.2 | 0.3 | 35188.7369 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5657.7765 | 5657.7765 | 5657.7765 | 5657.7765 | 5657.7765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12358 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 28885.8243 | 0.2 | 0.3 | 45061.886 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.042 | 5201.042 | 5201.042 | 5201.042 | 5201.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12359 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16673.9819 | 0.2 | 0.3 | 26011.4117 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3893 | 5200.3893 | 5200.3893 | 5200.3893 | 5200.3893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12360 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9156 | 5199.9156 | 5199.9156 | 5199.9156 | 5199.9156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12361 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13438.8014 | 0.2 | 0.3 | 20964.5302 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9938 | 5199.9938 | 5199.9938 | 5199.9938 | 5199.9938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12362 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 3054.0289 | 0.2 | 0.3 | 4764.2851 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8733.5122 | 8733.5122 | 8733.5122 | 8733.5122 | 8733.5122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12363 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16900.6789 | 0.2 | 0.3 | 26365.059 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9274.3415 | 9274.3415 | 9274.3415 | 9274.3415 | 9274.3415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12364 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16674.9004 | 0.2 | 0.3 | 26012.8446 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12365 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 23872.476 | 0.2 | 0.3 | 37241.0626 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7407.0377 | 7407.0377 | 7407.0377 | 7407.0377 | 7407.0377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12366 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 23328.7021 | 0.2 | 0.3 | 36392.7752 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2595.261 | 2595.261 | 2595.261 | 2595.261 | 2595.261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12367 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13187.2319 | 0.2 | 0.3 | 20572.0818 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8971.3299 | 8971.3299 | 8971.3299 | 8971.3299 | 8971.3299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12368 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16889.2358 | 0.2 | 0.3 | 26347.2078 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6400.1373 | 6400.1373 | 6400.1373 | 6400.1373 | 6400.1373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12369 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16788.952 | 0.2 | 0.3 | 26190.7651 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5544.8092 | 5544.8092 | 5544.8092 | 5544.8092 | 5544.8092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12370 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16670.1713 | 0.2 | 0.3 | 26005.4673 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1393 | 5200.1393 | 5200.1393 | 5200.1393 | 5200.1393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12371 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22613.9047 | 0.2 | 0.3 | 35277.6913 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12372 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 27560.8072 | 0.2 | 0.3 | 42994.8592 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12373 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14836.6175 | 0.2 | 0.3 | 23145.1232 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3784 | 5200.3784 | 5200.3784 | 5200.3784 | 5200.3784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12374 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17003.2473 | 0.2 | 0.3 | 26525.0657 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8894.4122 | 8894.4122 | 8894.4122 | 8894.4122 | 8894.4122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12375 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16778.6275 | 0.2 | 0.3 | 26174.659 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9803.2549 | 9803.2549 | 9803.2549 | 9803.2549 | 9803.2549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12376 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15296.4861 | 0.2 | 0.3 | 23862.5184 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12377 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 33135.4629 | 0.2 | 0.3 | 51691.3222 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7401.7553 | 7401.7553 | 7401.7553 | 7401.7553 | 7401.7553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12378 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 33291.1397 | 0.2 | 0.3 | 51934.1779 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2727.2758 | 2727.2758 | 2727.2758 | 2727.2758 | 2727.2758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12379 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 25698.9891 | 0.2 | 0.3 | 40090.4229 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12380 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 25217.4455 | 0.2 | 0.3 | 39339.2149 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12381 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 0.89353 | 0.2 | 0.3 | 1.3939 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7178.7152 | 7178.7152 | 7178.7152 | 7178.7152 | 7178.7152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12382 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 34533.1679 | 0.2 | 0.3 | 53871.7419 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9402.4122 | 9402.4122 | 9402.4122 | 9402.4122 | 9402.4122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12383 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 38486.6332 | 0.2 | 0.3 | 60039.1478 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5209.9613 | 5209.9613 | 5209.9613 | 5209.9613 | 5209.9613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12384 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 24999.4299 | 0.2 | 0.3 | 38999.1107 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5250.4592 | 5250.4592 | 5250.4592 | 5250.4592 | 5250.4592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12385 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 33791.7873 | 0.2 | 0.3 | 52715.1882 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6294.7228 | 6294.7228 | 6294.7228 | 6294.7228 | 6294.7228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12386 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18088.7063 | 0.2 | 0.3 | 28218.3819 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6085 | 5200.6085 | 5200.6085 | 5200.6085 | 5200.6085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12387 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 45862.173 | 0.2 | 0.3 | 71544.9899 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7217 | 5200.7217 | 5200.7217 | 5200.7217 | 5200.7217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12388 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4436.5178 | 4436.5178 | 4436.5178 | 4436.5178 | 4436.5178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12389 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14889.1038 | 0.2 | 0.3 | 23227.0019 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5614.4166 | 5614.4166 | 5614.4166 | 5614.4166 | 5614.4166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12390 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 32842.3263 | 0.2 | 0.3 | 51234.029 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12391 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 33333.7468 | 0.2 | 0.3 | 52000.645 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12392 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 34888.9405 | 0.2 | 0.3 | 54426.7471 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1576 | 5200.1576 | 5200.1576 | 5200.1576 | 5200.1576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12393 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 26140.8215 | 0.2 | 0.3 | 40779.6816 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9087.993 | 9087.993 | 9087.993 | 9087.993 | 9087.993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12394 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18060.2405 | 0.2 | 0.3 | 28173.9751 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.4849 | 9778.4849 | 9778.4849 | 9778.4849 | 9778.4849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12395 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16703.3135 | 0.2 | 0.3 | 26057.169 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12396 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19273.0666 | 0.2 | 0.3 | 30065.9839 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5573.7238 | 5573.7238 | 5573.7238 | 5573.7238 | 5573.7238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12397 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 7972.717 | 0.2 | 0.3 | 12437.4385 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4688.8305 | 4688.8305 | 4688.8305 | 4688.8305 | 4688.8305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12398 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19488.7545 | 0.2 | 0.3 | 30402.4571 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9713.3115 | 9713.3115 | 9713.3115 | 9713.3115 | 9713.3115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12399 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0952 | 0.2 | 0.3 | 26000.6685 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12400 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1565 | 0.2 | 0.3 | 26000.7641 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12401 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16667.2643 | 0.2 | 0.3 | 26000.9323 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7223.838 | 7223.838 | 7223.838 | 7223.838 | 7223.838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12402 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18199.4911 | 0.2 | 0.3 | 28391.2061 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1080.5208 | 1080.5208 | 1080.5208 | 1080.5208 | 1080.5208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12403 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 8922.7231 | 0.2 | 0.3 | 13919.448 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7722.1892 | 7722.1892 | 7722.1892 | 7722.1892 | 7722.1892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12404 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 25343.3213 | 0.2 | 0.3 | 39535.5813 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5209.5294 | 5209.5294 | 5209.5294 | 5209.5294 | 5209.5294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12405 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16668.2404 | 0.2 | 0.3 | 26002.455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5238.1342 | 5238.1342 | 5238.1342 | 5238.1342 | 5238.1342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12406 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21983.6175 | 0.2 | 0.3 | 34294.4432 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7534.483 | 7534.483 | 7534.483 | 7534.483 | 7534.483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12407 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17130.8938 | 0.2 | 0.3 | 26724.1943 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4616 | 5200.4616 | 5200.4616 | 5200.4616 | 5200.4616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12408 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2217.5701 | 0.2 | 0.3 | 3459.4094 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6516 | 5200.6516 | 5200.6516 | 5200.6516 | 5200.6516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12409 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15882.3349 | 0.2 | 0.3 | 24776.4424 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9483.4276 | 9483.4276 | 9483.4276 | 9483.4276 | 9483.4276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12410 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 534.1857 | 0.2 | 0.3 | 833.3297 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5195.8563 | 5195.8563 | 5195.8563 | 5195.8563 | 5195.8563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12411 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16647.6643 | 0.2 | 0.3 | 25970.3563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9579.4223 | 9579.4223 | 9579.4223 | 9579.4223 | 9579.4223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12412 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 27585.9098 | 0.2 | 0.3 | 43034.0193 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5834.9348 | 5834.9348 | 5834.9348 | 5834.9348 | 5834.9348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12413 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16677.1441 | 0.2 | 0.3 | 26016.3448 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7269.522 | 7269.522 | 7269.522 | 7269.522 | 7269.522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12414 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16677.2298 | 0.2 | 0.3 | 26016.4785 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7291.3304 | 7291.3304 | 7291.3304 | 7291.3304 | 7291.3304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12415 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21468.9146 | 0.2 | 0.3 | 33491.5068 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12416 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 23151.399 | 0.2 | 0.3 | 36116.1824 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1169.3198 | 1169.3198 | 1169.3198 | 1169.3198 | 1169.3198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12417 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16851.2527 | 0.2 | 0.3 | 26287.9543 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4907.2275 | 4907.2275 | 4907.2275 | 4907.2275 | 4907.2275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12418 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18138.0767 | 0.2 | 0.3 | 28295.3997 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5207.517 | 5207.517 | 5207.517 | 5207.517 | 5207.517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12419 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22612.4108 | 0.2 | 0.3 | 35275.3608 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5235.9491 | 5235.9491 | 5235.9491 | 5235.9491 | 5235.9491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12420 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16944.6697 | 0.2 | 0.3 | 26433.6847 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8722.4599 | 8722.4599 | 8722.4599 | 8722.4599 | 8722.4599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12421 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 8042.7489 | 0.2 | 0.3 | 12546.6883 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8766.408 | 8766.408 | 8766.408 | 8766.408 | 8766.408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12422 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 9222.1957 | 0.2 | 0.3 | 14386.6252 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5368.9605 | 5368.9605 | 5368.9605 | 5368.9605 | 5368.9605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12423 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2484.9707 | 0.2 | 0.3 | 3876.5542 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12424 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19893.3217 | 0.2 | 0.3 | 31033.5818 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9110.0349 | 9110.0349 | 9110.0349 | 9110.0349 | 9110.0349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12425 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20317.895 | 0.2 | 0.3 | 31695.9162 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1097 | 2600.1097 | 2600.1097 | 2600.1097 | 2600.1097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12426 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17437.7117 | 0.2 | 0.3 | 27202.8302 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12427 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 7889.9465 | 0.2 | 0.3 | 12308.3165 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3156.7063 | 3156.7063 | 3156.7063 | 3156.7063 | 3156.7063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12428 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14203.9107 | 0.2 | 0.3 | 22158.1007 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8687.8102 | 8687.8102 | 8687.8102 | 8687.8102 | 8687.8102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12429 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 27700.4589 | 0.2 | 0.3 | 43212.7159 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8004.5844 | 8004.5844 | 8004.5844 | 8004.5844 | 8004.5844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12430 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16671.2479 | 0.2 | 0.3 | 26007.1467 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8196.088 | 8196.088 | 8196.088 | 8196.088 | 8196.088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12431 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14665.9721 | 0.2 | 0.3 | 22878.9164 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9350.2032 | 9350.2032 | 9350.2032 | 9350.2032 | 9350.2032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12432 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12091.1591 | 0.2 | 0.3 | 18862.2081 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12433 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16862.6651 | 0.2 | 0.3 | 26305.7576 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7315.1697 | 7315.1697 | 7315.1697 | 7315.1697 | 7315.1697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12434 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 31493.8909 | 0.2 | 0.3 | 49130.4699 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7245.5552 | 7245.5552 | 7245.5552 | 7245.5552 | 7245.5552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12435 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12376.8707 | 0.2 | 0.3 | 19307.9183 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12436 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11608.5109 | 0.2 | 0.3 | 18109.2771 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5664.2636 | 5664.2636 | 5664.2636 | 5664.2636 | 5664.2636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12437 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 5830.7061 | 0.2 | 0.3 | 9095.9016 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 292.8063 | 292.8063 | 292.8063 | 292.8063 | 292.8063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12438 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16872.7117 | 0.2 | 0.3 | 26321.4302 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 560.6225 | 560.6225 | 560.6225 | 560.6225 | 560.6225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12439 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 4063.3659 | 0.2 | 0.3 | 6338.8509 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8210.5089 | 8210.5089 | 8210.5089 | 8210.5089 | 8210.5089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12440 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16746.6294 | 0.2 | 0.3 | 26124.7419 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8557.3165 | 8557.3165 | 8557.3165 | 8557.3165 | 8557.3165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12441 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 9340.6615 | 0.2 | 0.3 | 14571.4319 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7785 | 5200.7785 | 5200.7785 | 5200.7785 | 5200.7785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12442 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20967.393 | 0.2 | 0.3 | 32709.1331 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12443 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15105.7951 | 0.2 | 0.3 | 23565.0404 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7263.2177 | 7263.2177 | 7263.2177 | 7263.2177 | 7263.2177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12444 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19368.4709 | 0.2 | 0.3 | 30214.8147 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5079.0705 | 5079.0705 | 5079.0705 | 5079.0705 | 5079.0705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12445 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18470.9349 | 0.2 | 0.3 | 28814.6585 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.746 | 5206.746 | 5206.746 | 5206.746 | 5206.746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12446 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13966.8885 | 0.2 | 0.3 | 21788.3461 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5179.2789 | 5179.2789 | 5179.2789 | 5179.2789 | 5179.2789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12447 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 4210.3797 | 0.2 | 0.3 | 6568.1924 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.602 | 5201.602 | 5201.602 | 5201.602 | 5201.602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12448 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16389.6375 | 0.2 | 0.3 | 25567.8344 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6062 | 5201.6062 | 5201.6062 | 5201.6062 | 5201.6062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12449 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17996.0462 | 0.2 | 0.3 | 28073.8321 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9223.4053 | 9223.4053 | 9223.4053 | 9223.4053 | 9223.4053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12450 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 29405.029 | 0.2 | 0.3 | 45871.8452 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12451 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16676.1305 | 0.2 | 0.3 | 26014.7636 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7360.2649 | 7360.2649 | 7360.2649 | 7360.2649 | 7360.2649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12452 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14954.7423 | 0.2 | 0.3 | 23329.3979 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7200.4143 | 7200.4143 | 7200.4143 | 7200.4143 | 7200.4143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12453 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18693.2217 | 0.2 | 0.3 | 29161.4258 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12454 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20256.5043 | 0.2 | 0.3 | 31600.1468 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7735.6903 | 7735.6903 | 7735.6903 | 7735.6903 | 7735.6903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12455 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15541.8313 | 0.2 | 0.3 | 24245.2569 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.256 | 5200.256 | 5200.256 | 5200.256 | 5200.256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12456 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17072.961 | 0.2 | 0.3 | 26633.8192 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.7149 | 5205.7149 | 5205.7149 | 5205.7149 | 5205.7149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12457 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17796.7812 | 0.2 | 0.3 | 27762.9787 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4668.014 | 4668.014 | 4668.014 | 4668.014 | 4668.014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12458 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22906.5444 | 0.2 | 0.3 | 35734.2093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1423.9429 | 1423.9429 | 1423.9429 | 1423.9429 | 1423.9429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12459 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20718.3571 | 0.2 | 0.3 | 32320.637 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7789.7261 | 7789.7261 | 7789.7261 | 7789.7261 | 7789.7261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12460 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16843.5005 | 0.2 | 0.3 | 26275.8608 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8430.1915 | 8430.1915 | 8430.1915 | 8430.1915 | 8430.1915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12461 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 3243.2996 | 0.2 | 0.3 | 5059.5474 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12462 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 43627.149 | 0.2 | 0.3 | 68058.3524 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7293.9277 | 7293.9277 | 7293.9277 | 7293.9277 | 7293.9277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12463 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 25274.7754 | 0.2 | 0.3 | 39428.6496 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6816.3897 | 6816.3897 | 6816.3897 | 6816.3897 | 6816.3897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12464 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17046.7726 | 0.2 | 0.3 | 26592.9653 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3864 | 5201.3864 | 5201.3864 | 5201.3864 | 5201.3864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12465 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22144.012 | 0.2 | 0.3 | 34544.6587 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12466 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14933.7399 | 0.2 | 0.3 | 23296.6343 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12467 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17899.9059 | 0.2 | 0.3 | 27923.8532 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12468 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16793.5276 | 0.2 | 0.3 | 26197.9031 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9096.0537 | 9096.0537 | 9096.0537 | 9096.0537 | 9096.0537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12469 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22854.5899 | 0.2 | 0.3 | 35653.1602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12470 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 8975.8877 | 0.2 | 0.3 | 14002.3848 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7405.3181 | 7405.3181 | 7405.3181 | 7405.3181 | 7405.3181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12471 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16674.075 | 0.2 | 0.3 | 26011.557 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7155.4891 | 7155.4891 | 7155.4891 | 7155.4891 | 7155.4891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12472 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 24443.4153 | 0.2 | 0.3 | 38131.7278 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12473 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17546.1637 | 0.2 | 0.3 | 27372.0153 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5212.245 | 5212.245 | 5212.245 | 5212.245 | 5212.245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12474 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2111.7369 | 0.2 | 0.3 | 3294.3095 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 5199.8939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12475 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 276.3963 | 0.2 | 0.3 | 431.1782 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.2369 | 5206.2369 | 5206.2369 | 5206.2369 | 5206.2369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12476 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11085.2935 | 0.2 | 0.3 | 17293.0579 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5225.4071 | 5225.4071 | 5225.4071 | 5225.4071 | 5225.4071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12477 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17620.8301 | 0.2 | 0.3 | 27488.495 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5259.9895 | 5259.9895 | 5259.9895 | 5259.9895 | 5259.9895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12478 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17327.5179 | 0.2 | 0.3 | 27030.928 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1736.2295 | 1736.2295 | 1736.2295 | 1736.2295 | 1736.2295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12479 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16767.6775 | 0.2 | 0.3 | 26157.577 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8330.0261 | 8330.0261 | 8330.0261 | 8330.0261 | 8330.0261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12480 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 33880.2466 | 0.2 | 0.3 | 52853.1847 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12481 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10490.3437 | 0.2 | 0.3 | 16364.9361 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6932.0763 | 6932.0763 | 6932.0763 | 6932.0763 | 6932.0763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12482 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 23647.5574 | 0.2 | 0.3 | 36890.1895 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6650.309 | 6650.309 | 6650.309 | 6650.309 | 6650.309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12483 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 7041.135 | 0.2 | 0.3 | 10984.1706 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3266 | 5201.3266 | 5201.3266 | 5201.3266 | 5201.3266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12484 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19485.569 | 0.2 | 0.3 | 30397.4876 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12485 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16730.0293 | 0.2 | 0.3 | 26098.8458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12486 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16744.6929 | 0.2 | 0.3 | 26121.721 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12487 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 26663.5123 | 0.2 | 0.3 | 41595.0791 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9080.109 | 9080.109 | 9080.109 | 9080.109 | 9080.109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12488 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14038.8755 | 0.2 | 0.3 | 21900.6457 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6915.432 | 6915.432 | 6915.432 | 6915.432 | 6915.432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12489 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17471.3992 | 0.2 | 0.3 | 27255.3828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5744.0929 | 5744.0929 | 5744.0929 | 5744.0929 | 5744.0929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12490 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16672.174 | 0.2 | 0.3 | 26008.5914 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5800.7146 | 5800.7146 | 5800.7146 | 5800.7146 | 5800.7146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12491 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14265.164 | 0.2 | 0.3 | 22253.6558 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5907.8124 | 5907.8124 | 5907.8124 | 5907.8124 | 5907.8124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12492 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16705.4345 | 0.2 | 0.3 | 26060.4779 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6265.826 | 6265.826 | 6265.826 | 6265.826 | 6265.826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12493 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12804.0355 | 0.2 | 0.3 | 19974.2953 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6898.1467 | 6898.1467 | 6898.1467 | 6898.1467 | 6898.1467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12494 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16689.4335 | 0.2 | 0.3 | 26035.5163 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7825.8832 | 7825.8832 | 7825.8832 | 7825.8832 | 7825.8832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12495 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 159.4161 | 0.2 | 0.3 | 248.6892 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8217.1984 | 8217.1984 | 8217.1984 | 8217.1984 | 8217.1984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12496 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14712.7644 | 0.2 | 0.3 | 22951.9125 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12497 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17016.941 | 0.2 | 0.3 | 26546.428 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5222.4069 | 5222.4069 | 5222.4069 | 5222.4069 | 5222.4069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12498 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14371.1051 | 0.2 | 0.3 | 22418.9239 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6303.3551 | 6303.3551 | 6303.3551 | 6303.3551 | 6303.3551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12499 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20927.7308 | 0.2 | 0.3 | 32647.26 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4554 | 5201.4554 | 5201.4554 | 5201.4554 | 5201.4554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12500 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16728.9589 | 0.2 | 0.3 | 26097.1758 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12501 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17481.4868 | 0.2 | 0.3 | 27271.1194 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4209 | 5201.4209 | 5201.4209 | 5201.4209 | 5201.4209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12502 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17151.3875 | 0.2 | 0.3 | 26756.1646 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4329 | 5201.4329 | 5201.4329 | 5201.4329 | 5201.4329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12503 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10378.0977 | 0.2 | 0.3 | 16189.8324 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6805.6979 | 6805.6979 | 6805.6979 | 6805.6979 | 6805.6979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12504 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 28825.5488 | 0.2 | 0.3 | 44967.8561 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2045 | 5200.2045 | 5200.2045 | 5200.2045 | 5200.2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12505 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12506 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 25011.9883 | 0.2 | 0.3 | 39018.7017 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12507 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 3260.307 | 0.2 | 0.3 | 5086.0789 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1805 | 5200.1805 | 5200.1805 | 5200.1805 | 5200.1805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12508 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 25914.4605 | 0.2 | 0.3 | 40426.5583 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2336 | 5200.2336 | 5200.2336 | 5200.2336 | 5200.2336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12509 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 22971.3295 | 0.2 | 0.3 | 35835.2741 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5079 | 5200.5079 | 5200.5079 | 5200.5079 | 5200.5079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12510 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 2866.4155 | 0.2 | 0.3 | 4471.6081 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1142 | 5201.1142 | 5201.1142 | 5201.1142 | 5201.1142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12511 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16789.3435 | 0.2 | 0.3 | 26191.3758 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5245.9247 | 5245.9247 | 5245.9247 | 5245.9247 | 5245.9247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12512 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 33557.6776 | 0.2 | 0.3 | 52349.9771 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8105.2161 | 8105.2161 | 8105.2161 | 8105.2161 | 8105.2161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12513 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16708.3402 | 0.2 | 0.3 | 26065.0107 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12514 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16674.1415 | 0.2 | 0.3 | 26011.6607 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5302.1932 | 5302.1932 | 5302.1932 | 5302.1932 | 5302.1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12515 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11531.7905 | 0.2 | 0.3 | 17989.5931 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6164.3656 | 6164.3656 | 6164.3656 | 6164.3656 | 6164.3656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12516 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17380.065 | 0.2 | 0.3 | 27112.9014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3152.4647 | 3152.4647 | 3152.4647 | 3152.4647 | 3152.4647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12517 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16893.2151 | 0.2 | 0.3 | 26353.4156 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4252.3649 | 4252.3649 | 4252.3649 | 4252.3649 | 4252.3649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12518 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11697.1339 | 0.2 | 0.3 | 18247.5289 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5198.2117 | 5198.2117 | 5198.2117 | 5198.2117 | 5198.2117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12519 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 23069.8977 | 0.2 | 0.3 | 35989.0404 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 16863.0279 | 16863.0279 | 16863.0279 | 16863.0279 | 16863.0279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12520 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 7551.7822 | 0.2 | 0.3 | 11780.7802 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3189 | 5201.3189 | 5201.3189 | 5201.3189 | 5201.3189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12521 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17181.7267 | 0.2 | 0.3 | 26803.4936 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12522 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16838.1043 | 0.2 | 0.3 | 26267.4428 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7192.7137 | 7192.7137 | 7192.7137 | 7192.7137 | 7192.7137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12523 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16671.7686 | 0.2 | 0.3 | 26007.959 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7055.5341 | 7055.5341 | 7055.5341 | 7055.5341 | 7055.5341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12524 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16915.9058 | 0.2 | 0.3 | 26388.813 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8312 | 5201.8312 | 5201.8312 | 5201.8312 | 5201.8312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12525 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 23565.3449 | 0.2 | 0.3 | 36761.938 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3933.3726 | 3933.3726 | 3933.3726 | 3933.3726 | 3933.3726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12526 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16980.4549 | 0.2 | 0.3 | 26489.5097 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5518.4793 | 5518.4793 | 5518.4793 | 5518.4793 | 5518.4793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12527 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19185.2398 | 0.2 | 0.3 | 29928.9741 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0635 | 5200.0635 | 5200.0635 | 5200.0635 | 5200.0635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12528 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17447.4183 | 0.2 | 0.3 | 27217.9725 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12529 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2404 | 0.2 | 0.3 | 26002.455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12530 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16671.5213 | 0.2 | 0.3 | 26007.5732 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1206 | 5200.1206 | 5200.1206 | 5200.1206 | 5200.1206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12531 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 2633.684 | 0.2 | 0.3 | 4108.547 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12532 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 28535.2063 | 0.2 | 0.3 | 44514.9218 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12533 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 22960.8373 | 0.2 | 0.3 | 35818.9061 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.932 | 5200.932 | 5200.932 | 5200.932 | 5200.932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12534 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 11171.5135 | 0.2 | 0.3 | 17427.5611 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5767.1205 | 5767.1205 | 5767.1205 | 5767.1205 | 5767.1205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12535 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 27158.8593 | 0.2 | 0.3 | 42367.8206 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6804.2036 | 6804.2036 | 6804.2036 | 6804.2036 | 6804.2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12536 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16800.0251 | 0.2 | 0.3 | 26208.0392 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7407.252 | 7407.252 | 7407.252 | 7407.252 | 7407.252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12537 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 13082.7605 | 0.2 | 0.3 | 20409.1064 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11261.9734 | 11261.9734 | 11261.9734 | 11261.9734 | 11261.9734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12538 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 17554.1039 | 0.2 | 0.3 | 27384.4021 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6324.821 | 6324.821 | 6324.821 | 6324.821 | 6324.821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12539 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 17552.4232 | 0.2 | 0.3 | 27381.7802 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4068.0432 | 4068.0432 | 4068.0432 | 4068.0432 | 4068.0432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12540 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15780.6623 | 0.2 | 0.3 | 24617.8331 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1273 | 5200.1273 | 5200.1273 | 5200.1273 | 5200.1273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12541 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17659.6295 | 0.2 | 0.3 | 27549.022 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12542 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 29768.9984 | 0.2 | 0.3 | 46439.6375 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1203.0956 | 1203.0956 | 1203.0956 | 1203.0956 | 1203.0956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12543 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10489.7651 | 0.2 | 0.3 | 16364.0336 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4967.1741 | 4967.1741 | 4967.1741 | 4967.1741 | 4967.1741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12544 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17476.6547 | 0.2 | 0.3 | 27263.5814 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3548.201 | 3548.201 | 3548.201 | 3548.201 | 3548.201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12545 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 8136.957 | 0.2 | 0.3 | 12693.6529 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2608.2336 | 2608.2336 | 2608.2336 | 2608.2336 | 2608.2336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12546 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 4344.6563 | 0.2 | 0.3 | 6777.6639 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 867.042 | 867.042 | 867.042 | 867.042 | 867.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12547 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 9663.8553 | 0.2 | 0.3 | 15075.6142 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5238.3845 | 5238.3845 | 5238.3845 | 5238.3845 | 5238.3845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12548 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17230.6777 | 0.2 | 0.3 | 26879.8572 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6488.7675 | 6488.7675 | 6488.7675 | 6488.7675 | 6488.7675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12549 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16724.3241 | 0.2 | 0.3 | 26089.9455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12550 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16730.7857 | 0.2 | 0.3 | 26100.0257 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12551 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17294.9435 | 0.2 | 0.3 | 26980.1118 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12552 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 3897.7882 | 0.2 | 0.3 | 6080.5496 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6572 | 5201.6572 | 5201.6572 | 5201.6572 | 5201.6572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12553 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14290.2637 | 0.2 | 0.3 | 22292.8114 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6107.1168 | 6107.1168 | 6107.1168 | 6107.1168 | 6107.1168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12554 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16693.9977 | 0.2 | 0.3 | 26042.6365 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1316.696 | 1316.696 | 1316.696 | 1316.696 | 1316.696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12555 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22406.0225 | 0.2 | 0.3 | 34953.395 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7551.9081 | 7551.9081 | 7551.9081 | 7551.9081 | 7551.9081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12556 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 25404.677 | 0.2 | 0.3 | 39631.2961 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1024 | 5200.1024 | 5200.1024 | 5200.1024 | 5200.1024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12557 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16716.2324 | 0.2 | 0.3 | 26077.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12558 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16862.7933 | 0.2 | 0.3 | 26305.9575 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2141 | 5200.2141 | 5200.2141 | 5200.2141 | 5200.2141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12559 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12712.5037 | 0.2 | 0.3 | 19831.5058 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2767 | 5200.2767 | 5200.2767 | 5200.2767 | 5200.2767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12560 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17108.2529 | 0.2 | 0.3 | 26688.8746 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.401 | 5200.401 | 5200.401 | 5200.401 | 5200.401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12561 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 8336.5808 | 0.2 | 0.3 | 13005.066 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7300.1956 | 7300.1956 | 7300.1956 | 7300.1956 | 7300.1956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12562 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10500.9982 | 0.2 | 0.3 | 16381.5572 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4338.5385 | 4338.5385 | 4338.5385 | 4338.5385 | 4338.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12563 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 25145.2765 | 0.2 | 0.3 | 39226.6314 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4479.3937 | 4479.3937 | 4479.3937 | 4479.3937 | 4479.3937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12564 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.6651 | 0.2 | 0.3 | 26006.2376 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9206.6972 | 9206.6972 | 9206.6972 | 9206.6972 | 9206.6972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12565 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16671.5213 | 0.2 | 0.3 | 26007.5732 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10641.6614 | 10641.6614 | 10641.6614 | 10641.6614 | 10641.6614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12566 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 17148.3501 | 0.2 | 0.3 | 26751.4262 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12636.2499 | 12636.2499 | 12636.2499 | 12636.2499 | 12636.2499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12567 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 69.4517 | 0.2 | 0.3 | 108.3447 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6059.4211 | 6059.4211 | 6059.4211 | 6059.4211 | 6059.4211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12568 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16803.3279 | 0.2 | 0.3 | 26213.1916 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6010.5717 | 6010.5717 | 6010.5717 | 6010.5717 | 6010.5717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12569 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 20418.4199 | 0.2 | 0.3 | 31852.735 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12570 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 9262.0994 | 0.2 | 0.3 | 14448.8751 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11706.3832 | 11706.3832 | 11706.3832 | 11706.3832 | 11706.3832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12571 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 17549.3315 | 0.2 | 0.3 | 27376.9571 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11362.7722 | 11362.7722 | 11362.7722 | 11362.7722 | 11362.7722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12572 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 11829.0463 | 0.2 | 0.3 | 18453.3122 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12060.6987 | 12060.6987 | 12060.6987 | 12060.6987 | 12060.6987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12573 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 30711.8731 | 0.2 | 0.3 | 47910.5221 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11282.5706 | 11282.5706 | 11282.5706 | 11282.5706 | 11282.5706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12574 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18504.519 | 0.2 | 0.3 | 28867.0496 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8601.4379 | 8601.4379 | 8601.4379 | 8601.4379 | 8601.4379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12575 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10576.4831 | 0.2 | 0.3 | 16499.3137 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9004.8135 | 9004.8135 | 9004.8135 | 9004.8135 | 9004.8135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12576 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13611.292 | 0.2 | 0.3 | 21233.6155 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3723.5777 | 3723.5777 | 3723.5777 | 3723.5777 | 3723.5777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12577 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16444.3749 | 0.2 | 0.3 | 25653.2249 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6918.7168 | 6918.7168 | 6918.7168 | 6918.7168 | 6918.7168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12578 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1297.7032 | 0.2 | 0.3 | 2024.417 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3785.3745 | 3785.3745 | 3785.3745 | 3785.3745 | 3785.3745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12579 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 8337.1276 | 0.2 | 0.3 | 13005.9191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12580 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 6171.9537 | 0.2 | 0.3 | 9628.2478 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2278 | 5200.2278 | 5200.2278 | 5200.2278 | 5200.2278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12581 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.6231 | 0.2 | 0.3 | 26006.172 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.2702 | 9777.2702 | 9777.2702 | 9777.2702 | 9777.2702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12582 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16671.0882 | 0.2 | 0.3 | 26006.8976 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0268 | 5201.0268 | 5201.0268 | 5201.0268 | 5201.0268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12583 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 1361.1937 | 0.2 | 0.3 | 2123.4622 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12584 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16609.9515 | 0.2 | 0.3 | 25911.5244 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8864.6076 | 8864.6076 | 8864.6076 | 8864.6076 | 8864.6076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12585 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16674.5287 | 0.2 | 0.3 | 26012.2647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2972.9635 | 2972.9635 | 2972.9635 | 2972.9635 | 2972.9635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12586 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 9273.971 | 0.2 | 0.3 | 14467.3948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3254 | 5200.3254 | 5200.3254 | 5200.3254 | 5200.3254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12587 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 8558.4917 | 0.2 | 0.3 | 13351.247 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2751 | 5200.2751 | 5200.2751 | 5200.2751 | 5200.2751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12588 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16669.8398 | 0.2 | 0.3 | 26004.9501 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1405 | 5200.1405 | 5200.1405 | 5200.1405 | 5200.1405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12589 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 22074.0087 | 0.2 | 0.3 | 34435.4536 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3385.0303 | 3385.0303 | 3385.0303 | 3385.0303 | 3385.0303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12590 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 20030.9439 | 0.2 | 0.3 | 31248.2725 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5297.3401 | 5297.3401 | 5297.3401 | 5297.3401 | 5297.3401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12591 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 24740.8148 | 0.2 | 0.3 | 38595.6711 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 433.8829 | 433.8829 | 433.8829 | 433.8829 | 433.8829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12592 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16964.1961 | 0.2 | 0.3 | 26464.146 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 976.9675 | 976.9675 | 976.9675 | 976.9675 | 976.9675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12593 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 26252.4109 | 0.2 | 0.3 | 40953.761 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1995.912 | 1995.912 | 1995.912 | 1995.912 | 1995.912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12594 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 25465.6741 | 0.2 | 0.3 | 39726.4515 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6699.8192 | 6699.8192 | 6699.8192 | 6699.8192 | 6699.8192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12595 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16894.816 | 0.2 | 0.3 | 26355.913 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6560.1748 | 6560.1748 | 6560.1748 | 6560.1748 | 6560.1748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12596 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 23701.1713 | 0.2 | 0.3 | 36973.8272 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4766.7338 | 4766.7338 | 4766.7338 | 4766.7338 | 4766.7338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12597 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 4340.5137 | 0.2 | 0.3 | 6771.2014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4222.926 | 4222.926 | 4222.926 | 4222.926 | 4222.926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12598 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22170.879 | 0.2 | 0.3 | 34586.5712 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3204.591 | 3204.591 | 3204.591 | 3204.591 | 3204.591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12599 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21490.9734 | 0.2 | 0.3 | 33525.9185 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6235.0384 | 6235.0384 | 6235.0384 | 6235.0384 | 6235.0384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12600 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 7951.5838 | 0.2 | 0.3 | 12404.4707 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2171 | 2171 | 2171 | 2171 | 2171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12601 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2157.9103 | 0.2 | 0.3 | 3366.34 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9475.8961 | 9475.8961 | 9475.8961 | 9475.8961 | 9475.8961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12602 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20038.7477 | 0.2 | 0.3 | 31260.4464 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2918.2591 | 2918.2591 | 2918.2591 | 2918.2591 | 2918.2591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12603 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12296.7493 | 0.2 | 0.3 | 19182.929 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7602.0999 | 7602.0999 | 7602.0999 | 7602.0999 | 7602.0999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12604 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12605 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.9745 | 0.2 | 0.3 | 26006.7202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5329.1758 | 5329.1758 | 5329.1758 | 5329.1758 | 5329.1758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12606 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16957.3457 | 0.2 | 0.3 | 26453.4592 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8546.2251 | 8546.2251 | 8546.2251 | 8546.2251 | 8546.2251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12607 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16727.5439 | 0.2 | 0.3 | 26094.9685 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7359.8143 | 7359.8143 | 7359.8143 | 7359.8143 | 7359.8143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12608 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 27881.2366 | 0.2 | 0.3 | 43494.7291 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4313.039 | 4313.039 | 4313.039 | 4313.039 | 4313.039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12609 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 11503.6765 | 0.2 | 0.3 | 17945.7354 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8087.3927 | 8087.3927 | 8087.3927 | 8087.3927 | 8087.3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12610 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6995.4244 | 6995.4244 | 6995.4244 | 6995.4244 | 6995.4244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12611 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16669.3291 | 0.2 | 0.3 | 26004.1533 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12612 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16670.0769 | 0.2 | 0.3 | 26005.32 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5911.2883 | 5911.2883 | 5911.2883 | 5911.2883 | 5911.2883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12613 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 23194.0141 | 0.2 | 0.3 | 36182.6619 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9221.2864 | 9221.2864 | 9221.2864 | 9221.2864 | 9221.2864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12614 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16670.9826 | 0.2 | 0.3 | 26006.7329 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12615 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16670.5427 | 0.2 | 0.3 | 26006.0467 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7168.7835 | 7168.7835 | 7168.7835 | 7168.7835 | 7168.7835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12616 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 925.8281 | 0.2 | 0.3 | 1444.2919 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6327.3224 | 6327.3224 | 6327.3224 | 6327.3224 | 6327.3224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12617 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 4148.3321 | 0.2 | 0.3 | 6471.398 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6977.3669 | 6977.3669 | 6977.3669 | 6977.3669 | 6977.3669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12618 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 7422.2547 | 0.2 | 0.3 | 11578.7173 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 115.8996 | 115.8996 | 115.8996 | 115.8996 | 115.8996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12619 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 3308.4494 | 0.2 | 0.3 | 5161.1811 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7187.5769 | 7187.5769 | 7187.5769 | 7187.5769 | 7187.5769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12620 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16944.1963 | 0.2 | 0.3 | 26432.9463 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12621 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16821.4557 | 0.2 | 0.3 | 26241.4708 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8426.9659 | 8426.9659 | 8426.9659 | 8426.9659 | 8426.9659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12622 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17118.3413 | 0.2 | 0.3 | 26704.6124 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7915.8161 | 7915.8161 | 7915.8161 | 7915.8161 | 7915.8161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12623 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13486.1313 | 0.2 | 0.3 | 21038.3648 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7229.4899 | 7229.4899 | 7229.4899 | 7229.4899 | 7229.4899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12624 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13297.0675 | 0.2 | 0.3 | 20743.4254 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5928.472 | 5928.472 | 5928.472 | 5928.472 | 5928.472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12625 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18082.8664 | 0.2 | 0.3 | 28209.2716 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9001.541 | 9001.541 | 9001.541 | 9001.541 | 9001.541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12626 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17379.7711 | 0.2 | 0.3 | 27112.4429 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12627 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.3119 | 0.2 | 0.3 | 26005.6865 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12628 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.9745 | 0.2 | 0.3 | 26006.7202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1731 | 5200.1731 | 5200.1731 | 5200.1731 | 5200.1731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12629 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16941.2057 | 0.2 | 0.3 | 26428.2809 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8633.9128 | 8633.9128 | 8633.9128 | 8633.9128 | 8633.9128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12630 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 17425.6727 | 0.2 | 0.3 | 27184.0495 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5968.8739 | 5968.8739 | 5968.8739 | 5968.8739 | 5968.8739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12631 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 17163.2805 | 0.2 | 0.3 | 26774.7175 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2418.0628 | 2418.0628 | 2418.0628 | 2418.0628 | 2418.0628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12632 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8039.411 | 8039.411 | 8039.411 | 8039.411 | 8039.411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12633 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16669.6074 | 0.2 | 0.3 | 26004.5875 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12634 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 21609.5944 | 0.2 | 0.3 | 33710.9673 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9261.76 | 9261.76 | 9261.76 | 9261.76 | 9261.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12635 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 9357.0089 | 0.2 | 0.3 | 14596.9339 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12636 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 9632.6636 | 0.2 | 0.3 | 15026.9552 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.619 | 5200.619 | 5200.619 | 5200.619 | 5200.619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12637 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 12176.8629 | 0.2 | 0.3 | 18995.9061 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3458 | 5200.3458 | 5200.3458 | 5200.3458 | 5200.3458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12638 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 30181.7121 | 0.2 | 0.3 | 47083.4709 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12639 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22439.8761 | 0.2 | 0.3 | 35006.2068 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9535.0218 | 9535.0218 | 9535.0218 | 9535.0218 | 9535.0218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12640 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10292.172 | 0.2 | 0.3 | 16055.7883 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2005 | 5200.2005 | 5200.2005 | 5200.2005 | 5200.2005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12641 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22560.0575 | 0.2 | 0.3 | 35193.6898 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9588.9446 | 9588.9446 | 9588.9446 | 9588.9446 | 9588.9446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12642 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15079.4547 | 0.2 | 0.3 | 23523.9494 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5977.428 | 5977.428 | 5977.428 | 5977.428 | 5977.428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12643 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 4472.4987 | 0.2 | 0.3 | 6977.0979 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12644 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13284.7732 | 0.2 | 0.3 | 20724.2462 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9249.1311 | 9249.1311 | 9249.1311 | 9249.1311 | 9249.1311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12645 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 4357.5111 | 0.2 | 0.3 | 6797.7174 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12646 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17914.1483 | 0.2 | 0.3 | 27946.0713 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12647 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 24379.5049 | 0.2 | 0.3 | 38032.0276 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3447.3708 | 3447.3708 | 3447.3708 | 3447.3708 | 3447.3708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12648 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 8496.7965 | 0.2 | 0.3 | 13255.0026 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8086 | 5199.8086 | 5199.8086 | 5199.8086 | 5199.8086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12649 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.1542 | 0.2 | 0.3 | 26005.4406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7456.0859 | 7456.0859 | 7456.0859 | 7456.0859 | 7456.0859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12650 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.9745 | 0.2 | 0.3 | 26006.7202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7466.016 | 7466.016 | 7466.016 | 7466.016 | 7466.016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12651 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16741.7374 | 0.2 | 0.3 | 26117.1103 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 443.5022 | 443.5022 | 443.5022 | 443.5022 | 443.5022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12652 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 6441.3666 | 0.2 | 0.3 | 10048.5319 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5161.9885 | 5161.9885 | 5161.9885 | 5161.9885 | 5161.9885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12653 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 12598.2449 | 0.2 | 0.3 | 19653.262 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4853.694 | 4853.694 | 4853.694 | 4853.694 | 4853.694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12654 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 20903.7599 | 0.2 | 0.3 | 32609.8655 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12655 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 26279.7221 | 0.2 | 0.3 | 40996.3664 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9788.7819 | 9788.7819 | 9788.7819 | 9788.7819 | 9788.7819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12656 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16878.4727 | 0.2 | 0.3 | 26330.4175 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4107 | 5201.4107 | 5201.4107 | 5201.4107 | 5201.4107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12657 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 31400.4333 | 0.2 | 0.3 | 48984.676 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12658 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 9186.1688 | 0.2 | 0.3 | 14330.4233 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7991.0302 | 7991.0302 | 7991.0302 | 7991.0302 | 7991.0302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12659 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 25134.0562 | 0.2 | 0.3 | 39209.1277 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9151 | 5202.9151 | 5202.9151 | 5202.9151 | 5202.9151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12660 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 19040.8363 | 0.2 | 0.3 | 29703.7046 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 435.5632 | 435.5632 | 435.5632 | 435.5632 | 435.5632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12661 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 16451.2029 | 0.2 | 0.3 | 25663.8765 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9051.4467 | 9051.4467 | 9051.4467 | 9051.4467 | 9051.4467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12662 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6071 | 0.2 | 0.3 | 25999.907 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7401.3352 | 7401.3352 | 7401.3352 | 7401.3352 | 7401.3352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12663 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6047 | 0.2 | 0.3 | 25999.9033 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9790.5411 | 9790.5411 | 9790.5411 | 9790.5411 | 9790.5411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12664 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6038 | 0.2 | 0.3 | 25999.9019 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7828.1642 | 7828.1642 | 7828.1642 | 7828.1642 | 7828.1642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12665 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 20328.258 | 0.2 | 0.3 | 31712.0825 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7218.6642 | 7218.6642 | 7218.6642 | 7218.6642 | 7218.6642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12666 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 16666.4107 | 0.2 | 0.3 | 25999.6007 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7444.3928 | 7444.3928 | 7444.3928 | 7444.3928 | 7444.3928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12667 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 16666.3266 | 0.2 | 0.3 | 25999.4695 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4693.634 | 4693.634 | 4693.634 | 4693.634 | 4693.634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12668 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4518.3431 | 4518.3431 | 4518.3431 | 4518.3431 | 4518.3431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12669 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 31334.8016 | 0.2 | 0.3 | 48882.2905 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5290.7556 | 5290.7556 | 5290.7556 | 5290.7556 | 5290.7556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12670 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 16666.5345 | 0.2 | 0.3 | 25999.7939 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4562.9963 | 4562.9963 | 4562.9963 | 4562.9963 | 4562.9963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12671 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5042.2997 | 5042.2997 | 5042.2997 | 5042.2997 | 5042.2997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12672 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5378.7204 | 5378.7204 | 5378.7204 | 5378.7204 | 5378.7204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12673 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5375.7403 | 5375.7403 | 5375.7403 | 5375.7403 | 5375.7403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12674 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6173 | 0.2 | 0.3 | 25999.9229 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5391.2252 | 5391.2252 | 5391.2252 | 5391.2252 | 5391.2252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12675 | BMSD | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 23121.1327 | 0.2 | 0.3 | 36068.9671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5342.5973 | 5342.5973 | 5342.5973 | 5342.5973 | 5342.5973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12676 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16443.4226 | 0.2 | 0.3 | 25651.7393 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5379.027 | 5379.027 | 5379.027 | 5379.027 | 5379.027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12677 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 7687.7229 | 0.2 | 0.3 | 11992.8477 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6876.0302 | 6876.0302 | 6876.0302 | 6876.0302 | 6876.0302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12678 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 318.4612 | 0.2 | 0.3 | 496.7995 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4871.9138 | 4871.9138 | 4871.9138 | 4871.9138 | 4871.9138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12679 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15849.0364 | 0.2 | 0.3 | 24724.4968 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10404.8699 | 10404.8699 | 10404.8699 | 10404.8699 | 10404.8699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12680 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16973.4172 | 0.2 | 0.3 | 26478.5308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5715.6052 | 5715.6052 | 5715.6052 | 5715.6052 | 5715.6052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12681 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21853.9714 | 0.2 | 0.3 | 34092.1954 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7694.5878 | 7694.5878 | 7694.5878 | 7694.5878 | 7694.5878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12682 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1387.576 | 0.2 | 0.3 | 2164.6186 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7926.9927 | 7926.9927 | 7926.9927 | 7926.9927 | 7926.9927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12683 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 24088.6712 | 0.2 | 0.3 | 37578.3271 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9249.4127 | 9249.4127 | 9249.4127 | 9249.4127 | 9249.4127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12684 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 33818.0979 | 0.2 | 0.3 | 52756.2328 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6753.3769 | 6753.3769 | 6753.3769 | 6753.3769 | 6753.3769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12685 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 40484.2122 | 0.2 | 0.3 | 63155.371 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5375.7026 | 5375.7026 | 5375.7026 | 5375.7026 | 5375.7026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12686 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.7803 | 0.2 | 0.3 | 26006.4173 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4483.5535 | 4483.5535 | 4483.5535 | 4483.5535 | 4483.5535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12687 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.9745 | 0.2 | 0.3 | 26006.7202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 895.5257 | 895.5257 | 895.5257 | 895.5257 | 895.5257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12688 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16776.7811 | 0.2 | 0.3 | 26171.7786 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5378.4299 | 5378.4299 | 5378.4299 | 5378.4299 | 5378.4299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12689 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 15194.52 | 0.2 | 0.3 | 23703.4512 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9041.0089 | 9041.0089 | 9041.0089 | 9041.0089 | 9041.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12690 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 10285.3328 | 0.2 | 0.3 | 16045.1192 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5376.8945 | 5376.8945 | 5376.8945 | 5376.8945 | 5376.8945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12691 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 19065.4445 | 0.2 | 0.3 | 29742.0934 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5375.7088 | 5375.7088 | 5375.7088 | 5375.7088 | 5375.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12692 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 17781.0021 | 0.2 | 0.3 | 27738.3632 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9078.5585 | 9078.5585 | 9078.5585 | 9078.5585 | 9078.5585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12693 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 1491.5078 | 0.2 | 0.3 | 2326.7522 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10129.9751 | 10129.9751 | 10129.9751 | 10129.9751 | 10129.9751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12694 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 12547.4983 | 0.2 | 0.3 | 19574.0974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5379.1123 | 5379.1123 | 5379.1123 | 5379.1123 | 5379.1123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12695 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 37385.2516 | 0.2 | 0.3 | 58320.9925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7631.8491 | 7631.8491 | 7631.8491 | 7631.8491 | 7631.8491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12696 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 29370.1973 | 0.2 | 0.3 | 45817.5077 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3511.902 | 3511.902 | 3511.902 | 3511.902 | 3511.902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12697 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16687.217 | 0.2 | 0.3 | 26032.0585 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5387.8984 | 5387.8984 | 5387.8984 | 5387.8984 | 5387.8984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12698 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 3211.8619 | 0.2 | 0.3 | 5010.5046 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6249.4873 | 6249.4873 | 6249.4873 | 6249.4873 | 6249.4873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12699 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 18714.2947 | 0.2 | 0.3 | 29194.2998 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5382.7803 | 5382.7803 | 5382.7803 | 5382.7803 | 5382.7803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12700 | COCONUT CREEK | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 25291.9769 | 0.2 | 0.3 | 39455.4839 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6929.26 | 6929.26 | 6929.26 | 6929.26 | 6929.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12701 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 6337.9471 | 0.2 | 0.3 | 9887.1975 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4718.306 | 4718.306 | 4718.306 | 4718.306 | 4718.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12702 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14999.2091 | 0.2 | 0.3 | 23398.7661 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4524.8332 | 4524.8332 | 4524.8332 | 4524.8332 | 4524.8332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12703 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16249.3217 | 0.2 | 0.3 | 25348.9418 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5378.5659 | 5378.5659 | 5378.5659 | 5378.5659 | 5378.5659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12704 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 8829.6097 | 0.2 | 0.3 | 13774.1912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6452.8533 | 6452.8533 | 6452.8533 | 6452.8533 | 6452.8533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12705 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 32950.7261 | 0.2 | 0.3 | 51403.1327 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2623.0472 | 2623.0472 | 2623.0472 | 2623.0472 | 2623.0472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12706 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.9745 | 0.2 | 0.3 | 26006.7202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2764.8674 | 2764.8674 | 2764.8674 | 2764.8674 | 2764.8674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12707 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.9745 | 0.2 | 0.3 | 26006.7202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5384.6471 | 5384.6471 | 5384.6471 | 5384.6471 | 5384.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12708 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 17447.0865 | 0.2 | 0.3 | 27217.455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5384.7422 | 5384.7422 | 5384.7422 | 5384.7422 | 5384.7422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12709 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 25334.0235 | 0.2 | 0.3 | 39521.0767 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9362.6502 | 9362.6502 | 9362.6502 | 9362.6502 | 9362.6502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12710 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 18230.7714 | 0.2 | 0.3 | 28440.0034 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5386.4079 | 5386.4079 | 5386.4079 | 5386.4079 | 5386.4079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12711 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3500.3672 | 3500.3672 | 3500.3672 | 3500.3672 | 3500.3672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12712 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 7751.9697 | 0.2 | 0.3 | 12093.0728 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11079.0577 | 11079.0577 | 11079.0577 | 11079.0577 | 11079.0577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12713 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 22906.2678 | 0.2 | 0.3 | 35733.7778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5383.1215 | 5383.1215 | 5383.1215 | 5383.1215 | 5383.1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12714 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16671.342 | 0.2 | 0.3 | 26007.2935 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5387.8131 | 5387.8131 | 5387.8131 | 5387.8131 | 5387.8131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12715 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16807.9489 | 0.2 | 0.3 | 26220.4003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7918.3576 | 7918.3576 | 7918.3576 | 7918.3576 | 7918.3576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12716 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 7532.1578 | 0.2 | 0.3 | 11750.1662 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5381.153 | 5381.153 | 5381.153 | 5381.153 | 5381.153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12717 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13916.3236 | 0.2 | 0.3 | 21709.4648 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5380.8025 | 5380.8025 | 5380.8025 | 5380.8025 | 5380.8025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12718 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18010.6232 | 0.2 | 0.3 | 28096.5722 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8317.1464 | 8317.1464 | 8317.1464 | 8317.1464 | 8317.1464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12719 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10915.0923 | 0.2 | 0.3 | 17027.5439 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6075.3409 | 6075.3409 | 6075.3409 | 6075.3409 | 6075.3409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12720 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 5575.0389 | 0.2 | 0.3 | 8697.0607 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5379.1458 | 5379.1458 | 5379.1458 | 5379.1458 | 5379.1458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12721 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 3661.2641 | 0.2 | 0.3 | 5711.572 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5264.7314 | 5264.7314 | 5264.7314 | 5264.7314 | 5264.7314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12722 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19226.4774 | 0.2 | 0.3 | 29993.3047 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8516.4352 | 8516.4352 | 8516.4352 | 8516.4352 | 8516.4352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12723 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22856.6943 | 0.2 | 0.3 | 35656.4431 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8268.036 | 8268.036 | 8268.036 | 8268.036 | 8268.036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12724 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 6873.1125 | 0.2 | 0.3 | 10722.0556 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6522.6432 | 6522.6432 | 6522.6432 | 6522.6432 | 6522.6432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12725 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2073.3485 | 0.2 | 0.3 | 3234.4236 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8703.7271 | 8703.7271 | 8703.7271 | 8703.7271 | 8703.7271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12726 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 23383.2075 | 0.2 | 0.3 | 36477.8038 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5580.3204 | 5580.3204 | 5580.3204 | 5580.3204 | 5580.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12727 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21783.9864 | 0.2 | 0.3 | 33983.0188 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5387.6425 | 5387.6425 | 5387.6425 | 5387.6425 | 5387.6425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12728 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.701 | 0.2 | 0.3 | 26006.2936 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8700.3443 | 8700.3443 | 8700.3443 | 8700.3443 | 8700.3443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12729 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.9745 | 0.2 | 0.3 | 26006.7202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5304.3339 | 5304.3339 | 5304.3339 | 5304.3339 | 5304.3339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12730 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 17741.5619 | 0.2 | 0.3 | 27676.8366 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5393.9078 | 5393.9078 | 5393.9078 | 5393.9078 | 5393.9078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12731 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 7109.4603 | 0.2 | 0.3 | 11090.758 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8224.4694 | 8224.4694 | 8224.4694 | 8224.4694 | 8224.4694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12732 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 22331.0207 | 0.2 | 0.3 | 34836.3922 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9293.1346 | 9293.1346 | 9293.1346 | 9293.1346 | 9293.1346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12733 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 24939.4111 | 0.2 | 0.3 | 38905.4813 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5379.1976 | 5379.1976 | 5379.1976 | 5379.1976 | 5379.1976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12734 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 18176.2253 | 0.2 | 0.3 | 28354.9115 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5387.3013 | 5387.3013 | 5387.3013 | 5387.3013 | 5387.3013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12735 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 30675.0115 | 0.2 | 0.3 | 47853.0179 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5394.783 | 5394.783 | 5394.783 | 5394.783 | 5394.783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12736 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 20945.5726 | 0.2 | 0.3 | 32675.0933 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5394.2627 | 5394.2627 | 5394.2627 | 5394.2627 | 5394.2627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12737 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 12552.5648 | 0.2 | 0.3 | 19582.0011 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3583.6664 | 3583.6664 | 3583.6664 | 3583.6664 | 3583.6664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12738 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 10401.4061 | 0.2 | 0.3 | 16226.1936 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6581.3992 | 6581.3992 | 6581.3992 | 6581.3992 | 6581.3992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12739 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 17506.1773 | 0.2 | 0.3 | 27309.6365 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9269.42 | 9269.42 | 9269.42 | 9269.42 | 9269.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12740 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 29523.3659 | 0.2 | 0.3 | 46056.4509 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5731.2786 | 5731.2786 | 5731.2786 | 5731.2786 | 5731.2786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12741 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 22851.8441 | 0.2 | 0.3 | 35648.8768 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7021.4927 | 7021.4927 | 7021.4927 | 7021.4927 | 7021.4927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12742 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 22761.2761 | 0.2 | 0.3 | 35507.5908 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4725.1624 | 4725.1624 | 4725.1624 | 4725.1624 | 4725.1624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12743 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 11600.3319 | 0.2 | 0.3 | 18096.5177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4511.7632 | 4511.7632 | 4511.7632 | 4511.7632 | 4511.7632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12744 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13953.3583 | 0.2 | 0.3 | 21767.239 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 16.3442 | 16.3442 | 16.3442 | 16.3442 | 16.3442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12745 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18001.5637 | 0.2 | 0.3 | 28082.4394 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5362.7367 | 5362.7367 | 5362.7367 | 5362.7367 | 5362.7367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12746 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 5902.9067 | 0.2 | 0.3 | 9208.5344 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6418.0432 | 6418.0432 | 6418.0432 | 6418.0432 | 6418.0432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12747 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18018.7645 | 0.2 | 0.3 | 28109.2726 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1628.9447 | 1628.9447 | 1628.9447 | 1628.9447 | 1628.9447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12748 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14206.2639 | 0.2 | 0.3 | 22161.7716 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6465.6009 | 6465.6009 | 6465.6009 | 6465.6009 | 6465.6009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12749 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18146.6341 | 0.2 | 0.3 | 28308.7492 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5263.8278 | 5263.8278 | 5263.8278 | 5263.8278 | 5263.8278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12750 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 23769.5716 | 0.2 | 0.3 | 37080.5317 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5388.111 | 5388.111 | 5388.111 | 5388.111 | 5388.111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12751 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 23848.8961 | 0.2 | 0.3 | 37204.2779 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6205.2571 | 6205.2571 | 6205.2571 | 6205.2571 | 6205.2571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12752 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2151.8517 | 0.2 | 0.3 | 3356.8887 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8152.7814 | 8152.7814 | 8152.7814 | 8152.7814 | 8152.7814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12753 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 36673.5012 | 0.2 | 0.3 | 57210.6619 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4644.6846 | 4644.6846 | 4644.6846 | 4644.6846 | 4644.6846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12754 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12668.8561 | 0.2 | 0.3 | 19763.4156 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7314.6959 | 7314.6959 | 7314.6959 | 7314.6959 | 7314.6959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12755 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11830.839 | 0.2 | 0.3 | 18456.1088 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4689.6457 | 4689.6457 | 4689.6457 | 4689.6457 | 4689.6457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12756 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18622.0238 | 0.2 | 0.3 | 29050.3571 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2229.3244 | 2229.3244 | 2229.3244 | 2229.3244 | 2229.3244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12757 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19427.7873 | 0.2 | 0.3 | 30307.3481 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9199.8847 | 9199.8847 | 9199.8847 | 9199.8847 | 9199.8847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12758 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21896.3242 | 0.2 | 0.3 | 34158.2658 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5386.5641 | 5386.5641 | 5386.5641 | 5386.5641 | 5386.5641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12759 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2166.7469 | 0.2 | 0.3 | 3380.1252 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7249.0263 | 7249.0263 | 7249.0263 | 7249.0263 | 7249.0263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12760 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 34742.6438 | 0.2 | 0.3 | 54198.5243 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10173.9912 | 10173.9912 | 10173.9912 | 10173.9912 | 10173.9912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12761 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 40592.3833 | 0.2 | 0.3 | 63324.1179 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7202.2475 | 7202.2475 | 7202.2475 | 7202.2475 | 7202.2475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12762 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.7011 | 0.2 | 0.3 | 26006.2937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5324.3923 | 5324.3923 | 5324.3923 | 5324.3923 | 5324.3923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12763 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16599.7741 | 0.2 | 0.3 | 25895.6476 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7472.8411 | 7472.8411 | 7472.8411 | 7472.8411 | 7472.8411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12764 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 71.027 | 0.2 | 0.3 | 110.8021 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4710.0019 | 4710.0019 | 4710.0019 | 4710.0019 | 4710.0019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12765 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 7458.5023 | 0.2 | 0.3 | 11635.2635 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7393.2655 | 7393.2655 | 7393.2655 | 7393.2655 | 7393.2655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12766 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 9331.9632 | 0.2 | 0.3 | 14557.8626 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3521.1369 | 3521.1369 | 3521.1369 | 3521.1369 | 3521.1369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12767 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 7635.1525 | 0.2 | 0.3 | 11910.838 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8408.4469 | 8408.4469 | 8408.4469 | 8408.4469 | 8408.4469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12768 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 6170.4611 | 0.2 | 0.3 | 9625.9194 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10147.4794 | 10147.4794 | 10147.4794 | 10147.4794 | 10147.4794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12769 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 19035.2623 | 0.2 | 0.3 | 29695.0091 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7695.0998 | 7695.0998 | 7695.0998 | 7695.0998 | 7695.0998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12770 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 26165.2044 | 0.2 | 0.3 | 40817.7189 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5383.0326 | 5383.0326 | 5383.0326 | 5383.0326 | 5383.0326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12771 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 33758.0567 | 0.2 | 0.3 | 52662.5684 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5414.4293 | 5414.4293 | 5414.4293 | 5414.4293 | 5414.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12772 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 35286.0321 | 0.2 | 0.3 | 55046.2101 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6992.6074 | 6992.6074 | 6992.6074 | 6992.6074 | 6992.6074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12773 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 31334.3264 | 0.2 | 0.3 | 48881.5492 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5541.3655 | 5541.3655 | 5541.3655 | 5541.3655 | 5541.3655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12774 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 31596.9276 | 0.2 | 0.3 | 49291.2071 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4083.0632 | 4083.0632 | 4083.0632 | 4083.0632 | 4083.0632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12775 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 21955.7871 | 0.2 | 0.3 | 34251.0278 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10098.4932 | 10098.4932 | 10098.4932 | 10098.4932 | 10098.4932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12776 | COCONUT CREEK | 10502 | Public | 2036 | 5 | Swales | 66.6667 | 23884.0943 | 0.2 | 0.3 | 37259.1871 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 413.0535 | 413.0535 | 413.0535 | 413.0535 | 413.0535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12777 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 613.0073 | 0.2 | 0.3 | 956.2913 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2334.4971 | 2334.4971 | 2334.4971 | 2334.4971 | 2334.4971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12778 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16923.8185 | 0.2 | 0.3 | 26401.1568 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6353.6037 | 6353.6037 | 6353.6037 | 6353.6037 | 6353.6037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12779 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18222.062 | 0.2 | 0.3 | 28426.4167 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5851.2516 | 5851.2516 | 5851.2516 | 5851.2516 | 5851.2516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12780 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17990.1369 | 0.2 | 0.3 | 28064.6135 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9303.5972 | 9303.5972 | 9303.5972 | 9303.5972 | 9303.5972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12781 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17693.9367 | 0.2 | 0.3 | 27602.5413 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9011.9256 | 9011.9256 | 9011.9256 | 9011.9256 | 9011.9256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12782 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19147.3305 | 0.2 | 0.3 | 29869.8356 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3831.7149 | 3831.7149 | 3831.7149 | 3831.7149 | 3831.7149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12783 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13339.1095 | 0.2 | 0.3 | 20809.0109 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11830.6094 | 11830.6094 | 11830.6094 | 11830.6094 | 11830.6094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12784 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 30457.9011 | 0.2 | 0.3 | 47514.3257 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9349.8963 | 9349.8963 | 9349.8963 | 9349.8963 | 9349.8963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12785 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 7400.0865 | 0.2 | 0.3 | 11544.1349 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2749.9333 | 2749.9333 | 2749.9333 | 2749.9333 | 2749.9333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12786 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10098.2643 | 0.2 | 0.3 | 15753.2923 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6467.646 | 6467.646 | 6467.646 | 6467.646 | 6467.646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12787 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18455.1799 | 0.2 | 0.3 | 28790.0807 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6536.9003 | 6536.9003 | 6536.9003 | 6536.9003 | 6536.9003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12788 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 27820.8461 | 0.2 | 0.3 | 43400.5199 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4516.6247 | 4516.6247 | 4516.6247 | 4516.6247 | 4516.6247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12789 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.7011 | 0.2 | 0.3 | 26006.2937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8175.9294 | 8175.9294 | 8175.9294 | 8175.9294 | 8175.9294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12790 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 11059.2418 | 0.2 | 0.3 | 17252.4172 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6142.8564 | 6142.8564 | 6142.8564 | 6142.8564 | 6142.8564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12791 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 5611.4246 | 0.2 | 0.3 | 8753.8224 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4944 | 5202.4944 | 5202.4944 | 5202.4944 | 5202.4944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12792 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 33.1831 | 0.2 | 0.3 | 51.7657 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5218.1229 | 5218.1229 | 5218.1229 | 5218.1229 | 5218.1229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12793 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 18781.5121 | 0.2 | 0.3 | 29299.1589 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9957 | 5202.9957 | 5202.9957 | 5202.9957 | 5202.9957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12794 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16627.784 | 0.2 | 0.3 | 25939.343 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4927 | 5202.4927 | 5202.4927 | 5202.4927 | 5202.4927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12795 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 20948.2117 | 0.2 | 0.3 | 32679.2103 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6653.2103 | 6653.2103 | 6653.2103 | 6653.2103 | 6653.2103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12796 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 26039.6043 | 0.2 | 0.3 | 40621.7828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5248.6065 | 5248.6065 | 5248.6065 | 5248.6065 | 5248.6065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12797 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 3884.1714 | 0.2 | 0.3 | 6059.3074 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5248.6011 | 5248.6011 | 5248.6011 | 5248.6011 | 5248.6011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12798 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 34868.8154 | 0.2 | 0.3 | 54395.352 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8350.2254 | 8350.2254 | 8350.2254 | 8350.2254 | 8350.2254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12799 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 20012.6873 | 0.2 | 0.3 | 31219.7921 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4823.7521 | 4823.7521 | 4823.7521 | 4823.7521 | 4823.7521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12800 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 33008.0455 | 0.2 | 0.3 | 51492.5509 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5772.8689 | 5772.8689 | 5772.8689 | 5772.8689 | 5772.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12801 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 16461.8853 | 0.2 | 0.3 | 25680.5411 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.5146 | 9776.5146 | 9776.5146 | 9776.5146 | 9776.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12802 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 28720.8943 | 0.2 | 0.3 | 44804.5951 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3325.8977 | 3325.8977 | 3325.8977 | 3325.8977 | 3325.8977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12803 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 236.3521 | 0.2 | 0.3 | 368.7092 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12804 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16474.8947 | 0.2 | 0.3 | 25700.8357 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12805 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10315.698 | 0.2 | 0.3 | 16092.4889 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12806 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16039.2878 | 0.2 | 0.3 | 25021.289 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5255.1158 | 5255.1158 | 5255.1158 | 5255.1158 | 5255.1158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12807 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18339.1924 | 0.2 | 0.3 | 28609.1401 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5252.2905 | 5252.2905 | 5252.2905 | 5252.2905 | 5252.2905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12808 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12673.0984 | 0.2 | 0.3 | 19770.0335 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6357.9199 | 6357.9199 | 6357.9199 | 6357.9199 | 6357.9199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12809 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11110.7528 | 0.2 | 0.3 | 17332.7744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5660.7348 | 5660.7348 | 5660.7348 | 5660.7348 | 5660.7348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12810 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17532.0884 | 0.2 | 0.3 | 27350.0579 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7943.3302 | 7943.3302 | 7943.3302 | 7943.3302 | 7943.3302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12811 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22205.4086 | 0.2 | 0.3 | 34640.4374 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7456.6995 | 7456.6995 | 7456.6995 | 7456.6995 | 7456.6995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12812 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17104.4937 | 0.2 | 0.3 | 26683.0101 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8642.5973 | 8642.5973 | 8642.5973 | 8642.5973 | 8642.5973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12813 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 9358.5939 | 0.2 | 0.3 | 14599.4065 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7799.7094 | 7799.7094 | 7799.7094 | 7799.7094 | 7799.7094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12814 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21503.3507 | 0.2 | 0.3 | 33545.2271 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5239.3157 | 5239.3157 | 5239.3157 | 5239.3157 | 5239.3157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12815 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 37098.2413 | 0.2 | 0.3 | 57873.2565 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5238.7914 | 5238.7914 | 5238.7914 | 5238.7914 | 5238.7914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12816 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20322.5572 | 0.2 | 0.3 | 31703.1892 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7163.9167 | 7163.9167 | 7163.9167 | 7163.9167 | 7163.9167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12817 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.5801 | 0.2 | 0.3 | 26006.1049 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5124.8411 | 5124.8411 | 5124.8411 | 5124.8411 | 5124.8411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12818 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 8335.4757 | 0.2 | 0.3 | 13003.3421 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3969.1872 | 3969.1872 | 3969.1872 | 3969.1872 | 3969.1872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12819 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 8335.4084 | 0.2 | 0.3 | 13003.2371 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9436.0071 | 9436.0071 | 9436.0071 | 9436.0071 | 9436.0071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12820 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 11941.4984 | 0.2 | 0.3 | 18628.7375 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5252.3823 | 5252.3823 | 5252.3823 | 5252.3823 | 5252.3823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12821 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16672.7955 | 0.2 | 0.3 | 26009.5609 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5251.9871 | 5251.9871 | 5251.9871 | 5251.9871 | 5251.9871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12822 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16669.1729 | 0.2 | 0.3 | 26003.9097 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7664.8214 | 7664.8214 | 7664.8214 | 7664.8214 | 7664.8214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12823 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 5855.1435 | 0.2 | 0.3 | 9134.0239 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10407.668 | 10407.668 | 10407.668 | 10407.668 | 10407.668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12824 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 17739.2825 | 0.2 | 0.3 | 27673.2808 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6615.106 | 6615.106 | 6615.106 | 6615.106 | 6615.106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12825 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 14694.1656 | 0.2 | 0.3 | 22922.8983 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 117.8621 | 117.8621 | 117.8621 | 117.8621 | 117.8621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12826 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 9396.9451 | 0.2 | 0.3 | 14659.2343 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.6175 | 2600.6175 | 2600.6175 | 2600.6175 | 2600.6175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12827 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.4385 | 2600.4385 | 2600.4385 | 2600.4385 | 2600.4385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12828 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17435.1122 | 0.2 | 0.3 | 27198.775 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1407 | 5201.1407 | 5201.1407 | 5201.1407 | 5201.1407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12829 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 936.7645 | 0.2 | 0.3 | 1461.3527 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9122.7792 | 9122.7792 | 9122.7792 | 9122.7792 | 9122.7792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12830 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17450.1299 | 0.2 | 0.3 | 27222.2026 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.013 | 5201.013 | 5201.013 | 5201.013 | 5201.013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12831 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 5876.675 | 0.2 | 0.3 | 9167.613 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12832 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21036.6155 | 0.2 | 0.3 | 32817.1202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12833 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16148.5424 | 0.2 | 0.3 | 25191.7261 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7521.6392 | 7521.6392 | 7521.6392 | 7521.6392 | 7521.6392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12834 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14080.4402 | 0.2 | 0.3 | 21965.4867 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10262.5848 | 10262.5848 | 10262.5848 | 10262.5848 | 10262.5848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12835 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2953.3325 | 0.2 | 0.3 | 4607.1986 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7025.9778 | 7025.9778 | 7025.9778 | 7025.9778 | 7025.9778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12836 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16971.4233 | 0.2 | 0.3 | 26475.4203 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7893.638 | 7893.638 | 7893.638 | 7893.638 | 7893.638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12837 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16856.581 | 0.2 | 0.3 | 26296.2664 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9058.8689 | 9058.8689 | 9058.8689 | 9058.8689 | 9058.8689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12838 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17956.7599 | 0.2 | 0.3 | 28012.5455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5229.8986 | 5229.8986 | 5229.8986 | 5229.8986 | 5229.8986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12839 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11418.2543 | 0.2 | 0.3 | 17812.4767 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8844.8234 | 8844.8234 | 8844.8234 | 8844.8234 | 8844.8234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12840 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.9744 | 0.2 | 0.3 | 26006.7201 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7850.7653 | 7850.7653 | 7850.7653 | 7850.7653 | 7850.7653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12841 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 7934.5164 | 0.2 | 0.3 | 12377.8456 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5084.3506 | 5084.3506 | 5084.3506 | 5084.3506 | 5084.3506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12842 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 8735.0261 | 0.2 | 0.3 | 13626.6408 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5659.0332 | 5659.0332 | 5659.0332 | 5659.0332 | 5659.0332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12843 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 24364.9219 | 0.2 | 0.3 | 38009.2781 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4994.1621 | 4994.1621 | 4994.1621 | 4994.1621 | 4994.1621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12844 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 12931.5426 | 0.2 | 0.3 | 20173.2065 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4942.3904 | 4942.3904 | 4942.3904 | 4942.3904 | 4942.3904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12845 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 8473.6397 | 0.2 | 0.3 | 13218.878 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5317.8808 | 5317.8808 | 5317.8808 | 5317.8808 | 5317.8808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12846 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 13109.9045 | 0.2 | 0.3 | 20451.4511 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7499.6261 | 7499.6261 | 7499.6261 | 7499.6261 | 7499.6261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12847 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 18740.5263 | 0.2 | 0.3 | 29235.2211 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5272.5593 | 5272.5593 | 5272.5593 | 5272.5593 | 5272.5593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12848 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 29653.277 | 0.2 | 0.3 | 46259.1121 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.5899 | 2600.5899 | 2600.5899 | 2600.5899 | 2600.5899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12849 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.5862 | 2600.5862 | 2600.5862 | 2600.5862 | 2600.5862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12850 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0066 | 5201.0066 | 5201.0066 | 5201.0066 | 5201.0066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12851 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6428 | 0.2 | 0.3 | 25999.9628 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9014.2055 | 9014.2055 | 9014.2055 | 9014.2055 | 9014.2055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12852 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 16961.5417 | 0.2 | 0.3 | 26460.005 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12853 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 2501.8063 | 0.2 | 0.3 | 3902.8178 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12854 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 15825.6953 | 0.2 | 0.3 | 24688.0846 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6439.3979 | 6439.3979 | 6439.3979 | 6439.3979 | 6439.3979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12855 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 10416.3348 | 0.2 | 0.3 | 16249.4823 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7894.7199 | 7894.7199 | 7894.7199 | 7894.7199 | 7894.7199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12856 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 63.3965 | 0.2 | 0.3 | 98.8986 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14375.2862 | 14375.2862 | 14375.2862 | 14375.2862 | 14375.2862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12857 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 9641.1475 | 0.2 | 0.3 | 15040.19 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1902.4881 | 1902.4881 | 1902.4881 | 1902.4881 | 1902.4881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12858 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 7014.1293 | 0.2 | 0.3 | 10942.0417 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5234.5702 | 5234.5702 | 5234.5702 | 5234.5702 | 5234.5702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12859 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16750.3853 | 0.2 | 0.3 | 26130.601 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5217.1957 | 5217.1957 | 5217.1957 | 5217.1957 | 5217.1957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12860 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16799.8686 | 0.2 | 0.3 | 26207.795 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7883.828 | 7883.828 | 7883.828 | 7883.828 | 7883.828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12861 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10846.9459 | 0.2 | 0.3 | 16921.2356 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6184.6129 | 6184.6129 | 6184.6129 | 6184.6129 | 6184.6129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12862 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17707.1839 | 0.2 | 0.3 | 27623.2068 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9206 | 5201.9206 | 5201.9206 | 5201.9206 | 5201.9206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12863 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15925.2574 | 0.2 | 0.3 | 24843.4015 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7571.4982 | 7571.4982 | 7571.4982 | 7571.4982 | 7571.4982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12864 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14779.2501 | 0.2 | 0.3 | 23055.6301 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7411.7122 | 7411.7122 | 7411.7122 | 7411.7122 | 7411.7122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12865 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18591.1357 | 0.2 | 0.3 | 29002.1717 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7453.4683 | 7453.4683 | 7453.4683 | 7453.4683 | 7453.4683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12866 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 5108.9659 | 0.2 | 0.3 | 7969.9868 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7462.4006 | 7462.4006 | 7462.4006 | 7462.4006 | 7462.4006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12867 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 9039.3741 | 0.2 | 0.3 | 14101.4235 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7681.8483 | 7681.8483 | 7681.8483 | 7681.8483 | 7681.8483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12868 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 30624.2204 | 0.2 | 0.3 | 47773.7838 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2418 | 5200.2418 | 5200.2418 | 5200.2418 | 5200.2418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12869 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 31209.7983 | 0.2 | 0.3 | 48687.2854 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8753.8629 | 8753.8629 | 8753.8629 | 8753.8629 | 8753.8629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12870 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14546.4307 | 0.2 | 0.3 | 22692.4319 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1788.0434 | 1788.0434 | 1788.0434 | 1788.0434 | 1788.0434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12871 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22222.7006 | 0.2 | 0.3 | 34667.4129 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6707.6188 | 6707.6188 | 6707.6188 | 6707.6188 | 6707.6188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12872 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2924.0097 | 0.2 | 0.3 | 4561.4552 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8878.5013 | 8878.5013 | 8878.5013 | 8878.5013 | 8878.5013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12873 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 26241.0657 | 0.2 | 0.3 | 40936.0625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12874 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16671.2479 | 0.2 | 0.3 | 26007.1467 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5739 | 5201.5739 | 5201.5739 | 5201.5739 | 5201.5739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12875 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 3740.9627 | 0.2 | 0.3 | 5835.9019 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5894.0228 | 5894.0228 | 5894.0228 | 5894.0228 | 5894.0228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12876 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 12926.7309 | 0.2 | 0.3 | 20165.7002 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1055.2576 | 1055.2576 | 1055.2576 | 1055.2576 | 1055.2576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12877 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 688.1641 | 0.2 | 0.3 | 1073.5359 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9974.0769 | 9974.0769 | 9974.0769 | 9974.0769 | 9974.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12878 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 17438.772 | 0.2 | 0.3 | 27204.4843 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2495.4919 | 2495.4919 | 2495.4919 | 2495.4919 | 2495.4919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12879 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 21573.393 | 0.2 | 0.3 | 33654.4931 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2904.0401 | 2904.0401 | 2904.0401 | 2904.0401 | 2904.0401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12880 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 28180.7461 | 0.2 | 0.3 | 43961.964 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7294.1606 | 7294.1606 | 7294.1606 | 7294.1606 | 7294.1606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12881 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8542 | 0.2 | 0.3 | 26000.2926 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8443.5303 | 8443.5303 | 8443.5303 | 8443.5303 | 8443.5303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12882 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4938 | 0.2 | 0.3 | 26001.2903 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5667.0707 | 5667.0707 | 5667.0707 | 5667.0707 | 5667.0707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12883 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 22301.7005 | 0.2 | 0.3 | 34790.6528 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 757.0533 | 757.0533 | 757.0533 | 757.0533 | 757.0533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12884 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 22659.0754 | 0.2 | 0.3 | 35348.1576 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5211.5415 | 5211.5415 | 5211.5415 | 5211.5415 | 5211.5415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12885 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 8333.388 | 0.2 | 0.3 | 13000.0853 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12886 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 8333.3 | 0.2 | 0.3 | 12999.948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6475.3094 | 6475.3094 | 6475.3094 | 6475.3094 | 6475.3094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12887 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 8587.2495 | 0.2 | 0.3 | 13396.1092 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8508.1336 | 8508.1336 | 8508.1336 | 8508.1336 | 8508.1336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12888 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 16755.5708 | 0.2 | 0.3 | 26138.6904 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7018.2373 | 7018.2373 | 7018.2373 | 7018.2373 | 7018.2373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12889 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 17549.8804 | 0.2 | 0.3 | 27377.8134 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7970.0864 | 7970.0864 | 7970.0864 | 7970.0864 | 7970.0864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12890 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 844.2043 | 0.2 | 0.3 | 1316.9588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7960.4803 | 7960.4803 | 7960.4803 | 7960.4803 | 7960.4803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12891 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 9301.0019 | 0.2 | 0.3 | 14509.563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12892 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 14067.9386 | 0.2 | 0.3 | 21945.9842 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8911.7183 | 8911.7183 | 8911.7183 | 8911.7183 | 8911.7183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12893 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 4131.1925 | 0.2 | 0.3 | 6444.6602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9207.2223 | 9207.2223 | 9207.2223 | 9207.2223 | 9207.2223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12894 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 18157.4833 | 0.2 | 0.3 | 28325.674 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7099.989 | 7099.989 | 7099.989 | 7099.989 | 7099.989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12895 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 21902.1488 | 0.2 | 0.3 | 34167.3521 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9499.4984 | 9499.4984 | 9499.4984 | 9499.4984 | 9499.4984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12896 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 29460.7435 | 0.2 | 0.3 | 45958.7599 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 16586.9034 | 16586.9034 | 16586.9034 | 16586.9034 | 16586.9034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12897 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21395.2382 | 0.2 | 0.3 | 33376.5716 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5559.1115 | 5559.1115 | 5559.1115 | 5559.1115 | 5559.1115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12898 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18258.8567 | 0.2 | 0.3 | 28483.8165 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6047.9425 | 6047.9425 | 6047.9425 | 6047.9425 | 6047.9425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12899 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 26769.2079 | 0.2 | 0.3 | 41759.9644 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2634.9894 | 2634.9894 | 2634.9894 | 2634.9894 | 2634.9894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12900 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15542.3509 | 0.2 | 0.3 | 24246.0674 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5144.8902 | 5144.8902 | 5144.8902 | 5144.8902 | 5144.8902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12901 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18483.0282 | 0.2 | 0.3 | 28833.524 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7729.2857 | 7729.2857 | 7729.2857 | 7729.2857 | 7729.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12902 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 424.1541 | 0.2 | 0.3 | 661.6804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12903 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2757.9424 | 0.2 | 0.3 | 4302.3901 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7510.2652 | 7510.2652 | 7510.2652 | 7510.2652 | 7510.2652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12904 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18983.322 | 0.2 | 0.3 | 29613.9823 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5916.2225 | 5916.2225 | 5916.2225 | 5916.2225 | 5916.2225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12905 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17299.1445 | 0.2 | 0.3 | 26986.6654 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7550.9488 | 7550.9488 | 7550.9488 | 7550.9488 | 7550.9488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12906 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13699.5356 | 0.2 | 0.3 | 21371.2755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7522.3502 | 7522.3502 | 7522.3502 | 7522.3502 | 7522.3502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12907 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22934.85 | 0.2 | 0.3 | 35778.366 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7638.5937 | 7638.5937 | 7638.5937 | 7638.5937 | 7638.5937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12908 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 879.0503 | 0.2 | 0.3 | 1371.3185 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7801.7741 | 7801.7741 | 7801.7741 | 7801.7741 | 7801.7741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12909 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 31332.096 | 0.2 | 0.3 | 48878.0698 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6841.9396 | 6841.9396 | 6841.9396 | 6841.9396 | 6841.9396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12910 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17038.0397 | 0.2 | 0.3 | 26579.3419 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8554.79 | 8554.79 | 8554.79 | 8554.79 | 8554.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12911 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16819.333 | 0.2 | 0.3 | 26238.1595 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8875.8613 | 8875.8613 | 8875.8613 | 8875.8613 | 8875.8613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12912 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 31184.8352 | 0.2 | 0.3 | 48648.3429 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7289.778 | 7289.778 | 7289.778 | 7289.778 | 7289.778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12913 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 8669.5621 | 0.2 | 0.3 | 13524.5168 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11169.7223 | 11169.7223 | 11169.7223 | 11169.7223 | 11169.7223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12914 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 19748.1114 | 0.2 | 0.3 | 30807.0538 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12345.0115 | 12345.0115 | 12345.0115 | 12345.0115 | 12345.0115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12915 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 394.1393 | 0.2 | 0.3 | 614.8573 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14087.8313 | 14087.8313 | 14087.8313 | 14087.8313 | 14087.8313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12916 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16668.0684 | 0.2 | 0.3 | 26002.1867 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 15030.3889 | 15030.3889 | 15030.3889 | 15030.3889 | 15030.3889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12917 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 5963.3203 | 0.2 | 0.3 | 9302.7797 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10911.2259 | 10911.2259 | 10911.2259 | 10911.2259 | 10911.2259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12918 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 8333.393 | 0.2 | 0.3 | 13000.0931 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 15532.3629 | 15532.3629 | 15532.3629 | 15532.3629 | 15532.3629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12919 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 8333.3 | 0.2 | 0.3 | 12999.948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9938.6222 | 9938.6222 | 9938.6222 | 9938.6222 | 9938.6222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12920 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 8135.7585 | 0.2 | 0.3 | 12691.7833 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9808.7749 | 9808.7749 | 9808.7749 | 9808.7749 | 9808.7749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12921 | PARKLAND | 10504 | Public | 2036 | 5 | Swales | 66.6667 | 3.3549 | 0.2 | 0.3 | 5.2337 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10225.7522 | 10225.7522 | 10225.7522 | 10225.7522 | 10225.7522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12922 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 17334.7165 | 0.2 | 0.3 | 27042.1577 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12923 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 11623.9115 | 0.2 | 0.3 | 18133.3019 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.1371 | 5204.1371 | 5204.1371 | 5204.1371 | 5204.1371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12924 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 1535.4132 | 0.2 | 0.3 | 2395.2446 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8932.6592 | 8932.6592 | 8932.6592 | 8932.6592 | 8932.6592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12925 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 16545.4376 | 0.2 | 0.3 | 25810.8827 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2601.4799 | 2601.4799 | 2601.4799 | 2601.4799 | 2601.4799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12926 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 189.1633 | 0.2 | 0.3 | 295.0948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5243.7077 | 5243.7077 | 5243.7077 | 5243.7077 | 5243.7077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12927 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 16478.739 | 0.2 | 0.3 | 25706.8328 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5188.7194 | 5188.7194 | 5188.7194 | 5188.7194 | 5188.7194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12928 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9182.5495 | 9182.5495 | 9182.5495 | 9182.5495 | 9182.5495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12929 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 15271.0925 | 0.2 | 0.3 | 23822.9042 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1204 | 5201.1204 | 5201.1204 | 5201.1204 | 5201.1204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12930 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 16749.4597 | 0.2 | 0.3 | 26129.1571 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12931 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 28124.8475 | 0.2 | 0.3 | 43874.7622 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9664 | 5200.9664 | 5200.9664 | 5200.9664 | 5200.9664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12932 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16836.5615 | 0.2 | 0.3 | 26265.0359 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12933 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16720.323 | 0.2 | 0.3 | 26083.7039 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3009 | 5201.3009 | 5201.3009 | 5201.3009 | 5201.3009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12934 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 29103.3269 | 0.2 | 0.3 | 45401.1899 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4857 | 5202.4857 | 5202.4857 | 5202.4857 | 5202.4857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12935 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 7637.1761 | 0.2 | 0.3 | 11913.9947 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4424.1593 | 4424.1593 | 4424.1593 | 4424.1593 | 4424.1593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12936 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11040.3327 | 0.2 | 0.3 | 17222.9191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11391.3994 | 11391.3994 | 11391.3994 | 11391.3994 | 11391.3994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12937 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 760.2791 | 0.2 | 0.3 | 1186.0353 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 358.7171 | 358.7171 | 358.7171 | 358.7171 | 358.7171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12938 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16067.546 | 0.2 | 0.3 | 25065.3718 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4694.2885 | 4694.2885 | 4694.2885 | 4694.2885 | 4694.2885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12939 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17710.608 | 0.2 | 0.3 | 27628.5485 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8989 | 5200.8989 | 5200.8989 | 5200.8989 | 5200.8989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12940 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15512.9356 | 0.2 | 0.3 | 24200.1795 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8412 | 5200.8412 | 5200.8412 | 5200.8412 | 5200.8412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12941 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19594.3871 | 0.2 | 0.3 | 30567.2439 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9325.8845 | 9325.8845 | 9325.8845 | 9325.8845 | 9325.8845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12942 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16927.1042 | 0.2 | 0.3 | 26406.2826 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12943 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 26326.0314 | 0.2 | 0.3 | 41068.609 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9519 | 5202.9519 | 5202.9519 | 5202.9519 | 5202.9519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12944 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 27578.4173 | 0.2 | 0.3 | 43022.331 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.7364 | 9779.7364 | 9779.7364 | 9779.7364 | 9779.7364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12945 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 5007.2601 | 0.2 | 0.3 | 7811.3258 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.4634 | 5203.4634 | 5203.4634 | 5203.4634 | 5203.4634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12946 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17438.7155 | 0.2 | 0.3 | 27204.3961 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5356.6306 | 5356.6306 | 5356.6306 | 5356.6306 | 5356.6306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12947 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10565.0809 | 0.2 | 0.3 | 16481.5263 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7632.054 | 7632.054 | 7632.054 | 7632.054 | 7632.054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12948 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16672.3415 | 0.2 | 0.3 | 26008.8527 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5764 | 5201.5764 | 5201.5764 | 5201.5764 | 5201.5764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12949 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5313.9453 | 5313.9453 | 5313.9453 | 5313.9453 | 5313.9453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12950 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2764 | 5201.2764 | 5201.2764 | 5201.2764 | 5201.2764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12951 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 33584.2972 | 0.2 | 0.3 | 52391.5036 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5295.0943 | 5295.0943 | 5295.0943 | 5295.0943 | 5295.0943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12952 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 17402.0286 | 0.2 | 0.3 | 27147.1646 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6404 | 5200.6404 | 5200.6404 | 5200.6404 | 5200.6404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12953 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 24795.9947 | 0.2 | 0.3 | 38681.7518 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6038.1969 | 6038.1969 | 6038.1969 | 6038.1969 | 6038.1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12954 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 10706.267 | 0.2 | 0.3 | 16701.7765 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6647.6988 | 6647.6988 | 6647.6988 | 6647.6988 | 6647.6988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12955 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 12123.9965 | 0.2 | 0.3 | 18913.4345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7882 | 5201.7882 | 5201.7882 | 5201.7882 | 5201.7882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12956 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16687.4746 | 0.2 | 0.3 | 26032.4604 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12946.8567 | 12946.8567 | 12946.8567 | 12946.8567 | 12946.8567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12957 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 5124.1343 | 0.2 | 0.3 | 7993.6495 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3136.2009 | 3136.2009 | 3136.2009 | 3136.2009 | 3136.2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12958 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 22644.8309 | 0.2 | 0.3 | 35325.9362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3220.2568 | 3220.2568 | 3220.2568 | 3220.2568 | 3220.2568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12959 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 30563.1835 | 0.2 | 0.3 | 47678.5663 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2660.257 | 2660.257 | 2660.257 | 2660.257 | 2660.257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12960 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 4158.4431 | 0.2 | 0.3 | 6487.1712 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7944 | 5202.7944 | 5202.7944 | 5202.7944 | 5202.7944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12961 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20272.0629 | 0.2 | 0.3 | 31624.4181 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6214.5673 | 6214.5673 | 6214.5673 | 6214.5673 | 6214.5673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12962 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2516.0697 | 0.2 | 0.3 | 3925.0688 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9002.2887 | 9002.2887 | 9002.2887 | 9002.2887 | 9002.2887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12963 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17144.4345 | 0.2 | 0.3 | 26745.3179 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11570.1023 | 11570.1023 | 11570.1023 | 11570.1023 | 11570.1023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12964 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 9535.4215 | 0.2 | 0.3 | 14875.2576 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6516.591 | 6516.591 | 6516.591 | 6516.591 | 6516.591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12965 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18977.424 | 0.2 | 0.3 | 29604.7814 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7221.9257 | 7221.9257 | 7221.9257 | 7221.9257 | 7221.9257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12966 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17480.539 | 0.2 | 0.3 | 27269.6408 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2580.0621 | 2580.0621 | 2580.0621 | 2580.0621 | 2580.0621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12967 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16674.5638 | 0.2 | 0.3 | 26012.3195 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9713 | 5201.9713 | 5201.9713 | 5201.9713 | 5201.9713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12968 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16701.7379 | 0.2 | 0.3 | 26054.7112 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 732.5144 | 732.5144 | 732.5144 | 732.5144 | 732.5144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12969 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17158.349 | 0.2 | 0.3 | 26767.0244 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8659.1341 | 8659.1341 | 8659.1341 | 8659.1341 | 8659.1341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12970 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11950.4724 | 0.2 | 0.3 | 18642.7369 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9967.3751 | 9967.3751 | 9967.3751 | 9967.3751 | 9967.3751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12971 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22615.4439 | 0.2 | 0.3 | 35280.0925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10793.5596 | 10793.5596 | 10793.5596 | 10793.5596 | 10793.5596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12972 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16719.6541 | 0.2 | 0.3 | 26082.6604 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4539.3359 | 4539.3359 | 4539.3359 | 4539.3359 | 4539.3359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12973 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19508.0915 | 0.2 | 0.3 | 30432.6227 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2997.0611 | 2997.0611 | 2997.0611 | 2997.0611 | 2997.0611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12974 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20954.2899 | 0.2 | 0.3 | 32688.6923 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3230.1976 | 3230.1976 | 3230.1976 | 3230.1976 | 3230.1976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12975 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16217.0675 | 0.2 | 0.3 | 25298.6254 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5220.9337 | 5220.9337 | 5220.9337 | 5220.9337 | 5220.9337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12976 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1233.3358 | 0.2 | 0.3 | 1924.0038 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6851.7779 | 6851.7779 | 6851.7779 | 6851.7779 | 6851.7779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12977 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12112.4592 | 0.2 | 0.3 | 18895.4364 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5921.7989 | 5921.7989 | 5921.7989 | 5921.7989 | 5921.7989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12978 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 5149.5893 | 0.2 | 0.3 | 8033.3594 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5776.6445 | 5776.6445 | 5776.6445 | 5776.6445 | 5776.6445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12979 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13686.3264 | 0.2 | 0.3 | 21350.6692 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 528.7624 | 528.7624 | 528.7624 | 528.7624 | 528.7624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12980 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 28561.4621 | 0.2 | 0.3 | 44555.8809 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10021.7149 | 10021.7149 | 10021.7149 | 10021.7149 | 10021.7149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12981 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1571.7972 | 0.2 | 0.3 | 2452.0036 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5559.2279 | 5559.2279 | 5559.2279 | 5559.2279 | 5559.2279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12982 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16822.0359 | 0.2 | 0.3 | 26242.376 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13779.3955 | 13779.3955 | 13779.3955 | 13779.3955 | 13779.3955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12983 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9841.6671 | 9841.6671 | 9841.6671 | 9841.6671 | 9841.6671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12984 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1691.01 | 1691.01 | 1691.01 | 1691.01 | 1691.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12985 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2165.7179 | 2165.7179 | 2165.7179 | 2165.7179 | 2165.7179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12986 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16854.6168 | 0.2 | 0.3 | 26293.2022 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5377.8978 | 5377.8978 | 5377.8978 | 5377.8978 | 5377.8978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12987 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16898.8461 | 0.2 | 0.3 | 26362.2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1542.6596 | 1542.6596 | 1542.6596 | 1542.6596 | 1542.6596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12988 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16774.9541 | 0.2 | 0.3 | 26168.9283 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 910.5374 | 910.5374 | 910.5374 | 910.5374 | 910.5374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12989 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 33702.4232 | 0.2 | 0.3 | 52575.7802 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8108.6973 | 8108.6973 | 8108.6973 | 8108.6973 | 8108.6973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12990 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 25227.2847 | 0.2 | 0.3 | 39354.5642 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5401.9561 | 5401.9561 | 5401.9561 | 5401.9561 | 5401.9561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12991 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 3965.883 | 0.2 | 0.3 | 6186.7775 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5167.8578 | 5167.8578 | 5167.8578 | 5167.8578 | 5167.8578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12992 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14163.0379 | 0.2 | 0.3 | 22094.3391 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7167.4176 | 7167.4176 | 7167.4176 | 7167.4176 | 7167.4176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12993 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 23110.1325 | 0.2 | 0.3 | 36051.8066 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7744.0788 | 7744.0788 | 7744.0788 | 7744.0788 | 7744.0788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12994 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21937.048 | 0.2 | 0.3 | 34221.7949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10559.0405 | 10559.0405 | 10559.0405 | 10559.0405 | 10559.0405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12995 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8338 | 0.2 | 0.3 | 26000.2607 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10825.8819 | 10825.8819 | 10825.8819 | 10825.8819 | 10825.8819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12996 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16719.9889 | 0.2 | 0.3 | 26083.1826 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4737.2703 | 4737.2703 | 4737.2703 | 4737.2703 | 4737.2703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12997 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16745.5943 | 0.2 | 0.3 | 26123.1271 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8292.0699 | 8292.0699 | 8292.0699 | 8292.0699 | 8292.0699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12998 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19703.6369 | 0.2 | 0.3 | 30737.6735 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1438 | 5203.1438 | 5203.1438 | 5203.1438 | 5203.1438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12999 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 23907.1699 | 0.2 | 0.3 | 37295.185 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10362.4002 | 10362.4002 | 10362.4002 | 10362.4002 | 10362.4002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13000 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16773.6391 | 0.2 | 0.3 | 26166.8769 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 15744.7317 | 15744.7317 | 15744.7317 | 15744.7317 | 15744.7317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13001 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16915.2411 | 0.2 | 0.3 | 26387.7761 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5731.4376 | 5731.4376 | 5731.4376 | 5731.4376 | 5731.4376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13002 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13840.0284 | 0.2 | 0.3 | 21590.4443 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 143.2836 | 143.2836 | 143.2836 | 143.2836 | 143.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13003 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19278.9889 | 0.2 | 0.3 | 30075.2227 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 391.1912 | 391.1912 | 391.1912 | 391.1912 | 391.1912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13004 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2361.8263 | 0.2 | 0.3 | 3684.4491 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7465.7991 | 7465.7991 | 7465.7991 | 7465.7991 | 7465.7991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13005 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 5474.6427 | 0.2 | 0.3 | 8540.4426 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8333.9149 | 8333.9149 | 8333.9149 | 8333.9149 | 8333.9149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13006 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16954.7142 | 0.2 | 0.3 | 26449.3542 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6839.0445 | 6839.0445 | 6839.0445 | 6839.0445 | 6839.0445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13007 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16760.7957 | 0.2 | 0.3 | 26146.8412 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6084 | 5200.6084 | 5200.6084 | 5200.6084 | 5200.6084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13008 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17563.7795 | 0.2 | 0.3 | 27399.4961 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3361 | 5203.3361 | 5203.3361 | 5203.3361 | 5203.3361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13009 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 4245.595 | 0.2 | 0.3 | 6623.1282 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1450.6267 | 1450.6267 | 1450.6267 | 1450.6267 | 1450.6267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13010 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12526.0213 | 0.2 | 0.3 | 19540.5933 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5991.1113 | 5991.1113 | 5991.1113 | 5991.1113 | 5991.1113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13011 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17127.5467 | 0.2 | 0.3 | 26718.9729 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5893.887 | 5893.887 | 5893.887 | 5893.887 | 5893.887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13012 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.6394 | 0.2 | 0.3 | 26003.0775 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10110.8084 | 10110.8084 | 10110.8084 | 10110.8084 | 10110.8084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13013 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16669.0367 | 0.2 | 0.3 | 26003.6973 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3565.1697 | 3565.1697 | 3565.1697 | 3565.1697 | 3565.1697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13014 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7881 | 0.2 | 0.3 | 26003.3094 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2645.8991 | 2645.8991 | 2645.8991 | 2645.8991 | 2645.8991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13015 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 6090.1204 | 0.2 | 0.3 | 9500.5878 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 235.0134 | 235.0134 | 235.0134 | 235.0134 | 235.0134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13016 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16876.761 | 0.2 | 0.3 | 26327.7472 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5501.168 | 5501.168 | 5501.168 | 5501.168 | 5501.168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13017 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16762.041 | 0.2 | 0.3 | 26148.784 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5562.4142 | 5562.4142 | 5562.4142 | 5562.4142 | 5562.4142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13018 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 5572.2891 | 0.2 | 0.3 | 8692.771 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11409.2187 | 11409.2187 | 11409.2187 | 11409.2187 | 11409.2187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13019 | COCONUT CREEK | 10502 | Private | 2036 | 5 | Swales | 66.6667 | 2937.8801 | 0.2 | 0.3 | 4583.0929 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3806.227 | 3806.227 | 3806.227 | 3806.227 | 3806.227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13020 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11119.8495 | 0.2 | 0.3 | 17346.9652 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6051.0511 | 6051.0511 | 6051.0511 | 6051.0511 | 6051.0511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13021 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 28878.3651 | 0.2 | 0.3 | 45050.2496 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 17807.9799 | 17807.9799 | 17807.9799 | 17807.9799 | 17807.9799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13022 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18412.6057 | 0.2 | 0.3 | 28723.6648 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2797.4098 | 2797.4098 | 2797.4098 | 2797.4098 | 2797.4098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13023 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16875.335 | 0.2 | 0.3 | 26325.5226 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8500.1491 | 8500.1491 | 8500.1491 | 8500.1491 | 8500.1491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13024 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6847.3232 | 6847.3232 | 6847.3232 | 6847.3232 | 6847.3232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13025 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20499.0162 | 0.2 | 0.3 | 31978.4653 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7344.0381 | 7344.0381 | 7344.0381 | 7344.0381 | 7344.0381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13026 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18334.6799 | 0.2 | 0.3 | 28602.1006 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5631.9816 | 5631.9816 | 5631.9816 | 5631.9816 | 5631.9816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13027 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12071.1141 | 0.2 | 0.3 | 18830.938 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2569.8369 | 2569.8369 | 2569.8369 | 2569.8369 | 2569.8369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13028 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17682.9975 | 0.2 | 0.3 | 27585.476 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7871.9562 | 7871.9562 | 7871.9562 | 7871.9562 | 7871.9562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13029 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2404 | 0.2 | 0.3 | 26002.455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3616.6993 | 3616.6993 | 3616.6993 | 3616.6993 | 3616.6993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13030 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8810.087 | 8810.087 | 8810.087 | 8810.087 | 8810.087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13031 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2704.8692 | 2704.8692 | 2704.8692 | 2704.8692 | 2704.8692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13032 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 2311.8173 | 0.2 | 0.3 | 3606.4349 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 779.1656 | 779.1656 | 779.1656 | 779.1656 | 779.1656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13033 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 28220.7254 | 0.2 | 0.3 | 44024.3316 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10514.8286 | 10514.8286 | 10514.8286 | 10514.8286 | 10514.8286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13034 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 7814.0819 | 0.2 | 0.3 | 12189.9678 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8410.7173 | 8410.7173 | 8410.7173 | 8410.7173 | 8410.7173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13035 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 9609.5819 | 0.2 | 0.3 | 14990.9477 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10236.4612 | 10236.4612 | 10236.4612 | 10236.4612 | 10236.4612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13036 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 17323.2594 | 0.2 | 0.3 | 27024.2847 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7914.0603 | 7914.0603 | 7914.0603 | 7914.0603 | 7914.0603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13037 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 7695.3427 | 0.2 | 0.3 | 12004.7347 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10431.2304 | 10431.2304 | 10431.2304 | 10431.2304 | 10431.2304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13038 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 18992.4938 | 0.2 | 0.3 | 29628.2903 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6593.7508 | 6593.7508 | 6593.7508 | 6593.7508 | 6593.7508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13039 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 20195.5258 | 0.2 | 0.3 | 31505.0202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7203.7783 | 7203.7783 | 7203.7783 | 7203.7783 | 7203.7783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13040 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17095.7857 | 0.2 | 0.3 | 26669.4256 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6806.5339 | 6806.5339 | 6806.5339 | 6806.5339 | 6806.5339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13041 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1382.897 | 0.2 | 0.3 | 2157.3193 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5268.1856 | 5268.1856 | 5268.1856 | 5268.1856 | 5268.1856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13042 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 5713.0093 | 0.2 | 0.3 | 8912.2945 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11585.8174 | 11585.8174 | 11585.8174 | 11585.8174 | 11585.8174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13043 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21.9787 | 0.2 | 0.3 | 34.2867 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12717.9308 | 12717.9308 | 12717.9308 | 12717.9308 | 12717.9308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13044 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 27915.679 | 0.2 | 0.3 | 43548.4592 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10754.0595 | 10754.0595 | 10754.0595 | 10754.0595 | 10754.0595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13045 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22848.2207 | 0.2 | 0.3 | 35643.2242 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6312.0619 | 6312.0619 | 6312.0619 | 6312.0619 | 6312.0619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13046 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16717.1729 | 0.2 | 0.3 | 26078.7897 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5926.6015 | 5926.6015 | 5926.6015 | 5926.6015 | 5926.6015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13047 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17936.8125 | 0.2 | 0.3 | 27981.4276 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10790.827 | 10790.827 | 10790.827 | 10790.827 | 10790.827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13048 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19839.0533 | 0.2 | 0.3 | 30948.9231 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9074.5235 | 9074.5235 | 9074.5235 | 9074.5235 | 9074.5235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13049 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16790.267 | 0.2 | 0.3 | 26192.8165 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 249.0567 | 249.0567 | 249.0567 | 249.0567 | 249.0567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13050 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16734.4293 | 0.2 | 0.3 | 26105.7098 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12986.4006 | 12986.4006 | 12986.4006 | 12986.4006 | 12986.4006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13051 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17273.7419 | 0.2 | 0.3 | 26947.0373 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8550.9532 | 8550.9532 | 8550.9532 | 8550.9532 | 8550.9532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13052 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10249.4323 | 0.2 | 0.3 | 15989.1144 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4633.4164 | 4633.4164 | 4633.4164 | 4633.4164 | 4633.4164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13053 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17334.6531 | 0.2 | 0.3 | 27042.0588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7419.9032 | 7419.9032 | 7419.9032 | 7419.9032 | 7419.9032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13054 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16796.59 | 0.2 | 0.3 | 26202.6804 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13316.3888 | 13316.3888 | 13316.3888 | 13316.3888 | 13316.3888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13055 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16667.5531 | 0.2 | 0.3 | 26001.3828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5707.3817 | 5707.3817 | 5707.3817 | 5707.3817 | 5707.3817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13056 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20527.6547 | 0.2 | 0.3 | 32023.1413 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10836.4891 | 10836.4891 | 10836.4891 | 10836.4891 | 10836.4891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13057 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1223 | 0.2 | 0.3 | 26000.7108 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7147.3475 | 7147.3475 | 7147.3475 | 7147.3475 | 7147.3475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13058 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18095.1491 | 0.2 | 0.3 | 28228.4325 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3951.3318 | 3951.3318 | 3951.3318 | 3951.3318 | 3951.3318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13059 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 4919.654 | 0.2 | 0.3 | 7674.6602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6827.0602 | 6827.0602 | 6827.0602 | 6827.0602 | 6827.0602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13060 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2666.0339 | 0.2 | 0.3 | 4159.0129 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5767.8033 | 5767.8033 | 5767.8033 | 5767.8033 | 5767.8033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13061 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14811.9596 | 0.2 | 0.3 | 23106.657 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1277.9957 | 1277.9957 | 1277.9957 | 1277.9957 | 1277.9957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13062 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16932.8085 | 0.2 | 0.3 | 26415.1812 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9014.6477 | 9014.6477 | 9014.6477 | 9014.6477 | 9014.6477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13063 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11549.6166 | 0.2 | 0.3 | 18017.4019 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3034.879 | 3034.879 | 3034.879 | 3034.879 | 3034.879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13064 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 27686.6938 | 0.2 | 0.3 | 43191.2423 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4271.2082 | 4271.2082 | 4271.2082 | 4271.2082 | 4271.2082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13065 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 5840.8322 | 0.2 | 0.3 | 9111.6982 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8119.9356 | 8119.9356 | 8119.9356 | 8119.9356 | 8119.9356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13066 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2404 | 0.2 | 0.3 | 26002.455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4252.2603 | 4252.2603 | 4252.2603 | 4252.2603 | 4252.2603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13067 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3794.4999 | 3794.4999 | 3794.4999 | 3794.4999 | 3794.4999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13068 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5496.4968 | 5496.4968 | 5496.4968 | 5496.4968 | 5496.4968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13069 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 7769.4683 | 0.2 | 0.3 | 12120.3705 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9247.3958 | 9247.3958 | 9247.3958 | 9247.3958 | 9247.3958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13070 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 13064.106 | 0.2 | 0.3 | 20380.0054 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 886.4745 | 886.4745 | 886.4745 | 886.4745 | 886.4745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13071 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 11510.4667 | 0.2 | 0.3 | 17956.328 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5209.8569 | 5209.8569 | 5209.8569 | 5209.8569 | 5209.8569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13072 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16666.013 | 0.2 | 0.3 | 25998.9803 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9940.4245 | 9940.4245 | 9940.4245 | 9940.4245 | 9940.4245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13073 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 8909.4726 | 0.2 | 0.3 | 13898.7773 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3261.1967 | 3261.1967 | 3261.1967 | 3261.1967 | 3261.1967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13074 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 34173.6148 | 0.2 | 0.3 | 53310.8391 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3523.6045 | 3523.6045 | 3523.6045 | 3523.6045 | 3523.6045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13075 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 43903.6288 | 0.2 | 0.3 | 68489.6609 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10147.3214 | 10147.3214 | 10147.3214 | 10147.3214 | 10147.3214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13076 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 29136.4833 | 0.2 | 0.3 | 45452.9139 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11551.2098 | 11551.2098 | 11551.2098 | 11551.2098 | 11551.2098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13077 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 37699.0273 | 0.2 | 0.3 | 58810.4826 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12306.2009 | 12306.2009 | 12306.2009 | 12306.2009 | 12306.2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13078 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 29710.8191 | 0.2 | 0.3 | 46348.8778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5370.4866 | 5370.4866 | 5370.4866 | 5370.4866 | 5370.4866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13079 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 17347.3182 | 0.2 | 0.3 | 27061.8164 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8902.1742 | 8902.1742 | 8902.1742 | 8902.1742 | 8902.1742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13080 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 8328.4101 | 0.2 | 0.3 | 12992.3197 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6601.6987 | 6601.6987 | 6601.6987 | 6601.6987 | 6601.6987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13081 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 8333.3 | 0.2 | 0.3 | 12999.948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4201.0418 | 4201.0418 | 4201.0418 | 4201.0418 | 4201.0418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13082 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 23335.2163 | 0.2 | 0.3 | 36402.9374 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9141.257 | 9141.257 | 9141.257 | 9141.257 | 9141.257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13083 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 31350.9091 | 0.2 | 0.3 | 48907.4182 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6624.5653 | 6624.5653 | 6624.5653 | 6624.5653 | 6624.5653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13084 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 27361.4851 | 0.2 | 0.3 | 42683.9167 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8256.9429 | 8256.9429 | 8256.9429 | 8256.9429 | 8256.9429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13085 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15529.6936 | 0.2 | 0.3 | 24226.322 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5743.4667 | 5743.4667 | 5743.4667 | 5743.4667 | 5743.4667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13086 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 23225.0437 | 0.2 | 0.3 | 36231.0682 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11573.5422 | 11573.5422 | 11573.5422 | 11573.5422 | 11573.5422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13087 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 320.1688 | 0.2 | 0.3 | 499.4633 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13545.4284 | 13545.4284 | 13545.4284 | 13545.4284 | 13545.4284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13088 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16657.2667 | 0.2 | 0.3 | 25985.336 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7034.7346 | 7034.7346 | 7034.7346 | 7034.7346 | 7034.7346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13089 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 3681.5127 | 0.2 | 0.3 | 5743.1599 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6983.6271 | 6983.6271 | 6983.6271 | 6983.6271 | 6983.6271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13090 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13615.9601 | 0.2 | 0.3 | 21240.8978 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9805.0319 | 9805.0319 | 9805.0319 | 9805.0319 | 9805.0319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13091 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16755.0421 | 0.2 | 0.3 | 26137.8656 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11129.3488 | 11129.3488 | 11129.3488 | 11129.3488 | 11129.3488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13092 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 29149.0995 | 0.2 | 0.3 | 45472.5953 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8111.0217 | 8111.0217 | 8111.0217 | 8111.0217 | 8111.0217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13093 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17228.6037 | 0.2 | 0.3 | 26876.6218 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7944.8062 | 7944.8062 | 7944.8062 | 7944.8062 | 7944.8062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13094 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 4306.8749 | 0.2 | 0.3 | 6718.7249 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7450.7337 | 7450.7337 | 7450.7337 | 7450.7337 | 7450.7337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13095 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18801.2091 | 0.2 | 0.3 | 29329.8862 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9298.818 | 9298.818 | 9298.818 | 9298.818 | 9298.818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13096 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 9562.2405 | 0.2 | 0.3 | 14917.0952 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4501.936 | 4501.936 | 4501.936 | 4501.936 | 4501.936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13097 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16577.7306 | 0.2 | 0.3 | 25861.2597 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5477.3939 | 5477.3939 | 5477.3939 | 5477.3939 | 5477.3939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13098 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1965.6968 | 0.2 | 0.3 | 3066.487 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6266.8381 | 6266.8381 | 6266.8381 | 6266.8381 | 6266.8381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13099 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13118.7287 | 0.2 | 0.3 | 20465.2168 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7410.797 | 7410.797 | 7410.797 | 7410.797 | 7410.797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13100 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 5730.2084 | 0.2 | 0.3 | 8939.1251 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4056.7129 | 4056.7129 | 4056.7129 | 4056.7129 | 4056.7129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13101 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2404 | 0.2 | 0.3 | 26002.455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6297.1925 | 6297.1925 | 6297.1925 | 6297.1925 | 6297.1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13102 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6726.1504 | 6726.1504 | 6726.1504 | 6726.1504 | 6726.1504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13103 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6547.5407 | 6547.5407 | 6547.5407 | 6547.5407 | 6547.5407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13104 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 17957.3217 | 0.2 | 0.3 | 28013.4219 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11559.6152 | 11559.6152 | 11559.6152 | 11559.6152 | 11559.6152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13105 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 26908.7397 | 0.2 | 0.3 | 41977.6339 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5406.8798 | 5406.8798 | 5406.8798 | 5406.8798 | 5406.8798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13106 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 31488.2127 | 0.2 | 0.3 | 49121.6119 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4480.4472 | 4480.4472 | 4480.4472 | 4480.4472 | 4480.4472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13107 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 19118.573 | 0.2 | 0.3 | 29824.9739 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6352.5911 | 6352.5911 | 6352.5911 | 6352.5911 | 6352.5911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13108 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 26363.8621 | 0.2 | 0.3 | 41127.6249 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1923 | 2600.1923 | 2600.1923 | 2600.1923 | 2600.1923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13109 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 29872.5021 | 0.2 | 0.3 | 46601.1033 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6946.2456 | 6946.2456 | 6946.2456 | 6946.2456 | 6946.2456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13110 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 51.0891 | 0.2 | 0.3 | 79.6989 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4472.4573 | 4472.4573 | 4472.4573 | 4472.4573 | 4472.4573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13111 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 4487.3363 | 0.2 | 0.3 | 7000.2446 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6169 | 5200.6169 | 5200.6169 | 5200.6169 | 5200.6169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13112 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 9327.5903 | 0.2 | 0.3 | 14551.0409 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8107.0732 | 8107.0732 | 8107.0732 | 8107.0732 | 8107.0732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13113 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 11967.5585 | 0.2 | 0.3 | 18669.3913 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5914.029 | 5914.029 | 5914.029 | 5914.029 | 5914.029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13114 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 11487.3955 | 0.2 | 0.3 | 17920.3369 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5561.1112 | 5561.1112 | 5561.1112 | 5561.1112 | 5561.1112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13115 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 12200.7144 | 0.2 | 0.3 | 19033.1145 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6313.1137 | 6313.1137 | 6313.1137 | 6313.1137 | 6313.1137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13116 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 17972.6303 | 0.2 | 0.3 | 28037.3033 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6242.7938 | 6242.7938 | 6242.7938 | 6242.7938 | 6242.7938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13117 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1088.0999 | 0.2 | 0.3 | 1697.4358 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2160.6255 | 2160.6255 | 2160.6255 | 2160.6255 | 2160.6255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13118 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 56682.6619 | 0.2 | 0.3 | 88424.9525 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5985.2333 | 5985.2333 | 5985.2333 | 5985.2333 | 5985.2333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13119 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 397.3956 | 0.2 | 0.3 | 619.9371 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5209.2341 | 5209.2341 | 5209.2341 | 5209.2341 | 5209.2341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13120 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 3637.3067 | 0.2 | 0.3 | 5674.1985 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5214.4703 | 5214.4703 | 5214.4703 | 5214.4703 | 5214.4703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13121 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15685.3695 | 0.2 | 0.3 | 24469.1764 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3233.7093 | 3233.7093 | 3233.7093 | 3233.7093 | 3233.7093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13122 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21219.4946 | 0.2 | 0.3 | 33102.4116 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9879.3471 | 9879.3471 | 9879.3471 | 9879.3471 | 9879.3471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13123 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 6295.1496 | 0.2 | 0.3 | 9820.4334 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6421 | 5200.6421 | 5200.6421 | 5200.6421 | 5200.6421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13124 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10406.9139 | 0.2 | 0.3 | 16234.7857 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5300.2495 | 5300.2495 | 5300.2495 | 5300.2495 | 5300.2495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13125 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16773.758 | 0.2 | 0.3 | 26167.0625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6710.0759 | 6710.0759 | 6710.0759 | 6710.0759 | 6710.0759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13126 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16779.2218 | 0.2 | 0.3 | 26175.586 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.2266 | 2600.2266 | 2600.2266 | 2600.2266 | 2600.2266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13127 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17167.6091 | 0.2 | 0.3 | 26781.4701 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2601.7639 | 2601.7639 | 2601.7639 | 2601.7639 | 2601.7639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13128 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22311.9603 | 0.2 | 0.3 | 34806.6581 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 368.5631 | 368.5631 | 368.5631 | 368.5631 | 368.5631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13129 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 29459.7127 | 0.2 | 0.3 | 45957.1519 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 160.4401 | 160.4401 | 160.4401 | 160.4401 | 160.4401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13130 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 4454.8996 | 0.2 | 0.3 | 6949.6434 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 936.2692 | 936.2692 | 936.2692 | 936.2692 | 936.2692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13131 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16809.0745 | 0.2 | 0.3 | 26222.1563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1777.4259 | 1777.4259 | 1777.4259 | 1777.4259 | 1777.4259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13132 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18289.4149 | 0.2 | 0.3 | 28531.4873 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3066.709 | 3066.709 | 3066.709 | 3066.709 | 3066.709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13133 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.5138 | 0.2 | 0.3 | 26002.8815 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6302.6745 | 6302.6745 | 6302.6745 | 6302.6745 | 6302.6745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13134 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13135 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5292.6182 | 5292.6182 | 5292.6182 | 5292.6182 | 5292.6182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13136 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16688.8124 | 0.2 | 0.3 | 26034.5473 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9822.7196 | 9822.7196 | 9822.7196 | 9822.7196 | 9822.7196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13137 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 26815.6013 | 0.2 | 0.3 | 41832.338 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13138 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 30237.3424 | 0.2 | 0.3 | 47170.2541 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9810.6004 | 9810.6004 | 9810.6004 | 9810.6004 | 9810.6004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13139 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 8333.2362 | 0.2 | 0.3 | 12999.8485 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6924 | 5201.6924 | 5201.6924 | 5201.6924 | 5201.6924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13140 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 29412.5321 | 0.2 | 0.3 | 45883.55 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.81 | 5201.81 | 5201.81 | 5201.81 | 5201.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13141 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 20891.3682 | 0.2 | 0.3 | 32590.5344 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6614.288 | 6614.288 | 6614.288 | 6614.288 | 6614.288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13142 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 31806.1882 | 0.2 | 0.3 | 49617.6536 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4305.9389 | 4305.9389 | 4305.9389 | 4305.9389 | 4305.9389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13143 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 31789.3287 | 0.2 | 0.3 | 49591.3527 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 896.8545 | 896.8545 | 896.8545 | 896.8545 | 896.8545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13144 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 32064.4765 | 0.2 | 0.3 | 50020.5834 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7562 | 5201.7562 | 5201.7562 | 5201.7562 | 5201.7562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13145 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 31759.801 | 0.2 | 0.3 | 49545.2896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1523 | 5202.1523 | 5202.1523 | 5202.1523 | 5202.1523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13146 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 29738.4118 | 0.2 | 0.3 | 46391.9224 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5213.1826 | 5213.1826 | 5213.1826 | 5213.1826 | 5213.1826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13147 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 45913.7444 | 0.2 | 0.3 | 71625.4413 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1380.4813 | 1380.4813 | 1380.4813 | 1380.4813 | 1380.4813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13148 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 8492.9135 | 0.2 | 0.3 | 13248.945 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9473.9587 | 9473.9587 | 9473.9587 | 9473.9587 | 9473.9587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13149 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17586.5812 | 0.2 | 0.3 | 27435.0667 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13150 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17394.5594 | 0.2 | 0.3 | 27135.5127 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10279.1896 | 10279.1896 | 10279.1896 | 10279.1896 | 10279.1896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13151 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12106.3389 | 0.2 | 0.3 | 18885.8886 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7772.2132 | 7772.2132 | 7772.2132 | 7772.2132 | 7772.2132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13152 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1532.2952 | 0.2 | 0.3 | 2390.3805 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6843 | 5201.6843 | 5201.6843 | 5201.6843 | 5201.6843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13153 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22623.4847 | 0.2 | 0.3 | 35292.6361 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6750.5607 | 6750.5607 | 6750.5607 | 6750.5607 | 6750.5607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13154 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13560.1081 | 0.2 | 0.3 | 21153.7687 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 231.4859 | 231.4859 | 231.4859 | 231.4859 | 231.4859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13155 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12344.2899 | 0.2 | 0.3 | 19257.0923 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4870.2211 | 4870.2211 | 4870.2211 | 4870.2211 | 4870.2211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13156 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17318.9286 | 0.2 | 0.3 | 27017.5286 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2601.2473 | 2601.2473 | 2601.2473 | 2601.2473 | 2601.2473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13157 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17016.0086 | 0.2 | 0.3 | 26544.9734 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7225 | 5201.7225 | 5201.7225 | 5201.7225 | 5201.7225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13158 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16725.9073 | 0.2 | 0.3 | 26092.4153 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3234 | 5202.3234 | 5202.3234 | 5202.3234 | 5202.3234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13159 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18707.5718 | 0.2 | 0.3 | 29183.812 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2898.9985 | 2898.9985 | 2898.9985 | 2898.9985 | 2898.9985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13160 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 26.7924 | 0.2 | 0.3 | 41.7961 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5240.025 | 5240.025 | 5240.025 | 5240.025 | 5240.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13161 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19472.1451 | 0.2 | 0.3 | 30376.5464 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9956.3629 | 9956.3629 | 9956.3629 | 9956.3629 | 9956.3629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13162 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18056.7432 | 0.2 | 0.3 | 28168.5194 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9781.3705 | 9781.3705 | 9781.3705 | 9781.3705 | 9781.3705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13163 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14849.8861 | 0.2 | 0.3 | 23165.8223 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8250.5772 | 8250.5772 | 8250.5772 | 8250.5772 | 8250.5772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13164 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16939.8478 | 0.2 | 0.3 | 26426.1626 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4275.1047 | 4275.1047 | 4275.1047 | 4275.1047 | 4275.1047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13165 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19993.7851 | 0.2 | 0.3 | 31190.3048 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7976.5756 | 7976.5756 | 7976.5756 | 7976.5756 | 7976.5756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13166 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 6.4985 | 0.2 | 0.3 | 10.1377 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4585.2398 | 4585.2398 | 4585.2398 | 4585.2398 | 4585.2398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13167 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18139.4159 | 0.2 | 0.3 | 28297.4889 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8055.3439 | 8055.3439 | 8055.3439 | 8055.3439 | 8055.3439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13168 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5085.7342 | 5085.7342 | 5085.7342 | 5085.7342 | 5085.7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13169 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4808.5954 | 4808.5954 | 4808.5954 | 4808.5954 | 4808.5954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13170 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3082.032 | 3082.032 | 3082.032 | 3082.032 | 3082.032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13171 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16667.7486 | 0.2 | 0.3 | 26001.6878 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7168.528 | 7168.528 | 7168.528 | 7168.528 | 7168.528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13172 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 45237.6913 | 0.2 | 0.3 | 70570.7985 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5253.2587 | 5253.2587 | 5253.2587 | 5253.2587 | 5253.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13173 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 17839.0445 | 0.2 | 0.3 | 27828.9095 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9641.5041 | 9641.5041 | 9641.5041 | 9641.5041 | 9641.5041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13174 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 23430.666 | 0.2 | 0.3 | 36551.839 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5361.0203 | 5361.0203 | 5361.0203 | 5361.0203 | 5361.0203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13175 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 30833.1311 | 0.2 | 0.3 | 48099.6845 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5476 | 5203.5476 | 5203.5476 | 5203.5476 | 5203.5476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13176 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 7154.5153 | 0.2 | 0.3 | 11161.0439 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5116.4161 | 5116.4161 | 5116.4161 | 5116.4161 | 5116.4161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13177 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 12104.7027 | 0.2 | 0.3 | 18883.3363 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7591.317 | 7591.317 | 7591.317 | 7591.317 | 7591.317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13178 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 18117.4553 | 0.2 | 0.3 | 28263.2302 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13179 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 11105.7557 | 0.2 | 0.3 | 17324.9788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7103.481 | 7103.481 | 7103.481 | 7103.481 | 7103.481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13180 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 38210.2835 | 0.2 | 0.3 | 59608.0423 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5652 | 5203.5652 | 5203.5652 | 5203.5652 | 5203.5652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13181 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 52.9976 | 0.2 | 0.3 | 82.6763 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 315.3175 | 315.3175 | 315.3175 | 315.3175 | 315.3175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13182 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 4728.0397 | 0.2 | 0.3 | 7375.7419 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4898.0076 | 4898.0076 | 4898.0076 | 4898.0076 | 4898.0076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13183 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16842.4116 | 0.2 | 0.3 | 26274.1621 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8875 | 5201.8875 | 5201.8875 | 5201.8875 | 5201.8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13184 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17431.8371 | 0.2 | 0.3 | 27193.6659 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4979.2891 | 4979.2891 | 4979.2891 | 4979.2891 | 4979.2891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13185 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19532.2417 | 0.2 | 0.3 | 30470.2971 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.6282 | 9779.6282 | 9779.6282 | 9779.6282 | 9779.6282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13186 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22369.3939 | 0.2 | 0.3 | 34896.2544 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7544.4906 | 7544.4906 | 7544.4906 | 7544.4906 | 7544.4906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13187 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18061.3688 | 0.2 | 0.3 | 28175.7353 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7687.9512 | 7687.9512 | 7687.9512 | 7687.9512 | 7687.9512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13188 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 25399.6793 | 0.2 | 0.3 | 39623.4997 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8874.4365 | 8874.4365 | 8874.4365 | 8874.4365 | 8874.4365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13189 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 947.0131 | 0.2 | 0.3 | 1477.3405 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8611 | 5199.8611 | 5199.8611 | 5199.8611 | 5199.8611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13190 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1288.3947 | 0.2 | 0.3 | 2009.8957 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6694.6956 | 6694.6956 | 6694.6956 | 6694.6956 | 6694.6956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13191 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17617.6915 | 0.2 | 0.3 | 27483.5987 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9822.6603 | 9822.6603 | 9822.6603 | 9822.6603 | 9822.6603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13192 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21231.6721 | 0.2 | 0.3 | 33121.4084 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.4178 | 9779.4178 | 9779.4178 | 9779.4178 | 9779.4178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13193 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9784.594 | 9784.594 | 9784.594 | 9784.594 | 9784.594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13194 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6120.8805 | 6120.8805 | 6120.8805 | 6120.8805 | 6120.8805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13195 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9748.5649 | 9748.5649 | 9748.5649 | 9748.5649 | 9748.5649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13196 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16667.5122 | 0.2 | 0.3 | 26001.319 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7734.3324 | 7734.3324 | 7734.3324 | 7734.3324 | 7734.3324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13197 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 10942.3774 | 0.2 | 0.3 | 17070.1087 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.5261 | 5205.5261 | 5205.5261 | 5205.5261 | 5205.5261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13198 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 21716.2643 | 0.2 | 0.3 | 33877.3723 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9179 | 5201.9179 | 5201.9179 | 5201.9179 | 5201.9179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13199 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 15067.7052 | 0.2 | 0.3 | 23505.6201 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1383 | 5202.1383 | 5202.1383 | 5202.1383 | 5202.1383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13200 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 35437.2967 | 0.2 | 0.3 | 55282.1829 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2342 | 5201.2342 | 5201.2342 | 5201.2342 | 5201.2342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13201 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 22987.0409 | 0.2 | 0.3 | 35859.7838 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3681 | 5201.3681 | 5201.3681 | 5201.3681 | 5201.3681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13202 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 22164.2019 | 0.2 | 0.3 | 34576.1549 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0732 | 5202.0732 | 5202.0732 | 5202.0732 | 5202.0732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13203 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16083.7661 | 0.2 | 0.3 | 25090.6752 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.996 | 5201.996 | 5201.996 | 5201.996 | 5201.996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13204 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 19972.6851 | 0.2 | 0.3 | 31157.3888 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5632.9758 | 5632.9758 | 5632.9758 | 5632.9758 | 5632.9758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13205 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 3975.8326 | 0.2 | 0.3 | 6202.2989 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2482.3526 | 2482.3526 | 2482.3526 | 2482.3526 | 2482.3526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13206 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 15324.7248 | 0.2 | 0.3 | 23906.5707 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1266 | 5201.1266 | 5201.1266 | 5201.1266 | 5201.1266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13207 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 10586.5062 | 0.2 | 0.3 | 16514.9497 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5122 | 5201.5122 | 5201.5122 | 5201.5122 | 5201.5122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13208 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 20333.1771 | 0.2 | 0.3 | 31719.7563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3772 | 5203.3772 | 5203.3772 | 5203.3772 | 5203.3772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13209 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16666.6344 | 0.2 | 0.3 | 25999.9497 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8578 | 5202.8578 | 5202.8578 | 5202.8578 | 5202.8578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13210 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16667.2 | 0.2 | 0.3 | 26000.832 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8112 | 5201.8112 | 5201.8112 | 5201.8112 | 5201.8112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13211 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16676.0616 | 0.2 | 0.3 | 26014.6561 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.8276 | 5205.8276 | 5205.8276 | 5205.8276 | 5205.8276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13212 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16684.7574 | 0.2 | 0.3 | 26028.2215 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6546.5252 | 6546.5252 | 6546.5252 | 6546.5252 | 6546.5252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13213 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 11934.1041 | 0.2 | 0.3 | 18617.2024 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8547 | 5201.8547 | 5201.8547 | 5201.8547 | 5201.8547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13214 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11975.9329 | 0.2 | 0.3 | 18682.4554 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3397 | 5202.3397 | 5202.3397 | 5202.3397 | 5202.3397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13215 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 26073.9089 | 0.2 | 0.3 | 40675.2978 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9869 | 5200.9869 | 5200.9869 | 5200.9869 | 5200.9869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13216 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 26424.8594 | 0.2 | 0.3 | 41222.7807 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3558 | 5201.3558 | 5201.3558 | 5201.3558 | 5201.3558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13217 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17904.992 | 0.2 | 0.3 | 27931.7875 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0012 | 5202.0012 | 5202.0012 | 5202.0012 | 5202.0012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13218 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15670.9628 | 0.2 | 0.3 | 24446.702 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9573 | 5201.9573 | 5201.9573 | 5201.9573 | 5201.9573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13219 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19635.2829 | 0.2 | 0.3 | 30631.0413 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13220 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 25463.9823 | 0.2 | 0.3 | 39723.8123 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1142 | 5201.1142 | 5201.1142 | 5201.1142 | 5201.1142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13221 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10786.6535 | 0.2 | 0.3 | 16827.1795 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4177 | 5201.4177 | 5201.4177 | 5201.4177 | 5201.4177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13222 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 24330.7692 | 0.2 | 0.3 | 37956 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3219 | 5202.3219 | 5202.3219 | 5202.3219 | 5202.3219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13223 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10771.9704 | 0.2 | 0.3 | 16804.2738 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7444 | 5202.7444 | 5202.7444 | 5202.7444 | 5202.7444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13224 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 25243.3327 | 0.2 | 0.3 | 39379.5991 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7972 | 5201.7972 | 5201.7972 | 5201.7972 | 5201.7972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13225 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 7428.1546 | 0.2 | 0.3 | 11587.9212 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7205 | 5202.7205 | 5202.7205 | 5202.7205 | 5202.7205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13226 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16146.616 | 0.2 | 0.3 | 25188.721 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6355.7571 | 6355.7571 | 6355.7571 | 6355.7571 | 6355.7571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13227 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22288.6359 | 0.2 | 0.3 | 34770.2721 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.8235 | 5203.8235 | 5203.8235 | 5203.8235 | 5203.8235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13228 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 5286.3711 | 0.2 | 0.3 | 8246.7389 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.8193 | 5203.8193 | 5203.8193 | 5203.8193 | 5203.8193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13229 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1247.0934 | 0.2 | 0.3 | 1945.4657 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7572.5341 | 7572.5341 | 7572.5341 | 7572.5341 | 7572.5341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13230 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7403.937 | 7403.937 | 7403.937 | 7403.937 | 7403.937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13231 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9774.0448 | 9774.0448 | 9774.0448 | 9774.0448 | 9774.0448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13232 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7189.8141 | 7189.8141 | 7189.8141 | 7189.8141 | 7189.8141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13233 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16745.6241 | 0.2 | 0.3 | 26123.1736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7148.4126 | 7148.4126 | 7148.4126 | 7148.4126 | 7148.4126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13234 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 6344.4207 | 0.2 | 0.3 | 9897.2962 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7630.0695 | 7630.0695 | 7630.0695 | 7630.0695 | 7630.0695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13235 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 19093.3253 | 0.2 | 0.3 | 29785.5874 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7618.0417 | 7618.0417 | 7618.0417 | 7618.0417 | 7618.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13236 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 3925.2672 | 0.2 | 0.3 | 6123.4168 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7016.2656 | 7016.2656 | 7016.2656 | 7016.2656 | 7016.2656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13237 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7153.9719 | 7153.9719 | 7153.9719 | 7153.9719 | 7153.9719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13238 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6393.868 | 6393.868 | 6393.868 | 6393.868 | 6393.868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13239 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6105 | 0.2 | 0.3 | 25999.9124 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6240.7787 | 6240.7787 | 6240.7787 | 6240.7787 | 6240.7787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13240 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8060.043 | 8060.043 | 8060.043 | 8060.043 | 8060.043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13241 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7148.0233 | 7148.0233 | 7148.0233 | 7148.0233 | 7148.0233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13242 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 2362.3356 | 0.2 | 0.3 | 3685.2435 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7424.3742 | 7424.3742 | 7424.3742 | 7424.3742 | 7424.3742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13243 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1487 | 0.2 | 0.3 | 26000.7519 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6773.5721 | 6773.5721 | 6773.5721 | 6773.5721 | 6773.5721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13244 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 35810.5298 | 0.2 | 0.3 | 55864.4265 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2299 | 5202.2299 | 5202.2299 | 5202.2299 | 5202.2299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13245 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16668.0427 | 0.2 | 0.3 | 26002.1467 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6591.0985 | 6591.0985 | 6591.0985 | 6591.0985 | 6591.0985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13246 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 29082.946 | 0.2 | 0.3 | 45369.3958 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2668.2139 | 2668.2139 | 2668.2139 | 2668.2139 | 2668.2139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13247 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 20920.4653 | 0.2 | 0.3 | 32635.9259 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5212.4991 | 5212.4991 | 5212.4991 | 5212.4991 | 5212.4991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13248 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2314 | 5201.2314 | 5201.2314 | 5201.2314 | 5201.2314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13249 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16667.4545 | 0.2 | 0.3 | 26001.229 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13250 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 6028.3011 | 0.2 | 0.3 | 9404.1497 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4446 | 5201.4446 | 5201.4446 | 5201.4446 | 5201.4446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13251 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 21592.0533 | 0.2 | 0.3 | 33683.6032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13252 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 31912.7516 | 0.2 | 0.3 | 49783.8925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8112.7969 | 8112.7969 | 8112.7969 | 8112.7969 | 8112.7969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13253 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 35449.8929 | 0.2 | 0.3 | 55301.833 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6885.0009 | 6885.0009 | 6885.0009 | 6885.0009 | 6885.0009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13254 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 2135.5682 | 0.2 | 0.3 | 3331.4864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7574.4109 | 7574.4109 | 7574.4109 | 7574.4109 | 7574.4109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13255 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 14377.8821 | 0.2 | 0.3 | 22429.4961 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7726.6238 | 7726.6238 | 7726.6238 | 7726.6238 | 7726.6238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13256 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 17158.8115 | 0.2 | 0.3 | 26767.746 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8080.4749 | 8080.4749 | 8080.4749 | 8080.4749 | 8080.4749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13257 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 19639.4004 | 0.2 | 0.3 | 30637.4646 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13258 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 17644.5249 | 0.2 | 0.3 | 27525.4589 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3153.7002 | 3153.7002 | 3153.7002 | 3153.7002 | 3153.7002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13259 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 18113.9798 | 0.2 | 0.3 | 28257.8085 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5191.0338 | 5191.0338 | 5191.0338 | 5191.0338 | 5191.0338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13260 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 5794.5787 | 0.2 | 0.3 | 9039.5428 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3772 | 5201.3772 | 5201.3772 | 5201.3772 | 5201.3772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13261 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 11352.35 | 0.2 | 0.3 | 17709.666 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1609 | 5201.1609 | 5201.1609 | 5201.1609 | 5201.1609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13262 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 31238.4229 | 0.2 | 0.3 | 48731.9397 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1654 | 5202.1654 | 5202.1654 | 5202.1654 | 5202.1654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13263 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 38364.4157 | 0.2 | 0.3 | 59848.4884 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6246 | 5201.6246 | 5201.6246 | 5201.6246 | 5201.6246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13264 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 102.2641 | 0.2 | 0.3 | 159.5319 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6077.0119 | 6077.0119 | 6077.0119 | 6077.0119 | 6077.0119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13265 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2069.1909 | 0.2 | 0.3 | 3227.9379 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 103.437 | 103.437 | 103.437 | 103.437 | 103.437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13266 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20780.6165 | 0.2 | 0.3 | 32417.7618 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5215.7454 | 5215.7454 | 5215.7454 | 5215.7454 | 5215.7454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13267 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19253.2947 | 0.2 | 0.3 | 30035.1397 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5651.7902 | 5651.7902 | 5651.7902 | 5651.7902 | 5651.7902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13268 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17967.4414 | 0.2 | 0.3 | 28029.2086 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5554.1224 | 5554.1224 | 5554.1224 | 5554.1224 | 5554.1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13269 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17534.4417 | 0.2 | 0.3 | 27353.729 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5620.5478 | 5620.5478 | 5620.5478 | 5620.5478 | 5620.5478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13270 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 6754.0338 | 0.2 | 0.3 | 10536.2927 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9172.1004 | 9172.1004 | 9172.1004 | 9172.1004 | 9172.1004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13271 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 24350.4517 | 0.2 | 0.3 | 37986.7046 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7128.982 | 7128.982 | 7128.982 | 7128.982 | 7128.982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13272 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 221.2959 | 0.2 | 0.3 | 345.2216 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7149.8328 | 7149.8328 | 7149.8328 | 7149.8328 | 7149.8328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13273 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14838.6311 | 0.2 | 0.3 | 23148.2645 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9317.7793 | 9317.7793 | 9317.7793 | 9317.7793 | 9317.7793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13274 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 7520.647 | 0.2 | 0.3 | 11732.2093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5371.4722 | 5371.4722 | 5371.4722 | 5371.4722 | 5371.4722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13275 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1311.9605 | 0.2 | 0.3 | 2046.6583 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5346.5866 | 5346.5866 | 5346.5866 | 5346.5866 | 5346.5866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13276 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20584.7336 | 0.2 | 0.3 | 32112.1844 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11316.5321 | 11316.5321 | 11316.5321 | 11316.5321 | 11316.5321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13277 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7901 | 0.2 | 0.3 | 26003.3125 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5996.5079 | 5996.5079 | 5996.5079 | 5996.5079 | 5996.5079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13278 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.4763 | 0.2 | 0.3 | 26002.823 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4298.5074 | 4298.5074 | 4298.5074 | 4298.5074 | 4298.5074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13279 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7883 | 0.2 | 0.3 | 26003.3097 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8087.3073 | 8087.3073 | 8087.3073 | 8087.3073 | 8087.3073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13280 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 18648.3605 | 0.2 | 0.3 | 29091.4424 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6741.2922 | 6741.2922 | 6741.2922 | 6741.2922 | 6741.2922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13281 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 1515.2483 | 0.2 | 0.3 | 2363.7874 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5269.4993 | 5269.4993 | 5269.4993 | 5269.4993 | 5269.4993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13282 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 19686.0216 | 0.2 | 0.3 | 30710.1937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 541.0108 | 541.0108 | 541.0108 | 541.0108 | 541.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13283 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 415.9496 | 415.9496 | 415.9496 | 415.9496 | 415.9496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13284 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16668.4265 | 0.2 | 0.3 | 26002.7453 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11336.1592 | 11336.1592 | 11336.1592 | 11336.1592 | 11336.1592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13285 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 26244.8485 | 0.2 | 0.3 | 40941.9637 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2882.5454 | 2882.5454 | 2882.5454 | 2882.5454 | 2882.5454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13286 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 25085.7768 | 0.2 | 0.3 | 39133.8118 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10368.0881 | 10368.0881 | 10368.0881 | 10368.0881 | 10368.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13287 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 22450.2027 | 0.2 | 0.3 | 35022.3163 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4085.4763 | 4085.4763 | 4085.4763 | 4085.4763 | 4085.4763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13288 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16488.7512 | 0.2 | 0.3 | 25722.4519 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13626.4589 | 13626.4589 | 13626.4589 | 13626.4589 | 13626.4589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13289 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 12457.5322 | 0.2 | 0.3 | 19433.7502 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10636.0707 | 10636.0707 | 10636.0707 | 10636.0707 | 10636.0707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13290 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 6210.1417 | 0.2 | 0.3 | 9687.8211 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7695.0057 | 7695.0057 | 7695.0057 | 7695.0057 | 7695.0057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13291 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 15579.2582 | 0.2 | 0.3 | 24303.6428 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10904.7311 | 10904.7311 | 10904.7311 | 10904.7311 | 10904.7311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13292 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 21696.8369 | 0.2 | 0.3 | 33847.0656 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8967.7147 | 8967.7147 | 8967.7147 | 8967.7147 | 8967.7147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13293 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 25335.0071 | 0.2 | 0.3 | 39522.611 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6743.8125 | 6743.8125 | 6743.8125 | 6743.8125 | 6743.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13294 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 42177.1851 | 0.2 | 0.3 | 65796.4087 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7447.4014 | 7447.4014 | 7447.4014 | 7447.4014 | 7447.4014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13295 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 36437.4855 | 0.2 | 0.3 | 56842.4774 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5130.9819 | 5130.9819 | 5130.9819 | 5130.9819 | 5130.9819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13296 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 30832.213 | 0.2 | 0.3 | 48098.2523 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7407.8161 | 7407.8161 | 7407.8161 | 7407.8161 | 7407.8161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13297 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 20.4159 | 0.2 | 0.3 | 31.8488 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9524.1869 | 9524.1869 | 9524.1869 | 9524.1869 | 9524.1869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13298 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 33402.2676 | 0.2 | 0.3 | 52107.5375 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10528.7219 | 10528.7219 | 10528.7219 | 10528.7219 | 10528.7219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13299 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16669.9066 | 0.2 | 0.3 | 26005.0543 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5355.9892 | 5355.9892 | 5355.9892 | 5355.9892 | 5355.9892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13300 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16728.0487 | 0.2 | 0.3 | 26095.7559 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6775.9128 | 6775.9128 | 6775.9128 | 6775.9128 | 6775.9128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13301 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16462.0998 | 0.2 | 0.3 | 25680.8757 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4850.3133 | 4850.3133 | 4850.3133 | 4850.3133 | 4850.3133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13302 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 25152.7198 | 0.2 | 0.3 | 39238.2429 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7993.737 | 7993.737 | 7993.737 | 7993.737 | 7993.737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13303 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 24849.9389 | 0.2 | 0.3 | 38765.9047 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8983 | 5200.8983 | 5200.8983 | 5200.8983 | 5200.8983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13304 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1944.0799 | 0.2 | 0.3 | 3032.7646 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9380.0398 | 9380.0398 | 9380.0398 | 9380.0398 | 9380.0398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13305 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19845.1685 | 0.2 | 0.3 | 30958.4629 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7155.7903 | 7155.7903 | 7155.7903 | 7155.7903 | 7155.7903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13306 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13579.1332 | 0.2 | 0.3 | 21183.4478 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5367.8878 | 5367.8878 | 5367.8878 | 5367.8878 | 5367.8878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13307 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6416 | 0.2 | 0.3 | 25999.9609 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.1907 | 5205.1907 | 5205.1907 | 5205.1907 | 5205.1907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13308 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 27310.3045 | 0.2 | 0.3 | 42604.075 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 922.7768 | 922.7768 | 922.7768 | 922.7768 | 922.7768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13309 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 3055.5694 | 0.2 | 0.3 | 4766.6883 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10458.4484 | 10458.4484 | 10458.4484 | 10458.4484 | 10458.4484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13310 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 6260.0535 | 0.2 | 0.3 | 9765.6835 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13311 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22204.9567 | 0.2 | 0.3 | 34639.7324 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13312 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 5766.3193 | 0.2 | 0.3 | 8995.4581 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.8253 | 5203.8253 | 5203.8253 | 5203.8253 | 5203.8253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13313 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20280.6127 | 0.2 | 0.3 | 31637.7558 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.4188 | 5203.4188 | 5203.4188 | 5203.4188 | 5203.4188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13314 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12713.2925 | 0.2 | 0.3 | 19832.7362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13315 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18938.9507 | 0.2 | 0.3 | 29544.763 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5093.2757 | 5093.2757 | 5093.2757 | 5093.2757 | 5093.2757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13316 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 9897.3345 | 0.2 | 0.3 | 15439.8418 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4056.9891 | 4056.9891 | 4056.9891 | 4056.9891 | 4056.9891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13317 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19027.0888 | 0.2 | 0.3 | 29682.2585 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9284.874 | 9284.874 | 9284.874 | 9284.874 | 9284.874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13318 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8575.1734 | 8575.1734 | 8575.1734 | 8575.1734 | 8575.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13319 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.5138 | 0.2 | 0.3 | 26002.8815 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8109.6103 | 8109.6103 | 8109.6103 | 8109.6103 | 8109.6103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13320 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0631 | 5202.0631 | 5202.0631 | 5202.0631 | 5202.0631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13321 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 20415.3125 | 0.2 | 0.3 | 31847.8876 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14150.6157 | 14150.6157 | 14150.6157 | 14150.6157 | 14150.6157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13322 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 20590.2253 | 0.2 | 0.3 | 32120.7515 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8633.6825 | 8633.6825 | 8633.6825 | 8633.6825 | 8633.6825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13323 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 12868.9379 | 0.2 | 0.3 | 20075.5432 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8072.9152 | 8072.9152 | 8072.9152 | 8072.9152 | 8072.9152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13324 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 14130.0223 | 0.2 | 0.3 | 22042.8348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9782.2027 | 9782.2027 | 9782.2027 | 9782.2027 | 9782.2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13325 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 20760.2237 | 0.2 | 0.3 | 32385.949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8649.8044 | 8649.8044 | 8649.8044 | 8649.8044 | 8649.8044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13326 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5673.0869 | 5673.0869 | 5673.0869 | 5673.0869 | 5673.0869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13327 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13328 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 21682.2839 | 0.2 | 0.3 | 33824.3628 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8032.2953 | 8032.2953 | 8032.2953 | 8032.2953 | 8032.2953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13329 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 11643.6837 | 0.2 | 0.3 | 18164.1466 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6561.4451 | 6561.4451 | 6561.4451 | 6561.4451 | 6561.4451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13330 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 20523.9418 | 0.2 | 0.3 | 32017.3492 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5955.3027 | 5955.3027 | 5955.3027 | 5955.3027 | 5955.3027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13331 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 28398.5021 | 0.2 | 0.3 | 44301.6633 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5352.7573 | 5352.7573 | 5352.7573 | 5352.7573 | 5352.7573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13332 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 6105.0284 | 0.2 | 0.3 | 9523.8443 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5150.7717 | 5150.7717 | 5150.7717 | 5150.7717 | 5150.7717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13333 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 20561.4129 | 0.2 | 0.3 | 32075.8042 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9644.2464 | 9644.2464 | 9644.2464 | 9644.2464 | 9644.2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13334 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 33335.6295 | 0.2 | 0.3 | 52003.582 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13335 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13336 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16672.0195 | 0.2 | 0.3 | 26008.3505 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3539 | 5203.3539 | 5203.3539 | 5203.3539 | 5203.3539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13337 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16690.386 | 0.2 | 0.3 | 26037.0022 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6307.1447 | 6307.1447 | 6307.1447 | 6307.1447 | 6307.1447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13338 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 29283.2428 | 0.2 | 0.3 | 45681.8588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.077 | 5203.077 | 5203.077 | 5203.077 | 5203.077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13339 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11986.7623 | 0.2 | 0.3 | 18699.3492 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13340 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16767.7839 | 0.2 | 0.3 | 26157.7428 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5232.3765 | 5232.3765 | 5232.3765 | 5232.3765 | 5232.3765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13341 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6374.2985 | 6374.2985 | 6374.2985 | 6374.2985 | 6374.2985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13342 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19405.7259 | 0.2 | 0.3 | 30272.9325 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6420.108 | 6420.108 | 6420.108 | 6420.108 | 6420.108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13343 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12578.4403 | 0.2 | 0.3 | 19622.3668 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9588.5013 | 9588.5013 | 9588.5013 | 9588.5013 | 9588.5013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13344 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16678.7082 | 0.2 | 0.3 | 26018.7848 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9508.4679 | 9508.4679 | 9508.4679 | 9508.4679 | 9508.4679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13345 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21840.8397 | 0.2 | 0.3 | 34071.7099 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9398.0706 | 9398.0706 | 9398.0706 | 9398.0706 | 9398.0706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13346 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 24009.1454 | 0.2 | 0.3 | 37454.2668 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10642.7351 | 10642.7351 | 10642.7351 | 10642.7351 | 10642.7351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13347 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20259.6517 | 0.2 | 0.3 | 31605.0566 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10404.2023 | 10404.2023 | 10404.2023 | 10404.2023 | 10404.2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13348 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18013.5311 | 0.2 | 0.3 | 28101.1086 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13062.1163 | 13062.1163 | 13062.1163 | 13062.1163 | 13062.1163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13349 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 3990.9642 | 0.2 | 0.3 | 6225.9042 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1866.3455 | 1866.3455 | 1866.3455 | 1866.3455 | 1866.3455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13350 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 20822.2685 | 0.2 | 0.3 | 32482.7388 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.921 | 9776.921 | 9776.921 | 9776.921 | 9776.921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13351 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 13334.6758 | 0.2 | 0.3 | 20802.0942 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3041 | 5200.3041 | 5200.3041 | 5200.3041 | 5200.3041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13352 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17085.1367 | 0.2 | 0.3 | 26652.8133 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13353 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0632 | 5200.0632 | 5200.0632 | 5200.0632 | 5200.0632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13354 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5268.5521 | 5268.5521 | 5268.5521 | 5268.5521 | 5268.5521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13355 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5711.462 | 5711.462 | 5711.462 | 5711.462 | 5711.462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13356 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 4141.5789 | 0.2 | 0.3 | 6460.8631 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10604.6291 | 10604.6291 | 10604.6291 | 10604.6291 | 10604.6291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13357 | PARKLAND | 10503 | Public | 2036 | 5 | Swales | 66.6667 | 3117.0521 | 0.2 | 0.3 | 4862.6012 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4321.2943 | 4321.2943 | 4321.2943 | 4321.2943 | 4321.2943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13358 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6240.6684 | 6240.6684 | 6240.6684 | 6240.6684 | 6240.6684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13359 | PARKLAND | 10504 | Private | 2036 | 5 | Swales | 66.6667 | 16668.4532 | 0.2 | 0.3 | 26002.787 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5249.0481 | 5249.0481 | 5249.0481 | 5249.0481 | 5249.0481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13360 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 13450.1294 | 0.2 | 0.3 | 20982.2019 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6852.321 | 6852.321 | 6852.321 | 6852.321 | 6852.321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13361 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16723.3987 | 0.2 | 0.3 | 26088.502 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3564.0664 | 3564.0664 | 3564.0664 | 3564.0664 | 3564.0664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13362 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7289 | 0.2 | 0.3 | 26000.097 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5191.8656 | 5191.8656 | 5191.8656 | 5191.8656 | 5191.8656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13363 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 31416.2399 | 0.2 | 0.3 | 49009.3342 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6332.8834 | 6332.8834 | 6332.8834 | 6332.8834 | 6332.8834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13364 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16715.6902 | 0.2 | 0.3 | 26076.4767 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5415.1194 | 5415.1194 | 5415.1194 | 5415.1194 | 5415.1194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13365 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 18845.6539 | 0.2 | 0.3 | 29399.2201 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3838 | 5200.3838 | 5200.3838 | 5200.3838 | 5200.3838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13366 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 24210.7597 | 0.2 | 0.3 | 37768.7851 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13367 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 19271.723 | 0.2 | 0.3 | 30063.8879 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10659.9968 | 10659.9968 | 10659.9968 | 10659.9968 | 10659.9968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13368 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 19516.8383 | 0.2 | 0.3 | 30446.2678 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8156.3587 | 8156.3587 | 8156.3587 | 8156.3587 | 8156.3587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13369 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 28897.7049 | 0.2 | 0.3 | 45080.4196 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7175.569 | 7175.569 | 7175.569 | 7175.569 | 7175.569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13370 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 95.535 | 0.2 | 0.3 | 149.0346 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5286.3896 | 5286.3896 | 5286.3896 | 5286.3896 | 5286.3896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13371 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16669.1027 | 0.2 | 0.3 | 26003.8003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2437.3189 | 2437.3189 | 2437.3189 | 2437.3189 | 2437.3189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13372 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 30168.4346 | 0.2 | 0.3 | 47062.758 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6496.7542 | 6496.7542 | 6496.7542 | 6496.7542 | 6496.7542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13373 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 31214.7162 | 0.2 | 0.3 | 48694.9573 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5219.6095 | 5219.6095 | 5219.6095 | 5219.6095 | 5219.6095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13374 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 13288.5351 | 0.2 | 0.3 | 20730.1148 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5221.9002 | 5221.9002 | 5221.9002 | 5221.9002 | 5221.9002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13375 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16681.9756 | 0.2 | 0.3 | 26023.8819 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6696.7233 | 6696.7233 | 6696.7233 | 6696.7233 | 6696.7233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13376 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16712.1487 | 0.2 | 0.3 | 26070.952 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5450.5048 | 5450.5048 | 5450.5048 | 5450.5048 | 5450.5048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13377 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 297.0879 | 0.2 | 0.3 | 463.4571 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8945 | 5199.8945 | 5199.8945 | 5199.8945 | 5199.8945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13378 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16285.7019 | 0.2 | 0.3 | 25405.695 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5210.1263 | 5210.1263 | 5210.1263 | 5210.1263 | 5210.1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13379 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 6251.5938 | 0.2 | 0.3 | 9752.4863 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13374.1967 | 13374.1967 | 13374.1967 | 13374.1967 | 13374.1967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13380 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18319.4197 | 0.2 | 0.3 | 28578.2947 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9531.8442 | 9531.8442 | 9531.8442 | 9531.8442 | 9531.8442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13381 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 21600.6327 | 0.2 | 0.3 | 33696.9871 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8009.9535 | 8009.9535 | 8009.9535 | 8009.9535 | 8009.9535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13382 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 19837.3892 | 0.2 | 0.3 | 30946.3272 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2596.2847 | 2596.2847 | 2596.2847 | 2596.2847 | 2596.2847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13383 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 6838.1751 | 0.2 | 0.3 | 10667.5532 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7560.8472 | 7560.8472 | 7560.8472 | 7560.8472 | 7560.8472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13384 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 12985.3701 | 0.2 | 0.3 | 20257.1774 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5303.4673 | 5303.4673 | 5303.4673 | 5303.4673 | 5303.4673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13385 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 28439.2794 | 0.2 | 0.3 | 44365.2759 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5301.1398 | 5301.1398 | 5301.1398 | 5301.1398 | 5301.1398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13386 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 26676.9267 | 0.2 | 0.3 | 41616.0057 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5285.6351 | 5285.6351 | 5285.6351 | 5285.6351 | 5285.6351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13387 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17183.9237 | 0.2 | 0.3 | 26806.921 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7443.1558 | 7443.1558 | 7443.1558 | 7443.1558 | 7443.1558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13388 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16784.6589 | 0.2 | 0.3 | 26184.0679 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13389 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 6403.8725 | 0.2 | 0.3 | 9990.0412 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5299.9897 | 5299.9897 | 5299.9897 | 5299.9897 | 5299.9897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13390 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 2884.4066 | 0.2 | 0.3 | 4499.6743 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10175.3541 | 10175.3541 | 10175.3541 | 10175.3541 | 10175.3541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13391 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16676.7768 | 0.2 | 0.3 | 26015.7718 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10112.296 | 10112.296 | 10112.296 | 10112.296 | 10112.296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13392 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 19175.9549 | 0.2 | 0.3 | 29914.4897 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9626.6622 | 9626.6622 | 9626.6622 | 9626.6622 | 9626.6622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13393 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16937.6368 | 0.2 | 0.3 | 26422.7134 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6329.8082 | 6329.8082 | 6329.8082 | 6329.8082 | 6329.8082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13394 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 17185.336 | 0.2 | 0.3 | 26809.1242 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6348.4809 | 6348.4809 | 6348.4809 | 6348.4809 | 6348.4809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13395 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 20760.3592 | 0.2 | 0.3 | 32386.1604 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 742.5303 | 742.5303 | 742.5303 | 742.5303 | 742.5303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13396 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 27471.1675 | 0.2 | 0.3 | 42855.0212 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8529.9726 | 8529.9726 | 8529.9726 | 8529.9726 | 8529.9726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13397 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8244.9126 | 8244.9126 | 8244.9126 | 8244.9126 | 8244.9126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13398 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 26731.7106 | 0.2 | 0.3 | 41701.4685 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8835.986 | 8835.986 | 8835.986 | 8835.986 | 8835.986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13399 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 18603.7583 | 0.2 | 0.3 | 29021.8629 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11001.8533 | 11001.8533 | 11001.8533 | 11001.8533 | 11001.8533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13400 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 872.7299 | 0.2 | 0.3 | 1361.4586 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1480.819 | 1480.819 | 1480.819 | 1480.819 | 1480.819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13401 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 13417.3522 | 0.2 | 0.3 | 20931.0694 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5284.1459 | 5284.1459 | 5284.1459 | 5284.1459 | 5284.1459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13402 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 10086.4997 | 0.2 | 0.3 | 15734.9396 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2414.8414 | 2414.8414 | 2414.8414 | 2414.8414 | 2414.8414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13403 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17229.6981 | 0.2 | 0.3 | 26878.329 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4617.4906 | 4617.4906 | 4617.4906 | 4617.4906 | 4617.4906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13404 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 11831.7723 | 0.2 | 0.3 | 18457.5648 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8817.39 | 8817.39 | 8817.39 | 8817.39 | 8817.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13405 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17451.2456 | 0.2 | 0.3 | 27223.9431 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3042.1867 | 3042.1867 | 3042.1867 | 3042.1867 | 3042.1867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13406 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 9674.0665 | 0.2 | 0.3 | 15091.5437 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4366.8198 | 4366.8198 | 4366.8198 | 4366.8198 | 4366.8198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13407 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16668.9644 | 0.2 | 0.3 | 26003.5845 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 920.4515 | 920.4515 | 920.4515 | 920.4515 | 920.4515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13408 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16637.6193 | 0.2 | 0.3 | 25954.6862 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2701.3853 | 2701.3853 | 2701.3853 | 2701.3853 | 2701.3853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13409 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 6709.7107 | 0.2 | 0.3 | 10467.1487 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8300.9365 | 8300.9365 | 8300.9365 | 8300.9365 | 8300.9365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13410 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 17105.1196 | 0.2 | 0.3 | 26683.9866 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7948.9327 | 7948.9327 | 7948.9327 | 7948.9327 | 7948.9327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13411 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 23860.3582 | 0.2 | 0.3 | 37222.1588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8462.4842 | 8462.4842 | 8462.4842 | 8462.4842 | 8462.4842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13412 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 5319.2177 | 0.2 | 0.3 | 8297.9797 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3750.3267 | 3750.3267 | 3750.3267 | 3750.3267 | 3750.3267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13413 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 24490.1587 | 0.2 | 0.3 | 38204.6475 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3180.8439 | 3180.8439 | 3180.8439 | 3180.8439 | 3180.8439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13414 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 29164.2602 | 0.2 | 0.3 | 45496.2459 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1675 | 5203.1675 | 5203.1675 | 5203.1675 | 5203.1675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13415 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 19306.5603 | 0.2 | 0.3 | 30118.234 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5674.4095 | 5674.4095 | 5674.4095 | 5674.4095 | 5674.4095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13416 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 17404.9205 | 0.2 | 0.3 | 27151.676 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1816 | 5203.1816 | 5203.1816 | 5203.1816 | 5203.1816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13417 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 17731.3813 | 0.2 | 0.3 | 27660.9549 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7273.879 | 7273.879 | 7273.879 | 7273.879 | 7273.879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13418 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16213.2143 | 0.2 | 0.3 | 25292.6143 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5414.1743 | 5414.1743 | 5414.1743 | 5414.1743 | 5414.1743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13419 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 30271.6477 | 0.2 | 0.3 | 47223.7705 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6627.7888 | 6627.7888 | 6627.7888 | 6627.7888 | 6627.7888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13420 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 27908.9305 | 0.2 | 0.3 | 43537.9315 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5297.554 | 5297.554 | 5297.554 | 5297.554 | 5297.554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13421 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 25535.4318 | 0.2 | 0.3 | 39835.2736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5117.3075 | 5117.3075 | 5117.3075 | 5117.3075 | 5117.3075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13422 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 26073.0222 | 0.2 | 0.3 | 40673.9146 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5220.547 | 5220.547 | 5220.547 | 5220.547 | 5220.547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13423 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 28738.5176 | 0.2 | 0.3 | 44832.0875 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9728.5156 | 9728.5156 | 9728.5156 | 9728.5156 | 9728.5156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13424 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 17568.0625 | 0.2 | 0.3 | 27406.1776 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6039.0149 | 6039.0149 | 6039.0149 | 6039.0149 | 6039.0149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13425 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 16781.5233 | 0.2 | 0.3 | 26179.1764 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6004.3134 | 6004.3134 | 6004.3134 | 6004.3134 | 6004.3134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13426 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 25593.0294 | 0.2 | 0.3 | 39925.1259 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8257.0039 | 8257.0039 | 8257.0039 | 8257.0039 | 8257.0039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13427 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 9864.0647 | 0.2 | 0.3 | 15387.941 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5644.1568 | 5644.1568 | 5644.1568 | 5644.1568 | 5644.1568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13428 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 24972.3016 | 0.2 | 0.3 | 38956.7905 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1590.875 | 1590.875 | 1590.875 | 1590.875 | 1590.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13429 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 17620.4203 | 0.2 | 0.3 | 27487.8557 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10221.0537 | 10221.0537 | 10221.0537 | 10221.0537 | 10221.0537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13430 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 4886.3037 | 0.2 | 0.3 | 7622.6338 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10224.9786 | 10224.9786 | 10224.9786 | 10224.9786 | 10224.9786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13431 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16178.8747 | 0.2 | 0.3 | 25239.0446 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1873.6971 | 1873.6971 | 1873.6971 | 1873.6971 | 1873.6971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13432 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16666.8077 | 0.2 | 0.3 | 26000.2201 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2309.0996 | 2309.0996 | 2309.0996 | 2309.0996 | 2309.0996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13433 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16666.6419 | 0.2 | 0.3 | 25999.9614 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5177.7266 | 5177.7266 | 5177.7266 | 5177.7266 | 5177.7266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13434 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 17407.582 | 0.2 | 0.3 | 27155.8279 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1625.1079 | 1625.1079 | 1625.1079 | 1625.1079 | 1625.1079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13435 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16844.243 | 0.2 | 0.3 | 26277.0191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6643.2218 | 6643.2218 | 6643.2218 | 6643.2218 | 6643.2218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13436 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 2048.4153 | 0.2 | 0.3 | 3195.5278 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8058.9822 | 8058.9822 | 8058.9822 | 8058.9822 | 8058.9822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13437 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17229.5991 | 0.2 | 0.3 | 26878.1746 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9851.3153 | 9851.3153 | 9851.3153 | 9851.3153 | 9851.3153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13438 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 904.4207 | 0.2 | 0.3 | 1410.8963 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5706.3496 | 5706.3496 | 5706.3496 | 5706.3496 | 5706.3496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13439 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 18093.3334 | 0.2 | 0.3 | 28225.6001 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9376.6352 | 9376.6352 | 9376.6352 | 9376.6352 | 9376.6352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13440 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 16794.6587 | 0.2 | 0.3 | 26199.6676 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7737.982 | 7737.982 | 7737.982 | 7737.982 | 7737.982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13441 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 10114.3272 | 0.2 | 0.3 | 15778.3504 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5802.9925 | 5802.9925 | 5802.9925 | 5802.9925 | 5802.9925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13442 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 9291.8857 | 0.2 | 0.3 | 14495.3417 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13443 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 13137.1333 | 0.2 | 0.3 | 20493.928 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6027.2987 | 6027.2987 | 6027.2987 | 6027.2987 | 6027.2987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13444 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 7342.2854 | 0.2 | 0.3 | 11453.9652 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0202 | 5204.0202 | 5204.0202 | 5204.0202 | 5204.0202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13445 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 25480.7636 | 0.2 | 0.3 | 39749.9912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13446 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.792 | 5203.792 | 5203.792 | 5203.792 | 5203.792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13447 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16605.9047 | 0.2 | 0.3 | 25905.2114 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8874.0742 | 8874.0742 | 8874.0742 | 8874.0742 | 8874.0742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13448 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 22524.9398 | 0.2 | 0.3 | 35138.9061 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6746.3698 | 6746.3698 | 6746.3698 | 6746.3698 | 6746.3698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13449 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16495.4236 | 0.2 | 0.3 | 25732.8608 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8155.9376 | 8155.9376 | 8155.9376 | 8155.9376 | 8155.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13450 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16669.0451 | 0.2 | 0.3 | 26003.7104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4151.3848 | 4151.3848 | 4151.3848 | 4151.3848 | 4151.3848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13451 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 20599.9957 | 0.2 | 0.3 | 32135.9933 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4032.7765 | 4032.7765 | 4032.7765 | 4032.7765 | 4032.7765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13452 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 40549.2759 | 0.2 | 0.3 | 63256.8705 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9664.3717 | 9664.3717 | 9664.3717 | 9664.3717 | 9664.3717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13453 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 41699.5368 | 0.2 | 0.3 | 65051.2774 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13454 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 32818.9794 | 0.2 | 0.3 | 51197.6079 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5997.9912 | 5997.9912 | 5997.9912 | 5997.9912 | 5997.9912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13455 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 30830.2849 | 0.2 | 0.3 | 48095.2445 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8770.045 | 8770.045 | 8770.045 | 8770.045 | 8770.045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13456 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 17409.4079 | 0.2 | 0.3 | 27158.6763 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6175.2194 | 6175.2194 | 6175.2194 | 6175.2194 | 6175.2194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13457 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 17490.7321 | 0.2 | 0.3 | 27285.542 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8386.1648 | 8386.1648 | 8386.1648 | 8386.1648 | 8386.1648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13458 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 28099.7182 | 0.2 | 0.3 | 43835.5604 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7564.8414 | 7564.8414 | 7564.8414 | 7564.8414 | 7564.8414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13459 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 1392.579 | 0.2 | 0.3 | 2172.4232 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8317.8337 | 8317.8337 | 8317.8337 | 8317.8337 | 8317.8337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13460 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 23888.0792 | 0.2 | 0.3 | 37265.4036 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5385.5193 | 5385.5193 | 5385.5193 | 5385.5193 | 5385.5193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13461 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 25781.4981 | 0.2 | 0.3 | 40219.1371 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10679.4917 | 10679.4917 | 10679.4917 | 10679.4917 | 10679.4917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13462 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 20907.6449 | 0.2 | 0.3 | 32615.9261 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6096.842 | 6096.842 | 6096.842 | 6096.842 | 6096.842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13463 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 16141.1179 | 0.2 | 0.3 | 25180.1439 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8.6964 | 8.6964 | 8.6964 | 8.6964 | 8.6964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13464 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 9242.3904 | 0.2 | 0.3 | 14418.129 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7020.4885 | 7020.4885 | 7020.4885 | 7020.4885 | 7020.4885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13465 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 31926.7248 | 0.2 | 0.3 | 49805.6907 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.004 | 5204.004 | 5204.004 | 5204.004 | 5204.004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13466 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 16667.0071 | 0.2 | 0.3 | 26000.531 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9107 | 5203.9107 | 5203.9107 | 5203.9107 | 5203.9107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13467 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 20178.3326 | 0.2 | 0.3 | 31478.1989 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5778.0538 | 5778.0538 | 5778.0538 | 5778.0538 | 5778.0538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13468 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 18969.4965 | 0.2 | 0.3 | 29592.4146 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3635 | 5200.3635 | 5200.3635 | 5200.3635 | 5200.3635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13469 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 17673.832 | 0.2 | 0.3 | 27571.1779 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2987 | 5200.2987 | 5200.2987 | 5200.2987 | 5200.2987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13470 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 18307.7424 | 0.2 | 0.3 | 28560.0781 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7799.7038 | 7799.7038 | 7799.7038 | 7799.7038 | 7799.7038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13471 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 22043.469 | 0.2 | 0.3 | 34387.8116 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13472 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 622.9745 | 0.2 | 0.3 | 971.8402 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13473 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17156.5691 | 0.2 | 0.3 | 26764.2477 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9483.7099 | 9483.7099 | 9483.7099 | 9483.7099 | 9483.7099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13474 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 2867.1573 | 0.2 | 0.3 | 4472.7654 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13475 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22113.076 | 0.2 | 0.3 | 34496.3986 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5434.687 | 5434.687 | 5434.687 | 5434.687 | 5434.687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13476 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1993.4897 | 0.2 | 0.3 | 3109.8439 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10965.6502 | 10965.6502 | 10965.6502 | 10965.6502 | 10965.6502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13477 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17139.1641 | 0.2 | 0.3 | 26737.096 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14621.6617 | 14621.6617 | 14621.6617 | 14621.6617 | 14621.6617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13478 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 15483.519 | 0.2 | 0.3 | 24154.2896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13256.7075 | 13256.7075 | 13256.7075 | 13256.7075 | 13256.7075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13479 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 15489.5429 | 0.2 | 0.3 | 24163.6869 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11007.5629 | 11007.5629 | 11007.5629 | 11007.5629 | 11007.5629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13480 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 30126.3663 | 0.2 | 0.3 | 46997.1315 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9271.0036 | 9271.0036 | 9271.0036 | 9271.0036 | 9271.0036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13481 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 451.8617 | 0.2 | 0.3 | 704.9042 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11335.9595 | 11335.9595 | 11335.9595 | 11335.9595 | 11335.9595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13482 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 30191.8818 | 0.2 | 0.3 | 47099.3356 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6999.9285 | 6999.9285 | 6999.9285 | 6999.9285 | 6999.9285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13483 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 20158.6961 | 0.2 | 0.3 | 31447.566 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2836 | 5203.2836 | 5203.2836 | 5203.2836 | 5203.2836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13484 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 18764.9483 | 0.2 | 0.3 | 29273.3193 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5489.1371 | 5489.1371 | 5489.1371 | 5489.1371 | 5489.1371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13485 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 3808.8779 | 0.2 | 0.3 | 5941.8496 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8011.9804 | 8011.9804 | 8011.9804 | 8011.9804 | 8011.9804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13486 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 25481.8341 | 0.2 | 0.3 | 39751.6612 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9191.0459 | 9191.0459 | 9191.0459 | 9191.0459 | 9191.0459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13487 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6498.248 | 6498.248 | 6498.248 | 6498.248 | 6498.248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13488 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16581.4509 | 0.2 | 0.3 | 25867.0634 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7088.8884 | 7088.8884 | 7088.8884 | 7088.8884 | 7088.8884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13489 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16619.5609 | 0.2 | 0.3 | 25926.5151 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3312.9353 | 3312.9353 | 3312.9353 | 3312.9353 | 3312.9353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13490 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2314 | 5200.2314 | 5200.2314 | 5200.2314 | 5200.2314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13491 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 22163.1163 | 0.2 | 0.3 | 34574.4615 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9461.3937 | 9461.3937 | 9461.3937 | 9461.3937 | 9461.3937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13492 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16418.1037 | 0.2 | 0.3 | 25612.2418 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13493 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16668.2383 | 0.2 | 0.3 | 26002.4517 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13494 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 17839.2259 | 0.2 | 0.3 | 27829.1924 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13495 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 34578.8757 | 0.2 | 0.3 | 53943.046 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9045 | 5200.9045 | 5200.9045 | 5200.9045 | 5200.9045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13496 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 30500.7471 | 0.2 | 0.3 | 47581.1655 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7126.342 | 7126.342 | 7126.342 | 7126.342 | 7126.342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13497 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 21635.7691 | 0.2 | 0.3 | 33751.7997 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 169.9318 | 169.9318 | 169.9318 | 169.9318 | 169.9318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13498 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 25938.2671 | 0.2 | 0.3 | 40463.6967 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5186.0431 | 5186.0431 | 5186.0431 | 5186.0431 | 5186.0431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13499 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16670.9745 | 0.2 | 0.3 | 26006.7202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2967 | 5201.2967 | 5201.2967 | 5201.2967 | 5201.2967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13500 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 20835.8661 | 0.2 | 0.3 | 32503.9512 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5310.7106 | 5310.7106 | 5310.7106 | 5310.7106 | 5310.7106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13501 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 15643.9599 | 0.2 | 0.3 | 24404.5775 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10283.8879 | 10283.8879 | 10283.8879 | 10283.8879 | 10283.8879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13502 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 20605.5232 | 0.2 | 0.3 | 32144.6162 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5209.0766 | 5209.0766 | 5209.0766 | 5209.0766 | 5209.0766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13503 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 16666.4901 | 0.2 | 0.3 | 25999.7246 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4151.5686 | 4151.5686 | 4151.5686 | 4151.5686 | 4151.5686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13504 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 44335.7055 | 0.2 | 0.3 | 69163.7006 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5271.2389 | 5271.2389 | 5271.2389 | 5271.2389 | 5271.2389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13505 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9816.5522 | 9816.5522 | 9816.5522 | 9816.5522 | 9816.5522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13506 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5676.7733 | 5676.7733 | 5676.7733 | 5676.7733 | 5676.7733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13507 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 17392.0641 | 0.2 | 0.3 | 27131.6199 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9781.2614 | 9781.2614 | 9781.2614 | 9781.2614 | 9781.2614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13508 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 20335.5981 | 0.2 | 0.3 | 31723.5331 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13509 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 377.0461 | 0.2 | 0.3 | 588.192 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5198.5181 | 5198.5181 | 5198.5181 | 5198.5181 | 5198.5181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13510 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 18179.8627 | 0.2 | 0.3 | 28360.5859 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7697.2592 | 7697.2592 | 7697.2592 | 7697.2592 | 7697.2592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13511 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 22282.7595 | 0.2 | 0.3 | 34761.1048 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.8101 | 9777.8101 | 9777.8101 | 9777.8101 | 9777.8101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13512 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 22091.8981 | 0.2 | 0.3 | 34463.3611 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7520.633 | 7520.633 | 7520.633 | 7520.633 | 7520.633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13513 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17058.6255 | 0.2 | 0.3 | 26611.4557 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7414.8278 | 7414.8278 | 7414.8278 | 7414.8278 | 7414.8278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13514 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17081.0465 | 0.2 | 0.3 | 26646.4325 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13515 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17175.8682 | 0.2 | 0.3 | 26794.3544 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9412.5042 | 9412.5042 | 9412.5042 | 9412.5042 | 9412.5042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13516 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 9593.7553 | 0.2 | 0.3 | 14966.2583 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8733.3257 | 8733.3257 | 8733.3257 | 8733.3257 | 8733.3257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13517 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 25298.3889 | 0.2 | 0.3 | 39465.4867 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4482.6523 | 4482.6523 | 4482.6523 | 4482.6523 | 4482.6523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13518 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16670.2017 | 0.2 | 0.3 | 26005.5146 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7641.544 | 7641.544 | 7641.544 | 7641.544 | 7641.544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13519 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16666.1655 | 0.2 | 0.3 | 25999.2181 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0398 | 5204.0398 | 5204.0398 | 5204.0398 | 5204.0398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13520 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 10863.1627 | 0.2 | 0.3 | 16946.5339 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6640.3171 | 6640.3171 | 6640.3171 | 6640.3171 | 6640.3171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13521 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22650.6534 | 0.2 | 0.3 | 35335.0193 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3840.5342 | 3840.5342 | 3840.5342 | 3840.5342 | 3840.5342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13522 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 14631.7513 | 0.2 | 0.3 | 22825.5321 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6022.3142 | 6022.3142 | 6022.3142 | 6022.3142 | 6022.3142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13523 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 1926.5266 | 0.2 | 0.3 | 3005.3815 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5 | 5202.5 | 5202.5 | 5202.5 | 5202.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13524 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 22929.0352 | 0.2 | 0.3 | 35769.2949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5618.2624 | 5618.2624 | 5618.2624 | 5618.2624 | 5618.2624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13525 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 9057.1419 | 0.2 | 0.3 | 14129.1414 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13526 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17068.5596 | 0.2 | 0.3 | 26626.953 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5481.032 | 5481.032 | 5481.032 | 5481.032 | 5481.032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13527 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 5151.0484 | 0.2 | 0.3 | 8035.6355 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7266.8404 | 7266.8404 | 7266.8404 | 7266.8404 | 7266.8404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13528 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 10670.4622 | 0.2 | 0.3 | 16645.921 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.821 | 9779.821 | 9779.821 | 9779.821 | 9779.821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13529 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 21497.7583 | 0.2 | 0.3 | 33536.5029 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0553 | 5202.0553 | 5202.0553 | 5202.0553 | 5202.0553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13530 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 1881.4697 | 0.2 | 0.3 | 2935.0928 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4462 | 5201.4462 | 5201.4462 | 5201.4462 | 5201.4462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13531 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 23727.5715 | 0.2 | 0.3 | 37015.0115 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6546 | 5201.6546 | 5201.6546 | 5201.6546 | 5201.6546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13532 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17574.2996 | 0.2 | 0.3 | 27415.9074 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8470.5373 | 8470.5373 | 8470.5373 | 8470.5373 | 8470.5373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13533 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 24987.8531 | 0.2 | 0.3 | 38981.0509 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4549.7253 | 4549.7253 | 4549.7253 | 4549.7253 | 4549.7253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13534 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 11791.1493 | 0.2 | 0.3 | 18394.193 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0884 | 5200.0884 | 5200.0884 | 5200.0884 | 5200.0884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13535 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 2861.4555 | 0.2 | 0.3 | 4463.8706 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3067.1703 | 3067.1703 | 3067.1703 | 3067.1703 | 3067.1703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13536 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 5847.9237 | 0.2 | 0.3 | 9122.761 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6307.7797 | 6307.7797 | 6307.7797 | 6307.7797 | 6307.7797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13537 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17268.0909 | 0.2 | 0.3 | 26938.2218 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6919 | 5200.6919 | 5200.6919 | 5200.6919 | 5200.6919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13538 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 23105.4393 | 0.2 | 0.3 | 36044.4854 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8834 | 5200.8834 | 5200.8834 | 5200.8834 | 5200.8834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13539 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 5842.9353 | 0.2 | 0.3 | 9114.979 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6760.9466 | 6760.9466 | 6760.9466 | 6760.9466 | 6760.9466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13540 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 22637.4095 | 0.2 | 0.3 | 35314.3589 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3937.1759 | 3937.1759 | 3937.1759 | 3937.1759 | 3937.1759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13541 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 24825.9219 | 0.2 | 0.3 | 38728.4381 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1263.1446 | 1263.1446 | 1263.1446 | 1263.1446 | 1263.1446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13542 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 22853.7723 | 0.2 | 0.3 | 35651.8847 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13543 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 17768.9505 | 0.2 | 0.3 | 27719.5627 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9571.568 | 9571.568 | 9571.568 | 9571.568 | 9571.568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13544 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16988.131 | 0.2 | 0.3 | 26501.4844 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13545 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 34283.7457 | 0.2 | 0.3 | 53482.6432 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13546 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16971.7479 | 0.2 | 0.3 | 26475.9267 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7025 | 5201.7025 | 5201.7025 | 5201.7025 | 5201.7025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13547 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16666.2495 | 0.2 | 0.3 | 25999.3493 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9786.4773 | 9786.4773 | 9786.4773 | 9786.4773 | 9786.4773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13548 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 14545.9081 | 0.2 | 0.3 | 22691.6166 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4648.6799 | 4648.6799 | 4648.6799 | 4648.6799 | 4648.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13549 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 8333.6917 | 0.2 | 0.3 | 13000.559 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3958.9301 | 3958.9301 | 3958.9301 | 3958.9301 | 3958.9301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13550 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 8333.8853 | 0.2 | 0.3 | 13000.8611 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3153.0572 | 3153.0572 | 3153.0572 | 3153.0572 | 3153.0572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13551 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 16027.7504 | 0.2 | 0.3 | 25003.2906 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2161.1901 | 2161.1901 | 2161.1901 | 2161.1901 | 2161.1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13552 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 18285.5082 | 0.2 | 0.3 | 28525.3928 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9897.5859 | 9897.5859 | 9897.5859 | 9897.5859 | 9897.5859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13553 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 30511.9387 | 0.2 | 0.3 | 47598.6243 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3901.9653 | 3901.9653 | 3901.9653 | 3901.9653 | 3901.9653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13554 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 16666.3981 | 0.2 | 0.3 | 25999.5811 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5473.9252 | 5473.9252 | 5473.9252 | 5473.9252 | 5473.9252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13555 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 16667.2108 | 0.2 | 0.3 | 26000.8488 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6059 | 5200.6059 | 5200.6059 | 5200.6059 | 5200.6059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13556 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 21747.0301 | 0.2 | 0.3 | 33925.367 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6668.7009 | 6668.7009 | 6668.7009 | 6668.7009 | 6668.7009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13557 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 20259.6289 | 0.2 | 0.3 | 31605.021 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4443.5949 | 4443.5949 | 4443.5949 | 4443.5949 | 4443.5949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13558 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 1904.5282 | 0.2 | 0.3 | 2971.064 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9513.7481 | 9513.7481 | 9513.7481 | 9513.7481 | 9513.7481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13559 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 23185.6263 | 0.2 | 0.3 | 36169.577 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13560 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16879.2183 | 0.2 | 0.3 | 26331.5805 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0943 | 5202.0943 | 5202.0943 | 5202.0943 | 5202.0943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13561 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 14069.8501 | 0.2 | 0.3 | 21948.9662 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0491 | 5202.0491 | 5202.0491 | 5202.0491 | 5202.0491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13562 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 4856.0093 | 0.2 | 0.3 | 7575.3745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5322.7512 | 5322.7512 | 5322.7512 | 5322.7512 | 5322.7512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13563 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 12667.1861 | 0.2 | 0.3 | 19760.8104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5633.2036 | 5633.2036 | 5633.2036 | 5633.2036 | 5633.2036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13564 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 28644.467 | 0.2 | 0.3 | 44685.3685 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3425.9339 | 3425.9339 | 3425.9339 | 3425.9339 | 3425.9339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13565 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 15950.6619 | 0.2 | 0.3 | 24883.0326 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4791.5383 | 4791.5383 | 4791.5383 | 4791.5383 | 4791.5383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13566 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16797.9085 | 0.2 | 0.3 | 26204.7372 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4839.4937 | 4839.4937 | 4839.4937 | 4839.4937 | 4839.4937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13567 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16675.5411 | 0.2 | 0.3 | 26013.8441 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8874.6768 | 8874.6768 | 8874.6768 | 8874.6768 | 8874.6768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13568 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16753.7697 | 0.2 | 0.3 | 26135.8807 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5416.3055 | 5416.3055 | 5416.3055 | 5416.3055 | 5416.3055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13569 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 20243.7449 | 0.2 | 0.3 | 31580.242 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8805.5867 | 8805.5867 | 8805.5867 | 8805.5867 | 8805.5867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13570 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 24847.8507 | 0.2 | 0.3 | 38762.647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9942 | 5201.9942 | 5201.9942 | 5201.9942 | 5201.9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13571 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13572 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7444 | 0.2 | 0.3 | 26000.1213 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2009 | 5202.2009 | 5202.2009 | 5202.2009 | 5202.2009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13573 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 19348.1689 | 0.2 | 0.3 | 30183.1435 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6766.6206 | 6766.6206 | 6766.6206 | 6766.6206 | 6766.6206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13574 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 8554.3289 | 0.2 | 0.3 | 13344.753 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4375.5265 | 4375.5265 | 4375.5265 | 4375.5265 | 4375.5265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13575 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 17752.9243 | 0.2 | 0.3 | 27694.5619 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2658.0176 | 2658.0176 | 2658.0176 | 2658.0176 | 2658.0176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13576 | PARKLAND | 10503 | Private | 2036 | 5 | Swales | 66.6667 | 26749.6713 | 0.2 | 0.3 | 41729.4873 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6173.1069 | 6173.1069 | 6173.1069 | 6173.1069 | 6173.1069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13577 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 15214.787 | 0.2 | 0.3 | 23735.0677 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1736.5777 | 1736.5777 | 1736.5777 | 1736.5777 | 1736.5777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13578 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 19202.8283 | 0.2 | 0.3 | 29956.4122 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5224 | 5201.5224 | 5201.5224 | 5201.5224 | 5201.5224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13579 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16858.0285 | 0.2 | 0.3 | 26298.5244 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5188.9671 | 5188.9671 | 5188.9671 | 5188.9671 | 5188.9671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13580 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 30413.2484 | 0.2 | 0.3 | 47444.6675 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9680.6708 | 9680.6708 | 9680.6708 | 9680.6708 | 9680.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13581 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 25844.0522 | 0.2 | 0.3 | 40316.7214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.1876 | 5205.1876 | 5205.1876 | 5205.1876 | 5205.1876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13582 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 1439.4424 | 0.2 | 0.3 | 2245.5301 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5179.1431 | 5179.1431 | 5179.1431 | 5179.1431 | 5179.1431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13583 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 28004.1682 | 0.2 | 0.3 | 43686.5024 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3671.7204 | 3671.7204 | 3671.7204 | 3671.7204 | 3671.7204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13584 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 11506.3831 | 0.2 | 0.3 | 17949.9576 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5124.9231 | 5124.9231 | 5124.9231 | 5124.9231 | 5124.9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13585 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 22965.5329 | 0.2 | 0.3 | 35826.2313 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2599.9051 | 2599.9051 | 2599.9051 | 2599.9051 | 2599.9051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13586 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 24403.4313 | 0.2 | 0.3 | 38069.3528 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5761.7366 | 5761.7366 | 5761.7366 | 5761.7366 | 5761.7366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13587 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 15520.8725 | 0.2 | 0.3 | 24212.561 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7273.778 | 7273.778 | 7273.778 | 7273.778 | 7273.778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13588 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 12885.6717 | 0.2 | 0.3 | 20101.6478 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6448.0705 | 6448.0705 | 6448.0705 | 6448.0705 | 6448.0705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13589 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 11272.2235 | 0.2 | 0.3 | 17584.6686 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6718.6297 | 6718.6297 | 6718.6297 | 6718.6297 | 6718.6297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13590 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 22529.1664 | 0.2 | 0.3 | 35145.4996 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6848.5695 | 6848.5695 | 6848.5695 | 6848.5695 | 6848.5695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13591 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16669.9194 | 0.2 | 0.3 | 26005.0743 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7986.7236 | 7986.7236 | 7986.7236 | 7986.7236 | 7986.7236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13592 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 5823.5697 | 0.2 | 0.3 | 9084.7688 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3514 | 5201.3514 | 5201.3514 | 5201.3514 | 5201.3514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13593 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 11905.0187 | 0.2 | 0.3 | 18571.8291 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13594 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16695.4775 | 0.2 | 0.3 | 26044.945 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.418 | 5201.418 | 5201.418 | 5201.418 | 5201.418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13595 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16696.6695 | 0.2 | 0.3 | 26046.8044 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9489.0038 | 9489.0038 | 9489.0038 | 9489.0038 | 9489.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13596 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 12084.9368 | 0.2 | 0.3 | 18852.5014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8698.4734 | 8698.4734 | 8698.4734 | 8698.4734 | 8698.4734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13597 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 14081.8923 | 0.2 | 0.3 | 21967.752 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13598 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16666.9423 | 0.2 | 0.3 | 26000.4299 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8797.482 | 8797.482 | 8797.482 | 8797.482 | 8797.482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13599 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1878 | 0.2 | 0.3 | 26000.813 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9780.6412 | 9780.6412 | 9780.6412 | 9780.6412 | 9780.6412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13600 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 13407.1704 | 0.2 | 0.3 | 20915.1858 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6135 | 5201.6135 | 5201.6135 | 5201.6135 | 5201.6135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13601 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 21219.6295 | 0.2 | 0.3 | 33102.622 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13602 | COCONUT CREEK | 10610 | Public | 2030 | 5 | Swales | 66.6667 | 20735.9661 | 0.2 | 0.3 | 32348.1072 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10267.0153 | 10267.0153 | 10267.0153 | 10267.0153 | 10267.0153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13603 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 19473.5833 | 0.2 | 0.3 | 30378.79 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5338.4617 | 5338.4617 | 5338.4617 | 5338.4617 | 5338.4617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13604 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 17560.5276 | 0.2 | 0.3 | 27394.4231 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7202 | 5201.7202 | 5201.7202 | 5201.7202 | 5201.7202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13605 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 30880.9109 | 0.2 | 0.3 | 48174.221 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5061 | 5201.5061 | 5201.5061 | 5201.5061 | 5201.5061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13606 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 21239.9263 | 0.2 | 0.3 | 33134.285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7601.1078 | 7601.1078 | 7601.1078 | 7601.1078 | 7601.1078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13607 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 15761.7024 | 0.2 | 0.3 | 24588.2557 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6549 | 5201.6549 | 5201.6549 | 5201.6549 | 5201.6549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13608 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 28823.2036 | 0.2 | 0.3 | 44964.1976 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13609 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 26995.5411 | 0.2 | 0.3 | 42113.0441 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5636 | 5201.5636 | 5201.5636 | 5201.5636 | 5201.5636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13610 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 17145.4877 | 0.2 | 0.3 | 26746.9609 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9231.2377 | 9231.2377 | 9231.2377 | 9231.2377 | 9231.2377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13611 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 21024.4431 | 0.2 | 0.3 | 32798.1313 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4809.6194 | 4809.6194 | 4809.6194 | 4809.6194 | 4809.6194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13612 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 486.8454 | 0.2 | 0.3 | 759.4788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13613 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16740.8132 | 0.2 | 0.3 | 26115.6686 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5172.7703 | 5172.7703 | 5172.7703 | 5172.7703 | 5172.7703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13614 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 7388.5529 | 0.2 | 0.3 | 11526.1425 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6562.8824 | 6562.8824 | 6562.8824 | 6562.8824 | 6562.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13615 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 12095.8709 | 0.2 | 0.3 | 18869.5586 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9224 | 5200.9224 | 5200.9224 | 5200.9224 | 5200.9224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13616 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 36499.5218 | 0.2 | 0.3 | 56939.254 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13617 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 9664.4411 | 0.2 | 0.3 | 15076.5281 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8222.6967 | 8222.6967 | 8222.6967 | 8222.6967 | 8222.6967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13618 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 15201.1403 | 0.2 | 0.3 | 23713.7788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7382.6925 | 7382.6925 | 7382.6925 | 7382.6925 | 7382.6925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13619 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 14811.9227 | 0.2 | 0.3 | 23106.5995 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13620 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 23682.9845 | 0.2 | 0.3 | 36945.4558 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13621 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 2999.2668 | 0.2 | 0.3 | 4678.8562 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7449.9668 | 7449.9668 | 7449.9668 | 7449.9668 | 7449.9668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13622 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 27003.0657 | 0.2 | 0.3 | 42124.7825 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9855.6449 | 9855.6449 | 9855.6449 | 9855.6449 | 9855.6449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13623 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 6305.5707 | 0.2 | 0.3 | 9836.6902 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9775.8303 | 9775.8303 | 9775.8303 | 9775.8303 | 9775.8303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13624 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 18406.5583 | 0.2 | 0.3 | 28714.2309 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7447.0253 | 7447.0253 | 7447.0253 | 7447.0253 | 7447.0253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13625 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 7256.1621 | 0.2 | 0.3 | 11319.6128 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9488.9997 | 9488.9997 | 9488.9997 | 9488.9997 | 9488.9997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13626 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 9955.2311 | 0.2 | 0.3 | 15530.1605 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1992.9812 | 1992.9812 | 1992.9812 | 1992.9812 | 1992.9812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13627 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 10593.7393 | 0.2 | 0.3 | 16526.2333 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7352.4374 | 7352.4374 | 7352.4374 | 7352.4374 | 7352.4374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13628 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 13841.8096 | 0.2 | 0.3 | 21593.223 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6957 | 5201.6957 | 5201.6957 | 5201.6957 | 5201.6957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13629 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16696.9665 | 0.2 | 0.3 | 26047.2677 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13630 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 19211.4483 | 0.2 | 0.3 | 29969.8594 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13631 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 1989.937 | 0.2 | 0.3 | 3104.3017 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9498.439 | 9498.439 | 9498.439 | 9498.439 | 9498.439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13632 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16669.2388 | 0.2 | 0.3 | 26004.0125 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.3536 | 5199.3536 | 5199.3536 | 5199.3536 | 5199.3536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13633 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16028.4444 | 0.2 | 0.3 | 25004.3733 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1808.52 | 1808.52 | 1808.52 | 1808.52 | 1808.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13634 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16677.3093 | 0.2 | 0.3 | 26016.6025 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11288.1836 | 11288.1836 | 11288.1836 | 11288.1836 | 11288.1836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13635 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 21108.3201 | 0.2 | 0.3 | 32928.9793 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9794.7366 | 9794.7366 | 9794.7366 | 9794.7366 | 9794.7366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13636 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 156.9069 | 0.2 | 0.3 | 244.7747 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 619.433 | 619.433 | 619.433 | 619.433 | 619.433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13637 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 25538.3546 | 0.2 | 0.3 | 39839.8332 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2620.4604 | 2620.4604 | 2620.4604 | 2620.4604 | 2620.4604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13638 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 18376.0727 | 0.2 | 0.3 | 28666.6734 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 350.4255 | 350.4255 | 350.4255 | 350.4255 | 350.4255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13639 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 17045.7193 | 0.2 | 0.3 | 26591.3221 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1594.7405 | 1594.7405 | 1594.7405 | 1594.7405 | 1594.7405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13640 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 20634.6077 | 0.2 | 0.3 | 32189.9881 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3038.8973 | 3038.8973 | 3038.8973 | 3038.8973 | 3038.8973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13641 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 14166.8719 | 0.2 | 0.3 | 22100.3202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 852.2402 | 852.2402 | 852.2402 | 852.2402 | 852.2402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13642 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16411.5974 | 0.2 | 0.3 | 25602.0919 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13643 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 1317.3148 | 0.2 | 0.3 | 2055.0111 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10403.0988 | 10403.0988 | 10403.0988 | 10403.0988 | 10403.0988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13644 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 3734.6019 | 0.2 | 0.3 | 5825.979 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13645 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 20081.8671 | 0.2 | 0.3 | 31327.7127 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13646 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 14520.7203 | 0.2 | 0.3 | 22652.3236 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8787.3214 | 8787.3214 | 8787.3214 | 8787.3214 | 8787.3214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13647 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16672.0531 | 0.2 | 0.3 | 26008.4028 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6934.301 | 6934.301 | 6934.301 | 6934.301 | 6934.301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13648 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 7875.4429 | 0.2 | 0.3 | 12285.691 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4443.7768 | 4443.7768 | 4443.7768 | 4443.7768 | 4443.7768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13649 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 33682.9385 | 0.2 | 0.3 | 52545.3841 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5264.1733 | 5264.1733 | 5264.1733 | 5264.1733 | 5264.1733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13650 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 29459.5745 | 0.2 | 0.3 | 45956.9362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1716 | 5201.1716 | 5201.1716 | 5201.1716 | 5201.1716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13651 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17849.1612 | 0.2 | 0.3 | 27844.6915 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2797 | 5201.2797 | 5201.2797 | 5201.2797 | 5201.2797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13652 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 14525.1487 | 0.2 | 0.3 | 22659.232 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7171.2006 | 7171.2006 | 7171.2006 | 7171.2006 | 7171.2006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13653 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 20851.5337 | 0.2 | 0.3 | 32528.3925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2584.774 | 2584.774 | 2584.774 | 2584.774 | 2584.774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13654 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 886.0039 | 0.2 | 0.3 | 1382.1661 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5329.4292 | 5329.4292 | 5329.4292 | 5329.4292 | 5329.4292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13655 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 28678.906 | 0.2 | 0.3 | 44739.0934 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2258 | 5202.2258 | 5202.2258 | 5202.2258 | 5202.2258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13656 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 7941.8443 | 0.2 | 0.3 | 12389.2771 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3608.2662 | 3608.2662 | 3608.2662 | 3608.2662 | 3608.2662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13657 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 19034.7557 | 0.2 | 0.3 | 29694.2189 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2166.4235 | 2166.4235 | 2166.4235 | 2166.4235 | 2166.4235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13658 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 15167.2343 | 0.2 | 0.3 | 23660.8855 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5581.0832 | 5581.0832 | 5581.0832 | 5581.0832 | 5581.0832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13659 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 19487.2885 | 0.2 | 0.3 | 30400.1701 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13660 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16207.9651 | 0.2 | 0.3 | 25284.4256 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10395.6061 | 10395.6061 | 10395.6061 | 10395.6061 | 10395.6061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13661 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 3826.6663 | 0.2 | 0.3 | 5969.5995 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6561.533 | 6561.533 | 6561.533 | 6561.533 | 6561.533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13662 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 22928.1053 | 0.2 | 0.3 | 35767.8443 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5071.1856 | 5071.1856 | 5071.1856 | 5071.1856 | 5071.1856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13663 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 14550.7881 | 0.2 | 0.3 | 22699.2294 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10377.1585 | 10377.1585 | 10377.1585 | 10377.1585 | 10377.1585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13664 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 22516.8731 | 0.2 | 0.3 | 35126.3221 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10441.6179 | 10441.6179 | 10441.6179 | 10441.6179 | 10441.6179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13665 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 18034.4468 | 0.2 | 0.3 | 28133.737 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7221.804 | 7221.804 | 7221.804 | 7221.804 | 7221.804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13666 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 63.3743 | 0.2 | 0.3 | 98.864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.4056 | 5203.4056 | 5203.4056 | 5203.4056 | 5203.4056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13667 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16695.1378 | 0.2 | 0.3 | 26044.415 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5211.7508 | 5211.7508 | 5211.7508 | 5211.7508 | 5211.7508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13668 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 1730.014 | 0.2 | 0.3 | 2698.8218 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5211.7508 | 5211.7508 | 5211.7508 | 5211.7508 | 5211.7508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13669 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 15414.172 | 0.2 | 0.3 | 24046.1083 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9611.4019 | 9611.4019 | 9611.4019 | 9611.4019 | 9611.4019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13670 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 15753.575 | 0.2 | 0.3 | 24575.577 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2419.1896 | 2419.1896 | 2419.1896 | 2419.1896 | 2419.1896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13671 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 23815.3049 | 0.2 | 0.3 | 37151.8757 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7498.6688 | 7498.6688 | 7498.6688 | 7498.6688 | 7498.6688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13672 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 25474.4677 | 0.2 | 0.3 | 39740.1696 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5050.3189 | 5050.3189 | 5050.3189 | 5050.3189 | 5050.3189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13673 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 25223.0603 | 0.2 | 0.3 | 39347.974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9817.8328 | 9817.8328 | 9817.8328 | 9817.8328 | 9817.8328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13674 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 29926.4306 | 0.2 | 0.3 | 46685.2317 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9104.2777 | 9104.2777 | 9104.2777 | 9104.2777 | 9104.2777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13675 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 1968.9939 | 0.2 | 0.3 | 3071.6304 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5782.9299 | 5782.9299 | 5782.9299 | 5782.9299 | 5782.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13676 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 1053.8387 | 0.2 | 0.3 | 1643.9884 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3738.691 | 3738.691 | 3738.691 | 3738.691 | 3738.691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13677 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 26200.0945 | 0.2 | 0.3 | 40872.1474 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1732.5957 | 1732.5957 | 1732.5957 | 1732.5957 | 1732.5957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13678 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 11906.0293 | 0.2 | 0.3 | 18573.4057 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5881.889 | 5881.889 | 5881.889 | 5881.889 | 5881.889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13679 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 4764.6575 | 0.2 | 0.3 | 7432.8658 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12468.2734 | 12468.2734 | 12468.2734 | 12468.2734 | 12468.2734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13680 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 20478.0156 | 0.2 | 0.3 | 31945.7043 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 18005.7892 | 18005.7892 | 18005.7892 | 18005.7892 | 18005.7892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13681 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 42392.759 | 0.2 | 0.3 | 66132.704 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13150.2394 | 13150.2394 | 13150.2394 | 13150.2394 | 13150.2394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13682 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 38875.1887 | 0.2 | 0.3 | 60645.2943 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13807.1976 | 13807.1976 | 13807.1976 | 13807.1976 | 13807.1976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13683 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 48906.558 | 0.2 | 0.3 | 76294.2305 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5142.2638 | 5142.2638 | 5142.2638 | 5142.2638 | 5142.2638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13684 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16866.9621 | 0.2 | 0.3 | 26312.4609 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8939.2342 | 8939.2342 | 8939.2342 | 8939.2342 | 8939.2342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13685 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 23800.878 | 0.2 | 0.3 | 37129.3697 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9803.1018 | 9803.1018 | 9803.1018 | 9803.1018 | 9803.1018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13686 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 2934.0042 | 0.2 | 0.3 | 4577.0466 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5390.1689 | 5390.1689 | 5390.1689 | 5390.1689 | 5390.1689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13687 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16980.794 | 0.2 | 0.3 | 26490.0386 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7402.2757 | 7402.2757 | 7402.2757 | 7402.2757 | 7402.2757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13688 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 291.9885 | 0.2 | 0.3 | 455.502 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5943.8021 | 5943.8021 | 5943.8021 | 5943.8021 | 5943.8021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13689 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16679.5208 | 0.2 | 0.3 | 26020.0524 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6066.6971 | 6066.6971 | 6066.6971 | 6066.6971 | 6066.6971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13690 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 19419.1153 | 0.2 | 0.3 | 30293.8198 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6391.9514 | 6391.9514 | 6391.9514 | 6391.9514 | 6391.9514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13691 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 20125.8703 | 0.2 | 0.3 | 31396.3576 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13692 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17568.5294 | 0.2 | 0.3 | 27406.9059 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9554.1694 | 9554.1694 | 9554.1694 | 9554.1694 | 9554.1694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13693 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16908.4101 | 0.2 | 0.3 | 26377.1198 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6050.5453 | 6050.5453 | 6050.5453 | 6050.5453 | 6050.5453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13694 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17937.6754 | 0.2 | 0.3 | 27982.7736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13695 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 1592.9658 | 0.2 | 0.3 | 2485.0266 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6727 | 5200.6727 | 5200.6727 | 5200.6727 | 5200.6727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13696 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 27102.4477 | 0.2 | 0.3 | 42279.8184 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13697 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 25079.1231 | 0.2 | 0.3 | 39123.4321 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5726.2487 | 5726.2487 | 5726.2487 | 5726.2487 | 5726.2487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13698 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17792.565 | 0.2 | 0.3 | 27756.4014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1204.6535 | 1204.6535 | 1204.6535 | 1204.6535 | 1204.6535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13699 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 126.4613 | 0.2 | 0.3 | 197.2796 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9952 | 5200.9952 | 5200.9952 | 5200.9952 | 5200.9952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13700 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 7612.9559 | 0.2 | 0.3 | 11876.2112 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10403.0364 | 10403.0364 | 10403.0364 | 10403.0364 | 10403.0364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13701 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17698.8938 | 0.2 | 0.3 | 27610.2743 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7800.4408 | 7800.4408 | 7800.4408 | 7800.4408 | 7800.4408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13702 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 24380.9459 | 0.2 | 0.3 | 38034.2757 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14140.3509 | 14140.3509 | 14140.3509 | 14140.3509 | 14140.3509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13703 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 38992.7828 | 0.2 | 0.3 | 60828.7412 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8277 | 5201.8277 | 5201.8277 | 5201.8277 | 5201.8277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13704 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 36417.2495 | 0.2 | 0.3 | 56810.9093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5763.4734 | 5763.4734 | 5763.4734 | 5763.4734 | 5763.4734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13705 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 38234.6018 | 0.2 | 0.3 | 59645.9788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10632.8736 | 10632.8736 | 10632.8736 | 10632.8736 | 10632.8736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13706 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 19541.6429 | 0.2 | 0.3 | 30484.963 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10524.3852 | 10524.3852 | 10524.3852 | 10524.3852 | 10524.3852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13707 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 41405.1085 | 0.2 | 0.3 | 64591.9693 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9781.2279 | 9781.2279 | 9781.2279 | 9781.2279 | 9781.2279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13708 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 16833.5047 | 0.2 | 0.3 | 26260.2674 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1315 | 5201.1315 | 5201.1315 | 5201.1315 | 5201.1315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13709 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 17456.9928 | 0.2 | 0.3 | 27232.9088 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1221 | 5202.1221 | 5202.1221 | 5202.1221 | 5202.1221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13710 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 18019.5091 | 0.2 | 0.3 | 28110.4341 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9776 | 5199.9776 | 5199.9776 | 5199.9776 | 5199.9776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13711 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 80.6828 | 0.2 | 0.3 | 125.8652 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6500.9162 | 6500.9162 | 6500.9162 | 6500.9162 | 6500.9162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13712 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16659.6516 | 0.2 | 0.3 | 25989.0565 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5317.886 | 5317.886 | 5317.886 | 5317.886 | 5317.886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13713 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 1635.4051 | 0.2 | 0.3 | 2551.2319 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6318 | 5201.6318 | 5201.6318 | 5201.6318 | 5201.6318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13714 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 37350.0225 | 0.2 | 0.3 | 58266.0352 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5211 | 5200.5211 | 5200.5211 | 5200.5211 | 5200.5211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13715 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 30500.3959 | 0.2 | 0.3 | 47580.6177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5194.7863 | 5194.7863 | 5194.7863 | 5194.7863 | 5194.7863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13716 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 30658.0619 | 0.2 | 0.3 | 47826.5765 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13717 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 8804.3841 | 0.2 | 0.3 | 13734.8392 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7825.346 | 7825.346 | 7825.346 | 7825.346 | 7825.346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13718 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 19206.5692 | 0.2 | 0.3 | 29962.248 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7779.2041 | 7779.2041 | 7779.2041 | 7779.2041 | 7779.2041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13719 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 29907.8445 | 0.2 | 0.3 | 46656.2375 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13720 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 30912.8854 | 0.2 | 0.3 | 48224.1012 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.042 | 5201.042 | 5201.042 | 5201.042 | 5201.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13721 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 22191.6193 | 0.2 | 0.3 | 34618.9261 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13722 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 26563.4608 | 0.2 | 0.3 | 41438.9988 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 158.7248 | 158.7248 | 158.7248 | 158.7248 | 158.7248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13723 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 18470.9659 | 0.2 | 0.3 | 28814.7069 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1204.6484 | 1204.6484 | 1204.6484 | 1204.6484 | 1204.6484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13724 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17911.0728 | 0.2 | 0.3 | 27941.2736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4654.5545 | 4654.5545 | 4654.5545 | 4654.5545 | 4654.5545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13725 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 31340.8563 | 0.2 | 0.3 | 48891.7359 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7808.8872 | 7808.8872 | 7808.8872 | 7808.8872 | 7808.8872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13726 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 19677.1676 | 0.2 | 0.3 | 30696.3815 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5842.0371 | 5842.0371 | 5842.0371 | 5842.0371 | 5842.0371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13727 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 14542.8001 | 0.2 | 0.3 | 22686.7681 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7045.9033 | 7045.9033 | 7045.9033 | 7045.9033 | 7045.9033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13728 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 6289.5647 | 0.2 | 0.3 | 9811.721 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9761.893 | 9761.893 | 9761.893 | 9761.893 | 9761.893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13729 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17723.7711 | 0.2 | 0.3 | 27649.0829 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9216.5205 | 9216.5205 | 9216.5205 | 9216.5205 | 9216.5205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13730 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 12783.0142 | 0.2 | 0.3 | 19941.5022 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7472.4433 | 7472.4433 | 7472.4433 | 7472.4433 | 7472.4433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13731 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 4705.3233 | 0.2 | 0.3 | 7340.3044 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5262.5259 | 5262.5259 | 5262.5259 | 5262.5259 | 5262.5259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13732 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 18624.0656 | 0.2 | 0.3 | 29053.5423 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7620.3416 | 7620.3416 | 7620.3416 | 7620.3416 | 7620.3416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13733 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 25866.7545 | 0.2 | 0.3 | 40352.1371 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7349.8735 | 7349.8735 | 7349.8735 | 7349.8735 | 7349.8735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13734 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17894.9238 | 0.2 | 0.3 | 27916.0811 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7529.0883 | 7529.0883 | 7529.0883 | 7529.0883 | 7529.0883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13735 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 18195.8011 | 0.2 | 0.3 | 28385.4497 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7428.5938 | 7428.5938 | 7428.5938 | 7428.5938 | 7428.5938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13736 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 9413.4056 | 0.2 | 0.3 | 14684.9127 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13737 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 12376.5862 | 0.2 | 0.3 | 19307.4745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13738 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 2280.5279 | 0.2 | 0.3 | 3557.6235 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13739 | COCONUT CREEK | 10610 | Private | 2030 | 5 | Swales | 66.6667 | 1247.1994 | 0.2 | 0.3 | 1945.6311 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5751.2491 | 5751.2491 | 5751.2491 | 5751.2491 | 5751.2491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13740 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 1128.0705 | 0.2 | 0.3 | 1759.79 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4618.9376 | 4618.9376 | 4618.9376 | 4618.9376 | 4618.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13741 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 17380.6069 | 0.2 | 0.3 | 27113.7467 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9078.9837 | 9078.9837 | 9078.9837 | 9078.9837 | 9078.9837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13742 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 23344.2853 | 0.2 | 0.3 | 36417.085 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7710.8246 | 7710.8246 | 7710.8246 | 7710.8246 | 7710.8246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13743 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 5253.2103 | 0.2 | 0.3 | 8195.008 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13744 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 19315.3508 | 0.2 | 0.3 | 30131.9472 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13745 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17038.037 | 0.2 | 0.3 | 26579.3377 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13746 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17375.6241 | 0.2 | 0.3 | 27105.9736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7787.0483 | 7787.0483 | 7787.0483 | 7787.0483 | 7787.0483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13747 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17519.5051 | 0.2 | 0.3 | 27330.428 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7817.495 | 7817.495 | 7817.495 | 7817.495 | 7817.495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13748 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 22470.0912 | 0.2 | 0.3 | 35053.3423 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3996 | 5201.3996 | 5201.3996 | 5201.3996 | 5201.3996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13749 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 24234.3174 | 0.2 | 0.3 | 37805.5351 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5118 | 5201.5118 | 5201.5118 | 5201.5118 | 5201.5118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13750 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 18846.4004 | 0.2 | 0.3 | 29400.3846 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.651 | 5201.651 | 5201.651 | 5201.651 | 5201.651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13751 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17138.6725 | 0.2 | 0.3 | 26736.3292 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5396 | 5201.5396 | 5201.5396 | 5201.5396 | 5201.5396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13752 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 18618.2945 | 0.2 | 0.3 | 29044.5394 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3784 | 5201.3784 | 5201.3784 | 5201.3784 | 5201.3784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13753 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16666.9857 | 0.2 | 0.3 | 26000.4976 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5000.896 | 5000.896 | 5000.896 | 5000.896 | 5000.896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13754 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16680.1384 | 0.2 | 0.3 | 26021.0159 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 201.3283 | 201.3283 | 201.3283 | 201.3283 | 201.3283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13755 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16715.539 | 0.2 | 0.3 | 26076.2408 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1.5886 | 1.5886 | 1.5886 | 1.5886 | 1.5886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13756 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 27022.0334 | 0.2 | 0.3 | 42154.3721 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9716.2585 | 9716.2585 | 9716.2585 | 9716.2585 | 9716.2585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13757 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 1125.8001 | 0.2 | 0.3 | 1756.2481 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6427.126 | 6427.126 | 6427.126 | 6427.126 | 6427.126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13758 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 9100.9192 | 0.2 | 0.3 | 14197.434 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.2602 | 5199.2602 | 5199.2602 | 5199.2602 | 5199.2602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13759 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 10327.4272 | 0.2 | 0.3 | 16110.7864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7233.3054 | 7233.3054 | 7233.3054 | 7233.3054 | 7233.3054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13760 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17547.4406 | 0.2 | 0.3 | 27374.0073 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4246.3782 | 4246.3782 | 4246.3782 | 4246.3782 | 4246.3782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13761 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16012.3723 | 0.2 | 0.3 | 24979.3007 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8196.923 | 8196.923 | 8196.923 | 8196.923 | 8196.923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13762 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 5710.2283 | 0.2 | 0.3 | 8907.9562 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13763 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16167.3529 | 0.2 | 0.3 | 25221.0705 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13764 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 2160.0053 | 0.2 | 0.3 | 3369.6083 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13765 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 2098.7901 | 0.2 | 0.3 | 3274.1126 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9048.2562 | 9048.2562 | 9048.2562 | 9048.2562 | 9048.2562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13766 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 13212.7951 | 0.2 | 0.3 | 20611.9603 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4297.5969 | 4297.5969 | 4297.5969 | 4297.5969 | 4297.5969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13767 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 21350.9973 | 0.2 | 0.3 | 33307.5558 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6004.1316 | 6004.1316 | 6004.1316 | 6004.1316 | 6004.1316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13768 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 35869.3015 | 0.2 | 0.3 | 55956.1103 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7817.9896 | 7817.9896 | 7817.9896 | 7817.9896 | 7817.9896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13769 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 8196.2117 | 0.2 | 0.3 | 12786.0902 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9084 | 5203.9084 | 5203.9084 | 5203.9084 | 5203.9084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13770 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 2423.7145 | 0.2 | 0.3 | 3780.9946 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3603 | 5201.3603 | 5201.3603 | 5201.3603 | 5201.3603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13771 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 24000.7739 | 0.2 | 0.3 | 37441.2073 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5589 | 5201.5589 | 5201.5589 | 5201.5589 | 5201.5589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13772 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 16989.216 | 0.2 | 0.3 | 26503.177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6627.9395 | 6627.9395 | 6627.9395 | 6627.9395 | 6627.9395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13773 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 310.9316 | 0.2 | 0.3 | 485.0533 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11548.5965 | 11548.5965 | 11548.5965 | 11548.5965 | 11548.5965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13774 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 21108.7065 | 0.2 | 0.3 | 32929.5821 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7642.6531 | 7642.6531 | 7642.6531 | 7642.6531 | 7642.6531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13775 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 16694.0941 | 0.2 | 0.3 | 26042.7868 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9610.5045 | 9610.5045 | 9610.5045 | 9610.5045 | 9610.5045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13776 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 16689.2896 | 0.2 | 0.3 | 26035.2918 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9790.2725 | 9790.2725 | 9790.2725 | 9790.2725 | 9790.2725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13777 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 16716.1937 | 0.2 | 0.3 | 26077.2621 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.2248 | 9778.2248 | 9778.2248 | 9778.2248 | 9778.2248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13778 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 21403.376 | 0.2 | 0.3 | 33389.2666 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1976.5341 | 1976.5341 | 1976.5341 | 1976.5341 | 1976.5341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13779 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 9998.6863 | 0.2 | 0.3 | 15597.9506 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6111.2364 | 6111.2364 | 6111.2364 | 6111.2364 | 6111.2364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13780 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16787.6974 | 0.2 | 0.3 | 26188.8079 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5635.3693 | 5635.3693 | 5635.3693 | 5635.3693 | 5635.3693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13781 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 22468.7219 | 0.2 | 0.3 | 35051.2062 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 113.5356 | 113.5356 | 113.5356 | 113.5356 | 113.5356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13782 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17460.1862 | 0.2 | 0.3 | 27237.8905 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6531.5161 | 6531.5161 | 6531.5161 | 6531.5161 | 6531.5161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13783 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 28635.2259 | 0.2 | 0.3 | 44670.9524 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6728.4114 | 6728.4114 | 6728.4114 | 6728.4114 | 6728.4114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13784 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 21678.7957 | 0.2 | 0.3 | 33818.9213 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7798.5342 | 7798.5342 | 7798.5342 | 7798.5342 | 7798.5342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13785 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 11181.9911 | 0.2 | 0.3 | 17443.9061 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13786 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 7833.1612 | 0.2 | 0.3 | 12219.7315 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7361.6218 | 7361.6218 | 7361.6218 | 7361.6218 | 7361.6218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13787 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16688.0018 | 0.2 | 0.3 | 26033.2828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4968.94 | 4968.94 | 4968.94 | 4968.94 | 4968.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13788 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 18137.7141 | 0.2 | 0.3 | 28294.8339 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5368.3823 | 5368.3823 | 5368.3823 | 5368.3823 | 5368.3823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13789 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 38477.9819 | 0.2 | 0.3 | 60025.6517 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2651.2037 | 2651.2037 | 2651.2037 | 2651.2037 | 2651.2037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13790 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 23078.0001 | 0.2 | 0.3 | 36001.6802 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 156.5207 | 156.5207 | 156.5207 | 156.5207 | 156.5207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13791 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 22312.4639 | 0.2 | 0.3 | 34807.4437 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2263.9734 | 2263.9734 | 2263.9734 | 2263.9734 | 2263.9734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13792 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 27457.4586 | 0.2 | 0.3 | 42833.6354 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2624.4135 | 2624.4135 | 2624.4135 | 2624.4135 | 2624.4135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13793 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 13781.1157 | 0.2 | 0.3 | 21498.5405 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2148.9641 | 2148.9641 | 2148.9641 | 2148.9641 | 2148.9641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13794 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 11464.8115 | 0.2 | 0.3 | 17885.1059 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9172.6035 | 9172.6035 | 9172.6035 | 9172.6035 | 9172.6035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13795 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 16688.3119 | 0.2 | 0.3 | 26033.7665 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9292.4432 | 9292.4432 | 9292.4432 | 9292.4432 | 9292.4432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13796 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17711.031 | 0.2 | 0.3 | 27629.2084 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12186.2981 | 12186.2981 | 12186.2981 | 12186.2981 | 12186.2981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13797 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 527.275 | 0.2 | 0.3 | 822.549 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7426.0938 | 7426.0938 | 7426.0938 | 7426.0938 | 7426.0938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13798 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 12029.418 | 0.2 | 0.3 | 18765.8921 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5373.1483 | 5373.1483 | 5373.1483 | 5373.1483 | 5373.1483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13799 | PARKLAND | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 10579.7431 | 0.2 | 0.3 | 16504.3992 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8743 | 5201.8743 | 5201.8743 | 5201.8743 | 5201.8743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13800 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 8619.4395 | 0.2 | 0.3 | 13446.3257 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.136 | 5202.136 | 5202.136 | 5202.136 | 5202.136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13801 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 23376.5055 | 0.2 | 0.3 | 36467.3485 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1403.6882 | 1403.6882 | 1403.6882 | 1403.6882 | 1403.6882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13802 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 21921.6429 | 0.2 | 0.3 | 34197.763 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10812.5275 | 10812.5275 | 10812.5275 | 10812.5275 | 10812.5275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13803 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16668.8885 | 0.2 | 0.3 | 26003.4661 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8303.6165 | 8303.6165 | 8303.6165 | 8303.6165 | 8303.6165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13804 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16669.2169 | 0.2 | 0.3 | 26003.9783 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8396.1959 | 8396.1959 | 8396.1959 | 8396.1959 | 8396.1959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13805 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 11214.1433 | 0.2 | 0.3 | 17494.0635 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5653 | 5201.5653 | 5201.5653 | 5201.5653 | 5201.5653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13806 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 16973.6298 | 0.2 | 0.3 | 26478.8625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6909.459 | 6909.459 | 6909.459 | 6909.459 | 6909.459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13807 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 9179.8883 | 0.2 | 0.3 | 14320.6258 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2782.2224 | 2782.2224 | 2782.2224 | 2782.2224 | 2782.2224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13808 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 16699.8651 | 0.2 | 0.3 | 26051.7895 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7448.9267 | 7448.9267 | 7448.9267 | 7448.9267 | 7448.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13809 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 19028.3306 | 0.2 | 0.3 | 29684.1957 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9472.4493 | 9472.4493 | 9472.4493 | 9472.4493 | 9472.4493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13810 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 18063.5744 | 0.2 | 0.3 | 28179.1761 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5045.5559 | 5045.5559 | 5045.5559 | 5045.5559 | 5045.5559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13811 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 16671.0957 | 0.2 | 0.3 | 26006.9093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2938.015 | 2938.015 | 2938.015 | 2938.015 | 2938.015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13812 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 15044.3705 | 0.2 | 0.3 | 23469.218 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2577.5014 | 2577.5014 | 2577.5014 | 2577.5014 | 2577.5014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13813 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17359.5506 | 0.2 | 0.3 | 27080.8989 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2860.0089 | 2860.0089 | 2860.0089 | 2860.0089 | 2860.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13814 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 24118.1204 | 0.2 | 0.3 | 37624.2678 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.8838 | 5199.8838 | 5199.8838 | 5199.8838 | 5199.8838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13815 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 23392.8554 | 0.2 | 0.3 | 36492.8544 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5064.9387 | 5064.9387 | 5064.9387 | 5064.9387 | 5064.9387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13816 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 8334.7274 | 0.2 | 0.3 | 13002.1747 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9593 | 5201.9593 | 5201.9593 | 5201.9593 | 5201.9593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13817 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 23726.8305 | 0.2 | 0.3 | 37013.8555 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9254 | 5201.9254 | 5201.9254 | 5201.9254 | 5201.9254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13818 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 23529.1098 | 0.2 | 0.3 | 36705.4113 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8353.2906 | 8353.2906 | 8353.2906 | 8353.2906 | 8353.2906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13819 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 12272.4721 | 0.2 | 0.3 | 19145.0564 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7252.0911 | 7252.0911 | 7252.0911 | 7252.0911 | 7252.0911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13820 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 13639.8665 | 0.2 | 0.3 | 21278.1917 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13821 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 1719.7935 | 0.2 | 0.3 | 2682.8779 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13822 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 6800.7943 | 0.2 | 0.3 | 10609.2392 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6345.1842 | 6345.1842 | 6345.1842 | 6345.1842 | 6345.1842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13823 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 37478.9813 | 0.2 | 0.3 | 58467.2108 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5440.9665 | 5440.9665 | 5440.9665 | 5440.9665 | 5440.9665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13824 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 45.8737 | 0.2 | 0.3 | 71.563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5228.3998 | 5228.3998 | 5228.3998 | 5228.3998 | 5228.3998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13825 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16915.7357 | 0.2 | 0.3 | 26388.5476 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11700.2034 | 11700.2034 | 11700.2034 | 11700.2034 | 11700.2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13826 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 18308.6384 | 0.2 | 0.3 | 28561.4759 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9984.3507 | 9984.3507 | 9984.3507 | 9984.3507 | 9984.3507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13827 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 28054.6815 | 0.2 | 0.3 | 43765.3032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9784.6078 | 9784.6078 | 9784.6078 | 9784.6078 | 9784.6078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13828 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 29279.8343 | 0.2 | 0.3 | 45676.5416 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7841.4415 | 7841.4415 | 7841.4415 | 7841.4415 | 7841.4415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13829 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16893.2837 | 0.2 | 0.3 | 26353.5226 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8388.6053 | 8388.6053 | 8388.6053 | 8388.6053 | 8388.6053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13830 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 7726.3282 | 0.2 | 0.3 | 12053.072 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5909 | 5202.5909 | 5202.5909 | 5202.5909 | 5202.5909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13831 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 20999.5117 | 0.2 | 0.3 | 32759.2382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13832 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 17719.1761 | 0.2 | 0.3 | 27641.9147 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7825.0517 | 7825.0517 | 7825.0517 | 7825.0517 | 7825.0517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13833 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 20927.6672 | 0.2 | 0.3 | 32647.1608 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13834 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 33486.9559 | 0.2 | 0.3 | 52239.6513 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8608.8479 | 8608.8479 | 8608.8479 | 8608.8479 | 8608.8479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13835 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 16630.7411 | 0.2 | 0.3 | 25943.9561 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13836 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 1.5654 | 0.2 | 0.3 | 2.442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13837 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 3065.8005 | 0.2 | 0.3 | 4782.6487 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7802.6131 | 7802.6131 | 7802.6131 | 7802.6131 | 7802.6131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13838 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 22513.7941 | 0.2 | 0.3 | 35121.5188 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7802.6984 | 7802.6984 | 7802.6984 | 7802.6984 | 7802.6984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13839 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 8871.1307 | 0.2 | 0.3 | 13838.9639 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13840 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17852.0925 | 0.2 | 0.3 | 27849.2644 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13841 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 29.9012 | 0.2 | 0.3 | 46.6459 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7801.9174 | 7801.9174 | 7801.9174 | 7801.9174 | 7801.9174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13842 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 1726.4459 | 0.2 | 0.3 | 2693.2557 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5007.0889 | 5007.0889 | 5007.0889 | 5007.0889 | 5007.0889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13843 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 26869.4018 | 0.2 | 0.3 | 41916.2668 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10778.9199 | 10778.9199 | 10778.9199 | 10778.9199 | 10778.9199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13844 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16670.1542 | 0.2 | 0.3 | 26005.4406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 880.5414 | 880.5414 | 880.5414 | 880.5414 | 880.5414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13845 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 11526.0946 | 0.2 | 0.3 | 17980.7076 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 885.9535 | 885.9535 | 885.9535 | 885.9535 | 885.9535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13846 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 10158.1141 | 0.2 | 0.3 | 15846.658 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13865.1611 | 13865.1611 | 13865.1611 | 13865.1611 | 13865.1611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13847 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 17002.9611 | 0.2 | 0.3 | 26524.6193 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8174.8888 | 8174.8888 | 8174.8888 | 8174.8888 | 8174.8888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13848 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 16658.9738 | 0.2 | 0.3 | 25987.9991 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8070.1705 | 8070.1705 | 8070.1705 | 8070.1705 | 8070.1705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13849 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 25325.7821 | 0.2 | 0.3 | 39508.2201 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5932.4875 | 5932.4875 | 5932.4875 | 5932.4875 | 5932.4875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13850 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 29598.0932 | 0.2 | 0.3 | 46173.0254 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5067.597 | 5067.597 | 5067.597 | 5067.597 | 5067.597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13851 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 34047.7681 | 0.2 | 0.3 | 53114.5183 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3911.2978 | 3911.2978 | 3911.2978 | 3911.2978 | 3911.2978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13852 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 19653.355 | 0.2 | 0.3 | 30659.2338 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7435.015 | 7435.015 | 7435.015 | 7435.015 | 7435.015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13853 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 12691.5518 | 0.2 | 0.3 | 19798.8208 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9305.878 | 9305.878 | 9305.878 | 9305.878 | 9305.878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13854 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 17706.2356 | 0.2 | 0.3 | 27621.7275 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13855 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 22711.3563 | 0.2 | 0.3 | 35429.7158 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8816.2101 | 8816.2101 | 8816.2101 | 8816.2101 | 8816.2101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13856 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 14994.0021 | 0.2 | 0.3 | 23390.6432 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13857 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 17924.1575 | 0.2 | 0.3 | 27961.6858 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13858 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 7663.9134 | 0.2 | 0.3 | 11955.7049 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6419.258 | 6419.258 | 6419.258 | 6419.258 | 6419.258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13859 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 20427.3557 | 0.2 | 0.3 | 31866.6748 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9186.0064 | 9186.0064 | 9186.0064 | 9186.0064 | 9186.0064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13860 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 16861.6749 | 0.2 | 0.3 | 26304.2128 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5761.7667 | 5761.7667 | 5761.7667 | 5761.7667 | 5761.7667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13861 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 16961.2201 | 0.2 | 0.3 | 26459.5034 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9782.0796 | 9782.0796 | 9782.0796 | 9782.0796 | 9782.0796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13862 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 26686.7901 | 0.2 | 0.3 | 41631.3926 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9181.3501 | 9181.3501 | 9181.3501 | 9181.3501 | 9181.3501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13863 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 23376.3625 | 0.2 | 0.3 | 36467.1254 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9848.2123 | 9848.2123 | 9848.2123 | 9848.2123 | 9848.2123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13864 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 33991.1794 | 0.2 | 0.3 | 53026.2399 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4209.1915 | 4209.1915 | 4209.1915 | 4209.1915 | 4209.1915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13865 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 33735.2793 | 0.2 | 0.3 | 52627.0357 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6326.9553 | 6326.9553 | 6326.9553 | 6326.9553 | 6326.9553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13866 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 27001.6538 | 0.2 | 0.3 | 42122.5799 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2951.8378 | 2951.8378 | 2951.8378 | 2951.8378 | 2951.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13867 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 19366.0127 | 0.2 | 0.3 | 30210.9799 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8016.5405 | 8016.5405 | 8016.5405 | 8016.5405 | 8016.5405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13868 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 12305.5729 | 0.2 | 0.3 | 19196.6937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5412.391 | 5412.391 | 5412.391 | 5412.391 | 5412.391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13869 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 9617.6724 | 0.2 | 0.3 | 15003.5689 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6751.7079 | 6751.7079 | 6751.7079 | 6751.7079 | 6751.7079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13870 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 12790.4981 | 0.2 | 0.3 | 19953.1771 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1203.0722 | 1203.0722 | 1203.0722 | 1203.0722 | 1203.0722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13871 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1819 | 0.2 | 0.3 | 26000.8038 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6321.858 | 6321.858 | 6321.858 | 6321.858 | 6321.858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13872 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 16667.5567 | 0.2 | 0.3 | 26001.3884 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4693.2983 | 4693.2983 | 4693.2983 | 4693.2983 | 4693.2983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13873 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 23863.4759 | 0.2 | 0.3 | 37227.0225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3847.1163 | 3847.1163 | 3847.1163 | 3847.1163 | 3847.1163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13874 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 3296.3873 | 0.2 | 0.3 | 5142.3641 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1741.4928 | 1741.4928 | 1741.4928 | 1741.4928 | 1741.4928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13875 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 16774.1403 | 0.2 | 0.3 | 26167.6588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1723.2749 | 1723.2749 | 1723.2749 | 1723.2749 | 1723.2749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13876 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 17234.9364 | 0.2 | 0.3 | 26886.5008 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3642.4964 | 3642.4964 | 3642.4964 | 3642.4964 | 3642.4964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13877 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 16530.0129 | 0.2 | 0.3 | 25786.8202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1670.9084 | 1670.9084 | 1670.9084 | 1670.9084 | 1670.9084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13878 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 16833.9565 | 0.2 | 0.3 | 26260.9722 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7043.7708 | 7043.7708 | 7043.7708 | 7043.7708 | 7043.7708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13879 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 197.7175 | 0.2 | 0.3 | 308.4392 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5194.885 | 5194.885 | 5194.885 | 5194.885 | 5194.885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13880 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 777.6119 | 0.2 | 0.3 | 1213.0745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.669 | 5201.669 | 5201.669 | 5201.669 | 5201.669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13881 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16346.9811 | 0.2 | 0.3 | 25501.2906 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5576 | 5201.5576 | 5201.5576 | 5201.5576 | 5201.5576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13882 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16852.5927 | 0.2 | 0.3 | 26290.0446 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10398.506 | 10398.506 | 10398.506 | 10398.506 | 10398.506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13883 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 4311.2905 | 0.2 | 0.3 | 6725.6132 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4156 | 5201.4156 | 5201.4156 | 5201.4156 | 5201.4156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13884 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 12985.5901 | 0.2 | 0.3 | 20257.5206 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7358.7543 | 7358.7543 | 7358.7543 | 7358.7543 | 7358.7543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13885 | COCONUT CREEK | 10609 | Private | 2036 | 5 | Swales | 66.6667 | 5735.1446 | 0.2 | 0.3 | 8946.8256 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1353 | 5202.1353 | 5202.1353 | 5202.1353 | 5202.1353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13886 | COCONUT CREEK | 10613 | Private | 2036 | 5 | Swales | 66.6667 | 22900.3112 | 0.2 | 0.3 | 35724.4855 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13887 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 13683.1091 | 0.2 | 0.3 | 21345.6502 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13888 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 22915.0825 | 0.2 | 0.3 | 35747.5288 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1447.0718 | 1447.0718 | 1447.0718 | 1447.0718 | 1447.0718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13889 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 17328.0889 | 0.2 | 0.3 | 27031.8187 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7136.2998 | 7136.2998 | 7136.2998 | 7136.2998 | 7136.2998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13890 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 13440.6982 | 0.2 | 0.3 | 20967.4892 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8054.9428 | 8054.9428 | 8054.9428 | 8054.9428 | 8054.9428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13891 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 19442.1911 | 0.2 | 0.3 | 30329.8182 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5196.0242 | 5196.0242 | 5196.0242 | 5196.0242 | 5196.0242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13892 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 17968.786 | 0.2 | 0.3 | 28031.3062 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2633.5009 | 2633.5009 | 2633.5009 | 2633.5009 | 2633.5009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13893 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 14801.5819 | 0.2 | 0.3 | 23090.4677 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9819.7461 | 9819.7461 | 9819.7461 | 9819.7461 | 9819.7461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13894 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 1874.0341 | 0.2 | 0.3 | 2923.4932 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6339 | 5201.6339 | 5201.6339 | 5201.6339 | 5201.6339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13895 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 14283.1373 | 0.2 | 0.3 | 22281.6942 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5973.0839 | 5973.0839 | 5973.0839 | 5973.0839 | 5973.0839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13896 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 18752.4711 | 0.2 | 0.3 | 29253.8549 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5270.1248 | 5270.1248 | 5270.1248 | 5270.1248 | 5270.1248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13897 | CORAL SPRINGS | 10601 | Private | 2036 | 5 | Swales | 66.6667 | 1374.9633 | 0.2 | 0.3 | 2144.9427 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5860.7586 | 5860.7586 | 5860.7586 | 5860.7586 | 5860.7586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13898 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 4251.8689 | 0.2 | 0.3 | 6632.9154 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.9257 | 5204.9257 | 5204.9257 | 5204.9257 | 5204.9257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13899 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 19321.7988 | 0.2 | 0.3 | 30142.0061 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3463.3584 | 3463.3584 | 3463.3584 | 3463.3584 | 3463.3584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13900 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 17116.0582 | 0.2 | 0.3 | 26701.0508 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5518.4354 | 5518.4354 | 5518.4354 | 5518.4354 | 5518.4354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13901 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 19918.222 | 0.2 | 0.3 | 31072.4263 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5186.3553 | 5186.3553 | 5186.3553 | 5186.3553 | 5186.3553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13902 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 12345.1643 | 0.2 | 0.3 | 19258.4564 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3530.1809 | 3530.1809 | 3530.1809 | 3530.1809 | 3530.1809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13903 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 31762.1833 | 0.2 | 0.3 | 49549.006 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7074.4569 | 7074.4569 | 7074.4569 | 7074.4569 | 7074.4569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13904 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 18133.9755 | 0.2 | 0.3 | 28289.0017 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.1969 | 9779.1969 | 9779.1969 | 9779.1969 | 9779.1969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13905 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 26153.9074 | 0.2 | 0.3 | 40800.0955 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.9566 | 9779.9566 | 9779.9566 | 9779.9566 | 9779.9566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13906 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 36614.8265 | 0.2 | 0.3 | 57119.1293 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12978.4709 | 12978.4709 | 12978.4709 | 12978.4709 | 12978.4709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13907 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 22412.0581 | 0.2 | 0.3 | 34962.8106 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6967.2186 | 6967.2186 | 6967.2186 | 6967.2186 | 6967.2186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13908 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 20426.8597 | 0.2 | 0.3 | 31865.9012 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9780.4825 | 9780.4825 | 9780.4825 | 9780.4825 | 9780.4825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13909 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 7541.6118 | 0.2 | 0.3 | 11764.9144 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6987.3926 | 6987.3926 | 6987.3926 | 6987.3926 | 6987.3926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13910 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 20008.4609 | 0.2 | 0.3 | 31213.1991 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9787.6678 | 9787.6678 | 9787.6678 | 9787.6678 | 9787.6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13911 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 9851.7834 | 0.2 | 0.3 | 15368.7821 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7279.8176 | 7279.8176 | 7279.8176 | 7279.8176 | 7279.8176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13912 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 19006.3971 | 0.2 | 0.3 | 29649.9795 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7417.5047 | 7417.5047 | 7417.5047 | 7417.5047 | 7417.5047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13913 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 16922.4633 | 0.2 | 0.3 | 26399.0428 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7540.7782 | 7540.7782 | 7540.7782 | 7540.7782 | 7540.7782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13914 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 12830.7513 | 0.2 | 0.3 | 20015.9721 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 156.8224 | 156.8224 | 156.8224 | 156.8224 | 156.8224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13915 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 19542.5043 | 0.2 | 0.3 | 30486.3067 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5260.6283 | 5260.6283 | 5260.6283 | 5260.6283 | 5260.6283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13916 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 20029.9728 | 0.2 | 0.3 | 31246.7576 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7210.4635 | 7210.4635 | 7210.4635 | 7210.4635 | 7210.4635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13917 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 16668.4572 | 0.2 | 0.3 | 26002.7932 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2312.591 | 2312.591 | 2312.591 | 2312.591 | 2312.591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13918 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 16651.0615 | 0.2 | 0.3 | 25975.656 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9848.2169 | 9848.2169 | 9848.2169 | 9848.2169 | 9848.2169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13919 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1596 | 0.2 | 0.3 | 26000.769 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9672.7648 | 9672.7648 | 9672.7648 | 9672.7648 | 9672.7648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13920 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 25104.0305 | 0.2 | 0.3 | 39162.2875 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1334 | 5202.1334 | 5202.1334 | 5202.1334 | 5202.1334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13921 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 16697.5523 | 0.2 | 0.3 | 26048.1816 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13922 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 20050.742 | 0.2 | 0.3 | 31279.1575 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6386 | 5201.6386 | 5201.6386 | 5201.6386 | 5201.6386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13923 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 25571.3406 | 0.2 | 0.3 | 39891.2913 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5968 | 5200.5968 | 5200.5968 | 5200.5968 | 5200.5968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13924 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 22356.3443 | 0.2 | 0.3 | 34875.8971 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6918.2131 | 6918.2131 | 6918.2131 | 6918.2131 | 6918.2131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13925 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 21356.0067 | 0.2 | 0.3 | 33315.3705 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9187.3654 | 9187.3654 | 9187.3654 | 9187.3654 | 9187.3654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13926 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16975.052 | 0.2 | 0.3 | 26481.0811 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13927 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 390.7436 | 0.2 | 0.3 | 609.56 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4440.0041 | 4440.0041 | 4440.0041 | 4440.0041 | 4440.0041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13928 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16667.0863 | 0.2 | 0.3 | 26000.6546 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13929 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16779.6154 | 0.2 | 0.3 | 26176.2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13930 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 12621.1897 | 0.2 | 0.3 | 19689.056 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7803.0396 | 7803.0396 | 7803.0396 | 7803.0396 | 7803.0396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13931 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17160.3402 | 0.2 | 0.3 | 26770.1307 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7801.8094 | 7801.8094 | 7801.8094 | 7801.8094 | 7801.8094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13932 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16736.5451 | 0.2 | 0.3 | 26109.0103 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.265 | 5203.265 | 5203.265 | 5203.265 | 5203.265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13933 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16818.2203 | 0.2 | 0.3 | 26236.4237 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1266 | 5202.1266 | 5202.1266 | 5202.1266 | 5202.1266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13934 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 20348.0282 | 0.2 | 0.3 | 31742.924 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13935 | COCONUT CREEK | 10613 | Private | 2036 | 5 | Swales | 66.6667 | 16668.8099 | 0.2 | 0.3 | 26003.3435 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13936 | COCONUT CREEK | 10613 | Private | 2036 | 5 | Swales | 66.6667 | 16342.8493 | 0.2 | 0.3 | 25494.8449 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13937 | COCONUT CREEK | 10613 | Private | 2036 | 5 | Swales | 66.6667 | 22073.6175 | 0.2 | 0.3 | 34434.8434 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13938 | COCONUT CREEK | 10613 | Private | 2036 | 5 | Swales | 66.6667 | 38108.8377 | 0.2 | 0.3 | 59449.7868 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6416.1587 | 6416.1587 | 6416.1587 | 6416.1587 | 6416.1587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13939 | COCONUT CREEK | 10613 | Private | 2036 | 5 | Swales | 66.6667 | 17569.4606 | 0.2 | 0.3 | 27408.3585 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6130.0965 | 6130.0965 | 6130.0965 | 6130.0965 | 6130.0965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13940 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 6273.1873 | 0.2 | 0.3 | 9786.1721 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1162.5987 | 1162.5987 | 1162.5987 | 1162.5987 | 1162.5987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13941 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 13187.4271 | 0.2 | 0.3 | 20572.3863 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5825.8601 | 5825.8601 | 5825.8601 | 5825.8601 | 5825.8601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13942 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 7458.582 | 0.2 | 0.3 | 11635.3879 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10665.7921 | 10665.7921 | 10665.7921 | 10665.7921 | 10665.7921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13943 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 27059.1786 | 0.2 | 0.3 | 42212.3186 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9477.9869 | 9477.9869 | 9477.9869 | 9477.9869 | 9477.9869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13944 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 45168.876 | 0.2 | 0.3 | 70463.4466 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7956 | 5201.7956 | 5201.7956 | 5201.7956 | 5201.7956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13945 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 23880.4873 | 0.2 | 0.3 | 37253.5601 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13946 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 24033.0742 | 0.2 | 0.3 | 37491.5958 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13947 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 8181.7622 | 0.2 | 0.3 | 12763.549 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.026 | 5202.026 | 5202.026 | 5202.026 | 5202.026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13948 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 8864.3271 | 0.2 | 0.3 | 13828.3503 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9259.85 | 9259.85 | 9259.85 | 9259.85 | 9259.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13949 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 16677.3065 | 0.2 | 0.3 | 26016.5981 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5368.2673 | 5368.2673 | 5368.2673 | 5368.2673 | 5368.2673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13950 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 18774.806 | 0.2 | 0.3 | 29288.6974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11777.2317 | 11777.2317 | 11777.2317 | 11777.2317 | 11777.2317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13951 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 22184.0603 | 0.2 | 0.3 | 34607.1341 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9752.9886 | 9752.9886 | 9752.9886 | 9752.9886 | 9752.9886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13952 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 12835.4206 | 0.2 | 0.3 | 20023.2561 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8519.6431 | 8519.6431 | 8519.6431 | 8519.6431 | 8519.6431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13953 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 32921.6736 | 0.2 | 0.3 | 51357.8108 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8396.0992 | 8396.0992 | 8396.0992 | 8396.0992 | 8396.0992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13954 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 35397.3769 | 0.2 | 0.3 | 55219.908 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8274.6529 | 8274.6529 | 8274.6529 | 8274.6529 | 8274.6529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13955 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 42514.1424 | 0.2 | 0.3 | 66322.0621 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9819.0229 | 9819.0229 | 9819.0229 | 9819.0229 | 9819.0229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13956 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 49681.5827 | 0.2 | 0.3 | 77503.2691 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7978.8413 | 7978.8413 | 7978.8413 | 7978.8413 | 7978.8413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13957 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 41366.9045 | 0.2 | 0.3 | 64532.371 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5462.8217 | 5462.8217 | 5462.8217 | 5462.8217 | 5462.8217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13958 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 13701.0389 | 0.2 | 0.3 | 21373.6207 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12920.9501 | 12920.9501 | 12920.9501 | 12920.9501 | 12920.9501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13959 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 17022.7478 | 0.2 | 0.3 | 26555.4866 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10405.1212 | 10405.1212 | 10405.1212 | 10405.1212 | 10405.1212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13960 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 17835.0666 | 0.2 | 0.3 | 27822.7039 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10085.4281 | 10085.4281 | 10085.4281 | 10085.4281 | 10085.4281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13961 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 11829.3429 | 0.2 | 0.3 | 18453.775 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10543.6528 | 10543.6528 | 10543.6528 | 10543.6528 | 10543.6528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13962 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 19868.3312 | 0.2 | 0.3 | 30994.5967 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9179.2152 | 9179.2152 | 9179.2152 | 9179.2152 | 9179.2152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13963 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 16667.8627 | 0.2 | 0.3 | 26001.8659 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7381.4498 | 7381.4498 | 7381.4498 | 7381.4498 | 7381.4498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13964 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 18867.8745 | 0.2 | 0.3 | 29433.8843 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6268.6549 | 6268.6549 | 6268.6549 | 6268.6549 | 6268.6549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13965 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 9208.8685 | 0.2 | 0.3 | 14365.8348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2444.4104 | 2444.4104 | 2444.4104 | 2444.4104 | 2444.4104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13966 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16716.0874 | 0.2 | 0.3 | 26077.0963 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9344.3043 | 9344.3043 | 9344.3043 | 9344.3043 | 9344.3043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13967 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 30280.4973 | 0.2 | 0.3 | 47237.5757 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1785 | 5201.1785 | 5201.1785 | 5201.1785 | 5201.1785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13968 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 13303.699 | 0.2 | 0.3 | 20753.7704 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13969 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 13961.5785 | 0.2 | 0.3 | 21780.0624 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0934 | 5202.0934 | 5202.0934 | 5202.0934 | 5202.0934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13970 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 24763.9369 | 0.2 | 0.3 | 38631.7416 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0639 | 5202.0639 | 5202.0639 | 5202.0639 | 5202.0639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13971 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16753.1431 | 0.2 | 0.3 | 26134.9032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7384.3068 | 7384.3068 | 7384.3068 | 7384.3068 | 7384.3068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13972 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16923.6329 | 0.2 | 0.3 | 26400.8674 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1328.2408 | 1328.2408 | 1328.2408 | 1328.2408 | 1328.2408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13973 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 15912.5037 | 0.2 | 0.3 | 24823.5057 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8251.4229 | 8251.4229 | 8251.4229 | 8251.4229 | 8251.4229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13974 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 25923.6628 | 0.2 | 0.3 | 40440.914 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6023.6755 | 6023.6755 | 6023.6755 | 6023.6755 | 6023.6755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13975 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16706.0701 | 0.2 | 0.3 | 26061.4693 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7451.7765 | 7451.7765 | 7451.7765 | 7451.7765 | 7451.7765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13976 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 14560.2956 | 0.2 | 0.3 | 22714.0611 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8174.2019 | 8174.2019 | 8174.2019 | 8174.2019 | 8174.2019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13977 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 24512.7972 | 0.2 | 0.3 | 38239.9636 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6626.1943 | 6626.1943 | 6626.1943 | 6626.1943 | 6626.1943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13978 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 12594.3715 | 0.2 | 0.3 | 19647.2195 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7287.9841 | 7287.9841 | 7287.9841 | 7287.9841 | 7287.9841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13979 | COCONUT CREEK | 10613 | Private | 2036 | 5 | Swales | 66.6667 | 2025.4925 | 0.2 | 0.3 | 3159.7682 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8292.0928 | 8292.0928 | 8292.0928 | 8292.0928 | 8292.0928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13980 | COCONUT CREEK | 10613 | Private | 2036 | 5 | Swales | 66.6667 | 39288.7957 | 0.2 | 0.3 | 61290.5212 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9343.3145 | 9343.3145 | 9343.3145 | 9343.3145 | 9343.3145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13981 | COCONUT CREEK | 10613 | Private | 2036 | 5 | Swales | 66.6667 | 29257.7835 | 0.2 | 0.3 | 45642.1422 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9406.6964 | 9406.6964 | 9406.6964 | 9406.6964 | 9406.6964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13982 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 18532.4059 | 0.2 | 0.3 | 28910.5533 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13983 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 994.972 | 0.2 | 0.3 | 1552.1563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6326.482 | 6326.482 | 6326.482 | 6326.482 | 6326.482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13984 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 16668.9573 | 0.2 | 0.3 | 26003.5734 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6402.3743 | 6402.3743 | 6402.3743 | 6402.3743 | 6402.3743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13985 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 33341.4021 | 0.2 | 0.3 | 52012.5872 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10008.641 | 10008.641 | 10008.641 | 10008.641 | 10008.641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13986 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 13685.447 | 0.2 | 0.3 | 21349.2973 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5802.3971 | 5802.3971 | 5802.3971 | 5802.3971 | 5802.3971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13987 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 29809.8121 | 0.2 | 0.3 | 46503.3068 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7326.2059 | 7326.2059 | 7326.2059 | 7326.2059 | 7326.2059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13988 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 245.5755 | 0.2 | 0.3 | 383.0978 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8018 | 5201.8018 | 5201.8018 | 5201.8018 | 5201.8018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13989 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 6954.7964 | 0.2 | 0.3 | 10849.4824 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8368 | 5202.8368 | 5202.8368 | 5202.8368 | 5202.8368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13990 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 13730.7383 | 0.2 | 0.3 | 21419.9518 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5783.6945 | 5783.6945 | 5783.6945 | 5783.6945 | 5783.6945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13991 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 30154.5273 | 0.2 | 0.3 | 47041.0625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7158.6259 | 7158.6259 | 7158.6259 | 7158.6259 | 7158.6259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13992 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 1241.3725 | 0.2 | 0.3 | 1936.541 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5921.3003 | 5921.3003 | 5921.3003 | 5921.3003 | 5921.3003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13993 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 2791.2169 | 0.2 | 0.3 | 4354.2983 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0662 | 5201.0662 | 5201.0662 | 5201.0662 | 5201.0662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13994 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 43343.7626 | 0.2 | 0.3 | 67616.2697 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9863.9144 | 9863.9144 | 9863.9144 | 9863.9144 | 9863.9144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13995 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 31591.5655 | 0.2 | 0.3 | 49282.8422 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9208 | 5203.9208 | 5203.9208 | 5203.9208 | 5203.9208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13996 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 19177.8555 | 0.2 | 0.3 | 29917.4546 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5266.113 | 5266.113 | 5266.113 | 5266.113 | 5266.113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13997 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 26362.4157 | 0.2 | 0.3 | 41125.3685 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10340.1645 | 10340.1645 | 10340.1645 | 10340.1645 | 10340.1645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13998 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 26470.9601 | 0.2 | 0.3 | 41294.6978 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6546.4166 | 6546.4166 | 6546.4166 | 6546.4166 | 6546.4166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13999 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 19380.2322 | 0.2 | 0.3 | 30233.1622 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5872.9686 | 5872.9686 | 5872.9686 | 5872.9686 | 5872.9686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14000 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 25443.8025 | 0.2 | 0.3 | 39692.3318 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9236.3221 | 9236.3221 | 9236.3221 | 9236.3221 | 9236.3221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14001 | CORAL SPRINGS | 10612 | Public | 2036 | 5 | Swales | 66.6667 | 8342.7725 | 0.2 | 0.3 | 13014.725 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9788.7348 | 9788.7348 | 9788.7348 | 9788.7348 | 9788.7348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14002 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 22058.4671 | 0.2 | 0.3 | 34411.2087 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7381.4962 | 7381.4962 | 7381.4962 | 7381.4962 | 7381.4962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14003 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 26243.5315 | 0.2 | 0.3 | 40939.9092 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.703 | 5200.703 | 5200.703 | 5200.703 | 5200.703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14004 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 24787.3831 | 0.2 | 0.3 | 38668.3177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.2351 | 9779.2351 | 9779.2351 | 9779.2351 | 9779.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14005 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 13661.1679 | 0.2 | 0.3 | 21311.422 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3279 | 5203.3279 | 5203.3279 | 5203.3279 | 5203.3279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14006 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 12279.5408 | 0.2 | 0.3 | 19156.0836 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5710.7561 | 5710.7561 | 5710.7561 | 5710.7561 | 5710.7561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14007 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 23577.0386 | 0.2 | 0.3 | 36780.1802 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6812.4537 | 6812.4537 | 6812.4537 | 6812.4537 | 6812.4537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14008 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 23339.3787 | 0.2 | 0.3 | 36409.4308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6923.3119 | 6923.3119 | 6923.3119 | 6923.3119 | 6923.3119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14009 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16667.5364 | 0.2 | 0.3 | 26001.3568 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3767.7436 | 3767.7436 | 3767.7436 | 3767.7436 | 3767.7436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14010 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 10208.6208 | 0.2 | 0.3 | 15925.4484 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14011 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 5032.6554 | 0.2 | 0.3 | 7850.9424 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5730.6317 | 5730.6317 | 5730.6317 | 5730.6317 | 5730.6317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14012 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16386.3915 | 0.2 | 0.3 | 25562.7707 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5542.3005 | 5542.3005 | 5542.3005 | 5542.3005 | 5542.3005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14013 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 18385.9836 | 0.2 | 0.3 | 28682.1344 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7237.529 | 7237.529 | 7237.529 | 7237.529 | 7237.529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14014 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16014.9424 | 0.2 | 0.3 | 24983.3101 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14015 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 18147.0206 | 0.2 | 0.3 | 28309.3521 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6021 | 5200.6021 | 5200.6021 | 5200.6021 | 5200.6021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14016 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 19577.3531 | 0.2 | 0.3 | 30540.6709 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5315.5096 | 5315.5096 | 5315.5096 | 5315.5096 | 5315.5096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14017 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 17812.6236 | 0.2 | 0.3 | 27787.6928 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3813.0424 | 3813.0424 | 3813.0424 | 3813.0424 | 3813.0424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14018 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 14677.4409 | 0.2 | 0.3 | 22896.8079 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8768.8886 | 8768.8886 | 8768.8886 | 8768.8886 | 8768.8886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14019 | COCONUT CREEK | 10613 | Private | 2036 | 5 | Swales | 66.6667 | 30789.7025 | 0.2 | 0.3 | 48031.9358 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4060.846 | 4060.846 | 4060.846 | 4060.846 | 4060.846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14020 | COCONUT CREEK | 10613 | Private | 2036 | 5 | Swales | 66.6667 | 27318.8685 | 0.2 | 0.3 | 42617.4349 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5195.8608 | 5195.8608 | 5195.8608 | 5195.8608 | 5195.8608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14021 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 254.1967 | 0.2 | 0.3 | 396.5469 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1039 | 5200.1039 | 5200.1039 | 5200.1039 | 5200.1039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14022 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 29788.6813 | 0.2 | 0.3 | 46470.3429 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8878 | 5200.8878 | 5200.8878 | 5200.8878 | 5200.8878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14023 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 30734.2352 | 0.2 | 0.3 | 47945.4069 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5232.6962 | 5232.6962 | 5232.6962 | 5232.6962 | 5232.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14024 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 44431.4461 | 0.2 | 0.3 | 69313.056 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5341.7917 | 5341.7917 | 5341.7917 | 5341.7917 | 5341.7917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14025 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 16668.6959 | 0.2 | 0.3 | 26003.1657 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2067 | 5202.2067 | 5202.2067 | 5202.2067 | 5202.2067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14026 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 14249.9897 | 0.2 | 0.3 | 22229.9839 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14027 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 2832.9971 | 0.2 | 0.3 | 4419.4755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14028 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 19939.8161 | 0.2 | 0.3 | 31106.1131 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.076 | 5201.076 | 5201.076 | 5201.076 | 5201.076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14029 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 28791.8421 | 0.2 | 0.3 | 44915.2736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6276.4298 | 6276.4298 | 6276.4298 | 6276.4298 | 6276.4298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14030 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 15501.6278 | 0.2 | 0.3 | 24182.5394 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8288.1305 | 8288.1305 | 8288.1305 | 8288.1305 | 8288.1305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14031 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 17123.6085 | 0.2 | 0.3 | 26712.8292 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6318.1972 | 6318.1972 | 6318.1972 | 6318.1972 | 6318.1972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14032 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 19925.5107 | 0.2 | 0.3 | 31083.7967 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6175.4707 | 6175.4707 | 6175.4707 | 6175.4707 | 6175.4707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14033 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 17174.0345 | 0.2 | 0.3 | 26791.4938 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2200.3962 | 2200.3962 | 2200.3962 | 2200.3962 | 2200.3962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14034 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 4470.0497 | 0.2 | 0.3 | 6973.2776 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5344.7774 | 5344.7774 | 5344.7774 | 5344.7774 | 5344.7774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14035 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 18712.1379 | 0.2 | 0.3 | 29190.9351 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2719.9033 | 2719.9033 | 2719.9033 | 2719.9033 | 2719.9033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14036 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 4896.8181 | 0.2 | 0.3 | 7639.0362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9647 | 5201.9647 | 5201.9647 | 5201.9647 | 5201.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14037 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 18032.3044 | 0.2 | 0.3 | 28130.3949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14038 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 19158.8704 | 0.2 | 0.3 | 29887.8378 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5745.4721 | 5745.4721 | 5745.4721 | 5745.4721 | 5745.4721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14039 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 23828.8455 | 0.2 | 0.3 | 37172.9989 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8322.8103 | 8322.8103 | 8322.8103 | 8322.8103 | 8322.8103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14040 | CORAL SPRINGS | 10612 | Public | 2036 | 5 | Swales | 66.6667 | 222.1663 | 0.2 | 0.3 | 346.5794 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9762.8477 | 9762.8477 | 9762.8477 | 9762.8477 | 9762.8477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14041 | CORAL SPRINGS | 10612 | Public | 2036 | 5 | Swales | 66.6667 | 37039.3075 | 0.2 | 0.3 | 57781.3196 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8694.1282 | 8694.1282 | 8694.1282 | 8694.1282 | 8694.1282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14042 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 24235.6499 | 0.2 | 0.3 | 37807.6138 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8865.2146 | 8865.2146 | 8865.2146 | 8865.2146 | 8865.2146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14043 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 13216.9383 | 0.2 | 0.3 | 20618.4237 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8988.993 | 8988.993 | 8988.993 | 8988.993 | 8988.993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14044 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 16954.117 | 0.2 | 0.3 | 26448.4225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5980.6907 | 5980.6907 | 5980.6907 | 5980.6907 | 5980.6907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14045 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 24467.1063 | 0.2 | 0.3 | 38168.6858 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1584 | 5202.1584 | 5202.1584 | 5202.1584 | 5202.1584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14046 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 31650.6854 | 0.2 | 0.3 | 49375.0692 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14047 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 23341.9134 | 0.2 | 0.3 | 36413.3849 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5656 | 5201.5656 | 5201.5656 | 5201.5656 | 5201.5656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14048 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 22797.1582 | 0.2 | 0.3 | 35563.5668 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5212.6324 | 5212.6324 | 5212.6324 | 5212.6324 | 5212.6324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14049 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17426.4362 | 0.2 | 0.3 | 27185.2405 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1161.2522 | 1161.2522 | 1161.2522 | 1161.2522 | 1161.2522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14050 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 32233.0867 | 0.2 | 0.3 | 50283.6152 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9802.4183 | 9802.4183 | 9802.4183 | 9802.4183 | 9802.4183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14051 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 20927.8411 | 0.2 | 0.3 | 32647.4321 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4856.3987 | 4856.3987 | 4856.3987 | 4856.3987 | 4856.3987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14052 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 24565.634 | 0.2 | 0.3 | 38322.389 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7654.5715 | 7654.5715 | 7654.5715 | 7654.5715 | 7654.5715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14053 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16968.4077 | 0.2 | 0.3 | 26470.7161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4651 | 5201.4651 | 5201.4651 | 5201.4651 | 5201.4651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14054 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 6095.8949 | 0.2 | 0.3 | 9509.596 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14055 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 23468.8791 | 0.2 | 0.3 | 36611.4513 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8982.2112 | 8982.2112 | 8982.2112 | 8982.2112 | 8982.2112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14056 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16670.738 | 0.2 | 0.3 | 26006.3513 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8714 | 5201.8714 | 5201.8714 | 5201.8714 | 5201.8714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14057 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16669.2491 | 0.2 | 0.3 | 26004.0286 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4335 | 5201.4335 | 5201.4335 | 5201.4335 | 5201.4335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14058 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 26928.6831 | 0.2 | 0.3 | 42008.7457 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4085 | 5201.4085 | 5201.4085 | 5201.4085 | 5201.4085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14059 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16671.5587 | 0.2 | 0.3 | 26007.6315 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14060 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16669.3381 | 0.2 | 0.3 | 26004.1675 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14061 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16667.5877 | 0.2 | 0.3 | 26001.4368 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5529.2975 | 5529.2975 | 5529.2975 | 5529.2975 | 5529.2975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14062 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 32010.8201 | 0.2 | 0.3 | 49936.8793 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14063 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 21176.023 | 0.2 | 0.3 | 33034.5959 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7529.9686 | 7529.9686 | 7529.9686 | 7529.9686 | 7529.9686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14064 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 21367.9619 | 0.2 | 0.3 | 33334.0206 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6956 | 5201.6956 | 5201.6956 | 5201.6956 | 5201.6956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14065 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 12324.5535 | 0.2 | 0.3 | 19226.3035 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14066 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 839.9383 | 0.2 | 0.3 | 1310.3037 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9780.2738 | 9780.2738 | 9780.2738 | 9780.2738 | 9780.2738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14067 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 26589.2798 | 0.2 | 0.3 | 41479.2765 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9328.5714 | 9328.5714 | 9328.5714 | 9328.5714 | 9328.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14068 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 17050.9323 | 0.2 | 0.3 | 26599.4543 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9716.0644 | 9716.0644 | 9716.0644 | 9716.0644 | 9716.0644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14069 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16756.8826 | 0.2 | 0.3 | 26140.7369 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.2378 | 9778.2378 | 9778.2378 | 9778.2378 | 9778.2378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14070 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 18785.7241 | 0.2 | 0.3 | 29305.7296 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.8463 | 9777.8463 | 9777.8463 | 9777.8463 | 9777.8463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14071 | COCONUT CREEK | 10613 | Private | 2036 | 5 | Swales | 66.6667 | 19468.4407 | 0.2 | 0.3 | 30370.7674 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9799.4822 | 9799.4822 | 9799.4822 | 9799.4822 | 9799.4822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14072 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 22345.1777 | 0.2 | 0.3 | 34858.4772 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3063.2437 | 3063.2437 | 3063.2437 | 3063.2437 | 3063.2437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14073 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 33334.4601 | 0.2 | 0.3 | 52001.7577 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6523.9352 | 6523.9352 | 6523.9352 | 6523.9352 | 6523.9352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14074 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 18337.7307 | 0.2 | 0.3 | 28606.8598 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14075 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 17602.1227 | 0.2 | 0.3 | 27459.3114 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1965 | 5202.1965 | 5202.1965 | 5202.1965 | 5202.1965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14076 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 15648.0007 | 0.2 | 0.3 | 24410.8811 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5353.3767 | 5353.3767 | 5353.3767 | 5353.3767 | 5353.3767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14077 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 16835.8283 | 0.2 | 0.3 | 26263.8922 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5261.9941 | 5261.9941 | 5261.9941 | 5261.9941 | 5261.9941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14078 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 13379.1843 | 0.2 | 0.3 | 20871.5276 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4349 | 5201.4349 | 5201.4349 | 5201.4349 | 5201.4349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14079 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 10943.3069 | 0.2 | 0.3 | 17071.5588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14080 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 22736.8731 | 0.2 | 0.3 | 35469.5221 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5084 | 5201.5084 | 5201.5084 | 5201.5084 | 5201.5084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14081 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 16935.7515 | 0.2 | 0.3 | 26419.7723 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7479.2106 | 7479.2106 | 7479.2106 | 7479.2106 | 7479.2106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14082 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 23721.635 | 0.2 | 0.3 | 37005.7506 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7428.1432 | 7428.1432 | 7428.1432 | 7428.1432 | 7428.1432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14083 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16835.9807 | 0.2 | 0.3 | 26264.1298 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5465.2647 | 5465.2647 | 5465.2647 | 5465.2647 | 5465.2647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14084 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 18163.3371 | 0.2 | 0.3 | 28334.8059 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5550.7426 | 5550.7426 | 5550.7426 | 5550.7426 | 5550.7426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14085 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 3538.6583 | 0.2 | 0.3 | 5520.307 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9272.8613 | 9272.8613 | 9272.8613 | 9272.8613 | 9272.8613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14086 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 19828.4938 | 0.2 | 0.3 | 30932.4503 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5748.6661 | 5748.6661 | 5748.6661 | 5748.6661 | 5748.6661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14087 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 7555.6093 | 0.2 | 0.3 | 11786.7506 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5266.2223 | 5266.2223 | 5266.2223 | 5266.2223 | 5266.2223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14088 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 10742.6894 | 0.2 | 0.3 | 16758.5955 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2986 | 5200.2986 | 5200.2986 | 5200.2986 | 5200.2986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14089 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 17475.5497 | 0.2 | 0.3 | 27261.8575 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1259 | 5201.1259 | 5201.1259 | 5201.1259 | 5201.1259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14090 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 21342.6901 | 0.2 | 0.3 | 33294.5965 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5358.3642 | 5358.3642 | 5358.3642 | 5358.3642 | 5358.3642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14091 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 18082.8239 | 0.2 | 0.3 | 28209.2053 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.7051 | 2600.7051 | 2600.7051 | 2600.7051 | 2600.7051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14092 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 13393.0142 | 0.2 | 0.3 | 20893.1022 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7525.0228 | 7525.0228 | 7525.0228 | 7525.0228 | 7525.0228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14093 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 17297.6059 | 0.2 | 0.3 | 26984.2652 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14094 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 16685.9879 | 0.2 | 0.3 | 26030.1411 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7757 | 5201.7757 | 5201.7757 | 5201.7757 | 5201.7757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14095 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 14229.5646 | 0.2 | 0.3 | 22198.1208 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4112 | 5200.4112 | 5200.4112 | 5200.4112 | 5200.4112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14096 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 18329.2247 | 0.2 | 0.3 | 28593.5905 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14097 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17184.9706 | 0.2 | 0.3 | 26808.5541 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1484 | 5202.1484 | 5202.1484 | 5202.1484 | 5202.1484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14098 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16242.663 | 0.2 | 0.3 | 25338.5543 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.087 | 5202.087 | 5202.087 | 5202.087 | 5202.087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14099 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 2312.1451 | 0.2 | 0.3 | 3606.9464 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5557.7101 | 5557.7101 | 5557.7101 | 5557.7101 | 5557.7101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14100 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 15665.6885 | 0.2 | 0.3 | 24438.474 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8190.3875 | 8190.3875 | 8190.3875 | 8190.3875 | 8190.3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14101 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17226.3577 | 0.2 | 0.3 | 26873.1181 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8085.328 | 8085.328 | 8085.328 | 8085.328 | 8085.328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14102 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 11913.9823 | 0.2 | 0.3 | 18585.8123 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7938.3944 | 7938.3944 | 7938.3944 | 7938.3944 | 7938.3944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14103 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 13776.0959 | 0.2 | 0.3 | 21490.7097 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7817.9446 | 7817.9446 | 7817.9446 | 7817.9446 | 7817.9446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14104 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17035.8508 | 0.2 | 0.3 | 26575.9272 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6831.952 | 6831.952 | 6831.952 | 6831.952 | 6831.952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14105 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17479.5363 | 0.2 | 0.3 | 27268.0766 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7741.954 | 7741.954 | 7741.954 | 7741.954 | 7741.954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14106 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16802.3394 | 0.2 | 0.3 | 26211.6495 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2877 | 5202.2877 | 5202.2877 | 5202.2877 | 5202.2877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14107 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16668.6779 | 0.2 | 0.3 | 26003.1375 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6692.9394 | 6692.9394 | 6692.9394 | 6692.9394 | 6692.9394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14108 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16668.6693 | 0.2 | 0.3 | 26003.1242 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8205.423 | 8205.423 | 8205.423 | 8205.423 | 8205.423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14109 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16670.1543 | 0.2 | 0.3 | 26005.4408 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14110 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16671.5213 | 0.2 | 0.3 | 26007.5732 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14111 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16671.0577 | 0.2 | 0.3 | 26006.8501 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1485 | 5201.1485 | 5201.1485 | 5201.1485 | 5201.1485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14112 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 3041.8211 | 0.2 | 0.3 | 4745.241 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7684.298 | 7684.298 | 7684.298 | 7684.298 | 7684.298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14113 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 18208.3942 | 0.2 | 0.3 | 28405.095 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7267.4207 | 7267.4207 | 7267.4207 | 7267.4207 | 7267.4207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14114 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 17437.4201 | 0.2 | 0.3 | 27202.3754 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8601.8119 | 8601.8119 | 8601.8119 | 8601.8119 | 8601.8119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14115 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 17372.1909 | 0.2 | 0.3 | 27100.6178 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8492.9989 | 8492.9989 | 8492.9989 | 8492.9989 | 8492.9989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14116 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 14846.1566 | 0.2 | 0.3 | 23160.0043 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8320.1694 | 8320.1694 | 8320.1694 | 8320.1694 | 8320.1694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14117 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 22380.1929 | 0.2 | 0.3 | 34913.1009 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6707.4492 | 6707.4492 | 6707.4492 | 6707.4492 | 6707.4492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14118 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16771.1447 | 0.2 | 0.3 | 26162.9857 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0309 | 5201.0309 | 5201.0309 | 5201.0309 | 5201.0309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14119 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 18178.8021 | 0.2 | 0.3 | 28358.9312 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14120 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 26715.5872 | 0.2 | 0.3 | 41676.316 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5647.1502 | 5647.1502 | 5647.1502 | 5647.1502 | 5647.1502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14121 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 28705.9757 | 0.2 | 0.3 | 44781.322 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9472.4057 | 9472.4057 | 9472.4057 | 9472.4057 | 9472.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14122 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 8217.9521 | 0.2 | 0.3 | 12820.0053 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5084.4012 | 5084.4012 | 5084.4012 | 5084.4012 | 5084.4012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14123 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 8803.6865 | 0.2 | 0.3 | 13733.7509 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.6251 | 5204.6251 | 5204.6251 | 5204.6251 | 5204.6251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14124 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 18905.1659 | 0.2 | 0.3 | 29492.0588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9670.0673 | 9670.0673 | 9670.0673 | 9670.0673 | 9670.0673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14125 | COCONUT CREEK | 10613 | Private | 2036 | 5 | Swales | 66.6667 | 15362.1129 | 0.2 | 0.3 | 23964.8962 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6376.361 | 6376.361 | 6376.361 | 6376.361 | 6376.361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14126 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 5850.0793 | 0.2 | 0.3 | 9126.1238 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5314.9083 | 5314.9083 | 5314.9083 | 5314.9083 | 5314.9083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14127 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 14776.8963 | 0.2 | 0.3 | 23051.9582 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5449.4437 | 5449.4437 | 5449.4437 | 5449.4437 | 5449.4437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14128 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 26478.0823 | 0.2 | 0.3 | 41305.8084 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4520.9064 | 4520.9064 | 4520.9064 | 4520.9064 | 4520.9064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14129 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1146 | 0.2 | 0.3 | 26000.6988 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7605.0436 | 7605.0436 | 7605.0436 | 7605.0436 | 7605.0436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14130 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 16966.1329 | 0.2 | 0.3 | 26467.1673 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6056.2953 | 6056.2953 | 6056.2953 | 6056.2953 | 6056.2953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14131 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 12851.4343 | 0.2 | 0.3 | 20048.2376 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3855 | 5203.3855 | 5203.3855 | 5203.3855 | 5203.3855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14132 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 17294.9336 | 0.2 | 0.3 | 26980.0964 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9393 | 5201.9393 | 5201.9393 | 5201.9393 | 5201.9393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14133 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 28024.6563 | 0.2 | 0.3 | 43718.4639 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8368 | 5201.8368 | 5201.8368 | 5201.8368 | 5201.8368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14134 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 26982.9465 | 0.2 | 0.3 | 42093.3965 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8243.2045 | 8243.2045 | 8243.2045 | 8243.2045 | 8243.2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14135 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 18085.6061 | 0.2 | 0.3 | 28213.5455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6868.6383 | 6868.6383 | 6868.6383 | 6868.6383 | 6868.6383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14136 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 16968.7485 | 0.2 | 0.3 | 26471.2477 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6995.9731 | 6995.9731 | 6995.9731 | 6995.9731 | 6995.9731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14137 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 19248.3963 | 0.2 | 0.3 | 30027.4982 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9739.3795 | 9739.3795 | 9739.3795 | 9739.3795 | 9739.3795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14138 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 20898.8635 | 0.2 | 0.3 | 32602.227 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.8118 | 5203.8118 | 5203.8118 | 5203.8118 | 5203.8118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14139 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 10696.4507 | 0.2 | 0.3 | 16686.4631 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9722.8839 | 9722.8839 | 9722.8839 | 9722.8839 | 9722.8839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14140 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 6920.8089 | 0.2 | 0.3 | 10796.4618 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5113.9083 | 5113.9083 | 5113.9083 | 5113.9083 | 5113.9083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14141 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 17041.7044 | 0.2 | 0.3 | 26585.0589 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5761.9204 | 5761.9204 | 5761.9204 | 5761.9204 | 5761.9204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14142 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 17796.0899 | 0.2 | 0.3 | 27761.9002 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5621.9495 | 5621.9495 | 5621.9495 | 5621.9495 | 5621.9495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14143 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 18866.9997 | 0.2 | 0.3 | 29432.5196 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6610.2627 | 6610.2627 | 6610.2627 | 6610.2627 | 6610.2627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14144 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16560.8904 | 0.2 | 0.3 | 25834.989 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6710.4837 | 6710.4837 | 6710.4837 | 6710.4837 | 6710.4837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14145 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16797.4241 | 0.2 | 0.3 | 26203.9816 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6511.2405 | 6511.2405 | 6511.2405 | 6511.2405 | 6511.2405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14146 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 17397.2439 | 0.2 | 0.3 | 27139.7004 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7036.8603 | 7036.8603 | 7036.8603 | 7036.8603 | 7036.8603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14147 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 879.596 | 0.2 | 0.3 | 1372.1698 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14148 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 16417.5019 | 0.2 | 0.3 | 25611.303 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2823.3846 | 2823.3846 | 2823.3846 | 2823.3846 | 2823.3846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14149 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 16752.598 | 0.2 | 0.3 | 26134.0529 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3983.6129 | 3983.6129 | 3983.6129 | 3983.6129 | 3983.6129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14150 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 18137.3425 | 0.2 | 0.3 | 28294.2542 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9586 | 5201.9586 | 5201.9586 | 5201.9586 | 5201.9586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14151 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 16667.7937 | 0.2 | 0.3 | 26001.7582 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5317.6766 | 5317.6766 | 5317.6766 | 5317.6766 | 5317.6766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14152 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 19452.9884 | 0.2 | 0.3 | 30346.6619 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9785.9198 | 9785.9198 | 9785.9198 | 9785.9198 | 9785.9198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14153 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 3942.901 | 0.2 | 0.3 | 6150.9256 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8341 | 5202.8341 | 5202.8341 | 5202.8341 | 5202.8341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14154 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 407.7273 | 0.2 | 0.3 | 636.0545 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8957.3646 | 8957.3646 | 8957.3646 | 8957.3646 | 8957.3646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14155 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 2319.4967 | 0.2 | 0.3 | 3618.4148 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14156 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 27253.3067 | 0.2 | 0.3 | 42515.1584 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3182 | 5202.3182 | 5202.3182 | 5202.3182 | 5202.3182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14157 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16629.4304 | 0.2 | 0.3 | 25941.9114 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5361.7137 | 5361.7137 | 5361.7137 | 5361.7137 | 5361.7137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14158 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 16285.3425 | 0.2 | 0.3 | 25405.1344 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4957 | 5200.4957 | 5200.4957 | 5200.4957 | 5200.4957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14159 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 17248.96 | 0.2 | 0.3 | 26908.3776 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5214.9825 | 5214.9825 | 5214.9825 | 5214.9825 | 5214.9825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14160 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 13522.706 | 0.2 | 0.3 | 21095.4214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 591.1707 | 591.1707 | 591.1707 | 591.1707 | 591.1707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14161 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 16663.9337 | 0.2 | 0.3 | 25995.7365 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6478.1387 | 6478.1387 | 6478.1387 | 6478.1387 | 6478.1387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14162 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 13345.1611 | 0.2 | 0.3 | 20818.4513 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6563.4146 | 6563.4146 | 6563.4146 | 6563.4146 | 6563.4146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14163 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 14279.4985 | 0.2 | 0.3 | 22276.0176 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6771.464 | 6771.464 | 6771.464 | 6771.464 | 6771.464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14164 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 21925.9032 | 0.2 | 0.3 | 34204.409 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7279.8776 | 7279.8776 | 7279.8776 | 7279.8776 | 7279.8776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14165 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 5328.9419 | 0.2 | 0.3 | 8313.1493 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6676.5567 | 6676.5567 | 6676.5567 | 6676.5567 | 6676.5567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14166 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 9233.6184 | 0.2 | 0.3 | 14404.4447 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14167 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 25415.6605 | 0.2 | 0.3 | 39648.4304 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9415 | 5202.9415 | 5202.9415 | 5202.9415 | 5202.9415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14168 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 28726.0075 | 0.2 | 0.3 | 44812.5716 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8339.7181 | 8339.7181 | 8339.7181 | 8339.7181 | 8339.7181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14169 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 28112.9105 | 0.2 | 0.3 | 43856.1404 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5218.6861 | 5218.6861 | 5218.6861 | 5218.6861 | 5218.6861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14170 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17574.9225 | 0.2 | 0.3 | 27416.879 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9795.7584 | 9795.7584 | 9795.7584 | 9795.7584 | 9795.7584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14171 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 13109.7971 | 0.2 | 0.3 | 20451.2834 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3602 | 5203.3602 | 5203.3602 | 5203.3602 | 5203.3602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14172 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 19759.0981 | 0.2 | 0.3 | 30824.1931 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7494 | 5201.7494 | 5201.7494 | 5201.7494 | 5201.7494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14173 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17197.3354 | 0.2 | 0.3 | 26827.8432 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5501.6004 | 5501.6004 | 5501.6004 | 5501.6004 | 5501.6004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14174 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 15915.1211 | 0.2 | 0.3 | 24827.589 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4611.8925 | 4611.8925 | 4611.8925 | 4611.8925 | 4611.8925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14175 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17541.7405 | 0.2 | 0.3 | 27365.1152 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4504.983 | 4504.983 | 4504.983 | 4504.983 | 4504.983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14176 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 11153.2435 | 0.2 | 0.3 | 17399.0598 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5387.1809 | 5387.1809 | 5387.1809 | 5387.1809 | 5387.1809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14177 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 3993.1843 | 0.2 | 0.3 | 6229.3675 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3839.9907 | 3839.9907 | 3839.9907 | 3839.9907 | 3839.9907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14178 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16668.637 | 0.2 | 0.3 | 26003.0737 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.087 | 5202.087 | 5202.087 | 5202.087 | 5202.087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14179 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16668.9333 | 0.2 | 0.3 | 26003.5359 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8547 | 5202.8547 | 5202.8547 | 5202.8547 | 5202.8547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14180 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 17761.9864 | 0.2 | 0.3 | 27708.6988 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.469 | 5201.469 | 5201.469 | 5201.469 | 5201.469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14181 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 32048.5343 | 0.2 | 0.3 | 49995.7136 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5221.0931 | 5221.0931 | 5221.0931 | 5221.0931 | 5221.0931 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14182 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 17124.7589 | 0.2 | 0.3 | 26714.6238 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.218 | 5203.218 | 5203.218 | 5203.218 | 5203.218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14183 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16910.8988 | 0.2 | 0.3 | 26381.0021 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14184 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 15045.045 | 0.2 | 0.3 | 23470.2702 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14185 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 3695.0913 | 0.2 | 0.3 | 5764.3424 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6.4523 | 6.4523 | 6.4523 | 6.4523 | 6.4523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14186 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16632.9715 | 0.2 | 0.3 | 25947.4356 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10407.4319 | 10407.4319 | 10407.4319 | 10407.4319 | 10407.4319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14187 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 26852.7502 | 0.2 | 0.3 | 41890.2903 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7154.252 | 7154.252 | 7154.252 | 7154.252 | 7154.252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14188 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 23027.0859 | 0.2 | 0.3 | 35922.254 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14189 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14190 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16819.9311 | 0.2 | 0.3 | 26239.0926 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14191 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 17375.8795 | 0.2 | 0.3 | 27106.3721 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14192 | COCONUT CREEK | 10613 | Private | 2036 | 5 | Swales | 66.6667 | 22821.3648 | 0.2 | 0.3 | 35601.3291 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9072.97 | 9072.97 | 9072.97 | 9072.97 | 9072.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14193 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 23597.3031 | 0.2 | 0.3 | 36811.7929 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14194 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 16602.1604 | 0.2 | 0.3 | 25899.3702 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6376.2287 | 6376.2287 | 6376.2287 | 6376.2287 | 6376.2287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14195 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 25326.9863 | 0.2 | 0.3 | 39510.0987 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6878 | 5201.6878 | 5201.6878 | 5201.6878 | 5201.6878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14196 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 13.8257 | 0.2 | 0.3 | 21.5681 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14197 | CORAL SPRINGS | 10612 | Private | 2033 | 5 | Swales | 66.6667 | 3261.1635 | 0.2 | 0.3 | 5087.4151 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14198 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 212.6543 | 0.2 | 0.3 | 331.7408 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7321 | 5201.7321 | 5201.7321 | 5201.7321 | 5201.7321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14199 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 11493.5573 | 0.2 | 0.3 | 17929.9494 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6718.6534 | 6718.6534 | 6718.6534 | 6718.6534 | 6718.6534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14200 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 8552.3505 | 0.2 | 0.3 | 13341.6667 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5197.7245 | 5197.7245 | 5197.7245 | 5197.7245 | 5197.7245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14201 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16668.1618 | 0.2 | 0.3 | 26002.3324 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0911 | 5202.0911 | 5202.0911 | 5202.0911 | 5202.0911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14202 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16985.0607 | 0.2 | 0.3 | 26496.6946 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9782.3522 | 9782.3522 | 9782.3522 | 9782.3522 | 9782.3522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14203 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 860.7023 | 0.2 | 0.3 | 1342.6955 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14204 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 683.3491 | 0.2 | 0.3 | 1066.0245 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9246.3884 | 9246.3884 | 9246.3884 | 9246.3884 | 9246.3884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14205 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 6106.8509 | 0.2 | 0.3 | 9526.6874 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 446.7156 | 446.7156 | 446.7156 | 446.7156 | 446.7156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14206 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 17284.8566 | 0.2 | 0.3 | 26964.3763 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5934.7722 | 5934.7722 | 5934.7722 | 5934.7722 | 5934.7722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14207 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 14639.4147 | 0.2 | 0.3 | 22837.487 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9518 | 5201.9518 | 5201.9518 | 5201.9518 | 5201.9518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14208 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 16668.8053 | 0.2 | 0.3 | 26003.3363 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9569 | 5202.9569 | 5202.9569 | 5202.9569 | 5202.9569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14209 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 16667.2706 | 0.2 | 0.3 | 26000.9421 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6143.7007 | 6143.7007 | 6143.7007 | 6143.7007 | 6143.7007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14210 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 16666.7418 | 0.2 | 0.3 | 26000.1172 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5679.3618 | 5679.3618 | 5679.3618 | 5679.3618 | 5679.3618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14211 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 16764.2891 | 0.2 | 0.3 | 26152.291 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6210.9177 | 6210.9177 | 6210.9177 | 6210.9177 | 6210.9177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14212 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 13983.8373 | 0.2 | 0.3 | 21814.7862 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.8191 | 2600.8191 | 2600.8191 | 2600.8191 | 2600.8191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14213 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 8240.1356 | 0.2 | 0.3 | 12854.6115 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3199.3346 | 3199.3346 | 3199.3346 | 3199.3346 | 3199.3346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14214 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 20819.0607 | 0.2 | 0.3 | 32477.7346 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5151.676 | 5151.676 | 5151.676 | 5151.676 | 5151.676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14215 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 4190.2831 | 0.2 | 0.3 | 6536.8416 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5491.6243 | 5491.6243 | 5491.6243 | 5491.6243 | 5491.6243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14216 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 17455.0104 | 0.2 | 0.3 | 27229.8162 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4.1788 | 4.1788 | 4.1788 | 4.1788 | 4.1788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14217 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 21449.5027 | 0.2 | 0.3 | 33461.2242 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2511 | 5202.2511 | 5202.2511 | 5202.2511 | 5202.2511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14218 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 12274.1097 | 0.2 | 0.3 | 19147.6111 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.231 | 5201.231 | 5201.231 | 5201.231 | 5201.231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14219 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 17820.5443 | 0.2 | 0.3 | 27800.0492 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7787.1417 | 7787.1417 | 7787.1417 | 7787.1417 | 7787.1417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14220 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16426.3985 | 0.2 | 0.3 | 25625.1816 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7659.0831 | 7659.0831 | 7659.0831 | 7659.0831 | 7659.0831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14221 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7206.1327 | 7206.1327 | 7206.1327 | 7206.1327 | 7206.1327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14222 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 14896.5099 | 0.2 | 0.3 | 23238.5554 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9858.6668 | 9858.6668 | 9858.6668 | 9858.6668 | 9858.6668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14223 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 20090.1713 | 0.2 | 0.3 | 31340.6672 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14224 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16647.1825 | 0.2 | 0.3 | 25969.6046 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8772.7013 | 8772.7013 | 8772.7013 | 8772.7013 | 8772.7013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14225 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 548.4913 | 0.2 | 0.3 | 855.6464 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.8417 | 2600.8417 | 2600.8417 | 2600.8417 | 2600.8417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14226 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 15724.2684 | 0.2 | 0.3 | 24529.8587 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2002.5511 | 2002.5511 | 2002.5511 | 2002.5511 | 2002.5511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14227 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 12741.633 | 0.2 | 0.3 | 19876.9475 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 50.3381 | 50.3381 | 50.3381 | 50.3381 | 50.3381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14228 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 8269.8463 | 0.2 | 0.3 | 12900.9602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4882 | 5202.4882 | 5202.4882 | 5202.4882 | 5202.4882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14229 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 17464.3877 | 0.2 | 0.3 | 27244.4449 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14230 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 11823.9671 | 0.2 | 0.3 | 18445.3886 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14231 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 25306.5156 | 0.2 | 0.3 | 39478.1643 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9120.0238 | 9120.0238 | 9120.0238 | 9120.0238 | 9120.0238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14232 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 14155.5241 | 0.2 | 0.3 | 22082.6175 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9470.514 | 9470.514 | 9470.514 | 9470.514 | 9470.514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14233 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 13994.538 | 0.2 | 0.3 | 21831.4793 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9783.5243 | 9783.5243 | 9783.5243 | 9783.5243 | 9783.5243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14234 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 782.6791 | 0.2 | 0.3 | 1220.9794 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14235 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 26268.1902 | 0.2 | 0.3 | 40978.3767 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8756.5269 | 8756.5269 | 8756.5269 | 8756.5269 | 8756.5269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14236 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 14440.1059 | 0.2 | 0.3 | 22526.5653 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2054 | 5202.2054 | 5202.2054 | 5202.2054 | 5202.2054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14237 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17230.4491 | 0.2 | 0.3 | 26879.5006 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14238 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 7791.3741 | 0.2 | 0.3 | 12154.5436 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3755 | 5202.3755 | 5202.3755 | 5202.3755 | 5202.3755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14239 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 27416.9513 | 0.2 | 0.3 | 42770.444 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3203 | 5201.3203 | 5201.3203 | 5201.3203 | 5201.3203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14240 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 30539.1991 | 0.2 | 0.3 | 47641.1505 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1960.5167 | 1960.5167 | 1960.5167 | 1960.5167 | 1960.5167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14241 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 15820.1866 | 0.2 | 0.3 | 24679.4911 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3103.6086 | 3103.6086 | 3103.6086 | 3103.6086 | 3103.6086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14242 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2066.2247 | 2066.2247 | 2066.2247 | 2066.2247 | 2066.2247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14243 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 5887.9021 | 0.2 | 0.3 | 9185.1273 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.87 | 5203.87 | 5203.87 | 5203.87 | 5203.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14244 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16691.7571 | 0.2 | 0.3 | 26039.141 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5354.5465 | 5354.5465 | 5354.5465 | 5354.5465 | 5354.5465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14245 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 15578.1677 | 0.2 | 0.3 | 24301.9417 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14246 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 28601.2112 | 0.2 | 0.3 | 44617.8895 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6210.4079 | 6210.4079 | 6210.4079 | 6210.4079 | 6210.4079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14247 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 30265.3658 | 0.2 | 0.3 | 47213.9706 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2079.1637 | 2079.1637 | 2079.1637 | 2079.1637 | 2079.1637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14248 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 17351.4059 | 0.2 | 0.3 | 27068.1933 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2103.7082 | 2103.7082 | 2103.7082 | 2103.7082 | 2103.7082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14249 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 20428.6856 | 0.2 | 0.3 | 31868.7495 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1566 | 5203.1566 | 5203.1566 | 5203.1566 | 5203.1566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14250 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 21927.0862 | 0.2 | 0.3 | 34206.2545 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5219 | 5202.5219 | 5202.5219 | 5202.5219 | 5202.5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14251 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 31338.4778 | 0.2 | 0.3 | 48888.0254 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5993.1756 | 5993.1756 | 5993.1756 | 5993.1756 | 5993.1756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14252 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 15051.4449 | 0.2 | 0.3 | 23480.2541 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8649 | 5200.8649 | 5200.8649 | 5200.8649 | 5200.8649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14253 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 20905.13 | 0.2 | 0.3 | 32612.0028 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9466.444 | 9466.444 | 9466.444 | 9466.444 | 9466.444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14254 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2056 | 5202.2056 | 5202.2056 | 5202.2056 | 5202.2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14255 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 26642.3079 | 0.2 | 0.3 | 41562.0004 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3126.3835 | 3126.3835 | 3126.3835 | 3126.3835 | 3126.3835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14256 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 34672.4858 | 0.2 | 0.3 | 54089.0778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5120.8565 | 5120.8565 | 5120.8565 | 5120.8565 | 5120.8565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14257 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 17726.7694 | 0.2 | 0.3 | 27653.7603 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3309.2494 | 3309.2494 | 3309.2494 | 3309.2494 | 3309.2494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14258 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16998.4459 | 0.2 | 0.3 | 26517.5757 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3500.9303 | 3500.9303 | 3500.9303 | 3500.9303 | 3500.9303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14259 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 18134.7861 | 0.2 | 0.3 | 28290.2663 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8070.6071 | 8070.6071 | 8070.6071 | 8070.6071 | 8070.6071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14260 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 38743.4794 | 0.2 | 0.3 | 60439.8279 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8384.0312 | 8384.0312 | 8384.0312 | 8384.0312 | 8384.0312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14261 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 35862.6142 | 0.2 | 0.3 | 55945.6782 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5218.396 | 5218.396 | 5218.396 | 5218.396 | 5218.396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14262 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 25014.3512 | 0.2 | 0.3 | 39022.3879 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5791.5699 | 5791.5699 | 5791.5699 | 5791.5699 | 5791.5699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14263 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 28964.9936 | 0.2 | 0.3 | 45185.39 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3099 | 5201.3099 | 5201.3099 | 5201.3099 | 5201.3099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14264 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 31855.4851 | 0.2 | 0.3 | 49694.5567 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14265 | COCONUT CREEK | 10613 | Public | 2036 | 5 | Swales | 66.6667 | 20119.852 | 0.2 | 0.3 | 31386.9691 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6719.1918 | 6719.1918 | 6719.1918 | 6719.1918 | 6719.1918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14266 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 24076.1475 | 0.2 | 0.3 | 37558.79 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5035.1785 | 5035.1785 | 5035.1785 | 5035.1785 | 5035.1785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14267 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 19259.7408 | 0.2 | 0.3 | 30045.1956 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1701.7028 | 1701.7028 | 1701.7028 | 1701.7028 | 1701.7028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14268 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16962.4006 | 0.2 | 0.3 | 26461.3449 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4687 | 5202.4687 | 5202.4687 | 5202.4687 | 5202.4687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14269 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16903.0619 | 0.2 | 0.3 | 26368.7765 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8623.1802 | 8623.1802 | 8623.1802 | 8623.1802 | 8623.1802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14270 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 15421.4533 | 0.2 | 0.3 | 24057.4672 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14271 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 6819.4387 | 0.2 | 0.3 | 10638.3244 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6031.4667 | 6031.4667 | 6031.4667 | 6031.4667 | 6031.4667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14272 | CORAL SPRINGS | 10612 | Public | 2036 | 5 | Swales | 66.6667 | 30852.5372 | 0.2 | 0.3 | 48129.958 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8193.4503 | 8193.4503 | 8193.4503 | 8193.4503 | 8193.4503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14273 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 17332.0625 | 0.2 | 0.3 | 27038.0174 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0292 | 5201.0292 | 5201.0292 | 5201.0292 | 5201.0292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14274 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 17034.6382 | 0.2 | 0.3 | 26574.0356 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14275 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 3250.1441 | 0.2 | 0.3 | 5070.2248 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7104.9653 | 7104.9653 | 7104.9653 | 7104.9653 | 7104.9653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14276 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 11674.4037 | 0.2 | 0.3 | 18212.0698 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7878.4124 | 7878.4124 | 7878.4124 | 7878.4124 | 7878.4124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14277 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 10858.2235 | 0.2 | 0.3 | 16938.8286 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6323 | 5202.6323 | 5202.6323 | 5202.6323 | 5202.6323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14278 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 22967.5051 | 0.2 | 0.3 | 35829.3079 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9592.5137 | 9592.5137 | 9592.5137 | 9592.5137 | 9592.5137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14279 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 25136.2581 | 0.2 | 0.3 | 39212.5626 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.0671 | 2600.0671 | 2600.0671 | 2600.0671 | 2600.0671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14280 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 18055.0635 | 0.2 | 0.3 | 28165.8991 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9100.5388 | 9100.5388 | 9100.5388 | 9100.5388 | 9100.5388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14281 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 7277.2307 | 0.2 | 0.3 | 11352.4799 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5373.1082 | 5373.1082 | 5373.1082 | 5373.1082 | 5373.1082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14282 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 11394.0805 | 0.2 | 0.3 | 17774.7655 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5420.1117 | 5420.1117 | 5420.1117 | 5420.1117 | 5420.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14283 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 22742.4033 | 0.2 | 0.3 | 35478.1491 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14284 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 2594.6379 | 0.2 | 0.3 | 4047.6351 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3722.3366 | 3722.3366 | 3722.3366 | 3722.3366 | 3722.3366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14285 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 31271.7508 | 0.2 | 0.3 | 48783.9312 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14286 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 17405.6885 | 0.2 | 0.3 | 27152.8741 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5240.7955 | 5240.7955 | 5240.7955 | 5240.7955 | 5240.7955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14287 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 13119.2599 | 0.2 | 0.3 | 20466.0454 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9741.8753 | 9741.8753 | 9741.8753 | 9741.8753 | 9741.8753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14288 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 8334.3936 | 0.2 | 0.3 | 13001.654 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7028.6148 | 7028.6148 | 7028.6148 | 7028.6148 | 7028.6148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14289 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 11573.5529 | 0.2 | 0.3 | 18054.7425 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14290 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16502.7574 | 0.2 | 0.3 | 25744.3015 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7801.4189 | 7801.4189 | 7801.4189 | 7801.4189 | 7801.4189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14291 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1911.9284 | 1911.9284 | 1911.9284 | 1911.9284 | 1911.9284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14292 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16669.2712 | 0.2 | 0.3 | 26004.0631 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14293 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 4969.4049 | 0.2 | 0.3 | 7752.2717 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4203.5768 | 4203.5768 | 4203.5768 | 4203.5768 | 4203.5768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14294 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 3620.0611 | 0.2 | 0.3 | 5647.2953 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2630.115 | 2630.115 | 2630.115 | 2630.115 | 2630.115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14295 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 28979.9335 | 0.2 | 0.3 | 45208.6963 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4940.5412 | 4940.5412 | 4940.5412 | 4940.5412 | 4940.5412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14296 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 18038.4393 | 0.2 | 0.3 | 28139.9654 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6446.7661 | 6446.7661 | 6446.7661 | 6446.7661 | 6446.7661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14297 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2753 | 0.2 | 0.3 | 26002.5094 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7567 | 5201.7567 | 5201.7567 | 5201.7567 | 5201.7567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14298 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16666.9976 | 0.2 | 0.3 | 26000.5163 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1837 | 5202.1837 | 5202.1837 | 5202.1837 | 5202.1837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14299 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 29534.4789 | 0.2 | 0.3 | 46073.787 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9787 | 5202.9787 | 5202.9787 | 5202.9787 | 5202.9787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14300 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 24029.0329 | 0.2 | 0.3 | 37485.2914 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14301 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 17693.3153 | 0.2 | 0.3 | 27601.5719 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9225 | 5202.9225 | 5202.9225 | 5202.9225 | 5202.9225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14302 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 11174.8495 | 0.2 | 0.3 | 17432.7652 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9780.1263 | 9780.1263 | 9780.1263 | 9780.1263 | 9780.1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14303 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 19123.1745 | 0.2 | 0.3 | 29832.1522 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7822.581 | 7822.581 | 7822.581 | 7822.581 | 7822.581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14304 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 17130.4163 | 0.2 | 0.3 | 26723.4495 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9538.0912 | 9538.0912 | 9538.0912 | 9538.0912 | 9538.0912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14305 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 19747.4425 | 0.2 | 0.3 | 30806.0104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9574 | 5201.9574 | 5201.9574 | 5201.9574 | 5201.9574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14306 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16667.4626 | 0.2 | 0.3 | 26001.2417 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2573.732 | 2573.732 | 2573.732 | 2573.732 | 2573.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14307 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16672.0379 | 0.2 | 0.3 | 26008.3792 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6185.0288 | 6185.0288 | 6185.0288 | 6185.0288 | 6185.0288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14308 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 19633.1543 | 0.2 | 0.3 | 30627.7207 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 832.0186 | 832.0186 | 832.0186 | 832.0186 | 832.0186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14309 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 13805.2783 | 0.2 | 0.3 | 21536.2342 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2364.4706 | 2364.4706 | 2364.4706 | 2364.4706 | 2364.4706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14310 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16667.3437 | 0.2 | 0.3 | 26001.0562 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5150.6012 | 5150.6012 | 5150.6012 | 5150.6012 | 5150.6012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14311 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 6932.0368 | 0.2 | 0.3 | 10813.9774 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14312 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 25814.0485 | 0.2 | 0.3 | 40269.9156 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14313 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2404 | 0.2 | 0.3 | 26002.455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2995 | 5201.2995 | 5201.2995 | 5201.2995 | 5201.2995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14314 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 29018.065 | 0.2 | 0.3 | 45268.1814 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14315 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16595.8343 | 0.2 | 0.3 | 25889.5016 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14316 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 19054.075 | 0.2 | 0.3 | 29724.357 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4555 | 5201.4555 | 5201.4555 | 5201.4555 | 5201.4555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14317 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 1035.8083 | 0.2 | 0.3 | 1615.861 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7323.0628 | 7323.0628 | 7323.0628 | 7323.0628 | 7323.0628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14318 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 9499.3028 | 0.2 | 0.3 | 14818.9124 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10637.9309 | 10637.9309 | 10637.9309 | 10637.9309 | 10637.9309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14319 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 23050.9903 | 0.2 | 0.3 | 35959.5448 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8027.5131 | 8027.5131 | 8027.5131 | 8027.5131 | 8027.5131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14320 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 21181.1382 | 0.2 | 0.3 | 33042.5756 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14321 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 13549.8971 | 0.2 | 0.3 | 21137.8394 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6968.3011 | 6968.3011 | 6968.3011 | 6968.3011 | 6968.3011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14322 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 15939.6855 | 0.2 | 0.3 | 24865.9093 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6022.1391 | 6022.1391 | 6022.1391 | 6022.1391 | 6022.1391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14323 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 25416.9254 | 0.2 | 0.3 | 39650.4036 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5247.9897 | 5247.9897 | 5247.9897 | 5247.9897 | 5247.9897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14324 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6650.5144 | 6650.5144 | 6650.5144 | 6650.5144 | 6650.5144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14325 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 26560.564 | 0.2 | 0.3 | 41434.4798 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3673 | 5200.3673 | 5200.3673 | 5200.3673 | 5200.3673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14326 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 17457.5595 | 0.2 | 0.3 | 27233.7929 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2096 | 5201.2096 | 5201.2096 | 5201.2096 | 5201.2096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14327 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16314.6701 | 0.2 | 0.3 | 25450.8853 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4707 | 5202.4707 | 5202.4707 | 5202.4707 | 5202.4707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14328 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 11848.1012 | 0.2 | 0.3 | 18483.0379 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4797 | 5202.4797 | 5202.4797 | 5202.4797 | 5202.4797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14329 | COCONUT CREEK | 10606 | Public | 2036 | 5 | Swales | 66.6667 | 12565.7351 | 0.2 | 0.3 | 19602.5468 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 213.2369 | 213.2369 | 213.2369 | 213.2369 | 213.2369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14330 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 16840.1832 | 0.2 | 0.3 | 26270.6858 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9383.5371 | 9383.5371 | 9383.5371 | 9383.5371 | 9383.5371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14331 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 24954.3693 | 0.2 | 0.3 | 38928.8162 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14332 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 28407.1854 | 0.2 | 0.3 | 44315.2092 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.6261 | 5203.6261 | 5203.6261 | 5203.6261 | 5203.6261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14333 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 10164.8348 | 0.2 | 0.3 | 15857.1423 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9754.1061 | 9754.1061 | 9754.1061 | 9754.1061 | 9754.1061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14334 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 24698.4678 | 0.2 | 0.3 | 38529.6098 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5540.3653 | 5540.3653 | 5540.3653 | 5540.3653 | 5540.3653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14335 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16672.4803 | 0.2 | 0.3 | 26009.0692 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1357.7319 | 1357.7319 | 1357.7319 | 1357.7319 | 1357.7319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14336 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 18825.4985 | 0.2 | 0.3 | 29367.7777 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7672.3759 | 7672.3759 | 7672.3759 | 7672.3759 | 7672.3759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14337 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 17122.6349 | 0.2 | 0.3 | 26711.3105 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9720.4268 | 9720.4268 | 9720.4268 | 9720.4268 | 9720.4268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14338 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 32555.6381 | 0.2 | 0.3 | 50786.7955 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0747 | 5201.0747 | 5201.0747 | 5201.0747 | 5201.0747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14339 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 29914.1064 | 0.2 | 0.3 | 46666.006 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6078.28 | 6078.28 | 6078.28 | 6078.28 | 6078.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14340 | CORAL SPRINGS | 10612 | Public | 2036 | 5 | Swales | 66.6667 | 30719.8977 | 0.2 | 0.3 | 47923.0405 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 48.4876 | 48.4876 | 48.4876 | 48.4876 | 48.4876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14341 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 26335.0278 | 0.2 | 0.3 | 41082.6434 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1966.0218 | 1966.0218 | 1966.0218 | 1966.0218 | 1966.0218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14342 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 10617.6949 | 0.2 | 0.3 | 16563.6041 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8140.6346 | 8140.6346 | 8140.6346 | 8140.6346 | 8140.6346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14343 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 10582.7957 | 0.2 | 0.3 | 16509.1612 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3355.9457 | 3355.9457 | 3355.9457 | 3355.9457 | 3355.9457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14344 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 9998.2243 | 0.2 | 0.3 | 15597.2299 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5152.0166 | 5152.0166 | 5152.0166 | 5152.0166 | 5152.0166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14345 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 8169.3611 | 0.2 | 0.3 | 12744.2034 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14346 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 10888.7741 | 0.2 | 0.3 | 16986.4876 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4243 | 5201.4243 | 5201.4243 | 5201.4243 | 5201.4243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14347 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 18793.4805 | 0.2 | 0.3 | 29317.8295 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14348 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16678.8688 | 0.2 | 0.3 | 26019.0353 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14349 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 19577.6014 | 0.2 | 0.3 | 30541.0582 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3849 | 5201.3849 | 5201.3849 | 5201.3849 | 5201.3849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14350 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 16802.2319 | 0.2 | 0.3 | 26211.4818 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7302.7779 | 7302.7779 | 7302.7779 | 7302.7779 | 7302.7779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14351 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 11876.6765 | 0.2 | 0.3 | 18527.6154 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8082.6769 | 8082.6769 | 8082.6769 | 8082.6769 | 8082.6769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14352 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 1021.8564 | 0.2 | 0.3 | 1594.096 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6192.3966 | 6192.3966 | 6192.3966 | 6192.3966 | 6192.3966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14353 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 17546.5437 | 0.2 | 0.3 | 27372.6082 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14354 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 1035.1533 | 0.2 | 0.3 | 1614.8392 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3033 | 5200.3033 | 5200.3033 | 5200.3033 | 5200.3033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14355 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 10587.0845 | 0.2 | 0.3 | 16515.8518 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5323.6972 | 5323.6972 | 5323.6972 | 5323.6972 | 5323.6972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14356 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16667.7842 | 0.2 | 0.3 | 26001.7434 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3103 | 5201.3103 | 5201.3103 | 5201.3103 | 5201.3103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14357 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 22062.6734 | 0.2 | 0.3 | 34417.7705 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14358 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 13918.8647 | 0.2 | 0.3 | 21713.4289 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6509 | 5200.6509 | 5200.6509 | 5200.6509 | 5200.6509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14359 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 19655.1278 | 0.2 | 0.3 | 30661.9994 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3354 | 5200.3354 | 5200.3354 | 5200.3354 | 5200.3354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14360 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16667.3981 | 0.2 | 0.3 | 26001.1411 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5248.615 | 5248.615 | 5248.615 | 5248.615 | 5248.615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14361 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 12361.8101 | 0.2 | 0.3 | 19284.4238 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.346 | 5200.346 | 5200.346 | 5200.346 | 5200.346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14362 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 10492.4613 | 0.2 | 0.3 | 16368.2397 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6749.5077 | 6749.5077 | 6749.5077 | 6749.5077 | 6749.5077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14363 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 11085.4963 | 0.2 | 0.3 | 17293.3743 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7805.8624 | 7805.8624 | 7805.8624 | 7805.8624 | 7805.8624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14364 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16671.2479 | 0.2 | 0.3 | 26007.1467 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6001.5422 | 6001.5422 | 6001.5422 | 6001.5422 | 6001.5422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14365 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 21120.5051 | 0.2 | 0.3 | 32947.988 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7527 | 5202.7527 | 5202.7527 | 5202.7527 | 5202.7527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14366 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16666.9204 | 0.2 | 0.3 | 26000.3958 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5818.0629 | 5818.0629 | 5818.0629 | 5818.0629 | 5818.0629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14367 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 23112.9401 | 0.2 | 0.3 | 36056.1865 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9784.4083 | 9784.4083 | 9784.4083 | 9784.4083 | 9784.4083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14368 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 9928.4184 | 0.2 | 0.3 | 15488.3327 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9915.212 | 9915.212 | 9915.212 | 9915.212 | 9915.212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14369 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 17269.5709 | 0.2 | 0.3 | 26940.5306 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7016 | 5200.7016 | 5200.7016 | 5200.7016 | 5200.7016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14370 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 20032.2491 | 0.2 | 0.3 | 31250.3085 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6039.9259 | 6039.9259 | 6039.9259 | 6039.9259 | 6039.9259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14371 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 24884.9209 | 0.2 | 0.3 | 38820.4766 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6854 | 5200.6854 | 5200.6854 | 5200.6854 | 5200.6854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14372 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 20318.0558 | 0.2 | 0.3 | 31696.167 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5286.145 | 5286.145 | 5286.145 | 5286.145 | 5286.145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14373 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17927.2135 | 0.2 | 0.3 | 27966.4531 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9830.7272 | 9830.7272 | 9830.7272 | 9830.7272 | 9830.7272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14374 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16667.2911 | 0.2 | 0.3 | 26000.9742 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.8101 | 9777.8101 | 9777.8101 | 9777.8101 | 9777.8101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14375 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.9824 | 9778.9824 | 9778.9824 | 9778.9824 | 9778.9824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14376 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16645.1347 | 0.2 | 0.3 | 25966.4102 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7689.0106 | 7689.0106 | 7689.0106 | 7689.0106 | 7689.0106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14377 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 25700.3477 | 0.2 | 0.3 | 40092.5425 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0267 | 5204.0267 | 5204.0267 | 5204.0267 | 5204.0267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14378 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 25727.7241 | 0.2 | 0.3 | 40135.2496 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3507 | 5202.3507 | 5202.3507 | 5202.3507 | 5202.3507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14379 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 20886.1245 | 0.2 | 0.3 | 32582.3543 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14380 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 19353.154 | 0.2 | 0.3 | 30190.9202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14381 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 6544.4707 | 0.2 | 0.3 | 10209.3743 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3058 | 5202.3058 | 5202.3058 | 5202.3058 | 5202.3058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14382 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 21603.0281 | 0.2 | 0.3 | 33700.7238 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5153.1753 | 5153.1753 | 5153.1753 | 5153.1753 | 5153.1753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14383 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 8334.1202 | 0.2 | 0.3 | 13001.2275 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3277.8773 | 3277.8773 | 3277.8773 | 3277.8773 | 3277.8773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14384 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 8334.6795 | 0.2 | 0.3 | 13002.1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9312.0465 | 9312.0465 | 9312.0465 | 9312.0465 | 9312.0465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14385 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 26929.4897 | 0.2 | 0.3 | 42010.004 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4496.7167 | 4496.7167 | 4496.7167 | 4496.7167 | 4496.7167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14386 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 112.8625 | 0.2 | 0.3 | 176.0656 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3176.7741 | 3176.7741 | 3176.7741 | 3176.7741 | 3176.7741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14387 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 18142.8349 | 0.2 | 0.3 | 28302.8224 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5091.7829 | 5091.7829 | 5091.7829 | 5091.7829 | 5091.7829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14388 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 13671.5131 | 0.2 | 0.3 | 21327.5605 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3476 | 5201.3476 | 5201.3476 | 5201.3476 | 5201.3476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14389 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 8365.1463 | 0.2 | 0.3 | 13049.6282 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14390 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 12094.3115 | 0.2 | 0.3 | 18867.126 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14391 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16220.4355 | 0.2 | 0.3 | 25303.8794 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3359 | 5201.3359 | 5201.3359 | 5201.3359 | 5201.3359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14392 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 17450.3646 | 0.2 | 0.3 | 27222.5688 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6517.9068 | 6517.9068 | 6517.9068 | 6517.9068 | 6517.9068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14393 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 20737.9235 | 0.2 | 0.3 | 32351.1606 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8947.0173 | 8947.0173 | 8947.0173 | 8947.0173 | 8947.0173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14394 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 29807.5986 | 0.2 | 0.3 | 46499.8538 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7804.6983 | 7804.6983 | 7804.6983 | 7804.6983 | 7804.6983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14395 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 17461.8151 | 0.2 | 0.3 | 27240.4316 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14396 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 37852.2427 | 0.2 | 0.3 | 59049.4987 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14397 | COCONUT CREEK | 10606 | Public | 2036 | 5 | Swales | 66.6667 | 16096.8571 | 0.2 | 0.3 | 25111.097 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.0923 | 9777.0923 | 9777.0923 | 9777.0923 | 9777.0923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14398 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 31853.7665 | 0.2 | 0.3 | 49691.8758 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3556 | 5200.3556 | 5200.3556 | 5200.3556 | 5200.3556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14399 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 16672.0823 | 0.2 | 0.3 | 26008.4483 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.272 | 9777.272 | 9777.272 | 9777.272 | 9777.272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14400 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 17017.0707 | 0.2 | 0.3 | 26546.6303 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6131.7791 | 6131.7791 | 6131.7791 | 6131.7791 | 6131.7791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14401 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 19306.3144 | 0.2 | 0.3 | 30117.8505 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1493.3871 | 1493.3871 | 1493.3871 | 1493.3871 | 1493.3871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14402 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 21104.8728 | 0.2 | 0.3 | 32923.6016 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.5607 | 5205.5607 | 5205.5607 | 5205.5607 | 5205.5607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14403 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 23789.7674 | 0.2 | 0.3 | 37112.0371 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8014.3742 | 8014.3742 | 8014.3742 | 8014.3742 | 8014.3742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14404 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7009.8274 | 7009.8274 | 7009.8274 | 7009.8274 | 7009.8274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14405 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16666.4579 | 0.2 | 0.3 | 25999.6743 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8395.9115 | 8395.9115 | 8395.9115 | 8395.9115 | 8395.9115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14406 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16927.3717 | 0.2 | 0.3 | 26406.6999 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2598.6198 | 2598.6198 | 2598.6198 | 2598.6198 | 2598.6198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14407 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 23525.5082 | 0.2 | 0.3 | 36699.7928 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5342.4562 | 5342.4562 | 5342.4562 | 5342.4562 | 5342.4562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14408 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 14384.6406 | 0.2 | 0.3 | 22440.0393 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8039 | 5201.8039 | 5201.8039 | 5201.8039 | 5201.8039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14409 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 21312.7333 | 0.2 | 0.3 | 33247.864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5398.7096 | 5398.7096 | 5398.7096 | 5398.7096 | 5398.7096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14410 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 1506.6641 | 0.2 | 0.3 | 2350.3959 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7328.7498 | 7328.7498 | 7328.7498 | 7328.7498 | 7328.7498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14411 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 19592.6805 | 0.2 | 0.3 | 30564.5815 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5783.1664 | 5783.1664 | 5783.1664 | 5783.1664 | 5783.1664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14412 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 11199.5651 | 0.2 | 0.3 | 17471.3216 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2964.751 | 2964.751 | 2964.751 | 2964.751 | 2964.751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14413 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 1255.0889 | 0.2 | 0.3 | 1957.9387 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9620.534 | 9620.534 | 9620.534 | 9620.534 | 9620.534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14414 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 17092.8468 | 0.2 | 0.3 | 26664.841 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8644 | 5201.8644 | 5201.8644 | 5201.8644 | 5201.8644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14415 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 10094.9444 | 0.2 | 0.3 | 15748.1133 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0278 | 5202.0278 | 5202.0278 | 5202.0278 | 5202.0278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14416 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 18927.0779 | 0.2 | 0.3 | 29526.2416 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.2481 | 9778.2481 | 9778.2481 | 9778.2481 | 9778.2481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14417 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 29938.4408 | 0.2 | 0.3 | 46703.9676 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8354.9131 | 8354.9131 | 8354.9131 | 8354.9131 | 8354.9131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14418 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16667.2871 | 0.2 | 0.3 | 26000.9678 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8088.7401 | 8088.7401 | 8088.7401 | 8088.7401 | 8088.7401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14419 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 8821.9517 | 0.2 | 0.3 | 13762.2447 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9417.0199 | 9417.0199 | 9417.0199 | 9417.0199 | 9417.0199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14420 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 6034.6773 | 0.2 | 0.3 | 9414.0965 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1465.5032 | 1465.5032 | 1465.5032 | 1465.5032 | 1465.5032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14421 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 29531.4821 | 0.2 | 0.3 | 46069.1121 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7115 | 5201.7115 | 5201.7115 | 5201.7115 | 5201.7115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14422 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1212 | 0.2 | 0.3 | 26000.7091 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5159.5737 | 5159.5737 | 5159.5737 | 5159.5737 | 5159.5737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14423 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 23109.9409 | 0.2 | 0.3 | 36051.5079 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8191.4152 | 8191.4152 | 8191.4152 | 8191.4152 | 8191.4152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14424 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 1487.8518 | 0.2 | 0.3 | 2321.0488 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4810.3957 | 4810.3957 | 4810.3957 | 4810.3957 | 4810.3957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14425 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 25421.0287 | 0.2 | 0.3 | 39656.8047 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4674.6505 | 4674.6505 | 4674.6505 | 4674.6505 | 4674.6505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14426 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 23470.4159 | 0.2 | 0.3 | 36613.8489 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3301.8538 | 3301.8538 | 3301.8538 | 3301.8538 | 3301.8538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14427 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 15246.9456 | 0.2 | 0.3 | 23785.2351 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5098.7536 | 5098.7536 | 5098.7536 | 5098.7536 | 5098.7536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14428 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 31141.5238 | 0.2 | 0.3 | 48580.7771 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14429 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16606.5397 | 0.2 | 0.3 | 25906.202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14430 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 23622.5351 | 0.2 | 0.3 | 36851.1548 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5155 | 5201.5155 | 5201.5155 | 5201.5155 | 5201.5155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14431 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 13398.1115 | 0.2 | 0.3 | 20901.0539 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5874.8976 | 5874.8976 | 5874.8976 | 5874.8976 | 5874.8976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14432 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 0.1326 | 0.2 | 0.3 | 0.20686 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9629.6719 | 9629.6719 | 9629.6719 | 9629.6719 | 9629.6719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14433 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 18301.9763 | 0.2 | 0.3 | 28551.0831 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14434 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 6771.516 | 0.2 | 0.3 | 10563.565 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7499 | 5201.7499 | 5201.7499 | 5201.7499 | 5201.7499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14435 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16679.8583 | 0.2 | 0.3 | 26020.5789 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.205 | 5201.205 | 5201.205 | 5201.205 | 5201.205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14436 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 5239.2497 | 0.2 | 0.3 | 8173.2295 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.4061 | 5204.4061 | 5204.4061 | 5204.4061 | 5204.4061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14437 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 8333.8468 | 0.2 | 0.3 | 13000.801 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8318 | 5201.8318 | 5201.8318 | 5201.8318 | 5201.8318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14438 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 8334.1322 | 0.2 | 0.3 | 13001.2462 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5227 | 5201.5227 | 5201.5227 | 5201.5227 | 5201.5227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14439 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 5704.4003 | 0.2 | 0.3 | 8898.8645 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14440 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 11653.6151 | 0.2 | 0.3 | 18179.6396 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14441 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 31810.0364 | 0.2 | 0.3 | 49623.6568 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3493.5778 | 3493.5778 | 3493.5778 | 3493.5778 | 3493.5778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14442 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 5460.0035 | 0.2 | 0.3 | 8517.6054 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7294.7639 | 7294.7639 | 7294.7639 | 7294.7639 | 7294.7639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14443 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 1888.6759 | 0.2 | 0.3 | 2946.3345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13564.1818 | 13564.1818 | 13564.1818 | 13564.1818 | 13564.1818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14444 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 33060.7819 | 0.2 | 0.3 | 51574.8197 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10421.0282 | 10421.0282 | 10421.0282 | 10421.0282 | 10421.0282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14445 | COCONUT CREEK | 10606 | Public | 2036 | 5 | Swales | 66.6667 | 16667.8419 | 0.2 | 0.3 | 26001.8333 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14393.3455 | 14393.3455 | 14393.3455 | 14393.3455 | 14393.3455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14446 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 23481.9791 | 0.2 | 0.3 | 36631.8873 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12113.0912 | 12113.0912 | 12113.0912 | 12113.0912 | 12113.0912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14447 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 16525.1262 | 0.2 | 0.3 | 25779.1969 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2852.8359 | 2852.8359 | 2852.8359 | 2852.8359 | 2852.8359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14448 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 16665.5775 | 0.2 | 0.3 | 25998.3008 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 611.4379 | 611.4379 | 611.4379 | 611.4379 | 611.4379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14449 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 23055.0107 | 0.2 | 0.3 | 35965.8167 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2237.0333 | 2237.0333 | 2237.0333 | 2237.0333 | 2237.0333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14450 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 16596.3356 | 0.2 | 0.3 | 25890.2835 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5383.0398 | 5383.0398 | 5383.0398 | 5383.0398 | 5383.0398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14451 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9759.9435 | 9759.9435 | 9759.9435 | 9759.9435 | 9759.9435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14452 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16726.6676 | 0.2 | 0.3 | 26093.6015 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2115 | 5201.2115 | 5201.2115 | 5201.2115 | 5201.2115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14453 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16785.3668 | 0.2 | 0.3 | 26185.1722 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9551.8156 | 9551.8156 | 9551.8156 | 9551.8156 | 9551.8156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14454 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 15142.9627 | 0.2 | 0.3 | 23623.0218 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2991.4168 | 2991.4168 | 2991.4168 | 2991.4168 | 2991.4168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14455 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 5184.4325 | 0.2 | 0.3 | 8087.7148 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3142.6041 | 3142.6041 | 3142.6041 | 3142.6041 | 3142.6041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14456 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 1466.5816 | 0.2 | 0.3 | 2287.8673 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4458.0376 | 4458.0376 | 4458.0376 | 4458.0376 | 4458.0376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14457 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 27945.8501 | 0.2 | 0.3 | 43595.5262 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2703.179 | 2703.179 | 2703.179 | 2703.179 | 2703.179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14458 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 9151.7102 | 0.2 | 0.3 | 14276.6679 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14459 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 19611.7689 | 0.2 | 0.3 | 30594.3594 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14460 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16249.3665 | 0.2 | 0.3 | 25349.0117 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7047 | 5201.7047 | 5201.7047 | 5201.7047 | 5201.7047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14461 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 29800.5445 | 0.2 | 0.3 | 46488.8495 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9224.0653 | 9224.0653 | 9224.0653 | 9224.0653 | 9224.0653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14462 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 18654.4517 | 0.2 | 0.3 | 29100.9446 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6330.9779 | 6330.9779 | 6330.9779 | 6330.9779 | 6330.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14463 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 9702.5788 | 0.2 | 0.3 | 15136.0229 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6453 | 5201.6453 | 5201.6453 | 5201.6453 | 5201.6453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14464 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 15485.9791 | 0.2 | 0.3 | 24158.1273 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0233 | 5201.0233 | 5201.0233 | 5201.0233 | 5201.0233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14465 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 4645.1507 | 0.2 | 0.3 | 7246.435 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5521.4415 | 5521.4415 | 5521.4415 | 5521.4415 | 5521.4415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14466 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 17613.4079 | 0.2 | 0.3 | 27476.9164 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5854 | 5201.5854 | 5201.5854 | 5201.5854 | 5201.5854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14467 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 14931.1235 | 0.2 | 0.3 | 23292.5527 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14468 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 17517.9722 | 0.2 | 0.3 | 27328.0366 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.965 | 5205.965 | 5205.965 | 5205.965 | 5205.965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14469 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 10195.3189 | 0.2 | 0.3 | 15904.6975 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.743 | 5201.743 | 5201.743 | 5201.743 | 5201.743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14470 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 22987.6282 | 0.2 | 0.3 | 35860.7 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2975 | 5200.2975 | 5200.2975 | 5200.2975 | 5200.2975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14471 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 30981.8432 | 0.2 | 0.3 | 48331.6754 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5.3222 | 5.3222 | 5.3222 | 5.3222 | 5.3222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14472 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16002.7521 | 0.2 | 0.3 | 24964.2932 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4167.6075 | 4167.6075 | 4167.6075 | 4167.6075 | 4167.6075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14473 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16765.1217 | 0.2 | 0.3 | 26153.5898 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2818.4177 | 2818.4177 | 2818.4177 | 2818.4177 | 2818.4177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14474 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 20834.7144 | 0.2 | 0.3 | 32502.1545 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6169 | 5201.6169 | 5201.6169 | 5201.6169 | 5201.6169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14475 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 9743.6489 | 0.2 | 0.3 | 15200.0922 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0658 | 5201.0658 | 5201.0658 | 5201.0658 | 5201.0658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14476 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 0.43433 | 0.2 | 0.3 | 0.67756 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.9721 | 9777.9721 | 9777.9721 | 9777.9721 | 9777.9721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14477 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16676.0941 | 0.2 | 0.3 | 26014.7067 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9718 | 5200.9718 | 5200.9718 | 5200.9718 | 5200.9718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14478 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 22799.2491 | 0.2 | 0.3 | 35566.8286 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4659.2805 | 4659.2805 | 4659.2805 | 4659.2805 | 4659.2805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14479 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 297.8973 | 0.2 | 0.3 | 464.7197 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3856.3648 | 3856.3648 | 3856.3648 | 3856.3648 | 3856.3648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14480 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16426.5554 | 0.2 | 0.3 | 25625.4264 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5198.3688 | 5198.3688 | 5198.3688 | 5198.3688 | 5198.3688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14481 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16632.8622 | 0.2 | 0.3 | 25947.265 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14482 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16459.1714 | 0.2 | 0.3 | 25676.3074 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14483 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17330.8846 | 0.2 | 0.3 | 27036.18 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14484 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16962.1987 | 0.2 | 0.3 | 26461.0299 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.917 | 5200.917 | 5200.917 | 5200.917 | 5200.917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14485 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 25759.2263 | 0.2 | 0.3 | 40184.393 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9430.672 | 9430.672 | 9430.672 | 9430.672 | 9430.672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14486 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 3580.3981 | 0.2 | 0.3 | 5585.4211 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8864.9899 | 8864.9899 | 8864.9899 | 8864.9899 | 8864.9899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14487 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 22973.7302 | 0.2 | 0.3 | 35839.0191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9822.4225 | 9822.4225 | 9822.4225 | 9822.4225 | 9822.4225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14488 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 30083.8661 | 0.2 | 0.3 | 46930.8312 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.3461 | 9778.3461 | 9778.3461 | 9778.3461 | 9778.3461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14489 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 29844.0952 | 0.2 | 0.3 | 46556.7885 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14490 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 29603.3101 | 0.2 | 0.3 | 46181.1638 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9304.7567 | 9304.7567 | 9304.7567 | 9304.7567 | 9304.7567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14491 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 26001.2735 | 0.2 | 0.3 | 40561.9866 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3025.5826 | 3025.5826 | 3025.5826 | 3025.5826 | 3025.5826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14492 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 24982.5307 | 0.2 | 0.3 | 38972.7478 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1278.3565 | 1278.3565 | 1278.3565 | 1278.3565 | 1278.3565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14493 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 2982.6581 | 0.2 | 0.3 | 4652.9467 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1036.0015 | 1036.0015 | 1036.0015 | 1036.0015 | 1036.0015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14494 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 19497.8155 | 0.2 | 0.3 | 30416.5921 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1501.7344 | 1501.7344 | 1501.7344 | 1501.7344 | 1501.7344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14495 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 20776.0841 | 0.2 | 0.3 | 32410.6911 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8860.1719 | 8860.1719 | 8860.1719 | 8860.1719 | 8860.1719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14496 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16672.442 | 0.2 | 0.3 | 26009.0095 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9780.8031 | 9780.8031 | 9780.8031 | 9780.8031 | 9780.8031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14497 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 7619.7364 | 0.2 | 0.3 | 11886.7888 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9790.3216 | 9790.3216 | 9790.3216 | 9790.3216 | 9790.3216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14498 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 5598.049 | 0.2 | 0.3 | 8732.9564 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.2536 | 5204.2536 | 5204.2536 | 5204.2536 | 5204.2536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14499 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6255 | 0.2 | 0.3 | 25999.9357 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6446.767 | 6446.767 | 6446.767 | 6446.767 | 6446.767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14500 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 15083.0636 | 0.2 | 0.3 | 23529.5792 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14501 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 19457.4359 | 0.2 | 0.3 | 30353.6001 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9677.1854 | 9677.1854 | 9677.1854 | 9677.1854 | 9677.1854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14502 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 26055.2167 | 0.2 | 0.3 | 40646.1381 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 66.7616 | 66.7616 | 66.7616 | 66.7616 | 66.7616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14503 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 19615.751 | 0.2 | 0.3 | 30600.5716 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5134.5752 | 5134.5752 | 5134.5752 | 5134.5752 | 5134.5752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14504 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 37614.0568 | 0.2 | 0.3 | 58677.9286 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7822.4879 | 7822.4879 | 7822.4879 | 7822.4879 | 7822.4879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14505 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 17641.9061 | 0.2 | 0.3 | 27521.3736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9700.885 | 9700.885 | 9700.885 | 9700.885 | 9700.885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14506 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 31360.347 | 0.2 | 0.3 | 48922.1413 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14507 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 6083.2601 | 0.2 | 0.3 | 9489.8857 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1707 | 5201.1707 | 5201.1707 | 5201.1707 | 5201.1707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14508 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 25067.1879 | 0.2 | 0.3 | 39104.8132 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.5679 | 9778.5679 | 9778.5679 | 9778.5679 | 9778.5679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14509 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 2678.6367 | 0.2 | 0.3 | 4178.6733 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9496 | 5200.9496 | 5200.9496 | 5200.9496 | 5200.9496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14510 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 18086.3023 | 0.2 | 0.3 | 28214.6315 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14511 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16905.9513 | 0.2 | 0.3 | 26373.2841 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4097.1489 | 4097.1489 | 4097.1489 | 4097.1489 | 4097.1489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14512 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 19661.4323 | 0.2 | 0.3 | 30671.8343 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3189.6256 | 3189.6256 | 3189.6256 | 3189.6256 | 3189.6256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14513 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 19810.9879 | 0.2 | 0.3 | 30905.1412 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2948.6607 | 2948.6607 | 2948.6607 | 2948.6607 | 2948.6607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14514 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 1015.9759 | 0.2 | 0.3 | 1584.9225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4876.526 | 4876.526 | 4876.526 | 4876.526 | 4876.526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14515 | COCONUT CREEK | 10606 | Public | 2036 | 5 | Swales | 66.6667 | 26429.7146 | 0.2 | 0.3 | 41230.3548 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14516 | COCONUT CREEK | 10606 | Public | 2036 | 5 | Swales | 66.6667 | 24221.6283 | 0.2 | 0.3 | 37785.7402 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8898 | 5200.8898 | 5200.8898 | 5200.8898 | 5200.8898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14517 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 23656.7074 | 0.2 | 0.3 | 36904.4635 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5321.4458 | 5321.4458 | 5321.4458 | 5321.4458 | 5321.4458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14518 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 16661.5001 | 0.2 | 0.3 | 25991.9402 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6476.8615 | 6476.8615 | 6476.8615 | 6476.8615 | 6476.8615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14519 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 26513.0185 | 0.2 | 0.3 | 41360.3088 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14520 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 18784.0328 | 0.2 | 0.3 | 29303.0912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.174 | 5201.174 | 5201.174 | 5201.174 | 5201.174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14521 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 20430.4545 | 0.2 | 0.3 | 31871.5091 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.217 | 5200.217 | 5200.217 | 5200.217 | 5200.217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14522 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 17060.4765 | 0.2 | 0.3 | 26614.3433 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5347 | 5201.5347 | 5201.5347 | 5201.5347 | 5201.5347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14523 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 7741.8181 | 0.2 | 0.3 | 12077.2362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.3063 | 9778.3063 | 9778.3063 | 9778.3063 | 9778.3063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14524 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 24188.1181 | 0.2 | 0.3 | 37733.4642 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0634 | 5201.0634 | 5201.0634 | 5201.0634 | 5201.0634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14525 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 8244.3819 | 0.2 | 0.3 | 12861.2357 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14526 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 14731.339 | 0.2 | 0.3 | 22980.8888 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14527 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 18263.8227 | 0.2 | 0.3 | 28491.5634 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4678.9658 | 4678.9658 | 4678.9658 | 4678.9658 | 4678.9658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14528 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 26474.4369 | 0.2 | 0.3 | 41300.1215 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4852.6021 | 4852.6021 | 4852.6021 | 4852.6021 | 4852.6021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14529 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 5420.6874 | 0.2 | 0.3 | 8456.2723 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3389.7579 | 3389.7579 | 3389.7579 | 3389.7579 | 3389.7579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14530 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 9963.837 | 0.2 | 0.3 | 15543.5857 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4833.5912 | 4833.5912 | 4833.5912 | 4833.5912 | 4833.5912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14531 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 21744.9326 | 0.2 | 0.3 | 33922.0949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8921.2018 | 8921.2018 | 8921.2018 | 8921.2018 | 8921.2018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14532 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 18939.6813 | 0.2 | 0.3 | 29545.9029 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8.4586 | 8.4586 | 8.4586 | 8.4586 | 8.4586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14533 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 33211.3059 | 0.2 | 0.3 | 51809.6372 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6334 | 5201.6334 | 5201.6334 | 5201.6334 | 5201.6334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14534 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 20652.1011 | 0.2 | 0.3 | 32217.2778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1379 | 5201.1379 | 5201.1379 | 5201.1379 | 5201.1379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14535 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 5744.3096 | 0.2 | 0.3 | 8961.123 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8563 | 5200.8563 | 5200.8563 | 5200.8563 | 5200.8563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14536 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 16512.8503 | 0.2 | 0.3 | 25760.0465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.037 | 5201.037 | 5201.037 | 5201.037 | 5201.037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14537 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 18612.0125 | 0.2 | 0.3 | 29034.7396 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.127 | 5201.127 | 5201.127 | 5201.127 | 5201.127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14538 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 33.9776 | 0.2 | 0.3 | 53.0051 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14539 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 11879.2463 | 0.2 | 0.3 | 18531.6243 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.5027 | 9779.5027 | 9779.5027 | 9779.5027 | 9779.5027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14540 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 18902.723 | 0.2 | 0.3 | 29488.2479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0521 | 5201.0521 | 5201.0521 | 5201.0521 | 5201.0521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14541 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 21948.5343 | 0.2 | 0.3 | 34239.7136 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14542 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 5624.409 | 0.2 | 0.3 | 8774.078 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14543 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16733.0884 | 0.2 | 0.3 | 26103.6179 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5137.007 | 5137.007 | 5137.007 | 5137.007 | 5137.007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14544 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 109.5501 | 0.2 | 0.3 | 170.8981 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5082.5586 | 5082.5586 | 5082.5586 | 5082.5586 | 5082.5586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14545 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16769.9351 | 0.2 | 0.3 | 26161.0988 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4735.5513 | 4735.5513 | 4735.5513 | 4735.5513 | 4735.5513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14546 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16926.8334 | 0.2 | 0.3 | 26405.8601 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9944.3579 | 9944.3579 | 9944.3579 | 9944.3579 | 9944.3579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14547 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16669.7261 | 0.2 | 0.3 | 26004.7727 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9929.0279 | 9929.0279 | 9929.0279 | 9929.0279 | 9929.0279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14548 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 19824.4737 | 0.2 | 0.3 | 30926.1789 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4223 | 5202.4223 | 5202.4223 | 5202.4223 | 5202.4223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14549 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 39033.8659 | 0.2 | 0.3 | 60892.8309 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.5366 | 9779.5366 | 9779.5366 | 9779.5366 | 9779.5366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14550 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 8162.9407 | 0.2 | 0.3 | 12734.1874 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.8435 | 9778.8435 | 9778.8435 | 9778.8435 | 9778.8435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14551 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 17141.2493 | 0.2 | 0.3 | 26740.349 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.7983 | 9778.7983 | 9778.7983 | 9778.7983 | 9778.7983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14552 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 972.7479 | 0.2 | 0.3 | 1517.4867 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4048 | 5202.4048 | 5202.4048 | 5202.4048 | 5202.4048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14553 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 24799.0403 | 0.2 | 0.3 | 38686.5028 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.447 | 5202.447 | 5202.447 | 5202.447 | 5202.447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14554 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 10399.2498 | 0.2 | 0.3 | 16222.8297 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.1595 | 9778.1595 | 9778.1595 | 9778.1595 | 9778.1595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14555 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 5446.8197 | 0.2 | 0.3 | 8497.0387 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7408.3117 | 7408.3117 | 7408.3117 | 7408.3117 | 7408.3117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14556 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 14474.8619 | 0.2 | 0.3 | 22580.7845 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7570.9883 | 7570.9883 | 7570.9883 | 7570.9883 | 7570.9883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14557 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 5106.2013 | 0.2 | 0.3 | 7965.6741 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14558 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 27598.3947 | 0.2 | 0.3 | 43053.4958 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8241 | 5200.8241 | 5200.8241 | 5200.8241 | 5200.8241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14559 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 22108.2565 | 0.2 | 0.3 | 34488.8801 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5926 | 5200.5926 | 5200.5926 | 5200.5926 | 5200.5926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14560 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 8093.2997 | 0.2 | 0.3 | 12625.5475 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5431.8284 | 5431.8284 | 5431.8284 | 5431.8284 | 5431.8284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14561 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17386.6228 | 0.2 | 0.3 | 27123.1316 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.7983 | 9778.7983 | 9778.7983 | 9778.7983 | 9778.7983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14562 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 14424.2427 | 0.2 | 0.3 | 22501.8186 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8476.1478 | 8476.1478 | 8476.1478 | 8476.1478 | 8476.1478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14563 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 5789.6189 | 0.2 | 0.3 | 9031.8055 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1419.5083 | 1419.5083 | 1419.5083 | 1419.5083 | 1419.5083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14564 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 18471.0565 | 0.2 | 0.3 | 28814.8482 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0001 | 5201.0001 | 5201.0001 | 5201.0001 | 5201.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14565 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 2869.4663 | 0.2 | 0.3 | 4476.3675 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0089 | 5201.0089 | 5201.0089 | 5201.0089 | 5201.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14566 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 30527.7927 | 0.2 | 0.3 | 47623.3567 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1661 | 5201.1661 | 5201.1661 | 5201.1661 | 5201.1661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14567 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 518.9309 | 0.2 | 0.3 | 809.5323 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9201 | 5200.9201 | 5200.9201 | 5200.9201 | 5200.9201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14568 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 26720.2791 | 0.2 | 0.3 | 41683.6353 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1338 | 5202.1338 | 5202.1338 | 5202.1338 | 5202.1338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14569 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 8189.2628 | 0.2 | 0.3 | 12775.25 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6639 | 5201.6639 | 5201.6639 | 5201.6639 | 5201.6639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14570 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 5310.9326 | 0.2 | 0.3 | 8285.0549 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14571 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 25204.341 | 0.2 | 0.3 | 39318.772 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.3044 | 9778.3044 | 9778.3044 | 9778.3044 | 9778.3044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14572 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16668.4187 | 0.2 | 0.3 | 26002.7331 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9406 | 5200.9406 | 5200.9406 | 5200.9406 | 5200.9406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14573 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16694.0806 | 0.2 | 0.3 | 26042.7657 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14574 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16666.3266 | 0.2 | 0.3 | 25999.4695 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14575 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 27820.6343 | 0.2 | 0.3 | 43400.1896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0419 | 5201.0419 | 5201.0419 | 5201.0419 | 5201.0419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14576 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 31037.5681 | 0.2 | 0.3 | 48418.6063 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2759.1206 | 2759.1206 | 2759.1206 | 2759.1206 | 2759.1206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14577 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 11909.7622 | 0.2 | 0.3 | 18579.229 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3756.4196 | 3756.4196 | 3756.4196 | 3756.4196 | 3756.4196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14578 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2087 | 0.2 | 0.3 | 26002.4055 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2712.8088 | 2712.8088 | 2712.8088 | 2712.8088 | 2712.8088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14579 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16668.3648 | 0.2 | 0.3 | 26002.6491 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11208.8651 | 11208.8651 | 11208.8651 | 11208.8651 | 11208.8651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14580 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 2482.4157 | 0.2 | 0.3 | 3872.5685 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6464.6694 | 6464.6694 | 6464.6694 | 6464.6694 | 6464.6694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14581 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 28317.975 | 0.2 | 0.3 | 44176.041 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9942 | 5200.9942 | 5200.9942 | 5200.9942 | 5200.9942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14582 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16735.9343 | 0.2 | 0.3 | 26108.0575 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.6673 | 9777.6673 | 9777.6673 | 9777.6673 | 9777.6673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14583 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16685.5637 | 0.2 | 0.3 | 26029.4793 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.9891 | 9777.9891 | 9777.9891 | 9777.9891 | 9777.9891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14584 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 18223.0867 | 0.2 | 0.3 | 28428.0152 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.8763 | 9777.8763 | 9777.8763 | 9777.8763 | 9777.8763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14585 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 13801.7861 | 0.2 | 0.3 | 21530.7863 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3032 | 5200.3032 | 5200.3032 | 5200.3032 | 5200.3032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14586 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 20776.0149 | 0.2 | 0.3 | 32410.5832 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3816 | 5200.3816 | 5200.3816 | 5200.3816 | 5200.3816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14587 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 18588.3665 | 0.2 | 0.3 | 28997.8517 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7870.4292 | 7870.4292 | 7870.4292 | 7870.4292 | 7870.4292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14588 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 20166.0696 | 0.2 | 0.3 | 31459.0686 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7534.3813 | 7534.3813 | 7534.3813 | 7534.3813 | 7534.3813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14589 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 8333.4759 | 0.2 | 0.3 | 13000.2224 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7444.3021 | 7444.3021 | 7444.3021 | 7444.3021 | 7444.3021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14590 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 8333.7211 | 0.2 | 0.3 | 13000.605 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14591 | COCONUT CREEK | 10606 | Public | 2036 | 5 | Swales | 66.6667 | 24060.2851 | 0.2 | 0.3 | 37534.0448 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14592 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 16640.0837 | 0.2 | 0.3 | 25958.5306 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7117 | 5200.7117 | 5200.7117 | 5200.7117 | 5200.7117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14593 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 19232.5119 | 0.2 | 0.3 | 30002.7186 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.3024 | 9778.3024 | 9778.3024 | 9778.3024 | 9778.3024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14594 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 23818.9067 | 0.2 | 0.3 | 37157.4945 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7097.3245 | 7097.3245 | 7097.3245 | 7097.3245 | 7097.3245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14595 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 19989.6629 | 0.2 | 0.3 | 31183.8742 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7427.0686 | 7427.0686 | 7427.0686 | 7427.0686 | 7427.0686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14596 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 414.6065 | 0.2 | 0.3 | 646.7862 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7635.8796 | 7635.8796 | 7635.8796 | 7635.8796 | 7635.8796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14597 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 12309.8782 | 0.2 | 0.3 | 19203.41 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.7792 | 9777.7792 | 9777.7792 | 9777.7792 | 9777.7792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14598 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 20526.0169 | 0.2 | 0.3 | 32020.5864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.1932 | 9777.1932 | 9777.1932 | 9777.1932 | 9777.1932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14599 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 3287.9397 | 0.2 | 0.3 | 5129.186 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.7819 | 9777.7819 | 9777.7819 | 9777.7819 | 9777.7819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14600 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 6399.2771 | 0.2 | 0.3 | 9982.8723 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.3652 | 9777.3652 | 9777.3652 | 9777.3652 | 9777.3652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14601 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 12007.9304 | 0.2 | 0.3 | 18732.3714 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.8963 | 9778.8963 | 9778.8963 | 9778.8963 | 9778.8963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14602 | CORAL SPRINGS | 10612 | Public | 2036 | 5 | Swales | 66.6667 | 2030.034 | 0.2 | 0.3 | 3166.853 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9783.0426 | 9783.0426 | 9783.0426 | 9783.0426 | 9783.0426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14603 | CORAL SPRINGS | 10612 | Public | 2036 | 5 | Swales | 66.6667 | 24056.7877 | 0.2 | 0.3 | 37528.5888 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14604 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 25396.0245 | 0.2 | 0.3 | 39617.7983 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.3514 | 9776.3514 | 9776.3514 | 9776.3514 | 9776.3514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14605 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 11814.9701 | 0.2 | 0.3 | 18431.3534 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14606 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 682.7644 | 0.2 | 0.3 | 1065.1125 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14607 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 18470.3851 | 0.2 | 0.3 | 28813.8007 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9485.4116 | 9485.4116 | 9485.4116 | 9485.4116 | 9485.4116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14608 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 13563.8514 | 0.2 | 0.3 | 21159.6082 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14609 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 38763.2722 | 0.2 | 0.3 | 60470.7046 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5160.84 | 5160.84 | 5160.84 | 5160.84 | 5160.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14610 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 25982.8892 | 0.2 | 0.3 | 40533.3072 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7117.3968 | 7117.3968 | 7117.3968 | 7117.3968 | 7117.3968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14611 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 13148.9973 | 0.2 | 0.3 | 20512.4358 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5353.308 | 5353.308 | 5353.308 | 5353.308 | 5353.308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14612 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 19393.2263 | 0.2 | 0.3 | 30253.433 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2016 | 5201.2016 | 5201.2016 | 5201.2016 | 5201.2016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14613 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 16658.9761 | 0.2 | 0.3 | 25988.0027 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 83.3023 | 83.3023 | 83.3023 | 83.3023 | 83.3023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14614 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 19078.0417 | 0.2 | 0.3 | 29761.745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2000.6278 | 2000.6278 | 2000.6278 | 2000.6278 | 2000.6278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14615 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 9344.6626 | 0.2 | 0.3 | 14577.6737 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6067 | 5200.6067 | 5200.6067 | 5200.6067 | 5200.6067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14616 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 13142.4026 | 0.2 | 0.3 | 20502.1481 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6073.8339 | 6073.8339 | 6073.8339 | 6073.8339 | 6073.8339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14617 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 6011.902 | 0.2 | 0.3 | 9378.5671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8905.0197 | 8905.0197 | 8905.0197 | 8905.0197 | 8905.0197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14618 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 15744.1771 | 0.2 | 0.3 | 24560.9162 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14619 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 2247.8209 | 0.2 | 0.3 | 3506.6006 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5775.8161 | 5775.8161 | 5775.8161 | 5775.8161 | 5775.8161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14620 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 1070.2792 | 0.2 | 0.3 | 1669.6356 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1858 | 5200.1858 | 5200.1858 | 5200.1858 | 5200.1858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14621 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 29954.636 | 0.2 | 0.3 | 46729.2322 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9476.144 | 9476.144 | 9476.144 | 9476.144 | 9476.144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14622 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 5809.0847 | 0.2 | 0.3 | 9062.1722 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14623 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 17837.3427 | 0.2 | 0.3 | 27826.2546 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7236.583 | 7236.583 | 7236.583 | 7236.583 | 7236.583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14624 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16866.0921 | 0.2 | 0.3 | 26311.1036 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2986.2166 | 2986.2166 | 2986.2166 | 2986.2166 | 2986.2166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14625 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 5710.7115 | 0.2 | 0.3 | 8908.7099 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14626 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 22844.2468 | 0.2 | 0.3 | 35637.025 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14627 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6375 | 0.2 | 0.3 | 25999.9544 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14628 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 7382.4547 | 0.2 | 0.3 | 11516.6294 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14629 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 335.0773 | 0.2 | 0.3 | 522.7205 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14630 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 18101.1379 | 0.2 | 0.3 | 28237.7752 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14631 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16851.5468 | 0.2 | 0.3 | 26288.413 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6703.5391 | 6703.5391 | 6703.5391 | 6703.5391 | 6703.5391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14632 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16667.0247 | 0.2 | 0.3 | 26000.5585 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8065 | 5201.8065 | 5201.8065 | 5201.8065 | 5201.8065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14633 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 23242.5595 | 0.2 | 0.3 | 36258.3928 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6526 | 5200.6526 | 5200.6526 | 5200.6526 | 5200.6526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14634 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 21872.5686 | 0.2 | 0.3 | 34121.207 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.7018 | 9777.7018 | 9777.7018 | 9777.7018 | 9777.7018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14635 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14636 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16667.4924 | 0.2 | 0.3 | 26001.2881 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14637 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 13190.5422 | 0.2 | 0.3 | 20577.2458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9466.4773 | 9466.4773 | 9466.4773 | 9466.4773 | 9466.4773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14638 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 19335.2767 | 0.2 | 0.3 | 30163.0317 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5435.9032 | 5435.9032 | 5435.9032 | 5435.9032 | 5435.9032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14639 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 4433.9863 | 0.2 | 0.3 | 6917.0186 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3200.6401 | 3200.6401 | 3200.6401 | 3200.6401 | 3200.6401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14640 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 14859.5473 | 0.2 | 0.3 | 23180.8937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 461.2593 | 461.2593 | 461.2593 | 461.2593 | 461.2593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14641 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 22088.6035 | 0.2 | 0.3 | 34458.2214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0686 | 5201.0686 | 5201.0686 | 5201.0686 | 5201.0686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14642 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 10108.8104 | 0.2 | 0.3 | 15769.7442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4524 | 5201.4524 | 5201.4524 | 5201.4524 | 5201.4524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14643 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 15243.7128 | 0.2 | 0.3 | 23780.192 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5949.3471 | 5949.3471 | 5949.3471 | 5949.3471 | 5949.3471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14644 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 38046.1288 | 0.2 | 0.3 | 59351.9609 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0072 | 5201.0072 | 5201.0072 | 5201.0072 | 5201.0072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14645 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 25064.6011 | 0.2 | 0.3 | 39100.7778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5302 | 5201.5302 | 5201.5302 | 5201.5302 | 5201.5302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14646 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 15396.3195 | 0.2 | 0.3 | 24018.2585 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5283.3767 | 5283.3767 | 5283.3767 | 5283.3767 | 5283.3767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14647 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16794.9777 | 0.2 | 0.3 | 26200.1652 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3983.225 | 3983.225 | 3983.225 | 3983.225 | 3983.225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14648 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 6771.9519 | 0.2 | 0.3 | 10564.2449 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5306.8007 | 5306.8007 | 5306.8007 | 5306.8007 | 5306.8007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14649 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 20907.7801 | 0.2 | 0.3 | 32616.137 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8505 | 5200.8505 | 5200.8505 | 5200.8505 | 5200.8505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14650 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 21804.9079 | 0.2 | 0.3 | 34015.6564 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14651 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 24948.6351 | 0.2 | 0.3 | 38919.8708 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8880.4856 | 8880.4856 | 8880.4856 | 8880.4856 | 8880.4856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14652 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 7281.9336 | 0.2 | 0.3 | 11359.8164 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7306.5394 | 7306.5394 | 7306.5394 | 7306.5394 | 7306.5394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14653 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 14386.1493 | 0.2 | 0.3 | 22442.393 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14654 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16577.4506 | 0.2 | 0.3 | 25860.8229 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6656.5531 | 6656.5531 | 6656.5531 | 6656.5531 | 6656.5531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14655 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 975.1407 | 0.2 | 0.3 | 1521.2194 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5971 | 5200.5971 | 5200.5971 | 5200.5971 | 5200.5971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14656 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17530.9635 | 0.2 | 0.3 | 27348.303 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6662.1637 | 6662.1637 | 6662.1637 | 6662.1637 | 6662.1637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14657 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 13775.2677 | 0.2 | 0.3 | 21489.4176 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14658 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16668.2404 | 0.2 | 0.3 | 26002.455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6738.1224 | 6738.1224 | 6738.1224 | 6738.1224 | 6738.1224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14659 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 17289.4371 | 0.2 | 0.3 | 26971.5219 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4403.2399 | 4403.2399 | 4403.2399 | 4403.2399 | 4403.2399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14660 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 30007.2612 | 0.2 | 0.3 | 46811.3275 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5023.6114 | 5023.6114 | 5023.6114 | 5023.6114 | 5023.6114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14661 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 22963.7191 | 0.2 | 0.3 | 35823.4017 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5233.0083 | 5233.0083 | 5233.0083 | 5233.0083 | 5233.0083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14662 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 22012.4485 | 0.2 | 0.3 | 34339.4197 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14663 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 405.6237 | 0.2 | 0.3 | 632.7729 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4238 | 5200.4238 | 5200.4238 | 5200.4238 | 5200.4238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14664 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2404 | 0.2 | 0.3 | 26002.455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6779.3583 | 6779.3583 | 6779.3583 | 6779.3583 | 6779.3583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14665 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3611 | 5200.3611 | 5200.3611 | 5200.3611 | 5200.3611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14666 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 10495.6233 | 0.2 | 0.3 | 16373.1723 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9441.5431 | 9441.5431 | 9441.5431 | 9441.5431 | 9441.5431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14667 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 17728.4061 | 0.2 | 0.3 | 27656.3136 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 363.3836 | 363.3836 | 363.3836 | 363.3836 | 363.3836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14668 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 30839.4313 | 0.2 | 0.3 | 48109.5129 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6050.5016 | 6050.5016 | 6050.5016 | 6050.5016 | 6050.5016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14669 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16659.8945 | 0.2 | 0.3 | 25989.4355 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 246.1862 | 246.1862 | 246.1862 | 246.1862 | 246.1862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14670 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 21217.3143 | 0.2 | 0.3 | 33099.0104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2317.601 | 2317.601 | 2317.601 | 2317.601 | 2317.601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14671 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16760.3923 | 0.2 | 0.3 | 26146.2119 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.672 | 2600.672 | 2600.672 | 2600.672 | 2600.672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14672 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 12854.1087 | 0.2 | 0.3 | 20052.4096 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.3532 | 5205.3532 | 5205.3532 | 5205.3532 | 5205.3532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14673 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 19282.0456 | 0.2 | 0.3 | 30079.9911 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5207.2374 | 5207.2374 | 5207.2374 | 5207.2374 | 5207.2374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14674 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 135.4407 | 0.2 | 0.3 | 211.2874 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2187.9559 | 2187.9559 | 2187.9559 | 2187.9559 | 2187.9559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14675 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 20989.3061 | 0.2 | 0.3 | 32743.3176 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7180.3742 | 7180.3742 | 7180.3742 | 7180.3742 | 7180.3742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14676 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 29000.1869 | 0.2 | 0.3 | 45240.2915 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14677 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 18750.6324 | 0.2 | 0.3 | 29250.9865 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6501 | 5201.6501 | 5201.6501 | 5201.6501 | 5201.6501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14678 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 8333.7099 | 0.2 | 0.3 | 13000.5875 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10748.162 | 10748.162 | 10748.162 | 10748.162 | 10748.162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14679 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 8333.4985 | 0.2 | 0.3 | 13000.2577 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5208.2432 | 5208.2432 | 5208.2432 | 5208.2432 | 5208.2432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14680 | COCONUT CREEK | 10606 | Public | 2036 | 5 | Swales | 66.6667 | 20543.0956 | 0.2 | 0.3 | 32047.2291 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2403.1175 | 2403.1175 | 2403.1175 | 2403.1175 | 2403.1175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14681 | COCONUT CREEK | 10606 | Public | 2036 | 5 | Swales | 66.6667 | 17831.9834 | 0.2 | 0.3 | 27817.8941 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2551.4046 | 2551.4046 | 2551.4046 | 2551.4046 | 2551.4046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14682 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 16667.2771 | 0.2 | 0.3 | 26000.9522 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2883.6507 | 2883.6507 | 2883.6507 | 2883.6507 | 2883.6507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14683 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 16667.7281 | 0.2 | 0.3 | 26001.6558 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.7573 | 2600.7573 | 2600.7573 | 2600.7573 | 2600.7573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14684 | COCONUT CREEK | 10615 | Public | 2036 | 5 | Swales | 66.6667 | 10485.6338 | 0.2 | 0.3 | 16357.5887 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4833.503 | 4833.503 | 4833.503 | 4833.503 | 4833.503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14685 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 31982.7176 | 0.2 | 0.3 | 49893.0395 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10400.087 | 10400.087 | 10400.087 | 10400.087 | 10400.087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14686 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 23759.2946 | 0.2 | 0.3 | 37064.4996 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11097.3102 | 11097.3102 | 11097.3102 | 11097.3102 | 11097.3102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14687 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 23561.4331 | 0.2 | 0.3 | 36755.8356 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5207.4744 | 5207.4744 | 5207.4744 | 5207.4744 | 5207.4744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14688 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 16116.2089 | 0.2 | 0.3 | 25141.2858 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1234.0318 | 1234.0318 | 1234.0318 | 1234.0318 | 1234.0318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14689 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 19246.423 | 0.2 | 0.3 | 30024.4199 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6198.9717 | 6198.9717 | 6198.9717 | 6198.9717 | 6198.9717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14690 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 68.9396 | 0.2 | 0.3 | 107.5458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14691 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 16550.9705 | 0.2 | 0.3 | 25819.514 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8764.7704 | 8764.7704 | 8764.7704 | 8764.7704 | 8764.7704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14692 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 15800.4599 | 0.2 | 0.3 | 24648.7175 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7245.2072 | 7245.2072 | 7245.2072 | 7245.2072 | 7245.2072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14693 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 13782.303 | 0.2 | 0.3 | 21500.3927 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14694 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 21973.5905 | 0.2 | 0.3 | 34278.8011 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2403.7482 | 2403.7482 | 2403.7482 | 2403.7482 | 2403.7482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14695 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 24291.6999 | 0.2 | 0.3 | 37895.0519 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2797.6678 | 2797.6678 | 2797.6678 | 2797.6678 | 2797.6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14696 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 24771.1867 | 0.2 | 0.3 | 38643.0512 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14697 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 10347.8067 | 0.2 | 0.3 | 16142.5784 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4374.5335 | 4374.5335 | 4374.5335 | 4374.5335 | 4374.5335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14698 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 19792.9053 | 0.2 | 0.3 | 30876.9323 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 166.3978 | 166.3978 | 166.3978 | 166.3978 | 166.3978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14699 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 2171.3487 | 0.2 | 0.3 | 3387.304 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4796.4281 | 4796.4281 | 4796.4281 | 4796.4281 | 4796.4281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14700 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 18381.0349 | 0.2 | 0.3 | 28674.4145 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.718 | 5206.718 | 5206.718 | 5206.718 | 5206.718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14701 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 28234.2597 | 0.2 | 0.3 | 44045.4451 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.5527 | 5199.5527 | 5199.5527 | 5199.5527 | 5199.5527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14702 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 24492.8592 | 0.2 | 0.3 | 38208.8604 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4644.1779 | 4644.1779 | 4644.1779 | 4644.1779 | 4644.1779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14703 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 18949.5601 | 0.2 | 0.3 | 29561.3137 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1965.7851 | 1965.7851 | 1965.7851 | 1965.7851 | 1965.7851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14704 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 304.8943 | 0.2 | 0.3 | 475.6352 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2719.5796 | 2719.5796 | 2719.5796 | 2719.5796 | 2719.5796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14705 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 6772.5835 | 0.2 | 0.3 | 10565.2302 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5583.9962 | 5583.9962 | 5583.9962 | 5583.9962 | 5583.9962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14706 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 26933.5907 | 0.2 | 0.3 | 42016.4015 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 206.0137 | 206.0137 | 206.0137 | 206.0137 | 206.0137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14707 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 6148.0339 | 0.2 | 0.3 | 9590.9328 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7020.0424 | 7020.0424 | 7020.0424 | 7020.0424 | 7020.0424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14708 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 12994.1366 | 0.2 | 0.3 | 20270.8531 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7990.1554 | 7990.1554 | 7990.1554 | 7990.1554 | 7990.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14709 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 17588.2089 | 0.2 | 0.3 | 27437.6059 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4115.5478 | 4115.5478 | 4115.5478 | 4115.5478 | 4115.5478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14710 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 19119.5168 | 0.2 | 0.3 | 29826.4462 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1253.8294 | 1253.8294 | 1253.8294 | 1253.8294 | 1253.8294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14711 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 18951.0118 | 0.2 | 0.3 | 29563.5784 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1977.9822 | 1977.9822 | 1977.9822 | 1977.9822 | 1977.9822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14712 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 1888.4611 | 0.2 | 0.3 | 2945.9994 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14713 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 17980.0879 | 0.2 | 0.3 | 28048.9371 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2599.9896 | 2599.9896 | 2599.9896 | 2599.9896 | 2599.9896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14714 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 11530.9379 | 0.2 | 0.3 | 17988.2632 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2601.9345 | 2601.9345 | 2601.9345 | 2601.9345 | 2601.9345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14715 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 19945.6018 | 0.2 | 0.3 | 31115.1388 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 152.7346 | 152.7346 | 152.7346 | 152.7346 | 152.7346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14716 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 19076.0992 | 0.2 | 0.3 | 29758.7148 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3352 | 5203.3352 | 5203.3352 | 5203.3352 | 5203.3352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14717 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 36949.7727 | 0.2 | 0.3 | 57641.6454 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.19182 | 0.19182 | 0.19182 | 0.19182 | 0.19182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14718 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 23100.7604 | 0.2 | 0.3 | 36037.1862 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3991.1078 | 3991.1078 | 3991.1078 | 3991.1078 | 3991.1078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14719 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 9992.1145 | 0.2 | 0.3 | 15587.6987 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3712.666 | 3712.666 | 3712.666 | 3712.666 | 3712.666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14720 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 18083.4792 | 0.2 | 0.3 | 28210.2276 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14721 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 26908.0203 | 0.2 | 0.3 | 41976.5116 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 2600.0749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14722 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 17269.7159 | 0.2 | 0.3 | 26940.7569 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2602.1474 | 2602.1474 | 2602.1474 | 2602.1474 | 2602.1474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14723 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8902 | 0.2 | 0.3 | 26000.3487 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5894.9673 | 5894.9673 | 5894.9673 | 5894.9673 | 5894.9673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14724 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16666.5554 | 0.2 | 0.3 | 25999.8264 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3287.9685 | 3287.9685 | 3287.9685 | 3287.9685 | 3287.9685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14725 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 18936.4483 | 0.2 | 0.3 | 29540.8594 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1915.2646 | 1915.2646 | 1915.2646 | 1915.2646 | 1915.2646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14726 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16543.2243 | 0.2 | 0.3 | 25807.43 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14727 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 17743.8711 | 0.2 | 0.3 | 27680.439 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8269.8808 | 8269.8808 | 8269.8808 | 8269.8808 | 8269.8808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14728 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 23548.7459 | 0.2 | 0.3 | 36736.0436 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14729 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 13649.7975 | 0.2 | 0.3 | 21293.6842 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6971.853 | 6971.853 | 6971.853 | 6971.853 | 6971.853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14730 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 6274.1147 | 0.2 | 0.3 | 9787.6189 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2055.1606 | 2055.1606 | 2055.1606 | 2055.1606 | 2055.1606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14731 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 11533.2524 | 0.2 | 0.3 | 17991.8737 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3504.6382 | 3504.6382 | 3504.6382 | 3504.6382 | 3504.6382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14732 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 19840.192 | 0.2 | 0.3 | 30950.6995 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5648.894 | 5648.894 | 5648.894 | 5648.894 | 5648.894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14733 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17340.0151 | 0.2 | 0.3 | 27050.4235 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14734 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 26827.8711 | 0.2 | 0.3 | 41851.4789 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2194 | 5203.2194 | 5203.2194 | 5203.2194 | 5203.2194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14735 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 12152.18 | 0.2 | 0.3 | 18957.4008 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5207.706 | 5207.706 | 5207.706 | 5207.706 | 5207.706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14736 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 29943.4717 | 0.2 | 0.3 | 46711.8158 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4812.9762 | 4812.9762 | 4812.9762 | 4812.9762 | 4812.9762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14737 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 26832.1313 | 0.2 | 0.3 | 41858.1249 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1369.8941 | 1369.8941 | 1369.8941 | 1369.8941 | 1369.8941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14738 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 7705.3263 | 0.2 | 0.3 | 12020.3091 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5986 | 5201.5986 | 5201.5986 | 5201.5986 | 5201.5986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14739 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 23379.1245 | 0.2 | 0.3 | 36471.4343 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14740 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 19691.8478 | 0.2 | 0.3 | 30719.2826 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14741 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 15405.6331 | 0.2 | 0.3 | 24032.7876 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.059 | 5202.059 | 5202.059 | 5202.059 | 5202.059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14742 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 18510.5681 | 0.2 | 0.3 | 28876.4863 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1027.7254 | 1027.7254 | 1027.7254 | 1027.7254 | 1027.7254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14743 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 18379.9708 | 0.2 | 0.3 | 28672.7544 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5279.1886 | 5279.1886 | 5279.1886 | 5279.1886 | 5279.1886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14744 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 325.5929 | 0.2 | 0.3 | 507.9249 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7280.6993 | 7280.6993 | 7280.6993 | 7280.6993 | 7280.6993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14745 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17253.2377 | 0.2 | 0.3 | 26915.0508 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9780.1497 | 9780.1497 | 9780.1497 | 9780.1497 | 9780.1497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14746 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 23075.5384 | 0.2 | 0.3 | 35997.8399 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6904 | 5201.6904 | 5201.6904 | 5201.6904 | 5201.6904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14747 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16669.8808 | 0.2 | 0.3 | 26005.014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14748 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 23761.9851 | 0.2 | 0.3 | 37068.6968 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4174.2146 | 4174.2146 | 4174.2146 | 4174.2146 | 4174.2146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14749 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 6179.3868 | 0.2 | 0.3 | 9639.8434 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6743.2503 | 6743.2503 | 6743.2503 | 6743.2503 | 6743.2503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14750 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 15464.7298 | 0.2 | 0.3 | 24124.9785 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3252.873 | 3252.873 | 3252.873 | 3252.873 | 3252.873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14751 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 20906.6843 | 0.2 | 0.3 | 32614.4276 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7836.25 | 7836.25 | 7836.25 | 7836.25 | 7836.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14752 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 20050.8893 | 0.2 | 0.3 | 31279.3874 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7609.5372 | 7609.5372 | 7609.5372 | 7609.5372 | 7609.5372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14753 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2554 | 0.2 | 0.3 | 26002.4784 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.5698 | 5204.5698 | 5204.5698 | 5204.5698 | 5204.5698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14754 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16666.1051 | 0.2 | 0.3 | 25999.124 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14755 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 19797.6634 | 0.2 | 0.3 | 30884.3549 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9172 | 5201.9172 | 5201.9172 | 5201.9172 | 5201.9172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14756 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 19089.8147 | 0.2 | 0.3 | 29780.1109 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2694.9664 | 2694.9664 | 2694.9664 | 2694.9664 | 2694.9664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14757 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 24203.8479 | 0.2 | 0.3 | 37758.0028 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.771 | 5202.771 | 5202.771 | 5202.771 | 5202.771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14758 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16602.0293 | 0.2 | 0.3 | 25899.1657 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6452 | 5201.6452 | 5201.6452 | 5201.6452 | 5201.6452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14759 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 2448.0023 | 0.2 | 0.3 | 3818.8836 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4754 | 5200.4754 | 5200.4754 | 5200.4754 | 5200.4754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14760 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 18597.4335 | 0.2 | 0.3 | 29011.9962 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7680.1944 | 7680.1944 | 7680.1944 | 7680.1944 | 7680.1944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14761 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 8396.2007 | 0.2 | 0.3 | 13098.0731 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 58.4113 | 58.4113 | 58.4113 | 58.4113 | 58.4113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14762 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 15346.0339 | 0.2 | 0.3 | 23939.8129 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7002.613 | 7002.613 | 7002.613 | 7002.613 | 7002.613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14763 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 28956.018 | 0.2 | 0.3 | 45171.3881 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4832.4648 | 4832.4648 | 4832.4648 | 4832.4648 | 4832.4648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14764 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 26262.6069 | 0.2 | 0.3 | 40969.6667 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14765 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 18526.078 | 0.2 | 0.3 | 28900.6817 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4976 | 5202.4976 | 5202.4976 | 5202.4976 | 5202.4976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14766 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 24885.3352 | 0.2 | 0.3 | 38821.1229 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5592 | 5203.5592 | 5203.5592 | 5203.5592 | 5203.5592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14767 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 24309.8685 | 0.2 | 0.3 | 37923.3949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5757 | 5203.5757 | 5203.5757 | 5203.5757 | 5203.5757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14768 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 15693.5631 | 0.2 | 0.3 | 24481.9585 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14769 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 19757.6509 | 0.2 | 0.3 | 30821.9354 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14770 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 2276.0021 | 0.2 | 0.3 | 3550.5632 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 5203.4766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14771 | COCONUT CREEK | 10606 | Public | 2036 | 5 | Swales | 66.6667 | 16666.9633 | 0.2 | 0.3 | 26000.4627 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14772 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 15642.5318 | 0.2 | 0.3 | 24402.3496 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14773 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 2919.0791 | 0.2 | 0.3 | 4553.7633 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.0914 | 5203.0914 | 5203.0914 | 5203.0914 | 5203.0914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14774 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 13083.3861 | 0.2 | 0.3 | 20410.0823 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14775 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 19150.3532 | 0.2 | 0.3 | 29874.551 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1772.2185 | 1772.2185 | 1772.2185 | 1772.2185 | 1772.2185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14776 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 18776.0214 | 0.2 | 0.3 | 29290.5934 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5510.3864 | 5510.3864 | 5510.3864 | 5510.3864 | 5510.3864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14777 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 18716.4699 | 0.2 | 0.3 | 29197.693 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10004.1343 | 10004.1343 | 10004.1343 | 10004.1343 | 10004.1343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14778 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 18443.3398 | 0.2 | 0.3 | 28771.6101 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8430.1499 | 8430.1499 | 8430.1499 | 8430.1499 | 8430.1499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14779 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 22063.2176 | 0.2 | 0.3 | 34418.6195 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2893.4388 | 2893.4388 | 2893.4388 | 2893.4388 | 2893.4388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14780 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16361.4731 | 0.2 | 0.3 | 25523.8981 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14781 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 9873.9086 | 0.2 | 0.3 | 15403.2974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.4182 | 5199.4182 | 5199.4182 | 5199.4182 | 5199.4182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14782 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 17942.7672 | 0.2 | 0.3 | 27990.7168 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.4692 | 9777.4692 | 9777.4692 | 9777.4692 | 9777.4692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14783 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 6441.0867 | 0.2 | 0.3 | 10048.0953 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9493.7395 | 9493.7395 | 9493.7395 | 9493.7395 | 9493.7395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14784 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 14250.4457 | 0.2 | 0.3 | 22230.6952 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4237.7726 | 4237.7726 | 4237.7726 | 4237.7726 | 4237.7726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14785 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 18801.4381 | 0.2 | 0.3 | 29330.2435 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3052 | 5200.3052 | 5200.3052 | 5200.3052 | 5200.3052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14786 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 18301.9825 | 0.2 | 0.3 | 28551.0928 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 223.4716 | 223.4716 | 223.4716 | 223.4716 | 223.4716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14787 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 16113.9575 | 0.2 | 0.3 | 25137.7736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5243.8514 | 5243.8514 | 5243.8514 | 5243.8514 | 5243.8514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14788 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 18018.6512 | 0.2 | 0.3 | 28109.0959 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3426 | 5200.3426 | 5200.3426 | 5200.3426 | 5200.3426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14789 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 21827.5082 | 0.2 | 0.3 | 34050.9128 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5809.3325 | 5809.3325 | 5809.3325 | 5809.3325 | 5809.3325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14790 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 8409.9941 | 0.2 | 0.3 | 13119.5908 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9661.7081 | 9661.7081 | 9661.7081 | 9661.7081 | 9661.7081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14791 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 13440.2459 | 0.2 | 0.3 | 20966.7836 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9669.4552 | 9669.4552 | 9669.4552 | 9669.4552 | 9669.4552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14792 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 25394.5588 | 0.2 | 0.3 | 39615.5117 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5505.1404 | 5505.1404 | 5505.1404 | 5505.1404 | 5505.1404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14793 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 17095.1486 | 0.2 | 0.3 | 26668.4318 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5287.2686 | 5287.2686 | 5287.2686 | 5287.2686 | 5287.2686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14794 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 25066.0577 | 0.2 | 0.3 | 39103.05 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7664.7656 | 7664.7656 | 7664.7656 | 7664.7656 | 7664.7656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14795 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 22046.0275 | 0.2 | 0.3 | 34391.8028 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6630.1301 | 6630.1301 | 6630.1301 | 6630.1301 | 6630.1301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14796 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 4498.6399 | 0.2 | 0.3 | 7017.8782 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14797 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 18754.998 | 0.2 | 0.3 | 29257.7969 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.312 | 5200.312 | 5200.312 | 5200.312 | 5200.312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14798 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 18232.9496 | 0.2 | 0.3 | 28443.4014 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6495.1035 | 6495.1035 | 6495.1035 | 6495.1035 | 6495.1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14799 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 20372.8862 | 0.2 | 0.3 | 31781.7025 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14800 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 21057.2993 | 0.2 | 0.3 | 32849.387 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2868.1411 | 2868.1411 | 2868.1411 | 2868.1411 | 2868.1411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14801 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 12401.8361 | 0.2 | 0.3 | 19346.8643 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6463.9726 | 6463.9726 | 6463.9726 | 6463.9726 | 6463.9726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14802 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 37.3335 | 0.2 | 0.3 | 58.2402 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9179 | 5200.9179 | 5200.9179 | 5200.9179 | 5200.9179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14803 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 28125.4599 | 0.2 | 0.3 | 43875.7175 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3705.6044 | 3705.6044 | 3705.6044 | 3705.6044 | 3705.6044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14804 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 21791.8194 | 0.2 | 0.3 | 33995.2383 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4422.3419 | 4422.3419 | 4422.3419 | 4422.3419 | 4422.3419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14805 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 14334.7569 | 0.2 | 0.3 | 22362.2208 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3756.2442 | 3756.2442 | 3756.2442 | 3756.2442 | 3756.2442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14806 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 7797.8697 | 0.2 | 0.3 | 12164.6768 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8262.7887 | 8262.7887 | 8262.7887 | 8262.7887 | 8262.7887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14807 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 18236.3791 | 0.2 | 0.3 | 28448.7514 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.701 | 5202.701 | 5202.701 | 5202.701 | 5202.701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14808 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 118.7543 | 0.2 | 0.3 | 185.2567 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7830.8317 | 7830.8317 | 7830.8317 | 7830.8317 | 7830.8317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14809 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 7584.2891 | 0.2 | 0.3 | 11831.4909 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8771.9417 | 8771.9417 | 8771.9417 | 8771.9417 | 8771.9417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14810 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 14748.9394 | 0.2 | 0.3 | 23008.3455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8150.2548 | 8150.2548 | 8150.2548 | 8150.2548 | 8150.2548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14811 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 1788.4821 | 0.2 | 0.3 | 2790.032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5483.1643 | 5483.1643 | 5483.1643 | 5483.1643 | 5483.1643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14812 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 23626.3542 | 0.2 | 0.3 | 36857.1126 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4309.9077 | 4309.9077 | 4309.9077 | 4309.9077 | 4309.9077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14813 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 26582.7125 | 0.2 | 0.3 | 41469.0316 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4634.7933 | 4634.7933 | 4634.7933 | 4634.7933 | 4634.7933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14814 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 23692.3737 | 0.2 | 0.3 | 36960.1029 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0152 | 5201.0152 | 5201.0152 | 5201.0152 | 5201.0152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14815 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 8553.7304 | 0.2 | 0.3 | 13343.8194 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5748.1797 | 5748.1797 | 5748.1797 | 5748.1797 | 5748.1797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14816 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 18995.6983 | 0.2 | 0.3 | 29633.2894 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9343.5764 | 9343.5764 | 9343.5764 | 9343.5764 | 9343.5764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14817 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 22847.2235 | 0.2 | 0.3 | 35641.6686 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10664.0962 | 10664.0962 | 10664.0962 | 10664.0962 | 10664.0962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14818 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 19191.0755 | 0.2 | 0.3 | 29938.0778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12340.8679 | 12340.8679 | 12340.8679 | 12340.8679 | 12340.8679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14819 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 21602.6887 | 0.2 | 0.3 | 33700.1944 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10402.1811 | 10402.1811 | 10402.1811 | 10402.1811 | 10402.1811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14820 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 14719.7181 | 0.2 | 0.3 | 22962.7602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4699.8721 | 4699.8721 | 4699.8721 | 4699.8721 | 4699.8721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14821 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 24223.6381 | 0.2 | 0.3 | 37788.8755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3527.066 | 3527.066 | 3527.066 | 3527.066 | 3527.066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14822 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 8051.0568 | 0.2 | 0.3 | 12559.6486 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5425.5914 | 5425.5914 | 5425.5914 | 5425.5914 | 5425.5914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14823 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 21971.6614 | 0.2 | 0.3 | 34275.7918 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 490.0382 | 490.0382 | 490.0382 | 490.0382 | 490.0382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14824 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 4953.3183 | 0.2 | 0.3 | 7727.1765 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4708.5904 | 4708.5904 | 4708.5904 | 4708.5904 | 4708.5904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14825 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16862.5923 | 0.2 | 0.3 | 26305.644 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 80.4246 | 80.4246 | 80.4246 | 80.4246 | 80.4246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14826 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6386.1656 | 6386.1656 | 6386.1656 | 6386.1656 | 6386.1656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14827 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16632.7563 | 0.2 | 0.3 | 25947.0999 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1932.9272 | 1932.9272 | 1932.9272 | 1932.9272 | 1932.9272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14828 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 8569.6528 | 0.2 | 0.3 | 13368.6584 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14829 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 32307.728 | 0.2 | 0.3 | 50400.0557 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14830 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 23592.4907 | 0.2 | 0.3 | 36804.2854 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5304.0941 | 5304.0941 | 5304.0941 | 5304.0941 | 5304.0941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14831 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16683.9874 | 0.2 | 0.3 | 26027.0203 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7520.7489 | 7520.7489 | 7520.7489 | 7520.7489 | 7520.7489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14832 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16669.4806 | 0.2 | 0.3 | 26004.3897 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5155.9119 | 5155.9119 | 5155.9119 | 5155.9119 | 5155.9119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14833 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16670.7018 | 0.2 | 0.3 | 26006.2948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4444.6463 | 4444.6463 | 4444.6463 | 4444.6463 | 4444.6463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14834 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 31337.8361 | 0.2 | 0.3 | 48887.0244 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5233.5563 | 5233.5563 | 5233.5563 | 5233.5563 | 5233.5563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14835 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 21193.0295 | 0.2 | 0.3 | 33061.126 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5235.8546 | 5235.8546 | 5235.8546 | 5235.8546 | 5235.8546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14836 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 14776.2391 | 0.2 | 0.3 | 23050.9329 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5232.8203 | 5232.8203 | 5232.8203 | 5232.8203 | 5232.8203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14837 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 12180.1691 | 0.2 | 0.3 | 19001.0638 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2334.7342 | 2334.7342 | 2334.7342 | 2334.7342 | 2334.7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14838 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 21663.7611 | 0.2 | 0.3 | 33795.4674 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14839 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 15238.4915 | 0.2 | 0.3 | 23772.0467 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5159.6253 | 5159.6253 | 5159.6253 | 5159.6253 | 5159.6253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14840 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 14629.3543 | 0.2 | 0.3 | 22821.7928 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5066.0394 | 5066.0394 | 5066.0394 | 5066.0394 | 5066.0394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14841 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 6762.2295 | 0.2 | 0.3 | 10549.0781 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2842.9738 | 2842.9738 | 2842.9738 | 2842.9738 | 2842.9738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14842 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 2162.9725 | 0.2 | 0.3 | 3374.2372 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7104.0427 | 7104.0427 | 7104.0427 | 7104.0427 | 7104.0427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14843 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 25413.1577 | 0.2 | 0.3 | 39644.526 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5144.024 | 5144.024 | 5144.024 | 5144.024 | 5144.024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14844 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16668.8254 | 0.2 | 0.3 | 26003.3676 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3042.0768 | 3042.0768 | 3042.0768 | 3042.0768 | 3042.0768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14845 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 20392.8192 | 0.2 | 0.3 | 31812.798 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2444.3378 | 2444.3378 | 2444.3378 | 2444.3378 | 2444.3378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14846 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 34490.0527 | 0.2 | 0.3 | 53804.4822 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 259.608 | 259.608 | 259.608 | 259.608 | 259.608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14847 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 14089.0209 | 0.2 | 0.3 | 21978.8726 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7515 | 5201.7515 | 5201.7515 | 5201.7515 | 5201.7515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14848 | COCONUT CREEK | 10606 | Public | 2036 | 5 | Swales | 66.6667 | 25996.971 | 0.2 | 0.3 | 40555.2748 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7111 | 5201.7111 | 5201.7111 | 5201.7111 | 5201.7111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14849 | COCONUT CREEK | 10606 | Public | 2036 | 5 | Swales | 66.6667 | 31392.0677 | 0.2 | 0.3 | 48971.6257 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14850 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 17316.1311 | 0.2 | 0.3 | 27013.1646 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9202 | 5201.9202 | 5201.9202 | 5201.9202 | 5201.9202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14851 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 16773.6304 | 0.2 | 0.3 | 26166.8634 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2171.9371 | 2171.9371 | 2171.9371 | 2171.9371 | 2171.9371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14852 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 13153.4547 | 0.2 | 0.3 | 20519.3894 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 810.7836 | 810.7836 | 810.7836 | 810.7836 | 810.7836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14853 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 8019.2603 | 0.2 | 0.3 | 12510.0461 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2596.3806 | 2596.3806 | 2596.3806 | 2596.3806 | 2596.3806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14854 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 16672.3415 | 0.2 | 0.3 | 26008.8527 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2702.674 | 2702.674 | 2702.674 | 2702.674 | 2702.674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14855 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16666.4169 | 0.2 | 0.3 | 25999.6104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4122.3217 | 4122.3217 | 4122.3217 | 4122.3217 | 4122.3217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14856 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 5997.4511 | 0.2 | 0.3 | 9356.0238 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6398.3671 | 6398.3671 | 6398.3671 | 6398.3671 | 6398.3671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14857 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 24738.7005 | 0.2 | 0.3 | 38592.3728 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4390.9399 | 4390.9399 | 4390.9399 | 4390.9399 | 4390.9399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14858 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 18679.1047 | 0.2 | 0.3 | 29139.4034 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2605.6312 | 2605.6312 | 2605.6312 | 2605.6312 | 2605.6312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14859 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 3121.7983 | 0.2 | 0.3 | 4870.0054 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2498.0913 | 2498.0913 | 2498.0913 | 2498.0913 | 2498.0913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14860 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 7746.3159 | 0.2 | 0.3 | 12084.2528 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2039.3302 | 2039.3302 | 2039.3302 | 2039.3302 | 2039.3302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14861 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 33573.5701 | 0.2 | 0.3 | 52374.7693 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5624.5923 | 5624.5923 | 5624.5923 | 5624.5923 | 5624.5923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14862 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 21909.98 | 0.2 | 0.3 | 34179.5688 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7235 | 5201.7235 | 5201.7235 | 5201.7235 | 5201.7235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14863 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16666.5792 | 0.2 | 0.3 | 25999.8636 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5837 | 5201.5837 | 5201.5837 | 5201.5837 | 5201.5837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14864 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 26171.8478 | 0.2 | 0.3 | 40828.0826 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14865 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 23186.2525 | 0.2 | 0.3 | 36170.5538 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5754.0597 | 5754.0597 | 5754.0597 | 5754.0597 | 5754.0597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14866 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 11420.8428 | 0.2 | 0.3 | 17816.5148 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 731.4244 | 731.4244 | 731.4244 | 731.4244 | 731.4244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14867 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 17158.5949 | 0.2 | 0.3 | 26767.4081 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14868 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 16996.819 | 0.2 | 0.3 | 26515.0376 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7121.3105 | 7121.3105 | 7121.3105 | 7121.3105 | 7121.3105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14869 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 19856.0955 | 0.2 | 0.3 | 30975.509 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2834 | 5203.2834 | 5203.2834 | 5203.2834 | 5203.2834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14870 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 38523.9545 | 0.2 | 0.3 | 60097.3691 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14871 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 1229.4497 | 0.2 | 0.3 | 1917.9416 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4421.7547 | 4421.7547 | 4421.7547 | 4421.7547 | 4421.7547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14872 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 8275.7664 | 0.2 | 0.3 | 12910.1956 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5212.3479 | 5212.3479 | 5212.3479 | 5212.3479 | 5212.3479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14873 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 16716.0043 | 0.2 | 0.3 | 26076.9667 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14874 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 11810.3441 | 0.2 | 0.3 | 18424.1367 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7203.7781 | 7203.7781 | 7203.7781 | 7203.7781 | 7203.7781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14875 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 17778.26 | 0.2 | 0.3 | 27734.0856 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6543.3053 | 6543.3053 | 6543.3053 | 6543.3053 | 6543.3053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14876 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 16624.1132 | 0.2 | 0.3 | 25933.6166 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.4775 | 5204.4775 | 5204.4775 | 5204.4775 | 5204.4775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14877 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 16548.5646 | 0.2 | 0.3 | 25815.7608 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4248.7642 | 4248.7642 | 4248.7642 | 4248.7642 | 4248.7642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14878 | CORAL SPRINGS | 10611 | Public | 2036 | 5 | Swales | 66.6667 | 24096.8613 | 0.2 | 0.3 | 37591.1037 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5590.7105 | 5590.7105 | 5590.7105 | 5590.7105 | 5590.7105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14879 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 39243.2297 | 0.2 | 0.3 | 61219.4384 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9813.4101 | 9813.4101 | 9813.4101 | 9813.4101 | 9813.4101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14880 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 19305.1831 | 0.2 | 0.3 | 30116.0856 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9022.6149 | 9022.6149 | 9022.6149 | 9022.6149 | 9022.6149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14881 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 23682.5387 | 0.2 | 0.3 | 36944.7603 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9258.9026 | 9258.9026 | 9258.9026 | 9258.9026 | 9258.9026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14882 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16688.5239 | 0.2 | 0.3 | 26034.0972 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14883 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 4424.8035 | 0.2 | 0.3 | 6902.6934 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8392.6145 | 8392.6145 | 8392.6145 | 8392.6145 | 8392.6145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14884 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 24421.2737 | 0.2 | 0.3 | 38097.187 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3301.1102 | 3301.1102 | 3301.1102 | 3301.1102 | 3301.1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14885 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 10572.0909 | 0.2 | 0.3 | 16492.4618 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6938.639 | 6938.639 | 6938.639 | 6938.639 | 6938.639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14886 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 31641.4054 | 0.2 | 0.3 | 49360.5924 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14887 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 21903.3499 | 0.2 | 0.3 | 34169.2259 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4074 | 5202.4074 | 5202.4074 | 5202.4074 | 5202.4074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14888 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 18477.9104 | 0.2 | 0.3 | 28825.5402 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6054.5885 | 6054.5885 | 6054.5885 | 6054.5885 | 6054.5885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14889 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 17423.8069 | 0.2 | 0.3 | 27181.1388 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14890 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16593.9181 | 0.2 | 0.3 | 25886.5123 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14891 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16668.9212 | 0.2 | 0.3 | 26003.5171 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14892 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 31334.5415 | 0.2 | 0.3 | 48881.8848 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14893 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16667.4696 | 0.2 | 0.3 | 26001.2526 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2564.2782 | 2564.2782 | 2564.2782 | 2564.2782 | 2564.2782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14894 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16757.7841 | 0.2 | 0.3 | 26142.1432 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7447.444 | 7447.444 | 7447.444 | 7447.444 | 7447.444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14895 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 19200.1727 | 0.2 | 0.3 | 29952.2694 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14896 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 17991.2898 | 0.2 | 0.3 | 28066.4121 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.679 | 5200.679 | 5200.679 | 5200.679 | 5200.679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14897 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 24964.283 | 0.2 | 0.3 | 38944.2815 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7758.499 | 7758.499 | 7758.499 | 7758.499 | 7758.499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14898 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 20277.3297 | 0.2 | 0.3 | 31632.6343 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.9279 | 2600.9279 | 2600.9279 | 2600.9279 | 2600.9279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14899 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17698.5993 | 0.2 | 0.3 | 27609.8149 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7069.5258 | 7069.5258 | 7069.5258 | 7069.5258 | 7069.5258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14900 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 8696.6923 | 0.2 | 0.3 | 13566.8399 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6026.977 | 6026.977 | 6026.977 | 6026.977 | 6026.977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14901 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 9196.4709 | 0.2 | 0.3 | 14346.4946 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3371 | 5202.3371 | 5202.3371 | 5202.3371 | 5202.3371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14902 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16682.9236 | 0.2 | 0.3 | 26025.3608 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14903 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 11030.4449 | 0.2 | 0.3 | 17207.4941 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4531 | 5202.4531 | 5202.4531 | 5202.4531 | 5202.4531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14904 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 8569.1394 | 0.2 | 0.3 | 13367.8575 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6146.9061 | 6146.9061 | 6146.9061 | 6146.9061 | 6146.9061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14905 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 318.7114 | 0.2 | 0.3 | 497.1898 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1221 | 5201.1221 | 5201.1221 | 5201.1221 | 5201.1221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14906 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 22624.8153 | 0.2 | 0.3 | 35294.7119 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9989 | 5201.9989 | 5201.9989 | 5201.9989 | 5201.9989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14907 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16641.5358 | 0.2 | 0.3 | 25960.7958 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3095 | 5202.3095 | 5202.3095 | 5202.3095 | 5202.3095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14908 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 20373.9923 | 0.2 | 0.3 | 31783.428 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7804 | 5200.7804 | 5200.7804 | 5200.7804 | 5200.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14909 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 38459.0476 | 0.2 | 0.3 | 59996.1143 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5279.687 | 5279.687 | 5279.687 | 5279.687 | 5279.687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14910 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 25282.0968 | 0.2 | 0.3 | 39440.071 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9999 | 5199.9999 | 5199.9999 | 5199.9999 | 5199.9999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14911 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 27378.5357 | 0.2 | 0.3 | 42710.5156 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4019.1041 | 4019.1041 | 4019.1041 | 4019.1041 | 4019.1041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14912 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 34697.2349 | 0.2 | 0.3 | 54127.6864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 645.5226 | 645.5226 | 645.5226 | 645.5226 | 645.5226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14913 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 18623.0524 | 0.2 | 0.3 | 29051.9617 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4555.276 | 4555.276 | 4555.276 | 4555.276 | 4555.276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14914 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16680.6535 | 0.2 | 0.3 | 26021.8195 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5216.6549 | 5216.6549 | 5216.6549 | 5216.6549 | 5216.6549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14915 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 17275.3706 | 0.2 | 0.3 | 26949.5781 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2601.0132 | 2601.0132 | 2601.0132 | 2601.0132 | 2601.0132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14916 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 18070.7151 | 0.2 | 0.3 | 28190.3156 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6762.319 | 6762.319 | 6762.319 | 6762.319 | 6762.319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14917 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 20270.0468 | 0.2 | 0.3 | 31621.273 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7109.5545 | 7109.5545 | 7109.5545 | 7109.5545 | 7109.5545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14918 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16669.6074 | 0.2 | 0.3 | 26004.5875 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7606 | 5202.7606 | 5202.7606 | 5202.7606 | 5202.7606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14919 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16670.1543 | 0.2 | 0.3 | 26005.4407 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0622 | 5202.0622 | 5202.0622 | 5202.0622 | 5202.0622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14920 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16671.7947 | 0.2 | 0.3 | 26007.9997 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.7968 | 5199.7968 | 5199.7968 | 5199.7968 | 5199.7968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14921 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 12904.6434 | 0.2 | 0.3 | 20131.2437 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.7342 | 9778.7342 | 9778.7342 | 9778.7342 | 9778.7342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14922 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 12772.4097 | 0.2 | 0.3 | 19924.9592 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9781.49 | 9781.49 | 9781.49 | 9781.49 | 9781.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14923 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 17248.1298 | 0.2 | 0.3 | 26907.0825 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9780.0887 | 9780.0887 | 9780.0887 | 9780.0887 | 9780.0887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14924 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 15824.5072 | 0.2 | 0.3 | 24686.2312 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.4119 | 9779.4119 | 9779.4119 | 9779.4119 | 9779.4119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14925 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 14577.1243 | 0.2 | 0.3 | 22740.314 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9780.1302 | 9780.1302 | 9780.1302 | 9780.1302 | 9780.1302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14926 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 25465.7862 | 0.2 | 0.3 | 39726.6265 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3638.2384 | 3638.2384 | 3638.2384 | 3638.2384 | 3638.2384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14927 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 37011.8226 | 0.2 | 0.3 | 57738.4433 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2090.0149 | 2090.0149 | 2090.0149 | 2090.0149 | 2090.0149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14928 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 18221.7745 | 0.2 | 0.3 | 28425.9682 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14929 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 27174.884 | 0.2 | 0.3 | 42392.819 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4196.5536 | 4196.5536 | 4196.5536 | 4196.5536 | 4196.5536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14930 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 49.8185 | 0.2 | 0.3 | 77.7168 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10625.2746 | 10625.2746 | 10625.2746 | 10625.2746 | 10625.2746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14931 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 17208.7499 | 0.2 | 0.3 | 26845.6498 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10405.4229 | 10405.4229 | 10405.4229 | 10405.4229 | 10405.4229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14932 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16288.6865 | 0.2 | 0.3 | 25410.3509 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10403.187 | 10403.187 | 10403.187 | 10403.187 | 10403.187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14933 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 24994.3407 | 0.2 | 0.3 | 38991.1715 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8212.836 | 8212.836 | 8212.836 | 8212.836 | 8212.836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14934 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 32486.7906 | 0.2 | 0.3 | 50679.3933 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4901 | 5202.4901 | 5202.4901 | 5202.4901 | 5202.4901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14935 | COCONUT CREEK | 10606 | Public | 2036 | 5 | Swales | 66.6667 | 45221.1856 | 0.2 | 0.3 | 70545.0495 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14936 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 12852.3487 | 0.2 | 0.3 | 20049.6639 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5486 | 5202.5486 | 5202.5486 | 5202.5486 | 5202.5486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14937 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 16844.5931 | 0.2 | 0.3 | 26277.5652 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6515.822 | 6515.822 | 6515.822 | 6515.822 | 6515.822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14938 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 17684.4607 | 0.2 | 0.3 | 27587.7586 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.3266 | 5204.3266 | 5204.3266 | 5204.3266 | 5204.3266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14939 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 7760.8933 | 0.2 | 0.3 | 12106.9935 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.953 | 5202.953 | 5202.953 | 5202.953 | 5202.953 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14940 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 32542.96 | 0.2 | 0.3 | 50767.0176 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2615 | 5202.2615 | 5202.2615 | 5202.2615 | 5202.2615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14941 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 16763.5234 | 0.2 | 0.3 | 26151.0965 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4709.2013 | 4709.2013 | 4709.2013 | 4709.2013 | 4709.2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14942 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 16749.7143 | 0.2 | 0.3 | 26129.5543 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2599.9911 | 2599.9911 | 2599.9911 | 2599.9911 | 2599.9911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14943 | COCONUT CREEK | 10615 | Private | 2036 | 5 | Swales | 66.6667 | 22898.2645 | 0.2 | 0.3 | 35721.2927 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2599.9911 | 2599.9911 | 2599.9911 | 2599.9911 | 2599.9911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14944 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5397 | 5200.5397 | 5200.5397 | 5200.5397 | 5200.5397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14945 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 17162.4395 | 0.2 | 0.3 | 26773.4057 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1006.6238 | 1006.6238 | 1006.6238 | 1006.6238 | 1006.6238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14946 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 8675.3916 | 0.2 | 0.3 | 13533.6109 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.3909 | 5205.3909 | 5205.3909 | 5205.3909 | 5205.3909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14947 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 11671.6453 | 0.2 | 0.3 | 18207.7667 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.421 | 5202.421 | 5202.421 | 5202.421 | 5202.421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14948 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 17415.5755 | 0.2 | 0.3 | 27168.2977 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14949 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16880.4489 | 0.2 | 0.3 | 26333.5003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3882 | 5202.3882 | 5202.3882 | 5202.3882 | 5202.3882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14950 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 12806.403 | 0.2 | 0.3 | 19977.9887 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6693.8031 | 6693.8031 | 6693.8031 | 6693.8031 | 6693.8031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14951 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 6394.1263 | 0.2 | 0.3 | 9974.837 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.0264 | 5203.0264 | 5203.0264 | 5203.0264 | 5203.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14952 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 26785.562 | 0.2 | 0.3 | 41785.4767 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6585 | 5202.6585 | 5202.6585 | 5202.6585 | 5202.6585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14953 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 27835.7853 | 0.2 | 0.3 | 43423.8251 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6425 | 5202.6425 | 5202.6425 | 5202.6425 | 5202.6425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14954 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 28725.5935 | 0.2 | 0.3 | 44811.9259 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2725.721 | 2725.721 | 2725.721 | 2725.721 | 2725.721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14955 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 32616.8945 | 0.2 | 0.3 | 50882.3555 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6438.1346 | 6438.1346 | 6438.1346 | 6438.1346 | 6438.1346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14956 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 4704.9143 | 0.2 | 0.3 | 7339.6664 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5662.591 | 5662.591 | 5662.591 | 5662.591 | 5662.591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14957 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 28718.2516 | 0.2 | 0.3 | 44800.4725 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5582.2758 | 5582.2758 | 5582.2758 | 5582.2758 | 5582.2758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14958 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2958 | 5200.2958 | 5200.2958 | 5200.2958 | 5200.2958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14959 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 16669.7279 | 0.2 | 0.3 | 26004.7755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5537.5395 | 5537.5395 | 5537.5395 | 5537.5395 | 5537.5395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14960 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 1188.7915 | 0.2 | 0.3 | 1854.5148 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14961 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 14163.7297 | 0.2 | 0.3 | 22095.4184 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9677.9272 | 9677.9272 | 9677.9272 | 9677.9272 | 9677.9272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14962 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 15046.5311 | 0.2 | 0.3 | 23472.5886 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4061 | 5201.4061 | 5201.4061 | 5201.4061 | 5201.4061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14963 | CORAL SPRINGS | 10603 | Private | 2036 | 5 | Swales | 66.6667 | 223.6741 | 0.2 | 0.3 | 348.9316 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14964 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 17522.0838 | 0.2 | 0.3 | 27334.4507 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9438 | 5201.9438 | 5201.9438 | 5201.9438 | 5201.9438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14965 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 5754.0489 | 0.2 | 0.3 | 8976.3162 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14966 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 9287.8279 | 0.2 | 0.3 | 14489.0115 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2116 | 5202.2116 | 5202.2116 | 5202.2116 | 5202.2116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14967 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 8894.2305 | 0.2 | 0.3 | 13874.9995 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6833.9054 | 6833.9054 | 6833.9054 | 6833.9054 | 6833.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14968 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16581.533 | 0.2 | 0.3 | 25867.1915 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9512 | 5200.9512 | 5200.9512 | 5200.9512 | 5200.9512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14969 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 25719.9558 | 0.2 | 0.3 | 40123.131 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.1393 | 5199.1393 | 5199.1393 | 5199.1393 | 5199.1393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14970 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16668.5147 | 0.2 | 0.3 | 26002.883 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3432.029 | 3432.029 | 3432.029 | 3432.029 | 3432.029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14971 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 25917.3139 | 0.2 | 0.3 | 40431.0096 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4374.6891 | 4374.6891 | 4374.6891 | 4374.6891 | 4374.6891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14972 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2404 | 0.2 | 0.3 | 26002.455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2776 | 5200.2776 | 5200.2776 | 5200.2776 | 5200.2776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14973 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16983.0539 | 0.2 | 0.3 | 26493.5641 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14974 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 298.2937 | 0.2 | 0.3 | 465.3382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3733.9771 | 3733.9771 | 3733.9771 | 3733.9771 | 3733.9771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14975 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 18202.1585 | 0.2 | 0.3 | 28395.3673 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9025.7573 | 9025.7573 | 9025.7573 | 9025.7573 | 9025.7573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14976 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16908.4465 | 0.2 | 0.3 | 26377.1765 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.536 | 5203.536 | 5203.536 | 5203.536 | 5203.536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14977 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 26788.1672 | 0.2 | 0.3 | 41789.5408 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8965.5548 | 8965.5548 | 8965.5548 | 8965.5548 | 8965.5548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14978 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16666.7069 | 0.2 | 0.3 | 26000.0628 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14979 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9562.0051 | 9562.0051 | 9562.0051 | 9562.0051 | 9562.0051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14980 | CORAL SPRINGS | 10604 | Public | 2036 | 5 | Swales | 66.6667 | 23870.9149 | 0.2 | 0.3 | 37238.6272 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5624.7756 | 5624.7756 | 5624.7756 | 5624.7756 | 5624.7756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14981 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16653.9658 | 0.2 | 0.3 | 25980.1866 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6097.6298 | 6097.6298 | 6097.6298 | 6097.6298 | 6097.6298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14982 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 20638.9977 | 0.2 | 0.3 | 32196.8364 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7262.4621 | 7262.4621 | 7262.4621 | 7262.4621 | 7262.4621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14983 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 9444.6017 | 0.2 | 0.3 | 14733.5786 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7131.2162 | 7131.2162 | 7131.2162 | 7131.2162 | 7131.2162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14984 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 26712.2801 | 0.2 | 0.3 | 41671.157 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7336.5952 | 7336.5952 | 7336.5952 | 7336.5952 | 7336.5952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14985 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16350.4107 | 0.2 | 0.3 | 25506.6406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6485.5495 | 6485.5495 | 6485.5495 | 6485.5495 | 6485.5495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14986 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 17299.998 | 0.2 | 0.3 | 26987.9969 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1032 | 5200.1032 | 5200.1032 | 5200.1032 | 5200.1032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14987 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 24051.1236 | 0.2 | 0.3 | 37519.7528 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14988 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 21312.1583 | 0.2 | 0.3 | 33246.967 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.4013 | 5203.4013 | 5203.4013 | 5203.4013 | 5203.4013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14989 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 15418.9943 | 0.2 | 0.3 | 24053.6312 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8708.2257 | 8708.2257 | 8708.2257 | 8708.2257 | 8708.2257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14990 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 33971.3906 | 0.2 | 0.3 | 52995.3693 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 64.5801 | 64.5801 | 64.5801 | 64.5801 | 64.5801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14991 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 12149.5266 | 0.2 | 0.3 | 18953.2615 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7540.7455 | 7540.7455 | 7540.7455 | 7540.7455 | 7540.7455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14992 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 12780.762 | 0.2 | 0.3 | 19937.9887 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1545.7675 | 1545.7675 | 1545.7675 | 1545.7675 | 1545.7675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14993 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 4518.396 | 0.2 | 0.3 | 7048.6978 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10788.0009 | 10788.0009 | 10788.0009 | 10788.0009 | 10788.0009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14994 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16670.7011 | 0.2 | 0.3 | 26006.2937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8343.5068 | 8343.5068 | 8343.5068 | 8343.5068 | 8343.5068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14995 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 18441.2728 | 0.2 | 0.3 | 28768.3856 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7910.1754 | 7910.1754 | 7910.1754 | 7910.1754 | 7910.1754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14996 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 11985.3817 | 0.2 | 0.3 | 18697.1954 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1008.2938 | 1008.2938 | 1008.2938 | 1008.2938 | 1008.2938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14997 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 23502.7252 | 0.2 | 0.3 | 36664.2513 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7449.1684 | 7449.1684 | 7449.1684 | 7449.1684 | 7449.1684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14998 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 18540.3142 | 0.2 | 0.3 | 28922.8902 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5988.6128 | 5988.6128 | 5988.6128 | 5988.6128 | 5988.6128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14999 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 10209.5277 | 0.2 | 0.3 | 15926.8633 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10718.4538 | 10718.4538 | 10718.4538 | 10718.4538 | 10718.4538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15000 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 7647.7343 | 0.2 | 0.3 | 11930.4655 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2809 | 5201.2809 | 5201.2809 | 5201.2809 | 5201.2809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15001 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 24165.8345 | 0.2 | 0.3 | 37698.7019 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 5202.1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15002 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2386 | 5202.2386 | 5202.2386 | 5202.2386 | 5202.2386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15003 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 24523.2241 | 0.2 | 0.3 | 38256.2295 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 473.709 | 473.709 | 473.709 | 473.709 | 473.709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15004 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 25290.1179 | 0.2 | 0.3 | 39452.5839 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5392.8163 | 5392.8163 | 5392.8163 | 5392.8163 | 5392.8163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15005 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 16706.8787 | 0.2 | 0.3 | 26062.7307 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15006 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 16696.0933 | 0.2 | 0.3 | 26045.9055 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3173 | 5200.3173 | 5200.3173 | 5200.3173 | 5200.3173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15007 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 16669.7201 | 0.2 | 0.3 | 26004.7633 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4718.9623 | 4718.9623 | 4718.9623 | 4718.9623 | 4718.9623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15008 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 14209.4351 | 0.2 | 0.3 | 22166.7187 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 689.7323 | 689.7323 | 689.7323 | 689.7323 | 689.7323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15009 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 18298.4494 | 0.2 | 0.3 | 28545.5811 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5231.5298 | 5231.5298 | 5231.5298 | 5231.5298 | 5231.5298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15010 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 3443.1876 | 0.2 | 0.3 | 5371.3727 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15011 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 19084.3985 | 0.2 | 0.3 | 29771.6616 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1732 | 5203.1732 | 5203.1732 | 5203.1732 | 5203.1732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15012 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 17980.6191 | 0.2 | 0.3 | 28049.7657 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2791.2789 | 2791.2789 | 2791.2789 | 2791.2789 | 2791.2789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15013 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 3785.0479 | 0.2 | 0.3 | 5904.6747 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2163.9659 | 2163.9659 | 2163.9659 | 2163.9659 | 2163.9659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15014 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 10682.7862 | 0.2 | 0.3 | 16665.1465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2061.7172 | 2061.7172 | 2061.7172 | 2061.7172 | 2061.7172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15015 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 17139.9449 | 0.2 | 0.3 | 26738.314 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 27.479 | 27.479 | 27.479 | 27.479 | 27.479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15016 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 16731.9288 | 0.2 | 0.3 | 26101.8089 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5226.508 | 5226.508 | 5226.508 | 5226.508 | 5226.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15017 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 14420.6692 | 0.2 | 0.3 | 22496.244 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4194.9444 | 4194.9444 | 4194.9444 | 4194.9444 | 4194.9444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15018 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 10848.6493 | 0.2 | 0.3 | 16923.893 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6266.0672 | 6266.0672 | 6266.0672 | 6266.0672 | 6266.0672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15019 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 20660.5715 | 0.2 | 0.3 | 32230.4915 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1284.6456 | 1284.6456 | 1284.6456 | 1284.6456 | 1284.6456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15020 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 21378.8333 | 0.2 | 0.3 | 33350.98 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2069.0544 | 2069.0544 | 2069.0544 | 2069.0544 | 2069.0544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15021 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 19843.8987 | 0.2 | 0.3 | 30956.482 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3133.0748 | 3133.0748 | 3133.0748 | 3133.0748 | 3133.0748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15022 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 20165.7746 | 0.2 | 0.3 | 31458.6084 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8153.9244 | 8153.9244 | 8153.9244 | 8153.9244 | 8153.9244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15023 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 11073.5778 | 0.2 | 0.3 | 17274.7814 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4072.5415 | 4072.5415 | 4072.5415 | 4072.5415 | 4072.5415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15024 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.722 | 5202.722 | 5202.722 | 5202.722 | 5202.722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15025 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2414.3782 | 2414.3782 | 2414.3782 | 2414.3782 | 2414.3782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15026 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 18390.7018 | 0.2 | 0.3 | 28689.4948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6195.5173 | 6195.5173 | 6195.5173 | 6195.5173 | 6195.5173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15027 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16667.6172 | 0.2 | 0.3 | 26001.4828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2730.083 | 2730.083 | 2730.083 | 2730.083 | 2730.083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15028 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 27605.7794 | 0.2 | 0.3 | 43065.0159 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4735 | 5200.4735 | 5200.4735 | 5200.4735 | 5200.4735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15029 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.508 | 5201.508 | 5201.508 | 5201.508 | 5201.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15030 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 8302.2284 | 0.2 | 0.3 | 12951.4763 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 45.9547 | 45.9547 | 45.9547 | 45.9547 | 45.9547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15031 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 13066.6108 | 0.2 | 0.3 | 20383.9128 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5156.1183 | 5156.1183 | 5156.1183 | 5156.1183 | 5156.1183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15032 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8192 | 0.2 | 0.3 | 26000.238 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8721.332 | 8721.332 | 8721.332 | 8721.332 | 8721.332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15033 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 16666.205 | 0.2 | 0.3 | 25999.2798 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3188.7315 | 3188.7315 | 3188.7315 | 3188.7315 | 3188.7315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15034 | CORAL SPRINGS | 10612 | Private | 2036 | 5 | Swales | 66.6667 | 13195.0597 | 0.2 | 0.3 | 20584.2931 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4363.7921 | 4363.7921 | 4363.7921 | 4363.7921 | 4363.7921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15035 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 16922.6665 | 0.2 | 0.3 | 26399.3598 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15036 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 2482.2223 | 0.2 | 0.3 | 3872.2668 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2441.5057 | 2441.5057 | 2441.5057 | 2441.5057 | 2441.5057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15037 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 35553.65 | 0.2 | 0.3 | 55463.694 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3302 | 5201.3302 | 5201.3302 | 5201.3302 | 5201.3302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15038 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 23038.0995 | 0.2 | 0.3 | 35939.4352 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2673 | 5201.2673 | 5201.2673 | 5201.2673 | 5201.2673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15039 | CORAL SPRINGS | 10611 | Private | 2036 | 5 | Swales | 66.6667 | 31404.7189 | 0.2 | 0.3 | 48991.3615 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1075 | 5200.1075 | 5200.1075 | 5200.1075 | 5200.1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15040 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 13562.4053 | 0.2 | 0.3 | 21157.3522 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3956.4392 | 3956.4392 | 3956.4392 | 3956.4392 | 3956.4392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15041 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16666.2555 | 0.2 | 0.3 | 25999.3586 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.627 | 5199.627 | 5199.627 | 5199.627 | 5199.627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15042 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 16666.5117 | 0.2 | 0.3 | 25999.7583 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3722 | 5201.3722 | 5201.3722 | 5201.3722 | 5201.3722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15043 | CORAL SPRINGS | 10603 | Public | 2036 | 5 | Swales | 66.6667 | 26451.6322 | 0.2 | 0.3 | 41264.5462 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3709.1362 | 3709.1362 | 3709.1362 | 3709.1362 | 3709.1362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15044 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 16618.7546 | 0.2 | 0.3 | 25925.2572 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7688.1635 | 7688.1635 | 7688.1635 | 7688.1635 | 7688.1635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15045 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8502 | 0.2 | 0.3 | 26000.2863 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7134.5974 | 7134.5974 | 7134.5974 | 7134.5974 | 7134.5974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15046 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 25390.7249 | 0.2 | 0.3 | 39609.5308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14205.2618 | 14205.2618 | 14205.2618 | 14205.2618 | 14205.2618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15047 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 16667.2377 | 0.2 | 0.3 | 26000.8908 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7443.9938 | 7443.9938 | 7443.9938 | 7443.9938 | 7443.9938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15048 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 12182.3173 | 0.2 | 0.3 | 19004.4149 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.0602 | 5203.0602 | 5203.0602 | 5203.0602 | 5203.0602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15049 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 12806.0545 | 0.2 | 0.3 | 19977.445 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1903.3961 | 1903.3961 | 1903.3961 | 1903.3961 | 1903.3961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15050 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 27912.6328 | 0.2 | 0.3 | 43543.7072 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1932.2706 | 1932.2706 | 1932.2706 | 1932.2706 | 1932.2706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15051 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 16882.944 | 0.2 | 0.3 | 26337.3926 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3318.5093 | 3318.5093 | 3318.5093 | 3318.5093 | 3318.5093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15052 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5059.7651 | 5059.7651 | 5059.7651 | 5059.7651 | 5059.7651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15053 | CORAL SPRINGS | 10604 | Private | 2036 | 5 | Swales | 66.6667 | 20675.8175 | 0.2 | 0.3 | 32254.2752 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1133.6871 | 1133.6871 | 1133.6871 | 1133.6871 | 1133.6871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15054 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16670.946 | 0.2 | 0.3 | 26006.6758 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8149.5934 | 8149.5934 | 8149.5934 | 8149.5934 | 8149.5934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15055 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16799.4253 | 0.2 | 0.3 | 26207.1035 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15056 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 14710.9084 | 0.2 | 0.3 | 22949.0171 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7500.8174 | 7500.8174 | 7500.8174 | 7500.8174 | 7500.8174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15057 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 16667.6151 | 0.2 | 0.3 | 26001.4796 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7480.9769 | 7480.9769 | 7480.9769 | 7480.9769 | 7480.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15058 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16667.543 | 0.2 | 0.3 | 26001.3671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15059 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16669.0781 | 0.2 | 0.3 | 26003.7619 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2210.7192 | 2210.7192 | 2210.7192 | 2210.7192 | 2210.7192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15060 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 16668.1659 | 0.2 | 0.3 | 26002.3389 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15061 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 15969.3744 | 0.2 | 0.3 | 24912.2241 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4499 | 5201.4499 | 5201.4499 | 5201.4499 | 5201.4499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15062 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15063 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 15623.0865 | 0.2 | 0.3 | 24372.0149 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15064 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 1500.5222 | 0.2 | 0.3 | 2340.8146 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6980.5843 | 6980.5843 | 6980.5843 | 6980.5843 | 6980.5843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15065 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 22666.0765 | 0.2 | 0.3 | 35359.0793 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5423.7764 | 5423.7764 | 5423.7764 | 5423.7764 | 5423.7764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15066 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 24287.1273 | 0.2 | 0.3 | 37887.9186 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13559.454 | 13559.454 | 13559.454 | 13559.454 | 13559.454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15067 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 16636.8023 | 0.2 | 0.3 | 25953.4116 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6827.6148 | 6827.6148 | 6827.6148 | 6827.6148 | 6827.6148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15068 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 22446.5079 | 0.2 | 0.3 | 35016.5524 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5196.0553 | 5196.0553 | 5196.0553 | 5196.0553 | 5196.0553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15069 | CORAL SPRINGS | 10605 | Private | 2036 | 5 | Swales | 66.6667 | 13703.3687 | 0.2 | 0.3 | 21377.2552 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5190.6799 | 5190.6799 | 5190.6799 | 5190.6799 | 5190.6799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15070 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 17646.5224 | 0.2 | 0.3 | 27528.5749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5195.7994 | 5195.7994 | 5195.7994 | 5195.7994 | 5195.7994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15071 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 23991.9796 | 0.2 | 0.3 | 37427.4882 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8179.0784 | 8179.0784 | 8179.0784 | 8179.0784 | 8179.0784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15072 | CORAL SPRINGS | 10605 | Public | 2036 | 5 | Swales | 66.6667 | 13998.8713 | 0.2 | 0.3 | 21838.2393 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9519.8171 | 9519.8171 | 9519.8171 | 9519.8171 | 9519.8171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15073 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 2911.1942 | 0.2 | 0.3 | 4541.463 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1212.552 | 1212.552 | 1212.552 | 1212.552 | 1212.552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15074 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 23604.7506 | 0.2 | 0.3 | 36823.4109 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13108.6446 | 13108.6446 | 13108.6446 | 13108.6446 | 13108.6446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15075 | COCONUT CREEK | 10606 | Private | 2036 | 5 | Swales | 66.6667 | 19823.1785 | 0.2 | 0.3 | 30924.1584 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10112.381 | 10112.381 | 10112.381 | 10112.381 | 10112.381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15076 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16677.8667 | 0.2 | 0.3 | 26017.4721 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5208.0698 | 5208.0698 | 5208.0698 | 5208.0698 | 5208.0698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15077 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 3897.4405 | 0.2 | 0.3 | 6080.0071 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5576.6833 | 5576.6833 | 5576.6833 | 5576.6833 | 5576.6833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15078 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 11447.0317 | 0.2 | 0.3 | 17857.3695 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6071 | 5202.6071 | 5202.6071 | 5202.6071 | 5202.6071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15079 | CORAL SPRINGS | 20326 | Private | 2036 | 5 | Swales | 66.6667 | 20906.5147 | 0.2 | 0.3 | 32614.1629 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3645 | 5202.3645 | 5202.3645 | 5202.3645 | 5202.3645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15080 | CORAL SPRINGS | 20326 | Private | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15081 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.9011 | 0.2 | 0.3 | 26000.3657 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15082 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 7471.1665 | 0.2 | 0.3 | 11655.0198 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0842 | 5202.0842 | 5202.0842 | 5202.0842 | 5202.0842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15083 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 13318.8356 | 0.2 | 0.3 | 20777.3835 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5895.9772 | 5895.9772 | 5895.9772 | 5895.9772 | 5895.9772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15084 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16666.8645 | 0.2 | 0.3 | 26000.3086 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 177.3099 | 177.3099 | 177.3099 | 177.3099 | 177.3099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15085 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 20793.9192 | 0.2 | 0.3 | 32438.514 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7080.5502 | 7080.5502 | 7080.5502 | 7080.5502 | 7080.5502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15086 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 18421.3811 | 0.2 | 0.3 | 28737.3545 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4067.9587 | 4067.9587 | 4067.9587 | 4067.9587 | 4067.9587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15087 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16667.8105 | 0.2 | 0.3 | 26001.7844 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7984.5962 | 7984.5962 | 7984.5962 | 7984.5962 | 7984.5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15088 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 29306.0059 | 0.2 | 0.3 | 45717.3693 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15089 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16645.9388 | 0.2 | 0.3 | 25967.6645 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7448.7736 | 7448.7736 | 7448.7736 | 7448.7736 | 7448.7736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15090 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16666.6431 | 0.2 | 0.3 | 25999.9632 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7535.1956 | 7535.1956 | 7535.1956 | 7535.1956 | 7535.1956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15091 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 17371.1246 | 0.2 | 0.3 | 27098.9544 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15092 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 22931.9108 | 0.2 | 0.3 | 35773.7808 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4221 | 5201.4221 | 5201.4221 | 5201.4221 | 5201.4221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15093 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 16601.8037 | 0.2 | 0.3 | 25898.8137 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15094 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 18430.6092 | 0.2 | 0.3 | 28751.7504 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15095 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 11767.3367 | 0.2 | 0.3 | 18357.0453 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15096 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 16702.6053 | 0.2 | 0.3 | 26056.0643 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8223.8924 | 8223.8924 | 8223.8924 | 8223.8924 | 8223.8924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15097 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 16669.5699 | 0.2 | 0.3 | 26004.529 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 5200.9175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15098 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 28423.0885 | 0.2 | 0.3 | 44340.0181 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9293.5219 | 9293.5219 | 9293.5219 | 9293.5219 | 9293.5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15099 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 13131.8835 | 0.2 | 0.3 | 20485.7383 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 14358.2973 | 14358.2973 | 14358.2973 | 14358.2973 | 14358.2973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15100 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16752.3344 | 0.2 | 0.3 | 26133.6417 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7009.4189 | 7009.4189 | 7009.4189 | 7009.4189 | 7009.4189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15101 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16669.9772 | 0.2 | 0.3 | 26005.1644 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5211.2363 | 5211.2363 | 5211.2363 | 5211.2363 | 5211.2363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15102 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 24543.8769 | 0.2 | 0.3 | 38288.448 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5224.8847 | 5224.8847 | 5224.8847 | 5224.8847 | 5224.8847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15103 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 7523.0383 | 0.2 | 0.3 | 11735.9398 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8152.0264 | 8152.0264 | 8152.0264 | 8152.0264 | 8152.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15104 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 17202.1546 | 0.2 | 0.3 | 26835.3612 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2417.1768 | 2417.1768 | 2417.1768 | 2417.1768 | 2417.1768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15105 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 16667.7102 | 0.2 | 0.3 | 26001.6279 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 135.1466 | 135.1466 | 135.1466 | 135.1466 | 135.1466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15106 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 8969.4503 | 0.2 | 0.3 | 13992.3424 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5977.7471 | 5977.7471 | 5977.7471 | 5977.7471 | 5977.7471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15107 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5306.3418 | 5306.3418 | 5306.3418 | 5306.3418 | 5306.3418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15108 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 7698.5615 | 0.2 | 0.3 | 12009.756 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3313.8305 | 3313.8305 | 3313.8305 | 3313.8305 | 3313.8305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15109 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 8969.1719 | 0.2 | 0.3 | 13991.9082 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7859.7872 | 7859.7872 | 7859.7872 | 7859.7872 | 7859.7872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15110 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 14320.7394 | 0.2 | 0.3 | 22340.3535 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15111 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 31663.2715 | 0.2 | 0.3 | 49394.7036 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5940.2735 | 5940.2735 | 5940.2735 | 5940.2735 | 5940.2735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15112 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 13721.3091 | 0.2 | 0.3 | 21405.2422 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9045.4438 | 9045.4438 | 9045.4438 | 9045.4438 | 9045.4438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15113 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 13286.8566 | 0.2 | 0.3 | 20727.4963 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15114 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 13267.7073 | 0.2 | 0.3 | 20697.6233 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3801 | 5201.3801 | 5201.3801 | 5201.3801 | 5201.3801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15115 | CORAL SPRINGS | 20326 | Private | 2036 | 5 | Swales | 66.6667 | 22607.3892 | 0.2 | 0.3 | 35267.5272 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15116 | CORAL SPRINGS | 20326 | Private | 2036 | 5 | Swales | 66.6667 | 1068.1499 | 0.2 | 0.3 | 1666.3139 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15117 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 18907.5789 | 0.2 | 0.3 | 29495.823 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15118 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16973.1926 | 0.2 | 0.3 | 26478.1805 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7337 | 5200.7337 | 5200.7337 | 5200.7337 | 5200.7337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15119 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16755.2437 | 0.2 | 0.3 | 26138.1802 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5857.7405 | 5857.7405 | 5857.7405 | 5857.7405 | 5857.7405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15120 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16661.9904 | 0.2 | 0.3 | 25992.705 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10831.6888 | 10831.6888 | 10831.6888 | 10831.6888 | 10831.6888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15121 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 14746.0375 | 0.2 | 0.3 | 23003.8186 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7205.2806 | 7205.2806 | 7205.2806 | 7205.2806 | 7205.2806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15122 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 23332.7215 | 0.2 | 0.3 | 36399.0456 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11205.1285 | 11205.1285 | 11205.1285 | 11205.1285 | 11205.1285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15123 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16671.0115 | 0.2 | 0.3 | 26006.778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10271.7857 | 10271.7857 | 10271.7857 | 10271.7857 | 10271.7857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15124 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 17583.7143 | 0.2 | 0.3 | 27430.5944 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6452.9502 | 6452.9502 | 6452.9502 | 6452.9502 | 6452.9502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15125 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 16489.0377 | 0.2 | 0.3 | 25722.8989 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15126 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 5049.9393 | 0.2 | 0.3 | 7877.9054 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5391.0897 | 5391.0897 | 5391.0897 | 5391.0897 | 5391.0897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15127 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 17993.385 | 0.2 | 0.3 | 28069.6806 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5242.5002 | 5242.5002 | 5242.5002 | 5242.5002 | 5242.5002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15128 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 6819.0505 | 0.2 | 0.3 | 10637.7188 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 666.0743 | 666.0743 | 666.0743 | 666.0743 | 666.0743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15129 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 13148.6362 | 0.2 | 0.3 | 20511.8725 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5466 | 5201.5466 | 5201.5466 | 5201.5466 | 5201.5466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15130 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 17027.4326 | 0.2 | 0.3 | 26562.7949 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1634 | 5202.1634 | 5202.1634 | 5202.1634 | 5202.1634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15131 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2813 | 0.2 | 0.3 | 26002.5189 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 52.8973 | 52.8973 | 52.8973 | 52.8973 | 52.8973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15132 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 15801.5247 | 0.2 | 0.3 | 24650.3785 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7640.9975 | 7640.9975 | 7640.9975 | 7640.9975 | 7640.9975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15133 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 16844.8388 | 0.2 | 0.3 | 26277.9485 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15134 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 26591.4239 | 0.2 | 0.3 | 41482.6212 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.4484 | 5203.4484 | 5203.4484 | 5203.4484 | 5203.4484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15135 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 18621.5461 | 0.2 | 0.3 | 29049.6119 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9781.5739 | 9781.5739 | 9781.5739 | 9781.5739 | 9781.5739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15136 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16668.3713 | 0.2 | 0.3 | 26002.6593 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15137 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 9351.0034 | 0.2 | 0.3 | 14587.5653 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2994 | 5201.2994 | 5201.2994 | 5201.2994 | 5201.2994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15138 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 14296.0877 | 0.2 | 0.3 | 22301.8968 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15139 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 22841.0135 | 0.2 | 0.3 | 35631.981 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 5201.1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15140 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 7845.9874 | 0.2 | 0.3 | 12239.7403 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2679 | 5201.2679 | 5201.2679 | 5201.2679 | 5201.2679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15141 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 27654.3913 | 0.2 | 0.3 | 43140.8505 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5393.8414 | 5393.8414 | 5393.8414 | 5393.8414 | 5393.8414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15142 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 20406.9879 | 0.2 | 0.3 | 31834.9011 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15143 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 19544.5183 | 0.2 | 0.3 | 30489.4485 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2954.93 | 2954.93 | 2954.93 | 2954.93 | 2954.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15144 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 25191.1758 | 0.2 | 0.3 | 39298.2342 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5567.0514 | 5567.0514 | 5567.0514 | 5567.0514 | 5567.0514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15145 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 25635.2784 | 0.2 | 0.3 | 39991.0343 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5744.1721 | 5744.1721 | 5744.1721 | 5744.1721 | 5744.1721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15146 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10398.1671 | 10398.1671 | 10398.1671 | 10398.1671 | 10398.1671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15147 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 25617.1685 | 0.2 | 0.3 | 39962.7829 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2028.4679 | 2028.4679 | 2028.4679 | 2028.4679 | 2028.4679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15148 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 23788.4009 | 0.2 | 0.3 | 37109.9055 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10666.4236 | 10666.4236 | 10666.4236 | 10666.4236 | 10666.4236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15149 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16667.0472 | 0.2 | 0.3 | 26000.5936 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8535.3301 | 8535.3301 | 8535.3301 | 8535.3301 | 8535.3301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15150 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 25398.5899 | 0.2 | 0.3 | 39621.8002 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 19.8437 | 19.8437 | 19.8437 | 19.8437 | 19.8437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15151 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16668.2213 | 0.2 | 0.3 | 26002.4253 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4441.1188 | 4441.1188 | 4441.1188 | 4441.1188 | 4441.1188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15152 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 21583.6595 | 0.2 | 0.3 | 33670.5088 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 144.4251 | 144.4251 | 144.4251 | 144.4251 | 144.4251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15153 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 3976.9155 | 0.2 | 0.3 | 6203.9881 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7260.4525 | 7260.4525 | 7260.4525 | 7260.4525 | 7260.4525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15154 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 5870.4495 | 0.2 | 0.3 | 9157.9013 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10322.8122 | 10322.8122 | 10322.8122 | 10322.8122 | 10322.8122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15155 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 25524.8009 | 0.2 | 0.3 | 39818.6894 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10403.797 | 10403.797 | 10403.797 | 10403.797 | 10403.797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15156 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 22968.6507 | 0.2 | 0.3 | 35831.095 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10404.3157 | 10404.3157 | 10404.3157 | 10404.3157 | 10404.3157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15157 | CORAL SPRINGS | 20326 | Private | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7423.1449 | 7423.1449 | 7423.1449 | 7423.1449 | 7423.1449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15158 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8432.5526 | 8432.5526 | 8432.5526 | 8432.5526 | 8432.5526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15159 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7389.4463 | 7389.4463 | 7389.4463 | 7389.4463 | 7389.4463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15160 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 18718.2728 | 0.2 | 0.3 | 29200.5056 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 289.2334 | 289.2334 | 289.2334 | 289.2334 | 289.2334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15161 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 12752.3461 | 0.2 | 0.3 | 19893.6599 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10607.4639 | 10607.4639 | 10607.4639 | 10607.4639 | 10607.4639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15162 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 11747.5772 | 0.2 | 0.3 | 18326.2204 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9218.6028 | 9218.6028 | 9218.6028 | 9218.6028 | 9218.6028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15163 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 18060.9824 | 0.2 | 0.3 | 28175.1325 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10313.4387 | 10313.4387 | 10313.4387 | 10313.4387 | 10313.4387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15164 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16686.1969 | 0.2 | 0.3 | 26030.4671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4689.6769 | 4689.6769 | 4689.6769 | 4689.6769 | 4689.6769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15165 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 13545.8756 | 0.2 | 0.3 | 21131.5659 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7519.8478 | 7519.8478 | 7519.8478 | 7519.8478 | 7519.8478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15166 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 24037.5593 | 0.2 | 0.3 | 37498.5925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6209 | 5202.6209 | 5202.6209 | 5202.6209 | 5202.6209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15167 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16721.4297 | 0.2 | 0.3 | 26085.4303 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.628 | 5202.628 | 5202.628 | 5202.628 | 5202.628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15168 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 17637.6873 | 0.2 | 0.3 | 27514.7922 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.4254 | 9779.4254 | 9779.4254 | 9779.4254 | 9779.4254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15169 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 426.3072 | 0.2 | 0.3 | 665.0392 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15170 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 27843.9378 | 0.2 | 0.3 | 43436.543 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15171 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 18715.1375 | 0.2 | 0.3 | 29195.6146 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15172 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 277.8843 | 0.2 | 0.3 | 433.4995 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1802 | 5201.1802 | 5201.1802 | 5201.1802 | 5201.1802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15173 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 5409.7321 | 0.2 | 0.3 | 8439.1821 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15174 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 14195.8886 | 0.2 | 0.3 | 22145.5862 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3247 | 5201.3247 | 5201.3247 | 5201.3247 | 5201.3247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15175 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 3318.0717 | 0.2 | 0.3 | 5176.1918 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15176 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 25574.7371 | 0.2 | 0.3 | 39896.5898 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15177 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 22112.1749 | 0.2 | 0.3 | 34494.9929 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3231 | 5201.3231 | 5201.3231 | 5201.3231 | 5201.3231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15178 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16667.6913 | 0.2 | 0.3 | 26001.5985 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7434.3481 | 7434.3481 | 7434.3481 | 7434.3481 | 7434.3481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15179 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10809.8155 | 10809.8155 | 10809.8155 | 10809.8155 | 10809.8155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15180 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 21801.0551 | 0.2 | 0.3 | 34009.646 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.0057 | 9779.0057 | 9779.0057 | 9779.0057 | 9779.0057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15181 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 22175.1284 | 0.2 | 0.3 | 34593.2003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13043.969 | 13043.969 | 13043.969 | 13043.969 | 13043.969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15182 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 27510.1523 | 0.2 | 0.3 | 42915.8376 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5241.8777 | 5241.8777 | 5241.8777 | 5241.8777 | 5241.8777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15183 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 25505.8519 | 0.2 | 0.3 | 39789.1289 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5869.1303 | 5869.1303 | 5869.1303 | 5869.1303 | 5869.1303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15184 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 31661.4011 | 0.2 | 0.3 | 49391.7857 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4170.7172 | 4170.7172 | 4170.7172 | 4170.7172 | 4170.7172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15185 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16666.1815 | 0.2 | 0.3 | 25999.2432 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6869.1325 | 6869.1325 | 6869.1325 | 6869.1325 | 6869.1325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15186 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 18356.3973 | 0.2 | 0.3 | 28635.9798 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1835 | 5200.1835 | 5200.1835 | 5200.1835 | 5200.1835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15187 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 20119.6098 | 0.2 | 0.3 | 31386.5913 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2399 | 5200.2399 | 5200.2399 | 5200.2399 | 5200.2399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15188 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16380.4959 | 0.2 | 0.3 | 25553.5737 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3561 | 5200.3561 | 5200.3561 | 5200.3561 | 5200.3561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15189 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 1396.7717 | 0.2 | 0.3 | 2178.9638 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5108.6487 | 5108.6487 | 5108.6487 | 5108.6487 | 5108.6487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15190 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16920.3512 | 0.2 | 0.3 | 26395.7479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 87.9114 | 87.9114 | 87.9114 | 87.9114 | 87.9114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15191 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 18587.1112 | 0.2 | 0.3 | 28995.8935 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5355.1921 | 5355.1921 | 5355.1921 | 5355.1921 | 5355.1921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15192 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 20368.3468 | 0.2 | 0.3 | 31774.621 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9611.8774 | 9611.8774 | 9611.8774 | 9611.8774 | 9611.8774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15193 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 16085.2127 | 0.2 | 0.3 | 25092.9319 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10406.0518 | 10406.0518 | 10406.0518 | 10406.0518 | 10406.0518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15194 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 23748.9663 | 0.2 | 0.3 | 37048.3874 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5265.6364 | 5265.6364 | 5265.6364 | 5265.6364 | 5265.6364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15195 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 20730.3048 | 0.2 | 0.3 | 32339.2755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10342.3784 | 10342.3784 | 10342.3784 | 10342.3784 | 10342.3784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15196 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 13945.8051 | 0.2 | 0.3 | 21755.456 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15197 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 17341.133 | 0.2 | 0.3 | 27052.1675 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7347.9148 | 7347.9148 | 7347.9148 | 7347.9148 | 7347.9148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15198 | CORAL SPRINGS | 20326 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9977 | 5202.9977 | 5202.9977 | 5202.9977 | 5202.9977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15199 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.3266 | 0.2 | 0.3 | 25999.4695 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.0668 | 5203.0668 | 5203.0668 | 5203.0668 | 5203.0668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15200 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.9907 | 9779.9907 | 9779.9907 | 9779.9907 | 9779.9907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15201 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 14661.361 | 0.2 | 0.3 | 22871.7232 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15202 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 22304.6953 | 0.2 | 0.3 | 34795.3246 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15203 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 18874.8415 | 0.2 | 0.3 | 29444.7527 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15204 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16668.3093 | 0.2 | 0.3 | 26002.5625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8277.3818 | 8277.3818 | 8277.3818 | 8277.3818 | 8277.3818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15205 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 5256.4426 | 0.2 | 0.3 | 8200.0505 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5745.4301 | 5745.4301 | 5745.4301 | 5745.4301 | 5745.4301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15206 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16723.3294 | 0.2 | 0.3 | 26088.3939 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5598.4862 | 5598.4862 | 5598.4862 | 5598.4862 | 5598.4862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15207 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 13404.7163 | 0.2 | 0.3 | 20911.3575 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5299.6131 | 5299.6131 | 5299.6131 | 5299.6131 | 5299.6131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15208 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 13324.2715 | 0.2 | 0.3 | 20785.8635 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15209 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16669.4837 | 0.2 | 0.3 | 26004.3946 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7081.5112 | 7081.5112 | 7081.5112 | 7081.5112 | 7081.5112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15210 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 6290.9823 | 0.2 | 0.3 | 9813.9323 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3898.3519 | 3898.3519 | 3898.3519 | 3898.3519 | 3898.3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15211 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 18076.2673 | 0.2 | 0.3 | 28198.9769 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11059.9997 | 11059.9997 | 11059.9997 | 11059.9997 | 11059.9997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15212 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 20166.1959 | 0.2 | 0.3 | 31459.2656 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15213 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 20892.0352 | 0.2 | 0.3 | 32591.5749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5215.0055 | 5215.0055 | 5215.0055 | 5215.0055 | 5215.0055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15214 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 11498.6167 | 0.2 | 0.3 | 17937.842 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5370.4894 | 5370.4894 | 5370.4894 | 5370.4894 | 5370.4894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15215 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 17079.9699 | 0.2 | 0.3 | 26644.7531 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9366.4925 | 9366.4925 | 9366.4925 | 9366.4925 | 9366.4925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15216 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 16670.6073 | 0.2 | 0.3 | 26006.1473 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11146.536 | 11146.536 | 11146.536 | 11146.536 | 11146.536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15217 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 939.3629 | 0.2 | 0.3 | 1465.4061 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.0934 | 5203.0934 | 5203.0934 | 5203.0934 | 5203.0934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15218 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 29408.4673 | 0.2 | 0.3 | 45877.209 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7161.2191 | 7161.2191 | 7161.2191 | 7161.2191 | 7161.2191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15219 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 17853.824 | 0.2 | 0.3 | 27851.9654 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2715 | 5203.2715 | 5203.2715 | 5203.2715 | 5203.2715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15220 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 7487.9929 | 0.2 | 0.3 | 11681.2689 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3536 | 5203.3536 | 5203.3536 | 5203.3536 | 5203.3536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15221 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 26797.2316 | 0.2 | 0.3 | 41803.6813 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9780.3987 | 9780.3987 | 9780.3987 | 9780.3987 | 9780.3987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15222 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16667.2515 | 0.2 | 0.3 | 26000.9124 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15223 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6819.7316 | 6819.7316 | 6819.7316 | 6819.7316 | 6819.7316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15224 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 24750.8152 | 0.2 | 0.3 | 38611.2717 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6606.9462 | 6606.9462 | 6606.9462 | 6606.9462 | 6606.9462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15225 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 7144.4844 | 0.2 | 0.3 | 11145.3957 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7682.3498 | 7682.3498 | 7682.3498 | 7682.3498 | 7682.3498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15226 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 20338.9479 | 0.2 | 0.3 | 31728.7588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5263.0894 | 5263.0894 | 5263.0894 | 5263.0894 | 5263.0894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15227 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 23760.8361 | 0.2 | 0.3 | 37066.9044 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9892.6334 | 9892.6334 | 9892.6334 | 9892.6334 | 9892.6334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15228 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 19095.2098 | 0.2 | 0.3 | 29788.5273 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3204.7758 | 3204.7758 | 3204.7758 | 3204.7758 | 3204.7758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15229 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 17221.3329 | 0.2 | 0.3 | 26865.2793 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6063.3667 | 6063.3667 | 6063.3667 | 6063.3667 | 6063.3667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15230 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 2.6006 | 0.2 | 0.3 | 4.0569 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6663.418 | 6663.418 | 6663.418 | 6663.418 | 6663.418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15231 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 21721.6731 | 0.2 | 0.3 | 33885.8101 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15232 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 3392.6761 | 0.2 | 0.3 | 5292.5748 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15233 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 25427.6109 | 0.2 | 0.3 | 39667.0731 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5580.8408 | 5580.8408 | 5580.8408 | 5580.8408 | 5580.8408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15234 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 19075.7382 | 0.2 | 0.3 | 29758.1516 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6918.8472 | 6918.8472 | 6918.8472 | 6918.8472 | 6918.8472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15235 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 28178.7045 | 0.2 | 0.3 | 43958.7791 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2007 | 5202.2007 | 5202.2007 | 5202.2007 | 5202.2007 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15236 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 24334.185 | 0.2 | 0.3 | 37961.3286 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1968 | 5202.1968 | 5202.1968 | 5202.1968 | 5202.1968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15237 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 19490.3493 | 0.2 | 0.3 | 30404.945 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9781.5726 | 9781.5726 | 9781.5726 | 9781.5726 | 9781.5726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15238 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 11306.6011 | 0.2 | 0.3 | 17638.2978 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15239 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 29696.9753 | 0.2 | 0.3 | 46327.2814 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8465 | 5202.8465 | 5202.8465 | 5202.8465 | 5202.8465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15240 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 21218.7919 | 0.2 | 0.3 | 33101.3154 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7248 | 5203.7248 | 5203.7248 | 5203.7248 | 5203.7248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15241 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 15126.9116 | 0.2 | 0.3 | 23597.9821 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7976 | 5203.7976 | 5203.7976 | 5203.7976 | 5203.7976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15242 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 17087.3899 | 0.2 | 0.3 | 26656.3283 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7878.5663 | 7878.5663 | 7878.5663 | 7878.5663 | 7878.5663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15243 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 16772.8679 | 0.2 | 0.3 | 26165.674 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1574 | 5201.1574 | 5201.1574 | 5201.1574 | 5201.1574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15244 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 31573.268 | 0.2 | 0.3 | 49254.2981 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9199.3314 | 9199.3314 | 9199.3314 | 9199.3314 | 9199.3314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15245 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 18618.5421 | 0.2 | 0.3 | 29044.9256 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 127.9457 | 127.9457 | 127.9457 | 127.9457 | 127.9457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15246 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 26419.2601 | 0.2 | 0.3 | 41214.0458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2510.7839 | 2510.7839 | 2510.7839 | 2510.7839 | 2510.7839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15247 | CORAL SPRINGS | 20326 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5495.5242 | 5495.5242 | 5495.5242 | 5495.5242 | 5495.5242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15248 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.3266 | 0.2 | 0.3 | 25999.4695 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4225.0749 | 4225.0749 | 4225.0749 | 4225.0749 | 4225.0749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15249 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16668.6927 | 0.2 | 0.3 | 26003.1606 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3738 | 5200.3738 | 5200.3738 | 5200.3738 | 5200.3738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15250 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16750.6747 | 0.2 | 0.3 | 26131.0526 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6286.3652 | 6286.3652 | 6286.3652 | 6286.3652 | 6286.3652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15251 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 187.5921 | 0.2 | 0.3 | 292.6436 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15252 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16668.2465 | 0.2 | 0.3 | 26002.4645 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5739.2111 | 5739.2111 | 5739.2111 | 5739.2111 | 5739.2111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15253 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 15825.6993 | 0.2 | 0.3 | 24688.0909 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 407.0932 | 407.0932 | 407.0932 | 407.0932 | 407.0932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15254 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 17483.1841 | 0.2 | 0.3 | 27273.7672 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4261.1714 | 4261.1714 | 4261.1714 | 4261.1714 | 4261.1714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15255 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 25663.1687 | 0.2 | 0.3 | 40034.5432 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9058.39 | 9058.39 | 9058.39 | 9058.39 | 9058.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15256 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16954.6821 | 0.2 | 0.3 | 26449.3041 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15257 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16883.1393 | 0.2 | 0.3 | 26337.6974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 2.9393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15258 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 25299.853 | 0.2 | 0.3 | 39467.7707 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5870.2292 | 5870.2292 | 5870.2292 | 5870.2292 | 5870.2292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15259 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 958.4098 | 0.2 | 0.3 | 1495.1193 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1663 | 2600.1663 | 2600.1663 | 2600.1663 | 2600.1663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15260 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 23017.6402 | 0.2 | 0.3 | 35907.5187 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2949.5894 | 2949.5894 | 2949.5894 | 2949.5894 | 2949.5894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15261 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 16869.6527 | 0.2 | 0.3 | 26316.6583 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7715.0068 | 7715.0068 | 7715.0068 | 7715.0068 | 7715.0068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15262 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 16671.5141 | 0.2 | 0.3 | 26007.5619 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1005.9975 | 1005.9975 | 1005.9975 | 1005.9975 | 1005.9975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15263 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 21037.8753 | 0.2 | 0.3 | 32819.0855 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 693.0586 | 693.0586 | 693.0586 | 693.0586 | 693.0586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15264 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 17295.2932 | 0.2 | 0.3 | 26980.6574 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 936.8624 | 936.8624 | 936.8624 | 936.8624 | 936.8624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15265 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 4911.0251 | 0.2 | 0.3 | 7661.1991 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15266 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 21143.32 | 0.2 | 0.3 | 32983.5792 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9191.2413 | 9191.2413 | 9191.2413 | 9191.2413 | 9191.2413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15267 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 5563.2787 | 0.2 | 0.3 | 8678.7148 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0168 | 5202.0168 | 5202.0168 | 5202.0168 | 5202.0168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15268 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 25878.2826 | 0.2 | 0.3 | 40370.1209 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3295.9981 | 3295.9981 | 3295.9981 | 3295.9981 | 3295.9981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15269 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7494.8596 | 7494.8596 | 7494.8596 | 7494.8596 | 7494.8596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15270 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 16639.5509 | 0.2 | 0.3 | 25957.6995 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4437.844 | 4437.844 | 4437.844 | 4437.844 | 4437.844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15271 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 28064.9708 | 0.2 | 0.3 | 43781.3544 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4974.1012 | 4974.1012 | 4974.1012 | 4974.1012 | 4974.1012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15272 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9020.5407 | 9020.5407 | 9020.5407 | 9020.5407 | 9020.5407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15273 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 29927.646 | 0.2 | 0.3 | 46687.1278 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8922.9482 | 8922.9482 | 8922.9482 | 8922.9482 | 8922.9482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15274 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 22088.4991 | 0.2 | 0.3 | 34458.0586 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4922.6557 | 4922.6557 | 4922.6557 | 4922.6557 | 4922.6557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15275 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16088.9659 | 0.2 | 0.3 | 25098.7868 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5230.2509 | 5230.2509 | 5230.2509 | 5230.2509 | 5230.2509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15276 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16211.0039 | 0.2 | 0.3 | 25289.166 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15277 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16130.7041 | 0.2 | 0.3 | 25163.8984 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9741.4837 | 9741.4837 | 9741.4837 | 9741.4837 | 9741.4837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15278 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 3013.2847 | 0.2 | 0.3 | 4700.7242 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6750.4315 | 6750.4315 | 6750.4315 | 6750.4315 | 6750.4315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15279 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 30162.8918 | 0.2 | 0.3 | 47054.1112 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4710.1526 | 4710.1526 | 4710.1526 | 4710.1526 | 4710.1526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15280 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16894.2549 | 0.2 | 0.3 | 26355.0377 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5596.6795 | 5596.6795 | 5596.6795 | 5596.6795 | 5596.6795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15281 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 9705.0347 | 0.2 | 0.3 | 15139.8541 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3024.2837 | 3024.2837 | 3024.2837 | 3024.2837 | 3024.2837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15282 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16905.9329 | 0.2 | 0.3 | 26373.2553 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5080.3558 | 5080.3558 | 5080.3558 | 5080.3558 | 5080.3558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15283 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 27673.1943 | 0.2 | 0.3 | 43170.1831 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2403.8352 | 2403.8352 | 2403.8352 | 2403.8352 | 2403.8352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15284 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 31716.5971 | 0.2 | 0.3 | 49477.8915 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5310.3831 | 5310.3831 | 5310.3831 | 5310.3831 | 5310.3831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15285 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 19878.983 | 0.2 | 0.3 | 31011.2135 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7432.0025 | 7432.0025 | 7432.0025 | 7432.0025 | 7432.0025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15286 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 17645.2426 | 0.2 | 0.3 | 27526.5785 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5277.9448 | 5277.9448 | 5277.9448 | 5277.9448 | 5277.9448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15287 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 29735.9051 | 0.2 | 0.3 | 46388.012 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9864.2631 | 9864.2631 | 9864.2631 | 9864.2631 | 9864.2631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15288 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 2784.1396 | 0.2 | 0.3 | 4343.2578 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5133.9287 | 5133.9287 | 5133.9287 | 5133.9287 | 5133.9287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15289 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 21903.3163 | 0.2 | 0.3 | 34169.1735 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5648.853 | 5648.853 | 5648.853 | 5648.853 | 5648.853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15290 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 16883.1353 | 0.2 | 0.3 | 26337.6911 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9124.642 | 9124.642 | 9124.642 | 9124.642 | 9124.642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15291 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 21086.0016 | 0.2 | 0.3 | 32894.1625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6989.7386 | 6989.7386 | 6989.7386 | 6989.7386 | 6989.7386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15292 | CORAL SPRINGS | 20326 | Private | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2177.3751 | 2177.3751 | 2177.3751 | 2177.3751 | 2177.3751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15293 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 121.3195 | 121.3195 | 121.3195 | 121.3195 | 121.3195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15294 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 22295.217 | 0.2 | 0.3 | 34780.5385 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15295 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1187 | 0.2 | 0.3 | 26000.7051 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1032.7722 | 1032.7722 | 1032.7722 | 1032.7722 | 1032.7722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15296 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8370.2906 | 8370.2906 | 8370.2906 | 8370.2906 | 8370.2906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15297 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5567.1587 | 5567.1587 | 5567.1587 | 5567.1587 | 5567.1587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15298 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 15421.6405 | 0.2 | 0.3 | 24057.7591 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5600.461 | 5600.461 | 5600.461 | 5600.461 | 5600.461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15299 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 9847.7562 | 0.2 | 0.3 | 15362.4997 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5530.027 | 5530.027 | 5530.027 | 5530.027 | 5530.027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15300 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 21261.4175 | 0.2 | 0.3 | 33167.8112 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5581.5922 | 5581.5922 | 5581.5922 | 5581.5922 | 5581.5922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15301 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16668.1877 | 0.2 | 0.3 | 26002.3728 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3374.6689 | 3374.6689 | 3374.6689 | 3374.6689 | 3374.6689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15302 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 28951.8747 | 0.2 | 0.3 | 45164.9246 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7993.4986 | 7993.4986 | 7993.4986 | 7993.4986 | 7993.4986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15303 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 17692.0491 | 0.2 | 0.3 | 27599.5965 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7037.8256 | 7037.8256 | 7037.8256 | 7037.8256 | 7037.8256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15304 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 22815.2499 | 0.2 | 0.3 | 35591.7898 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5842.5784 | 5842.5784 | 5842.5784 | 5842.5784 | 5842.5784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15305 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 5829.1573 | 0.2 | 0.3 | 9093.4853 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4816.6607 | 4816.6607 | 4816.6607 | 4816.6607 | 4816.6607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15306 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 13947.7554 | 0.2 | 0.3 | 21758.4984 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5459.7742 | 5459.7742 | 5459.7742 | 5459.7742 | 5459.7742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15307 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 24613.0417 | 0.2 | 0.3 | 38396.3451 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5574.2822 | 5574.2822 | 5574.2822 | 5574.2822 | 5574.2822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15308 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 17913.2461 | 0.2 | 0.3 | 27944.6639 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3984.2473 | 3984.2473 | 3984.2473 | 3984.2473 | 3984.2473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15309 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 18049.4342 | 0.2 | 0.3 | 28157.1174 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3982.581 | 3982.581 | 3982.581 | 3982.581 | 3982.581 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15310 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 17799.3835 | 0.2 | 0.3 | 27767.0382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5929.6648 | 5929.6648 | 5929.6648 | 5929.6648 | 5929.6648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15311 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 26270.0431 | 0.2 | 0.3 | 40981.2672 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5112.8371 | 5112.8371 | 5112.8371 | 5112.8371 | 5112.8371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15312 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16667.2709 | 0.2 | 0.3 | 26000.9426 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8263.4844 | 8263.4844 | 8263.4844 | 8263.4844 | 8263.4844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15313 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8654.1209 | 8654.1209 | 8654.1209 | 8654.1209 | 8654.1209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15314 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1642 | 0.2 | 0.3 | 26000.7762 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4685.8592 | 4685.8592 | 4685.8592 | 4685.8592 | 4685.8592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15315 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 33459.6011 | 0.2 | 0.3 | 52196.9778 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0515 | 5200.0515 | 5200.0515 | 5200.0515 | 5200.0515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15316 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 16668.6168 | 0.2 | 0.3 | 26003.0422 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.247 | 5200.247 | 5200.247 | 5200.247 | 5200.247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15317 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 12202.1363 | 0.2 | 0.3 | 19035.3326 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6807 | 5201.6807 | 5201.6807 | 5201.6807 | 5201.6807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15318 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 14437.5735 | 0.2 | 0.3 | 22522.6147 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1049.51 | 1049.51 | 1049.51 | 1049.51 | 1049.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15319 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 27851.5487 | 0.2 | 0.3 | 43448.416 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5485.5735 | 5485.5735 | 5485.5735 | 5485.5735 | 5485.5735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15320 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 30100.8969 | 0.2 | 0.3 | 46957.3992 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.224 | 5201.224 | 5201.224 | 5201.224 | 5201.224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15321 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 12074.5712 | 0.2 | 0.3 | 18836.3311 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4735.6958 | 4735.6958 | 4735.6958 | 4735.6958 | 4735.6958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15322 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 23797.4401 | 0.2 | 0.3 | 37124.0065 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4396.6679 | 4396.6679 | 4396.6679 | 4396.6679 | 4396.6679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15323 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4847.5725 | 4847.5725 | 4847.5725 | 4847.5725 | 4847.5725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15324 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 14141.2999 | 0.2 | 0.3 | 22060.4279 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1117.7215 | 1117.7215 | 1117.7215 | 1117.7215 | 1117.7215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15325 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4462.5238 | 4462.5238 | 4462.5238 | 4462.5238 | 4462.5238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15326 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 23710.776 | 0.2 | 0.3 | 36988.8106 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9368.5183 | 9368.5183 | 9368.5183 | 9368.5183 | 9368.5183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15327 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 13132.6474 | 0.2 | 0.3 | 20486.9299 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.1453 | 5205.1453 | 5205.1453 | 5205.1453 | 5205.1453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15328 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 23241.1311 | 0.2 | 0.3 | 36256.1646 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8025.5732 | 8025.5732 | 8025.5732 | 8025.5732 | 8025.5732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15329 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 22050.0615 | 0.2 | 0.3 | 34398.096 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8687.5441 | 8687.5441 | 8687.5441 | 8687.5441 | 8687.5441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15330 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 29139.8308 | 0.2 | 0.3 | 45458.136 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5363.4677 | 5363.4677 | 5363.4677 | 5363.4677 | 5363.4677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15331 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 8276.4795 | 0.2 | 0.3 | 12911.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7474.9398 | 7474.9398 | 7474.9398 | 7474.9398 | 7474.9398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15332 | CORAL SPRINGS | 20309 | Private | 2026 | 5 | Swales | 66.6667 | 1798.2874 | 0.2 | 0.3 | 2805.3283 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9233 | 5199.9233 | 5199.9233 | 5199.9233 | 5199.9233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15333 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 28038.3587 | 0.2 | 0.3 | 43739.8396 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3892.6015 | 3892.6015 | 3892.6015 | 3892.6015 | 3892.6015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15334 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 32757.2074 | 0.2 | 0.3 | 51101.2435 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1485.1503 | 1485.1503 | 1485.1503 | 1485.1503 | 1485.1503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15335 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 18474.5521 | 0.2 | 0.3 | 28820.3013 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6134.9118 | 6134.9118 | 6134.9118 | 6134.9118 | 6134.9118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15336 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 15056.3057 | 0.2 | 0.3 | 23487.8369 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10140.3362 | 10140.3362 | 10140.3362 | 10140.3362 | 10140.3362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15337 | CORAL SPRINGS | 20326 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1670.4877 | 1670.4877 | 1670.4877 | 1670.4877 | 1670.4877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15338 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4713.1124 | 4713.1124 | 4713.1124 | 4713.1124 | 4713.1124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15339 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16668.8531 | 0.2 | 0.3 | 26003.4108 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7289.6796 | 7289.6796 | 7289.6796 | 7289.6796 | 7289.6796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15340 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 1486.6437 | 0.2 | 0.3 | 2319.1642 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15341 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 22277.3065 | 0.2 | 0.3 | 34752.5981 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3207 | 5200.3207 | 5200.3207 | 5200.3207 | 5200.3207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15342 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 23819.3107 | 0.2 | 0.3 | 37158.1246 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6327 | 5200.6327 | 5200.6327 | 5200.6327 | 5200.6327 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15343 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16999.1828 | 0.2 | 0.3 | 26518.7252 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1287.7757 | 1287.7757 | 1287.7757 | 1287.7757 | 1287.7757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15344 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 23464.9547 | 0.2 | 0.3 | 36605.3293 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6424.7576 | 6424.7576 | 6424.7576 | 6424.7576 | 6424.7576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15345 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 18302.3679 | 0.2 | 0.3 | 28551.6939 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6081.3471 | 6081.3471 | 6081.3471 | 6081.3471 | 6081.3471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15346 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 19298.0275 | 0.2 | 0.3 | 30104.923 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6689 | 5202.6689 | 5202.6689 | 5202.6689 | 5202.6689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15347 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 17847.0572 | 0.2 | 0.3 | 27841.4092 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6279.2706 | 6279.2706 | 6279.2706 | 6279.2706 | 6279.2706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15348 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 16718.3274 | 0.2 | 0.3 | 26080.5907 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6027.2175 | 6027.2175 | 6027.2175 | 6027.2175 | 6027.2175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15349 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 4332.6915 | 0.2 | 0.3 | 6758.9987 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6298.0733 | 6298.0733 | 6298.0733 | 6298.0733 | 6298.0733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15350 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 12473.2825 | 0.2 | 0.3 | 19458.3206 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7449.9748 | 7449.9748 | 7449.9748 | 7449.9748 | 7449.9748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15351 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16667.5799 | 0.2 | 0.3 | 26001.4246 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6134.5734 | 6134.5734 | 6134.5734 | 6134.5734 | 6134.5734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15352 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6718.716 | 6718.716 | 6718.716 | 6718.716 | 6718.716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15353 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16784.2483 | 0.2 | 0.3 | 26183.4274 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5104 | 5201.5104 | 5201.5104 | 5201.5104 | 5201.5104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15354 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 7543.7326 | 0.2 | 0.3 | 11768.2229 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15355 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 32289.9991 | 0.2 | 0.3 | 50372.3986 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5217.5223 | 5217.5223 | 5217.5223 | 5217.5223 | 5217.5223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15356 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 16876.6109 | 0.2 | 0.3 | 26327.513 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4618 | 5201.4618 | 5201.4618 | 5201.4618 | 5201.4618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15357 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 21344.2251 | 0.2 | 0.3 | 33296.9911 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7670.2393 | 7670.2393 | 7670.2393 | 7670.2393 | 7670.2393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15358 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 17653.3048 | 0.2 | 0.3 | 27539.1555 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15359 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 30651.9023 | 0.2 | 0.3 | 47816.9675 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8913.2674 | 8913.2674 | 8913.2674 | 8913.2674 | 8913.2674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15360 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 17327.1198 | 0.2 | 0.3 | 27030.3069 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5374 | 5200.5374 | 5200.5374 | 5200.5374 | 5200.5374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15361 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 17714.4759 | 0.2 | 0.3 | 27634.5824 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7934 | 5200.7934 | 5200.7934 | 5200.7934 | 5200.7934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15362 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 10449.211 | 0.2 | 0.3 | 16300.7692 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6749.5185 | 6749.5185 | 6749.5185 | 6749.5185 | 6749.5185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15363 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 14025.3859 | 0.2 | 0.3 | 21879.602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5881.2436 | 5881.2436 | 5881.2436 | 5881.2436 | 5881.2436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15364 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 13919.3739 | 0.2 | 0.3 | 21714.2233 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15365 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 22255.2318 | 0.2 | 0.3 | 34718.1616 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15366 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 22044.5667 | 0.2 | 0.3 | 34389.5241 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15367 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16717.6954 | 0.2 | 0.3 | 26079.6048 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5255 | 5203.5255 | 5203.5255 | 5203.5255 | 5203.5255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15368 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16666.7932 | 0.2 | 0.3 | 26000.1974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2056 | 5201.2056 | 5201.2056 | 5201.2056 | 5201.2056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15369 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 28543.0277 | 0.2 | 0.3 | 44527.1232 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3951 | 5201.3951 | 5201.3951 | 5201.3951 | 5201.3951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15370 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15371 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7091 | 0.2 | 0.3 | 26003.1862 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.451 | 5200.451 | 5200.451 | 5200.451 | 5200.451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15372 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 16683.0389 | 0.2 | 0.3 | 26025.5406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.1232 | 5204.1232 | 5204.1232 | 5204.1232 | 5204.1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15373 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 5303.2738 | 0.2 | 0.3 | 8273.1071 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9152 | 5200.9152 | 5200.9152 | 5200.9152 | 5200.9152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15374 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 16556.0151 | 0.2 | 0.3 | 25827.3835 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15375 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 16667.8663 | 0.2 | 0.3 | 26001.8714 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15376 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 16779.9259 | 0.2 | 0.3 | 26176.6845 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15377 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 21823.9624 | 0.2 | 0.3 | 34045.3813 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15378 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 18776.7909 | 0.2 | 0.3 | 29291.7938 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3895.1133 | 3895.1133 | 3895.1133 | 3895.1133 | 3895.1133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15379 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 8774.1097 | 0.2 | 0.3 | 13687.6112 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7515.1351 | 7515.1351 | 7515.1351 | 7515.1351 | 7515.1351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15380 | CORAL SPRINGS | 20326 | Private | 2036 | 5 | Swales | 66.6667 | 10439.6346 | 0.2 | 0.3 | 16285.83 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15381 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9048.4821 | 9048.4821 | 9048.4821 | 9048.4821 | 9048.4821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15382 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7463 | 0.2 | 0.3 | 26003.2443 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5564.7618 | 5564.7618 | 5564.7618 | 5564.7618 | 5564.7618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15383 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 2613.4511 | 0.2 | 0.3 | 4076.9838 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9588.3793 | 9588.3793 | 9588.3793 | 9588.3793 | 9588.3793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15384 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 4048.5402 | 0.2 | 0.3 | 6315.7227 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9517.3308 | 9517.3308 | 9517.3308 | 9517.3308 | 9517.3308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15385 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 25296.6937 | 0.2 | 0.3 | 39462.8421 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9448.7895 | 9448.7895 | 9448.7895 | 9448.7895 | 9448.7895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15386 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 15322.8089 | 0.2 | 0.3 | 23903.5819 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9400.0455 | 9400.0455 | 9400.0455 | 9400.0455 | 9400.0455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15387 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 16666.6211 | 0.2 | 0.3 | 25999.929 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9330.7145 | 9330.7145 | 9330.7145 | 9330.7145 | 9330.7145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15388 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 11570.6905 | 0.2 | 0.3 | 18050.2772 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9275.5481 | 9275.5481 | 9275.5481 | 9275.5481 | 9275.5481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15389 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 3946.5035 | 0.2 | 0.3 | 6156.5454 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9198.4549 | 9198.4549 | 9198.4549 | 9198.4549 | 9198.4549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15390 | CORAL SPRINGS | 20325 | Public | 2033 | 5 | Swales | 66.6667 | 16656.8847 | 0.2 | 0.3 | 25984.7401 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7900.3212 | 7900.3212 | 7900.3212 | 7900.3212 | 7900.3212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15391 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 19002.1527 | 0.2 | 0.3 | 29643.3583 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8365.2788 | 8365.2788 | 8365.2788 | 8365.2788 | 8365.2788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15392 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 7682.4453 | 0.2 | 0.3 | 11984.6146 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9072.8391 | 9072.8391 | 9072.8391 | 9072.8391 | 9072.8391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15393 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 16668.0085 | 0.2 | 0.3 | 26002.0933 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9047.127 | 9047.127 | 9047.127 | 9047.127 | 9047.127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15394 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 24178.9551 | 0.2 | 0.3 | 37719.1699 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8940.7611 | 8940.7611 | 8940.7611 | 8940.7611 | 8940.7611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15395 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 25089.2754 | 0.2 | 0.3 | 39139.2696 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8877.2902 | 8877.2902 | 8877.2902 | 8877.2902 | 8877.2902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15396 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8687.1999 | 8687.1999 | 8687.1999 | 8687.1999 | 8687.1999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15397 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 22748.7636 | 0.2 | 0.3 | 35488.0712 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8679.8818 | 8679.8818 | 8679.8818 | 8679.8818 | 8679.8818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15398 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16863.9637 | 0.2 | 0.3 | 26307.7833 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15399 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 18085.9367 | 0.2 | 0.3 | 28214.0612 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8523.0403 | 8523.0403 | 8523.0403 | 8523.0403 | 8523.0403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15400 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 6649.4663 | 0.2 | 0.3 | 10373.1675 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.9646 | 5204.9646 | 5204.9646 | 5204.9646 | 5204.9646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15401 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16669.4547 | 0.2 | 0.3 | 26004.3494 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7237.3611 | 7237.3611 | 7237.3611 | 7237.3611 | 7237.3611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15402 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 16667.8241 | 0.2 | 0.3 | 26001.8055 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1380.8559 | 1380.8559 | 1380.8559 | 1380.8559 | 1380.8559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15403 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2173 | 0.2 | 0.3 | 26002.4189 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1206.6348 | 1206.6348 | 1206.6348 | 1206.6348 | 1206.6348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15404 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2801 | 0.2 | 0.3 | 26002.5169 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2466.4813 | 2466.4813 | 2466.4813 | 2466.4813 | 2466.4813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15405 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 16680.5389 | 0.2 | 0.3 | 26021.6407 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2599.9478 | 2599.9478 | 2599.9478 | 2599.9478 | 2599.9478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15406 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 18611.2383 | 0.2 | 0.3 | 29033.5318 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.2926 | 2600.2926 | 2600.2926 | 2600.2926 | 2600.2926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15407 | CORAL SPRINGS | 20309 | Public | 2033 | 5 | Swales | 66.6667 | 10124.2462 | 0.2 | 0.3 | 15793.8241 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3649.0618 | 3649.0618 | 3649.0618 | 3649.0618 | 3649.0618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15408 | CORAL SPRINGS | 20309 | Private | 2036 | 5 | Swales | 66.6667 | 10000.3626 | 0.2 | 0.3 | 15600.5657 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4993.6878 | 4993.6878 | 4993.6878 | 4993.6878 | 4993.6878 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15409 | CORAL SPRINGS | 20309 | Private | 2036 | 5 | Swales | 66.6667 | 16717.6335 | 0.2 | 0.3 | 26079.5082 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5848.0192 | 5848.0192 | 5848.0192 | 5848.0192 | 5848.0192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15410 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 403.126 | 0.2 | 0.3 | 628.8766 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2426.3149 | 2426.3149 | 2426.3149 | 2426.3149 | 2426.3149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15411 | CORAL SPRINGS | 20326 | Private | 2036 | 5 | Swales | 66.6667 | 15922.6645 | 0.2 | 0.3 | 24839.3566 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 203.0272 | 203.0272 | 203.0272 | 203.0272 | 203.0272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15412 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5360.9752 | 5360.9752 | 5360.9752 | 5360.9752 | 5360.9752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15413 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 17153.4865 | 0.2 | 0.3 | 26759.439 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5173.4868 | 5173.4868 | 5173.4868 | 5173.4868 | 5173.4868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15414 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16667.0908 | 0.2 | 0.3 | 26000.6616 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7910.6155 | 7910.6155 | 7910.6155 | 7910.6155 | 7910.6155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15415 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5786.8412 | 5786.8412 | 5786.8412 | 5786.8412 | 5786.8412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15416 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 26309.5281 | 0.2 | 0.3 | 41042.8638 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7999 | 5200.7999 | 5200.7999 | 5200.7999 | 5200.7999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15417 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 23518.2989 | 0.2 | 0.3 | 36688.5462 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3872 | 5200.3872 | 5200.3872 | 5200.3872 | 5200.3872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15418 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 14453.1899 | 0.2 | 0.3 | 22546.9763 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9744.2735 | 9744.2735 | 9744.2735 | 9744.2735 | 9744.2735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15419 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 8270.5799 | 0.2 | 0.3 | 12902.1047 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4350.4925 | 4350.4925 | 4350.4925 | 4350.4925 | 4350.4925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15420 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 24705.9185 | 0.2 | 0.3 | 38541.2328 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7514.0078 | 7514.0078 | 7514.0078 | 7514.0078 | 7514.0078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15421 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 25167.9316 | 0.2 | 0.3 | 39261.9733 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7463.226 | 7463.226 | 7463.226 | 7463.226 | 7463.226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15422 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 16669.3008 | 0.2 | 0.3 | 26004.1092 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7518.9547 | 7518.9547 | 7518.9547 | 7518.9547 | 7518.9547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15423 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 16668.0369 | 0.2 | 0.3 | 26002.1376 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6568.2984 | 6568.2984 | 6568.2984 | 6568.2984 | 6568.2984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15424 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 16674.7207 | 0.2 | 0.3 | 26012.5643 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8730.2399 | 8730.2399 | 8730.2399 | 8730.2399 | 8730.2399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15425 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 11486.8583 | 0.2 | 0.3 | 17919.4989 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6572.1173 | 6572.1173 | 6572.1173 | 6572.1173 | 6572.1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15426 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 2041.1829 | 0.2 | 0.3 | 3184.2454 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7098 | 5200.7098 | 5200.7098 | 5200.7098 | 5200.7098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15427 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 18156.8854 | 0.2 | 0.3 | 28324.7412 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7416.7719 | 7416.7719 | 7416.7719 | 7416.7719 | 7416.7719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15428 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 16555.9518 | 0.2 | 0.3 | 25827.2848 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9041.4123 | 9041.4123 | 9041.4123 | 9041.4123 | 9041.4123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15429 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 16667.9901 | 0.2 | 0.3 | 26002.0646 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7099.23 | 7099.23 | 7099.23 | 7099.23 | 7099.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15430 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 25030.8865 | 0.2 | 0.3 | 39048.183 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9730.8575 | 9730.8575 | 9730.8575 | 9730.8575 | 9730.8575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15431 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16665.4083 | 0.2 | 0.3 | 25998.0369 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9767.2092 | 9767.2092 | 9767.2092 | 9767.2092 | 9767.2092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15432 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16665.4305 | 0.2 | 0.3 | 25998.0715 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5556.2343 | 5556.2343 | 5556.2343 | 5556.2343 | 5556.2343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15433 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 24868.0631 | 0.2 | 0.3 | 38794.1784 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.865 | 5205.865 | 5205.865 | 5205.865 | 5205.865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15434 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 23098.196 | 0.2 | 0.3 | 36033.1858 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.8114 | 5203.8114 | 5203.8114 | 5203.8114 | 5203.8114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15435 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 14272.9309 | 0.2 | 0.3 | 22265.7723 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6230.9851 | 6230.9851 | 6230.9851 | 6230.9851 | 6230.9851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15436 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 22706.3868 | 0.2 | 0.3 | 35421.9634 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.815 | 5200.815 | 5200.815 | 5200.815 | 5200.815 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15437 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 22651.0403 | 0.2 | 0.3 | 35335.6228 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15438 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 3419.8551 | 0.2 | 0.3 | 5334.9739 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15439 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 23024.9377 | 0.2 | 0.3 | 35918.9029 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15440 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 17595.5788 | 0.2 | 0.3 | 27449.1029 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8207.6045 | 8207.6045 | 8207.6045 | 8207.6045 | 8207.6045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15441 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7015 | 0.2 | 0.3 | 26003.1743 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3247.7218 | 3247.7218 | 3247.7218 | 3247.7218 | 3247.7218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15442 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 17662.2027 | 0.2 | 0.3 | 27553.0362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5252 | 5200.5252 | 5200.5252 | 5200.5252 | 5200.5252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15443 | CORAL SPRINGS | 20326 | Private | 2036 | 5 | Swales | 66.6667 | 16633.2449 | 0.2 | 0.3 | 25947.8621 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3944.5099 | 3944.5099 | 3944.5099 | 3944.5099 | 3944.5099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15444 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6458.9376 | 6458.9376 | 6458.9376 | 6458.9376 | 6458.9376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15445 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8701 | 5201.8701 | 5201.8701 | 5201.8701 | 5201.8701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15446 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2404 | 0.2 | 0.3 | 26002.455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 5201.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15447 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 7774.8582 | 0.2 | 0.3 | 12128.7788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 5201.5999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15448 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 17258.8382 | 0.2 | 0.3 | 26923.7876 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15449 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 21429.1697 | 0.2 | 0.3 | 33429.5048 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.0351 | 5206.0351 | 5206.0351 | 5206.0351 | 5206.0351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15450 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 29993.1609 | 0.2 | 0.3 | 46789.331 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5284.4052 | 5284.4052 | 5284.4052 | 5284.4052 | 5284.4052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15451 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 26309.2672 | 0.2 | 0.3 | 41042.4568 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4715.2428 | 4715.2428 | 4715.2428 | 4715.2428 | 4715.2428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15452 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 13354.5553 | 0.2 | 0.3 | 20833.1062 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6816.4658 | 6816.4658 | 6816.4658 | 6816.4658 | 6816.4658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15453 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 10258.4924 | 0.2 | 0.3 | 16003.2481 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8293 | 5200.8293 | 5200.8293 | 5200.8293 | 5200.8293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15454 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 23463.5569 | 0.2 | 0.3 | 36603.1487 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8777 | 5200.8777 | 5200.8777 | 5200.8777 | 5200.8777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15455 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 16676.4525 | 0.2 | 0.3 | 26015.266 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6827 | 5200.6827 | 5200.6827 | 5200.6827 | 5200.6827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15456 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 16840.3014 | 0.2 | 0.3 | 26270.8702 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6868.9943 | 6868.9943 | 6868.9943 | 6868.9943 | 6868.9943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15457 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 10751.263 | 0.2 | 0.3 | 16771.9703 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10405.6728 | 10405.6728 | 10405.6728 | 10405.6728 | 10405.6728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15458 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 6386.8273 | 0.2 | 0.3 | 9963.4505 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5885.3903 | 5885.3903 | 5885.3903 | 5885.3903 | 5885.3903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15459 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 3557.6769 | 0.2 | 0.3 | 5549.9759 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2601.3234 | 2601.3234 | 2601.3234 | 2601.3234 | 2601.3234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15460 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 21305.5751 | 0.2 | 0.3 | 33236.6971 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6097.8844 | 6097.8844 | 6097.8844 | 6097.8844 | 6097.8844 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15461 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 25286.0749 | 0.2 | 0.3 | 39446.2769 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6905.9322 | 6905.9322 | 6905.9322 | 6905.9322 | 6905.9322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15462 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 9350.0889 | 0.2 | 0.3 | 14586.1387 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15463 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 8951.4751 | 0.2 | 0.3 | 13964.3011 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6287.1722 | 6287.1722 | 6287.1722 | 6287.1722 | 6287.1722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15464 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 9772.5611 | 0.2 | 0.3 | 15245.1953 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8741.1934 | 8741.1934 | 8741.1934 | 8741.1934 | 8741.1934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15465 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 23436.4723 | 0.2 | 0.3 | 36560.8967 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6855.385 | 6855.385 | 6855.385 | 6855.385 | 6855.385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15466 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 31333.8972 | 0.2 | 0.3 | 48880.8796 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6826.5391 | 6826.5391 | 6826.5391 | 6826.5391 | 6826.5391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15467 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 24000.6321 | 0.2 | 0.3 | 37440.986 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15468 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 8110.5619 | 0.2 | 0.3 | 12652.4765 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6649.3952 | 6649.3952 | 6649.3952 | 6649.3952 | 6649.3952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15469 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 9017.8962 | 0.2 | 0.3 | 14067.9181 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6559.2987 | 6559.2987 | 6559.2987 | 6559.2987 | 6559.2987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15470 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 14239.4588 | 0.2 | 0.3 | 22213.5557 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6541.4619 | 6541.4619 | 6541.4619 | 6541.4619 | 6541.4619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15471 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 17753.2645 | 0.2 | 0.3 | 27695.0926 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2798.2791 | 2798.2791 | 2798.2791 | 2798.2791 | 2798.2791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15472 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 15830.1218 | 0.2 | 0.3 | 24694.99 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2439 | 5201.2439 | 5201.2439 | 5201.2439 | 5201.2439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15473 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 1626.9357 | 0.2 | 0.3 | 2538.0196 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5717.0216 | 5717.0216 | 5717.0216 | 5717.0216 | 5717.0216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15474 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 2321.7857 | 0.2 | 0.3 | 3621.9856 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.4377 | 2600.4377 | 2600.4377 | 2600.4377 | 2600.4377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15475 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 21315.5649 | 0.2 | 0.3 | 33252.2812 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5339 | 5201.5339 | 5201.5339 | 5201.5339 | 5201.5339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15476 | CORAL SPRINGS | 20302 | Public | 2033 | 5 | Swales | 66.6667 | 16670.3624 | 0.2 | 0.3 | 26005.7653 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2798.1027 | 2798.1027 | 2798.1027 | 2798.1027 | 2798.1027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15477 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 17126.3883 | 0.2 | 0.3 | 26717.1658 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9024 | 5200.9024 | 5200.9024 | 5200.9024 | 5200.9024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15478 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16668.6825 | 0.2 | 0.3 | 26003.1448 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2628.9971 | 2628.9971 | 2628.9971 | 2628.9971 | 2628.9971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15479 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16669.2583 | 0.2 | 0.3 | 26004.0429 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5499.9563 | 5499.9563 | 5499.9563 | 5499.9563 | 5499.9563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15480 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 22534.8279 | 0.2 | 0.3 | 35154.3315 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 5199.9792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15481 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 6719.5041 | 0.2 | 0.3 | 10482.4263 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1654 | 5200.1654 | 5200.1654 | 5200.1654 | 5200.1654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15482 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 21325.7738 | 0.2 | 0.3 | 33268.2071 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15483 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16664.8297 | 0.2 | 0.3 | 25997.1343 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15484 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16665.9407 | 0.2 | 0.3 | 25998.8674 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3289 | 5200.3289 | 5200.3289 | 5200.3289 | 5200.3289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15485 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 21684.3372 | 0.2 | 0.3 | 33827.566 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6563.9186 | 6563.9186 | 6563.9186 | 6563.9186 | 6563.9186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15486 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 23325.6713 | 0.2 | 0.3 | 36388.0473 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4009.8041 | 4009.8041 | 4009.8041 | 4009.8041 | 4009.8041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15487 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 10027.3729 | 0.2 | 0.3 | 15642.7018 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4206.3609 | 4206.3609 | 4206.3609 | 4206.3609 | 4206.3609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15488 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 17277.4213 | 0.2 | 0.3 | 26952.7773 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4061.0588 | 4061.0588 | 4061.0588 | 4061.0588 | 4061.0588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15489 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 11039.4731 | 0.2 | 0.3 | 17221.5781 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7923.4523 | 7923.4523 | 7923.4523 | 7923.4523 | 7923.4523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15490 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 17265.2019 | 0.2 | 0.3 | 26933.715 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15491 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 28615.2953 | 0.2 | 0.3 | 44639.8607 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7191.9619 | 7191.9619 | 7191.9619 | 7191.9619 | 7191.9619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15492 | CORAL SPRINGS | 20309 | Private | 2026 | 5 | Swales | 66.6667 | 17694.1805 | 0.2 | 0.3 | 27602.9215 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3318 | 5200.3318 | 5200.3318 | 5200.3318 | 5200.3318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15493 | CORAL SPRINGS | 20309 | Private | 2026 | 5 | Swales | 66.6667 | 10416.7351 | 0.2 | 0.3 | 16250.1068 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15494 | CORAL SPRINGS | 20309 | Private | 2026 | 5 | Swales | 66.6667 | 7064.0375 | 0.2 | 0.3 | 11019.8984 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15495 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 20643.6669 | 0.2 | 0.3 | 32204.1203 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2686 | 5200.2686 | 5200.2686 | 5200.2686 | 5200.2686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15496 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 26200.4401 | 0.2 | 0.3 | 40872.6865 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6612.7176 | 6612.7176 | 6612.7176 | 6612.7176 | 6612.7176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15497 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 26521.0369 | 0.2 | 0.3 | 41372.8176 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5246.7089 | 5246.7089 | 5246.7089 | 5246.7089 | 5246.7089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15498 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 16686.0371 | 0.2 | 0.3 | 26030.2179 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5231.0892 | 5231.0892 | 5231.0892 | 5231.0892 | 5231.0892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15499 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 16666.9885 | 0.2 | 0.3 | 26000.502 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 5201.5146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15500 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 16667.8003 | 0.2 | 0.3 | 26001.7684 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15501 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 16717.7011 | 0.2 | 0.3 | 26079.6137 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.894 | 5200.894 | 5200.894 | 5200.894 | 5200.894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15502 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 18559.6155 | 0.2 | 0.3 | 28953.0001 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7140.9078 | 7140.9078 | 7140.9078 | 7140.9078 | 7140.9078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15503 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16597.7027 | 0.2 | 0.3 | 25892.4162 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6832 | 5200.6832 | 5200.6832 | 5200.6832 | 5200.6832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15504 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1128 | 5200.1128 | 5200.1128 | 5200.1128 | 5200.1128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15505 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 23894.6046 | 0.2 | 0.3 | 37275.5832 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15506 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 24374.8402 | 0.2 | 0.3 | 38024.7507 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1845 | 5200.1845 | 5200.1845 | 5200.1845 | 5200.1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15507 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 14373.0777 | 0.2 | 0.3 | 22422.0012 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6745.5847 | 6745.5847 | 6745.5847 | 6745.5847 | 6745.5847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15508 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 4323.479 | 0.2 | 0.3 | 6744.6272 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2802.1106 | 2802.1106 | 2802.1106 | 2802.1106 | 2802.1106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15509 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 0.61013 | 0.2 | 0.3 | 0.95181 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8675.8235 | 8675.8235 | 8675.8235 | 8675.8235 | 8675.8235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15510 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 21121.9468 | 0.2 | 0.3 | 32950.237 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1828 | 5201.1828 | 5201.1828 | 5201.1828 | 5201.1828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15511 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 3454.7508 | 0.2 | 0.3 | 5389.4112 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7773.2006 | 7773.2006 | 7773.2006 | 7773.2006 | 7773.2006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15512 | CORAL SPRINGS | 20302 | Private | 2033 | 5 | Swales | 66.6667 | 351.8939 | 0.2 | 0.3 | 548.9545 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3878.6669 | 3878.6669 | 3878.6669 | 3878.6669 | 3878.6669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15513 | CORAL SPRINGS | 20302 | Private | 2033 | 5 | Swales | 66.6667 | 30769.749 | 0.2 | 0.3 | 48000.8084 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9778.058 | 9778.058 | 9778.058 | 9778.058 | 9778.058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15514 | CORAL SPRINGS | 20302 | Private | 2033 | 5 | Swales | 66.6667 | 8814.7849 | 0.2 | 0.3 | 13751.0644 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6900.7515 | 6900.7515 | 6900.7515 | 6900.7515 | 6900.7515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15515 | CORAL SPRINGS | 20302 | Public | 2033 | 5 | Swales | 66.6667 | 16669.4465 | 0.2 | 0.3 | 26004.3366 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7360.8653 | 7360.8653 | 7360.8653 | 7360.8653 | 7360.8653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15516 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 22400.9751 | 0.2 | 0.3 | 34945.5212 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5209.7425 | 5209.7425 | 5209.7425 | 5209.7425 | 5209.7425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15517 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 21104.8548 | 0.2 | 0.3 | 32923.5735 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0416 | 5200.0416 | 5200.0416 | 5200.0416 | 5200.0416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15518 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16669.5788 | 0.2 | 0.3 | 26004.5429 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1323 | 5200.1323 | 5200.1323 | 5200.1323 | 5200.1323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15519 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 22201.1927 | 0.2 | 0.3 | 34633.8607 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15520 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16769.9911 | 0.2 | 0.3 | 26161.1861 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1669 | 5200.1669 | 5200.1669 | 5200.1669 | 5200.1669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15521 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 26159.3103 | 0.2 | 0.3 | 40808.524 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.3431 | 9777.3431 | 9777.3431 | 9777.3431 | 9777.3431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15522 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 22118.2233 | 0.2 | 0.3 | 34504.4283 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4686.3322 | 4686.3322 | 4686.3322 | 4686.3322 | 4686.3322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15523 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 14210.0281 | 0.2 | 0.3 | 22167.6438 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10410.9615 | 10410.9615 | 10410.9615 | 10410.9615 | 10410.9615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15524 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 33541.8603 | 0.2 | 0.3 | 52325.302 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 332.1754 | 332.1754 | 332.1754 | 332.1754 | 332.1754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15525 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 18132.3085 | 0.2 | 0.3 | 28286.4013 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5252.4493 | 5252.4493 | 5252.4493 | 5252.4493 | 5252.4493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15526 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 27567.8089 | 0.2 | 0.3 | 43005.7819 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2942 | 5201.2942 | 5201.2942 | 5201.2942 | 5201.2942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15527 | CORAL SPRINGS | 20309 | Private | 2026 | 5 | Swales | 66.6667 | 2483.9198 | 0.2 | 0.3 | 3874.9149 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9952 | 5201.9952 | 5201.9952 | 5201.9952 | 5201.9952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15528 | CORAL SPRINGS | 20309 | Private | 2026 | 5 | Swales | 66.6667 | 25060.6455 | 0.2 | 0.3 | 39094.6069 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.272 | 5200.272 | 5200.272 | 5200.272 | 5200.272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15529 | CORAL SPRINGS | 20309 | Private | 2026 | 5 | Swales | 66.6667 | 26983.1125 | 0.2 | 0.3 | 42093.6556 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7197.7578 | 7197.7578 | 7197.7578 | 7197.7578 | 7197.7578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15530 | CORAL SPRINGS | 20309 | Private | 2026 | 5 | Swales | 66.6667 | 35871.8323 | 0.2 | 0.3 | 55960.0584 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1331.1323 | 1331.1323 | 1331.1323 | 1331.1323 | 1331.1323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15531 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1832.9277 | 1832.9277 | 1832.9277 | 1832.9277 | 1832.9277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15532 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 16667.57 | 0.2 | 0.3 | 26001.4092 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6511.6528 | 6511.6528 | 6511.6528 | 6511.6528 | 6511.6528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15533 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 19659.3527 | 0.2 | 0.3 | 30668.5903 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15534 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16663.1919 | 0.2 | 0.3 | 25994.5794 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11059.9399 | 11059.9399 | 11059.9399 | 11059.9399 | 11059.9399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15535 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6053 | 0.2 | 0.3 | 25999.9042 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9988.1859 | 9988.1859 | 9988.1859 | 9988.1859 | 9988.1859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15536 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 17114.0002 | 0.2 | 0.3 | 26697.8403 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3065.4337 | 3065.4337 | 3065.4337 | 3065.4337 | 3065.4337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15537 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6027 | 0.2 | 0.3 | 25999.9003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5218.8308 | 5218.8308 | 5218.8308 | 5218.8308 | 5218.8308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15538 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 25161.9817 | 0.2 | 0.3 | 39252.6914 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15539 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 22781.8148 | 0.2 | 0.3 | 35539.6311 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8521.1139 | 8521.1139 | 8521.1139 | 8521.1139 | 8521.1139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15540 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 26016.2461 | 0.2 | 0.3 | 40585.344 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7486.3864 | 7486.3864 | 7486.3864 | 7486.3864 | 7486.3864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15541 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 17463.9749 | 0.2 | 0.3 | 27243.8009 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4645.1865 | 4645.1865 | 4645.1865 | 4645.1865 | 4645.1865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15542 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 5096.6324 | 0.2 | 0.3 | 7950.7465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15543 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 1584.0125 | 0.2 | 0.3 | 2471.0594 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5565.4268 | 5565.4268 | 5565.4268 | 5565.4268 | 5565.4268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15544 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 7152.2906 | 0.2 | 0.3 | 11157.5733 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8835.8253 | 8835.8253 | 8835.8253 | 8835.8253 | 8835.8253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15545 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 15902.0201 | 0.2 | 0.3 | 24807.1514 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9790.7254 | 9790.7254 | 9790.7254 | 9790.7254 | 9790.7254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15546 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 6270.1021 | 0.2 | 0.3 | 9781.3593 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7980.2908 | 7980.2908 | 7980.2908 | 7980.2908 | 7980.2908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15547 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 18171.4268 | 0.2 | 0.3 | 28347.4258 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8355.3637 | 8355.3637 | 8355.3637 | 8355.3637 | 8355.3637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15548 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 21945.6489 | 0.2 | 0.3 | 34235.2123 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7275.7418 | 7275.7418 | 7275.7418 | 7275.7418 | 7275.7418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15549 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 5593.5017 | 0.2 | 0.3 | 8725.8626 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 2600.1602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15550 | CORAL SPRINGS | 20302 | Private | 2033 | 5 | Swales | 66.6667 | 3660.1994 | 0.2 | 0.3 | 5709.9111 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6971.4088 | 6971.4088 | 6971.4088 | 6971.4088 | 6971.4088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15551 | CORAL SPRINGS | 20302 | Private | 2033 | 5 | Swales | 66.6667 | 25604.6649 | 0.2 | 0.3 | 39943.2773 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 935.6731 | 935.6731 | 935.6731 | 935.6731 | 935.6731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15552 | CORAL SPRINGS | 20302 | Private | 2033 | 5 | Swales | 66.6667 | 8323.9779 | 0.2 | 0.3 | 12985.4055 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8464.9622 | 8464.9622 | 8464.9622 | 8464.9622 | 8464.9622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15553 | CORAL SPRINGS | 20302 | Public | 2033 | 5 | Swales | 66.6667 | 2325.3775 | 0.2 | 0.3 | 3627.5888 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7740 | 7740 | 7740 | 7740 | 7740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15554 | CORAL SPRINGS | 20302 | Public | 2033 | 5 | Swales | 66.6667 | 176.0182 | 0.2 | 0.3 | 274.5884 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8033.324 | 8033.324 | 8033.324 | 8033.324 | 8033.324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15555 | CORAL SPRINGS | 20302 | Public | 2033 | 5 | Swales | 66.6667 | 16667.9223 | 0.2 | 0.3 | 26001.9588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6980.4677 | 6980.4677 | 6980.4677 | 6980.4677 | 6980.4677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15556 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 17372.8768 | 0.2 | 0.3 | 27101.6878 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 961.1956 | 961.1956 | 961.1956 | 961.1956 | 961.1956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15557 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16834.5628 | 0.2 | 0.3 | 26261.918 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6328.2624 | 6328.2624 | 6328.2624 | 6328.2624 | 6328.2624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15558 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 3018.2945 | 0.2 | 0.3 | 4708.5394 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13984.4465 | 13984.4465 | 13984.4465 | 13984.4465 | 13984.4465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15559 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16108.1921 | 0.2 | 0.3 | 25128.7797 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8922.3393 | 8922.3393 | 8922.3393 | 8922.3393 | 8922.3393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15560 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 17290.8986 | 0.2 | 0.3 | 26973.8018 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 16362.3514 | 16362.3514 | 16362.3514 | 16362.3514 | 16362.3514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15561 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 24074.6332 | 0.2 | 0.3 | 37556.4278 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 13828.9089 | 13828.9089 | 13828.9089 | 13828.9089 | 13828.9089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15562 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 16859.9995 | 0.2 | 0.3 | 26301.5993 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10117.6763 | 10117.6763 | 10117.6763 | 10117.6763 | 10117.6763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15563 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 9377.4642 | 0.2 | 0.3 | 14628.8442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2268.2751 | 2268.2751 | 2268.2751 | 2268.2751 | 2268.2751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15564 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 32748.0473 | 0.2 | 0.3 | 51086.9537 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3079.0921 | 3079.0921 | 3079.0921 | 3079.0921 | 3079.0921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15565 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 23944.6972 | 0.2 | 0.3 | 37353.7276 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5076.5522 | 5076.5522 | 5076.5522 | 5076.5522 | 5076.5522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15566 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 7885.8975 | 0.2 | 0.3 | 12302 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4964.7734 | 4964.7734 | 4964.7734 | 4964.7734 | 4964.7734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15567 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 20692.6993 | 0.2 | 0.3 | 32280.6109 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7015.268 | 7015.268 | 7015.268 | 7015.268 | 7015.268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15568 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 19728.2212 | 0.2 | 0.3 | 30776.0251 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5087.4712 | 5087.4712 | 5087.4712 | 5087.4712 | 5087.4712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15569 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 9178.3937 | 0.2 | 0.3 | 14318.2942 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8681.4129 | 8681.4129 | 8681.4129 | 8681.4129 | 8681.4129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15570 | CORAL SPRINGS | 20309 | Private | 2026 | 5 | Swales | 66.6667 | 2184.0787 | 0.2 | 0.3 | 3407.1628 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15571 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 18522.3268 | 0.2 | 0.3 | 28894.8298 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7593.0829 | 7593.0829 | 7593.0829 | 7593.0829 | 7593.0829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15572 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 23695.9856 | 0.2 | 0.3 | 36965.7375 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6419.517 | 6419.517 | 6419.517 | 6419.517 | 6419.517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15573 | COCONUT CREEK | 10614 | Private | 2036 | 5 | Swales | 66.6667 | 32810.9169 | 0.2 | 0.3 | 51185.0303 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8488.1304 | 8488.1304 | 8488.1304 | 8488.1304 | 8488.1304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15574 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9546.9696 | 9546.9696 | 9546.9696 | 9546.9696 | 9546.9696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15575 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6213 | 0.2 | 0.3 | 25999.9293 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7375.3526 | 7375.3526 | 7375.3526 | 7375.3526 | 7375.3526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15576 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16985.0225 | 0.2 | 0.3 | 26496.6352 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6254.4333 | 6254.4333 | 6254.4333 | 6254.4333 | 6254.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15577 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16667.4793 | 0.2 | 0.3 | 26001.2677 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8661.8232 | 8661.8232 | 8661.8232 | 8661.8232 | 8661.8232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15578 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.1923 | 5205.1923 | 5205.1923 | 5205.1923 | 5205.1923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15579 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16667.992 | 0.2 | 0.3 | 26002.0675 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9707.0647 | 9707.0647 | 9707.0647 | 9707.0647 | 9707.0647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15580 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 20624.4363 | 0.2 | 0.3 | 32174.1206 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6595 | 5201.6595 | 5201.6595 | 5201.6595 | 5201.6595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15581 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16666.3004 | 0.2 | 0.3 | 25999.4286 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3162 | 5200.3162 | 5200.3162 | 5200.3162 | 5200.3162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15582 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16667.9693 | 0.2 | 0.3 | 26002.0321 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9790.6292 | 9790.6292 | 9790.6292 | 9790.6292 | 9790.6292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15583 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 17010.8531 | 0.2 | 0.3 | 26536.9308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8311 | 5200.8311 | 5200.8311 | 5200.8311 | 5200.8311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15584 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 10767.167 | 0.2 | 0.3 | 16796.7805 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7445 | 5200.7445 | 5200.7445 | 5200.7445 | 5200.7445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15585 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 17169.4824 | 0.2 | 0.3 | 26784.3925 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6688.8437 | 6688.8437 | 6688.8437 | 6688.8437 | 6688.8437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15586 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 716.539 | 0.2 | 0.3 | 1117.8008 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15587 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 22834.9361 | 0.2 | 0.3 | 35622.5004 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6965 | 5200.6965 | 5200.6965 | 5200.6965 | 5200.6965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15588 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 14931.6402 | 0.2 | 0.3 | 23293.3587 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6812.6332 | 6812.6332 | 6812.6332 | 6812.6332 | 6812.6332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15589 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 16958.5003 | 0.2 | 0.3 | 26455.2605 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3869 | 5200.3869 | 5200.3869 | 5200.3869 | 5200.3869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15590 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 29920.1088 | 0.2 | 0.3 | 46675.3697 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9420.4284 | 9420.4284 | 9420.4284 | 9420.4284 | 9420.4284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15591 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 17060.9703 | 0.2 | 0.3 | 26615.1136 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15592 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 13201.3926 | 0.2 | 0.3 | 20594.1725 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9864.3513 | 9864.3513 | 9864.3513 | 9864.3513 | 9864.3513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15593 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 35797.3175 | 0.2 | 0.3 | 55843.8152 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.197 | 5200.197 | 5200.197 | 5200.197 | 5200.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15594 | CORAL SPRINGS | 20302 | Public | 2033 | 5 | Swales | 66.6667 | 28718.9745 | 0.2 | 0.3 | 44801.6002 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5224.6328 | 5224.6328 | 5224.6328 | 5224.6328 | 5224.6328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15595 | CORAL SPRINGS | 20302 | Public | 2033 | 5 | Swales | 66.6667 | 16491.0836 | 0.2 | 0.3 | 25726.0904 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8824 | 5201.8824 | 5201.8824 | 5201.8824 | 5201.8824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15596 | CORAL SPRINGS | 20302 | Public | 2033 | 5 | Swales | 66.6667 | 31336.7363 | 0.2 | 0.3 | 48885.3087 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2203.8729 | 2203.8729 | 2203.8729 | 2203.8729 | 2203.8729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15597 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16667.0596 | 0.2 | 0.3 | 26000.613 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9002.0644 | 9002.0644 | 9002.0644 | 9002.0644 | 9002.0644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15598 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4069.9704 | 4069.9704 | 4069.9704 | 4069.9704 | 4069.9704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15599 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 20221.2011 | 0.2 | 0.3 | 31545.0737 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15600 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 44137.5848 | 0.2 | 0.3 | 68854.6323 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 5200.2351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15601 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 7519.2163 | 0.2 | 0.3 | 11729.9774 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0772 | 5200.0772 | 5200.0772 | 5200.0772 | 5200.0772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15602 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 7484.7246 | 0.2 | 0.3 | 11676.1704 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5712.9954 | 5712.9954 | 5712.9954 | 5712.9954 | 5712.9954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15603 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 15970.6289 | 0.2 | 0.3 | 24914.181 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5546.8143 | 5546.8143 | 5546.8143 | 5546.8143 | 5546.8143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15604 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 32844.4143 | 0.2 | 0.3 | 51237.2864 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5742 | 5200.5742 | 5200.5742 | 5200.5742 | 5200.5742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15605 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 19863.1563 | 0.2 | 0.3 | 30986.5239 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5707.0932 | 5707.0932 | 5707.0932 | 5707.0932 | 5707.0932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15606 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 20550.3815 | 0.2 | 0.3 | 32058.5952 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5209.0467 | 5209.0467 | 5209.0467 | 5209.0467 | 5209.0467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15607 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 2903.5008 | 0.2 | 0.3 | 4529.4612 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1317.8951 | 1317.8951 | 1317.8951 | 1317.8951 | 1317.8951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15608 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 18552.4941 | 0.2 | 0.3 | 28941.8907 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9803.7927 | 9803.7927 | 9803.7927 | 9803.7927 | 9803.7927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15609 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 21431.0783 | 0.2 | 0.3 | 33432.4821 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8716.0962 | 8716.0962 | 8716.0962 | 8716.0962 | 8716.0962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15610 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 22785.6501 | 0.2 | 0.3 | 35545.6142 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5328.4352 | 5328.4352 | 5328.4352 | 5328.4352 | 5328.4352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15611 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 16513.9519 | 0.2 | 0.3 | 25761.7649 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5427.7045 | 5427.7045 | 5427.7045 | 5427.7045 | 5427.7045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15612 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 24589.2789 | 0.2 | 0.3 | 38359.275 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15613 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 25604.3279 | 0.2 | 0.3 | 39942.7516 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5978.2412 | 5978.2412 | 5978.2412 | 5978.2412 | 5978.2412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15614 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 8912.4583 | 0.2 | 0.3 | 13903.435 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3536.537 | 3536.537 | 3536.537 | 3536.537 | 3536.537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15615 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 23883.2189 | 0.2 | 0.3 | 37257.8215 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7402.4601 | 7402.4601 | 7402.4601 | 7402.4601 | 7402.4601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15616 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15617 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6394.3079 | 6394.3079 | 6394.3079 | 6394.3079 | 6394.3079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15618 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16668.3826 | 0.2 | 0.3 | 26002.6769 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2816 | 5200.2816 | 5200.2816 | 5200.2816 | 5200.2816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15619 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16669.6504 | 0.2 | 0.3 | 26004.6546 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9779.3937 | 9779.3937 | 9779.3937 | 9779.3937 | 9779.3937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15620 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 26737.1524 | 0.2 | 0.3 | 41709.9577 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.2446 | 9776.2446 | 9776.2446 | 9776.2446 | 9776.2446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15621 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16733.6596 | 0.2 | 0.3 | 26104.509 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6540.8496 | 6540.8496 | 6540.8496 | 6540.8496 | 6540.8496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15622 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 23800.9797 | 0.2 | 0.3 | 37129.5283 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5794.7428 | 5794.7428 | 5794.7428 | 5794.7428 | 5794.7428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15623 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 26625.2933 | 0.2 | 0.3 | 41535.4576 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0918 | 5200.0918 | 5200.0918 | 5200.0918 | 5200.0918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15624 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16705.2686 | 0.2 | 0.3 | 26060.219 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5226.109 | 5226.109 | 5226.109 | 5226.109 | 5226.109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15625 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 15841.6133 | 0.2 | 0.3 | 24712.9167 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 5200.8322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15626 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 7390.6395 | 0.2 | 0.3 | 11529.3976 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 5200.1498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15627 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 19759.1162 | 0.2 | 0.3 | 30824.2213 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.4015 | 5203.4015 | 5203.4015 | 5203.4015 | 5203.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15628 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 28801.6047 | 0.2 | 0.3 | 44930.5034 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0291 | 5202.0291 | 5202.0291 | 5202.0291 | 5202.0291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15629 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 20022.3199 | 0.2 | 0.3 | 31234.8191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4693.3817 | 4693.3817 | 4693.3817 | 4693.3817 | 4693.3817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15630 | CORAL SPRINGS | 20325 | Public | 2036 | 5 | Swales | 66.6667 | 476.9501 | 0.2 | 0.3 | 744.0422 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4388.8371 | 4388.8371 | 4388.8371 | 4388.8371 | 4388.8371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15631 | CORAL SPRINGS | 20325 | Private | 2036 | 5 | Swales | 66.6667 | 1893.2471 | 0.2 | 0.3 | 2953.4655 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5811.6115 | 5811.6115 | 5811.6115 | 5811.6115 | 5811.6115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15632 | CORAL SPRINGS | 20302 | Public | 2033 | 5 | Swales | 66.6667 | 30201.2383 | 0.2 | 0.3 | 47113.9317 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.369 | 5200.369 | 5200.369 | 5200.369 | 5200.369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15633 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16852.879 | 0.2 | 0.3 | 26290.4912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9374.4848 | 9374.4848 | 9374.4848 | 9374.4848 | 9374.4848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15634 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 26169.922 | 0.2 | 0.3 | 40825.0783 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2419 | 5200.2419 | 5200.2419 | 5200.2419 | 5200.2419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15635 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1795 | 5200.1795 | 5200.1795 | 5200.1795 | 5200.1795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15636 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 21043.7639 | 0.2 | 0.3 | 32828.2716 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2649 | 5200.2649 | 5200.2649 | 5200.2649 | 5200.2649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15637 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 22171.0291 | 0.2 | 0.3 | 34586.8054 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.909 | 5200.909 | 5200.909 | 5200.909 | 5200.909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15638 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 97.395 | 0.2 | 0.3 | 151.9362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4560.9101 | 4560.9101 | 4560.9101 | 4560.9101 | 4560.9101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15639 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16620.9448 | 0.2 | 0.3 | 25928.6739 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7390.7176 | 7390.7176 | 7390.7176 | 7390.7176 | 7390.7176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15640 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 20778.1734 | 0.2 | 0.3 | 32413.9505 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 19.8048 | 19.8048 | 19.8048 | 19.8048 | 19.8048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15641 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 13708.1429 | 0.2 | 0.3 | 21384.7029 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8712.5473 | 8712.5473 | 8712.5473 | 8712.5473 | 8712.5473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15642 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 13654.0477 | 0.2 | 0.3 | 21300.3145 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3696.2193 | 3696.2193 | 3696.2193 | 3696.2193 | 3696.2193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15643 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 24645.8869 | 0.2 | 0.3 | 38447.5836 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7817 | 5200.7817 | 5200.7817 | 5200.7817 | 5200.7817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15644 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 16912.7526 | 0.2 | 0.3 | 26383.8941 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8603.5362 | 8603.5362 | 8603.5362 | 8603.5362 | 8603.5362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15645 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 26625.4462 | 0.2 | 0.3 | 41535.6961 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 502.4222 | 502.4222 | 502.4222 | 502.4222 | 502.4222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15646 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 13963.2633 | 0.2 | 0.3 | 21782.6907 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5443.3024 | 5443.3024 | 5443.3024 | 5443.3024 | 5443.3024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15647 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 8807.8487 | 0.2 | 0.3 | 13740.244 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5942 | 5203.5942 | 5203.5942 | 5203.5942 | 5203.5942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15648 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 8462.0131 | 0.2 | 0.3 | 13200.7405 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3086 | 5200.3086 | 5200.3086 | 5200.3086 | 5200.3086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15649 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 8334.786 | 0.2 | 0.3 | 13002.2662 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7902.6899 | 7902.6899 | 7902.6899 | 7902.6899 | 7902.6899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15650 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 8834.6302 | 0.2 | 0.3 | 13782.0231 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7316.1676 | 7316.1676 | 7316.1676 | 7316.1676 | 7316.1676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15651 | CORAL SPRINGS | 20309 | Public | 2036 | 5 | Swales | 66.6667 | 10962.0887 | 0.2 | 0.3 | 17100.8584 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5921.9971 | 5921.9971 | 5921.9971 | 5921.9971 | 5921.9971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15652 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7309.5261 | 7309.5261 | 7309.5261 | 7309.5261 | 7309.5261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15653 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6055 | 0.2 | 0.3 | 25999.9046 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4212.2825 | 4212.2825 | 4212.2825 | 4212.2825 | 4212.2825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15654 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16621.6952 | 0.2 | 0.3 | 25929.8445 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6797.7928 | 6797.7928 | 6797.7928 | 6797.7928 | 6797.7928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15655 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 46.9523 | 0.2 | 0.3 | 73.2456 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6268.6724 | 6268.6724 | 6268.6724 | 6268.6724 | 6268.6724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15656 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16670.4713 | 0.2 | 0.3 | 26005.9353 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3861.2417 | 3861.2417 | 3861.2417 | 3861.2417 | 3861.2417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15657 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 31342.8259 | 0.2 | 0.3 | 48894.8084 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 342.4387 | 342.4387 | 342.4387 | 342.4387 | 342.4387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15658 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16877.8665 | 0.2 | 0.3 | 26329.4717 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6395.0248 | 6395.0248 | 6395.0248 | 6395.0248 | 6395.0248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15659 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 14693.0792 | 0.2 | 0.3 | 22921.2036 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3520.5817 | 3520.5817 | 3520.5817 | 3520.5817 | 3520.5817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15660 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 22413.0361 | 0.2 | 0.3 | 34964.3364 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7371.318 | 7371.318 | 7371.318 | 7371.318 | 7371.318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15661 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 23303.5141 | 0.2 | 0.3 | 36353.4819 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 936.7818 | 936.7818 | 936.7818 | 936.7818 | 936.7818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15662 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 17873.6105 | 0.2 | 0.3 | 27882.8323 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2690.4539 | 2690.4539 | 2690.4539 | 2690.4539 | 2690.4539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15663 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 911.5248 | 0.2 | 0.3 | 1421.9787 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2511.1635 | 2511.1635 | 2511.1635 | 2511.1635 | 2511.1635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15664 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 30336.1937 | 0.2 | 0.3 | 47324.4622 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3499 | 5200.3499 | 5200.3499 | 5200.3499 | 5200.3499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15665 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 17122.8929 | 0.2 | 0.3 | 26711.713 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1194.0403 | 1194.0403 | 1194.0403 | 1194.0403 | 1194.0403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15666 | CORAL SPRINGS | 20325 | Private | 2036 | 5 | Swales | 66.6667 | 9933.938 | 0.2 | 0.3 | 15496.9433 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6614.6447 | 6614.6447 | 6614.6447 | 6614.6447 | 6614.6447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15667 | CORAL SPRINGS | 20325 | Private | 2036 | 5 | Swales | 66.6667 | 31770.532 | 0.2 | 0.3 | 49562.0299 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2535.8894 | 2535.8894 | 2535.8894 | 2535.8894 | 2535.8894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15668 | CORAL SPRINGS | 20325 | Private | 2036 | 5 | Swales | 66.6667 | 29817.9022 | 0.2 | 0.3 | 46515.9274 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2665.7352 | 2665.7352 | 2665.7352 | 2665.7352 | 2665.7352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15669 | CORAL SPRINGS | 20325 | Private | 2036 | 5 | Swales | 66.6667 | 16825.4977 | 0.2 | 0.3 | 26247.7764 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3357.2901 | 3357.2901 | 3357.2901 | 3357.2901 | 3357.2901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15670 | CORAL SPRINGS | 20325 | Private | 2036 | 5 | Swales | 66.6667 | 16829.2451 | 0.2 | 0.3 | 26253.6223 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5468.6222 | 5468.6222 | 5468.6222 | 5468.6222 | 5468.6222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15671 | CORAL SPRINGS | 20302 | Public | 2033 | 5 | Swales | 66.6667 | 17871.8688 | 0.2 | 0.3 | 27880.1153 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.6927 | 5206.6927 | 5206.6927 | 5206.6927 | 5206.6927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15672 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6275.1215 | 6275.1215 | 6275.1215 | 6275.1215 | 6275.1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15673 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 25747.3414 | 0.2 | 0.3 | 40165.8526 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3485.3759 | 3485.3759 | 3485.3759 | 3485.3759 | 3485.3759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15674 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5258.4523 | 5258.4523 | 5258.4523 | 5258.4523 | 5258.4523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15675 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 30005.5797 | 0.2 | 0.3 | 46808.7044 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6434.4012 | 6434.4012 | 6434.4012 | 6434.4012 | 6434.4012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15676 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 976.8855 | 0.2 | 0.3 | 1523.9413 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1009 | 5200.1009 | 5200.1009 | 5200.1009 | 5200.1009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15677 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 15894.33 | 0.2 | 0.3 | 24795.1548 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4999.9349 | 4999.9349 | 4999.9349 | 4999.9349 | 4999.9349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15678 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 17648.7157 | 0.2 | 0.3 | 27531.9965 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6017.6576 | 6017.6576 | 6017.6576 | 6017.6576 | 6017.6576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15679 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 24770.7259 | 0.2 | 0.3 | 38642.3325 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2187 | 5202.2187 | 5202.2187 | 5202.2187 | 5202.2187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15680 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 20083.8625 | 0.2 | 0.3 | 31330.8254 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 5202.2823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15681 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16836.5316 | 0.2 | 0.3 | 26264.9893 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3082 | 5202.3082 | 5202.3082 | 5202.3082 | 5202.3082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15682 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 17968.9859 | 0.2 | 0.3 | 28031.6181 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 570.6904 | 570.6904 | 570.6904 | 570.6904 | 570.6904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15683 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 12677.1512 | 0.2 | 0.3 | 19776.3559 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4630.8989 | 4630.8989 | 4630.8989 | 4630.8989 | 4630.8989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15684 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 25273.4684 | 0.2 | 0.3 | 39426.6107 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3420.0864 | 3420.0864 | 3420.0864 | 3420.0864 | 3420.0864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15685 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 18403.1468 | 0.2 | 0.3 | 28708.909 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4507.0537 | 4507.0537 | 4507.0537 | 4507.0537 | 4507.0537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15686 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 1091.6 | 0.2 | 0.3 | 1702.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5710.8138 | 5710.8138 | 5710.8138 | 5710.8138 | 5710.8138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15687 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8323.0397 | 8323.0397 | 8323.0397 | 8323.0397 | 8323.0397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15688 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 12461.6737 | 0.2 | 0.3 | 19440.2109 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4610.7436 | 4610.7436 | 4610.7436 | 4610.7436 | 4610.7436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15689 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 4207.1135 | 0.2 | 0.3 | 6563.0971 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5277.1654 | 5277.1654 | 5277.1654 | 5277.1654 | 5277.1654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15690 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 806.7669 | 0.2 | 0.3 | 1258.5564 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2895 | 5200.2895 | 5200.2895 | 5200.2895 | 5200.2895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15691 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 17950.1186 | 0.2 | 0.3 | 28002.185 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 5200.4057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15692 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 16666.8354 | 0.2 | 0.3 | 26000.2632 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4074 | 5200.4074 | 5200.4074 | 5200.4074 | 5200.4074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15693 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 22641.2675 | 0.2 | 0.3 | 35320.3772 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6287.4173 | 6287.4173 | 6287.4173 | 6287.4173 | 6287.4173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15694 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 15612.1018 | 0.2 | 0.3 | 24354.8788 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5934.3934 | 5934.3934 | 5934.3934 | 5934.3934 | 5934.3934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15695 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 17280.5696 | 0.2 | 0.3 | 26957.6886 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8259.1216 | 8259.1216 | 8259.1216 | 8259.1216 | 8259.1216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15696 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 22823.9425 | 0.2 | 0.3 | 35605.3502 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5599.1258 | 5599.1258 | 5599.1258 | 5599.1258 | 5599.1258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15697 | CORAL SPRINGS | 20325 | Private | 2036 | 5 | Swales | 66.6667 | 11714.2373 | 0.2 | 0.3 | 18274.2102 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4261 | 5202.4261 | 5202.4261 | 5202.4261 | 5202.4261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15698 | CORAL SPRINGS | 20325 | Private | 2036 | 5 | Swales | 66.6667 | 21068.9573 | 0.2 | 0.3 | 32867.5733 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15699 | CORAL SPRINGS | 20325 | Private | 2036 | 5 | Swales | 66.6667 | 16882.4529 | 0.2 | 0.3 | 26336.6266 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6841 | 5202.6841 | 5202.6841 | 5202.6841 | 5202.6841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15700 | CORAL SPRINGS | 20325 | Private | 2036 | 5 | Swales | 66.6667 | 16685.8573 | 0.2 | 0.3 | 26029.9373 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5999.3927 | 5999.3927 | 5999.3927 | 5999.3927 | 5999.3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15701 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16669.7854 | 0.2 | 0.3 | 26004.8652 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5267.7871 | 5267.7871 | 5267.7871 | 5267.7871 | 5267.7871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15702 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 27662.3512 | 0.2 | 0.3 | 43153.2679 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15703 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 22226.5886 | 0.2 | 0.3 | 34673.4782 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15704 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4725 | 5201.4725 | 5201.4725 | 5201.4725 | 5201.4725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15705 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 26590.7544 | 0.2 | 0.3 | 41481.5769 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5357.0523 | 5357.0523 | 5357.0523 | 5357.0523 | 5357.0523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15706 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 4675.6833 | 0.2 | 0.3 | 7294.0659 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4480.5127 | 4480.5127 | 4480.5127 | 4480.5127 | 4480.5127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15707 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 18556.5247 | 0.2 | 0.3 | 28948.1785 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5492.8457 | 5492.8457 | 5492.8457 | 5492.8457 | 5492.8457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15708 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16685.5455 | 0.2 | 0.3 | 26029.4509 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9399.9372 | 9399.9372 | 9399.9372 | 9399.9372 | 9399.9372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15709 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 15580.6863 | 0.2 | 0.3 | 24305.8707 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5634.8904 | 5634.8904 | 5634.8904 | 5634.8904 | 5634.8904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15710 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 23817.9908 | 0.2 | 0.3 | 37156.0656 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2271 | 5202.2271 | 5202.2271 | 5202.2271 | 5202.2271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15711 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 17178.1583 | 0.2 | 0.3 | 26797.927 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5947.9908 | 5947.9908 | 5947.9908 | 5947.9908 | 5947.9908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15712 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 16741.9773 | 0.2 | 0.3 | 26117.4846 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5106 | 5202.5106 | 5202.5106 | 5202.5106 | 5202.5106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15713 | COCONUT CREEK | 10606 | Public | 2036 | 5 | Swales | 66.6667 | 15320.9127 | 0.2 | 0.3 | 23900.6239 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8805.5882 | 8805.5882 | 8805.5882 | 8805.5882 | 8805.5882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15714 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 29.1336 | 0.2 | 0.3 | 45.4484 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.8465 | 9777.8465 | 9777.8465 | 9777.8465 | 9777.8465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15715 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 18390.2907 | 0.2 | 0.3 | 28688.8534 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.673 | 5200.673 | 5200.673 | 5200.673 | 5200.673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15716 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16632.29 | 0.2 | 0.3 | 25946.3724 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2378.0597 | 2378.0597 | 2378.0597 | 2378.0597 | 2378.0597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15717 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 34159.2107 | 0.2 | 0.3 | 53288.3687 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5258.0083 | 5258.0083 | 5258.0083 | 5258.0083 | 5258.0083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15718 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 22624.4469 | 0.2 | 0.3 | 35294.1372 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5142.8095 | 5142.8095 | 5142.8095 | 5142.8095 | 5142.8095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15719 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16664.5881 | 0.2 | 0.3 | 25996.7574 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9699 | 5201.9699 | 5201.9699 | 5201.9699 | 5201.9699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15720 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16667.9641 | 0.2 | 0.3 | 26002.024 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15721 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16668.0302 | 0.2 | 0.3 | 26002.1271 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15722 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7371 | 5200.7371 | 5200.7371 | 5200.7371 | 5200.7371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15723 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6645.2011 | 6645.2011 | 6645.2011 | 6645.2011 | 6645.2011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15724 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 23708.6637 | 0.2 | 0.3 | 36985.5154 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0657 | 5200.0657 | 5200.0657 | 5200.0657 | 5200.0657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15725 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 24126.7379 | 0.2 | 0.3 | 37637.7111 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15726 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0976 | 5200.0976 | 5200.0976 | 5200.0976 | 5200.0976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15727 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 19105.5501 | 0.2 | 0.3 | 29804.6581 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6806.51 | 6806.51 | 6806.51 | 6806.51 | 6806.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15728 | CORAL SPRINGS | 20326 | Public | 2036 | 5 | Swales | 66.6667 | 193.1394 | 0.2 | 0.3 | 301.2975 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6241.3839 | 6241.3839 | 6241.3839 | 6241.3839 | 6241.3839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15729 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 27285.6937 | 0.2 | 0.3 | 42565.6821 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4772.4996 | 4772.4996 | 4772.4996 | 4772.4996 | 4772.4996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15730 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 13710.4123 | 0.2 | 0.3 | 21388.2431 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8138 | 5202.8138 | 5202.8138 | 5202.8138 | 5202.8138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15731 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 27220.9259 | 0.2 | 0.3 | 42464.6444 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 771.3944 | 771.3944 | 771.3944 | 771.3944 | 771.3944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15732 | CORAL SPRINGS | 20326 | Private | 2033 | 5 | Swales | 66.6667 | 15138.1795 | 0.2 | 0.3 | 23615.5601 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9812.3778 | 9812.3778 | 9812.3778 | 9812.3778 | 9812.3778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15733 | CORAL SPRINGS | 20326 | Private | 2033 | 5 | Swales | 66.6667 | 19122.4196 | 0.2 | 0.3 | 29830.9746 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2071 | 5202.2071 | 5202.2071 | 5202.2071 | 5202.2071 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15734 | CORAL SPRINGS | 20326 | Private | 2033 | 5 | Swales | 66.6667 | 4039.7893 | 0.2 | 0.3 | 6302.0714 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4293 | 5202.4293 | 5202.4293 | 5202.4293 | 5202.4293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15735 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 16740.896 | 0.2 | 0.3 | 26115.7978 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9781.5692 | 9781.5692 | 9781.5692 | 9781.5692 | 9781.5692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15736 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 16684.5128 | 0.2 | 0.3 | 26027.84 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15737 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 18500.9417 | 0.2 | 0.3 | 28861.469 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8538.1191 | 8538.1191 | 8538.1191 | 8538.1191 | 8538.1191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15738 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16821.8969 | 0.2 | 0.3 | 26242.1592 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3562.5129 | 3562.5129 | 3562.5129 | 3562.5129 | 3562.5129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15739 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 23740.4717 | 0.2 | 0.3 | 37035.1359 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8935.252 | 8935.252 | 8935.252 | 8935.252 | 8935.252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15740 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 14311.9457 | 0.2 | 0.3 | 22326.6353 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8190.1437 | 8190.1437 | 8190.1437 | 8190.1437 | 8190.1437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15741 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 17999.3657 | 0.2 | 0.3 | 28079.0105 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9440.0864 | 9440.0864 | 9440.0864 | 9440.0864 | 9440.0864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15742 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6895 | 0.2 | 0.3 | 26000.0357 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2855.2074 | 2855.2074 | 2855.2074 | 2855.2074 | 2855.2074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15743 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 16666.7981 | 0.2 | 0.3 | 26000.205 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5672.0479 | 5672.0479 | 5672.0479 | 5672.0479 | 5672.0479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15744 | CORAL SPRINGS | 20308 | Public | 2030 | 5 | Swales | 66.6667 | 18222.1425 | 0.2 | 0.3 | 28426.5424 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3103 | 5200.3103 | 5200.3103 | 5200.3103 | 5200.3103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15745 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 27130.1379 | 0.2 | 0.3 | 42323.0151 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15746 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 22928.7423 | 0.2 | 0.3 | 35768.8379 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4784 | 5200.4784 | 5200.4784 | 5200.4784 | 5200.4784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15747 | CORAL SPRINGS | 20308 | Private | 2030 | 5 | Swales | 66.6667 | 24639.4694 | 0.2 | 0.3 | 38437.5723 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4807.6892 | 4807.6892 | 4807.6892 | 4807.6892 | 4807.6892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15748 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 15620.9331 | 0.2 | 0.3 | 24368.6557 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 943.4413 | 943.4413 | 943.4413 | 943.4413 | 943.4413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15749 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 1224.3801 | 0.2 | 0.3 | 1910.0329 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2490.8204 | 2490.8204 | 2490.8204 | 2490.8204 | 2490.8204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15750 | CORAL SPRINGS | 20326 | Public | 2033 | 5 | Swales | 66.6667 | 2956.2372 | 0.2 | 0.3 | 4611.73 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 177.6628 | 177.6628 | 177.6628 | 177.6628 | 177.6628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15751 | CORAL SPRINGS | 20326 | Private | 2033 | 5 | Swales | 66.6667 | 22528.6715 | 0.2 | 0.3 | 35144.7275 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2916 | 5200.2916 | 5200.2916 | 5200.2916 | 5200.2916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15752 | CORAL SPRINGS | 20326 | Private | 2033 | 5 | Swales | 66.6667 | 39668.2227 | 0.2 | 0.3 | 61882.4275 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5217.7682 | 5217.7682 | 5217.7682 | 5217.7682 | 5217.7682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15753 | CORAL SPRINGS | 20326 | Private | 2033 | 5 | Swales | 66.6667 | 25000.9625 | 0.2 | 0.3 | 39001.5016 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5213.2517 | 5213.2517 | 5213.2517 | 5213.2517 | 5213.2517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15754 | CORAL SPRINGS | 20326 | Private | 2033 | 5 | Swales | 66.6667 | 23632.1373 | 0.2 | 0.3 | 36866.1342 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15755 | CORAL SPRINGS | 20326 | Private | 2033 | 5 | Swales | 66.6667 | 17460.169 | 0.2 | 0.3 | 27237.8636 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5216.9018 | 5216.9018 | 5216.9018 | 5216.9018 | 5216.9018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15756 | CORAL SPRINGS | 20326 | Private | 2033 | 5 | Swales | 66.6667 | 25153.6837 | 0.2 | 0.3 | 39239.7465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4606.8391 | 4606.8391 | 4606.8391 | 4606.8391 | 4606.8391 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15757 | CORAL SPRINGS | 20325 | Private | 2036 | 5 | Swales | 66.6667 | 27232.023 | 0.2 | 0.3 | 42481.9559 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4555.6866 | 4555.6866 | 4555.6866 | 4555.6866 | 4555.6866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15758 | CORAL SPRINGS | 20325 | Private | 2036 | 5 | Swales | 66.6667 | 16638.5391 | 0.2 | 0.3 | 25956.121 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5757.4015 | 5757.4015 | 5757.4015 | 5757.4015 | 5757.4015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15759 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 27601.7953 | 0.2 | 0.3 | 43058.8006 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 5200.3204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15760 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15761 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 16666.7714 | 0.2 | 0.3 | 26000.1634 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3876.4898 | 3876.4898 | 3876.4898 | 3876.4898 | 3876.4898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15762 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 16667.0338 | 0.2 | 0.3 | 26000.5727 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9864.4757 | 9864.4757 | 9864.4757 | 9864.4757 | 9864.4757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15763 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 16817.6762 | 0.2 | 0.3 | 26235.5749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8151.5043 | 8151.5043 | 8151.5043 | 8151.5043 | 8151.5043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15764 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 16699.9885 | 0.2 | 0.3 | 26051.982 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4851.4509 | 4851.4509 | 4851.4509 | 4851.4509 | 4851.4509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15765 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 15771.563 | 0.2 | 0.3 | 24603.6383 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3358.4989 | 3358.4989 | 3358.4989 | 3358.4989 | 3358.4989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15766 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 21351.8245 | 0.2 | 0.3 | 33308.8463 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 355.2389 | 355.2389 | 355.2389 | 355.2389 | 355.2389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15767 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 17993.5123 | 0.2 | 0.3 | 28069.8792 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4416 | 5200.4416 | 5200.4416 | 5200.4416 | 5200.4416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15768 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4999 | 5200.4999 | 5200.4999 | 5200.4999 | 5200.4999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15769 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 16666.9161 | 0.2 | 0.3 | 26000.3892 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15770 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 16667.4585 | 0.2 | 0.3 | 26001.2352 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5655 | 5200.5655 | 5200.5655 | 5200.5655 | 5200.5655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15771 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 2045.0137 | 0.2 | 0.3 | 3190.2214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6187.0383 | 6187.0383 | 6187.0383 | 6187.0383 | 6187.0383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15772 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6324 | 0.2 | 0.3 | 25999.9465 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.0666 | 5203.0666 | 5203.0666 | 5203.0666 | 5203.0666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15773 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6029 | 0.2 | 0.3 | 25999.9005 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15774 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6148 | 0.2 | 0.3 | 25999.9191 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15775 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 26127.1139 | 0.2 | 0.3 | 40758.2976 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.188 | 5203.188 | 5203.188 | 5203.188 | 5203.188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15776 | CORAL SPRINGS | 20302 | Private | 2036 | 5 | Swales | 66.6667 | 16667.126 | 0.2 | 0.3 | 26000.7166 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5169 | 5203.5169 | 5203.5169 | 5203.5169 | 5203.5169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15777 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 31336.1725 | 0.2 | 0.3 | 48884.429 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.2867 | 5205.2867 | 5205.2867 | 5205.2867 | 5205.2867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15778 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 26133.9949 | 0.2 | 0.3 | 40769.0321 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5277.6635 | 5277.6635 | 5277.6635 | 5277.6635 | 5277.6635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15779 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4349.2099 | 4349.2099 | 4349.2099 | 4349.2099 | 4349.2099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15780 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4852.0841 | 4852.0841 | 4852.0841 | 4852.0841 | 4852.0841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15781 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 16667.1468 | 0.2 | 0.3 | 26000.749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5494.2866 | 5494.2866 | 5494.2866 | 5494.2866 | 5494.2866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15782 | CORAL SPRINGS | 20302 | Public | 2036 | 5 | Swales | 66.6667 | 25807.8428 | 0.2 | 0.3 | 40260.2348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5761.859 | 5761.859 | 5761.859 | 5761.859 | 5761.859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15783 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 34417.2544 | 0.2 | 0.3 | 53690.9169 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5888.786 | 5888.786 | 5888.786 | 5888.786 | 5888.786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15784 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 9644.4831 | 0.2 | 0.3 | 15045.3937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6222.1715 | 6222.1715 | 6222.1715 | 6222.1715 | 6222.1715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15785 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 17030.9141 | 0.2 | 0.3 | 26568.226 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10341.3764 | 10341.3764 | 10341.3764 | 10341.3764 | 10341.3764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15786 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 9313.5248 | 0.2 | 0.3 | 14529.0987 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2094 | 5201.2094 | 5201.2094 | 5201.2094 | 5201.2094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15787 | CORAL SPRINGS | 20326 | Private | 2033 | 5 | Swales | 66.6667 | 5501.759 | 0.2 | 0.3 | 8582.744 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1993.5866 | 1993.5866 | 1993.5866 | 1993.5866 | 1993.5866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15788 | CORAL SPRINGS | 20326 | Private | 2033 | 5 | Swales | 66.6667 | 14585.6606 | 0.2 | 0.3 | 22753.6305 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5850.9286 | 5850.9286 | 5850.9286 | 5850.9286 | 5850.9286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15789 | CORAL SPRINGS | 20326 | Private | 2033 | 5 | Swales | 66.6667 | 8320.0231 | 0.2 | 0.3 | 12979.2361 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7601 | 5201.7601 | 5201.7601 | 5201.7601 | 5201.7601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15790 | CORAL SPRINGS | 20326 | Private | 2033 | 5 | Swales | 66.6667 | 1567.9002 | 0.2 | 0.3 | 2445.9243 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15791 | CORAL SPRINGS | 20326 | Private | 2033 | 5 | Swales | 66.6667 | 6799.8121 | 0.2 | 0.3 | 10607.7069 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8659 | 5201.8659 | 5201.8659 | 5201.8659 | 5201.8659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15792 | CORAL SPRINGS | 20325 | Private | 2036 | 5 | Swales | 66.6667 | 10980.0933 | 0.2 | 0.3 | 17128.9456 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4731.3419 | 4731.3419 | 4731.3419 | 4731.3419 | 4731.3419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15793 | CORAL SPRINGS | 20325 | Private | 2036 | 5 | Swales | 66.6667 | 6701.7683 | 0.2 | 0.3 | 10454.7586 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9143 | 5200.9143 | 5200.9143 | 5200.9143 | 5200.9143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15794 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 11163.5181 | 0.2 | 0.3 | 17415.0883 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15795 | CORAL SPRINGS | 20311 | Public | 2036 | 5 | Swales | 66.6667 | 11569.6008 | 0.2 | 0.3 | 18048.5772 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8552.8765 | 8552.8765 | 8552.8765 | 8552.8765 | 8552.8765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15796 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 7989.9979 | 0.2 | 0.3 | 12464.3968 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5066.3918 | 5066.3918 | 5066.3918 | 5066.3918 | 5066.3918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15797 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 13712.722 | 0.2 | 0.3 | 21391.8463 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6751 | 5200.6751 | 5200.6751 | 5200.6751 | 5200.6751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15798 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 37068.3235 | 0.2 | 0.3 | 57826.5846 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5269.9514 | 5269.9514 | 5269.9514 | 5269.9514 | 5269.9514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15799 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 3787.1055 | 0.2 | 0.3 | 5907.8845 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5226.7407 | 5226.7407 | 5226.7407 | 5226.7407 | 5226.7407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15800 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 6031.2431 | 0.2 | 0.3 | 9408.7393 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7509.2752 | 7509.2752 | 7509.2752 | 7509.2752 | 7509.2752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15801 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 15790.0265 | 0.2 | 0.3 | 24632.4413 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5311.7207 | 5311.7207 | 5311.7207 | 5311.7207 | 5311.7207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15802 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 15400.7049 | 0.2 | 0.3 | 24025.0996 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.3012 | 5200.3012 | 5200.3012 | 5200.3012 | 5200.3012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15803 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 16666.9557 | 0.2 | 0.3 | 26000.4508 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7681.1381 | 7681.1381 | 7681.1381 | 7681.1381 | 7681.1381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15804 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 16668.8866 | 0.2 | 0.3 | 26003.4631 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1397.8912 | 1397.8912 | 1397.8912 | 1397.8912 | 1397.8912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15805 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 4621.1343 | 0.2 | 0.3 | 7208.9695 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7900.8102 | 7900.8102 | 7900.8102 | 7900.8102 | 7900.8102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15806 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 8122.6163 | 0.2 | 0.3 | 12671.2814 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7409.0306 | 7409.0306 | 7409.0306 | 7409.0306 | 7409.0306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15807 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 23532.2326 | 0.2 | 0.3 | 36710.2829 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5445.7021 | 5445.7021 | 5445.7021 | 5445.7021 | 5445.7021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15808 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 23060.0427 | 0.2 | 0.3 | 35973.6667 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1426 | 5201.1426 | 5201.1426 | 5201.1426 | 5201.1426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15809 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 6744.5028 | 0.2 | 0.3 | 10521.4244 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1159 | 5201.1159 | 5201.1159 | 5201.1159 | 5201.1159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15810 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 6.6195 | 0.2 | 0.3 | 10.3264 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6033 | 5200.6033 | 5200.6033 | 5200.6033 | 5200.6033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15811 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 24082.6377 | 0.2 | 0.3 | 37568.9149 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8459 | 5200.8459 | 5200.8459 | 5200.8459 | 5200.8459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15812 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 13180.6237 | 0.2 | 0.3 | 20561.773 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9899 | 5200.9899 | 5200.9899 | 5200.9899 | 5200.9899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15813 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 20429.7489 | 0.2 | 0.3 | 31870.4082 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8668.4394 | 8668.4394 | 8668.4394 | 8668.4394 | 8668.4394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15814 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 23948.0177 | 0.2 | 0.3 | 37358.9076 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2696.8877 | 2696.8877 | 2696.8877 | 2696.8877 | 2696.8877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15815 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 33995.2552 | 0.2 | 0.3 | 53032.5981 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7709.2725 | 7709.2725 | 7709.2725 | 7709.2725 | 7709.2725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15816 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 80.1705 | 0.2 | 0.3 | 125.0659 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3224 | 5202.3224 | 5202.3224 | 5202.3224 | 5202.3224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15817 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 12180.0399 | 0.2 | 0.3 | 19000.8623 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1982.9821 | 1982.9821 | 1982.9821 | 1982.9821 | 1982.9821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15818 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 21395.1037 | 0.2 | 0.3 | 33376.3617 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5879.2122 | 5879.2122 | 5879.2122 | 5879.2122 | 5879.2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15819 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 24085.8723 | 0.2 | 0.3 | 37573.9607 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15820 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 8278.2311 | 0.2 | 0.3 | 12914.0406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9323 | 5201.9323 | 5201.9323 | 5201.9323 | 5201.9323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15821 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 31360.798 | 0.2 | 0.3 | 48922.8449 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15822 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 25466.4343 | 0.2 | 0.3 | 39727.6375 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4731.9876 | 4731.9876 | 4731.9876 | 4731.9876 | 4731.9876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15823 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 23375.3043 | 0.2 | 0.3 | 36465.4747 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8695.0855 | 8695.0855 | 8695.0855 | 8695.0855 | 8695.0855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15824 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6165 | 0.2 | 0.3 | 25999.9217 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8688.3872 | 8688.3872 | 8688.3872 | 8688.3872 | 8688.3872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15825 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16666.6606 | 0.2 | 0.3 | 25999.9905 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.1587 | 5200.1587 | 5200.1587 | 5200.1587 | 5200.1587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15826 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16667.6041 | 0.2 | 0.3 | 26001.4624 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5038.0594 | 5038.0594 | 5038.0594 | 5038.0594 | 5038.0594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15827 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7580.2788 | 7580.2788 | 7580.2788 | 7580.2788 | 7580.2788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15828 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16667.6103 | 0.2 | 0.3 | 26001.472 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5248.0202 | 5248.0202 | 5248.0202 | 5248.0202 | 5248.0202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15829 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 18054.3488 | 0.2 | 0.3 | 28164.7841 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6235.2107 | 6235.2107 | 6235.2107 | 6235.2107 | 6235.2107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15830 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 5521.6483 | 0.2 | 0.3 | 8613.7713 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5118 | 5200.5118 | 5200.5118 | 5200.5118 | 5200.5118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15831 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 26287.4969 | 0.2 | 0.3 | 41008.4952 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.53 | 5200.53 | 5200.53 | 5200.53 | 5200.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15832 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 23836.2217 | 0.2 | 0.3 | 37184.5059 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3082.1381 | 3082.1381 | 3082.1381 | 3082.1381 | 3082.1381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15833 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 23777.1055 | 0.2 | 0.3 | 37092.2846 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.5223 | 5204.5223 | 5204.5223 | 5204.5223 | 5204.5223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15834 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 23644.9121 | 0.2 | 0.3 | 36886.0629 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8150.1731 | 8150.1731 | 8150.1731 | 8150.1731 | 8150.1731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15835 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 23607.623 | 0.2 | 0.3 | 36827.8919 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 827.7683 | 827.7683 | 827.7683 | 827.7683 | 827.7683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15836 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 25920.9213 | 0.2 | 0.3 | 40436.6373 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15837 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15838 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 16681.5116 | 0.2 | 0.3 | 26023.1581 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15839 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 11942.4929 | 0.2 | 0.3 | 18630.2889 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 5201.344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15840 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 20222.0163 | 0.2 | 0.3 | 31546.3455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 5201.0881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15841 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 16667.9385 | 0.2 | 0.3 | 26001.984 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 5200.491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15842 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 29522.8833 | 0.2 | 0.3 | 46055.698 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 5200.7469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15843 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 3951.3483 | 0.2 | 0.3 | 6164.1034 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 5201.0028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15844 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 17516.5087 | 0.2 | 0.3 | 27325.7535 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7820.7722 | 7820.7722 | 7820.7722 | 7820.7722 | 7820.7722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15845 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 6874.9546 | 0.2 | 0.3 | 10724.9292 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10037.8302 | 10037.8302 | 10037.8302 | 10037.8302 | 10037.8302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15846 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 18048.3471 | 0.2 | 0.3 | 28155.4214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8121.8515 | 8121.8515 | 8121.8515 | 8121.8515 | 8121.8515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15847 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 11857.6859 | 0.2 | 0.3 | 18497.9901 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5888 | 5200.5888 | 5200.5888 | 5200.5888 | 5200.5888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15848 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 28830.3133 | 0.2 | 0.3 | 44975.2888 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9602 | 5201.9602 | 5201.9602 | 5201.9602 | 5201.9602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15849 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 23093.9999 | 0.2 | 0.3 | 36026.6398 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 5201.2587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15850 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 33362.2335 | 0.2 | 0.3 | 52045.0843 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6125.7393 | 6125.7393 | 6125.7393 | 6125.7393 | 6125.7393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15851 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 46002.1979 | 0.2 | 0.3 | 71763.4288 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4618.3853 | 4618.3853 | 4618.3853 | 4618.3853 | 4618.3853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15852 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 45701.1405 | 0.2 | 0.3 | 71293.7792 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9372 | 5200.9372 | 5200.9372 | 5200.9372 | 5200.9372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15853 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 39317.6217 | 0.2 | 0.3 | 61335.4899 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1772.3908 | 1772.3908 | 1772.3908 | 1772.3908 | 1772.3908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15854 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 36939.1986 | 0.2 | 0.3 | 57625.1498 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5751.0994 | 5751.0994 | 5751.0994 | 5751.0994 | 5751.0994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15855 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 17298.2291 | 0.2 | 0.3 | 26985.2374 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8886.5938 | 8886.5938 | 8886.5938 | 8886.5938 | 8886.5938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15856 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 13407.5091 | 0.2 | 0.3 | 20915.7142 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7458 | 5203.7458 | 5203.7458 | 5203.7458 | 5203.7458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15857 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 19618.8598 | 0.2 | 0.3 | 30605.4213 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5604.9897 | 5604.9897 | 5604.9897 | 5604.9897 | 5604.9897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15858 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 18417.3253 | 0.2 | 0.3 | 28731.0275 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6827 | 5200.6827 | 5200.6827 | 5200.6827 | 5200.6827 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15859 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 41090.4861 | 0.2 | 0.3 | 64101.1584 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.3814 | 5201.3814 | 5201.3814 | 5201.3814 | 5201.3814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15860 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 33619.1092 | 0.2 | 0.3 | 52445.8104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.2869 | 5201.2869 | 5201.2869 | 5201.2869 | 5201.2869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15861 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 17168.3684 | 0.2 | 0.3 | 26782.6547 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.363 | 5201.363 | 5201.363 | 5201.363 | 5201.363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15862 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 24808.6222 | 0.2 | 0.3 | 38701.4506 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.0498 | 5201.0498 | 5201.0498 | 5201.0498 | 5201.0498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15863 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 3390.0636 | 0.2 | 0.3 | 5288.4992 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8044.2101 | 8044.2101 | 8044.2101 | 8044.2101 | 8044.2101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15864 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 7739.4112 | 0.2 | 0.3 | 12073.4815 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4321.0859 | 4321.0859 | 4321.0859 | 4321.0859 | 4321.0859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15865 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 9319.7908 | 0.2 | 0.3 | 14538.8736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9166 | 5200.9166 | 5200.9166 | 5200.9166 | 5200.9166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15866 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 278.7682 | 0.2 | 0.3 | 434.8784 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5211.1842 | 5211.1842 | 5211.1842 | 5211.1842 | 5211.1842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15867 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 4292.314 | 0.2 | 0.3 | 6696.0098 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3355.809 | 3355.809 | 3355.809 | 3355.809 | 3355.809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15868 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 2479.9736 | 0.2 | 0.3 | 3868.7588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7595.2871 | 7595.2871 | 7595.2871 | 7595.2871 | 7595.2871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15869 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 23311.0341 | 0.2 | 0.3 | 36365.2131 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6130.2599 | 6130.2599 | 6130.2599 | 6130.2599 | 6130.2599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15870 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 17470.3933 | 0.2 | 0.3 | 27253.8136 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9839.5831 | 9839.5831 | 9839.5831 | 9839.5831 | 9839.5831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15871 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 16973.6428 | 0.2 | 0.3 | 26478.8828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5067.9229 | 5067.9229 | 5067.9229 | 5067.9229 | 5067.9229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15872 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 20977.8251 | 0.2 | 0.3 | 32725.4071 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1456 | 5201.1456 | 5201.1456 | 5201.1456 | 5201.1456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15873 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 18958.3522 | 0.2 | 0.3 | 29575.0294 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8923.7264 | 8923.7264 | 8923.7264 | 8923.7264 | 8923.7264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15874 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 15836.1202 | 0.2 | 0.3 | 24704.3475 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.6708 | 9777.6708 | 9777.6708 | 9777.6708 | 9777.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15875 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 19905.3971 | 0.2 | 0.3 | 31052.4194 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9025.1035 | 9025.1035 | 9025.1035 | 9025.1035 | 9025.1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15876 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16669.0051 | 0.2 | 0.3 | 26003.6479 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6718.0102 | 6718.0102 | 6718.0102 | 6718.0102 | 6718.0102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15877 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 7583.0753 | 0.2 | 0.3 | 11829.5974 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8536.3797 | 8536.3797 | 8536.3797 | 8536.3797 | 8536.3797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15878 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 9067.8603 | 0.2 | 0.3 | 14145.862 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9807.1459 | 9807.1459 | 9807.1459 | 9807.1459 | 9807.1459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15879 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 8133.1457 | 0.2 | 0.3 | 12687.7073 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8197.9623 | 8197.9623 | 8197.9623 | 8197.9623 | 8197.9623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15880 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 25352.2085 | 0.2 | 0.3 | 39549.4452 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5082.7474 | 5082.7474 | 5082.7474 | 5082.7474 | 5082.7474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15881 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5083.4708 | 5083.4708 | 5083.4708 | 5083.4708 | 5083.4708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15882 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 17610.7198 | 0.2 | 0.3 | 27472.7229 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5681.596 | 5681.596 | 5681.596 | 5681.596 | 5681.596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15883 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16048.8371 | 0.2 | 0.3 | 25036.1858 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6569.8223 | 6569.8223 | 6569.8223 | 6569.8223 | 6569.8223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15884 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16396.2401 | 0.2 | 0.3 | 25578.1345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7654.32 | 7654.32 | 7654.32 | 7654.32 | 7654.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15885 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16709.7059 | 0.2 | 0.3 | 26067.1412 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5314.3412 | 5314.3412 | 5314.3412 | 5314.3412 | 5314.3412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15886 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 24404.7691 | 0.2 | 0.3 | 38071.4398 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6308.5451 | 6308.5451 | 6308.5451 | 6308.5451 | 6308.5451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15887 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 24416.6645 | 0.2 | 0.3 | 38089.9966 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3266.7225 | 3266.7225 | 3266.7225 | 3266.7225 | 3266.7225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15888 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1129.3057 | 1129.3057 | 1129.3057 | 1129.3057 | 1129.3057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15889 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 584.2799 | 0.2 | 0.3 | 911.4767 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5360.1281 | 5360.1281 | 5360.1281 | 5360.1281 | 5360.1281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15890 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 16084.2302 | 0.2 | 0.3 | 25091.3991 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6273.9893 | 6273.9893 | 6273.9893 | 6273.9893 | 6273.9893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15891 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.1231 | 5201.1231 | 5201.1231 | 5201.1231 | 5201.1231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15892 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5163.802 | 5163.802 | 5163.802 | 5163.802 | 5163.802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15893 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2355.0599 | 2355.0599 | 2355.0599 | 2355.0599 | 2355.0599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15894 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 16667.967 | 0.2 | 0.3 | 26002.0285 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.8566 | 5200.8566 | 5200.8566 | 5200.8566 | 5200.8566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15895 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 16670.4276 | 0.2 | 0.3 | 26005.8671 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15896 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 16668.3702 | 0.2 | 0.3 | 26002.6575 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9130.2194 | 9130.2194 | 9130.2194 | 9130.2194 | 9130.2194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15897 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 22499.8548 | 0.2 | 0.3 | 35099.7735 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4406.4203 | 4406.4203 | 4406.4203 | 4406.4203 | 4406.4203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15898 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 25184.3509 | 0.2 | 0.3 | 39287.5874 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6472.8823 | 6472.8823 | 6472.8823 | 6472.8823 | 6472.8823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15899 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 8930.3014 | 0.2 | 0.3 | 13931.2702 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9777.914 | 9777.914 | 9777.914 | 9777.914 | 9777.914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15900 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 14719.7018 | 0.2 | 0.3 | 22962.7348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6832.3912 | 6832.3912 | 6832.3912 | 6832.3912 | 6832.3912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15901 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 14398.4963 | 0.2 | 0.3 | 22461.6543 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6994.0004 | 6994.0004 | 6994.0004 | 6994.0004 | 6994.0004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15902 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 20899.8777 | 0.2 | 0.3 | 32603.8092 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7152.1867 | 7152.1867 | 7152.1867 | 7152.1867 | 7152.1867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15903 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 23200.8401 | 0.2 | 0.3 | 36193.3105 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7386.7944 | 7386.7944 | 7386.7944 | 7386.7944 | 7386.7944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15904 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 19667.8982 | 0.2 | 0.3 | 30681.9212 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3883.2727 | 3883.2727 | 3883.2727 | 3883.2727 | 3883.2727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15905 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 14406.1693 | 0.2 | 0.3 | 22473.6242 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5083.56 | 5083.56 | 5083.56 | 5083.56 | 5083.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15906 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 28738.5347 | 0.2 | 0.3 | 44832.1142 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6413.1547 | 6413.1547 | 6413.1547 | 6413.1547 | 6413.1547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15907 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 31821.9388 | 0.2 | 0.3 | 49642.2245 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8622.8598 | 8622.8598 | 8622.8598 | 8622.8598 | 8622.8598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15908 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 21022.771 | 0.2 | 0.3 | 32795.5228 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6209.307 | 6209.307 | 6209.307 | 6209.307 | 6209.307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15909 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 23833.6232 | 0.2 | 0.3 | 37180.4522 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8849.7651 | 8849.7651 | 8849.7651 | 8849.7651 | 8849.7651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15910 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 16720.3284 | 0.2 | 0.3 | 26083.7123 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8986.7638 | 8986.7638 | 8986.7638 | 8986.7638 | 8986.7638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15911 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 31337.4115 | 0.2 | 0.3 | 48886.362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1871 | 5202.1871 | 5202.1871 | 5202.1871 | 5202.1871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15912 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 33210.7532 | 0.2 | 0.3 | 51808.775 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 5203.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15913 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 27193.5603 | 0.2 | 0.3 | 42421.954 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2975 | 5202.2975 | 5202.2975 | 5202.2975 | 5202.2975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15914 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 28264.0835 | 0.2 | 0.3 | 44091.9702 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15915 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 26110.5575 | 0.2 | 0.3 | 40732.4696 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.999 | 5202.999 | 5202.999 | 5202.999 | 5202.999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15916 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 22454.7365 | 0.2 | 0.3 | 35029.3889 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1063 | 5203.1063 | 5203.1063 | 5203.1063 | 5203.1063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15917 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 28982.6075 | 0.2 | 0.3 | 45212.8678 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6972.1403 | 6972.1403 | 6972.1403 | 6972.1403 | 6972.1403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15918 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 25718.8473 | 0.2 | 0.3 | 40121.4018 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6741.3278 | 6741.3278 | 6741.3278 | 6741.3278 | 6741.3278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15919 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 31619.5888 | 0.2 | 0.3 | 49326.5585 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6753.0242 | 6753.0242 | 6753.0242 | 6753.0242 | 6753.0242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15920 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 31140.323 | 0.2 | 0.3 | 48578.9039 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.1199 | 5205.1199 | 5205.1199 | 5205.1199 | 5205.1199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15921 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 9077.9566 | 0.2 | 0.3 | 14161.6123 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4586.5808 | 4586.5808 | 4586.5808 | 4586.5808 | 4586.5808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15922 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 34000.2951 | 0.2 | 0.3 | 53040.4603 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5309 | 5200.5309 | 5200.5309 | 5200.5309 | 5200.5309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15923 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 13101.2202 | 0.2 | 0.3 | 20437.9035 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5123.4549 | 5123.4549 | 5123.4549 | 5123.4549 | 5123.4549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15924 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 22764.2866 | 0.2 | 0.3 | 35512.2871 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7058.3618 | 7058.3618 | 7058.3618 | 7058.3618 | 7058.3618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15925 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 22228.803 | 0.2 | 0.3 | 34676.9327 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8161.3596 | 8161.3596 | 8161.3596 | 8161.3596 | 8161.3596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15926 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 21226.1267 | 0.2 | 0.3 | 33112.7577 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15927 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 21004.6445 | 0.2 | 0.3 | 32767.2455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15928 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 54638.3779 | 0.2 | 0.3 | 85235.8695 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15929 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 43463.0946 | 0.2 | 0.3 | 67802.4276 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8589.5507 | 8589.5507 | 8589.5507 | 8589.5507 | 8589.5507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15930 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 31488.7391 | 0.2 | 0.3 | 49122.433 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.2432 | 5200.2432 | 5200.2432 | 5200.2432 | 5200.2432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15931 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 2783.3679 | 0.2 | 0.3 | 4342.0539 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6652.4868 | 6652.4868 | 6652.4868 | 6652.4868 | 6652.4868 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15932 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 19369.1823 | 0.2 | 0.3 | 30215.9243 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.018 | 5202.018 | 5202.018 | 5202.018 | 5202.018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15933 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 33173.6539 | 0.2 | 0.3 | 51750.9001 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2161.6028 | 2161.6028 | 2161.6028 | 2161.6028 | 2161.6028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15934 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 28827.1823 | 0.2 | 0.3 | 44970.4044 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 5200.5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15935 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 16668.648 | 0.2 | 0.3 | 26003.0909 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3041.9389 | 3041.9389 | 3041.9389 | 3041.9389 | 3041.9389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15936 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16668.3383 | 0.2 | 0.3 | 26002.6078 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15937 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15938 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 1936.4771 | 0.2 | 0.3 | 3020.9042 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15939 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 14732.3279 | 0.2 | 0.3 | 22982.4315 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15940 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 23827.826 | 0.2 | 0.3 | 37171.4086 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 5200.0645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15941 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16697.8096 | 0.2 | 0.3 | 26048.583 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5197.2496 | 5197.2496 | 5197.2496 | 5197.2496 | 5197.2496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15942 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 22696.4085 | 0.2 | 0.3 | 35406.3973 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5194.5199 | 5194.5199 | 5194.5199 | 5194.5199 | 5194.5199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15943 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 678.5245 | 0.2 | 0.3 | 1058.4982 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5191.7903 | 5191.7903 | 5191.7903 | 5191.7903 | 5191.7903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15944 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 18039.5943 | 0.2 | 0.3 | 28141.7672 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8560.9536 | 8560.9536 | 8560.9536 | 8560.9536 | 8560.9536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15945 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2153 | 0.2 | 0.3 | 26002.4159 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2645 | 5203.2645 | 5203.2645 | 5203.2645 | 5203.2645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15946 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16613.8334 | 0.2 | 0.3 | 25917.5801 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15947 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 23678.993 | 0.2 | 0.3 | 36939.2291 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.611 | 5201.611 | 5201.611 | 5201.611 | 5201.611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15948 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 9824.4163 | 0.2 | 0.3 | 15326.0895 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 5201.7705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15949 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 18731.7627 | 0.2 | 0.3 | 29221.5499 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15950 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 14069.7363 | 0.2 | 0.3 | 21948.7886 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15951 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 15128.0249 | 0.2 | 0.3 | 23599.7189 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7309 | 5201.7309 | 5201.7309 | 5201.7309 | 5201.7309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15952 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 19787.8055 | 0.2 | 0.3 | 30868.9766 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8720.2502 | 8720.2502 | 8720.2502 | 8720.2502 | 8720.2502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15953 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 18025.7238 | 0.2 | 0.3 | 28120.1291 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2993.0608 | 2993.0608 | 2993.0608 | 2993.0608 | 2993.0608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15954 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 22970.2757 | 0.2 | 0.3 | 35833.6301 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.4859 | 5200.4859 | 5200.4859 | 5200.4859 | 5200.4859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15955 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 17991.9725 | 0.2 | 0.3 | 28067.477 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9776.8883 | 9776.8883 | 9776.8883 | 9776.8883 | 9776.8883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15956 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 34702.9164 | 0.2 | 0.3 | 54136.5496 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.274 | 5201.274 | 5201.274 | 5201.274 | 5201.274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15957 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 16667.0103 | 0.2 | 0.3 | 26000.536 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.4158 | 5201.4158 | 5201.4158 | 5201.4158 | 5201.4158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15958 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 20152.7607 | 0.2 | 0.3 | 31438.3066 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6285.7316 | 6285.7316 | 6285.7316 | 6285.7316 | 6285.7316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15959 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 26013.8349 | 0.2 | 0.3 | 40581.5825 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5774 | 5200.5774 | 5200.5774 | 5200.5774 | 5200.5774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15960 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 6051.3544 | 0.2 | 0.3 | 9440.1129 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6205.5493 | 6205.5493 | 6205.5493 | 6205.5493 | 6205.5493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15961 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 20887.5994 | 0.2 | 0.3 | 32584.6551 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5136 | 5203.5136 | 5203.5136 | 5203.5136 | 5203.5136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15962 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 11851.9221 | 0.2 | 0.3 | 18488.9985 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15963 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 23297.273 | 0.2 | 0.3 | 36343.7459 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15964 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 14978.3281 | 0.2 | 0.3 | 23366.1919 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7519 | 5203.7519 | 5203.7519 | 5203.7519 | 5203.7519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15965 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 32352.9247 | 0.2 | 0.3 | 50470.5625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7761 | 5202.7761 | 5202.7761 | 5202.7761 | 5202.7761 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15966 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 15442.821 | 0.2 | 0.3 | 24090.8008 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15967 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 12050.4886 | 0.2 | 0.3 | 18798.7622 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15968 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 16060.6219 | 0.2 | 0.3 | 25054.5701 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9667 | 5202.9667 | 5202.9667 | 5202.9667 | 5202.9667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15969 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 26195.7215 | 0.2 | 0.3 | 40865.3255 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7078.7261 | 7078.7261 | 7078.7261 | 7078.7261 | 7078.7261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15970 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 23338.6647 | 0.2 | 0.3 | 36408.3169 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8255 | 5202.8255 | 5202.8255 | 5202.8255 | 5202.8255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15971 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 19552.1196 | 0.2 | 0.3 | 30501.3066 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15972 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 20647.0614 | 0.2 | 0.3 | 32209.4158 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9782.734 | 9782.734 | 9782.734 | 9782.734 | 9782.734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15973 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 25426.05 | 0.2 | 0.3 | 39664.638 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7990.9811 | 7990.9811 | 7990.9811 | 7990.9811 | 7990.9811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15974 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 29390.5638 | 0.2 | 0.3 | 45849.2795 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6439.5437 | 6439.5437 | 6439.5437 | 6439.5437 | 6439.5437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15975 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 23246.3633 | 0.2 | 0.3 | 36264.3267 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6743.7691 | 6743.7691 | 6743.7691 | 6743.7691 | 6743.7691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15976 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 26021.9091 | 0.2 | 0.3 | 40594.1781 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4734.0794 | 4734.0794 | 4734.0794 | 4734.0794 | 4734.0794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15977 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 33319.2692 | 0.2 | 0.3 | 51978.06 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6558.4546 | 6558.4546 | 6558.4546 | 6558.4546 | 6558.4546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15978 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 29676.807 | 0.2 | 0.3 | 46295.8189 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6605.915 | 6605.915 | 6605.915 | 6605.915 | 6605.915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15979 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 11927.4457 | 0.2 | 0.3 | 18606.8153 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7634.9223 | 7634.9223 | 7634.9223 | 7634.9223 | 7634.9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15980 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 6873.7541 | 0.2 | 0.3 | 10723.0563 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5005.1314 | 5005.1314 | 5005.1314 | 5005.1314 | 5005.1314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15981 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 19308.1563 | 0.2 | 0.3 | 30120.7239 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8383.0107 | 8383.0107 | 8383.0107 | 8383.0107 | 8383.0107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15982 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 17448.5354 | 0.2 | 0.3 | 27219.7152 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5157.5748 | 5157.5748 | 5157.5748 | 5157.5748 | 5157.5748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15983 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 35761.0264 | 0.2 | 0.3 | 55787.2012 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6071.4751 | 6071.4751 | 6071.4751 | 6071.4751 | 6071.4751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15984 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 27824.8021 | 0.2 | 0.3 | 43406.6912 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.1293 | 5204.1293 | 5204.1293 | 5204.1293 | 5204.1293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15985 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 27808.4942 | 0.2 | 0.3 | 43381.251 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15986 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 20013.5566 | 0.2 | 0.3 | 31221.1483 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15987 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 45269.8672 | 0.2 | 0.3 | 70620.9928 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.3975 | 5204.3975 | 5204.3975 | 5204.3975 | 5204.3975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15988 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 21963.3911 | 0.2 | 0.3 | 34262.8901 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1483 | 5202.1483 | 5202.1483 | 5202.1483 | 5202.1483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15989 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 47165.1739 | 0.2 | 0.3 | 73577.6713 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15990 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 29049.8102 | 0.2 | 0.3 | 45317.7039 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15991 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 33137.6567 | 0.2 | 0.3 | 51694.7445 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1438 | 5202.1438 | 5202.1438 | 5202.1438 | 5202.1438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15992 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 21974.2532 | 0.2 | 0.3 | 34279.835 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7213.087 | 7213.087 | 7213.087 | 7213.087 | 7213.087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15993 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 16821.6893 | 0.2 | 0.3 | 26241.8354 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.6433 | 5203.6433 | 5203.6433 | 5203.6433 | 5203.6433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15994 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 16916.2331 | 0.2 | 0.3 | 26389.3237 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 5203.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15995 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 10981.2373 | 0.2 | 0.3 | 17130.7301 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8807.8291 | 8807.8291 | 8807.8291 | 8807.8291 | 8807.8291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15996 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16650.7997 | 0.2 | 0.3 | 25975.2475 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7088.6349 | 7088.6349 | 7088.6349 | 7088.6349 | 7088.6349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15997 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16711.918 | 0.2 | 0.3 | 26070.5921 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0078 | 5202.0078 | 5202.0078 | 5202.0078 | 5202.0078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15998 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16672.5094 | 0.2 | 0.3 | 26009.1147 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15999 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16938.8283 | 0.2 | 0.3 | 26424.5722 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16000 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 1.4858 | 0.2 | 0.3 | 2.3178 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9856 | 5201.9856 | 5201.9856 | 5201.9856 | 5201.9856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16001 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16668.2404 | 0.2 | 0.3 | 26002.455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3022.864 | 3022.864 | 3022.864 | 3022.864 | 3022.864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16002 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 25524.7107 | 0.2 | 0.3 | 39818.5487 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6212.6471 | 6212.6471 | 6212.6471 | 6212.6471 | 6212.6471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16003 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 9160.8324 | 0.2 | 0.3 | 14290.8985 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9561.6334 | 9561.6334 | 9561.6334 | 9561.6334 | 9561.6334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16004 | CORAL SPRINGS | 20323 | Private | 2033 | 5 | Swales | 66.6667 | 1195.2989 | 0.2 | 0.3 | 1864.6662 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9453.3568 | 9453.3568 | 9453.3568 | 9453.3568 | 9453.3568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16005 | CORAL SPRINGS | 20323 | Private | 2033 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5973.4673 | 5973.4673 | 5973.4673 | 5973.4673 | 5973.4673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16006 | CORAL SPRINGS | 20323 | Private | 2033 | 5 | Swales | 66.6667 | 13289.7463 | 0.2 | 0.3 | 20732.0043 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.1173 | 5204.1173 | 5204.1173 | 5204.1173 | 5204.1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16007 | CORAL SPRINGS | 20323 | Private | 2033 | 5 | Swales | 66.6667 | 8398.5514 | 0.2 | 0.3 | 13101.7402 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16008 | CORAL SPRINGS | 20323 | Private | 2033 | 5 | Swales | 66.6667 | 14506.0142 | 0.2 | 0.3 | 22629.3822 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 5204.0737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16009 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 25208.0946 | 0.2 | 0.3 | 39324.6276 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.1438 | 5204.1438 | 5204.1438 | 5204.1438 | 5204.1438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16010 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 17163.7945 | 0.2 | 0.3 | 26775.5195 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7281 | 5202.7281 | 5202.7281 | 5202.7281 | 5202.7281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16011 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 10283.5188 | 0.2 | 0.3 | 16042.2893 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16012 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 7746.2499 | 0.2 | 0.3 | 12084.1499 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16013 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 18170.2953 | 0.2 | 0.3 | 28345.6606 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.0227 | 5203.0227 | 5203.0227 | 5203.0227 | 5203.0227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16014 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 33395.2885 | 0.2 | 0.3 | 52096.6501 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9781.7742 | 9781.7742 | 9781.7742 | 9781.7742 | 9781.7742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16015 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 8725.0953 | 0.2 | 0.3 | 13611.1487 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2501 | 5203.2501 | 5203.2501 | 5203.2501 | 5203.2501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16016 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 17525.1782 | 0.2 | 0.3 | 27339.278 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 5203.306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16017 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 1640.4286 | 0.2 | 0.3 | 2559.0686 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4409.3206 | 4409.3206 | 4409.3206 | 4409.3206 | 4409.3206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16018 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 18773.8666 | 0.2 | 0.3 | 29287.2319 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16019 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 373.8057 | 0.2 | 0.3 | 583.1368 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 5203.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16020 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 13080.4454 | 0.2 | 0.3 | 20405.4948 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.119 | 5203.119 | 5203.119 | 5203.119 | 5203.119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16021 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 25684.6688 | 0.2 | 0.3 | 40068.0833 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9090.6342 | 9090.6342 | 9090.6342 | 9090.6342 | 9090.6342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16022 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 2004.8228 | 0.2 | 0.3 | 3127.5236 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3494.9061 | 3494.9061 | 3494.9061 | 3494.9061 | 3494.9061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16023 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 17004.4971 | 0.2 | 0.3 | 26527.0155 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16024 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 20364.4918 | 0.2 | 0.3 | 31768.6072 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16025 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 10212.3081 | 0.2 | 0.3 | 15931.2007 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9136 | 5202.9136 | 5202.9136 | 5202.9136 | 5202.9136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16026 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 4160.5644 | 0.2 | 0.3 | 6490.4805 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7725.5017 | 7725.5017 | 7725.5017 | 7725.5017 | 7725.5017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16027 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 9123.3235 | 0.2 | 0.3 | 14232.3847 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5999.3955 | 5999.3955 | 5999.3955 | 5999.3955 | 5999.3955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16028 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 24458.0435 | 0.2 | 0.3 | 38154.5478 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7691.7642 | 7691.7642 | 7691.7642 | 7691.7642 | 7691.7642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16029 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 16679.1209 | 0.2 | 0.3 | 26019.4287 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 230.5484 | 230.5484 | 230.5484 | 230.5484 | 230.5484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16030 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 16039.5284 | 0.2 | 0.3 | 25021.6643 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.1524 | 5204.1524 | 5204.1524 | 5204.1524 | 5204.1524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16031 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 5773.6377 | 0.2 | 0.3 | 9006.8749 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1851.32 | 1851.32 | 1851.32 | 1851.32 | 1851.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16032 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 24744.3449 | 0.2 | 0.3 | 38601.1781 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8115.082 | 8115.082 | 8115.082 | 8115.082 | 8115.082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16033 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2494.6383 | 2494.6383 | 2494.6383 | 2494.6383 | 2494.6383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16034 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 14604.9603 | 0.2 | 0.3 | 22783.7381 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5858.7303 | 5858.7303 | 5858.7303 | 5858.7303 | 5858.7303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16035 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16318.1467 | 0.2 | 0.3 | 25456.3088 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0122 | 5204.0122 | 5204.0122 | 5204.0122 | 5204.0122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16036 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 11376.8264 | 0.2 | 0.3 | 17747.8492 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 5204.3296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16037 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 14543.6317 | 0.2 | 0.3 | 22688.0654 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 5204.4149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16038 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 2123.7885 | 0.2 | 0.3 | 3313.1101 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.5719 | 5204.5719 | 5204.5719 | 5204.5719 | 5204.5719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16039 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16668.3637 | 0.2 | 0.3 | 26002.6474 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3775 | 5202.3775 | 5202.3775 | 5202.3775 | 5202.3775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16040 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16670.8124 | 0.2 | 0.3 | 26006.4673 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 5202.3676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16041 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16630.7217 | 0.2 | 0.3 | 25943.9259 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.2296 | 5202.2296 | 5202.2296 | 5202.2296 | 5202.2296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16042 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 16669.4756 | 0.2 | 0.3 | 26004.3819 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.3431 | 5202.3431 | 5202.3431 | 5202.3431 | 5202.3431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16043 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 31729.4425 | 0.2 | 0.3 | 49497.9304 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4063.1191 | 4063.1191 | 4063.1191 | 4063.1191 | 4063.1191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16044 | CORAL SPRINGS | 20323 | Private | 2033 | 5 | Swales | 66.6667 | 26764.9573 | 0.2 | 0.3 | 41753.3333 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6643.1749 | 6643.1749 | 6643.1749 | 6643.1749 | 6643.1749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16045 | CORAL SPRINGS | 20323 | Private | 2033 | 5 | Swales | 66.6667 | 28074.3804 | 0.2 | 0.3 | 43796.0334 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5208.2583 | 5208.2583 | 5208.2583 | 5208.2583 | 5208.2583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16046 | CORAL SPRINGS | 20323 | Private | 2033 | 5 | Swales | 66.6667 | 22080.6311 | 0.2 | 0.3 | 34445.7846 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6814.4842 | 6814.4842 | 6814.4842 | 6814.4842 | 6814.4842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16047 | CORAL SPRINGS | 20323 | Public | 2033 | 5 | Swales | 66.6667 | 0.63707 | 0.2 | 0.3 | 0.99382 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5271.383 | 5271.383 | 5271.383 | 5271.383 | 5271.383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16048 | CORAL SPRINGS | 20323 | Public | 2033 | 5 | Swales | 66.6667 | 1241.251 | 0.2 | 0.3 | 1936.3516 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1683.0058 | 1683.0058 | 1683.0058 | 1683.0058 | 1683.0058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16049 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 3085.7709 | 0.2 | 0.3 | 4813.8027 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3267.7623 | 3267.7623 | 3267.7623 | 3267.7623 | 3267.7623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16050 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 17489.415 | 0.2 | 0.3 | 27283.4874 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7203.6666 | 7203.6666 | 7203.6666 | 7203.6666 | 7203.6666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16051 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 16688.1457 | 0.2 | 0.3 | 26033.5073 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1133 | 5203.1133 | 5203.1133 | 5203.1133 | 5203.1133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16052 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 6246.8697 | 0.2 | 0.3 | 9745.1167 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16053 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 7705.0143 | 0.2 | 0.3 | 12019.8223 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1675 | 5203.1675 | 5203.1675 | 5203.1675 | 5203.1675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16054 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 33384.9449 | 0.2 | 0.3 | 52080.5141 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9425.6469 | 9425.6469 | 9425.6469 | 9425.6469 | 9425.6469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16055 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 32603.0705 | 0.2 | 0.3 | 50860.79 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5365.2177 | 5365.2177 | 5365.2177 | 5365.2177 | 5365.2177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16056 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 28584.4989 | 0.2 | 0.3 | 44591.8183 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8439.3962 | 8439.3962 | 8439.3962 | 8439.3962 | 8439.3962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16057 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3739.5577 | 3739.5577 | 3739.5577 | 3739.5577 | 3739.5577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16058 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 16664.3375 | 0.2 | 0.3 | 25996.3664 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9766.5916 | 9766.5916 | 9766.5916 | 9766.5916 | 9766.5916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16059 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9605.6735 | 9605.6735 | 9605.6735 | 9605.6735 | 9605.6735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16060 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 25893.0637 | 0.2 | 0.3 | 40393.1794 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5021 | 5200.5021 | 5200.5021 | 5200.5021 | 5200.5021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16061 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 20769.9157 | 0.2 | 0.3 | 32401.0684 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6619.2027 | 6619.2027 | 6619.2027 | 6619.2027 | 6619.2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16062 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 27580.7943 | 0.2 | 0.3 | 43026.0391 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8336.5961 | 8336.5961 | 8336.5961 | 8336.5961 | 8336.5961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16063 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 6007.0566 | 0.2 | 0.3 | 9371.0083 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7007.6456 | 7007.6456 | 7007.6456 | 7007.6456 | 7007.6456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16064 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 20431.3495 | 0.2 | 0.3 | 31872.9052 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.5358 | 5204.5358 | 5204.5358 | 5204.5358 | 5204.5358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16065 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 27292.2487 | 0.2 | 0.3 | 42575.908 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8727.4351 | 8727.4351 | 8727.4351 | 8727.4351 | 8727.4351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16066 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 6739.6386 | 0.2 | 0.3 | 10513.8362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5220.6584 | 5220.6584 | 5220.6584 | 5220.6584 | 5220.6584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16067 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 19210.7118 | 0.2 | 0.3 | 29968.7104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 5201.6852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16068 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 8095.2189 | 0.2 | 0.3 | 12628.5414 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9016 | 5201.9016 | 5201.9016 | 5201.9016 | 5201.9016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16069 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 6854.6477 | 0.2 | 0.3 | 10693.2504 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7997.2805 | 7997.2805 | 7997.2805 | 7997.2805 | 7997.2805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16070 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 13288.4902 | 0.2 | 0.3 | 20730.0447 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5429 | 5200.5429 | 5200.5429 | 5200.5429 | 5200.5429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16071 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 19080.5351 | 0.2 | 0.3 | 29765.6347 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.5913 | 5201.5913 | 5201.5913 | 5201.5913 | 5201.5913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16072 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 21069.0857 | 0.2 | 0.3 | 32867.7736 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.6449 | 5201.6449 | 5201.6449 | 5201.6449 | 5201.6449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16073 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.9655 | 5204.9655 | 5204.9655 | 5204.9655 | 5204.9655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16074 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 21043.8399 | 0.2 | 0.3 | 32828.3903 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 5204.6708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16075 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 26160.2811 | 0.2 | 0.3 | 40810.0386 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3542.5733 | 3542.5733 | 3542.5733 | 3542.5733 | 3542.5733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16076 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 21532.9742 | 0.2 | 0.3 | 33591.4398 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8578 | 5201.8578 | 5201.8578 | 5201.8578 | 5201.8578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16077 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 26543.5983 | 0.2 | 0.3 | 41408.0134 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 5202.0264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16078 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 9867.7604 | 0.2 | 0.3 | 15393.7062 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16079 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16795.1078 | 0.2 | 0.3 | 26200.3682 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5413 | 5202.5413 | 5202.5413 | 5202.5413 | 5202.5413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16080 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 864.7332 | 0.2 | 0.3 | 1348.9838 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4017 | 5202.4017 | 5202.4017 | 5202.4017 | 5202.4017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16081 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16661.077 | 0.2 | 0.3 | 25991.2801 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5476.2976 | 5476.2976 | 5476.2976 | 5476.2976 | 5476.2976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16082 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16670.9744 | 0.2 | 0.3 | 26006.7201 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7774.7052 | 7774.7052 | 7774.7052 | 7774.7052 | 7774.7052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16083 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16668.7872 | 0.2 | 0.3 | 26003.308 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5335.8675 | 5335.8675 | 5335.8675 | 5335.8675 | 5335.8675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16084 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9946 | 5201.9946 | 5201.9946 | 5201.9946 | 5201.9946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16085 | CORAL SPRINGS | 20323 | Private | 2036 | 5 | Swales | 66.6667 | 33424.4036 | 0.2 | 0.3 | 52142.0696 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8142.9691 | 8142.9691 | 8142.9691 | 8142.9691 | 8142.9691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16086 | CORAL SPRINGS | 20323 | Private | 2033 | 5 | Swales | 66.6667 | 16241.8609 | 0.2 | 0.3 | 25337.303 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5247.508 | 5247.508 | 5247.508 | 5247.508 | 5247.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16087 | CORAL SPRINGS | 20323 | Private | 2033 | 5 | Swales | 66.6667 | 21931.9643 | 0.2 | 0.3 | 34213.8643 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8532.4294 | 8532.4294 | 8532.4294 | 8532.4294 | 8532.4294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16088 | CORAL SPRINGS | 20323 | Private | 2033 | 5 | Swales | 66.6667 | 17721.8869 | 0.2 | 0.3 | 27646.1435 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7216.9734 | 7216.9734 | 7216.9734 | 7216.9734 | 7216.9734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16089 | CORAL SPRINGS | 20323 | Private | 2033 | 5 | Swales | 66.6667 | 36243.6925 | 0.2 | 0.3 | 56540.1604 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5756 | 5202.5756 | 5202.5756 | 5202.5756 | 5202.5756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16090 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 29184.1543 | 0.2 | 0.3 | 45527.2808 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 5202.6235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16091 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 15843.7355 | 0.2 | 0.3 | 24716.2273 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 5202.7088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16092 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 1231.7572 | 0.2 | 0.3 | 1921.5412 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5275.8963 | 5275.8963 | 5275.8963 | 5275.8963 | 5275.8963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16093 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 17101.2243 | 0.2 | 0.3 | 26677.91 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8175.4228 | 8175.4228 | 8175.4228 | 8175.4228 | 8175.4228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16094 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 16879.7494 | 0.2 | 0.3 | 26332.4091 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5321.3921 | 5321.3921 | 5321.3921 | 5321.3921 | 5321.3921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16095 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 2524.2671 | 0.2 | 0.3 | 3937.8566 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8307.8705 | 8307.8705 | 8307.8705 | 8307.8705 | 8307.8705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16096 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 14374.6642 | 0.2 | 0.3 | 22424.4762 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1992.2716 | 1992.2716 | 1992.2716 | 1992.2716 | 1992.2716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16097 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 33383.1062 | 0.2 | 0.3 | 52077.6457 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.7755 | 5201.7755 | 5201.7755 | 5201.7755 | 5201.7755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16098 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 11718.5667 | 0.2 | 0.3 | 18280.9641 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 5201.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16099 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 39642.6172 | 0.2 | 0.3 | 61842.4828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6076.9702 | 6076.9702 | 6076.9702 | 6076.9702 | 6076.9702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16100 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 30283.3153 | 0.2 | 0.3 | 47241.9719 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16101 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 16666.8734 | 0.2 | 0.3 | 26000.3225 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16102 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 31008.2652 | 0.2 | 0.3 | 48372.8937 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 5203.1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16103 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 16667.6936 | 0.2 | 0.3 | 26001.602 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3105 | 5203.3105 | 5203.3105 | 5203.3105 | 5203.3105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16104 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 26718.2554 | 0.2 | 0.3 | 41680.4784 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7760.5607 | 7760.5607 | 7760.5607 | 7760.5607 | 7760.5607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16105 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 2513.5576 | 0.2 | 0.3 | 3921.1499 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5631.2766 | 5631.2766 | 5631.2766 | 5631.2766 | 5631.2766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16106 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 447.6705 | 0.2 | 0.3 | 698.3659 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.1259 | 5202.1259 | 5202.1259 | 5202.1259 | 5202.1259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16107 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 30620.6941 | 0.2 | 0.3 | 47768.2827 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 5202.197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16108 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 34643.9875 | 0.2 | 0.3 | 54044.6206 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4911 | 5202.4911 | 5202.4911 | 5202.4911 | 5202.4911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16109 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 19643.2915 | 0.2 | 0.3 | 30643.5348 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16110 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 29405.8115 | 0.2 | 0.3 | 45873.0659 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16111 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 444.0357 | 0.2 | 0.3 | 692.6957 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4074 | 5202.4074 | 5202.4074 | 5202.4074 | 5202.4074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16112 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 2701.0274 | 0.2 | 0.3 | 4213.6027 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5740.89 | 5740.89 | 5740.89 | 5740.89 | 5740.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16113 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 8559.6853 | 0.2 | 0.3 | 13353.1091 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8938.8305 | 8938.8305 | 8938.8305 | 8938.8305 | 8938.8305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16114 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 16747.0057 | 0.2 | 0.3 | 26125.3288 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3885.076 | 3885.076 | 3885.076 | 3885.076 | 3885.076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16115 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 16813.2138 | 0.2 | 0.3 | 26228.6135 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.304 | 5203.304 | 5203.304 | 5203.304 | 5203.304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16116 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 7191.2465 | 0.2 | 0.3 | 11218.3446 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16117 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16669.0362 | 0.2 | 0.3 | 26003.6965 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16118 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16669.5283 | 0.2 | 0.3 | 26004.4642 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6626.2069 | 6626.2069 | 6626.2069 | 6626.2069 | 6626.2069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16119 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 9523.0673 | 0.2 | 0.3 | 14855.9849 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7950.9837 | 7950.9837 | 7950.9837 | 7950.9837 | 7950.9837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16120 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 21091.304 | 0.2 | 0.3 | 32902.4342 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8388.9963 | 8388.9963 | 8388.9963 | 8388.9963 | 8388.9963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16121 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 3284.4455 | 0.2 | 0.3 | 5123.7349 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1852.5479 | 1852.5479 | 1852.5479 | 1852.5479 | 1852.5479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16122 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 21385.0469 | 0.2 | 0.3 | 33360.6731 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7862.9735 | 7862.9735 | 7862.9735 | 7862.9735 | 7862.9735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16123 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16670.9744 | 0.2 | 0.3 | 26006.7201 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5192.8183 | 5192.8183 | 5192.8183 | 5192.8183 | 5192.8183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16124 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16669.0606 | 0.2 | 0.3 | 26003.7345 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6309.9596 | 6309.9596 | 6309.9596 | 6309.9596 | 6309.9596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16125 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.274 | 5203.274 | 5203.274 | 5203.274 | 5203.274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16126 | CORAL SPRINGS | 20323 | Private | 2036 | 5 | Swales | 66.6667 | 33337.4494 | 0.2 | 0.3 | 52006.4211 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16127 | CORAL SPRINGS | 20323 | Private | 2033 | 5 | Swales | 66.6667 | 15654.9505 | 0.2 | 0.3 | 24421.7228 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16128 | CORAL SPRINGS | 20324 | Private | 2033 | 5 | Swales | 66.6667 | 33141.4005 | 0.2 | 0.3 | 51700.5847 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6318.5203 | 6318.5203 | 6318.5203 | 6318.5203 | 6318.5203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16129 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 19536.4649 | 0.2 | 0.3 | 30476.8852 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4084.834 | 4084.834 | 4084.834 | 4084.834 | 4084.834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16130 | CORAL SPRINGS | 20324 | Private | 2033 | 5 | Swales | 66.6667 | 7507.4195 | 0.2 | 0.3 | 11711.5745 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5637.7227 | 5637.7227 | 5637.7227 | 5637.7227 | 5637.7227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16131 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 2862.5635 | 0.2 | 0.3 | 4465.5991 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4588.1741 | 4588.1741 | 4588.1741 | 4588.1741 | 4588.1741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16132 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 20140.3614 | 0.2 | 0.3 | 31418.9638 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.0842 | 5205.0842 | 5205.0842 | 5205.0842 | 5205.0842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16133 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 22330.8666 | 0.2 | 0.3 | 34836.1519 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.3753 | 5205.3753 | 5205.3753 | 5205.3753 | 5205.3753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16134 | CORAL SPRINGS | 20324 | Private | 2036 | 5 | Swales | 66.6667 | 13345.2745 | 0.2 | 0.3 | 20818.6282 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7747.4467 | 7747.4467 | 7747.4467 | 7747.4467 | 7747.4467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16135 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 29360.3921 | 0.2 | 0.3 | 45802.2116 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7078.7565 | 7078.7565 | 7078.7565 | 7078.7565 | 7078.7565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16136 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 17220.2818 | 0.2 | 0.3 | 26863.6396 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9788.4848 | 9788.4848 | 9788.4848 | 9788.4848 | 9788.4848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16137 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 16.9707 | 0.2 | 0.3 | 26.4743 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9800.5025 | 9800.5025 | 9800.5025 | 9800.5025 | 9800.5025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16138 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 40611.6897 | 0.2 | 0.3 | 63354.2359 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5230.1896 | 5230.1896 | 5230.1896 | 5230.1896 | 5230.1896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16139 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 8662.8173 | 0.2 | 0.3 | 13513.995 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5212.9136 | 5212.9136 | 5212.9136 | 5212.9136 | 5212.9136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16140 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 22838.6898 | 0.2 | 0.3 | 35628.3561 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3736.9307 | 3736.9307 | 3736.9307 | 3736.9307 | 3736.9307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16141 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 25442.6971 | 0.2 | 0.3 | 39690.6074 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2374.5955 | 2374.5955 | 2374.5955 | 2374.5955 | 2374.5955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16142 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 30486.0443 | 0.2 | 0.3 | 47558.2292 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6067.6462 | 6067.6462 | 6067.6462 | 6067.6462 | 6067.6462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16143 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 10343.3549 | 0.2 | 0.3 | 16135.6337 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9541 | 5201.9541 | 5201.9541 | 5201.9541 | 5201.9541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16144 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 16647.442 | 0.2 | 0.3 | 25970.0095 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3137.191 | 3137.191 | 3137.191 | 3137.191 | 3137.191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16145 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 17340.9089 | 0.2 | 0.3 | 27051.8179 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.1861 | 5204.1861 | 5204.1861 | 5204.1861 | 5204.1861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16146 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 5401.1189 | 0.2 | 0.3 | 8425.7455 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5275.7017 | 5275.7017 | 5275.7017 | 5275.7017 | 5275.7017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16147 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 15260.9991 | 0.2 | 0.3 | 23807.1586 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.9278 | 5200.9278 | 5200.9278 | 5200.9278 | 5200.9278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16148 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 30886.9275 | 0.2 | 0.3 | 48183.607 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6836.8575 | 6836.8575 | 6836.8575 | 6836.8575 | 6836.8575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16149 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6661 | 5202.6661 | 5202.6661 | 5202.6661 | 5202.6661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16150 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 28343.6741 | 0.2 | 0.3 | 44216.1315 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4978 | 5202.4978 | 5202.4978 | 5202.4978 | 5202.4978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16151 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 16667.4202 | 0.2 | 0.3 | 26001.1755 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6210.5484 | 6210.5484 | 6210.5484 | 6210.5484 | 6210.5484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16152 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 27070.1361 | 0.2 | 0.3 | 42229.4124 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6926.4283 | 6926.4283 | 6926.4283 | 6926.4283 | 6926.4283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16153 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 1328.8491 | 0.2 | 0.3 | 2073.0046 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1168.7421 | 1168.7421 | 1168.7421 | 1168.7421 | 1168.7421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16154 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 42237.4844 | 0.2 | 0.3 | 65890.4757 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6716.2891 | 6716.2891 | 6716.2891 | 6716.2891 | 6716.2891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16155 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 18990.7993 | 0.2 | 0.3 | 29625.647 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2018.881 | 2018.881 | 2018.881 | 2018.881 | 2018.881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16156 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 22851.7559 | 0.2 | 0.3 | 35648.7393 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8937.6875 | 8937.6875 | 8937.6875 | 8937.6875 | 8937.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16157 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 32178.1639 | 0.2 | 0.3 | 50197.9357 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3363.8992 | 3363.8992 | 3363.8992 | 3363.8992 | 3363.8992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16158 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 30283.2469 | 0.2 | 0.3 | 47241.8651 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5949.9651 | 5949.9651 | 5949.9651 | 5949.9651 | 5949.9651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16159 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 38522.8571 | 0.2 | 0.3 | 60095.6571 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1965.1269 | 1965.1269 | 1965.1269 | 1965.1269 | 1965.1269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16160 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 29751.0052 | 0.2 | 0.3 | 46411.5681 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6041.7622 | 6041.7622 | 6041.7622 | 6041.7622 | 6041.7622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16161 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 23285.5069 | 0.2 | 0.3 | 36325.3908 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2005.7709 | 2005.7709 | 2005.7709 | 2005.7709 | 2005.7709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16162 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 8152.8319 | 0.2 | 0.3 | 12718.4177 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3211.2254 | 3211.2254 | 3211.2254 | 3211.2254 | 3211.2254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16163 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 11579.6812 | 0.2 | 0.3 | 18064.3027 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16164 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 23086.7511 | 0.2 | 0.3 | 36015.3317 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.0155 | 5203.0155 | 5203.0155 | 5203.0155 | 5203.0155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16165 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 16894.8844 | 0.2 | 0.3 | 26356.0197 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5842 | 5203.5842 | 5203.5842 | 5203.5842 | 5203.5842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16166 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 6602.474 | 0.2 | 0.3 | 10299.8594 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5959.449 | 5959.449 | 5959.449 | 5959.449 | 5959.449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16167 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16667.5293 | 0.2 | 0.3 | 26001.3458 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2044.316 | 2044.316 | 2044.316 | 2044.316 | 2044.316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16168 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9528.6237 | 9528.6237 | 9528.6237 | 9528.6237 | 9528.6237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16169 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 7156.0298 | 0.2 | 0.3 | 11163.4065 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.5533 | 5200.5533 | 5200.5533 | 5200.5533 | 5200.5533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16170 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 13988.5357 | 0.2 | 0.3 | 21822.1157 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6166.1193 | 6166.1193 | 6166.1193 | 6166.1193 | 6166.1193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16171 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 27666.7903 | 0.2 | 0.3 | 43160.1929 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 410.7639 | 410.7639 | 410.7639 | 410.7639 | 410.7639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16172 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 21134.4273 | 0.2 | 0.3 | 32969.7066 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2333.1579 | 2333.1579 | 2333.1579 | 2333.1579 | 2333.1579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16173 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 18780.7559 | 0.2 | 0.3 | 29297.9793 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 3400.3564 | 3400.3564 | 3400.3564 | 3400.3564 | 3400.3564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16174 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16668.5952 | 0.2 | 0.3 | 26003.0085 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16175 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 13184.2574 | 0.2 | 0.3 | 20567.4415 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2916 | 5203.2916 | 5203.2916 | 5203.2916 | 5203.2916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16176 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16787.8361 | 0.2 | 0.3 | 26189.0244 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10921.4408 | 10921.4408 | 10921.4408 | 10921.4408 | 10921.4408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16177 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16666.0532 | 0.2 | 0.3 | 25999.043 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5257.5579 | 5257.5579 | 5257.5579 | 5257.5579 | 5257.5579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16178 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16670.9745 | 0.2 | 0.3 | 26006.7202 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16179 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16669.6074 | 0.2 | 0.3 | 26004.5875 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 5202.8794 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16180 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.6728 | 5202.6728 | 5202.6728 | 5202.6728 | 5202.6728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16181 | CORAL SPRINGS | 20323 | Private | 2036 | 5 | Swales | 66.6667 | 45110.9613 | 0.2 | 0.3 | 70373.0996 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2870.3014 | 2870.3014 | 2870.3014 | 2870.3014 | 2870.3014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16182 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 14044.4945 | 0.2 | 0.3 | 21909.4114 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1803.2124 | 1803.2124 | 1803.2124 | 1803.2124 | 1803.2124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16183 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 23242.5743 | 0.2 | 0.3 | 36258.416 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 544.9109 | 544.9109 | 544.9109 | 544.9109 | 544.9109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16184 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 25009.2766 | 0.2 | 0.3 | 39014.4715 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7157.9107 | 7157.9107 | 7157.9107 | 7157.9107 | 7157.9107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16185 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 3248.4581 | 0.2 | 0.3 | 5067.5946 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 5204.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16186 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 16509.3471 | 0.2 | 0.3 | 25754.5814 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5680.4585 | 5680.4585 | 5680.4585 | 5680.4585 | 5680.4585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16187 | CORAL SPRINGS | 20324 | Private | 2033 | 5 | Swales | 66.6667 | 34847.266 | 0.2 | 0.3 | 54361.735 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7224.2774 | 7224.2774 | 7224.2774 | 7224.2774 | 7224.2774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16188 | CORAL SPRINGS | 20324 | Public | 2036 | 5 | Swales | 66.6667 | 16833.1833 | 0.2 | 0.3 | 26259.7659 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 5200.6616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16189 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 12094.4533 | 0.2 | 0.3 | 18867.3472 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7902.6405 | 7902.6405 | 7902.6405 | 7902.6405 | 7902.6405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16190 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 29687.7803 | 0.2 | 0.3 | 46312.9373 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5247.718 | 5247.718 | 5247.718 | 5247.718 | 5247.718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16191 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 21939.3829 | 0.2 | 0.3 | 34225.4374 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.9922 | 5201.9922 | 5201.9922 | 5201.9922 | 5201.9922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16192 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 23408.5069 | 0.2 | 0.3 | 36517.2707 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 303.8957 | 303.8957 | 303.8957 | 303.8957 | 303.8957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16193 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 40769.6689 | 0.2 | 0.3 | 63600.6834 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5307.1124 | 5307.1124 | 5307.1124 | 5307.1124 | 5307.1124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16194 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 14900.9668 | 0.2 | 0.3 | 23245.5082 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4764.3284 | 4764.3284 | 4764.3284 | 4764.3284 | 4764.3284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16195 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 25001.267 | 0.2 | 0.3 | 39001.9765 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9795.0659 | 9795.0659 | 9795.0659 | 9795.0659 | 9795.0659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16196 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 8350.6157 | 0.2 | 0.3 | 13026.9604 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.4666 | 5204.4666 | 5204.4666 | 5204.4666 | 5204.4666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16197 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 16963.5699 | 0.2 | 0.3 | 26463.1691 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6100.0038 | 6100.0038 | 6100.0038 | 6100.0038 | 6100.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16198 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 19987.7653 | 0.2 | 0.3 | 31180.9139 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8823.6441 | 8823.6441 | 8823.6441 | 8823.6441 | 8823.6441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16199 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 11484.5897 | 0.2 | 0.3 | 17915.96 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 5201.8558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16200 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 26463.5313 | 0.2 | 0.3 | 41283.1088 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8038.1999 | 8038.1999 | 8038.1999 | 8038.1999 | 8038.1999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16201 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 21291.9357 | 0.2 | 0.3 | 33215.4197 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7406 | 5202.7406 | 5202.7406 | 5202.7406 | 5202.7406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16202 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 15773.2502 | 0.2 | 0.3 | 24606.2703 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16203 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 33963.6831 | 0.2 | 0.3 | 52983.3457 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7766 | 5202.7766 | 5202.7766 | 5202.7766 | 5202.7766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16204 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 16666.6 | 0.2 | 0.3 | 25999.896 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5199.9 | 5199.9 | 5199.9 | 5199.9 | 5199.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16205 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 2512.8049 | 0.2 | 0.3 | 3919.9757 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2601.3937 | 2601.3937 | 2601.3937 | 2601.3937 | 2601.3937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16206 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 20127.1017 | 0.2 | 0.3 | 31398.2786 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8982.6522 | 8982.6522 | 8982.6522 | 8982.6522 | 8982.6522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16207 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 30737.3107 | 0.2 | 0.3 | 47950.2047 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 5203.5619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16208 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 24540.1149 | 0.2 | 0.3 | 38282.5792 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6006.1334 | 6006.1334 | 6006.1334 | 6006.1334 | 6006.1334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16209 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 22519.6698 | 0.2 | 0.3 | 35130.6849 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1540.4187 | 1540.4187 | 1540.4187 | 1540.4187 | 1540.4187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16210 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 27035.5523 | 0.2 | 0.3 | 42175.4616 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 12245.3108 | 12245.3108 | 12245.3108 | 12245.3108 | 12245.3108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16211 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 2270.81 | 0.2 | 0.3 | 3542.4636 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7813.6958 | 7813.6958 | 7813.6958 | 7813.6958 | 7813.6958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16212 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 19131.1669 | 0.2 | 0.3 | 29844.6203 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9130.7087 | 9130.7087 | 9130.7087 | 9130.7087 | 9130.7087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16213 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 42434.2284 | 0.2 | 0.3 | 66197.3963 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5194.0934 | 5194.0934 | 5194.0934 | 5194.0934 | 5194.0934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16214 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 19006.6903 | 0.2 | 0.3 | 29650.4369 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5252.8241 | 5252.8241 | 5252.8241 | 5252.8241 | 5252.8241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16215 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 10337.5867 | 0.2 | 0.3 | 16126.6353 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9758.3082 | 9758.3082 | 9758.3082 | 9758.3082 | 9758.3082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16216 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 18093.4899 | 0.2 | 0.3 | 28225.8443 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 5203.9031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16217 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 9376.919 | 0.2 | 0.3 | 14627.9936 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6368.8891 | 6368.8891 | 6368.8891 | 6368.8891 | 6368.8891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16218 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 10490.6253 | 0.2 | 0.3 | 16365.3754 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9289.4735 | 9289.4735 | 9289.4735 | 9289.4735 | 9289.4735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16219 | COCONUT CREEK | 30703 | Private | 2030 | 5 | Swales | 66.6667 | 2611.2889 | 0.2 | 0.3 | 4073.6107 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16220 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 16667.167 | 0.2 | 0.3 | 26000.7805 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.8549 | 5204.8549 | 5204.8549 | 5204.8549 | 5204.8549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16221 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 16667.9707 | 0.2 | 0.3 | 26002.0343 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16222 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 7359.5702 | 0.2 | 0.3 | 11480.9295 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0823 | 5204.0823 | 5204.0823 | 5204.0823 | 5204.0823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16223 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 9380.1419 | 0.2 | 0.3 | 14633.0214 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.5279 | 5204.5279 | 5204.5279 | 5204.5279 | 5204.5279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16224 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 12052.9289 | 0.2 | 0.3 | 18802.5691 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 2752.4642 | 2752.4642 | 2752.4642 | 2752.4642 | 2752.4642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16225 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 15785.2522 | 0.2 | 0.3 | 24624.9934 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1151.2425 | 1151.2425 | 1151.2425 | 1151.2425 | 1151.2425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16226 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 13212.5857 | 0.2 | 0.3 | 20611.6337 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 132.7221 | 132.7221 | 132.7221 | 132.7221 | 132.7221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16227 | CORAL SPRINGS | 20312 | Public | 2036 | 5 | Swales | 66.6667 | 5560.4603 | 0.2 | 0.3 | 8674.318 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.644 | 5203.644 | 5203.644 | 5203.644 | 5203.644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16228 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16669.8883 | 0.2 | 0.3 | 26005.0258 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 5203.7325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16229 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 16669.334 | 0.2 | 0.3 | 26004.161 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5071.0204 | 5071.0204 | 5071.0204 | 5071.0204 | 5071.0204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16230 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 17636.082 | 0.2 | 0.3 | 27512.2879 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 5205.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16231 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 12621.1402 | 0.2 | 0.3 | 19688.9787 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5205.0894 | 5205.0894 | 5205.0894 | 5205.0894 | 5205.0894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16232 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 6681.4527 | 0.2 | 0.3 | 10423.0663 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6920.3074 | 6920.3074 | 6920.3074 | 6920.3074 | 6920.3074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16233 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 13076.2574 | 0.2 | 0.3 | 20398.9615 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 5204.159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16234 | CORAL SPRINGS | 20313 | Public | 2036 | 5 | Swales | 66.6667 | 21052.7559 | 0.2 | 0.3 | 32842.2992 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.0357 | 5204.0357 | 5204.0357 | 5204.0357 | 5204.0357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16235 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16666.8041 | 0.2 | 0.3 | 26000.2143 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.7594 | 5203.7594 | 5203.7594 | 5203.7594 | 5203.7594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16236 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 13722.7465 | 0.2 | 0.3 | 21407.4845 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 5203.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16237 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 17299.989 | 0.2 | 0.3 | 26987.9828 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.9422 | 5203.9422 | 5203.9422 | 5203.9422 | 5203.9422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16238 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16670.1542 | 0.2 | 0.3 | 26005.4406 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8388.2504 | 8388.2504 | 8388.2504 | 8388.2504 | 8388.2504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16239 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16670.7367 | 0.2 | 0.3 | 26006.3492 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.1227 | 5204.1227 | 5204.1227 | 5204.1227 | 5204.1227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16240 | CORAL SPRINGS | 20314 | Public | 2030 | 5 | Swales | 66.6667 | 16652.8073 | 0.2 | 0.3 | 25978.3794 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 5204.8414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16241 | CORAL SPRINGS | 20323 | Public | 2036 | 5 | Swales | 66.6667 | 16669.2264 | 0.2 | 0.3 | 26003.9932 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 5204.9267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16242 | CORAL SPRINGS | 20323 | Private | 2036 | 5 | Swales | 66.6667 | 33678.4523 | 0.2 | 0.3 | 52538.3856 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7943.1313 | 7943.1313 | 7943.1313 | 7943.1313 | 7943.1313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16243 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 17077.3683 | 0.2 | 0.3 | 26640.6945 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6491.4103 | 6491.4103 | 6491.4103 | 6491.4103 | 6491.4103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16244 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 18377.9442 | 0.2 | 0.3 | 28669.593 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.3378 | 5204.3378 | 5204.3378 | 5204.3378 | 5204.3378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16245 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 19746.2467 | 0.2 | 0.3 | 30804.1449 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5481.4051 | 5481.4051 | 5481.4051 | 5481.4051 | 5481.4051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16246 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 10685.7765 | 0.2 | 0.3 | 16669.8114 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9702.9471 | 9702.9471 | 9702.9471 | 9702.9471 | 9702.9471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16247 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 29979.5486 | 0.2 | 0.3 | 46768.0958 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10743.6906 | 10743.6906 | 10743.6906 | 10743.6906 | 10743.6906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16248 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 10041.5811 | 0.2 | 0.3 | 15664.8666 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.9478 | 5204.9478 | 5204.9478 | 5204.9478 | 5204.9478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16249 | CORAL SPRINGS | 20324 | Public | 2033 | 5 | Swales | 66.6667 | 11302.7657 | 0.2 | 0.3 | 17632.3144 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.831 | 5204.831 | 5204.831 | 5204.831 | 5204.831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16250 | CORAL SPRINGS | 20324 | Public | 2036 | 5 | Swales | 66.6667 | 9632.2451 | 0.2 | 0.3 | 15026.3024 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 5203.2207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16251 | MARGATE | 20204 | Private | 2036 | 5 | Swales | 66.6667 | 17088.9505 | 0.2 | 0.3 | 26658.7627 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9904.3966 | 9904.3966 | 9904.3966 | 9904.3966 | 9904.3966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16252 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 11489.7099 | 0.2 | 0.3 | 17923.9474 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9945 | 5202.9945 | 5202.9945 | 5202.9945 | 5202.9945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16253 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 2100.5797 | 0.2 | 0.3 | 3276.9043 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7908.0876 | 7908.0876 | 7908.0876 | 7908.0876 | 7908.0876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16254 | MARGATE | 20205 | Private | 2036 | 5 | Swales | 66.6667 | 35724.3745 | 0.2 | 0.3 | 55730.0243 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9785.0081 | 9785.0081 | 9785.0081 | 9785.0081 | 9785.0081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16255 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 3648.2991 | 0.2 | 0.3 | 5691.3466 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7463.8419 | 7463.8419 | 7463.8419 | 7463.8419 | 7463.8419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16256 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 29062.4899 | 0.2 | 0.3 | 45337.4842 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3361 | 5203.3361 | 5203.3361 | 5203.3361 | 5203.3361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16257 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 7941.9856 | 0.2 | 0.3 | 12389.4975 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8165.9024 | 8165.9024 | 8165.9024 | 8165.9024 | 8165.9024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16258 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 22358.1598 | 0.2 | 0.3 | 34878.7293 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5204.5168 | 5204.5168 | 5204.5168 | 5204.5168 | 5204.5168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16259 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 16650.0555 | 0.2 | 0.3 | 25974.0866 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6155.4317 | 6155.4317 | 6155.4317 | 6155.4317 | 6155.4317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16260 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 16699.505 | 0.2 | 0.3 | 26051.2278 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8039.3817 | 8039.3817 | 8039.3817 | 8039.3817 | 8039.3817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16261 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 16693.2645 | 0.2 | 0.3 | 26041.4926 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6686.9532 | 6686.9532 | 6686.9532 | 6686.9532 | 6686.9532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16262 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 22782.6301 | 0.2 | 0.3 | 35540.903 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 8490.3611 | 8490.3611 | 8490.3611 | 8490.3611 | 8490.3611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16263 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 27105.2391 | 0.2 | 0.3 | 42284.1729 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 7201.9239 | 7201.9239 | 7201.9239 | 7201.9239 | 7201.9239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16264 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 37814.9522 | 0.2 | 0.3 | 58991.3254 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5206.3537 | 5206.3537 | 5206.3537 | 5206.3537 | 5206.3537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16265 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 40179.8237 | 0.2 | 0.3 | 62680.5249 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6705.067 | 6705.067 | 6705.067 | 6705.067 | 6705.067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16266 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 26248.2884 | 0.2 | 0.3 | 40947.3299 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 5202.9647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16267 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 31322.5555 | 0.2 | 0.3 | 48863.1865 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.964 | 5202.964 | 5202.964 | 5202.964 | 5202.964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16268 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 28837.3762 | 0.2 | 0.3 | 44986.3069 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5426.148 | 5426.148 | 5426.148 | 5426.148 | 5426.148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16269 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 36394.328 | 0.2 | 0.3 | 56775.1517 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 254.4156 | 254.4156 | 254.4156 | 254.4156 | 254.4156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16270 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 23571.8948 | 0.2 | 0.3 | 36772.1559 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 6460.8801 | 6460.8801 | 6460.8801 | 6460.8801 | 6460.8801 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16271 | MARGATE | 20205 | Public | 2036 | 5 | Swales | 66.6667 | 20897.6797 | 0.2 | 0.3 | 32600.3803 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.4283 | 5203.4283 | 5203.4283 | 5203.4283 | 5203.4283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16272 | MARGATE | 20101 | Private | 2033 | 5 | Swales | 66.6667 | 26611.1265 | 0.2 | 0.3 | 41513.3574 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 5203.3913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16273 | MARGATE | 20101 | Private | 2033 | 5 | Swales | 66.6667 | 53847.9145 | 0.2 | 0.3 | 84002.7467 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5203.4174 | 5203.4174 | 5203.4174 | 5203.4174 | 5203.4174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16274 | MARGATE | 20101 | Private | 2033 | 5 | Swales | 66.6667 | 50002.4151 | 0.2 | 0.3 | 78003.7675 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10349.1787 | 10349.1787 | 10349.1787 | 10349.1787 | 10349.1787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16275 | MARGATE | 20101 | Private | 2033 | 5 | Swales | 66.6667 | 42895.0115 | 0.2 | 0.3 | 66916.2179 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 1102.7333 | 1102.7333 | 1102.7333 | 1102.7333 | 1102.7333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16276 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 29810.8661 | 0.2 | 0.3 | 46504.9512 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 4100.0147 | 4100.0147 | 4100.0147 | 4100.0147 | 4100.0147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16277 | MARGATE | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 10333.2534 | 0.2 | 0.3 | 16119.8753 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.8323 | 5202.8323 | 5202.8323 | 5202.8323 | 5202.8323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16278 | MARGATE | 20101 | Public | 2036 | 5 | Swales | 66.6667 | 16661.9193 | 0.2 | 0.3 | 25992.5941 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 5202.7941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16279 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 16329.9095 | 0.2 | 0.3 | 25474.6588 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 11172.9238 | 11172.9238 | 11172.9238 | 11172.9238 | 11172.9238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16280 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 16868.8152 | 0.2 | 0.3 | 26315.3517 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 5202.5382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16281 | COCONUT CREEK | 20101 | Private | 2036 | 5 | Swales | 66.6667 | 17723.6181 | 0.2 | 0.3 | 27648.8442 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 5202.4529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0